## ClimAA rev logframe May 2014
PROJECT NAME: Africa-Brazil partnership on climate-smart agriculture and food security (CLIMAA). Revised logframe May 2014
IMPACT | Impact Indicator 1 |  | Baseline - Sept 2013 | Milestone 1 - Sept 2014 | Milestone 2 - Sept 2015 | Milestone 3 - Sept 2016 | Target - March 2017
Emerging Powers contribute to MDG 8 on Global Partnership through MDG 1 on Food Security in line with HMG strategy on emerging powers | Progress made against MDG 1 and MDG 8 | Planned
Achieved
Source
|  |  | Baseline - Sept 2013 | Milestone 1 - Sept 2014 | Milestone 2 - Sept 2015 | Milestone 3 - Sept 2016 | Target - March 2017
Planned
Achieved
Source
OUTCOME | Outcome Indicator 1 |  | Baseline - Sept 2013 | Milestone 1 - Sept 2014 | Milestone 2 - Sept 2015 | Milestone 3 - Sept 2016 | Target - March 2017 | Assumptions
Brazil's international reputation in sustainable agricultural development and food security strengthened through south-south partnerships. | Nr of requests for agriculture and food security support received by Brazilian Cooperation Agency (ABC) | Planned | [5 empty] | No major political instablity in Brazil after elections No major political instability in LIC countries engaged in CLIMAA Proof of concepts and best practices exist that meet the needs of selected LICs and can be adapted according to the specific country context.
Achieved
Source
| Outcome Indicator 2 |  | Baseline - Sept 2013 | Milestone 1 - Sept 2014 | Milestone 2 - Sept 2015 | Milestone 3 - Sept 2016 | Target - March 2017
| Nr of ClimAA proof of concepts being adapted and taken up in LICs through new programmes and pilots. New countries and proof of concepts. | Planned |  |  | 2 | 5 | 14
|  | Achieved |  |  | 5
Source
| Outcome Indicator 3 |  | Baseline - Sept 2013 | Milestone 1 - Sept 2014 | Milestone 2 - Sept 2015 | Milestone 3 - Sept 2016 | Target - March 2017
| Nr of policies and national implementation strategies revised based on CLIMAA related lessons learnt and evidence. Countries and policies. | Planned |  |  | 2 | 2 | 10
|  | Achieved |  |  | 2
Source
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline - Sept 2013 | Milestone 1 - Sept 2014 | Milestone 2 - Sept 2015 | Milestone 3 - Sept 2016 | Target - March 2017 | Assumption
Increased capacity of LIC researchers, government institutions and extension staff through participation in LIC-Brazilian pilots, training and policy dialogue | Nr of LIC researchers participating in joint research/pilots programmes and exchange visits disaggregated by gender, institutional affiliation and seniority | Planned | 131(12) | 93(31) | 50(20) | 61(28) | 254(117) | Participants have institutional support to engage in CLIMAA programme activities and training events. There are sufficient women with relevant background and expertise and institutional support to engage in CLIMAA programme and training activities.
|  | Achieved |  | 156 (61) | 147 (30)
Source
CLIMAA project progress reports and visit reports
| Output Indicator 1.2 |  | Baseline - Sept 2013 | Milestone 1 - Sept 2014 | Milestone 2 - Sept 2015 | Milestone 3 - Sept 2016 | Target - March 2017
| Nr of people trained in adaptive research, climate smart technologies, local food purchase systems and extension approaches disaggregated by gender | Planned | 0 | 110(25) | 115 (40) | 25 | 250(76)
|  | Achieved |  | 126 (28) | 180 (97)
Source
CLIMAA project progress reports and training reports
IMPACT WEIGHTING (%) | Output Indicator 1.3 |  | Baseline - Sept 2013 | Milestone 1 - Sept 2014 | Milestone 2 - Sept 2015 | Milestone 3 - Sept 2016 | Target - March 2017
25 | Nr of training materials and capacity building events addressing gender issues | Planned | 2 | 1 | 5 | 4 | 13
|  | Achieved |  | 1 | 11
|  | Source | [5 empty] | RISK RATING
ClimAA project training materials and workshop reports
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline - Sept 2013 | Milestone 1 - Sept 2014 | Milestone 2 - Sept 2015 | Milestone 3 - Sept 2016 | Target - March 2017 | Assumptions
Proof of concepts tested and validated for LIC- specific context for potential outscaling | Nr of proof of concepts/pilots initiated | Planned | 47 | 1 | 17 | 11 | 71 | Proof of concepts and best practices exist that meet the needs of selected LICs with potential for adaptation according to the specific country context. Local conditions in pilot countries allow effective implementation of testing and validation of proof of concepts and pilots. LIC host institutions are able and committed to take successful proof of concepts further beyond testing and validation.
|  | Achieved |  | 2 | 18
Source
ClimAA project progress reports
| Output Indicator 2.2 |  | Baseline - Sept 2013 | Milestone 1 - Sept 2014 | Milestone 2 - Sept 2015 | Milestone 3 - Sept 2016 | Target - March 2017
| Nr of proof of concepts/pilot tested and validated, with at least 40% showing potential positive impact on women and girls | Planned | 15 | 0 | 25 | 9 | 71
|  | Achieved |  | 0 | 25
Source
ClimAA project evaluation reports
IMPACT WEIGHTING (%) | Output Indicator 2.3 |  | Baseline - Sept 2013 | Milestone 1 - Sept 2014 | Milestone 2 - Sept 2015 | Milestone 3 - Sept 2016 | Target - March 2017
25 | Nr of proof of concepts identified with potential for upscaling (and number of projects with upscaling initiated and completed) | Planned | 2 | 5 | 10 | 2 | 11
|  | Achieved |  | 5 | 10
|  | Source | [5 empty] | RISK RATING
ClimAA project evaluation reports and project steering committee minutes
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline - Sept 2013 | Milestone 1 - Sept 2014 | Milestone 2 - Sept 2015 | Milestone 3 - Sept 2016 | Target - March 2017 | Assumptions
Lessons learnt and robust evidence generated on adoption of Brazilian technologies and interventions relevant for policy and programme development in LIC | Nr of best practices, lessons learnt documents, internet discuss and policy briefs widely disseminated with at least 30% of papers/briefs addressing gender dimensions | Planned | 3 | 2 | 6 | 8 | 20 | Stakeholders in LIC and Brazil recognise the relevance of international collaboration and exchange of experiences and technologies. Stakeholders in LIC and Brazil recognise the importance of adopting lessons learnt and 'proof of concepts' to specific contexts building on evidence from evaluation studies and case studies.
|  | Achieved |  | 1 | 14
Source
ClimAA project progress reports and evaluation reports
| Output Indicator 3.2 |  | Baseline - Sept 2013 | Milestone 1 - Sept 2014 | Milestone 2 - Sept 2015 | Milestone 3 - Sept 2016 | Target - March 2017
| Nr of evalulation studies/action plans initiated and completed | Planned | 5(5) | 3(0) | 11 (0) | 10 | 22
|  | Achieved |  | 4 | 8
Source
ClimAA project progress reports
IMPACT WEIGHTING (%) | Output Indicator 3.3 |  | Baseline - Sept 2013 | Milestone 1 - Sept 2014 | Milestone 2 - Sept 2015 | Milestone 3 - Sept 2016 | Target - March 2017
25 | Nr of learning and policy events organised by ClimAA partners | Planned | 4 | 3 | 7 | 6 | 23
|  | Achieved |  |  | 8
Source
ClimAA project progress reports
| Output Indicator 3.4 |  | Baseline - Sept 2013 | Milestone 1 - Sept 2014 | Milestone 2 - Sept 2015 | Milestone 3 - Sept 2016 | Target - March 2017
| Nr of presentations of lessons learnt from ClimAA at international and national events | Planned | 8 | 4 | 11 | 15 | 39
|  | Achieved |  |  | 8
|  | Source | [5 empty] | RISK RATING
ClimAA project progress reports
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 4 | Output Indicator 4.1 |  | Baseline - Sept 2013 | Milestone 1 - Sept 2014 | Milestone 2 - Sept 2015 | Milestone 3 - Sept 2016 | Target - March 2017 | Assumptions
South-South collaboration strengthened between Brazil and LIC government, research and development institutions working on agriculture and food security | Nr of Brazilian and LIC institutions collaborating as part of CLIMAA | Planned | 17 | 2 | 24 | 0 | 47 | LIC and Brazilian institutions see the mutual benefits of strong south-south collaboration. No major changes in political context that may affect international collaboration on agriculture and food security
|  | Achieved |  | 2 | 26
Source
ClimAA project progress reports
| Output Indicator 4.2 |  | Baseline - Sept 2013 | Milestone 1 - Sept 2014 | Milestone 2 - Sept 2015 | Milestone 3 - Sept 2016 | Target - March 2017
| Nr of joint partnerships with signed MoU between LIC and Brazilian institutions working under CLIMAA programme | Planned | 9 | 0 | 19 | 0 | 33
|  | Achieved |  | 0 | 15
Source
ClimAA project progress reports
IMPACT WEIGHTING (%) | Output Indicator 4.3 |  | Baseline - Sept 2013 | Milestone 1 - Sept 2014 | Milestone 2 - Sept 2015 | Milestone 3 - Sept 2016 | Target - March 2017
25 | Nr of Presentations to Brazilian Institutes to demonstarte relevance of Brazilian Expertise to South-South cooperation and technology transfer | Planned | 0 | 0 | 4 | 2 | 6
|  | Achieved |  | 0 | 4
|  | Source | [5 empty] | RISK RATING
ClimAA project progress reports
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)