## Sheet1
Logical Framework: Increasing Access to Reproductive Health Commodities in Ethiopia
Organization:- DKT Ethiopia
Project Title : Increasing Access to Reproductive Health Commodities in Ethiopia
Project Period: July 2012-March 2015
IMPACT | Impact Indicator 1 |  | Baseline (2011) | Milestone 1(2012/13) | Milestone 2 (2013/14) | Target (2014/15) | Assumptions
Improved Reproductive and Sexual Health in Ethiopia | Decreased Prevalence of HIV/AIDS | Planned |  |  |  | 1.4%
|  | Achieved | 1.5%
|  | Source: | Ethiopian Demographic Health Survey (DHS) 2011. Endline - EDHS 2015
| Impact Indicator 2 |  | Baseline (2011) | Milestone 1(2012/13) | Milestone 2 (2013/14) | Target (2014/15) | Assumptions
| Total Fertility Rate Reduced | Planned |  | 4.5 | 4.3 | 4
|  | Achieved | 4.8
|  | Source: | Ethiopian Demographic Health Survey (DHS) 2011. Endline -EDHS 2015
| Impact Indicator 3 |  | Baseline (2011) | Milestone 1(2012/13) | Milestone 2 (2013/14) | Target (2014/15) | Assumptions
| Maternal Mortality Ratio Reduced | Planned |  | 520 | 380 | 267
|  | Achieved | 676
|  | Source: | Ethiopian Demographic Health Survey (EDHS) 2011/2015, FMOH HSDP IV Document
| Impact Indicator 4 |  | Baseline (2011) | Milestone 1(2012/13) | Milestone 2 (2013/14) | Target (2014/15) | Assumptions
| Percentage of Currently Married Women aged 15-49 who use a modern family planning method increases | Planned |  |  |  | 48%
|  | Achieved | 27%
|  | Source: | Ethiopian Demographic Health Survey (EDHS) 2011/2015, FMOH HSDP IV Document
OUTCOME | Outcome Indicator 1 |  | Baseline (2012) | Milestone 1(2012/13) | Milestone 2 (2013/14) | Target (2014/15) | Assumptions
Increase in consistent condom use by sex workers, their clients and regular partners in Wise-up program intervention towns | Percentage of female sex workers in DKT Wise Up towns reporting consistent condom use in the last 7 days with paying partners increases from 86% to 90% | Planned |  |  |  | 90% | Sex work remains Primary driver of HIV epidemic
|  | Achieved | 86% |  |  | 94%
|  | Source: | FSWs BCIS (Behavior Change Impact Survey) No annual measurement of milestones
| Outcome Indicator 2 |  | Baseline (2012) | Milestone 1(2012/13) | Milestone 2 (2013/14) | Target (2014/15)
| Percentage of female sex workers in DKT Wise Up towns reporting consistent condom use in the last 30 days with non- paying partners increases from 43% to 60% | Planned |  |  |  | 60%
|  | Achieved | 43% |  |  | 36%
|  | Source: | DKT's FSWs BCIS (baseline and endline) No annual measurement of milestones
| Outcome Indicator 3 |  | Baseline (2012) | Milestone 1(2012/13) | Milestone 2 (2013/14) | Target (2014/15) | Assumptions
Decrease in unprotected sex among students in DKT HEI Universities | Percentage of students reporting having unprotected sex in past 12 months declines in DKT HEI Universities | Planned |  |  |  | 70%
|  | Achieved | 78% |  |  | 64.3%
|  | Source: | DKT's HEI students BCIS (baseline and endline) No annual measurement of milestones
Increase in CPR in DKT project areas | Outcome Indicator 4 |  | Baseline (2012) | Milestone 1(2012/13) | Milestone 2 (2013/14) | Target (2014/15) | Assumptions
| Percentage of WRA in Market Town project areas* who use a modern method of contraception increases from baseline to endline | Planned |  |  |  |  | GOE policy continues to support RH and Social Marketing
|  | Achieved | 32.2% |  |  | 44%
|  | Source: | DKT's Rural BCIS (baseline and endline) and/or EDHS. No annual milestones
OUTPUT 1 | Output Indicator 1.1 |  | Baseline (2012) | Milestone 1(2012/13) | Milestone 2 (2013/14) | Target (2014/15) | Comments
Improved supply of Reproductive Health Products in Rural and Urban Ethiopia | Couple Years Protection provided by reproductive health products sold by DKT | Planned | 1714207 | 3651321 | 5825903 | 8268263 | Cumulative milestones for 33 months, the life of project for CYP will be changed
|  | Achieved | 2093301 | 4741793 | 7336685 | 9362666
|  | Source: | DKT Sales Records
| Output Indicator 1.2 |  | Baseline (2012) | Milestone 1(2012/13) | Milestone 2 (2013/14) | Target (2014/15) | Comments
| % of pharmaceutical outlets in market towns stocking at least three DKT RH product categories | Planned |  |  |  | 80%
|  | Achieved |  | 88% | 95% | 91%
|  | Source: | DKT's MAP (LQAS)**
| Output Indicator 1.3 |  | Baseline (2012) | Milestone 1(2012/13) | Milestone 2 (2013/14) | Target (2014/15) | Comments
| % of market town service providers (clinical outlets) stock at least three DKT product categories | Planned |  |  |  | 80%
|  | Achieved |  | 93% | 90% | 90.1%
|  | Source: | DKT's MAP (LQAS)
| Output Indicator 1.4 |  | Baseline (2012) | Milestone 1(2012/13) | Milestone 2 (2013/14) | Target (2014/15) | Comments
| % of urban (excluding market towns) pharmaceutical outlets stocking at least five DKT product categories | Planned |  |  |  | 76%
|  | Achieved |  | 71.5% | 71.3% | 71.2%
|  | Source: | DKT's MAP (LQAS)
| Output Indicator 1.5 |  | Baseline (2012) | Milestone 1(2012/13) | Milestone 2 (2013/14) | Target (2014/15) | Comments
| 35% of non-pharmaceutical outlets in urban areas stock condoms | Planned |  | 32% | 33% | 35% | Reviesed Target
|  | Achieved | 22% | 30% | 26.3% | 17.1%
|  | Source: | Urban Coverage Assessment survey (LQAS)
| Output Indicator 1.6 |  | Baseline (2012) | Milestone 1(2012/13) | Milestone 2 (2013/14) | Target (2014/15)
| 40% of the urban towns meet minimum coverage standards (2 outlets/1000 population) for condom in non-pharmaceutical outlets | Planned |  | 35% | 37% | 40%
|  | Achieved | 54% | 38% | 23.8% | 26.1%
|  | Source: | *** Urban Coverage Assessment survey (LQAS)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline (2012) | Milestone 1(2012/13) | Milestone 2 (2013/14) | Target (2014/15) | Comments
Increased demand for these reproductive health commodities among target groups 1) Female Sex Workers 2) Rural Women 3) HEI Students | Opportunity: 'Social Norms' score increases from 3.12 to 4.5 among FSW in DKT Wise-Up Areas | Planned |  | 3.5 | 4 | 4.5
|  | Achieved | 3.12 |  | 3.54 | 2.78
|  | Source: | BCIS baseline and endline /OTS (Output Tracking Survey
| Ability: 'Self Efficacy' score increases from 4.63 to 4.80 among FSW in DKT Wise-Up Areas | Planned |  | 4.7 | 4.75 | 4.8
|  | Achieved | 4.63 |  | 4.64 | 4.83
|  | Source: | BCIS baseline and endline /OTS (Output Tracking Survey
| Motivation: 'Attitude' score increases from 4.16 to 4.5 'Belief' score increases from 4.23 to 4.6 among FSW in DKT Wise-Up Areas | Planned |  | 4.30/4.35 | 4.40/4.50 | 4.50/4.60
|  | Achieved | 4.16 (Attitude) 4.23 (Belief) |  | 4.72/4.49 | Attitude and Belife are no more statstically imporatnt indicators
|  | Source: | BCIS baseline and endline /OTS (Output Tracking Survey
| Number of FSW with non-paying partners received key HIV prevention messages including 'boyfriend' messages | Planned |  | 2487 | 3312 | 4000 | Newly recommended
|  | Achieved | 0 | 2512 | 5678 | 4335
|  | Source: | DKT records
| Output Indicator 2.2 |  | Baseline (2012) | Milestone 1(2012/13) | Milestone 2 (2013/14) | Target (2014/15) | Comments
| Significant Opportunity factor (Percieved Availability of FP product/Service) score among rural WRA in Market Town project areas increases from x to y | Planned |  |  |  | 4
|  | Achieved |  | 3.62 | 3.96 | 4.3
* "Opportunity" , "Ability" and Motivation are the 3 major categories of factors affecting behavior. The DKT BCIS research will provide significant factors from each category with baseline levels. These factors will be measured annually with DKT's Output Tracking Surveys (OTS). An endline BCIS will confirm to what extent behavior has changed as a result of DKT's programs. |  | Source: | BCIS baseline and endline /OTS (Output Tracking Survey
| Significant Ability factor (Social Support) score among rural WRA in Market Town project areas increases from x to y | Planned |  |  |  | 3.3
|  | Achieved |  | 2.6 | 3.1 | 3.6
|  | Source: | BCIS baseline and endline /OTS (Output Tracking Survey
| Significant Motivation factor (Belief/Misconsuptions) score among rural WRA in Market Town project areas increases from x to y | Planned |  |  |  | 4
|  | Achieved |  | 3.1 | 3.23 | 3.7
|  | Source: | BCIS baseline and endline /OTS (Output Tracking Survey
| Number counselled for FP in Market Towns (individual counseling) | Planned |  | 7000 | 24300 | 48600 | Newly recommended
|  | Achieved | 0 | 7763 | 32143 | 42651
|  | Source: | DKT records
| Output Indicator 2.3 |  | Baseline (2012) | Milestone 1(2012/13) | Milestone 2 (2013/14) | Target (2014/15) | Comments
| Significant Opportunity score among HEI Students increases from x to y | Planned
|  | Achieved |  | NA
|  | Source: | BCIS baseline and endline /OTS (Output Tracking Survey)
| Significant Ability Factor (Social Support) score among HEI Students increases from x to y | Planned
|  | Achieved |  | 3.1 | 3.5 | 3.64
|  | Source: | BCIS baseline and endline /OTS (Output Tracking Survey)
| Significant Motivation Factor (Outcome Expectation) score among HEI Students increases from x to y | Planned
|  | Achieved |  | 3.4 | 3.31 | 2.88
|  | Source: | BCIS baseline and endline /OTS (Output Tracking Survey)
| Number of Events with majority male target group held in DKT project HEIs | Planned |  | 115 | 228 | 250 | Newly recommended
|  | Achieved | 67 | 308 | 474 | 371
|  | Source: | HEI Project Activty Reports
| Number of sessions with female target group in DKT project HEIs | Planned |  | 48 | 200 | 500
|  | Achieved | 0 | 50 | 224 | 247
|  | Source: | HEI Project Activty Reports
OUTPUT 3 | Output Indicator 3.1 |  | Baseline (2012) | Milestone 1(2012/13) | Milestone 2 (2013/14) | Target (2014/15) | Comments
Improved environment and capacity for supply and promotion of Reproductive Health Products and Services | Increased number of outlets reporting positive experience of DKT training, detailing visits | Planned |  | 60% | 70% | 80% | DKT is establishing a new data collection technique on this indicator
|  | Achieved | To Be Determined | Data not collected (NA)
|  | Source: | DKT Training Records and Semi-Annual Reports
| Output Indicator 3.2 |  | Baseline (2012) | Milestone 1(2012/13) | Milestone 2 (2013/14) | Target (2014/15) | Comments
| Improved policies supporting private sector distribution of RH products | Planned |  | Improved | Improved | Improved
|  | Achieved |  | Improved, new policy is launched on condoms strategy | Improved | Improved, supported the registration of 5 new types of contracpetives
|  | Source: | GOE Policy Documents
| Output Indicator 3.3 |  | Baseline (2012) | Milestone 1(2012/13) | Milestone 2 (2013/14) | Target (2014/15) | Comments
| Research methodology and results shared with RH community | Planned |  | FSW BCIS Results Shared | Rural BCIS Results Shared | Rural BCIS Results Shared
|  | Achieved |  | FSW and Rural BICS shared | Rural BCIS Results Shared | OTS Results Shared
|  | Source: | Dissemination workshop reports and DKT Semi-Annual Reports
* Market Town Project Area - Six regions - Oromia, Amhara, SNNP, Tigray, Afar And Somali
** First round of the MAP survey Data was collected from February to March 2013. The survey surved as a baseline
** First round of the Condom Coverage Assessment (MAP for Condom) survey Data was collected in April 2012 and the second round from May to June 2013.