Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Bihar Agricultural Growth and Reform Initiative (BAGRI)
Programme Value: £10 Million		Review Date: 08 August 2016
Programme Code: 204135	Start Date: 29/06/2015	End Date: 28/06/2020

Summary of Programme Performance
Year	2014	2015	2016
Programme Score	B	A	A
Risk Rating	Medium	Medium	Medium

Summary of progress and lessons learnt since last review

Good progress has been made over the course of the year. Though there has been delay in completing the inception phase primarily due to the state assembly elections, things have started picking up momentum in the implementation phase. The inception pahse which was originally scheduled to be completed in Decemeber, 2015 got completed in March, 2016 and implementation started from April 2016.

 The BAGRI TAST (Technical Assistance Support Team) initiated the inception phase by mobilising the TA team and setting up the office infrastructure at Patna in July 2015. To effectively plan and execute the inception phase work, project mobilisation report (PMR) was prepared, elaborating the detailed work plan, research protocol, research framework, block/village selection, sample plan, quality assurance mechanism and delivery timelines. The PMR was approved by the Government. During the inception phase, the TA team carried out primary and secondary surveys and conducted state and national level workshops to identify and agree priorities for interventions in the areas of Agribusiness, institutional reforms, policy reforms, private sector investment promotion and other related governance reforms in Agriculture.

These activities helped in designing interventions (categoried as state and district level interventions) and in preparing a clear delivery plan. Progress of the inception phase activities was periodically discussed and reviewed by senior GoB civil servants. A draft Inception Report was submitted to GoB in February 2016. Stakeholder consultation workshop was organised in March 2016 inviting feedback on the draft inception report. A consolidated final inception report incorporating feedback gathered from various stakeholders was produced in March 2016.

The implementation phase commenced from April 2016. During April-July 2016, TAST has carried out several activities at state and district level as per the plan included in the inception report. Activities in this period were focussed on: formation of farmer producer organisations; policy support, piloting of price information systems; investment promotion; and infrastructure development. Bihar Agriculture Marketing and Development Authority (BAMDA) Bill was prepared in June 2016. This bill is aimed at providing the appropriate institutional framework for development, promotion and regulation of agriculture marketing in Bihar. Seed sector scan and incentive design, based on the analysys of the existing seed value chain in Bihar, was also prepared.

Under District level interventions TAST carried out work on mobilisation of farmers and has so far formed 136 farmer producer groups. Other district level interventions include training and capacity building of farmers, market linkage activities and price-information dissemination system pilot. Efforts aimed at creating an enabling environment for convergence of the work of the District level GoB officials with the work of other relevant institutions have also been made in this period.

The implementation phase (April-July 2016) witnessed two important national level events at Patna, attracting experts who shared their views and suggestions on reforms in Agricultural marketing and the seed sector of Bihar. This has led to validation of the BAMDA Bill and seed sctor scan report. These events were organised as part of TAST’s intervention execution methodology.

Summary of recommendations for the next year

Agree on prioratisation of activities and milestones for the project and agree project logframe by October.

TAST will ensure timely delivery and continue the Implementation phase activities as per the plan.

The TA team needs to closely coordinate with the B-Grow TA team and the Industries Department on policy issues and to facilitate private investment in food processing and infrastructure .

Improved inter-deaprtmental coordination and grass-roots level convergence with Jeevika, Comfed, and allied agencies will help effective and time bound delivery.

TA Team, in consultation with GoB, needs to start preparing plans for scaling up and instituionalising reforms to ensure programme targets are achieved on a sustainable basis.

TA team should work with the exisiting FPOs (famer producer organisations) and FPO federations formed by Jeevika and NABARD to establish improved market linkages.

Greater attention should be paid to ensure active participation of women memebers in FPOs and for formation of women-led groups.

Value chain analysis conducted during the inception phase needs to be revisited and strengthened for the implementation phase by taking stock of possible options and analysis of pros and cons of such options.

TAST should leverage financial and human resources and converge with the relevant GoB departments/agencies to enhance the programme impact.

TAST needs to build the capacity of the relevant line departments and develop models aimed at bringing about internally-led sustainable changes

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/4158341.odt
DevTracker Link to Log frame:	Quest ID 5538977

Outline of the programme
Bihar is a DFID partner state. It is the poorest state in India with a per capita income of roughly £309[1]. Nearly 80%[2] of the population is dependent on agriculture for livelihood, which contributes around 22%[3] of the GSDP (2010-13 at 2004-05 prices), much higher than the Indian average (14%?). The agriculture sector in Bihar needs reform, investment and regulation. One third of farm produce is wasted for want of post-harvest infrastructure. Farm operations aren not sufficiently profitable because individual landholdings of farmers are small. Farmers are not using technology to to obtain information on commodity prices and weather conditions. The farm–price realisation is very poor due to lack of infrastructure, information and market access. Lack of proper marketing outlets forces them to sell their produce through exploitative middlemen.
[1] Bihar’s Economic Survey (2013-14) highlights that the estimated GSDP at current prices in 2012-13 is Rs. 3.09 lakh crore, implying a per capita income of Rs. 30,930 (approx. £ 309)
[2] www.krishi.bih.nic.in (accessed 28 July 2014)
[3] Bihar’s Economic Survey (2013-14) pp. 6

DFID has agreed to invest £10 million in technical assistance to support Bihar’s Plan for Agriculture and Allied Sectors to raise poor farmers’ income. Primarily, it will do four things: mobilise farmers, build producer federations and create market access by linking with large retail chains, corporate buyers and exporters, promote food processing industries and; help develop institutions that provide regulation, attract investment and conduct research; facilitate technology transfer and help make finance and agriculture information more readily available to farmers through one stop shops; build partnership and linkages between UK and Bihar agriculture research instituions The desired outcome of the project are-
1. Organise more than 75000 farmers into supplier groups that are equipped to access corporate buyers in the market via 20 or more producer companies.
2. Facilitate private investment in storage and supply chain for agriculture and horticulture produce. (Private investment in agriculture storage and infrastructure increased by 100% during the project period).
3. Increased farmer’s access to credit and crop insurance by 50% or at least 1, 00,000 new farmers.
4. Increased access to price information through new technologies to more than 1m farmers.
5. Improved functioning of the public extension network and increase private sector participation.
6. Introduce regulatory reforms for improved market access and farm price realisation for poor and marginal farmers.
7. More than 75,000 farmers are supported on increased production, productivity and improved farm price realisation to improve production as well as marketing.
8. At least 20 producer companies are linked with wholesale markets, big retailers, exporters and food processor.
9. Strengthen existing institutions with appropriate reforms/ restructuring or set up agency/ institutions for: regulating agricultural markets; sharing up-to-date information; attracting investments into agriculture; and commissioning research and market analysis.
10. And promote sector specific partnership between UK and Bihar Institutions.
DFID will use in house and external expert to support Government of Bihar achieve the above mentioned targets. A technical support agency has been contracted through international competitive tender.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

The programme has met expectations and rated as A. Both the outputs have achieved their target. Howeverthere has been three month delays in completion of the inception phase primarily due to state elections. Good progress has been made in the implementation phase. Many of the project activities have been initiated parallelly to recover the lost time and to have demonstartable impact after the first year of implementation. The inception report contains rich analysis and has suggested the schedule of interventions. This is based on the need gap analysis. The report has incorporated the emerging priorities of GoB.

During the course of the year, continuous support to GoB has been ensured through strong rapport building and relationship management, infusing ownership of the programme objectives across different levels in the government. In the implementation phase, the TA team has been responsive to the GoB demands and has ensured quality deliverables. Quality of deliverables has been validated through multiple stakeholder consultations

Overall output score and description: A

As the context of operation was changing the output indicators targets were agreed for one year.
Both the outputs have achieved the agreed milestones and scored A. Under Output 1, the PMR was submitted on time and the state team were deployed within one month of signing of contract. The cluster team and district teams were deployed from November onwards and the first few months the cluster and district teams were engaged in identifying bloks, villages, carrying out the qualitative and quantitative survey, establishing relationship at grassrot level agencies The inception report has rich analysis and deliverables reflect the priorities of the Governemnt and programme objectives.

Under output 2, good pogress has been made in the past three months on formulation of the BAMDA bill, seed policy and formation of FPOs, market linkages and piloting of price information model. More tangible results could have been achieved if implementation phase had started a few months earlier and speedier decisions and approvals had came from the government.

Key lessons
1. In a multi stakeholder large consortium it is important to devote adequate time in the first few months of the project to team building to ensure better team dynamics
2. For projects involving long drawn out inception phase, periodic review of developments by key stakeholders helps in evolution of inclusive interventions with shared ownerships. This was done in this assignment. Howevever, this can be more structured in future projects.
3. Agriculture is a very emotive and politically sensitive subject in Bihar. Therefore, many of the policy and other interventions need state Cabinet approval or CM’s consent. It is, therefore, important to design policies or interventions which are politically acceptable and pragmatic enough for implementation in Bihar’s context.

Key actions
TAST to focus on tangible deliverables and carry out different set of prioratised activities/pilots in a parallel manner so that many of the intrventions can be evaluated and scaled up from next year onwards.

Has the log frame been updated since the last review?

Yes, the mobilisation phase log frame has been amended to capture the implementation phase work for six months period covering all the programme outputs. A separate project log frame for four years of implementation has also been prepared and shared. It is now under consultation with GOB . The logframe to be finalised by October this year.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Project Mobilisation Report and Inception report completed and agreed by GoB
Output number per LF	1	Output Score	A
Risk:	Minor	Impact weighting (%):	50%
Risk revised since last AR?	Y	Impact weighting % revised since last AR?	Y/N

Indicator(s)	Milestones	Progress
PMR endorsed by DoA, GoB / Inception report and delivery plan endorsed by DoA, GoB / Team deployed and relationship and network developed	August, 2015 / Inception report submitted by December 2015 and approved by February 2016 / District and cluster team deployed ; linkgaes with Other GOB partners and private players established	PMR approved by GoB in September’2015 / Inception report submitted in March 2016 and in principle agreement reached with GoB in June 2016 / Team deployment started in Nov- Dec 2015 and relationship and network building from Nov 2015. Full cluster and district teams deployed from March 2016

Key Points

Project Mobilisation Report (PMR)
PMR was prepared with the objective to summarize the shared understanding of the scope of the BAGRI programme, document various activities to be carried out by BAGRI-TAST for project mobilisation and to spell out the proposed methodology and to agree a work plan for execution of the inception phase work.

Inception Report
The inception report has deliberated on the findings of studies carried out on the current agribusiness scenario of Bihar, including an in-depth study of issues faced by farmers during production, post-harvest handling and marketing of produce, private sector involvement across the Agri-value chain and the institutional and policy framework that governs the operation of agribusiness in the state. A detailed primary survey was undertaken and strategies and methodologies for interventions were developed. On the basis of the primary survey and related analysis, a baseline has been developed.The report has identified need-gaps and state and district level interventions that are planned to be implemented during the implementation phase for all the four outputs along with a clear M&E framework.

Team deployment and rapport building with key institutions & departments

District and cluster teams have been deployed.TAST is coordinating with all the relevant institutions and departnments to leverage their strengths for effective implementation of intervention in various districts.

Summary of responses to issues raised in previous annual reviews (where relevant)

Most of the recommendations like fornightly review,submission of the Project initiation document have been adhered. The inception report also covered other recommendations made in last year’s review- like focus on women groups and small and marginal farmers, developed baselines through primary survey and delivery plan and staretgy covered issues on leveraging resources and building partnership. However, the recommendation on submission of inception report by December 2015 couldn’t be met. The first draft of the Inception report was shared in February 2016 . This was primarily due to change in bureaucracy and state elections.

Recommendations
None

Output Title	Policy support and Field level interventions started
Output number per LF	2	Output Score	A
Risk:	Minor	Impact weighting (%):	50
Risk revised since last AR?	Y/N	Impact weighting % revised since last AR?	Y/N

Indicator(s)	Milestones	Progress
Producer GroupFormed	110	136 Farmer Producer Groups formed
BAMDA Bill prepared and legislated ”	BAMDA bill prepared and submitted by March 2016	Draft Bill was prepared and submitted in April 2016 and final bill in June 2016 after incorporating the GoB feedback
Seed policy drafted and submitted	June 2016	Concept note and draft policy shared with GoB in June 2016. Consultation process is on within and beyond GoB
Model for sharing of price Information system developed	Pilot model for a single district to be launched in July 2016	District pilot for price information system has been launched on 2nd August
Forward Market linkages developed	At least one forward linkage model developed with an identified prtner	Feasibility for Comfed based F&V retail going on. Initial discussions held and in-principle agreement has been reached between Comfed and the Dept. for Agriculture. / Tie up with ITC for procuring potatoes is in final stages.

Key Points

The TA team has already formed 136 farmer producer groups against a target of 110 groups. Apart from mobilisation and formation of the goups, the TA team has carried out sensitisation workshops in all the districts and identified blocks. It has also carried out training programmes, has developed tool kits and explored convergence and linkages with other established farmers federations formed under NABARD and Jeevika.

Bihar Agricultural Marketing Development Agency (BAMDA) Bill

BAMDA Bill is intended to provide an effective institutional framework for development, promotion and regulation of agriculture marketing throughout the state of Bihar with an aim to safeguard and promote the interests of farmers and other relevant stakeholders. The bill intends to establish the Bihar Agricultural Marketing Development Authority to act as the apex state institution for development of agricultural marketing in Bihar and to implement the minimal regulatory requirements contained in the bill. The draft bill has been prepared and a national level workshop has also been conducted to learn from the experiences of other states. The bill has gone through several iterations and is now with the state Cabinet.

Seed Production Promotion Policy
The TA team has carried out sector-scan of the existing seed value chain in Bihar, taking into account aspects of production, processing, procurement, marketing and distribution. Need-gap study and market size mapping for field and vegetable crops has also been carried out. The report contains analysis of the existing institutions involved in seed value chain in Bihar such as BRBN ,BSSCA and other institutions relevant for strategic institutional reforms.The report also contains the situational analysis of seed multiplication farms and has identified strategies for their strengthening. A critical analysis of the prevailing schemes, government programs and incentives to promote private sector participation has been elaborated in the report. A workshop was organised on this theme. Based on the comments and the feedback received from investors, farmers and the experience of other states, the TA team is drafting the Seed production policy and trying to attract investors interested in seed production and distribution.

Price information system pilot completed. Launch scheduled

Under output 2 for developing market information systems, the TA team has analysed the existing market information dissemination scenario, best practices and potential bottelenecks . The team will roll out various pilots and strategies to test what works and then scale up the successful strategies. A price information systems pilot has been developed. It was rolled out on 2 August, 2016 for potatoes and onions. Based on the lessons learnt, this pilot will be scaled up for other vegetables as well.

Forward Market linkages developed-

As part of the forward market linkages, the TA team is working on various product value chains. TA team is consulting some big corporates on contract farming and some local companies for investment in food processing / warehousing facilities. The feasibility study and discussion with the COMFED are at an advance stages for direct retail initaives in fruits and vegetables through COMFED outlets.

Summary of responses to issues raised in previous annual reviews (where relevant)
NA

Recommendations
TA team should adhere to the timelines and deliverable targets.

GOB and DFID should continue to have a meeting with the TA team on a fortnightly basis to assess progress and iron out implementation issues and bottlenecks.

The TA team needs to build master trainers and hire local resource persons under resource pool for continuous nurturing and hand holding support of Farmer Producer Organisations. This is important to achieve the programme targets and objectives.

TA team need to use resource pool and leverage GoB funds for procuring hardwares or additional human resources for pilots and demonstration projects.

The TA team need to work in cordination with the B-Grow TA team for facilitating investments in foodprocessing, farm mechanisation and seed production.

Various options and models should be developed and piloted for market linkages, price information systems and warehousing in the next one year for identifying right solutions/models for sclaing up.
## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

BAGRI is one of the first TA only projects in Bihar. Main cost drivers under BAGRI TA are fees and travel/logistics costs of experts for implementing reform initiatives and pilot projects. DFID has agreement with Government of Bihar to provide furnished office space and cost of utilities of TA team which is a substantial saving. Thus far the programme has spent £0.436 million towards the cost of inception phase.

VfM performance compared to the original VfM proposition in the business case
The TA programme completed its inception phase in June 2016 and moved to implementation in July 2016. The full vfm cannot be compared at this stage. Many of the policy and implementation measures which are been identified for the implementation phase will lead to significant impact on farmers income and private investment . Propoer vfm assessment can be done when the schemees and interventions are fully rolled out and after one or two cropping cycle.

Assessment of whether the programme continues to represent value for money

We have agreement with GoB and TA team to identify payment based deliverables on an yearly basis, clearly linking them with the logframe indicators, so that proper assessment of value for money can be carried out during the annual review and make necessary adjustments.

Quality of financial management

BAGRI project has yearly budget allocation for the next 3 years (2016-17- 2018-19). This budget has been profiled into the ARIES system based on the payment based deliverables agreed with the TA team. DFID project team closely monitor the performance of TA team and the quality of deliverables. Payments will be cleared only after the GoB and SRO confirms in writing that the TA team delivered the agreed milestone deliverables satisfactorily and invoices may be cleared. All project expenses, including TA team’s travel, accommodation, and other related costs will be made on a reimbursable basis on submission of invoices.

Date of last narrative financial report
Date of last audited annual statement

E: RISK (½ page)

Overall risk rating: Moderate

Overview of programme risk

Risks	Mitigation measures
Frequent shifting of senior GoB officials involved in project may delay the process of implementation	BAGRI TAST to request for and facilitate a smooth handover process for such transitions.
Proposed policy reforms may be delayed because of need of wider discussions and consensus of political representatives and various departments/agencies of GoB	Buy-in from DoA, Chief minster, the state Cabinet and other relevant GoB departments will be ensured at the concept stage itself. In addition each policy proposal will be subjected through a multi-stakeholder workshop to obtain views and buy-in from sectoral experts while ensuring key decision makers from GoB
Inadequate response from private sector investors due to external business environment	TAST has extensive relationships with private sector – both within and outside Bihar which will be leveraged. In addition, the TAST’s past experience in implementation of agribusiness specific investment promotion activities and greater coordination and linkage with the Indutries Department and the B-grow team will be used to create greater awareness about government’s intent to promote private investment in the state.
There may be delay on behalf of the Government of Bihar on converting existing investment proposals into actual investments	Our methodology for promoting private sector investment addresses this issue to a great extent by setting up a dedicated investor facilitation desk. A key function of TA team would be to follow up with various departments and bodies to track the point at which the investment proposal is stuck and facilitate a dialogue between the Department and the investor.
Implementation of institutional reforms initiatives might be delayed due to long drawn government procedures and processes in place for implementation of the same	Key stakeholder buy in for each of the institutional capacity building initiatives has been obtained during the inception phase. During the implementation phase, BAGRI TAST will closely engage with key stakeholders and decision makers to speed up the process of approval. In addition, a quarterly review meeting chaired by the APC will be taken up to monitor progress and address hurdles and challenges faced during implementation.

Outstanding actions from risk assessment

- APC, who has ably led this programme from the GoB side so far, is like to retire in 2016. It will be useful to gently take up this issue at the appropriate level in GoB to minimise the possibility of an inappropriate replacement.
- To avoid further slippages on programme delivery, reasons that may cause delays will be identified and addressed through appropriate actions.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe – Y

BAGRI programme design contains 54 months of Implementation phase and 6 months of Inception phase. However, Inception phase was delayed by 3 months majorly due to state elections and administrative changes in the state..

However, accelerated efforts are being made by TAST in implementation phase to cover the time lost during inception through preponement of deliverables. Therefore no further remedial action is required.

Performance of partnership (s)

There has been a very high quality engagement with GoB officials and senior bureaucrates during the last year of project execution. Fortnightly review by the APC,Bihar during inception phase helped in designing BAGRI interventions.This was further supported by frequent interactions with the Project Director, BAGRI - cum – Director Agriculture, DoA,GoB and nodal officer,BAGRI. Project execution is being done in close coordination and collaboration with respective project district GoB officials (DAO.DHO,PD-ATMA)

Asset monitoring and control
NA

G: CONDITIONALITY (½ page)
FID India support to GoB is based on a shared commitment to the four principles for all development partnerships (to support poverty reduction and the MDGs, human rights and international obligations, public financial management, good governance and transparency, and domestic accountability).

Principles	Overall	Programme specific
PP 1: Poverty reduction and the MDGs	GoB is strongly committed to poverty reduction. Poverty in Bihar declined from 54.4 per cent of the population in 2004-05 to 37.9 per cent in 2009-10 and, thereafter, to 33.7 per cent in 2011-12. However, it is still home for about 15% of India’s poor.	BAGRI will have direct impact on poverty levels in 11 focus districts. The programme aspires to impact the income levels of about 1 million farmers engaged in horticulture (directly mobilising 125,000 small farmers into producer organisations) through strengthening market linkages. GoB has keen interest in supporting BAGRI interventions as evidence building for bringing in pro-poor policies on agriculture and scaling up the BAGRI interventions to remaining districts of Bihar.
PP2: Human Rights	Since 2007, incidences of human rights violation in the state have seen dramatic reduction. However, 15 districts out of 38 districts in Bihar continue to be categorised as Left Wing Extremist (LWE) hit by Government of India. Last year (2013) 176 incidences of naxal violence was reported in the state (significantly less than previous years, 232 in 2009, 307 in 2010 and 316 in 2011) with about 70 civilian casualties. Bihar has also been known for caste based violence and existence of caste centric extremist groups such as Ranvir Sena, but such incidences have reduced in recent past.	BAGRI will not have any significant contribution on the human rights situation in the state. But it is expected that the project interventions will support dignified living through improved access to agriculture programmes, and private sector investment in agriculture – all leading to improvements in farm price realisation by small and marginal farmers in the state.
PP3: Strengthening financial management and accountability, and reducing the risk of funds being misused through weak administration or corruption	Bihar has been able to contain its Gross Fiscal Deficit within 3% of GSDP for last three years and could steer substantial surge in domestic revenues. However, its dependence on central resources remains to be highest in the country with lowest own tax: GSDP ratio at around 5%. The state introduced several reforms but continues to be known for its low administrative and institutional capacity.	BAGRI will directly address the gaps in fiscal and administrative capacity of the state, though restricted to departments having influence over agriculture sector in Bihar (such as Agriculture and Food Processing Directorate). It is expected that the programme will influence fiscal spending of prominent agriculture sector programmes (the extent of such an influence will be adjusted when the baseline and yearly milestones are finalised).
PP4: Strengthening domestic accountability	Bihar in the last eight years brought in several inclusive social policies with new legislated ‘right to public services’. The state government has adopted ‘development with justice’ as its overarching principle and steered large state sponsored social programmes from its own revenues.	Several interventions planned under BAGRI will have implications on strengthening domestic accountability. At this stage it is anticipated that formation of farmers’ institutions and their capacity building to interact effectively with formal technology, finance and market institutions will put pressure on the government institutions to respond to their needs. Design and institutionalisation of farmer centric agriculture policies will also strengthen the demand and supply side relationships in the state.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

The programme lays significant impetus on evidence guided planning and implementation. Best practices within the country and from outside will be used to design and implement the project interventions. Further, during inception phase, baseline has been established arriving at yearly milestone and indicators against each output and outcome. There is also a provision for a third party impact evaluation towards end of the project. The monitoring and evaluation activities will entail participation of all the project stakeholders including all stakeholders (farmers, district level officials, concerned GoB departments at state level, TA agency and Task Team).

Monitoring progress throughout the review period

As per the programme memorandum, the project progress is being monitored on a quarterly basis by partner departments and DFID against agreed work plans and on a six-monthly basis by the Governing Council. With GoB, DFID will undertake annual Output to Purpose Reviews (OPR) in line with standard DFID policies and based on the Programme logical framework.

Further, a mid term review is planned for the project after 2.5 years from the implementation of project. This will assess the performance of the TA agency and the efficacy of partnership with GoB within the ambit of prevailing political situation in the state to take informed course corrections in the remaining project period.

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. The Aid Management Platform (AMP) and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
A: Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the log frame been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Output Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the log frame (and which will need to be entered on AMP as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Minor/Moderate/Major/Severe / Enter: Minor, Moderate, Major or Severe / The Risk Rating here should match the Risk currently shown on the log frame (and which will need to be entered on AMP as part of loading the Annual Review for approval). / Where the Risk for this Output has been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section E Risk
Key points
Summary of response to programme issues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D: Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of financial management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E: Risk
Overall Risk Rating: Minor/Moderate/Major/Severe / Enter Minor, Moderate, Major or Severe, taken from the overall Output risk score entered in AMP
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Detail the key risks that affect the successful delivery of the expected results and mitigating actions. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix etc. / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process