Tax Administration Diagnostic Assessment Tool: 2016 Annual Review

Programme Title: / Support for the Tax Administration Diagnostic Assessment Tool (TADAT)
Programme Code: / 204114	Review Date: / 19 Aug 2016
Programme Value: / £1,783,000	Programme Duration: / 24 Jul 2013 - 30 Jun 2019

Programme Performance

Year	2015	2016	2017	2018	2019
Type	Annual / Review	Annual / Review	Annual / Review	Annual / Review	Project Completion / Review
Period	24/07/2013 – / 19/05/2015	20/05/2015 – / 19/08/2016	20/08/2016 – / 19/08/2017	20/08/2017 – / 19/08/2018	20/08/2018 – / 30/06/2019
Duration	12 months / (Plus 10 mths’ planning)	15 months	12 months	12 months	10 months
Score	B	A
Risk Rating	Medium	Moderate

Programme Description

TADAT assesses countries’ tax systems and produces a performance assessment report (PAR) detailing its strengths and weaknesses. This provides the basis for more targeted and effective tax reform and capacity building work. Repeat assessments allow for evaluation of progress. TADAT complements a similar tool called PEFA which assesses public financial management systems.

TADAT activity is managed by a small secretariat based in the International Monetary Fund (IMF). The direction of TADAT activity is directed by a Steering Committee comprised of representatives from the IMF, the World Bank and partner donor countries (the UK, Norway, Switzerland, the Netherlands, Germany, Japan and the European Commission), which is assisted by a Technical Advisory Group (TAG).

DFID is contributing £1,678,000 to the TADAT trust fund over four financial years as follows:
Financial Year	2014/15	2015/16	2016/17	2017/18
Amount	£425,000	£253,000	£500,000	£500,000

DFID also reserved £175,000 for use by DFID for TADAT assessments in priority countries including £100,000 for 2015/16.

TADAT Business Case	http://iati.dfid.gov.uk/iati_documents/4454879.docx
TADAT Logframe	http://iati.dfid.gov.uk/iati_documents/4454890.xlsx

About this Document

The UK Government’s Department for International Development spends UK international aid (known as ‘Official Development Assistance’) by designing and implementing programmes, often in partnership with other countries and organisations.

This Annual Review is part of a continuous process of improvement to assess the performance and relevance of the programme. Spending and programme management teams then decide whether the programme should continue, be amended or stopped entirely. The review includes specific, time-bound recommendations for action, consistent with the key findings.

This document reviews the activity of a programme called ‘Support for the Tax Administration Diagnostic Assessment Tool’, known as ‘TADAT’ for short. The programme runs over four financial years until 2019. This is the second annual review; the first, conducted in May 2015, can be found here.

This review covers the period since the last review until August 2016. It covers 15 months’ activity rather than 12 because the review date was changed to align with the TADAT Secretariat’s reporting calendar. The TADAT website can be found here.

This review covers progress against the targets and aims to set out in the programme’s business case and logframe and makes recommendations on how to improve the programme. This was a desk-based review (no field visits) which primarily reviewed documents but also incorporated information from interviews with key personnel.

The Annual Review assesses and rates outputs using the following rating scale: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

This document is 17 pages and is written in plain English.

We welcome your feedback. Details of how to contact DFID can be found here.

Review Summary

Summary of Changes since 2015 Annual Review

The TADAT Steering Committee produces its annual report for the Steering committee meeting in June. The annual review date has therefore been amended to August to allow time to reflect on the information in the annual report.

DFID’s internal risk register has changed since the 2015 annual review was published. This document uses the new risk ratings. This is explained in more detail on page 14.

The DFID logframe has also been amended. Initially the logframe included indicators detailing the set-up of the management structure and other start-up activity and a number of the indicators finished in 2016. These are no longer necessary and have therefore been changed to better align with indicators in the TADAT internal logframe. This is detailed on page 16 Monitoring and Evaluation.

Update on 2015 Annual Review Recommendations

Recommendations for Logframe Amendments	Update
Outcome indicators 1 and 2 should be merged so that all assessments facilitate dialogue and influence reform plans.	Completed. Logframe updated May 2015.
Indicator 1.1 should be met by Nov 2015 due to Steering Committee decision to extend pilot period.	Completed. Logframe updated May 2015. / Field Guide officially launched on 18 Nov 2015.
Milestones for indicator 2.1 to drop stipulation that 50% of assessments should be done in developing countries as most will be anyway.	Completed. Logframe updated May 2015. Since May 2015 10 assessments have been in low income countries, 6 in lower middle income countries and 11 in upper middle income countries.
Indicator 2.3 should be revised to ‘80% (indicative) of feedback from stakeholders through perception survey is positive’. Should be reviewed before perception survey is conducted in 2018.	Completed. Logframe updated May 2015.
Other Recommendations	Update
TADAT should be promoted in low- and lower-middle-income countries as this is where there is most need for capacity development.	Ongoing.

Summary of Performance

Output Indicators	2016 Milestone	Impact Weighting	2016 Progress	2016 / Score	2016 Grade
Indicator 1.1	Assessment tool and indicators are finalised and in use.	30%	Achieved	15 / /15	A
Indicator 1.2	Annual work programme continues to be delivered. Management stable.		Achieved	15 / /15	A
Indicator 2.1	15 assessments in developing countries (including pilot assessments)	70%	100% achieved	60 / /60	A
Indicator 2.2	One DFID- led and funded assessment in a DFID priority country.		Not achieved	0 / /10	C
Total		100%	86% achieved	86 / /100	A

See page 8 for full details. Click here for the existing logframe.

TADAT 2016 Annual Review Recommendations

Recommendation 1: DFID should work with the Secretariat to develop the formal survey planned for December 2016 that will monitor the use of assessments in developing reform plans and ensure that it seeks feedback from DFID tax programmes.

Recommendation 2: Output Indicator 1 - Now that the TADAT tool has been launched, indicator 1 should be amended so that it measures the continual delivery of the workplan as delivered against the TADAT programme Log Frame.

Recommendation 3: Output Indicator 2.2 - It is recommended that DFID works with its country offices to strongly encourage the use of TADAT as a diagnostic tool with the aim of leading and participating in further assessments in DFID countries.

Recommendation 4: DFID should compare costs of funding other similar diagnostic tools and assessment missions, against that of the TADAT to ensure value for money, including staff travel and subsistence cost and assessor training. DFID should work with the Secretariat to ensure that the external evaluation assesses the value for money of the programme.

Summary of Risk

Risks	2016 AR / Risk Assessment
Tax authorities in TADAT countries have insufficient capacity to implement necessary reforms.	Impact: Major / Likelihood: Possible
Too few assessments are carried out in DFID priority countries.	Impact: Major / Likelihood: Possible
Take-up of TADAT by developing country tax administrations is low.	Impact: Major / Likelihood: Unlikely
The TADAT Secretariat cannot recruit technical experts to carry out TADAT assessments.	Impact: Major / Likelihood: Unlikely

This programme has been assessed against DFID’s new risk management matrix. Please see page 14 for full details.

Summary of Progress
Launch of the tool: Originally planned to commence in early 2015, the TADAT Field Guide was officially launched on 18 Nov 2015, following an extension to the pilot phase. This extended pilot phase allowed for various improvements to be made to the assessment methodology and highlighted several tax system weaknesses, unreliable data being the most notable and far-reaching.

Training of assessors: Between May 2015 to May 2016, 345 people completed TADAT training through a mixture of online learning and training workshops. Of these, 141 are “trained TADAT assessors”, i.e. they have international technical assistance experience. The TADAT secretariat has identified the need to convert the large numbers of “Trained TADAT persons” to “trained assessor” status, which they can do by conducting two assessor missions to try to increase the numbers of TADAT assessors from Africa and the Middle East. Eleven team leaders were successfully trained at a formal workshop in Slovenia in January 2016. A further team leaders' workshop is taking place in September in Washington.

Trust fund management: Since the last annual review, the TADAT Steering Committee has met twice annually (on 16 June 2015, 2 December 2015 and 16 June 2016) and made progress on a number of issues, including the training of assessors, the number of assessments being successfully completed. The Secretariat has produced a more detailed Log Frame to monitor delivery of the programme, which has now been approved by the Steering committee.

TADAT assessments: Between May 2015 and August 2016, 27 TADAT assessments were carried out. In total, 16 assessments were carried out in lower- and lower middle income countries (59% of all assessments), eleven of which are DFID priority countries. A further six pilots were completed before the review period which are not shown on the table below.

DFID assessments: Although DFID has not yet led and funded a TADAT assessment we have sent HRMC accredited assessors to assessments in Uganda, Tanzania and Sierra Leone and was involved in the assessment mission in Ethiopia.

Quality assurance: A quality assurance process for all TADAT Performance Assessment Reports (PARs) is now in place and since March 2016 a double review of reports by TAG and Secretariat members has increased assurance. All PARs reviewed between May 2015 and April 2016 have been approved.

TADAT outreach: TADAT is becoming a recognised diagnostic tool in the field of tax. All TADAT partners and leading technical assistance providers are now using the tool. TADAT material has been translated into various languages to aid effective dissemination, and TADAT outreach activities continue to be undertaken globally by the Secretariat and proxies.

Further work: Additionally, feedback is being analysed for any potential issues that require attention. So far, the Secretariat has identified that meeting training needs requires more resources than initially envisaged and that donor partners could be more responsive/proactive in their roles as lead assessors.

Programme Performance

Annual Outcome Assessment

Outcome Indicator 1: The extent to which TADAT assessments facilitate dialogue about tax administration reform and directly influence donor programmes and tax administration reform plans.

- Milestone 1 (June 2016): TADAT assessments facilitate dialogue and influence reform plans in all cases.
- Evidence Source: Feedback from stakeholders as to the extent that TADAT assessments facilitate discussion – supplied by TADAT Secretariat and DFID country programmes.

Comment: The TADAT secretariat has report that TADAT assessments are being used to inform reform plans in Fiji, Rwanda and Tanzania. Furthermore Comoros is keen to use assessment results to reform their tax administration and is collaborating with the World Bank in this regard. Last year’s annual review noted that the TADAT pilot in Mozambique was used to formulate a reform programme for the tax authority and in Malawi, GIZ used the TADAT pilot to refine their tax capacity building programme.

Although there has been some early positive feedback it is still too early to say definitely whether TADAT assessments are starting to influence dialogue amongst donors and tax authority reform plans and so it’s too early to judge whether the theory of change is holding true. DFID has repeatedly raised this issue in steering committee meetings and as a result the Secretariat have included an outcome in their own log frame that monitors use of assessments to develop reform plans and plan to conduct a formal survey in this regard by December 2016.

The Impact (improved performance of tax administrations in developing countries) can only be judged when there have been a number of repeat assessments.

The 2017 annual review should report on the results of this survey against the DFID Log Frame Outcome indicator.

Recommendation: DFID should work with the Secretariat to develop the formal survey planned for December 2016 that will monitor the use of assessments in developing reform plans and ensure that it seeks feedback from DFID tax programmes.

Detailed Output scoring

The table below gives an overview of the programme’s performance against the indicator milestones set out in the logframe. The majority of the programme’s targets have been achieved; outputs therefore met expectation (scoring A).

Two things to note:
1. Indicator 2.1 has met its target through 16 assessments, pilots and full assessments, in developing countries (lower- and lower middle income countries) with a further eleven assessments in upper-middle income countries. Eleven of the assessments in the last year were in DFID priority countries.
2. Indicator 2.3 has not been included in the table below as the next relevant milestone is not due for assessment until 2018.

Output Indicators	2016 Milestone	Impact Weighting	2016 Progress	2016 / Score	2016 Grade
Indicator 1.1	Assessment tool and indicators are finalised and in use.	30%	Achieved	15/15	A
Indicator 1.2	Annual work programme continues to be delivered. Management stable.		Achieved	15/15	A
Indicator 2.1	15 assessments in developing countries (including pilot assessments)	70%	Achieved	60/60	A
Indicator 2.2	One DFID- led and funded assessment in a DFID priority country.		Not achieved	0/10	C
Total		100%	86% achieved	86/100	A

Output Indicator 1: TADAT infrastructure is in place and delivering its agreed work-plan. The assessment tool is finalised, the management structure is in place and TADAT is fully operational.

Output Indicator 1.1: Extent to which the assessment tool and the indicators are finalised.
- Target (2016): Tool continues to be used in assessments.
- Evidence Source: TADAT Secretariat Annual Reports, external audits.
- Result: Achieved. TADAT’s Field Guide was officially launched in November 2015 and the tool is now fully operational. The TADAT assessment indicators are also finalised (these can be found here).

Output Indicator 1.2: Extent to which management structure is in place.
- Target (2016): Annual work programme continues to be delivered. Management in steady state.
- Evidence Source: TADAT Secretariat Annual Reports, external audits.
- Result: Achieved
As well as delivering the work-plan as agreed by the Steering Committee, a TADAT logframe has been developed by the Secretariat and approved by the Steering Committee.

Comment: The key outputs of the programme over the last year are outlined in the summary of progress on page 6.

One of the key new instruments that will be used for monitoring the progress of the programme is the TADAT Log Frame that was approved by the Steering committee on a lapse of time basis in time for the June Steering committee meeting. The TADAT Log Frame tracks and measures the following outcomes: 1) preferred assessment tool; 2) effective dissemination; 3) systemic quality assurance; and 4) positive impact. It also has an overall objective for TADAT to contribute to strengthened tax administration systems and domestic revenue mobilisation efforts globally, with an indicator on whether assessments are a key input into tax administration reform strategies mirroring the DFID outcome indicator.

Although it is different in structure to the DFID programme Log Frame and has more detail there are considerable overlaps between the two and the TADAT Log Frame can serve as a good tool to monitor the ongoing progress against output indicator 1.2.

Output Indicator 1 Recommendation: Now that the TADAT tool has been launched, indicator 1 should be amended so that it measures the continual delivery of the workplan as delivered against the TADAT programme Log Frame.

Output Indicator 2: TADAT is globally recognised as producing high quality and standardised tax administration diagnostic assessments which are undertaken in a sufficient proportion of developing countries, identifying the relative strengths and weaknesses of their tax administration systems.

Output Indicator 2.1: The number of assessments undertaken by TADAT in developing countries.
- Milestone 1 (2016): 15 assessments in developing countries (includes pilots converted to full assessments).
- Evidence Source: TADAT Secretariat extranet/ Annual Reports.
- Result: Achieved. Between May 2015 and August 2016, 16 assessments have been carried out in developing countries[1]. See table on next page.
  [1] Defined in this case as those categorised by the World Bank as ‘Low/Lower Income’ or ‘Lower Middle Income’

Output Indicator 2.2: Number of TADAT assessments facilitated and funded by DFID.
Milestone 1 (end 2015): TADAT assessment facilitated and funded by DFID in one DFID priority country.
Evidence Source: DFID Staff in the UK and Country Offices.
Result: Not achieved. Although DFID has not yet led and funded an assessment we are actively promoting the tool and have facilitated and taken part in a number of assessments in DFID countries.

Comment: This indicator was originally intended to measure the use of DFID funds allocated in the original programme budget for DFID-led assessments. This contingency has not been used as other donor have led on assessments in DFID priority countries since the launch of the tool, meaning that we have yet to act as the lead facilitator for a TADAT mission.

Despite not leading a mission DFID has engaged in the delivering missions in country. In Ethiopia, our HMRC long term adviser attended assessment meetings and advised the assessment mission. In Tanzania, our HMRC long term adviser was one of the TADAT assessors on the mission, having become accredited. Both missions were led by the IMF. We have pursued assessments in Nepal and Ghana but have yet to receive permission from the tax authority to progress. The UK has also sent an HMRC-accredited assessor on the Uganda mission in August 2015 and will send an HMRC assessor on the upcoming Sierra Leone mission. Overall, the “hit” rate of assessments in DFID countries is relatively high – eleven countries out of 27 assessments since May 2015.

Although the TADAT secretariat has been facilitating TADAT assessments since roll out, it is donors that should take up this responsibility in the long term and use TADAT to inform their programmes. DFID should be at the forefront of this effort by leading and participating in missions where we have tax programmes.

Output Indicator 2.2 Recommendation: It is recommended that DFID works with its country offices to strongly encourage the use of TADAT as a diagnostic tool with the aim of leading and participating in further assessments in DFID countries.

Output Indicator 2.3: TADAT is recognised as the principle assessment tool for objectively assessing tax administration performance.
Target (2018): 80% positive (indicative) stakeholder feedback from perception survey.
Result: This is not due for review until 2018. The TADAT secretariat plan to conduct a perception survey in 2018.

TADAT Assessments – May 2015 to August 2016
Country Name	Type	Date
Kosovo	Pilot	May 2015
Malawi* ^	Pilot	May 2015
Cote d’Ivoire ^	Pilot	Jun 2015
Madagascar ^	Pilot	Jun 2015
Malaysia	Pilot	Jul 2015
Rwanda* ^	Pilot	Aug 2015
Uganda* ^	Pilot	Aug 2015
Egypt ^	Pilot	Oct 2015
Philippines ^	Pilot	Oct 2015
Montenegro	Pilot	Oct 2015
Jamaica* ^	Pilot	Oct 2015
Comoros ^	Full	Jan 2016
Tanzania* ^	Full	Feb 2016
Jordan	Full	Mar 2016
Ethiopia* ^	Full	Apr 2016
Serbia	Full	Apr 2016
FYROM	Full	May 2016
Namibia	Full	May 2016
Vietnam ^	Full	May 2016
Zambia* ^	Full	May 2016
Georgia	Full	May 2016
Albania	Full	Jun 2016
Liberia* ^	Full	Jun 2016
Lebanon	Full	Jul 2016
DRC* ^	Full	Aug 2016
Kyrgyzstan* ^	Full	Aug 2016
Sierra Leone* ^	Full	Aug 2016
DFID Countries: 11	Total: 27	15 months

(* denotes DFID priority country, ^ denotes low or lower-middle income country[2])
[2] World Bank country lending groups, https://datahelpdesk.worldbank.org/knowledgebase/articles/906519-world-bank-country-and-lending-groups

Value for Money and Financial Performance

Key Cost Drivers and performance

DFID has four financial components to fund TADAT. They are detailed below. Payments are issued twice yearly in instalments.

Code	Use	2015-16 Budget
204114-101	TADAT Trust Fund	£500,000
204114-102	Programme development	No longer active.
204114-103	Assessments by DFID Country Offices	N/A. None undertaken.
204114-104	Travel	£3,000
TOTAL		£503,000

As of 30 April 2016, the key areas of expenditure for the programme are staff salary, and travel and subsistence. The table below shows expenditure for financial year 2015-16. Despite the steering committee approving an increase in the budget by almost $200,000 to US$2,636,598 in December, total expenditures for 2015/16 came in under budget at US$2,392,164. All TADAT partner donors fund this activity, not just DFID. As it is a multi-donor trust fund, we cannot trace exactly which activity has been paid for by DFID.

Category of Expenditure	Amount (USD)
Staff salary	$1,189,081
Travel and salary	$519,699
Staff travel	$377,063
7% trust fund management fee	$156,497
Interpretation/translation	$72,197
Workshops/seminars	$61,358
IT systems/web design	$10,000
Office supplies and equipment	$6,269
TOTAL	$2,392,164

TADAT is growing in reputation amongst donors, which is reflected in additional donors indicating an interest in funding the tool. The total pledged resources for the TADAT trust fund sub account are estimated at US $8.2 million. The European Commission will sign an agreement in summer 2016 to contribute a further US $2.2 million to the trust fund raising the Programme Budget to $10,373,000. This means that the sub-account is over-resourced, also an issue flagged at the last annual review. The steering committee will have to decide how to allocate the extra resources; possible options include funding for assessments where there is no lead donor, research and analysis of TADAT results or potentially rolling it over to the next phase of the trust fund.

Based on projections for year 4 (2016/17) activities the TADAT secretariat expects to see high levels of activity and has proposed a budget of US$2,319,927 which has been approved by the Steering Committee. It is likely that the Secretariat will continue its support for ongoing assessments, while non-Secretariat assessors gain the confidence to conduct assessments on their own. The Secretariat will also grow outreach activities to promote the tool further and they will have a greater focus on quality assurance.

Value for Money

DFID assesses the value for money of TADAT by monitoring the programme’s accounts as a member of the steering committee. The programme budgets have been approved by the steering committee and spending has been broadly in line with the budgets.

As set out in the business case, the costs to DFID are less than the World Bank’s PEFA programme, which DFID also funds and which performs a similar task in assessing PFM performance. However, we have not performed a detailed comparison of costings between the two programmes.

It should also be noted that by paying into the TADAT trust fund DFID is paying for the maintenance and promotion of the TADAT tool, we are not paying for TADAT assessments. These should be funded by donors and in the case of DFID out of tax programme funds.

In the second half of 2017, after three full years of operation, an independent evaluation of the work under the trust fund will be conducted. External experts will assess the effectiveness of this work and formulate recommendations. The findings will inform discussions on operations for the remainder of the programme. The terms of reference, methodology, and performance indicators will be proposed by the IMF to be endorsed by the Steering Committee in December.

Recommendation: DFID should compare costs of funding other similar diagnostic tools and assessment missions, against that of the TADAT to ensure value for money, including staff travel and subsistence cost and assessor training. DFID should work with the Secretariat to ensure that the external evaluation assesses the value for money of the programme.

Financial Management

DFID has no issues or recommendations regarding the quality of the TADAT Secretariat’s financial management. Detailed financial reports are received regularly and annual financial reports are received in June each year ahead of the Steering Committee meetings.

Risk

Overall risk rating: Minor/Moderate

The programme has been given this risk rating because although there are several risks rated moderate, the overall programme is an administrative undertaking, managed by a professional multi-lateral organisation and has the backing of the world’s more professionalised donor agencies. The most risky part is proving efficacy and VFM.

In April 2016, the way DFID classifies risk changed. Under the previous system, the following risks were identified and classified as per the table below:

Risks	2013 BC / Risk Assessment	2015 AR / Risk Assessment
Take-up of TADAT by developing country tax administrations is low.	Impact: High	Impact: High
	Likelihood: Medium	Likelihood: Low
Tax authorities in TADAT countries have insufficient capacity to implement necessary reforms.	Impact: Medium	Impact: Medium
	Likelihood: Medium	Likelihood: Medium
Difficulty recruiting technical experts to carry out TADAT assessments.	Impact: Medium	Impact: Medium
	Likelihood: Low	Likelihood: Medium
Pilots are not carried out in DFID priority countries.	Not identified as a risk at BC stage.	Impact: Medium
		Likelihood: Medium

Under the new risk management approach, this programme’s risks are set out according to the risk matrix below:

Risks	2016 AR / Risk Assessment	Comment
Tax authorities in TADAT countries have insufficient capacity to implement necessary reforms.	Impact: Major / Likelihood: Possible	Too early to assess. The Addis Tax Initiative commitment for donors to double support to tax capacity projects should help to mitigate the risk.
Too few assessments are carried out in DFID priority countries.	Impact: Major / Likelihood: Possible	Since launch, four of the twelve TADAT assessments have taken place in DFID countries (more during pilot phase) with two further planned for Aug/Sept. ‘Hit rate’ needs to be maintained to ensure TADAT delivers to DFID priorities. DFID should continue to push assessments in DFID countries and seek to fund and lead assessment missions over the next year.
Take-up of TADAT by developing country tax administrations is low.	Impact: Major / Likelihood: Unlikely	This risk has so far not been realised. The vast majority of TADAT assessments are in developing countries.
The TADAT Secretariat cannot recruit technical experts to carry out TADAT assessments.	Impact: Major / Likelihood: Unlikely	This risk has not so far been realised. If anything accreditation is oversubscribed. Focus should remain on ensuring quality of accredited assessors.

Of the three risks in orange above, the comments on mitigating action is as follows:

Commercial Considerations

After the roll out of TADAT was pushed back in 2015, the work programme is now delivering at pace and on track. Over the coming year the Secretariat will continue to assist donors in delivering assessments and grow outreach activities to promote the tool further and have a greater focus on quality assurance.

The relationship between DFID and the TADAT Secretariat continues to operate smoothly with DFID attending Steering Committee meetings and engaging regularly in any relevant day-to-day programme activity. We are in regular contact with the Secretariat and conducted an interview in preparation for this review. HMRC continues to engage via the Technical Advisory Group (TAG), though meetings are now less frequent. The UK now has three HMRC employees that are TADAT accredited that can be deployed for missions.

Monitoring and Evaluation

The DFID programme Log Frame should be updated to reflect the recommendations of this annual review and the future direction of the programme. The key changes are:
- Update all Log Frame milestones so they beyond 2016 to 2018 (end of programme)
- Merge indicators 1.1 and 1.2 so that they monitor the ongoing delivery of the programme workplan as monitored by TADAT’s Log Frame.
- Change indicator 2.2 so that it reflects whatever the outcome of review into how DFID programmes should engage with TADAT.

The new TADAT Log Frame will provide a good basis going forwards for which to monitor results delivered by the programme.

Capturing the more qualitative aspects of the programme (the impact TADAT assessment have on facilitating dialogue amongst donors and the tax authority and informing reform plans, for example) will be key to proving the efficacy of a diagnostic tool. There is some evidence emerging of whether results of assessments are feeding into reform programmes (outcome indicator 1) but we will be able to better assess this at the next annual review once the Secretariat has conducted its formal survey of this issue by December 2016. DFID should also raise these issues with country offices and TADAT assessors to gain further feedback.

DFID monitors progress in the programme through its membership of the TADAT Steering Committee, where it has been influential in shaping the programme. Prior to the annual review DFID also met with the TADAT Secretariat to reflect on what has been achieved over the annual review period.

TADAT’s external evaluation in 2017 and perception survey in 2018 will provide a rich source data for us to monitor the programme.

Gender assessment

We assess that the programme does not have a significant impact on gender outcomes. TADAT assesses the strengths and weaknesses of a tax administration for which there are no obvious gender impact. It does not assess tax policy making which would have a greater read across to gender issues.

The TADAT business case was approved before the introduction of the International Development (Gender Equality) Act 2014 meaning that no gender impact assessment has been done.