Project Completion Review - Summary Sheet

This Top Sheet captures the headlines on the programme performances over the course of its lifetime. Teams should attach summary sheets from each annual review over the life of the programme.

Review Date:	16-22 March 2016

Title: Facility for Oil Sector Transparency (FOSTER) in Nigeria
Programme Code:	Start Date January 2011	End Date: June 2016

Summary of Programme Performance

Outcome Score: A+
Output Score: A+

Year	2011	2012	2013	2014	2015
Programme Score	A+	A	A+	A	A+
Risk Rating	Medium	Medium	Medium	Medium	Medium

Financial Position

Original Programme Value	22/12/2010: £8,926,590
Extensions/ amendments	1/01/2011 – Amendment / 15/09/2011 – Amendment / 16/07/2013 – Extension to £9,126,590 / 03/12/2013 – Extension to £13,389,885 / 14/11/2014 – Amendment / 18/11/2015 – 3 no cost date extensions (end Dec 2015 to end April 2016); a further one to end May 2016; and a final one to end June 2016.
Log-frame revisions (with dates)	2012: The logframe was redesigned and the following changes were adopted: / Impact: More effective use of Nigeria’s natural resources / Outcome: Enhanced management of Nigeria’s natural resources / Output areas: / 1. Increase in extractive industries revenues identified; / 2. Improved management and accountability of extractive industry revenues; / 3. Improved policy outcomes for local communities affected by natural resource extraction. / 2013: Language used to describe output indicator 1.1 was changed to include ‘advocacy initiatives’ / 2014: Language used to describe output indicators 1.1, 2.1, and 3.1 was changed to reflect results achieved from work with demand-side actors (as well as supply side actors) / The assumptions column of the logframe was reviewed and expanded to capture more fully the assumptions made in the programme and changes in the operating context / 2015: Logframe targets were adjusted to increase the revenue target by £100m since the previous programme target of £300m had already been achieved; to incorporate cumulative programme end targets and to accommodate shift in the programme end date – from December 2015 to April 2016.
Total programme spend	£11,769,998 by end February 2016

Follow up actions required following closure

- Lesson Learning Workshop between FOSTER and Successor programme;
- Handover between programme teams.
- Finalise audit from March 2016 and any follow-up steps.
- Work with FOSTER 2 on new risk matrix as part of inception period.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/4570094.odt
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/4569728.xls

Outline of the Programme

The Facility for Oil Sector Transparency and Reform (FOSTER) was a flexible five year technical assistance programme designed in 2010 as a new approach to increase transparency and accountability within Nigeria’s opaque oil and gas sector. Its overall intended impact was for ‘More effective use of Nigeria's Natural Resources’ and its intended outcome was ‘Enhanced management of Nigeria's natural resources’. It pursued this through three outputs:

1. Increase in extractive industries revenue identified
2. Improved management and accountability of extractive industry revenues
3. Improved policy outcome for local communities affected by natural resource extraction.
The programme value was initially £10 million over five years (2011 to 2016) but on the back of a business case made in 2013, due to ramped up activities in 2012, the budget was increased to £14 million. No-cost time extensions were also granted to take the programme conclusion up to June 2016 to ensure a smooth transition with its successor programme.

Context

The governance of Nigeria’s oil and gas sector is transforming in a way that was not plausibly conceivable at the start of the FOSTER programme in early 2011. For most of the time span the programme operated in one of the most politically challenging reform environments possible, with a largely unaccountable, closed-door national oil company, industry policy and regulation that was distorted or neglected by rent-seeking motivations and poor management, and a global backdrop of bumper oil prices which were mostly in excess of $100 per barrel, providing no financial imperative for Nigeria to reform. Through-out this period the FOSTER team served as a catalyst for those within Nigeria that were willing to challenge bad practices and demand reform. FOSTER’s approach was politically savvy and opportunistic providing technical support, research and evidence to those dissenting voices in government or groups outside of government that were willing to champion the cause of reform.

The last year of the programme saw a radical change in this programme context. With the election of President Buhari on an anti-corruption platform and the crash of global oil prices, the mainstream oil and gas institutions in Nigeria went from being the main blockers of reform to being a willing partner on transparency and accountability. The appointment of Minister of State for Petroleum Kachikwu with his 20 fixes strategy that included “stop the bleeding[1]” and “shine the light[2]” provided a credible basis under which to provide support to this central oil and gas institution. FOSTER had to adapt and shift its focus away from being mostly about facilitating challenge of these institutions to that of rapidly providing technical assistance to keep up with a reform agenda.
[1] Referring to lost oil revenues
[2] Greater transparency

At the time of programme design in 2010, previous approaches toward the same end had largely been contained to providing technical assistance to help set-up the Nigerian Extractive Industries Transparency Initiative (NEITI), a Nigerian government institution set-up to locally drive the international principles and industry audits envisaged under the global Extractive Industries Transparency Initiative (EITI). There had been some success through this approach with audits carried out and made public, identifying large revenue losses to government, and it was a helpful additional ‘check and balance’ on the industry, but little had changed within Nigeria as to how the industry was fundamentally governed, and many argued that corruption within the industry in Nigeria was actually increasing.

There was a growing sense that initiatives like EITI whilst helpful to improve transparency would never be sufficient in themselves to over-turn the deep-rooted political dynamics which drove the poor governance of extractive industries in countries like Nigeria[3]. FOSTER was designed with that in mind and was given the mandate to focus more on the political constraints to reform of the oil and gas sector, and to operate in flexible and politically astute ways to try and catalyse reform. The programme commenced in early 2011 with its inception phase and started its full implementation in the middle of 2011. Given the vested interests within this sector, early project expectations of success were modest and whilst outputs were designed within the control of the programme there was a chasm between the outputs of what the programme would deliver on a yearly basis (e.g. evidence reports, disseminations etc) and the high level outcome of improved transparency and accountability that was intended. In 2012 the logframe was restructured to address this, by raising programme outputs to a much higher level to create a stronger link with the programme outcome. Whilst the achievements of the outputs were no longer as much in control of the programme team, it did mean the programme was being annually assessed against measures that had hope of helping the programme achieve its overall outcome- as difficult as it may have been. It also led to the introduction of a local communities output, which gave the programme licence to pursue policy reforms that would have better outcomes on the people of the oil producing region of the Niger Delta.
[3] See IDC hearing on EITI 2010

Table 1: Key Results targeted under the original design and the major changes made in 2012.

	Original Design (2010)	Major Revision (2012)
Impact	Improved governance of Nigeria’s oil sector	More effective use of Nigeria's Natural Resources
Outcome	Improved transparency and accountability in oil sector governance	Enhanced management of Nigeria's natural resources
Output 1	Generation of technical analysis of key oil sector governance issues / Weight: 30%	Increase in extractive industries revenue identified / Weight: 40%
Output 2	Communication of NEITI audits and other key information about oil sector governance / Weight: 30%	Improved management and accountability of extractive industry revenues / Weight: 40%
Output 3	More effective institutions involved in oil sector transparency and accountability functions / Weight:40%	Improved policy outcome for local communities affected by natural resource extraction. / Weight: 20%

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Outcome assessment

Over the course of the programme the direction of travel in how Nigeria’s oil and gas resources are managed has been turned around. The Nigerian National Petroleum Corporation (NNPC), has begun a journey of greater openness, efficiency and corporatisation, as articulated in its “20 fixes” plan in 2015. It has made industry data more transparent through its monthly reports and in January 2016 produced its first public accounts for over 10 years. It cancelled a number of doubtful oil for refined product swap contracts which were identified as high risk for revenue loss and embarked on a more open process for replacing these.

DFID’s FOSTER programme was not responsible for this transformation. The pressure grew from the period of several years leading up to Nigeria’s 2015 elections where a lack of accountability for a series of government scandals in the oil and gas sector[4] and beyond[5] led to such a high degree of public dissatisfaction that enabled APC’s Presidential Candidate, General Buhari to captivate appetite in a “change” agenda. Most visually striking was the campaign symbol of a local Nigerian broom. Tackling corruption and by implication cleaning up the oil and gas sector was top of the new list of reforms.
[4] See FT article on Missing $20 billion
[5] For example see open source reporting on global concern at government handling of Chibok Girls (2014), Nigerian Immigration Recruitment scandal (2014), and general insecurity in the North East

Yet, this change in industry governance was by no means inevitable. FOSTER did play a catalytic role that helped amplify pressure, expose weak systems and revenue losses and provide a platform to empower those seeking this positive change.

The overall outcome of the programme is ‘Enhanced management of Nigeria’s natural resources’. Two outcome indicators were set for FOSTER: the value of additional revenues realised from Nigeria's natural resources; and the proportion of natural resource revenues regularly accounted for. Both of these outcome indicators have been achieved. The cumulative revenue target for the programme was achieved more than a year before the end of the programme and so it was agreed in year 4 to raise the target by a further £100 million. This revised target has also been met.

Outcome Indicator 1: ‘Value of additional revenue realised’ (contributed by results from FOSTER programme)
- Target by end March 2016: £400m contribution by the FOSTER programme.
- Original target £300m. Revised target of £400m set by the 2014 AR after the initial target had been exceeded four years into the project cycle.
- Final Achievement: Over £403m (see breakdown in table below)

Issue	Overall result	FOSTER / Action	FOSTER Contribution	Counterfactual
Oil revenue losses from Crude SWAPS	$1.5 billion saved due to changes in SWAP deals	Built an evidence base over the five years of the programme identifying swap contracts as a major revenue leakage and made recommendations to address this. Targeted key individuals within the PMB administration early-on to push for reform on this area. NRGI report[6], launched the day Petroleum Minister appointed, captured years of ongoing work and advocacy from FOSTER programme.	5% (£52.5 million contribution)	Problems would be there and understood by some in the industry but perhaps not flagged so systematically. Link with Sanusi allegations. Unclear how quickly these issues would have been dealt with.
National Executive Council (NEC) Audits of Revenue Agencies	Reduction in audit company fees by £5.3 million	FOSTER provided technical assistance to help construct the terms of reference for these audits and identify cost savings for government from the bids.	High- 75% / £ 3.975 million	TORs would likely have been less well defined, Value for Money considerations may not have been as a high a consideration in absence of FOSTER involvement.
Existing Revenues / claimed under previous annual reviews	Contribution to removing fraudulent fuel subsidy claims, recovery of revenues following NEITI audits etc	See previous annual reviews.	£346 million	See previous annual reviews.
Total			£403 million
[6] NRGI Report ‘Inside NNPC oil sales’ report 2014

The revenues in the table above are those that the FOSTER programme made a contribution towards the Nigerian Government either recovering or preventing from being lost. There was more than £2.2 billion more revenue losses identified by the programme (see output 1 below) most of which had not yet been either stopped or recovered at the time of the programme PCR.

Outcome indicator 2: ‘Proportion of natural resource revenues regularly accounted for’

- Target by end 2015: ‘Improved price and volume information for oil, gas and mining revenues made public by the Federal Accounts Allocation Committee’.
- Final Achievement: This target too has been exceeded with systemic changes in three important governance and management structures for the sector. FOSTER interventions have improved (a) NNPC’s process of reporting oil and gas activities (b) RMAFCs template for reporting and publication of oil production figures (c) revenue collection agencies’ adoption of new reporting systems.

Qualitative Outcome achievements of FOSTER

Beyond the outcome indicators above there were three key qualitative areas where the FOSTER programme made a positive impact.

Raised the state of knowledge and calibre of public debate on oil and gas policy: FOSTER’s work with a wide range of civil society and media actors has significantly raised the level of understanding about how the oil sector works and the policies and practices that give rise to corruption and inefficiency. This work has included the creation of online platforms that provide a mechanism for holding government accountable (e.g. the gas flare tracker), as well as deepening the understanding and capability of the media to report on oil sector issues through training investigative journalists.

Significant agreement about what the legal framework for the sector should be: Although FOSTER’s support for the Petroleum Industry Bill did not lead to the passage of the bill in both the House and the Senate, the programmes’ work with legislators and all the actors associated with the legislative process have led to a wide understanding among key stakeholders of the key principles that should underpin legislation in the sector. These ideas and the associated legal text are forming the basis for renewed attempts to craft framing legislation for the sector under the current administration.

Institutionalisation of transparency and accountability: Through FOSTER’s long-term support, NEITI has developed to become an effective institution for the promotion of transparency and acountibility in the sector (and is widely regarded as one of the best country EITI institutions globally). FOSTER has helped to build the capacity of NOSDRA to tackle oil spills and improve the Joint Investigative Visit process. And FOSTER’s recent support for NNPC has facilitated a sea-change in NNPC’s approach to transparency and accountability, supporting NNPC to publish their Annual Report for the first time in over a decade, strengthening their capability to reform refineries and tackle fuel subsidies.

Outcome Score:

On the basis of the revised logframe in 2015 this annual review assesses that the programme met its overall outcome target and should score an ‘A’. However, this score underplays the success given the overall (much more modest) initial expectations of this programme and how FOSTER programming has contributed to a much more significant change in the sector than could have reasonably been expected in 2011. If compared with original expectations, and along with the qualitative achievements set out above this programme should score at least an A+ in terms of outcomes exceeding initial expectations. This review concludes that an A+ is an appropriate outcome level score.

Observations on impact-level achievement:

Whilst the PCR is not required to comment on ‘impact’ targets the review offers a chance to assess progress towards longer-term impact level goals. This is of particular interest in a context where the project’s performance has been seen to be critically dependent on political economy conditions, and where this context has altered significantly and Outcome level targets have been surpassed.

IMPACT	Indicator	Target (March End 2016)	Achieved
More effective use of Nigeria’s natural resources	Indicator 1: Nigeria’s Natural Resources Charter Score (NNRC)	Improvements in 4 Precepts over project life cycle	Improvements in 2 precepts as at 2014
	Indicator 2: Nigeria’s score on the Natural Resource Governance Institute (NRGI) Resource Governance Index (RGI)– Biannual survey	50/100	Score of 42/100 as at 2014

Unfortunately, the project will come to an end before data will be available from the sources specified (the NNRC Charter assessment, and the NRGI Index) to assess progress towards the impact level targets. Both these surveys are likely to be undertaken in 2016. However, given the considerable reform progress made in 2015 it is the view of this Project Completion Review that the programme is highly likely to have hit its impact indicators.

Overall output score and description

Over the years the programme has either met output targets or moderately exceeded them.

Year	2011	2012	2013	2014	2015
Programme Score	A+	A	A+	A	A+
Risk Rating	Medium	Medium	Medium	Medium	Major

The quick response of the FOSTER programme, and the high quality work delivered by the programme in areas such as revisions made to Nigeria’s fuel pricing template, monthly data reports, strong calibre of the technical team mobilised to provide technical audits of Nigeria’s domestic refinery capacity etc in its final year warrant a score that reflects achievement above logframe expectations. This review considers the output score in 2015 to have been A+.

The overall output score for the programme over the five years of activities is A+

Key lessons

- Housing demand-side pressure and supply side technical assistance for reform under one programme is challenging – but if managed well can be transformational. Important that DFID and the programme remain conscious of both the risks and opportunities of this model and makes sure the programmes has the systems in place to manage and mitigate the risks appropriately (e.g. strong information management, Chinese walls where necessary etc) and all staff, whether permanent or short term, model the behaviours required to make this type of sensitive programming a success.
- Shifting to a logframe that better reflects theory of change (but maintaining the high ambition). Whilst the FOSTER 1 logframe outputs were raised to be higher level and more ambitious in 2012 bridging the gulf between the outputs and outcome of the programme, there was a partial disconnect in the logframe on the demand side of the programme’s theory of change. This was addressed partially in logframe amendments following the 2013 and 2014 annual reviews- but making the outputs explicitly focused on the programme’s theory of change, with outputs on creating widespread understanding of oil and gas sector issues, providing strengthened capability to those committed to reform, and empowering those demanding reform, presents an opportunity to keep FOSTER 2 focused on the ingredients of the FOSTER 1 approach that were so successful.
- Explore a wide range of opportunities but have a shared game-plan and vision on what specific clusters of interventions are ultimately about and pre-identify the conditions under which FOSTER 2 would discontinue support[7]. This will be important to avoid programmatic drift need to avoid being mechanistically applied and will need to be updated as the situation changes or new information is brought in.
  [7] This needs to be shared between DFID and the FOSTER 2 team.

Key actions

Increase the overall risk rating for FOSTER 2. In 2016 DFID adjusted its approach to risk management, more explicitly defining its risk appetite in specific areas and a new risk matrix has been created for FOSTER and for FOSTER 2. Given the increased challenges for FOSTER 2 working more directly with central oil and gas institutions whilst simultaneously working with demand side actors and creating widespread understanding of often sensitive oil and gas sector issues, the risk level should be increased from moderate to major going forward.

Ensure that recommendations from this review are taken forward into FOSTER 2.

Has the logframe been updated since the last review?

Yes, logframe targets were adjusted to increase the revenue target by £100m since the previous programme target of £300m had already been achieved; to incorporate cumulative programme end targets and to accommodate shift in the programme end date – from December 2015 to April 2016
## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Increase in extractive industries revenues identified / Expenditure / £2,924,773 on Output 1 (43%)
Output number per LF		1	Output Score	A+
Risk:		Moderate	Impact weighting (%):	40%
Risk revised since last AR?		Y/N / N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Indicator 1.1: Research, analysis, reports transparency and advocacy initiatives that lead to sector reform recommendations and adoption by demand and supply side actors. / Expenditure / £1,699,890 on Output 1.1	6 sector reform recommendations aimed at increasing revenues proposed by supply or demand side actors / 3 sector reform recommendation adopted / Total revenue identified increased by £400m as a result of new sector reform recommendations supported by FOSTER	Achieved (2015) / Review on NNPC crude sales and FOSTER influencing of new government helped lead to reform of swap arrangements. / Support to Nigerian Export Supervision Scheme produced recommendations on how to improve the scheme. Govt. adopts key recommendations. / Support to National Executive Council leading to revenue audits being commissioned. / + those covered in past annual reviews. / Total revenue risks identified of over £2.2 billion as a result of new sector reform recommendations supported by FOSTER.
Indicator 1.2: Capacity building interventions in supply side revenue management agencies and supply and demand side accountability organisations / Expenditure / £621,468 on Output 1.2	6 capacity building initiatives targeted at improved supply and demand side revenue management agencies and accountability organisations	Achieved (2015) / Training of civil society organisations on state-level advocacy for accountability based on NEITI Fiscal Allocations and Statutory Disbursement Audit. / Training of journalists on Excess Crude Account flows / + those covered in past annual reviews.
Indicator 1.3: Systems and processes improved in supply side revenue management agencies and supply and demand side accountability organisations / Expenditure / £603,415 on Output 1.3	6 systems strengthening initiatives targeted at improved revenue management agencies and supporting transparency recommended	Achieved (2015) / Supported NNPC to improve its monthly public reporting / Revenue template for RMAFC / + those covered in past annual reviews.

Key Points and highlights:

- FOSTER had already been moderately exceeding expectations in this output at the time of the 2014 Annual Review. Since then the programme has had a strong period of achievement under this output.
- Notable achievements in 2015 include:
1. ‘Inside NNPC Oil Sales’ report by the Natural Resource Governance Institute (NRGI). Highlighted areas to be strengthened in how the national oil company sells Nigeria’s oil. This reflected extensive research and evidence that the FOSTER team and its programme partner NRGI had built up since the launch of the programme in 2011.
  1. It highlighted arrangements where NNPC would swap crude oil for refined product under an opaque process and through terms viewed by the report to be potentially unfavourable for Nigeria. It contained a series of recommendations on how to overhaul this system.
  2. FOSTER followed-up with targeted advocacy with influential individuals within the new government. The report launch was also well timed, coinciding with the day the new Head of the National Oil Company was appointed (who later became the Minister of State for Petroleum). This was further complemented by UK Government influencing with the British High Commissioner presenting a copy of the report to him in their first meeting.
- Since then NNPC has cancelled a number of the swap contracts, adapted its approach and ran a more transparent process for selecting new companies to provide Nigeria with petroleum products.
- FOSTER was able to continue engagement with NNPC on this issue under output two to help NNPC push through this reform.

The total savings to Nigeria for adopting these reforms are estimated to be £988 million.
Whilst recognising that the political willingness of the Nigerian Government was key to this change and NNPC has driven this reform forward, on the basis of FOSTER’s raising the issues, highlighting ways to address it, and significant engagement with NNPC and key political players to help them address it – this review assess that FOSTER did play an important role in this change. In terms of attribution to FOSTER, it is this review’s judgement that FOSTER can claim a conservative 5% contribution against the total revenues Nigeria protected in this reform. Therefore, £52.5 million can be legitimately scored against the overall outcome revenue target.

Support to Presidential Committee reviewing the Nigerian Export Supervision Scheme (NESS). The NESS is a levy imposed on all exports, monitored and implemented through a number of private companies contracted on behalf of the Nigerian Government and expected to remit back into government coffers. For Nigeria over 90% of this is oil exports. After 2015 elections, the new Government identified that the scheme had poor oversight and the private companies contracted to monitor were inconsistent in remitting their levies, leading to large revenue losses for the government. A Presidential Committee was established to look into the deficiencies of the Nigerian Export Supervision Scheme (NESS):
FOSTER quickly made contact with committee members sharing FOSTER’s study on the issue carried out in 2012. The committee members, keen for support, invited FOSTER to present their study to the group.
- FOSTER was able to provide short-term embedded support to work with the committee and facilitate an audit of this scheme which identified £158 million that was being lost.
- The findings of the audit led to the Nigerian government cancelling the scheme and the government is now working to establish a new mechanism.

Until a new scheme is put in place it is difficult to know how much Nigeria will have saved but if Nigeria can establish a robust, transparent structure then FOSTER will have played a key role in this reform.

1. National Executive Council (NEC) Audits of Revenue Institutions. Here FOSTER engaged with the National Executive Council – a body chaired by the Vice President and comprising of State Governors and key Ministers of the Federal Government to identify potential losses to the Excess Crude Account (ECA). The purpose was to draw attention to the loose administrative structure surrounding the ECA. This was a challenging area as there was limited public information to help quantify what losses there could have been.
  1. On the advocacy side, FOSTER supported the production of an analytical report by a local journalist whom, given the lack of data available, used ‘back of the envelope calculations’ to try and quantify losses. His newspaper made the decision to run with the analysis and carried the story based on the figure the report had identified. Whilst the numbers in his report were too high to be credible, it raised attention to the issue and the lack of public data and led to many more public questions.
  2. On the supply side, FOSTER’s initial engagement with NEC quickly led to direct technical assistance, and influential members of NEC enabled access to more detailed figures from government. From this information and the technical assistance provided to the NEC committee it was able to estimate over £50 million in unaccounted revenues. Audits have now been commissioned with key revenue agencies to help NEC fully account for missing revenues.

One procedural fall-out from the work with NEC was how the FOSTER team used evidence, particularly where it was at the more speculative end of the evidence spectrum. The initial report by the journalist produced some sensational figures. Whilst the journalist’s institution was happy to run with these, they were not robust enough to use as formal analysis to present to NEC. This issue reinforces the complexity in working with both demand and supply side actors. It was agreed by both DFID and the service provider to strengthen quality assurance procedures for reporting and have a clear approach on how different grades of evidence should be applied by the FOSTER team.

NNPC Monthly Reporting.

As part of its ‘20 fixes’ strategy NNPC launched a series of monthly reports from August 2015. On the request of NNPC, FOSTER provided advice following the first report, feeding back views from a range of external stakeholders on what information was relevant and how best to present it. Most of FOSTER’s recommendations to NNPC were adopted and changes reflected in the October report. FOSTER then helped NNPC communicate these reports, organising over a hundred demand-side actors mainly from the media and civil-society who had an interest in extractive industries governance.

This was a significant result as it helped FOSTER achieve its outcome target to improve price and volume of extractive revenues publicly provided.

Summary of responses to issues raised in previous annual reviews (where relevant)

Key recommendations on this output from the last annual review included:

- Balancing the need for maintaining flexible and responsive approach to seize emerging opportunities, but also ensuring some degree of continuity of support with partners like NEITI for their planning purposes. This remains a challenge but good evidence that FOSTER have been able to keep seizing opportunities. Finding ways to balance this with longer-term partnerships with Nigerian institutions will be increasingly important as FOSTER 2 expands its work with key institutions.
- FOSTER’s coordination with NRGI in relation to NEITI –FOSTER and NRGI shared workplans in early 2015 to consider appropriate division of labour.
- Theory of change and evidence base around demand side work – This has continued to be a challenge although lesson learning studies commissioned by FOSTER in 2015 looked specifically at FOSTER’s demand side work as part of its case studies. Issues about under-representation of demand side in logframe under FOSTER 1 is addressed in FOSTER 2’s new results framework.

Recommendations

FOSTER 1 has produced a number of seminal evidence papers on the challenges within Nigeria’s oil and gas industry and has helped surface critical issues and brought new perspectives into the public debate. This has been a success of the programme with high profile reports such as the Chatham House ‘Criminal Crude Report’, Stakeholder Democracy Network’s ‘Communities not criminals’ and NRGI’s ‘Inside NNPC oil Sales’. These have influenced the public discourse both locally and internationally and have provided important platforms for FOSTER’s technical assistance to build on.

FOSTER 2 should build on this success through its new output, dedicated to creating widespread understanding of key industry issues and during its inception period identify ideas for key evidence papers that might further help reveal major industry reform issues or bring in neglected perspectives into the policy debate.

The calibre of the FOSTER team and the experts used and the political traction that they have been able to achieve has been critical to the effectiveness of FOSTER’s work. Mostly the work and analysis produced have been high quality, however, it is worth reinforcing the complexity of Nigeria’s oil and gas industry work, and there were a few instances where the quality has not been robust enough – particularly when, on the demand side, groups have been challenging the government position.

FOSTER 2 will need to consistently apply quality assurance mechanisms for reports which nuances the approach to take with advocacy pieces supported by FOSTER but ultimately owned by other organisations, and those that are produced by FOSTER and provided to government. Not all reports will be expected to be at the same standard, but the FOSTER team will need the capacity to grade evidence quality and know how best to use it.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Improved management and accountability of extractive industry revenues / Expenditure / £2,424,710 on Output 2 (36%)
Output number per LF		2	Output Score	A/ A+
Risk:		Moderate	Impact weighting (%):	40%
Risk revised since last AR?		Y/N / N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Indicator 2.1: Research, analysis, reports transparency and advocacy initiatives that lead to sector reform recommendations and adoption by demand and supply side actors / Expenditure / £1,475,638 on Output 2.1	6 sector reform recommendations strengthened that improve management and support accountability in the extractive industry and 3 recommendations adopted	Achieved (2015) / Petroleum Industries Bill- final push. / Petroleum Industries Bill – new thinking. Feasible strategy for splitting the Bill along lines of governance, fiscals and industry restructuring + draw on existing PIB analysis. / NEITI recommendations, a policy paper summarising the key points of NEITI 2012 audit presented by EITI and FOSTER to the Vice President / + those covered in past annual reviews.
Indicator 2.2: Capacity building interventions in supply side resource management agencies and supply and demand side accountability agencies / Expenditure / £606,075 on Output 2.2	6 capacity building initiatives targeted at improved supply side industry restructuring agencies or supply and demand side accountability organisations	Achieved (2015) / Capacity building & Advocacy training with Civil Society Groups on oil and gas reform and influencing political parties in run-up to election. / Media trainings on crude sales reform. / + those covered in past annual reviews.
Indicator 2.3: Systems and processes improved in supply side resource management agencies and supply and demand side accountability agencies / Expenditure / £342,997 on Output 2.3	5 systems strengthened in supply side resource management agencies and supply and demand side accountability agencies	Achieved (2015) / Repositioning of NEITI for EITI validation. Support to NEITI to establish companies forum which held its inaugural meeting in Lagos and commitment from companies to participate going forward. / + those covered in past annual reviews.

Key Points

- FOSTER was designed with the potential to partner with government agencies championing reforms, as well as support groups and individuals outside of government to increase pressure for reform. As such, FOSTER has been seen as a programme working on both the demand and supply sides of reform. Yet throughout four of the five years of FOSTER’s programming, there were limited opportunities for partnerships to reform with the most relevant organisations. FOSTER has essentially been a ‘behind the scenes’ advocacy programme that could deploy technical assistance and partnered with parts of government where it could strengthen challenge to the core petroleum institutions.
- Areas where FOSTER was working with parts of Government (e.g. Ministry of Finance, Revenue Mobilisation Allocation and Fiscal Commission (RMAFC), National Oil Spill Detection and Response Agency (NOSDRA) etc) this was mostly targeted to strengthen their capacity to scrutinise or respond to areas that were being driven by central oil and gas institutions.
- The exception of where FOSTER tried to engage with a core institution was with the industry regulator. Despite a credible appointment of Director General and early positive signals from him of willingness to reform, one of the key objectives of using the support to get transparency into the licensing process for marginal fields was not achieved, and organisational support in the absence of a clear mandate for reform was discontinued at the end of 2012.
- Genuine partnerships with key oil and gas institutions developed in the final year of the programme and FOSTER technical assistance has been highly regarded. Interviews with officials from NNPC and the Ministry of Petroleum confirmed this. However, early engagement has already begun to surface risks between FOSTER’s work to bring out other voices to keep pressure for reform, and to be able to sustainably partner with these core-institutions. There have also been good examples of opportunities to bring these two sides together to collaborate on solutions (e.g. monthly revenue reports).
- Petroleum Industries Bill (PIB) is an area where FOSTER invested significant resources in building the pressure for, and the quality of, game-changing legislation. This was also accompanied with complementary UK government influencing at a variety of levels, much of which was informed by the early analysis the FOSTER programme carried out. Whilst the bill did not get signed into law before the end of the last parliamentary term, the programme did achieve significant agreement across a number of groups about what this legal framework should be. Renewed interest and commitment from both the National Assembly and the Minister of State for Petroleum in 2016 suggested that oil and gas legislation will almost certainly pass before the end of this parliamentary period and the work that FOSTER has done will help make this a stronger bill. This example does speak to the core risk taking approach of FOSTER, which means that not every intervention is expected to yield direct results in the lifespan of the programme, and some interventions have such high potential return for sector governance that they are worth pursuing even when no guarantee of immediate success.
- Nigeria Natural Resource Charter Group (NNRC). FOSTER’s role in establishing this group of industry experts to play a challenge function was highly valuable and the scoring of Nigeria’s extractive industry governance provided an objective basis for monitoring progress and targeting advocacy. Momentum unfortunately slipped in the final two years of the programme, particularly when the facilitation function was passed away from the core FOSTER team to NRGI to directly support. Enthusiasm and commitment by the eminent and respected panel members has unfortunately been under-tapped.
- Nigeria Extractive Industries Initiative (NEITI). FOSTER’s support to NEITI was highly valued by both the former Executive Secretary and the former Chairman of the Board. FOSTER’s engagement with NEITI over the past five years has helped to strengthen its communication of audit findings and also facilitated the recovery of funds identified as having been lost (see AR 2014).
- Post Nigeria’s elections in 2015, opportunities for partnership under this output was substantially increased. FOSTER had been moderately under-achieving in this output at the time of the last annual review in 2014. However, this been turned around and the FOSTER team seized the opportunities that were presented.

Summary of responses to issues raised in previous annual reviews (where relevant)

The 2014 Annual Review recommended that more could be done to capitalise on the experience and expertise on the NNRC Expert Panel members. This was not addressed directly with FOSTER as responsibilities were passed onto NRGI. Feedback from panel members interviewed indicated that there had not been any further meetings of the NNRC convened. FOSTER should plan for possibility that neither PIB and NOSDRA bill is passed before end of parliamentary term. Whilst a final push was made on the PIB this was done fully recognising the risk that it may not pass beyond the parliamentary term. Strengthening theory of change on demand side work. This will be refined under FOSTER 2 inception period.

Recommendations

- FOSTER 2 will need a ‘game plan’ to manage the trade-offs of where to target technical assistance and prioritise scarce resources against substantial need. Important for upfront political economy analysis on major institutions and a common game plan that is held by both DFID and the FOSTER team for what success looks like and clear conditions when support might be phased out.
- Whilst there is strong political will for reform of the oil and gas sector, FOSTER 2 should not be complacent that this will remain or be sufficient through-out the programme life-span. FOSTER should keep demand side support going to help continue momentum for reform. Identifying where this would add the most value, and where bringing those demanding reform together with those with the potential to supply it will be important.
- Working with reformers and those demanding reform can be a difficult balance with risks that both sides can be unhappy and broader risks for UK Government reputation if handled badly. FOSTER 2 will need to have a clear approach which is understood across the whole team and agreed with DFID.
- Identify scale of both primary and secondary benefits for particular intervention clusters. Where calculated risks are taken (e.g. PIB), consideration should be given to both the magnitude of the direct benefits (should the intervention succeed) but also to identify secondary benefits if the primary objectives are not met. Consideration should be given as to whether these are sufficient to warrant the investment risk when viewed across the whole portfolio of interventions. Join up between the programme and DFID will be important in making these decisions.
- Low hanging fruit: FOSTER 2 should step in to resuscitate the Nigerian Natural Resource Charter Group and use it to revitalise discussions and debate on the future of oil industry governance.
- FOSTER 2 should develop clear but proportionate theories of change for its work across high level clusters of work. Where the clusters or work are sizable, the programme should consider targeted political economy analysis.
- FOSTER 2 should help NEITI to take its advocacy and challenge within government to a new level. This will be critical to the relevance of the institution if NNPC sustain their commitment to be more transparent in its operations. FOSTER 2 should help strengthen NEITI to champion the new areas under EITI + principles such as the recommendations on beneficial ownership as agreed between President Buhari and Prime Minister David Cameron during the May Anti-Corruption Summit in London.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Improved policy outcome for local communities affected by natural resource extraction / Expenditure / £1,438,178 on Output 3 (21%)
Output number per LF		3	Output Score	A
Risk:		Moderate	Impact weighting (%):	20%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Indicator 3.1: Research, analysis, reports transparency and advocacy initiatives that lead to sector reform recommendations and adoption by demand and supply side actors / Expenditure / £606,040 on Output 3.1	6 sector reform recommendations supporting and / 3 recommendations adopted	Achieved (2015): / Transition strategy for amnesty programme. (adopted) / Decommissioning of oil and gas installations. (in process) / + those covered in past annual reviews.
Indicator 3.2: Capacity building interventions for supply and demand side actors that have a role in improving outcomes for local communities / Expenditure / £136,420 on Output 3.2	3 capacity building initiatives targeted at improved outcomes for local communities	Achieved (2015): / Capacity building with demand side actors on gas flaring issues / Local communities equipped to act as watchdogs to implementation of oil spills clean up in Delta. / + those covered in past annual reviews.
Indicator 3.3: Systems and processes improved in supply and demand side organisations that have a role in improving outcomes for local communities / Expenditure / £695,718 on Output 3.3	3 systems strengthened supporting improved outcomes for communities affected by NR extraction	Achieved: / This milestone had been achieved as at the 2014 annual review. No additional ones have been strengthened since with focus on strengthening the demand side activities.

Key Points

- Peace and stability in the Niger Delta region have become major issues for President Buhari’s administration. The recent return of systematic attacks and sabotage on oil and gas infrastructure (first half of 2016) have led to oil production falling by more than a third and disruption to gas supply creating a significant drop in power generation: average utilised capacity has fallen from 4000 MW to less than 2600MW. (The Government says that 6000MW is the minimum needed).
- Nigeria’s commitment to implement the findings of the UNEP report on oil spills in the Ogoniland has strengthened in 2016, with the Minister of Environment and Vice President launching the clean-up effort.
- Final year activities rightly focused on helping Nigeria develop a transition strategy for the amnesty programme, including the recommendation to extend the Presidential Amnesty Programme for an additional six months which was agreed. FOSTER played an important role in mobilising different groups and key political leaders to highlight issues that need to be considered for long term stability in the Delta (including economic, community and political dimensions). Whilst FOSTER has done good work in this area and collaborated successfully with other DFID programmes, the scale of the challenge is substantial.
- Major achievements under this output through-out the life of the programme include the innovative platforms created by Stakeholder Democracy Network (SDN) and hosted within Nigeria’s environmental regulator (NOSDRA), that track and monitor oil spills and gas flaring with the aim of improving the responsiveness of the Nigerian government to these issues.

Summary of responses to issues raised in previous annual reviews (where relevant)

Clear strategies to ensure revenues identified from unpaid flaring fines are realised and invested in initiatives that build resilience among communities affected by gas flaring. This should continue to be pursued under FOSTER 2 and approaches developed under the inception period. Do more to draw out the links between programme’s activities and tangible improvements in the lives of poor communities affected by natural resource extraction in Nigeria. This also needs to be strengthened.

Recommendations

- Given the major challenges on the Niger Delta- important to consider as part of FOSTER 2 inception phase how deeply involved FOSTER 2 should become and division of labour with DFID’s Niger –Delta stability programmes.
- As FOSTER 2 continues to work more closely with central policy on extractives the programme will need to have clear procedures to assess conflict sensitivity of potential policy recommendations to make sure at a minimum they ‘do no harm’.
- Renewed appetite on oil spills clean-up and tackling gas flaring give FOSTER 2 the opportunity to help Nigeria take significant steps forward on the environmental agenda, help some of these issues be addressed.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

The major cost element for FOSTER is the cost of technical experts and partners (mostly Nigerian rather than international consultants) to implement the numerous interventions. The resources for this area were drawn from the Managed Fund which has represented around 57.5% of the cost of the programme. The second major element of cost is the cost of programme management. One of the reasons for the strong performance of the project has been the use of knowledgeable, connected and politically savvy local team. The cost of the contractors management services (Oxford Policy Management) as well as the cost of the local Nigerian team implementing the project on the ground, has constituted around a third of overall cost (although most of this has been on substantive programming work rather than management and administration). Eight percent of the programme cost has constituted expenses. The main elements of these expenses have been accommodation (for Team Leader/Programme Manager), office costs (including vehicles, security, furniture, and rent, running costs, meeting and stationary costs, communication and cleaners), and flights (both international and domestic).

The table below provides a financial summary of the project accurate as of February 28th 2016.
OVERALL PROJECT	Contract Value	Expenditure TD	Balance
Total Fees	£4,160,955	£3,853,975	£306,980
Total Expenses	£1,172,344	£1,146,978	£25,366
Managed Fund	£8,056,586	£6,769,045	£1,287,541
Total	£13,389,885	£11,769,998	£1,619,887

The FOSTER team have also done well tracking expenditure for specific outputs and key intervention areas based on expenditure from the managed fund. The table below shows the situation as at February 2016:
Output	Managed Fund / (% spent)	Output weighting
Revenues Identified	43%	40%
Revenue Management	36%	40%
Policy outcomes on Local Communities	21%	20%
Total	100%	100%

VfM performance compared to the original VfM proposition in the business case

The VfM proposition of the FOSTER programme is to increase extractive industry revenues, improve management and accountability within the oil and gas sector and improve policy outcomes for local communities affected by natural resource extraction. An underlying assumption of FOSTER is that small improvements in the governance of the oil and gas sector have the potential to deliver significant returns for the government of Nigeria and Nigerian citizens. This logic remains valid.

The change of government has provided an opportunity for a dramatic improvement in overall VfM performance because several policy initiatives supported by FOSTER are now being implemented by the government with large implications, both for revenues recovered and for the longer term efficiency and integrity of the sector. Given the success of FOSTER 1 and the improving political environment for reform, DFID should be even more ambitious in results expected under the FOSTER 2 programme. However, the ability to scale up and down both ambition and resources will be important to maintain throughout the programme given how quickly the political scene can change.

Assessment of whether the programme represented value for money

Effectiveness: The overall effectiveness of the programme is judged from two key perspectives. First, in the short-term by the revenues that FOSTER helped Nigeria safeguard through-out the course of the programme. This review concludes that FOSTER contributed to the Nigerian government preventing £403 million from having been lost. This means on average, for every pound that DFID spent on FOSTER, it helped the Nigerian Government to prevent more than £30 from having been lost. Second, the significant contribution that FOSTER played towards the longer term governance of the sector through:
- Raising the state of knowledge and calibre of public debate on oil and gas policy
- Achieving significant agreement about what the legal framework for the sector should be
- Increasing the institutionalisation of transparency and accountability in the oil and gas sector.

On both counts, the overall value for money of the FOSTER programme has proven to be excellent.

Efficiency: With flexible, adaptive programmes a key driver of the overall value for money of the programme is the quality of the portfolio of interventions and how this is managed over the time. As noted in the 2014 FOSTER Annual Review, political economy analysis with reliable local knowledge can help improve the chances of a given intervention leading to successful results, but there is still need to actively expand and contract interventions based on the extent of traction they are able to achieve once implementation takes place. This was mostly strong in the programme, and there were innovative examples of where the programme has applied this approach effectively. However lesson learning work commissioned by the programme looked at five case studies including work with the Department of Petroleum Resources and identified the need for a more systematic approach to clusters of interventions and having a shared understanding upfront with DFID on what the interventions were trying to achieve and when it would be appropriate to phase out support. This review supports this view, and FOSTER 2 should use its inception period to work through what this process should look like in practice.

Economy: As the key cost driver is the technical expertise that FOSTER provides in an expensive oil and gas industry, keeping down some costs will be challenging. FOSTER has generally responded to this well and some notable examples include:
1. Establishing a strong local network of experts in the various elements of the oil and gas sector.
2. Being able to draw on global expertise to supplement the local approach (in selected areas where necessary) e.g. quickly mobilising international refinery experts and using market intelligence to successfully negotiate discounted rates. This work was highly regarded by staff interviewed within NNPC, and helped establish a good working partnership between DFID and NNPC.
3. Bringing in high-level advisers to the Minister of State for Petroleum within DFID guidelines on cost for these positions- despite the expectations of individuals being much higher.

This experience and ways of working within the programme will be important for FOSTER 2 to learn from and will help make sure that every pound of UK aid spent can go as far as possible to deliver transformation in this politically challenging area.

Quality of financial management

Financial management has been good overall and the service provider strengthened systems in 2013 and early 2015. This does not mean that the five years of the programme have been without substantial challenges, including:
- A period of rapid commitment in 2012 which led to a squeeze in commitment space in 2013 and the programme had to adjust its portfolio until a contract extension was provided.
- Times where DFID has needed to adjust the annual expenditure limit of the programme due to financial constraints across the department and the programme has had to reprioritise accordingly.
- Greater pressure from DFID on accurately profiling expenditure and minimising expenditure within the last quarter of the financial year.

Whilst these challenges have inevitably had some impact on programming, and constrain the programme from operating perfectly flexibly (as a purist model may dictate), the service provider has responded to DFID’s expectations and strengthened those areas where needed. FOSTER 2 will need to also ensure it has the ability to deliver its flexible adaptive approach whilst recognising the various financial challenges it will face through-out the five years of the new programme, leaving space to scale up and down as required, and making sure the elements within its control are as strong as possible. This will require strong collaboration between the DFID team and the Service Provider.

Date of last narrative financial report	12 November 2014
Date of last audited annual statement	30 Sept 2013
Date of last audit	March 2016

E: RISK (½ page)

Overall risk rating: Minor/Moderate/Major/Severe

Despite the programme having achieved its outcome, after the various mitigations that were put in place in terms of the programmatic approach the overall residual risk for the programme achieving its outcome is assessed as having been moderate. Going forward for FOSTER 2 this should be raised to major to recognise the more ambitious results and the importance of key partnerships.

Overview of programme risk

The section below highlights the five main risks areas from the FOSTER risk register and maps this against DFID Nigeria’s risk appetite. There is one area which exceeds DFID Nigeria’s risk appetite which is on reputational risk which the SRO needs to continue to monitor.

External Context: Changing political conditions for reform of the oil and gas sector, resulting in limited ability for the programme to work directly with government.
DFID Nigeria risk appetite: Severe
Gross risk: Severe
Mitigation: Robust and regular political economy analyses to identify changing trends within government and key decision makers. Regular reviews on this between programme and DFID to highlight risks and agree on changes in strategy. Encouraging variety of different stakeholders for programme to engage with.
Net risk: Major

Delivery: Key actors who stand to lose from reforms in oil and gas sector blocking FOSTER supported reforms.
DFID Nigeria risk appetite: Major
Gross risk: Severe
Mitigation: Identify key reform champions and those likely to be against the reform. Have programmatic flexibility to work with demand-side actors to help strengthen the support for reform.
Net risk: Major.

Operational: Programme unable to source quality technical assistance with the necessary political nous and specialist technical expertise.
DFID Nigeria risk appetite: Minor
Gross risk: Minor
Mitigation: an established network of tested consultants and delivery partners.
Net risk: Minor

Safeguards: Risk of negative impact on Delta communities from policies supported through key Federal or State Agencies.
DFID Nigeria risk appetite: Minor
Gross risk: Minor
Mitigation: Programme to be aware potential conflict sensitivity in its interventions and continue to have dialogue with a number of Delta-based groups to be aware of potential impact.
Net Risk: Minor

Fiduciary: Risk of fraud or corruption on DFID's resources
DFID Nigeria risk appetite: Minor
Gross risk: Minor
Mitigation: No DFID funds put through Nigerian Government systems and service provider expected to have robust systems and processes for managing aid and subject to periodic audits
Net risks: Minor

Reputational: (i) Risk of FOSTER partnering with individuals or institutions engaged in corrupt activities within Nigeria and (ii) UK Government seen as undermining Nigerian Government through FOSTER’s demand side work
DFID Nigeria risk appetite: Moderate
Gross Risk: Major
Mitigation: (i) Stakeholder analysis from programme, and sharing information on individuals across government agencies. (ii) Ways of working of FOSTER programme, appropriate branding and ensuring appropriate systems and processes in place to manage both demand and supply side interventions
Net Risk: Moderate/ Major

Outstanding actions from risk assessment

DFID to work closely with the service provider for FOSTER 2 to develop the new risk matrix. There is one area in the existing framework which could potentially exceed DFID Nigeria’s risk appetite which is on reputational risk. The SRO and programme officer need to continue to monitor and engage with FOSTER team to ensure the systems developed and ways of working of the team under FOSTER 2 are sufficiently robust.

Upgrade the overall risk assessment for FOSTER 2.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

The programme was ultimately extended till the end of June 2016, in order to ensure that sufficient time was provided for the logframe results to be achieved (given constrained expenditure in 2014/15) and also to ensure the successful completion of the commercial process for FOSTER 2 without leaving programming gaps.

Performance of partnership (s)

The service provider has managed the programme well and responded to periodic requests from DFID. DFID engages with Oxford Policy Management (OPM) regularly to monitor progress and assess risk. The programme has had a challenge in retaining senior members of the programme, having had 3 programme directors and five Programme Managers over the course of the five years of the programme. OPM responded well to a 6 month management strengthening plan that was imposed in early 2015 following the loss of a former programme manager, and dedicated intensive, high quality support to the in-country team to help keep the programme on track and increase pace and quality of delivery. This ultimately led to the programme’s strongest year of performance and ensured the in-country team were well placed to respond to the opportunities after the Nigerian elections.

Asset monitoring and control

The programme’s assets were managed properly and when new items are purchased, the asset register was updated accordingly. A copy of the updated register is shared with DFID and saved in DFID’s electronic filing system. Programme assets, including vehicles have been used for their intended purposes and the programme has followed correct procedures for the disposal of assets. An independent audit was conducted in March 2016 prior to closure which will be finalised before programme closure.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

Partnership Principles were not assessed during business case design. The principles are however considered valid in reviewing FOSTER’s approach and objectives. This project aims to support Nigeria government make more effective use of its natural resources by strengthening the governance of the oil and gas sector, at different stages of the value chain, and working with accountability actors for reform. The programme is implemented through a commercially contracted service provider and no funds are passed through government systems. This is in direct response to the high fiduciary risk associated with funding through the Nigerian Government.

Emerging partnerships with the core oil and gas institutions are considered appropriate given the commitments and demonstrated measures taken by President Buhari’s administration on the anti-corruption agenda and cleaning up the governance of the oil and gas sector.

The programme will enhance domestic accountability through strengthening of accountability actors such as civil society organisations and media organisations.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

There was no comprehensive evaluation for this programme. However, a chapter was included in the Overseas Development Institute (ODI) publication ‘politically smart support to economic development- DFID experiences’ (March 2016)[8] which considered lessons learnt from the FOSTER model, and work is underway to look at lessons learnt from five specific areas of FOSTER programming.
[8] Bhalla, Waddell and Ough (March 2016), ‘The spoils of oil: working politically on extractives in Nigeria’

The revised theory of change for the programme has been captured as part of the FOSTER 2 Business Case which builds on the lessons learnt from FOSTER 1.

Monitoring progress throughout the programme

This Project Completion Review was carried out by a multidisciplinary DFID team drawing on findings from a self-assessment report from the programme and triangulated with a number of interviews with key stakeholders in Abuja during March 2016. This included meetings with the FOSTER team and interviews with senior officials from the Ministry of Finance, NEITI, NNPC, as well as representatives from the Nigerian Natural Resource Charter (NNRC) Group and Stakeholder Democracy Network (SDN).

This is the fifth and final review for the programme and builds on the findings from the four previous reviews. All previous reviews involved field visits and interviews with stakeholders with the exception of the 2011 annual review which, due to its proximity to the independent inception review, was carried out as a desk review.