Annual Review

Title: Sustaining Action on Nutrition (SAN) Programme
Programme Value £ (full life): £12,500,000		Review date: 18 May 2020
Programme Code: 300590	AMP start date: 18 May 2018	AMP end date: 30 April 2022

Summary of Programme Performance
Year	2019	2020
Overall Output Score	A	A
Risk Rating	Moderate	Moderate

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-GOV-1-300590/documents
DevTracker Link to results framework:	https://devtracker.dfid.gov.uk/projects/GB-GOV-1-300590/documents

A. SUMMARY AND OVERVIEW

Description of programme
The Sustaining Action on Nutrition (SAN) Programme aims to achieve longer-term impact on preventing and reducing malnutrition by supporting key building blocks for sustainable government and business action on nutrition. As per the original Business Case, DFID’s £12.5 million investment between May 2018 and April 2022 includes:

Output 1: £750,000 to the Scaling Up Nutrition (SUN) Civil Society Network’s (CSN) Secretariat and Output 2: £2.25m to the SUN Pooled Fund - both over a three-year period, to strengthen the capacity of SUN Civil Society Alliances (CSAs) to hold governments and business to account and advocate for their increased action on nutrition;
Output 3: £2m over four years to the Access To Nutrition Initiative (ATNI) to strengthen business accountability and action on nutrition;
Output 4: £3m over three years to the Global Panel on Agriculture and Food Systems for Nutrition in order to influence and support governments and other global stakeholders to adopt policies and practices to improve food systems and diets;
Output 5: £4.5m over four years to establish a new Food Systems for Nutrition Partnership (FSNP) that enables businesses to innovate and invest in products, services and technologies that make nutritious diets more affordable and accessible to the poor, in particular women, adolescent girls and children, and improves the enabling environment for such investments.

In March 2020, a Business Case Addendum was approved with the following changes:
- Upscaling ATNI’s work with up to £1.5m additional funds between 2020/21 and 2021/22 to influence a larger number of businesses and investors to take action on nutrition, including in a COVID-19 context and through the Nutrition for Growth (N4G) and Food Systems Summits
- Supporting the UK Food Foundation with a grant of up to £900,000 over two years, from April 2020 to March 2022 to drive forward efforts to mobilise commitments from government, cities and UK businesses at the N4G and Food Systems Summits and establish links between the UK food system and food systems in developing countries in their response to COVID-19
- Not proceeding with FSNP and reallocating budgeted funds to the activities above
In this Annual Review performance has been assessed against the Outputs as per the original Business Case. The section on assessment of Output 5 explains the rationale for discontinuing the planned Food Systems for Nutrition Partnership but carries a zero weighting because no work was undertaken under it during the period under review.

Summary supporting narrative for the overall score in this review
The programme overall met expectations this year, scoring an A. Milestones were not fully met however across all components. In particular, the SUN CSN Secretariat and the Global Panel missed some targets due to delays on various activities as a result of staffing constraints. Both ATNI and the Pooled Fund have performed particularly well and are assessed as delivering excellent value for money. The programme is making positive contributions to the intended outcomes, although it is likely that some delays will be faced over the coming period in fully achieving the intended outcomes and impact as a result of delays to the Nutrition for Growth Summit and the ongoing impact of the COVID-19 pandemic.

Major lessons and recommendations for the year ahead
The following major lessons have been identified from the reporting period 2019/2020:
- The focus of the SAN programme on creating a better enabling environment for government and business action on nutrition and its Theory of Change on how to achieve this remain highly relevant. All existing partners play an important role in this.
- As lessons have been learned through the programme and the wider focus on food systems has shifted it was no longer necessary to support the Food Systems for Nutrition Partnership and the adjustments that have been made will be more appropriate for supporting the intended outcomes and impacts of the programme.
- SAN partners made the most of forging links with each other (a recommendation from the last AR) even though the opportunities and feasibility for doing so were less than originally anticipated particularly as the Food Systems for Nutrition Partnership (which included a coordinating function) did not proceed as planned.
- DFID will need to continue to work with some partners to further strengthen programme management and their approach to VfM.
The year ahead will be particularly challenging due to the impact of COVID-19 on partners’ staff, delivery partners and the stakeholders they work with and try to influence. All partners are well placed to help respond to the pandemic and address secondary impacts on food systems and nutrition. The Global Panel and ATNI have already started doing so. A major recommendation for all partners is to closely monitor COVID-19 implications and take mitigating actions wherever possible. This will require updates to work plans and budgets on a frequent basis and for any risks and issues to be flagged to DFID early. In addition, all partners should proactively seek out opportunities to influence a ‘Building Back Better’ agenda at global and country level.

The other key recommendations by partner:

SUN CSN Secretariat:
- Identify and implement a strategy to achieve sustainability
- Sharpen its focus on results by strengthening monitoring and reporting of its own actions and contribution towards outputs and outcomes
- Improve monitoring and management of risks through a comprehensive risk matrix shared with donors
SUN Pooled Fund:
- Ensure a solid approach to risk management including in relation to COVID-19 and the ability of Fund recipients to deliver
- Support Fund recipients to adapt approaches to maximise impacts on mitigating the impacts of COVID-19 on nutrition where feasible
- Explore innovative approaches to programme management and M&E that will reduce reporting gaps and provide up-to-date information to donors and other stakeholders;
- Ensure effective coordination with the SUN CSN Secretariat in supporting grantees
- Update logframe indicators and milestones to ensure these reflect expected results from recipients and agree VfM indicators with DFID
ATNI
- Implement its fundraising strategy in order to secure core funding beyond 2021
- Start tracking how its products are being used by businesses, investors, civil society and governments and undertake an independent impact review
- Continue to strengthen collaboration with the World Benchmarking Alliance and align with other relevant accountability mechanisms for nutrition
- Continue to play a leading role in mobilising commitments for the N4G Summit and start engaging in preparations for the UN Food Systems Summit
Global Panel
- Further strengthen their engagement with policymakers at country level in order to help mobilise government commitments to transform food systems and diets, in particular in the context of N4G and the Food Systems Summit
- Track the impact of its publications among governments and development partners and monitor ownership and uptake of policy actions in follow-up to country roundtables
- Work more strategically with Panel Members to promote the Panel’s messages across their networks and monitor and track this in quarterly progress reports.
- Further strengthen VfM and the way this is reflected in quarterly financial reports.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.
This programme is expected to contribute towards reducing the burden of malnutrition in developing countries by mobilising sustainable government and business action on nutrition. It is designed to contribute to two outcomes:
1. Governments effectively and sustainably implement policies and programmes on nutrition and nutrition-smart food systems
2. Businesses adopt responsible policies and practices on nutrition and invest in low-income markets for nutritious foods, including products, services and technologies that help increase poor people’s access to safe, nutritious diets.
At impact level, these outcomes are expected to lead to improvements in the diets of the poor, particularly women, adolescent girls and children, and ultimately reduce malnutrition in its various forms (stunting, wasting, micronutrient deficiencies, overweight/obesity).

As per the original Business Case, outcomes are meant to be achieved through civil society advocacy (Outputs 1 and 2), business accountability (Output 3), policymakers receiving advice from the Global Panel on how to improve food systems and diets (Output 4) as well as businesses improving their knowledge on how to invest in nutrition and being linked up with potential investors (Output 5).

The Theory of Change for the programme was revised at Output level in the recent Business Case Addendum to reflect the shift to programme activities designed to enhance delivery of the existing intended outcomes and impact. The changes respond to lessons learned and changes in circumstances and need. These include:
- Businesses are unlikely to increase investments in nutrition in the absence of the right enabling environment. Government policy, business accountability and the influence of investors are particularly powerful instruments to incentivise business investments in nutrition. There is scope for SAN to scale up work in these areas.
- Business access to global knowledge products and to services to link them with investors is no longer a critical gap as this is being addressed by other initiatives.
- Cities and youth leaders are beginning to play an important role in changing food environments and influencing policymakers and business leaders to take action.
- Upcoming N4G and Food Systems Summits provide a unique opportunity to mobilise government and business commitments and to involve cities and young people.
- COVID-19 secondary impacts on food security and nutrition affect and are affected by links between different countries’ food systems. These need to be better understood.
- The UK national food strategy provides valuable lessons for other countries.
Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?
The programme is on track to contribute to its expected outcome regarding business action on nutrition. ATNI has exceeded its outcome target on the number of businesses improving their engagement and scores. Eight out of 9 previously assessed companies in India have improved their scores between 2016 and 2019 (compared to a 40% target for this year). The average score increased from 3 to 4.2 over the same period, and 7 companies provided data on their product profiles in 2019 compared to only 3 previously. In the year ahead, ATNI will expand its work in developing countries and its engagement with major food companies to monitor and shape their response to COVID-19. ATNI will also play a role in mobilising business and investor commitments for the N4G and Food Systems Summits.

The programme is also largely on track to contribute to the outcome on government action on nutrition. This is the result of the work of the SUN Civil Society Network, the SUN Pooled Fund and the Global Panel. The SUN CSN and Pooled Fund are on track to achieve or exceed the target to ensure 10 SUN countries have SMART, costed multi-stakeholder, multi-sector nutrition plans in place. The SUN CSN has mobilised international and domestic resources to fully finance national nutrition plans in 5 countries. Last year, more donors joined the Pooled Fund, increasing the budget from USD 3 million at its inception to USD 18.5 million today. This increase in funding enables more Civil Society Alliances to support governments with the design, financing and implementation of costed multi-sector national nutrition plans. It has also enabled more support to be provided to multi-stakeholder platforms designed to promote coordinated, government-led action on nutrition. Support through the Pooled Fund is linked to increased engagement by parliamentarians and key influencers on nutrition in key decision-making processes related to legislation, policy making, planning and budgeting.

The Global Panel has made slower progress this year, due to delayed timelines and reduced capacity at various periods during the year. However, it is still on track to contribute to the outcome target of ensuring six SUN countries have improved policies and regulations for nutrition-smart food systems. The Panel’s messaging reached multiple new key audiences, strengthening its international profile. In addition, as a result of the Global Panel’s input, the Government of Uganda’s new Nutrition Action Plan has been realigned towards a food systems approach, Pakistan’s new social protection programme now has a component designed to deliver better nutrition outcomes and the Nepalese Government signed a ‘Statement of Intent’ with development partners on the need to address food systems issues.

While all partners continue to firmly orient their work towards achieving the programme’s intended impact, the extent to which outcomes and impact will be achieved will significantly depend on the impact of COVID-19 on people’s lives and livelihoods and the ability of governments and businesses to invest in nutrition. This will need to be monitored closely and adjustments to approaches made where relevant to ensure the programme continues to contribute positively to efforts to reduce malnutrition in the long term.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio
The rationale for continuing with the SAN programme remains strong. Its intended impact and outcomes are key for achieving the UK Government’s manifesto commitment on Ending Preventable Deaths. Its existing partners continue to play an important role in improving the enabling environment for government and business action on nutrition, including as they pivot their work to address secondary impacts of COVID-19. Measures to improve capacity and VfM for some partners have been identified and will be implemented over the coming period.

## C. DETAILED OUTPUT SCORING

Output Title	Improved effectiveness and sustainability of civil society action in SUN countries
Output number:		1	Output Score:	A
Impact weighting (%):		15%	Weighting revised since last AR?	Yes, up from 10%

Indicator(s)	Milestone(s) for this review	Progress
1.1. Number of Civil Society Alliances (CSAs) that are functioning effectively with robust governance structure and sustainable funding secured.	90% of alliances currently funded / 10 CSAs in focus countries on track with implementing national alliance plans	Exceeded. / 91% of total CSAs and 100% of those that are active are currently funded. / 41 CSAs on track with implementing national alliance plans.
1.2. CSAs influence governments, private sector and donors at international and regional level	3 global or regional advocacy events attended by members of CSAs with youth or civil society participation / 5 global and regional campaigns implemented by youth and CSA members of the CSN / 3 opportunities where CSN members informed the development of nutrition-related campaigns resulting in respective civil society recommendations being reflected	Achieved. / Youth and CSA representatives supported to participate in 7 global or regional advocacy events. / 5 global and regional campaigns implemented / 2 opportunities where CSN members informed the development of nutrition-related campaigns resulting in respective civil society recommendations being reflected
1.3. Key stakeholders (decision makers, UN private sector and other NGOs) are provided with the evidence to make informed nutrition plans (Outcome 1.2)	5 case studies / briefs developed and available / 1 guidance material produced on key global frameworks reflecting best practices, challenges opportunities / 10 published reports on CSN experiences	Not met. / 2 case studies developed and available on SUN website, 6 in progress. / 1 regional meeting guidance document, produced defining best practice for organising a SUN CSN regional meeting / 5 published reports and articles

Briefly describe the output and provide supporting narrative for the score.
Although not all milestones for this Output have been fully achieved, significant progress has been made in key areas and on balance it is reasonable to conclude that expectations have been met. The SUN CSN Secretariat made significant progress towards building civil society leadership to improve coordination and accountability in the global nutrition community. Milestones regarding CSA capacity and influence have been exceeded or achieved. Due to several long-term staff gaps that were outside the control of the SUN CSN Secretariat, the Secretariat’s capacity was reduced through parts of 2019, which contributed to delays and consequently some milestones not being achieved.

Over the past year, the SUN CSN Secretariat prioritised support to CSAs on fundraising advice, proposal writing and identification of future funding opportunities. Direct fundraising support was provided to CSAs in Kenya, Myanmar, Zimbabwe, Senegal, Rwanda, Burundi, Bangladesh, Sri Lanka, Zambia, Cambodia, Papua New Guinea, and Afghanistan. A Fundraising and Strategy template was developed and is being used by CSAs. This work is an important step for strengthening the future sustainability and strategic impact of the CSAs.
The SUN CSN also continued to lead on the global Youth Leader programme on the basis that young people can play an effective role at advocating for shifts in government policy and practice. Youth leaders were supported to participate at multiple global events, including at: the Women Deliver conference, the Tokyo International Conference for Investment in Aid and at the SUN Global Gathering. Regional meetings were organised in West and Central Africa and Asia to foster exchange and build capacity in budget advocacy and approaches to monitoring, accountability, evaluation and learning.

The SUN CSN Secretariat inputted into the design of the next phase of the SUN Movement. Two CSN members are part of the advisory group for the N4G Summit and SUN CSN engagement with the Government of Japan enabled approval of a set of Principles of Engagement for the N4G that would enable responsible participation by all actors.

For reasons outside of CSN Secretariat’s control some activities were delayed – with particular impact on case studies and documenting CSN experiences. COVID-19 is further delaying some planned activities. There is growing interest among academia to document the role of multi-stakeholder partnerships and the SUN CSN Secretariat is encouraging CSAs to support research efforts in this area to maximise the role and impact that the CSAs and multi-stakeholder partnerships can have.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year
The underlying parameters and VfM assessment that was presented in the Business Case continue to hold and the SUN CSN Secretariat continues to deliver good VfM. There is evidence that the Secretariat looks for ways to keep costs down and to streamline their work to make it more efficient. This includes by restructuring processes, prioritising workload and coordinating with other SUN networks and the SUN Movement Secretariat to improve efficiency and quality of technical support. In last year’s review a slight drop in the SUN CSN’s efficiency was noted compared to a strong initial assessment in the business case. This continues to hold true. For example, reduced staff capacity resulted in delays and in potentially missed windows of opportunity.

Save the Children as hosts of the SUN Civil Society Network Secretariat have taken steps to address the reasons for staffing gaps and have proactively engaged with donors on how it is providing more support for staff in the SUN CSN to address issues that have arisen. The SUN CSN Secretariat team is subject to Save the Children policies on Gender Equality and Equal Opportunities and Diversity, as well as to its mandatory training on workplace culture and inclusion. The SUN CSN Secretariat is committed to the SUN Movement principles of engagement, which includes strong elements on inclusivity, rights and equity. Where possible, data generated by the SUN CSN Secretariat is segregated by gender and for other key groups. Specific indicators to enable the SUN CSN Secretariat to monitor equity will need to be agreed with DFID to track how well it is promoting an equitable approach to how it works and the impact it has.

Describe any changes to this output, and any planned changes as a result of this review.
The impact weighting of this Output was increased from 10% to 15% with approval from the Head of HDD to account for the closure of component 5 of the programme. DFID and other donors will work with the SUN CSN Secretariat to ensure it updates its priorities and milestones and identifies windows of opportunity to flex its workplan in light of the COVID-19 pandemic so that it is able to achieve intended outputs.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
Despite efforts to support SUN CSAs to develop fundraising strategies, future of funding in many cases remains uncertain – with a continued reliance in some cases on the SUN Pooled Fund. Current restrictions around COVID-19 pandemic and diversion of attention away from nutrition might make it even more difficult for SUN CSAs to secure long-term funding. The SUN CSN will need to play a role to identify how the future support for SUN CSAs can be best ensured, particularly through the development of the next phase of the SUN Movement overall.

Gaps in staffing in the SUN CSN Secretariat have already been addressed to some extent with workload prioritisation and restructuring. The SUN CSN Secretariat is still struggling to meet the demand for support from SUN CSAs but is identifying a model to enable more effective provision of TA, including in discussion with the SUN Pooled Fund Team and the SUN Movement Secretariat to better align and coordinate TA requests. The 2019 SUN Strategic Review raised important questions about the sustainability and mandate of the SUN CSN, as well as the potential conflict of interest associated with the SUN CSN Secretariat being hosted by Save the Children. The SUN CSN Secretariat will need to carefully consider its priorities, structure and hosting arrangements to enable it to achieve greatest impact beyond 2020.

The SUN CSN Secretariat will need to continue to proactively monitor the external environment – and impacts of COVID-19 – and to review its workplan, capacity and expertise to ensure it can make the best contribution to the progress of the SUN Movement overall. Staffing levels and workload will need to be monitored and contingency plans managed to minimise negative impact on delivery in case of future staff gaps.

Limited progress has been made over the past year to strengthen monitoring and reporting on this component – this is largely due to staffing gaps in both DFID and the SUN CSN Secretariat.

Key recommendations for the coming year are that the SUN CSN Secretariat will need to:
- Regularly update a comprehensive risk matrix to monitor the external environment and its impact on delivery and to outline mitigating actions. This must include close monitoring of the impact of the COVID-19 pandemic and how the SUN CSN Secretariat can remain flexible to opportunities to ensure its work and the work of SUN CSAs supports efforts to minimise impacts of COVID-19 on nutrition. The risk matrix should be shared with donors at least quarterly.
- Regularly review its workplan and prioritise activities that are relevant, address needs, feasible and that will achieve maximum impact.
- Give particular focus to strategies that will enable future relevance and sustainability of the SUN CSN – including through discussions about the strategy for the next phase of the SUN Movement.
- Strengthen monitoring and reporting of its own actions and contribution towards results.
- Prioritise knowledge management and communication by documenting and disseminating best practice on strategically important topics (e.g. sustainability, funding, governance, COVID-19 etc).
- Review its communication strategy to ensure that it is adapted to the current situation and supports visibility of SUN CSN activities (end June).
- DFID and the Secretariat need to update the milestones for this Output and ensure they are aligned with CSN’s reporting. A set of VfM indicators to assess equity will be agreed with the CSN Secretariat.

Output Title	Participation by in-country non-state stakeholders and parliamentarians in national multi-stakeholder platforms to implement scale up nutrition plans is strengthened
Output number:		2	Output Score:	A+
Impact weighting (%):		20%	Weighting revised since last AR?	Yes, up from 15%

Indicator(s)	Milestone(s) for this review	Progress
2.1. Number of roundtables and consultations organised with local, marginalised CSOs at subnational level	61	Exceeded. / 130
2.2. Number of parliamentarian champions and key influencers that speak about nutrition in key decision-making processes related to legislation, policy making, planning and budgeting as a result of SUN influence.	Total: 151 / Men: 86 / Women: 65	Exceeded. / Total: 161 / Men: 47, women: 44, not disaggregated by sex: 70
2.3. Number and quality of national and subnational plans that clearly incorporate contributions by CSAs	10	Exceeded. / Total: 27; 17 national and 10 subnational
2.4. % of national nutrition plans that show CSAs inputs in regard to gender inequality and women's empowerment	7	Exceeded. / 9

Briefly describe the output and provide supporting narrative for the score.
The SUN Pooled Fund is demonstrating positive results through its support for 43 SUN Civil Society Alliances. Milestones have been exceeded and the output has been assessed as having moderately exceeded expectations.

Seven donors (Canada, Germany, Ireland, Norway, Switzerland, the European Commission, and the United Kingdom) contribute to the Pooled Fund. To date four calls for proposals have been launched and the Pooled Fund currently supports 54 active projects in 44 countries:
- Two calls under Window 1 (cycles 1 and 2), launched in 2018, aimed to strengthen national Civil Society Alliances for a period of 12 and 18 months (9 + 19 projects remaining active);
- Window 2 Cycle 1 call launched in 2019 and aims to accelerate the coordinated delivery of nutrition interventions by Multi-Stakeholder and Multisectoral Platforms (MSPs) to deliver core nutrition interventions together in 12 countries for a period of 14 months (12 active projects);
- Window 1, cycle 3 call launched in February 2020 and targets the creation and/or strengthening of national business alliances in 13 countries for a period of 11 months (13 active projects)
Positive examples of work done through the Pooled Fund over the past year include:
- Enabling 191 roundtable discussions across a range of countries at national and sub-national level including key stakeholders and media. These roundtables serve as a platform for women, marginalized communities and CSOs at sub-national levels to ensure their voices on nutrition issues are heard and factored into national planning processes. Since the start of the Pooled Fund, these roundtables helped CSAs reach a total of 3096 stakeholders, 44% of whom were women.
- There is evidence that inputs from civil society are being taken up in national planning processes for nutrition – including as a result of roundtables and the more direct engagement with parliamentarians and others. A total of 60 (27 national and 33 subnational) plans that incorporate contributions by CSAs have been submitted to governments for approval.
- With support through the SUN Pooled Fund, seven countries (Myanmar, Mali, Papua New Guinea and Somalia) have developed new national nutrition plans which include inputs from SUN CSAs on gender equality and women’s empowerment. This is an important step forward as this remained a key gap in national nutrition plans that had been developed to date.

A number of key decisions were taken about the SUN Pooled Fund over the past year. The Fund was shifted from being ‘last resort’ funding to enabling ‘catalytic and innovative support’. This has been done to maximise the impact of the funds that are available. The scope of the Fund has been broadened to help establishment and/or operationalise SUN Business Networks. A no-cost extension has been approved by the Pooled Fund consultative group until December 2021 to allow successful completion of the projects, closure of contracts and reporting. The Results Framework for the Fund has been broadened to enable flexibility for recipients and to enable them to develop their own logframes tailored to their country contexts with the assistance of UNOPS’ Monitoring and Evaluation team.

The 2019 SUN Strategic Review acknowledged the importance of the Pooled Fund in providing support to CSAs, but it also raised many questions about the future structure and function of the Pooled Fund. Donors hold diverse views about the future of the Pooled Fund – including its design, purpose and objectives. Discussions about the form and function of a new Fund will be very important this year as the new SUN Movement roadmap is developed. DFID can play a role in ensuring the future of the Fund is well aligned to the needs of the SUN Movement as it moves into its next phase.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year
The underlying parameters and VfM assessment that was presented in the Business Case continue to hold. The SUN Pooled Fund has been able to attract additional funding which was identified as important for ensuring efficiency and effectiveness of the mechanism. As of 2020, the Pooled Fund has secured approximately USD$18.5 million funding, a 516% increase from the original go/no-go milestone of USD 3 million set out in the Business Case. DFID’s share is now 15.7% compared with 25% set out in the original Business Case. Efficiency is assessed as moderate (revision from high in the business case). In its first year the Fund experienced challenges with absorption capacity and delays in setting up the grants. Despite relatively high management costs (7%), the Fund continues to deliver good VfM compared to possible alternatives and delivers reasonably robust monitoring and reporting.

The Pooled Fund has a strong equity angle. Promoting diversity inclusion, gender equality and women’s and girls’ empowerment in the context of country-driven efforts is at the centre of the SUN Movement’s efforts to leave no one behind and the Pool Fund follows this vision. Gender equality and diversity inclusion are factored into both the Pooled Fund management and the individual grant project’s activities. Contribution to gender equality and/or the empowerment of women, adolescent girls, youth, indigenous people, grassroots groups and/or vulnerable communities is one of the major evaluation criteria for the selection of grant recipients. Gender mainstreaming is also an important dimension of UNOPS’ approach to recruiting project personnel.

Describe any changes this output, and any planned changes as a result of this review.
The impact weighting of this Output was increased from 15% to 20% with approval from the Head of HDD to account for the closure of component 5 of the programme. UNOPS (who manage the SUN Pooled Fund) have submitted a request for a no cost extension until December 2021. If approved, output and targets will be adjusted accordingly.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
The recommendations in the previous Annual Review to work with DFID to make sure financial and risk reporting align with DFID requirements have been taken on board although further work is needed to clarify risk management expectations. While the indicators and milestones have been updated, more work is needed to align them with UNOPS joint donor reporting.

Key recommendations for the coming year for the SUN Pooled Fund are to:
- Ensure there is a solid approach to risk management in place – including in relation to COVID-19 and the ability of Fund recipients to deliver.
- Support Fund recipients to adapt approaches to maximise impacts on mitigating the impacts of COVID-19 on nutrition where feasible.
- Explore innovative approaches to programme management and M&E that will reduce reporting gaps and provide up-to-date information to donors and relevant stakeholders.
- Ensure effective coordination with the SUN CSN Secretariat to ensure effective and efficient support is provided to grantees.
- Update logframe indicators and milestones to ensure these reflect expected results from recipients and agree VfM indicators with DFID.

Output Title	Accountability for responsible business action on nutrition is strengthened.
Output number:		3	Output Score:	A+
Impact weighting (%):		25%	Weighting revised since last AR?	Yes, up from 15%

Indicator(s)	Milestone(s) for this review	Progress
3.1. Number of global and country indexes or other newly developed company accountability tools	At least 4 (India 2019, 2 country specific SME self-assessment tools, 1 or 2 BMS projects)	Achieved. / 3 published (second India Index February 2020, first UK Product Profile September 2019, first UK Supermarket Spotlight Study March 2020) / 2 Nutrition Business Monitor self-assessment tools for SMEs developed and tested in Nigeria and Bangladesh / 1 BMS in-country assessment started in January 2020, data collection is largely completed but analysis is delayed because of Covid-19.
3.2. Number of businesses included in ATNI indexes and other publications / assessments	50 companies	Exceeded. / 93 companies
3.3. Number of investors, CSOs, governments and business platforms using ATNI to inform their decisions and actions	65 investors, 20 CSOs, 6 governments, 8 business platforms	Exceeded. / 72 investor organizations signed up to the ATNI investor statement / ATNI engaged with many more than 20 NGOs, 6 governments and 9 business platforms
3.4. Number of funders	5 funders	Exceeded. / 7 (Gates Foundation, DFID, Netherlands, ShareAction, GAIN, IrishAid, The Robert Wood Johnson Foundation)
3.5. Percentage of budget funded	100%	Achieved. / 100%

Briefly describe the output and provide supporting narrative for the score.
In 2019/20, the Access To Nutrition Initiative significantly scaled up its influence and relevance as an effective accountability mechanism for business action on nutrition. Overall expectations for this Output have been exceeded over the past year. There has been some slippage on one milestone regarding in-country BMS assessments due to COVID-19. Beyond its core work plan, ATNI played an instrumental role in engaging with the private sector to mobilise their commitments for the upcoming Nutrition for Growth (N4G) Summit.

ATNI has expanded its global and country level tools to assess company performance and updated its methodology to capture a greater scope of business performance and to streamline data collection. Most notable is ATNI’s ability to hold many more companies to account than originally expected. Twenty-five companies have been selected for the ongoing Global Index 2020 (announced February 2020) – three more than in 2018. Its BMS ranking is being extended to cover 3 additional companies – 9 in total. Sixteen companies were assessed in the 2020 India Spotlight Index compared to 9 in 2016. Eighteen manufacturers were included in a first UK Product Profile report and 10 UK retailers assessed in a UK Supermarket study. Eleven companies have been selected for the ongoing US 2021 Index (announced March 2020). Five companies tested the Nutrition Business Monitor in Nigeria and in Bangladesh respectively.

The high number of investors using ATNI to inform decisions is further testament to ATNI’s impact. 72 investor organisations have signed up to ATNI’s investor statement. In addition, ATNI continues to maintain close links with civil society organisations. Many more than 20 NGOs participated in stakeholder meetings or as reviewer of analysis for the India Index 2020; Nutrition Business Monitor in Bangladesh and Nigeria; BMS in-country studies; and the N4G pre-conference in The Hague June 2019. In the context of its index work and N4G preparations, ATNI engaged with representatives from 6 governments (India, Japan, Nigeria, Bangladesh, the Netherlands and the UK) and 9 business platforms (Consumer Goods Forum, Chartered Insurance Institute, Food Industry Asia, International Food and Beverage Association, Japan Food Industry Association, Nutrition Japan Public Private Platform, SUN Business Network, United States Council for International Business, World Business Council for Sustainable Development). The extent to which these stakeholders are using ATNI to inform their decisions and actions is however not know and will require separate tracking.

Over the past few weeks, ATNI has initiated discussions with food companies on how they can play a positive role in responding to COVID-19. DFID’s additional grant of £1.5m will enable it to further act upon these issues in 2020/21.

ATNI has been able to cover its budget by continuing to rely on BMGF, the Netherlands and DFID as its core funders but also by diversifying the number of funders of particular activities. For example, the SME self-assessment tool was prepared in collaboration with (including with dedicated funding from) GAIN. The two studies on UK food manufacturers and retailers were funded by UK-based non-profit organisation ShareAction. The report on UK supermarkets served as a test case for ATNI to expand into assessing retailers in other regions in the future. ATNI faces however an uncertain future, as core funding from BMGF and the Netherlands ends in 2021. Without additional core funding, it will be unable to continue its work in 2022.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year
DFID’s support to ATNI continues to present good VfM. In the original Business Case, this was calculated in terms of the cost of holding the 22 largest food companies in the world to account for their actions. At that point, DFID’s contribution to ATNI was 0.12% of the annual sales revenue of these companies (calculated on the basis of two years’ worth of ATNI’s budget to produce the Global Index). This cost has been reduced further as ATNI has expanded the number of companies being held to account for the same budget. More companies are also being held to account through the India Spotlight Index for a similar budget in 2020 compared to the first index in 2016. In addition, ATNI’s influence extends far beyond directly assessed companies through their engagement with various business associations.

While the cost of major inputs has remained unchanged, ATNI is looking for ways to further reduce cost by making processes to conduct global and in-country company assessments more efficient. It proactively monitors and seeks to ensure VfM through constant dialogue with suppliers and sub-contractors on price levels of services provided. It has increased the visibility of its findings by using a lower cost rolling system of publication of results throughout the year. ATNI has a strong focus on equity. It assesses and influences how company practices affect the nutrition of women and young children. It has also started to uncover inequities in the healthiness of the product portfolios of businesses between high income and emerging markets – an area which ATNI will work on further with DFID’s additional grant.

Describe any changes this output, and any planned changes as a result of this review.
The impact weighting of this Output was increased from 15% to 25% with approval from the Head of HDD to account for the closure of component 5 of the programme. Milestones / deliverables were also updated to reflect the approval of a cost-extension to ATNI to enable it to respond to COVID-19, mobilise business and investor commitments to N4G and the UN Food Systems Summit, and to further expand ATNI’s work in developing countries.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
ATNI acted on all recommendations from the previous Annual Review. It developed a fundraising strategy and hired a donor manager. It developed an internal M&E framework to serve as the basis for ATNI’s first external review of its impact in 2020. It also updated its theory of change for its new strategic plan 2020-2024, which has been approved by the Board. It has continued to expand the relevance of its tools and action research for developing countries. A draft report on the affordability and affordability of healthy diets in developing countries has been prepared. Implications of the COVID-19 pandemic on access and affordability will be studied by ATNI as part of the extra activities supported by DFID under the addendum agreement.

As part of a comprehensive exercise to update and streamline its global index methodology, ATNI has incorporated indicators to measure the healthiness of companies’ product portfolio. It has also played an active role in discussions on aligning and strengthening business accountability mechanisms, including as co-lead of the N4G Working Group on Accountability. It has been asked to monitor business commitments made during the N4G Summit and to develop and monitor a new WHO Global Corporate Action Tracker on Nutrition. ATNI has managed to agree areas of alignment and collaboration with the World Benchmarking Alliance. ATNI’s future will largely depend on its ability to secure core funding beyond 2021, when the current funding cycle for BMGF and the Dutch Government come to an end. While ATNI is exploring options of streamlining global and country indexes in order to cut costs, its increasing remit and influence, in particular in follow-up to N4G and the Food Systems Summit, must be matched by an increasing funding base. To demonstrate its impact, ATNI should start tracking how its products are being used to inform business, government and CSO decisions / actions.

Success in the year ahead will significantly depend on ATNI’s ability to deal with the risks that COVID-19 present to its own staff as well as the stakeholders it engages with. For the coming year, it is recommended that ATNI:
- Closely monitors COVID-19 associated risks and tailors its engagement strategy and offer to effective support to reach its target groups – SAN logframe targets for 2020/21 may have to be revised in light of COVID-19
- Plays an active role in shaping the global ‘Building Back Better’ agenda as it pertains to food systems and the role of the private sector
- Continues to play a lead role in preparations for the N4G Summit and engages as appropriate in preparations for the UN Food Systems Summit
- Continues to work on aligning and strengthening collaboration with the World Benchmarking Alliance including on COVID-19, N4G and the Food Systems Summit
- Undertakes an independent impact assessment in 2020/21 and identifies ways of tracking how its products are being used by businesses and their platforms, investors, governments and CSOs to inform their decisions and actions
- Continues to prioritise its fundraising strategy to ensure it can secure funding beyond 2021 when support from the Netherlands and Gates comes to an end.

Output Title	Government engagement on nutrition-smart food systems and their ability to adopt policies to improve food systems for nutrition is enhanced.
Output number:		4	Output Score:	B
Impact weighting (%):		40%	Weighting revised since last AR?	Yes – increased.

Indicator(s)	Milestone(s) for this review	Progress
4.1. Number of governments engaging with the Global Panel (at country or regional level meetings and dialogue) to review and / or strengthen their policies in support of nutrition-smart food systems	2 / (8 cumulative)	Not met. 1 / additional government (Nepal), 3 continued engagement (Ghana, Uganda, Pakistan)
4.2. Number of quality and relevant evidence-based policy recommendations (briefs, tools, foresight analysis) published	3 / (19 cumulative)	Not met. 2 / (trade policy brief and handbook of essential policies)
4.3. Number of other global initiatives / international organisations engaging with the Global Panel	3 / (27 cumulative)	Achieved. 3 / global initiatives (TICAD, AGRF and SUN GG) and ongoing engagement with others.

Briefly describe the output and provide supporting narrative for the score.
The Global Panel has made reasonable progress over the past 12 months in promoting actions to improve food systems for nutrition among government partners and stakeholders. The Panel has struggled with staffing constraints and capacity over the last 12 months, which delayed some of their timelines and hence not all milestones have been met. There are concerns about the Global Panel’s ability to effectively embed value for money into all their activities. This Output has therefore been scored a B, ‘moderately did not meet expectation’.

The Global Panel hosted one High Level Roundtable (HLRT) this year (in Nepal in December 2020). A key outcome was a joint statement on healthy diets by the Government of Nepal and development partners. Positive feedback was received in terms of the Global Panel’s ability to attract senior level decision-makers from government and engage them on new issues. However, further work is needed to ensure the longer-term impact and ownership of the actions set out in the Statement of Intent signed, post-roundtable. Another roundtable in Zambia was planned to take place in March 2020 but due to a slow response from the Government of Zambia and staffing constraints in the Secretariat, this has now been postponed until the autumn. Instead, a recce visit to kick off engagement took place in March 2020.

The Panel has continued to strengthen its contact with existing government partners, including by hosting a workshop in Ghana with government advisers on food systems in urban settings, providing speaking points for the First Lady of Ghana’s speech on nutrition at the African Green Revolution Forum (AGRF) as well as a public event on micronutrient deficiencies, input to the Ugandan Nutrition Action Plan II, and technical input to Pakistan’s new nutrition-focused cash transfer initiative in September 2019.

The Global Panel produced 2 new policy briefs this year. The Panel published a policy brief on ‘Re-thinking trade policies to support sustainable food systems and healthy diets’ in February 2020. This is the first brief that has tried to help bridge the gap between trade and nutrition. This brief took longer than the Global Panel expected – hence timelines were delayed, and it was published online in February 2020. A physical launch has been pushed to the next financial year (2020-21) with potentially a virtual launch to accommodate restrictions related COVID-19. The Global Panel also produced an online compendium of all policy briefs to date to help decision-makers navigate the key recommendations of each of the Panel’s policy briefs – ‘Food Systems and Diets: a handbook of essential policies’. This was launched in Nepal in December 2019 and was well received. Another policy brief was originally planned for this year on food systems in fragile and conflicted-affected states. However, due to the trade policy brief taking longer to finalise than expected and given reduced capacity, this has now been pushed to 2020-21. Work on the Foresight 2.0 Report has been progressing well.

The Panel has continued to maintain and strengthen partnerships and ensure its voice is heard at multiple key international events. Its participation in 3 new international events has provided additional opportunities to share critical messages on food systems and healthy diets with new audiences. These were:
- A side event that was part of the GGG+ Forum on ‘Ending Malnutrition in Africa: Towards Nutrition for Growth 2020 and Beyond’ in Japan in August 2019. Through this event they were able to reach new audiences including donors such as Japan and the Netherlands.
- A keynote for a session on ‘Nourishing Africa: Driving a Nutrition-led Agriculture Transformation in Africa’ at the AGRF in Ghana in September 2019. As one of only two sessions focussed on nutrition, this provided an opportunity to highlight issues across the food system affecting health, climate and economies – and push for a better functioning food system focussed on healthy diets, empowering youth and engaging private sector.
- A short presentation on Making food systems work for healthy and sustainable diets at the SUN Global Gathering. The Panel also participated in a marketplace and shared its briefs and other materials with attendees.
The Global Panel has also strengthened its relationship with key organisations, continuing to provide policy guidance and support, for example by presenting at the World Food Programme’s (WFP) Annual Nutrition Retreat and engaging new partners in shaping the Foresight Report such as Kellogg’s.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year
The Global Panel has kept its deliverables in line with the original budget. Where individual budget lines have increased, savings in other lines have been made to ensure the overall budget is maintained. Salary costs and consulting fees remain as agreed in the original contract. However, the Global Panel should continue to identify further cost savings where possible, e.g. in event planning and travel. Economy and efficiency are further discussed in section E.

Its focus on equity continues to be a central part of the Global Panel’s work, as it advises policymakers on how to improve access and affordability of healthy diets to the most vulnerable including women and children.

Describe any changes this output, and any planned changes as a result of this review.
The impact weighting of this Output was increased from 35% to 40% with approval from the Head of HDD to account for the closure of component 5 of the programme. As a result of COVID-19 the Global Panel will continue to closely monitor activities and identify opportunities where they will be best placed to respond. This may result in some changes in output milestones.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
The Global Panel has made progress on the recommendations from the previous AR. It has continued to engage strategically with a selected number of countries with whom the Panel has established strong relationships (Pakistan, Uganda, Ghana) and fed into key policy areas. It also improved its financial reporting and agreed a new travel and expense policy with DFID in order to strengthen VfM. It has not yet found a way to track the contribution of its publications and policy tools on SAN outcomes. Panel Members’ actions to promote the Panel’s messages across their individual networks have been limited.

The Global Panel has made positive steps this year to ensure that nutrition is included in discussions on food systems and new stakeholders are being reached, even though progress has been slower than in the year before. Moreover, the Global Panel has strengthened its social media presence to help raise the profile of its work. Going forward the Panel will further increase presence on social media through electronic newsletters and make the most of online opportunities – especially relevant in the current context of covid-19. To increase its impact at country level, it will be useful to explore embedding a process post-roundtables to track and help facilitate uptake and ownership of policy actions by Governments. As the Panel’s funding ends in March 2021 (DFID being its only funder), DFID and the Global Panel need to agree a plan for the future shortly (i.e. the Panel coming to an end or extending it to 2022).

Key recommendations for the coming year are for the Global Panel to:
- Be more realistic regarding timelines and what can be achieved within the next year, especially given constraints around COVID-19, and continue to raise issues with DFID well in advance.
- Take a strategic approach to responding to COVID-19 by serving as a global voice and adviser to governments to ensure that the impact of the pandemic on food systems and nutrition is being addressed both in the short and long term – this requires carefully adjusting and tailoring their earlier recommendations to a COVID-19 context and audience.
- Use its relationships with policymakers to help mobilise commitments for the N4G Summit and the UN Food Systems Summit, and feed into plans for a global governance mechanism for food
- Take action on the recommendation from last year to track the impact of their publications used by governments and partners and also monitor and follow up on ownership and uptake of policy actions post-roundtables including in Nepal
- Work more strategically with Panel Members to promote the Panel’s messages across their networks and monitor and track this in quarterly progress reports.
- Strengthen its application and reporting on VfM across all its activities by agreeing updated VfM indicators with DFID, identifying potential cost savings across its portfolio and reporting on VfM on quarterly basis.

Output Title	Ability of business to invest in nutrition-smart food systems and capacity of DFID and other stakeholders to support business investment in nutrition are enhanced.
Output number:		5	Output Score:	N/A
Impact weighting (%):		0	Weighting revised since last AR?	Yes, down from 35%

Indicator(s)	Milestone(s) for this review	Progress
5.1. Number of businesses benefitting from FSNP services to inform their investment decisions in nutrition	None	None
5.2. Number of knowledge and evidence products generated	None	None
5.3. Number of business to business linkages to (i) share expertise or (ii) collaborate in investing in nutrition-smart food systems facilitated.	None	None
5.4. Number of DFID programmes able to better target nutrition as a result of using FSNP knowledge and technical assistance services	None	None

Briefly describe the output and provide supporting narrative for the score.
The tender for the Food Systems for Nutrition Partnership was unsuccessful as DFID was unable to identify suppliers who were able to deliver on the Terms of Reference. New initiatives have emerged within DFID and externally that are able to offer similar services that FSNP was meant to deliver. Duplicating these efforts would have put FSNP at high risk of failing to achieve its objectives. It was therefore decided in March 2020 not to proceed with this component and to redirect funds to other activities that will enable the SAN programme to deliver its overarching objectives. DFID will make maximum use of other initiatives it is supporting to facilitate greater business investment in nutrition.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year
Lessons learned over the past year and the failure to procure an implementing agent for FSNP have shown that the originally envisaged approach to enabling and incentivising business investments in nutrition no longer represents VfM. However, the changes to programme outputs through the Business Case addendum and efforts to support business engagement through other DFID programmes will achieve better VfM overall.

Describe any changes this output, and any planned changes as a result of this review.
This output has been removed and its impact weighting adjusted to zero in agreement with the Head of HDD. A new output is being added to reflect the shifts set out in the Business Case addendum. This will be assessed for the first time in the next annual review as grant agreements have only just been signed.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
The key lesson from the year is that the rationale for the Food Systems for Nutrition Partnership no longer holds. Alternative approaches can be adopted through the SAN programme and through other DFID programmes to achieve the intended outcome and impact of this programme.
D: RISK

Overview of risk management
The programme risk is assessed as moderate with regards to ability to deliver on outputs. FSNP, the only component classified as ‘major risk’, did not move to implementation. COVID-19 has created a major external risk that will significantly impact ability to achieve outcomes and impact. Governments and businesses may prioritise other actions to respond to COVID-19 than investing in food systems and nutrition and because their resources to take action on nutrition will likely also decrease.

COVID-19 has already led to delays of some activities. Going forward, output targets and activities need to be adjusted to COVID-19 in order to keep risks at moderate level. SAN partners have been asked to actively monitor and pivot activities to maximise their influence on programme outcomes. These have been reflected in their work plans for 2020/21. The programme’s risk register was updated in April 2020 to reflect COVID-19 related risks.

In addition to COVID-19, SAN partners faced the following key risks and addressed them to varying degrees of success:

For the SUN CSN Secretariat, a key risk which materialised in 2019/20 has been its ability to deliver its work plan in the face of staffing gaps outside of CSN Secretariat’s control. As a result, a range of activities had to be delayed or could not be undertaken and its risk rating has been increased from moderate to major. Due to COVID-19, the risk of staffing gaps remains a potential challenge for the coming year – although for different reasons than seen in 2019/20. Additional risks include CSAs not securing a sustainable funding source and their demand for technical support outstripping CSN capacity and resources. Although DFID does manage a risk matrix for this component of the programme, the SUN CSN Secretariat only began to systematically record challenges and risks associated with escalated risks for country CSAs at the end of 2019. The Secretariat reports challenges as part of its joint donor quarterly report but until now does not have a standalone risk register. This will need to be addressed.

For the SUN Pooled Fund, the main risks identified were external factors that impeded delivery of planned activities (e.g. unfavourable political context), financial management (e.g. misuse of grant funds) and reputational risks to UNOPS if grant recipients don’t meet their deliverables. To mitigate, UNOPS has developed a robust monitoring framework. UNOPS documents and monitors risks using a Risk Response matrix. Although this matrix has not been routinely shared with the donors or as part of annual reporting, it is available on request. No risks emerged over the past year on the areas set out above. However, COVID-19 is hampering efforts by grant recipients to proceed with activities as planned. This is being monitored.

ATNI developed a risk management policy in 2019 which was adopted by the Board end 2019. It has strong monitoring and management mechanisms in place – using regular staff meetings, quarterly Board meetings and annual Audit and Risk Committee meetings to review and address risks. Among others, ATNI successfully mitigated the risk of duplication with the World Benchmarking Alliance by getting agreement on respective roles. It managed to keep companies and investors interested in engaging with it and expanded its impact on developing countries through its work in India, Nigeria and Bangladesh. It was able to diversify its funding sources. However, from next year onwards, maintaining sufficient levels of core funding will be a major risk as funding from coming to an end.

The Global Panel reports on any challenges in monthly meetings with DFID and also provides an updated internal risk register on a quarterly basis. Risk is discussed internally by the Secretariat’s Senior Management Team. Key risks have been, and continue into the next year:
- Policymakers are not interested in engaging with the Global Panel (e.g. in country level meetings) due to other priorities (this risk will increase due to the impact of Covid-19).
- Staff turnover and lack of absence cover further delays timelines and impacts the Global Panel’s ability to deliver – while new staff has since been hired, the risk persists and needs careful management.

E: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and DFID, notably on commercial and financial issues, and including consideration of VfM measures of economy and efficiency.
SUN CSN Secretariat
The SUN CSN Secretariat has delivered reasonably well over the past year but has faced several challenges in programme management. It is evident that it is working to improve this and the timeliness of the quarterly progress and financial reports submitted by the Secretariat has improved. Although the quality of reporting is good, further work is still needed to make sure that reports fully meet DFID’s needs.

The main costs for the Secretariat are personnel (37%), sub-grants to CSAs (26%), consultants (15%) and travel (10%). Save the Children applies a standard 11% cost recovery rate. This aligns with what was expected in the Business Case VfM assessment. The Secretariat has continued to consistently underspend compared to its planned budget for the year. This was due to gaps in staffing, delays in invoicing and, most recently impacts of COVID-19. The Secretariat has made progress more recently to align financial forecasts with its absorption capacity and has reduced underspend. The Secretariat has a relatively small operating budget and hence is inherently required to identify ways to ensure economy in its work.

The Secretariat has been less efficient than it could have been as result of staffing gaps. There is evidence that it is streamlining work to improve efficiency (as described under output 1) but this will need to be monitored this year, particularly as the impact of COVID-19 may require rapid shifts in priorities and workplan adjustments and create risks around efficiency.

SUN Pooled Fund
The Pooled Fund is well managed by UNOPS, with reports received on time and expenditures in line with forecasts. Economy remains assessed as moderate. The main costs in 2019 were grants, personnel and fees for hosting arrangements at UNOPS (7%). The latest financial report shows that during the past year, total expenditure amounted to USD $6,684,741: with 81.7% on grants, 9.7% on personnel, 0.2% on communication, 0.9% on travel, and 1.9% on locally managed direct costs. Costs per grant allocated are difficult to assess at this stage because payments are made in stages and some grantees have received top-up grants. The VfM metrics to assess economy will be reviewed and new indicators agreed before next annual review.

When setting up grants for CSAs, the issues encountered by UNOPS team included low absorption rates, poor documentation, and/or errors in financial reporting. These often resulted in delays in payment approval, which delayed activity implementation. UNOPS mitigated these risks by running webinars on M&E and grant management for all recipients at the start of their project, providing one-on-one monitoring support, adding optional reporting webinars, and notifying the Civil Society Network and SUN Movement Secretariat about the need for technical assistance to grant recipients.

Global Panel
The Global Panel underspent this year by 14% as a result of delays in timelines and delivery of outputs. In line with the requirements of the accountable grant agreement, the Global Panel consistently send detailed quarterly reports to DFID on progress, risks, finances, delivery chain map and assets. The quality of reports has improved compared to the previous year and the Panel Secretariat has taken DFID recommendations on board, including through a revised travel and expense policy agreed with DFID during the year. There are signs of improvements in making cost savings such as a 23% reduction in spend for the High-level Roundtable in Nepal. However, quarterly financial reports should reflect more consistently how cost savings are being made and provide more detailed information on how its travel and expense policy is being implemented.

At the business case stage, the overall budget and individual items, staff salaries and consulting rates were benchmarked against rates of comparable organisations and found reasonable. This has stayed the same. There are some concerns about using consultants for activities that DFID would expect to be done in-house e.g. note-taking, presentations and briefing packs. DFID expects the Global Panel to continue to strengthen their VfM strategy in consultation with DFID and to identify additional cost-savings periodically.

ATNI
The Access to Nutrition Foundation continues to demonstrate strong programme management capacity and ability to deliver VfM. It has consistently submitted quarterly reports, updates to its risk register and delivery chain map on time. In addition, it successfully completed outstanding actions on DFID’s Safeguarding Due Diligence Assessment. It has maintained efficiency by continuing to demonstrate adequate capacity to deliver, with efficient internal procedures and systems in place. At the business case stage, the overall budget and individual items, staff salaries and consulting rates were benchmarked against rates of comparable organisations and found reasonable. This has stayed the same.

SUN CSN
Date of last narrative financial report	15 April 2020
Date of last audited annual statement	May 2019
SUN Pooled Fund
Date of last narrative financial report	April 2020
Date of last audited annual statement	24 June 2019 – certified, not audited
ATNF
Date of last narrative financial report	May 2020
Date of last audited annual statement	June 2019
Global Panel
Date of last narrative financial report	April 2020
Date of last audited annual statement	September 2019