Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: AMPLIFY: Open Innovation for Development
Programme Value: £10.1 million		Review Date: August 2016
Programme Code: 203798-102	Start Date: Feb-14	End Date: Mar-18

Summary of Programme Performance
Year	2014	2015	2016
Programme Score	A	A
Risk Rating	Medium	Medium

Summary of progress and lessons learnt since last review

Amplify has made substantial progress in its third year. On a practical level, this year, Amplify has completed two challenges, one on urban resilience and one on agricultural innovation. As of August 2016, Amplify is supporting 26 partners in 15 countries, 21 of whom are actively prototyping or piloting their solution. Last year, Amplify had committed $130,000 and disbursed $70,000. As of August 2016, Amplify has now committed $1.6 million, disbursed $1 million, and is on track to bring that commitment up to $2.8 million over the next quarter. Previous Annual Reviews raised the risk that the programme was slow in disbursing grants and developing a clear strategy for managing grantees. Now, Amplify has dedicated personnel to portfolio management, and a clear and simple approach to coaching, monitoring and providing support to grantees (which is annexed to this review). The programme has enabled the partner, IDEO.org, to develop its capacity for managing and monitoring grantees and projects in a way few other Human-Centred Design focused consultancies currently do.

Broadly, the programme is hitting logframe targets, although the ‘reach’ of Amplify, in terms of number of beneficiaries, remains low, at approximately 12,000, with a target to hit 60,000 by February 2017. The programme inherently gives small grants to small projects, and is focused on experimenting with and understanding the value of Human-Centred Design in international development, as much as the basic reach of the programme. Nonetheless, this indicator remains important as a proxy for impact of Amplify’s grantees. Other output indicators are showing strong progress, to the extent that a recommendation of this Annual Review is to reconsider those indicators which now seem under-ambitious, in the flexible and adaptive spirit of the programme.

On a strategic level, logframe outputs and broader goals of the programme which are more focused on the value and influence of Human-Centred Design are harder to measure. A key recommendation of this Annual Review is that Amplify, in concert with an independent evaluator, find a stronger way to measure and capture the ‘value-added’ of Human-Centred Design Support – this will also supplement the ‘beneficiary reach’ of the programme as a measure of its overall value. Currently, 78% of Amplify grantees report that they have seen improved outcomes in their organisation's programming as a result of working with Amplify and 57% of grantees reported that Amplify contributed to them receiving increased funding or developing additional partnerships. Like most of the current measures within the programme of the value of Amplify and HCD, these figures are largely based on feedback surveys. Validating and verifying this positive feedback in a more structured way will be crucial in the second half of the programme.

A further goal of the programme is to influence other development organisations – both through smaller projects Amplify supports and larger organisations with whom Amplify partners or otherwise works. For the former, Amplify’s portfolio is now primarily made up of groups which sit within Amplify’s target ‘sweet spot’ – that is, locally-based organisations who have developed an idea based on their experience with users, with an annual budget in the range of USD 1million. The wider influence of Amplify’s work with these projects has been difficult to capture, and a key recommendation for the year ahead is to develop ways to report on and communicate insights gained from each challenge’s cohorts of grantees. In recent tests with a small DFID audience, short summaries of lessons learned and provocations developed based on work with grantees from each challenge have received a positive response and led to potential further discussions about influencing broader policy and programming decisions. A more developed communications strategy that is focused on results and insights arising from Amplify’s work, not just Amplify’s existence and approach, would be a good way to build on this initial response.

In terms of influence on bigger organisations – two major development organisations, BRAC and Rockefeller Foundation, have given clear feedback they will base their future strategy and, in one case, one of their own challenge funds, on an Amplify-influenced approach. This is a strong early indication of Amplify’s influence, and again, an external evaluator to capture more of this will helpful. To really build on its influence, Amplify should consider how and when to communicate insights gained from working with its cohorts of grantees to policy-makers and institutions as they make broader programming decisions. Positioning future challenges to tackle topics of emerging policy relevance, and possibly to focus on one or more specific regions or DFID country offices may be an important experiment to understand how insights from an Amplify challenge might influence the international development agenda, not just development methods. This is one suggested part of a broader strategy, which IDEO.org should consider, on the future of Amplify.

Key risks remain in the programme, not least exchange rate fluctuation following the UK’s EU referendum diminishing the value of the US dollar grant, and the need to capture and aggregate the broad impact of the programme as it enters its second half. Mitigating actions and recommendations in response to these risks are covered in the rest of this Review.

Summary of recommendations for the next year

Review logframe indicators where these now appear less relevant or under-ambitious. In particular, more ambition on output 1.2, making output 2.2 more relevant and meaningful, and a general review of output 3 indicators.
Owner: IDEO.org
Timeline: new logframe by March 2017

Experiment with communicating insights gained from Amplify challenges to contribute to policy and programming decisions, including by developing ‘insights reports’ for Challenge 2-5 by end 2016 and presenting these to at least three external organisations by end 2016 – in line with building a communication and influencing strategy around Amplify’s results and insights in key areas, not just communicating the existence and approach of the programme.
Owner: IDEO.org with DFID support
Timeline: Finalised and presented to at least 3 external organisations by end 2016; review Output 3 (c.f recommendation 2)

Recruit new external evaluation team to accelerate program learning.
In recruiting a new external evaluation team, it will be important to set up communication rhythms and an evaluation plan that is in line with the nimble and iterative Amplify design, but also allows for sufficient rigor in evaluating the program’s effectiveness.
Owner: DFID
Timeline: By the end of 2016

Cultivate relationships among portfolio organizations that increase connections and influence cross-sharing.
One of Amplify’s strongest assets is the portfolio of innovative and vibrant grantees that it continues to build with each Challenge. While meaningful connections have already been fostered between grantees, thus far it has been an informal process of introduction. Amplify aims to foster a culture of sharing across grantees, and will seek to put structures in place to do so during year 4.
Owner: IDEO.org
Timeline: 3 experiments in year 4

Provide explicit support to help grantees scale or replicate their solutions—either directly or via introductions to other technical assistance providers.
This should include partnering with UNHCR to adapt one Refugee Education solution for the Gambela context and at least one other concerted attempt.
Owner: IDEO.org
Timeline: At least 2 attempts in year 4

Experiment with new ways of measuring HCD support on grantees’ capabilities and behavior. Work on capturing the role of HCD in improving the impact of beneficiaries, with the goal of having clear, communicable examples from each challenge.
Many development organizations—including DFID—are experimenting with the assessment of organizational innovation capacity. Using Creative Difference (an IDEO-developed survey tool) and other methods, Amplify hopes to get a more complete sense of the organizational culture and attitudes of the winners of each challenge and understand how they may have changed over time. Additionally, hiring an external evaluator in line with government procurement processes will take several months. Prior to this, summarising and aggregating what the Amplify team can already show about the value of HCD in improving grantee impact is important. Showing the value that HCD adds to small projects is an important supplement to Amplify’s basic beneficiary-reach measure and Amplify will also continue to examine and prototype different ways to effectively monitor innovation and impact in the non-traditional environment in which the program sits.
Owner: IDEO.org
Timeline: Years 4-6

In recognition of the limited number of challenges left, refresh the partnerships strategy - to increase the likelihood of securing follow-on funding for grantees and increasing the influence of Amplify, while limiting the additional time and resources required from the Amplify programme team for securing partnerships.

Programme Management: Complete a financial spot check in line with DFID’s Programme Management Rules, and develop meaningful and relevant statements of expenditure to record programme outputs in relation to spending – discussions on both these activities have now begun with the hiring of a new financial manager on the Amplify team - the DFID team have noted that staff changes have made both these goals challenging in the past, and dedicated personnel working on them both is a promising start.
Owner: IDEO.og
Timeline: by end 2016

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/4048206.odt
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/4114178.xlsx

Outline of the programme

DFID’s Amplify program will provide £10.1m over five years to IDEO.org through an accountable grant to test, prototype and roll-out a new model for addressing development challenges. The program is tackling ten development challenges over 5 years, with $500,000 available for funding the strongest ideas to emerge from each challenge. Amplify anticipates funding five ideas per Challenge to varying degrees based on the strengths and needs of each organization and idea.
The business case for the program was approved by the Secretary of State in July 2013 and the first challenge was launched in late 2013.  An external evaluation management unit is currently being recruited to replace the initial evaluation team led by IMC. This unit will conduct a separate, ongoing evaluation of the program over the course of the program term.
Expected results: A direct result of the program is to design, prototype and roll-out a new model for distributing aid that makes small initial investments and provides design support to organizations to test and iterate on new ideas. Amplify leverages input from a broad range of people and organizations from around the globe to address challenges faced by poor communities in the developing world. Funding for winners focuses specifically on DFID’s 28 priority countries. Each Challenge is run on the OpenIDEO online platform where participants share innovative ideas, and collaborate to improve upon contributions. IDEO.org’s human centered design tools and processes are shared to encourage iteration and growth of each idea. With this new model, Amplify is able to identify replicable and scalable solutions to pressing development challenges rooted in human needs.
In April 2015 the Amplify team met with counterparts at DFID’s Innovation Hub to reexamine the goals of the program. While the overall objective remains the same, Amplify’s Theory of Change was refined to highlight a prioritization of goals after the first two years.
Impact: The desired impact of Amplify is to improve the lives of the poor through replicable, scalable solutions tailored to their needs.
Outcome: Amplify aims to do this by creating a new model for solving development challenges that leverages collaboration and human-centered design to find and support implementation of high-quality solutions rooted in human insights.

If done correctly, this model will:

- Make small initial investments and provide design support to help organizations test and iterate;
- Facilitate pathways for solutions to scale and/or spread;
- Respond directly to human needs and helps organizations uncover them;
- Invest in solutions outside of DFID’s traditional funding pool;
- Leverage outside expertise to improve ideas;
- Encourage collaboration to improve ideas;
- Provide an application process that is easier and more accessible than the traditional funding model;
- Be completely open to anyone interested in participating.

Reaching this outcome will mean that Amplify-funded organizations are effectively using human-centered design to improve their work. The program aims to see growing interest in Amplify’s solutions from traditional and non-traditional partners in the international development and social good space. Finally, with this cultivated network actively engaged, the program looks to create a rich marketplace for learning and networking across the development sector.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

Amplify has made strong progress against logframe goals this year, and has in several cases exceeded indicator targets. It is broadly on track to achieve its overall outcome goal - leveraging collaboration and human-centered design to find and support implementation of high-quality solutions rooted in human insights – as far as can be measured at this stage in the programme and within the logframe structure.

As a result the overall output grade for this year is: A+

The programme has overcome previous concerns about delays, accelerating its disbursement of grants and increasing its portfolio rapidly to 21 projects. Amplify has also improved its focus on and capturing of its broader influence, to the extent that the team can now point to two major development organisations already adopting elements of Amplify’s approach in their own work, and explicitly attributing this to the programme.

The programme has secured partnerships for some challenges, a strategy which was developed to increase the potential follow-on funding available for grantees, but has also experimented with cultivating lighter-touch strategic partnerships with several organisations per challenge, instead of focusing on a single partner per challenge. It remains early to measure the results of these different approaches and their relative cost/benefit. In the remaining years of the programme, this Review recommends refreshing the partnerships strategy to reflect whichever approach provides the most realistic chance of securing additional funding for grantees and influence for the programme in relation to the time and resources required for partnerships to work.

Inherent challenges still remain in terms of the cost-effectiveness of the programme – the challenge process and design support is inherently expensive and the grants disbursed and projects supported are small. This is a structural, rather than a performance-related, issue with the programme, and is to some extent a condition of an experimental and innovative approach. Nonetheless it does increase the need for Amplify to demonstrate the efficacy and impact of Human-Centred Design and Amplify methods in general, as well as ensure grantees can show improved outcomes, secure follow-on funding and develop strategies for scaling up. Recommendations on cost savings are included in the ‘Finance’ section of this review. Otherwise, Amplify is overall on track, and recommendations for this Annual Review focus on aggregating and communicating the value and impact of HCD within the Amplify programme – whether through DFID bringing in external expertise to verify programme results, or through the Amplify team developing reports which capture insights gained from the Amplify process for each challenge and communicating these widely.

Key lessons

In each year of the Amplify program, a number of lessons arise from iteration and synthesis that help to ensure the following year is as focused and efficient as possible. In year three, learnings emerged in a number of different categories including insights on the structure of the challenges, highlighting ways to maximize the benefit of funding to our grantees, and strengthening the relationships between Amplify and its grantees.

Flexibility (in both funding and technical assistance) is a key ingredient for catalyzing grantee innovation: In supporting early-stage innovations across DFID’s priority countries, it has become increasingly apparent that a one-size-fits-all model of funding and support is limiting. By providing a more bespoke package of support that is not traditionally available to small-to-midsize organizations, IDEO.org has been able to support a number of grantees in overcoming the common hurdles of early implementaiton.

For example, i-Act, one of the Refugee Education Challenge winners, is working primarily in Darfuri refugee camps in Chad, a setting with limited connectivity and unpredictable conditions where outside designers are not advised to travel. In order to support i-Act in implementing their in-home preschool pilot, our team set up a remote project plan and used a private, internal blog (built on Tumblr) to work collaboratively despite connectivity challenges. This allowed the IDEO.org team the information we needed to provide deep design support to a project half a world away, and provided the i-Act team with a manageable and transparent view into the design process. KTJ, i-Act’s co-founder, remarked that the design team’s flexibility in leveraging non-traditional communication tools and ways of working throughout the process was a significant improvement to past offers of consulting and coaching they have received from other partners, which often neglects to accommodate for the realities of working in such extreme environments. By designing for i-Act’s unique needs throughout the process, Amplify was able to support them to prototype and learn quickly, something UNHCR has identified as being a key challenge of many refugee-focused organizations.

While this bespoke model of support is producing exciting results, one key question moving forward will be how DFID and other funders might incorporate similar practices in a scalable and cost-effective way (beyond Amplify).

Enhanced guidance and feedback in the OpenIDEO challenge improved the process for both contributors and the Amplify team. Amplify continues to work to improve the experience of OpenIDEO challenges for contributors, incorporating insights from previous challenges. During Challenge 5, the online process was reconfigured in order to offer more support and guidance to the evolution of ideas throughout the challenge period. This meant introducing three new, more-targeted phases: Beneficiary Feedback, Expert Feedback, and Improve. In Beneficiary Feedback, contributors were given experience maps and other human-centered design tools to help them gather feedback on their design so far from real users in their community.

Additionally, Amplify sought to engage experts in a more robust way throughout the process by giving them dedicated time to review the ideas and ask targeted questions. In the ‘Improve’ phase of the challenge, contributors were invited to synthesize the beneficiary and expert feedback to further refine their idea. These strategic shifts in challenge structure created a more mature set of ideas, helped Amplify make better portfolio decisions, and added real value to challenge participants—even those who did not win. An example of the beneficial impact of the challenge process can be seen in a video developed by Farm.ink (an eventual winner), where they documented the process and articulated their thoughtful evolution of the idea at each stage.

Clear communication is a crucial counterpoint to the ambiguity of the innovation process: Design innovation involves prototyping, iteration, and rapid failure—new and uncomfortable processes for many organizations. Amplify has received feedback through the evaluation case studies as well as our own feedback mechanisms that some early grantees—most notably Challenge 1 winner Kidogo—had felt uneasy about the prototyping and design process. Over the course of the last few challenges, Amplify has sought to mitigate this unease by communicating milestones, timelines, and expectations with grantees from the outset. In year three, Amplify made several shifts on this front, which resulted in better scaffolding for grantees to experiment and test new concepts with ease:
- Added design bootcamps at the beginning of the Amplify process: Bootcamp provides a dedicated time to get to know the grantees, come to a shared mindset around HCD, give the grantees a sense of what it will feel like to work with IDEO.org, and build relationships that sustain positive collaboration throughout the challenging and uncertain early implementation phase. Amplify found that design bootcamp was a great moment for setting expectations, and produced more trust and honesty about roadblocks and failure.
- Defined levels and types of design support earlier: By communicating openly with grantees about the differing levels of design support and the ways IDEO.org may work with them throughout their prototyping and piloting phases, grantees were much more comfortable with the flexible process that followed. Amplify was better able to design a journey with predictable milestones, and then provide additional design support at key moments.
  - In Amplify’s collaboration with Challenge 3 winner, iAct, the level of transparency and expectations of design support were key to the success of the work. iAct’s Chief Operation Officer, Katie-Jay Scott said, “Every week, our iACT and Amplify teams spent at least an hour (often times a bit more because of the contagious energy), pinging questions and answers between us. There was at least one email per week and a blog post that also needed detailed responses. Because the process was transparent and our iACT team was included in their synthesizing of our information, I was confident that every minute spent on the video calls, providing feedback on the blog, and answering an email was truly contributing to the design process.”

Challenge-specific partnerships are important to grantee sustainability, but they can come in different forms: As the Amplify program matures, funding partner engagement has been explored in a number of different ways. For Challenge 4, the Rockefeller Foundation’s Global Resilience Partnership (and by extension, USAID and SIDA) signed on as formal challenge partners. This brought new resources into the program to the tune of $1M in funding—$300,000 to expand the portfolio to eight organizations, $400,000 in committed scale-up funding (post-Amplify) for successful solutions, and the balance in additional design support to build the capacity of the expanded portfolio. While this partnership afforded Amplify the opportunity to broaden its portfolio, both geographically and in numbers, it also meant increased demands on stewardship and staff support. In Challenge 5, Amplify experimented with a more flexible partnership structure—inviting a number of sector-specific organizations with smallholder agriculture portfolios (Skoll, Gates, Acumen, and the Global Fund for Women) to follow the challenge and connect at key moments. These organizations helped provide input to scope the challenge brief, participated in expert feedback, and will be invited to follow along with the grantees’ progress from our Amplify bootcamp in Nairobi through the 18-month experimentation and pilot phase. We were confident in testing this approach after discovering through our own monitoring and evaluation that many of our grantees were already receiving increased funding opportunities catalyzed by Amplify, and getting feedback from many foundations that struggle with pipeline development. For example, the Portfolio Lead for the Gates Foundation’s Agricultural work reached out to Amplify to learn more about Challenge 5 and get a copy of the top ~30 list. “These are exactly the type of organizations we want to keep an eye on over the next few years,” she said.

By testing multiple levels of partnership, the Amplify team seeks to understand how best to cultivate post-Amplify funding opportunities for our portfolio of grantees, and the activities needed to support each type of partnership.

Has the logframe been updated since the last review?
In May 2016, the logframe was jointly reviewed by IDEO.org and DFID, and an additional output indicator was added to capture the influence that Amplify is having on other donors, funders, and implementers to explore or adopt some of Amplify’s approaches. Output Indicator 3.3 now reads as follows: Amplify influences and communicates with other donors, funders, and implementers to adopt or learn from elements of the Amplify ‘model’ (use of HCD, use of open innovation marketplace approaches to procurement, collaborative flexible approaches to problem-solving). This indicator will be measured through Insights reports, which will capture feedback from donors or implementers, as well as through feedback from challenge partners which demonstrates uptake of Amplify’s approaches.

## C: DETAILED OUTPUT SCORING (1 page per output)

IMPACT
Output Title	Impact - Improve the lives of the poor through replicable, scalable solutions tailored to their needs
Output number per LF			Output Score
Risk:		Low/Medium/High	Impact weighting (%):
Risk revised since last AR?		Y/N	Impact weighting % revised since last AR?	Y/N

IDEO.org to provide info in the below table (use one table per output)

Indicator(s)	Milestones	Progress
Number of beneficiaries served by Amplify-funded solutions	60k lives impacted (Feb - 17) 200k lives impacted (Aug - 18)	12,185 lives impacted
Evidence of indirect benefit to target beneficiary populations through Amplify influence on organizations	25% of grantees and non-grantees who participated in Amplify report better outcomes or increased funding post-challenge based on Amplify influence (Feb - 17) / 50% of grantees and non-grantees who participated in Amplify report better outcomes or increased funding post-challenge based on Amplify influence (Aug - 18)	78% of grantees reported improved outcomes in their organization’s work (outside of their Amplify project) as a result of working with Amplify; 61% of grantees reported that Amplify contributed to them receiving increased funding or developing additional partnerships.

- The number of beneficiaries served has increased from 2,176 to 12,185 between March 2016 and July 2016. This is largely a result of two cohorts of challenge (Challenge 2 and 3) winners transitioning from prototyping into full-scale piloting during this time period. We anticipate significant growth in the next several months, as grantees with large catchment areas roll-out their pilots (Possible and Atma).
- Amplify looks forward to collaborating with the new team of external evaluators to better understand how to capture and measure impact in a way that feels relevant, rigorous, and representative of the program’s goals. The impact of innovation, especially in its early stages, is notoriously difficult to grasp, so this will be an ongoing process for the Amplify program.

OUTCOME
Output Title	Outcome - A new model for solving poverty-related issues that leverages collaboration and human-centered design to find and support implementation of high-quality solutions rooted in human insights
Output number per LF			Output Score
Risk:		Low/Medium/High	Impact weighting (%):
Risk revised since last AR?		Y/N	Impact weighting % revised since last AR?	Y/N

IDEO.org to provide info in the below table (use one table per output)

Indicator(s)	Milestones	Progress
Number of solutions funded and receiving design support from Amplify	30 organizations through Challenge 6 (Feb - 17) / 50 organizations through Challenge 10 (Aug - 18)	As of July 2016, Amplify is supporting 26 grantees, with 13 currently implementing pilots, 8 transitioning from prototyping to piloting, and 5 having just been selected and heading into design bootcamp at the end of August.
Number of beneficiaries served by Amplify-funded solutions	60k lives impacted (Feb - 17) / 200k lives impacted (Aug - 18)	12,185 lives impacted

In year 3, Amplify primarily supported 21 grantees, adding five more to the portfolio at the end of June through selection of winners for Challenge 5. Of the 21 grantees who are in the prototyping or pilot stages, seven have received design support in the form of a dedicated design project (SHOFCO, Kidogo, Ayzh, Possible Health, We Love Reading, Finn Church Aid, and Atma), while one received a short design sprint (i-Act). Design projects are scheduled with two other Challenge 4 grantees for the coming months (Q3-Q4 2016).

OUTPUT 1
Output Title	Output 1: Effective use of human-centered design by grantee organizations to improve their solutions
Output number per LF		1	Output Score	A+
Risk:		High	Impact weighting (%):	35%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

IDEO.org to provide info in the below table (use one table per output)

Indicator(s)	Milestones	Progress
1.1 Number of grantees who have received design support to prototype their solutions.	All winners to date have created at least one prototyping plan with the Amplify design team (Feb - 17) / All winners to date have tested at least one prototype with target users (Aug - 18)	21 winners have created prototyping plans to date, and 5 additional winners have been selected and will be creating prototyping plans during their design bootcamp at the end of August.
1.2 Percentage of grantee organizations that have used end-user feedback to evolve their solution	30% of organizations surveyed can identify a change in their model based on user feedback (Feb - 17) / 75% of organizations surveyed can identify a change made to their model based on user feedback (Aug - 18)	94% of organizations surveyed have identified an adaptation made on their idea as a result of feedback from customers or beneficiaries (20 out of 21 grantees submitted responses to the impact survey)

Output 1.1:
Please see description of design support and funded grantees under the Outcome indicator section, above.

Output 1.2:
Based on results from a partner survey sent out in July 2016, 90% of responding organizations (19 of 21 partners) have made at least one adaptation to their idea based on feedback from their end-users. This demonstrates that Amplify’s grantees are taking up HCD principles and implementing them effectively, becoming more user-centric. Most are also reporting positive results. For example, Challenge 2 grantee Village HopeCore identified one specific way that end-user feedback shifted their work: “The program has changed to fit the desires of the mothers and children more directly...the health hotline also has changed its name after user feedback indicated people feared to call a ‘hotline.”

OUTPUT 2
Output Title	Output 2: Increased interest and engagement of traditional and nontraditional partners in the Amplify program and solutions it generates.
Output number per LF		2	Output Score	A+
Risk:		Medium	Impact weighting (%):	35%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

IDEO.org to provide info in the below table (use one table per output)

Indicator(s)	Milestones	Progress
2.1 Shared sponsorship of Amplify challenges beyond initial DFID funding	2 challenges between 1-5 receive sponsorship which provides promotional and/or financial support / 6 challenges between 1-10 receive sponsorship which provides promotional and/or financial support	Partnered with UNHCR, UNICEF, and DFID’s HIEP to run Challenge 3 on refugee education; partnered with the Rockefeller Foundation (and USAID/SIDA) to run Challenge 4 on urban resilience. / 4 organisations partnered with between 1-5
2.2 Follow-up funding or resources secured for Amplify-funded solutions after their Amplify grant support period ends	75% of graduated Amplify organizations have had discussions with other partners for continued support (Feb 17) / 75% of graduated Amplify organizations have had discussions with other partners for continued support, and 25% have secured it (Aug 18)	Currently, 61% of grantees reported that Amplify contributed to them receiving increased funding or developing additional partnerships.
2.3 Solutions surfaced in Amplify challenges are tested, piloted, or implemented by organizations other than those originally submitted them to the challenge	1 solution that originated on the platform has been implemented via non-Amplify support (Feb 17) / 10 solutions that originated on the platform have been implemented via non-Amplify support (Aug 18)	We Love Reading (Taghyeer) and the Women for Human Rights/NYU have each had discussions and made progress with outside organizations who want to replicate their work in different spaces.

IDEO.org to write any notes relating to each output if additional info required under each table.
Output 2.1:
Amplify successfully achieved the first milestone for output 2.1, and continues to explore different mechanisms for partnerships that adds value to the program and grantees without overburdening the team. The partnerships in Year 3 with UNHCR, UNICEF, and Rockefeller Foundation provided numerous valuable insights, as discussed above.

Output 2.2:
- As the challenges progress, the Amplify team continues to receive positive feedback from grantees about the opportunities and discussions for complementary and follow-on funding that have resulted from their involvement with the Amplify program:
  - Village HopeCore received two large grants after beginning to work with Amplify from a donor who had previously provided a much lower level of support but gained confidence after Amplify’s recognition. Additionally, they are now participating in the GE healthyimagination program after a referral from Amplify.
  - Ayzh leveraged Amplify funding to unlock committed investment funding from Grand Challenges Canada, which came out to $262,000 USD as a 1:1 match ($100,000 USD in-kind from IDEO.org and $162,000 USD in cash)
  - While a direct correlation cannot be drawn between Amplify and additional funding received, Kidogo received grants of $80,000 and $35,000 to build on their Amplify work.
  - Recycler recently won a grant of $150,000 USD from the African Enterprise Challenge Fund to further develop an aspect of their Amplify project.

Output 2.3:
- Amplify grantees have shown great potential for developing replicable, scalable ideas, as evidenced by a few instances of early interest from organizations seeking to adopt models of Amplify grantees.
  - Taghyeer (We Love Reading) has partnered with the Norwegian Refugee Council to pilot their curriculum in several refugee camps in Jordan. They are also anticipating a partnership with an organization called Ghiras in Turkey to roll out their trainings in Turkish refugee camps.
  - The partnership of Women for Human Rights and New York University was approached by an NGO in Mumbai who wanted to use their approach to develop a program in a slum in Mumbai. They have shared their materials with the organization and are waiting to see if a full partnership develops.

OUTPUT 3
Output Title	Output 3: A rich marketplace for learning and networking across the development sector
Output number per LF		3	Output Score	A++
Risk:		Medium	Impact weighting (%):	30%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

IDEO.org to provide info in the below table (use one table per output)

Indicator(s)	Milestones	Progress
3.1 Amplify challenge participants report improved programmatic outcomes based on incorporating tools or strategies gained through Amplify participation	25% of respondents to Amplify post-Challenge survey report improved programmatic approach or outcomes by 6 months after Challenge ends (Feb 17) / 50% of respondents to Amplify post-Challenge survey report improved programmatic approach or outcomes by 6 months after Challenge ends (Aug 18)	78% of Amplify grantees report that they have seen improved outcomes in other aspects of their organization's programming (outside of Amplify project) as a result of working with Amplify. The Amplify program is exploring how to capture this information from a broader set of challenge participants in time for the Feb 17 interim indicator.
3.2 New networks and connections formed through Amplify that influence participating organizations; thinking and behavior	10% of participants have developed meaningful conversations with other participants via online comments (measured by comments with >3 exchanges) - (Feb 17) / 25% of participants have developed meaningful conversations with other participants via online comments (measured by comments with >3 exchanges) - (Aug 18)	61% of Amplify winners surveyed report having connected with someone they met through Amplify (challenge participants, other grantees) to exchange information outside of the Amplify platforms. / Amplify recommends amending this indicator, as commenting functionality on the platform does not seem to be a good representation of the output goals. This is a discussion we will have with the new evaluation contractors.
3.3 Amplify influences and communicates with other donors, funders, and implementers to adopt or learn from elements of the Amplify ‘model’ (use of HCD, use of open innovation marketplace approaches to procurement, collaborative flexible approaches to problem solving)	Amplify produces insights report on each cohort of grantees from Challenge 2 onwards - feedback from minimum 3 donors (including DFID), funders or implementers showing positive uptake of lessons / 2 Amplify Challenge partners report the uptake of one of: HCD, open innovation platforms, prototyping in programme development	Insights reports submitted to DFID in July 2016; Amplify has already seen two instances of program elements being replicated by other funders—Rockefeller Foundation’s Global Resilience Partnership and BRAC are both incorporating both HCD and open innovation into upcoming challenges Additionally, 94% of current grantees have reported incorporating HCD principles and tools into their work.

Output 3.1:
Since the design bootcamp, Village HopeCore has conducted three internal workshops using IDEO.org’s materials and pocket handbooks as tools. They noted that, “staff are more inclined to participate in brainstorming sessions and offer ideas that seem outside of the box. We have applied feedback sessions to other programs within HopeCore, staff voice opinions more widely, and there is a great focus on user feedback.”

Output 3.2:
- In the OpenIDEO submission process, contributors are encouraged to engage with one another in order to refine their ideas. During Challenge 5, Amplify saw numerous examples of contributors collaborating in the comments section on OpenIDEO and making connections that they continued outside of the online platform.
  - Using the Challenge 5 winners as a sample, Amplify examined the amount and type of collaboration in the OpenIDEO platform. Each idea received between 11 and 105 comments, with a total of 241 comments amongst all five winning submissions. Moreover, two of the five winners (SimGas and Herb Nepal) used the OpenIDEO comment section to host online polls to gather peer feedback about certain aspects of their products. Additionally, Farm.ink received a volunteer inquiry via comments as well as connecting with an entrepreneur in Myanmar who could be a potential collaborator in the future. These examples demonstrate how the OpenIDEO platform offers different ways for people and organizations to connect and collaborate in an organic way beyond the scope of Amplify.
  - Challenge 3 winners YARID and Finn Church Aid collaborated after bootcamp to work together on classroom management tools and techniques that may be applicable in each of the settings in which they are working.
  - Challenge 4 winner Kounkuey Design Initiative reported that they have connected directly on other initiatives with at least two of the other winners and expect to work with others in the future.

Output 3.3:
- As the newest addition to the logframe, this indicator provides an unprecedented look at how Amplify is secondarily affecting the international aid sector. While Amplify still represents a very non-traditional approach, early results demonstrate that aspects of the program are intriguing and seem promising to other actors in the space.
  - BRAC is in the process of organizing a five-year, five-challenge Urban Innovation Challenge series to foster innovative approaches of tackling urban issues beginning in September 2016. They intend to develop a process to gather ideas from a range of individuals and organizations, select two to three ideas to support through human centered design, implement them in the field and develop an appropriate mechanism to turn them into business solutions that will eventually run sustainably on their own. BRAC has reached out to IDEO.org to explore ways to partner or to serve on the advisory committee. Discussions are ongoing, but at a minimum, BRAC intends to use IDEO.org open source materials such as the Design Kit, and to engage IDEO.org for strategic guidance and grantee selection support.
  - Rockefeller Foundation and its partners at the Global Resilience Partnership are exploring elements of their global innovation challenges that can be modeled off of their Amplify experience, including the use of human-centered design tools. The Urban Resilience Challenge received more diverse and early-stage submissions than they normally see, especially as it relates to a nearly identical (in topic) challenge they ran in the months leading up to the Amplify/Rockefeller collaboration.
  - In addition to these formal processes, YARID—a Challenge 3 grantee based in Uganda—facilitated a human-centered design workshop using IDEO.org curriculum tools at a UNHCR conference in Kampala for practitioners in the humanitarian field.

Key Points

The above summary of logframe outputs indicates the programme is in a strong position and has made progress, but given the extent to which some of the target indicators have been massively exceeded, and some no longer seem relevant, this Review recommends refreshing the logframe this year.

It is difficult in the structure of a logframe to capture more nebulous concepts like ‘influence’ as well as the impact of design support on both grantee organisations and the sector more broadly, but any review of the logframe should focus on developing relevant and meaningful indicators as far as possible on this topic.

Where output targets relate to Amplify securing partnerships, this was always in service of securing further funding, growth and influence for both Amplify and its grantees. If the partnerships strategy as currently conceived is not doing this efficiently, then a review makes sense, and will affect some of the logframe targets on this topic.

Specific outputs recommended for review have been highlighted in the ‘Recommendations’ section of this review.

Summary of responses to issues raised in previous annual reviews (where relevant)

Recommendation: Level of activities implemented is extensive, but the amount of money distributed is low. Increase amount of money disbursed per year in order to spend the grant funds in a timely manner.
Response: During the past year, Amplify has accelerated the number and amount of commitments and disbursements significantly, with the dollar amount committed now nearing $2.5 million. This increase reflects the fact that delays in challenges 1 and 2 that had pushed back deployment of funds have since moved forward, and winners are now well into their piloting phases along with the winners from Challenge 3. In accordance with feedback from the previous annual review, Amplify also worked to reduce the cost of program operations and convenings in order to invest more resources towards technical assistance for grantees. See full list of current grantees in Annex 3.

Recommendation: Increase the proportion of human resources allocated towards design support by hiring additional designers, so that organizations are properly equipped to scale or spread their solutions after their incubation period with Amplify.
Response: Throughout year 3, Amplify has shifted its staffing structure to include five full-time designers, which allows for more consistent support to the entire Amplify portfolio. The program also continues to benefit from strategic use of IDEO designers at-cost, which provides flexibility for the program to accommodate ebbs and flows in support needs across challenges without relying on high-priced contractors.

Recommendation: Build challenge-specific partnerships that can influence the success or scale of Amplify-funded solutions, but carefully scope terms of each partnership to ensure the relationship creates impact and does not overly deplete team capacity.
Response: Two key approaches tested in Year 3, as captured in Key Lessons section.

Recommendation: Reconfigure the structure (phases) of the online challenge process to encourage more human-centered solutions and better incorporate expert feedback.
Response: Accomplished in year 3, as captured in Key Lessons section.

Recommendation: Develop tailored messaging for challenges that will attract and inspire participation from the type of organizations best positioned to benefit from Amplify support.
Response: For challenges 4 and 5, we experimented with a new landing page aimed at better targeting participation by organizations of the type best positioned to benefit from Amplify. This landing page includes a few key features: specific evaluation criteria for each phase, more definition of design support, case studies of past winners, and an “e-mail us” feature. In challenges 4 and 5, 57% and 64% (respectively) of submissions received were from the type of organizations in our Amplify sweet-spot (community-based organizations off of DFID’s traditional funding radar, which have more than 1 year of implementation experience locally and the organizational capacity to bring a new offering to life).

Recommendation: Invite each new batch of grantees to a “design bootcamp,” allowing the Amplify team to plan and tailor each organization’s funding and design support in a cost-effective way.
Response: Human-Centered Design bootcamps were held in year 3 for all grantees from challenges 3 and 4 in East Africa.

Recommendation: Strengthen the data collected from grantees to show impact and disaggregate numbers of beneficiaries by gender.
See section H for current monitoring and impact measurement practices, which were revised and improved based on feedback in previous reports. We are currently not equipped across all partners to disaggregate by gender, and seek guidance from the to-be-hired evaluation unit to advise how best to capture this data, given the diversity (in content and organizational capacity) among our grantees.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

Grants: This year, Amplify massively accelerated the deployment of funds from a total of $130,472 committed funds in Year 2 to $1,469,492 ($1,599,963 cumulatively) in Year 3. With the current Amplify budget (ratified in the early part of Year 3), Grants will represent ⅓ of the program’s total spend throughout the lifecycle of the program.

Design Support: Design support (technical assistance provided by IDEO.org to support grantees in implementing their challenge-winning solutions, is also a significant portion of the budget. At a minimum, this affords all grantees a four-day, immersive bootcamp experience and regular, remote coaching sessions over Skype (monthly on average) with IDEO.org designers. At the highest end of support, this also includes three months of dedicated design consulting. The funding for these more robust design support activities was largely reallocated in a 2015 re-budget of the program from pre-challenge convenings and other program management activities to increase the program’s impact and ensure a greater proportion of funds was spent on direct support of portfolio organizations’ innovations. In the initial scope of Amplify, the budget included 14 weeks of deep design support. The current iteration of the program includes 2, 12-week projects per challenge, plus the capacity for lighter-touch support and bootcamps throughout the year. This allows the programme to react to and support grantee needs in a much more holistic way.

Hosting online challenges: IDEO.org is examining ways to reduce the platform costs for hosting Amplify challenges, as this has been a major expenditure over the first three years of the project. Amplify has partnered with OpenIDEO to host and manage the past five challenges, and discussions between IDEO.org, OpenIDEO, and DFID are ongoing to determine how we might reduce the cost of the online submission process, which comprises 3-6 months of the two-year challenge cycle.

VfM performance compared to the original VfM proposition in the business case
This program continues to test new, emergent approaches to persistent challenges and then looks to ascertain the best ways to achieve more effective and more cost-efficient innovations for communities in developing countries. IDEO.org continues to provide value for money because it operates as a ‘lean start-up’ non-profit organization. Amplify Challenges now utilize the full-time design team staffed to Amplify, rather than relying on design talent from IDEO, though the program will continue to use IDEO talent on an as-needed basis.

The guided online challenge process provides valuable insight for many (if not all) shortlisted ideas—leveraging the cost of hosting an online submission process to support the growth of many nascent innovations (beyond those in the final portfolio of five). The online selection process also leverages the time and expertise of high-value subject matter experts who provide their input to ideas directly pro bono. This is of great value to small-to-medium-sized organizations, who may not have the resources to attend international conferences or other venues where they interact with international experts. In a post-challenge survey answered by 37 organizations after the winners were selected for Challenge 5, eight organizations identified the expert feedback phase as the most valuable part of participating in the Amplify challenge.

Additionally, Amplify has continued to strengthen the cohort-building element of the program, which amplifies the impact of design support by connecting grantees to each other to share lessons and support during the notoriously challenging innovation process.

Assessment of whether the programme continues to represent value for money

The items below were articulated in the business case:

Cost of running each challenge and the potential for making savings: Amplify has experimented with various ways to run each Challenge in an attempt to increase efficiency and make program savings. With each iteration the program has improved both value for money and the output of the activity.

Engagement of new actors from one challenge to the next: Amplify puts effort towards identifying organisations in the target area, and encouraging them to participate I the Challenge. While the hope is that many organisations will return to the platform for future Challenges, there are others that will be limited by the Challenge topic.

Retention of new actors within the challenge community: Amplify is conscious to encourage lasting engagement both online and offline, through strategic outreach to past Challenge participants, and to organisations in its wider network. Amplify is cultivating a network of like-minded funders and grant-making organisations whose portfolios align with the program’s goals, both to connect grantees to future support and to identify promising community-level organisations to participate in Amplify Challenges. The goal is to bring past actors back to the Challenge at the right moments.

Quality of financial management

The Amplify program has continued to make progress in delivering strong financial management.

To date the programme has spent £3,771,708.80 and we have seen improvements in financial forecasting since last year. Additionally, it has been good to see an increase in spending on grants compared with last year’s annual budget. Overall, however, the size of the grants and the cost of challenges and design support does make the budget look unbalanced – the cost of the process versus the size of grants given out is something we will continue to review and consider options for mitigating this.

Exchange Rate fluctuations:
An ongoing considerable challenge for Amplify has been loss of funds due to exchange rate fluctuations.

DFID payments to the Amplify programme were always made in sterling, as part of the terms in the accountable grant. Throughout the year ‘15-16 Amplify claimed they were experiencing exchange rate losses due to payments made in sterling and was a cause for concern for them. This was due to changes in currency rates due to timing differences between the payment requests and when the invoices were paid to them, in particular on one instance whereby the payment request they sent us in GBP in Sept (converted at the Sept rate) was not paid until December.

As a result, the SRO, the programme team and EPIC’s Finance analyst worked collaboratively and sought guidance from the relevant teams (i.e.: FCPD, accounts payable etc.) to assess the impact on the Amplify programme and to come up with a solution.

In order for DFID to understand the impact of the losses, EPIC’s finance analyst calculated and analysed all DFID payments made to Amplify, going back to the start of the programme and compared the amount DFID paid in GBP against how much was received in USD when converted using historic average conversion rates found on Oanda website. These calculations were then reconciled with the partner’s losses calculations and these were in line with the amount of losses which they had claimed.

To address the issue the following was agreed:
· The Smart rules strictly states that all commitments are to be made in sterling. It was clear from the advice received from FCPD that DFID does not carry any exchange rate risks and this hit is taken by the partner, in the same way they would gain if the exchange rate was in their favour. (and DFID would not request the additional gains back part way through the programme).
· DFID kept the payment request and the reporting in Sterling, (in line with smart rules), however the payment was changed to USD based on a sterling request, which was a preferable option for the partner. (this was fine to do as guidance was sought prior to this and it was agreed by the accounts payable team)
· Amplify would detail on their financial statement the extent of the loss/ gain at each reporting period which would then help DFID have an open and transparent communication with them on the viability of their cash flow and identify if it is a serious issue that would jeopardise completion of the objectives.
· If the losses were a serious issue and would jeopardise the completion of objectives than Amplify could claim the corresponding amounts from the grant total to cover them, especially if they were having serious cash-flow problems, or to look at other mitigation strategies.

Disbursement requests:
Amplify continues to submit timely financial reporting and disbursement requests.

While forecasting has improved since Year 1, this is still an area that requires some attention and was discussed at a recent IDEO.org/DFID meeting on financial progress.

At this meeting it was agreed that:
 - Amplify will flag delays or accelerations in spend more frequently, especially as it relates to sub-grants, which have been the largest driver of variance to date
- Amplify will add notes in each forecast flagging key areas of risk for over/underspend
- Amplify will add in variance analysis in future quarterly requests, which will be delivered in a consistent format
- DFID will allow a 4-week gap between end of quarter and submission of request for funds to allow for more accurate reporting

Recommendation: Amplify will also propose a new structure for forecasting that aligns with IDEO.org general ledger and provides clarity to DFID Programme Management team as to how program activities relate to spend

Annual Audit:
This year IDEO.org have recently appointed a new Director of Finance who joins the team having had 10 years experience in not-for-profit finance. There was a gap between the previous Director of Finance’s departure and the new Director of Finance’s start date which has resulted in a delay in the submission of IDEO.org’s Annual Audit Accounts but DFID have been given assurance that these will be signed off in the next 2 months and by the end of June in future years as per the terms of the accountable grant.

Recommendation: Schedule a financial spot check by the end of this 16/17 financial year

Date of last narrative financial report	20/07/2016
Date of last audited annual statement	31/12/2014

E: RISK (½ page)

Overall risk rating: Low/Medium/High

In discussion with the programme lead at IDEO.org, the SRO and Programme Manager for Amplify have agreed that the Amplify team will refresh the existing risk register to include new and reworded risks instead of referring to risks outlined in the initial Business Case in these reviews every year. For reference, the risks identified in the Business Case were the following:

1. That funds made available for the implementation of winning solutions are misused or wasted.
  1. Risk Rating: Medium - this continues, as with any programme, to be a live risk, and the Amplify team recommend keeping this in the register and rating it Medium, as any programme working with small actors in uncertain contexts generates some risks on this front.
2. The offline convenings have insufficient attendance to strengthen the offline networks, and drive participation by experts and implementers in the online Challenge.
  1. Risk Rating: No longer relevant
3. The existing OpenIDEO platform is not suitable or sufficient for running Amplify’s 10 Challenges.
  1. Risk Rating: Low - application numbers are similar to or better than other challenge funds of a similar size and this has been the case for every challenge so far.
4. Not enough ideas get taken to implementation or cannot be tested in local situations.
  1. Risk Rating: High - although this risk is to be reworded to more specifically refer to the structural risk within this programme of the grants being too small, and the risks inherently involved in innovating and prototyping. This is both more specific and more relevant - see below for the new wording.
5. The platform fails to attract the right community or gets less engagement and innovation than expected.
  1. Risk Rating: No longer relevant

In discussion, the team agreed that risks 1,3 and 4 remain relevant, although may be re-worded to cover broader programme risks. Risks 2 and 5 will be reworked into one broader risk reflecting concerns that the programme will not attract the right level of participation and engagement across the board. Additional risks to be added to register are outlined in the next section:

Overview of programme risk

1. Sterling value: Due to the British vote to leave the European Union and the subsequent devaluation of the British pound, Amplify is exploring scenarios for reducing program activities in order to accommodate the decrease in available funding based on the fixed amount of the Amplify grant. Amplify is examining its disbursement schedule and planned activities to determine whether strategic shifts in program activities could provide a workaround for the program as the UK currency stabilizes, however, scenario planning is also ongoing to determine how Amplify would truncate activities if the devaluation holds. This may include reducing the amount of challenges that are run, reducing the number of grantees supported in some of the remaining challenges, or other efforts to decrease expenditure over the remaining years of the program. These scenarios should mitigate the risk posed, and will be explored in concert with DFID. The risk involved here is High.

2. DFID staff changes: This programme is so dependent on influencing and developing an approach to systems change, that a strong link to a consistent programme team in DFID has been an important aspect. Suggested mitigating actions for this risk including building wider networks of communication and influence in DFID, including in country offices. Risk level is High

3. Size of grants and innovation risks insufficient for quantifiable impact:
4. Fewer than half grantees implementing viable solutions by end programme: Both these risks relate to structural challenges inherent in what is a flexible, experimental, and early-stage focused programme. Mitigating actions include the hiring of a portfolio manager (completed) to monitor the overall group of projects, developing strategies for follow-on funding for each grantee and developing plans to measure impact in non-traditional ways to account for small, flexible projects. Risk level is Medium.

5. Insufficient participation and engagement in the programme overall: Given progress the programme has made in outreach, increasing the number of applicants from DFID priority countries and increasing the proportion of ideas submitted which meet basic criteria, this new risk is rated as Low

Outstanding actions from risk assessment:

The Amplify team will draft a renewed risk register (in a concise format which is meaningful to the programme team) and assign risk owners to newly surfaced or re-worded risks (including DFID owners), who will enact the mitigating actions outlined above.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

Delivery for year three is primarily on schedule. In year three, Amplify recovered from delays in year two by onboarding grantees for Challenges 2 and 3 with design bootcamps that were held two months apart. Additionally, Amplify made significant efforts to approve grantee budgets and increase disbursements during year three as discussed in the recommendations section above. The Amplify team is continually improving the process of vetting, onboarding, and providing funding to grantees in order to ensure timeliness and coherent workflows as the portfolio grows. Based on learnings from Challenges 1-3, Amplify has established timelines that lengthen the period of due diligence before grantee selection to include gathering organizational documents, conducting Skype calls with each potential grantee, and performing a survey to understand nuanced organizational details that may not have been highlighted in the OpenIDEO submission. Amplify has gained a better understanding of the operational flow of the program, and is better placed to plan ahead for the timeline of each challenge, with bootcamp occurring 1-2 months after grantee selection, followed by the three-month prototyping period, followed closely by the 12-month pilot phase. The program is now on track to begin graduating grantees in year three and reducing the number of active grantees at any one time, which will unburden the core team and ensure timelines remain stable.

Performance of partnership(s)

DFID/IDEO.org partnership: The partnership between DFID and IDEO.org continues to be a strong and fruitful relationship, with regular communication and transparent discussion of successes, challenges, and ambitions for the program. The openness of the partnership allows for constant iteration in program implementation and enables the Amplify program to remain nimble and adjust to best support its portfolio of grantees. DFID’s strategic involvement in partnership building is critical to ensuring the program leverages complementary funding and support where it will be most valuable, while being cautious not to commit to additional partnerships that will not yield positive results for all parties. Beyond the Innovation Unit, participation in the Amplify process by subject-matter experts in resilience, housing, humanitarian crises, education, agriculture, and M&E have provided significant value to challenges and the overall program strategy in Year 3.

External evaluation unit: The initial external evaluation unit working on Amplify completed two case studies on the early stages of the programme. A new evaluation unit will be contracted in the third year of the programme to assess the programme more broadly and review its impact in its later stages.

Asset monitoring and control

The program has made limited investments in assets, but in the event of any assets being purchased over £1000, these are to be reported in the Accountable Grant inventory provided on signature of the Accountable Grant letter, and discussed with the Program Manager. These such assets are maintained in an Excel spreadsheet, which is maintained by Amplify’s Program Coordinator. (See Annex 1)

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

Amplify has made substantial progress in codifying and standardising the way it monitors grantees. In terms of measuring the broader impact of the programme, including its effect on the wider development sector’s approach to problem-solving, the small team at IDEO.org rely primarily on grantee and partner feedback, which is collected at standard points, and on data which is collected through the prototyping process to help grantees measure impact. As far as wider influence, DFID can begin the process of taking an empirical review of this by surveying previous and current partners of the programme, and surveying internal DFID teams.

For both impact and influence measures, an external evaluator who can bring more time, resources and expertise to these questions will be critical. The procurement process for this has begun, and DFID should aim to procure a supplier this financial year.

This programme represents a critical innovation, in that it is a longer-term, grantee-supporting programme which uses Human-Centred Design. Frequently, other work with Human-Centred Design in development has involved short consultancies without long-term commitment to both analysing impact and building capacity across a diverse portfolio of projects. Aggregating and communicating evidence of impact and influence is challenging, but a critical part of the programme.

Monitoring progress throughout the review period

In order to effectively monitor the grantees throughout the lifecycle of their projects, the Amplify team has increased the frequency and depth of information gathering and monitoring for all challenge winners. Monitoring activities are broken down into two phases: the selection period and the support period, and include monthly, quarterly, and annual touchpoints, and both qualitative and quantitative methods. See Annex 2 for current Monitoring Plan.

ANNEX:
The annexes linked here will be added as physical attachments in the final version of the Annual Review.
1. Asset Log
2. M&E Plan
3. List of current grantees