## Original logframe
Project Name | Assistance to Refugees and Internally Displaced People 2012-2015
Impact | Impact Indicator 1 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015
Improve the quality of life and reduce the vulnerability of refugees and displaced persons along Burma’s border, including preparation for their voluntary return. | Under 5 mortality rate (U5MR) in Burmese refugee camps in Thailand. (DFID standard outcome indicator) | Planned | 4/1000 | annual: <8/1000 | annual: <8/1000 | annual: <8/1000
Achieved
Source:
Baseline data was from Thailand Burma Border Consortium's bi-annual programme report for mortality rates. UNESCAP's 2011 statistical yearbook for Asia and the Pacific.
| Impact Indicator 2 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015
| Refugee camp residents’ awareness of their rights and satisfaction with the actions taken to protect them. | Planned | Knowledge: Existing camps: 65%, New camps: 56% know Thai laws and systems. | 80% (original camps); 70% (new camps) | 85% (original camps); 75% (new camps) | 90% (original camps); 80% (new camps)
|  |  | Satisfaction: 68% | 75% | 80% | 85%
Achieved
Source:
Baseline: IRC LAC Assessment on Protection, Access to Justice and the Rule of Law in camps. Y2: random sampling Y3: Repeat Assessment and Project Evaluation. Collected by IRC Legal Assistance Centre Staff and External Evaluator. Note: Sex disaggregated targets will be developed in the first 3 months of the project.
| Impact Indicator 3 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015
| Percentage of women in refugee camp management. (Camp Committees, security and other stipend positions). | Planned | 33% | 35% | 40% | 45%
Achieved
Source:
Thailand Burma Border Consortium's bi-annual programme report.
| Impact Indicator 4 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015
| Number of displaced people that opt for voluntary return to Eastern Burma. | Planned | 0 | Voluntary return framework and principles agreed and disseminated. | Tripartite agreements established and adhered to by relevant stakeholders. | 100,000 refugees opt for assistance for voluntary return.
Achieved
Source:
UNHCR and Government and project data, annually. TBBC annual reports.
| Impact Indicator 5 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015
| Number of maternal deaths reported in hospitals/health centres by TBAs in the past year. | Planned | 61 | 64 | 49 | 41
Achieved
Source:
|  |  | Hospital / health centre project staff. | records collected by the | local health authorities in | conjunction with HPA
OUTCOME | Outcome Indicator 1 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015 | Assumptions • RTG Ministry of Interior continues to grant NGO partners access to refugee camps. • Good cooperation between health agencies. • Security situation in camps remains stable. • Dramatic reductions in other donors’ contributions to TBBC do not undermine its ability to meet the basic needs of refugees. • Other donors contribute extra support to community-based organisations providing assistance to IDPs. • Refugees and IDPs remain largely isolated from the effects of the global economic downturn.
Meet more of the basic humanitarian needs of Burmese refugees and displaced and persons in conflict-affected border areas in Burma; and equip them with the knowledge and skills for return and reintegration to Burma. | Percentage of births attended by skilled health personnel (doctors, nurses, midwives or trained AMW). | Planned | 22.47% | 25.5% | 26.9% | 32.2%
Achieved
Source:
HPA's household annual surveys
| Outcome Indicator2 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015
| Children under 5 malnutrition reates in refugee and IDP camps. | Planned | 2% across 9 refugee camps: WHO 2005 Growth Standards (2011 Nutrition Surveys) | annual: <5% | annual: <5%. Nutrition surveys data available early 2014. | annual: <5%
Achieved
Source:
Nutrition Surveys (biennial), TBBC IDP Survey, TBBC SE Burma Programme reports (annual)
| Outcome Indicator 3 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015
| Number of people in communities affected by conflict and displacement benefiting from community-based humanitarian relief. | Planned | 0 | 58446 | 76949 | 94959
Achieved
Source:
Village profile (PRA records), project records, mid-term evaluation and end of project evaluation.
| Outcome Indicator 4 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015
| Number of businesses established following entrepreneurial development supported by the programme. | Planned | 478 businesses | 200 | 200 | 1100 (accumulative)
Achieved
Source:
TBBC bi-annual programme report, Entrepreneurship Development, Grant, Savings & Loans Project (EDGSLP) Monitoring System Data (annual).
| Outcome Indicator 5 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015
| Percentage of refugee communities members report overall satisfaction with Legal Assistance Centre project activities. | Planned | 0% (pending development of community accountability scorecards) | 60% | 70% | 80%
Achieved
Source:
IRC LAC 's Annual assessment on protection, access to justice and rule of law with sampled refugee camp population by LAC.
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
| 25854578 |  | 0 | TBC | 25854578 | 100%
INPUTS (HR) | DFID (FTEs)
50% FTE Humanitarian Coordinator (Bangkok). 50% Programme Officer (Bangkok). 20% Evaluation Adviser (DFID Vietnam). 20% Economic Adviser (DFID Burma). 20% Senior Governance Adviser (DFID Burma)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015 | Assumption
Effective delivery of food and relief items and other means to enable refugees / IDPs to sustain a basic livelihood. | Number of displaced persons (in Thailand and eastern Burma) have access to food in camps. | Planned | 139,771 refugees (69,459 F, 70,312 M) 17,595 IDPs (8,719 F; 8,876 M) (April 2012) | 139,000 (68,945 F; 70,055 M) refugees in 9 camps 17,000 in IDP (8,415 F, 8,585 M) camps and resettlement sites | Remaining caseloads in camps | Remaining caseloads in camps | • Donor commitment to funding. • Partners continue to be able to access IDP communities. • Sufficient commodities available in market place. • Royal Thai Government allow appropriate levels of independence for aid agencies to operate.. • Other donors contribute extra support to community-based organisations providing assistance to IDPs. - Cross border access maintained for aid agencies.
Achieved
Source:
Monthly Population Report (MPR), Monthly Monitoring Report (MMR), Nutrition Surveys, TBBC SE Burma / Myanmar Annual Programme Report, TBBC Bi-annual Programme Report.
| Output Indicator 1.2 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015
| Number of HH benefiting from livelihood in-kind grants (e.g. pig banks, cow bank, solar lighting, homestead garden and vermi-composting). | Planned | 0 | 4690 (old 2400 + new 2290) | 7370 (old 4690 + new 2680) | 9900 (accumulative)
Achieved
Source:
FLD and KND's Delivery Reports, Quarterly Reports and End of Year Report
| Output Indicator 1.3 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015
| Number of vulnerable people suffering livelihood shocks in SE Burma that receive cash equivalent to 3 months supply of rice. | Planned | 451093 (2006-2012) | 45,000 people in SE Burma (22,500 F, 22,500 M) | 45,000 people in SE Burma (22,500 F, 22,500 M) | 135,000 people in SE Burma (67,500 F, 67,500 M) - Accumulative
Achieved
Source:
TBBC bi-annual programme report, TBBC SE Burma / Myanmar annual programme report, Request summaries / Financial records.
IMPACT WEIGHTING (%) | [6 empty] | RISK RATING
20% | [6 empty] | Low
RISK RATING
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
| 1692605 | 30% of TBBC | 0 | 19291507.5 | 20984112.5 | 8.066%
INPUTS (HR) | DFID (FTEs)
INPUTS (HR) | DFID (FTEs)
50% FTE Humanitarian Coordinator (Bangkok). 50% Programme Officer (Bangkok). 20% Evaluation Adviser (DFID Vietnam). 20% Economic Adviser (DFID Burma). 20% Senior Governance Adviser (DFID Burma)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015 | Assumptions
Effective delivery of needs-based humanitarian assistance to people in communities in Burma affected by displacement and conflict. | Number of people directly assisted by food security programmes (via village-based community mechanisms (e.g. rice banks). (DFID Standard Indicator) | Planned | 0 | 10352 (9690 + 662) HHs in 142 (132 + 10) villages having access to one month of rice stock. | 13698 (10352 + 3346) HHs in 188 (142 + 46) villages having access to one month of rick stock. | 16896 (13698 + 3198) HHs in 234 (188 + 46) villages having access to one month of rick stock. | • No major changes in the political situation affecting border areas. • Partners continue to be able to access IDP communities. • Reliable data can be collected on support to IDPs. • Collection of new baseline data on vulnerable populations. • Other donors contribute extra support to community-based organisations providing assistance to IDPs.
Achieved
Source:
FLD and KDN's Delivery Report, Quarterly Reports and Rice Bank End Year Report
| Output Indicator 2.2 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015
| Number of people with sustainable access to an improved sanitation facility as a result of DFID support (cumulative). (DFID Standard Indicator) | Planned | 29369 | 32919 | 37394 | 37869
Achieved
Source:
HPA and KDN's Work records (annual).
| Output Indicator 2.3 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015
| Number of households provided with new/improved drinking water sources. (DFID Standard Indicator) | Planned | 1282 (KND)+ 6240 (CBO)=7522 | 1397 + 11360 respectively= 12739 | 1817+ 15040 respectively=16857 | 2417 (KND) + 18720 (CBO)= 21137
Achieved
Source:
FLD, HPA, KDN Work records and project reports from community organisations (annual).
DFID (FTEs)
| Output Indicator 2.4 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015
| Number of communities able to influence / define development in their village and receive improved quality and quantity of social services provided by civil society organisations. | Planned | 0 | 60 | 90 | 120
Achieved
Source:
KDN and FLD ' participatory reviews and monitoring visit reports, programme reports, end of project evaluation report.
IMPACT WEIGHTING (%) | [6 empty] | RISK RATING
15% | [6 empty] | High
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
| 6605075 | (40% TBBC+ 100%FLD+ 100%KND+ 100%Shan+ 100%HMSF) | 0 | TBC | 6605075 | 100%
INPUTS (HR) | DFID (FTEs)
50% FTE Humanitarian Coordinator (Bangkok). 50% Programme Officer (Bangkok). 20% Evaluation Adviser (DFID Vietnam). 20% Economic Adviser (DFID Burma). 20% Senior Governance Adviser (DFID Burma)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015 | Assumption
Improved health awareness and basic health facilities and services in the programme communities. | Full immunization coverage of children under two years old in the programme communities. | Planned | 25.82% | 42.3% | 45.6% | 50.4% | • Local Medical Officers are cooperative ; -No major external shortage/problems in medical and health supplies • Access to all sites continues • Baselines can be collected • There is sufficient M&E capacity to collect HH surveys
Achieved
Source:
Work records of TBAs and health facilities collected by HPA project staff. Annual household surveys.
| Output Indicator 3.2 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015
| Number of pregnant women who receive at least 4 antenatal care visits as a results of DFID funding in the programme communities. | Planned | 2210 | 4910 | 8020 | 11560
Achieved
Source:
HPA 's Work records of TBAs and health facilities collected by HPA project staff.
| Output Indicator 3.3 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015
| Percentage of population aware of key messages related to personal hygiene, health and environmental sanitation in the project villages. | Planned | 27.56% | 37.4% | 44.84% | 51.9%
Achieved
Source:
HPA's Household surveys by project implementers, annually.
| Output Indicator 3.4 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015
| Number of women and men who receive appropriate treatment for malaria through DFID funding. | Planned | 552 | 552 | 3954 | 15424
Achieved
Source:
HPA project progress report (annual).
| Output Indicator 3.5 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015
| Percentage of children under 5 years old treated with ORS after diarrhoea episode in last 14 days in programme villages. | Planned | 21.99% | 23.54% | 28.04% | 32.8%
Achieved
Source:
Baseline: HPA's Household survey in February 2012. Milestone 1: Estimate based on observation and records of TBAs, MWs and VHC. Milestone 2: Household survey in June 2014. Target: Household survey in June 2014.
IMPACT WEIGHTING (%)
15%
RISK RATING
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
| 7000000 | (100%HPA) | 0 | 9714690 | 16714690 | 41.88% | Risk: Medium
INPUTS (HR) | DFID (FTEs)
INPUTS (HR) | DFID (FTEs)
50% FTE Humanitarian Coordinator (Bangkok). 50% Programme Officer (Bangkok). 20% Evaluation Adviser (DFID Vietnam). 20% Economic Adviser (DFID Burma). 20% Senior Governance Adviser (DFID Burma)
OUTPUT 4 | Output Indicator 4.1 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015 | Assumptions
Refugee communities have increased opportunities to access justice, protection and good governance from accountable refugee leadership and local authorities. | Percentage of all appropriate serious crimes reported to the camp justice committee or LAC that are successfully referred (with client consent) to the Thai justice system. | Planned | 93% appropriate serious crimes camps reported in 5 camps | 95% appropriate serious crimes reported in 5 camps | 98% appropriate serious crimes reported in 5 camps | 100% appropriate serious crimes reported in 5 camps | • Enabling environment prevails • Appropriate policies and practices supported by the Government of Myanmar and other stakeholders - Cooperation by local authorities (both in Thailand and in Burma) • Central level engagement continues to be possible ; • RTG Ministry of Interior continues to grant IRC access to refugee camps along the Thai-Burma border. • Continued willingness of Thai government justice system to take on cases from refugee camps. • Security situation in camps remains stable. • Significant numbers of trained paralegals do not apply for resettlement to third countries (these are currently selected from individuals with no resettlement plans). • Continued engagement of the Ministry of Interior and Ministry of Justice in the development of guidelines.
Achieved
Source:
IRC LAC database and annual reports.
| Output Indicator 4.2 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015
| Percentage of local authorities, refugee community leadership and members, and civil society demonstrate improved knowledge and skills in mediation, conflict and dispute resolution, administration of justice and good governance principles. | Planned | 41% | 50% | 60% | 70%
Achieved
Source:
IRC LAC's Annual assessment on protection, access to justice and rule of law with sampled refugee camp population.
| Output Indicator 4.3 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015
| Number of refugee community members receive high quality, tailored counselling, referral and follow up services. | Planned | 291 clients in original camps and 78 in newer camps receive legal counselling, referral and follow up services. | 300 Clients in original camps and 120 in newer camps receive legal counselling, referral and follow up services. | 300 Clients in original camps in and 150 in newer camps receive legal counselling, referral and follow up services. | 300 Client in original camps and 170 in newer camps receive legal counselling, referral and follow up services.
Achieved
Source:
LAC database and annual reports
| Output Indicator 4.4 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015
| Percentage of gender-based violence and child protection cases reported to IRC receive coordinated and comprehensive support services. | Planned | 0% - no written protocol between agencies outside / inside camps | 70% of cases | 85% of cases | 95% of cases
Achieved
Source:
LAC database, case checklist, annually.
INPUTS (HR) | DFID (FTEs)
IMPACT WEIGHTING (%)
10%
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
| 2013876 | 100% LAC | 0 | 1370089 | 3383965 | 59.51% | Risk: Medium
INPUTS (HR) | DFID (FTEs)
50% FTE Humanitarian Coordinator (Bangkok). 50% Programme Officer (Bangkok). 20% Evaluation Adviser (DFID Vietnam). 20% Economic Adviser (DFID Burma). 20% Senior Governance Adviser (DFID Burma)
OUTPUT 5 | Output Indicator 5.1 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015 | Assumption
Refugees and displaced people are equipped with knowledge and skills to be prepared for eventual return. | Number of stipend workers and project participants receiving certificates to support efforts to secure future employment. | Planned | 0 | 650 current stipend staff (250 F; 350 M) 1000 participants (450 F, 550 M) | 650 stipend staff (325 F, 325 M) 1000 participants (500 F, 500 M) | 1950 stipend staff (900 F, 1050 M) 3000 participants (1450 F, 1550 M) | Continued engagement of the Burmese government, Ministry of Interior and Ministry of Justice in developing any guidance on refugees and their return; Political and social conditions in Burma are progressive and positive for voluntary return.
Achieved
Source:
Stipend staff regular records, Activity participant regular records, TBBC programme reports (biannual)
| Output Indicator 5.2 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015
| Number of refugee community members who have received information on Myanmar legal framework relevant to potential refugee and IDP return. | Planned | 0 | 7000 all 5 camps (cumulative) | 7500 all 5 camps (cumulative) | 8000 all 5 camps (cumulative)
Achieved
Source:
Community dissemination activity records (regular) by LAC.
| Output Indicator 5.3 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015
| Number of participants (including camp residents, refugee representatives and CBO partners) in trainings on diverse topics with emphasis on capacities needed for return. | Planned | 6,557 participants (2,871 F, 3,686 M) in camp-based capacity building trainings 47 CBO partner staff trained (2011) | 6,600 (3,000 F, 3,600 M) participants in camp based training participants 48 CBO participants | 6,700 (3,350 F; 3,350 M) camp based training participants 50 CBO participants | 20,100 (9,700 F; 10,400 M) camp based training participants 50 CBO participants
Achieved
Source:
TBBC Southeast Burma/Myanmar Programme Report (Annual) Camp Management Support Programme Capacity Building Records
IMPACT WEIGHTING (%)
20% | [6 empty] | RISK RATING
High
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
| 1692605 | 30% TBBC funds by dfid | 0 | 19702534.2 | 21395139.2 | 7.911%
INPUTS (HR) | DFID (FTEs)
INPUTS (HR) | DFID (FTEs)
50% FTE Humanitarian Coordinator (Bangkok). 50% Programme Officer (Bangkok). 20% Evaluation Adviser (DFID Vietnam). 20% Economic Adviser (DFID Burma). 20% Senior Governance Adviser (DFID Burma)
OUTPUT 6 | Output Indicator 6.1 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015 | Assumption
Confidence built in the ceasefires by providing improved living and economic opportunities in the conflict affected communities. | A timely joint funding mechanism in place to support peace keeping work in Burma. | Planned | 0 | The fund framework formulated and agreed with all key partners. | Liason offices in ceasefire areas established and operational. | Pilot projects well underway and scaled up. | Government continues to welcome donors' support to the peace keeping process. - The political and economic environment in Burma does not get worse. -Consultations with key partners of the peace keeping and recovery process including with local communities is supported by the Govenrment.
Achieved
Source:
The fund management office reports, annually.
| Output indicator 6.2 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015
| Confidence building measures e.g. the demining of non-military areas, provision of basic infrustructure and services, support on economic opportunities, in place to facilitate the resettlement of IDPs. | Planned | 0 | 2 measures in place |  | 4 measures.
Achieved
Source:
The fund management office reports, annually.
| Output Indicator 6.3 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015
| Number of community-led peace and reconciliation initiatives | Planned | 0 | 6 | 9 | 21
Achieved
Source:
TBBC Annual Reports
IMPACT WEIGHTING (%) | [6 empty] | RISK RATING
15% | [6 empty] | High
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
| 4500000 | 100% Peace Keeping funds by DFID | 0 | TBC | 4500000 | 100%
INPUTS (HR) | DFID (FTEs) | a
50% FTE Humanitarian Coordinator (Bangkok). 50% Programme Officer (Bangkok). 20% Evaluation Adviser (DFID Vietnam). 20% Economic Adviser (DFID Burma). 20% Senior Governance Adviser (DFID Burma)
OUTPUT 7 | Output Indicator 7.1 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015 | Assumption
Optimal fund management results in generated evidence utilised to inform policy, funding, and programming decisions; and improved fiduciary risk management. | Availability of an M&E framework by each subproject to collect data and evidence on sub-project activities which include tools for collecting feedback from refugees and displaced people. | Planned | NA | The framework formulated and agreed with all key partners. | annual reports generated from the framework | Final report on M&E and project results. | • Government enables access for implementation and monitoring • Implementing partners have capacity to effectively monitor their programmes
Achieved
Source:
Programme M&E report (Annual).
| Output indicator 7.2 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015
| Availability of accurate, up-to-date information on refugee and IDP populations to stakeholders (UNHCR, agencies, CBOs in Thailand and Burma). | Planned | 12 monthly updates | 12 updates reflecting monthly population changes. | 12 updates reflecting monthly population changes. | 12 updates reflecting monthly population changes.
Achieved
Source:
Monthly population report; TBBC monthly Population maps.
| Output Indicator 7.3 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015
| Number of refugee camps using information technology (laptops) to complete Ration Distribution Register (RDR) at food distributions. | Planned | 1 camp piloting IT. Draft IT strategy developed. | 2 camps piloting IT. Review of IT use and strategy. | 4 camps piloting IT. | 9 Camps use computers for RDR data.
Achieved
Source:
Post-distribution monitoring surveys, staff reports, TBBC programme reports.
| Output Indicator 7.4 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015
| Availability of an evaluation framework for the programme which includes a repeat of the VFM evaluation. | Planned | NA | A framework developed. Start baseline data collection. | Mid-term review evaluation. | VFM evaluation and possible an evaluation of impact.
Achieved
Source:
Programme annual monitoring reports.
| Output Indicator 7.5 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015
| Availability of sound fiduciary management measures in place by project implementers, evidenced by independent monitoring/tracking. | Planned | 0 | A fiduciary risk framework for the overall programme in place. | annual report on its implemementation and independent tracking study. | annual report on its implementation with no major problems on fiduciary management*.
Achieved
Source:
Programme annual monitoring reports.
IMPACT WEIGHTING (%) | [6 empty] | RISK RATING
5% | [6 empty] | High
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
| 2350416 | 100% of DFID funds for M&E and fiduciary risk | 0 | TBC | 2350416 | 100%
INPUTS (HR) | DFID (FTEs)
50% FTE Humanitarian Coordinator (Bangkok). 50% Programme Officer (Bangkok). 20% Evaluation Adviser (DFID Vietnam). 20% Economic Adviser (DFID Burma). 20% Senior Governance Adviser (DFID Burma)
Footnotes:
Impact Indicator 1- Data source: | Annual targets are based on mortality rates for East Asia & Pacific region. An increase to twice the target (16 per 1000) would indicate a significant public health emergency.
Purpose Indicator 1 - Data source: | Annual targets are based on mortality rates for East Asia & Pacific region. An increase to twice the target (14 per 1000) would indicate a significant public health emergency.
Target for indicator 7.5: the target will be defined and agreed by partners after the project has been approved.

## Revision1asof2015
Project Name | Assistance to Refugees and Internally Displaced People 2012-2015
Impact | Impact Indicator 1 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015
Improve the quality of life and reduce the vulnerability of refugees and displaced persons along Burma’s border, including preparation for their voluntary return. | Under 5 mortality rate (U5MR) in Burmese refugee camps in Thailand. (DFID standard outcome indicator) | Planned | 4/1000 | annual: <8/1000 | annual: 8 </1000 | annual: 8</1000
|  | Achieved |  |  | 3.65 | To be assessed
Source:
Baseline data was from Thailand Burma Border Consortium's bi-annual programme report for mortality rates. UNESCAP's 2011 statistical yearbook for Asia and the Pacific.
| Impact Indicator 2 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015
| Refugee camp residents’ awareness of their rights and satisfaction with the actions taken to protect them. | Planned | Knowledge: Existing camps: 65%, New camps: 56% know Thai laws and systems. | 80% (original camps); 70% (new camps) | 85% (original camps); 75% (new camps) | 90% (original camps); 80% (new camps)
|  |  | Satisfaction: 68% | 75% | 78% | 78%
|  | Achieved |  | 93% | 74.35% | report due in November 2015
Source:
Baseline: IRC LAC Assessment on Protection, Access to Justice and the Rule of Law in camps. Y2: random sampling Y3: Repeat Assessment and Project Evaluation. Collected by IRC Legal Assistance Centre Staff and External Evaluator. Note: Sex disaggregated targets will be developed in the first 3 months of the project.
| Impact Indicator 3 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015
| Percentage of women in refugee camp management. (Camp Committees, security and other stipend positions). | Planned | 33% | 35% | 40% | 45%
|  | Achieved |  | 28% | 40% | 38%
Source:
Thailand Burma Border Consortium's bi-annual programme report.
| Impact Indicator 4 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015
| Number of displaced people that opt for voluntary return to Eastern Burma. | Planned | 0 | Voluntary return framework and principles agreed and disseminated. | Tripartite agreements established and adhered to by relevant stakeholders. | 100,000 refugees opt for assistance for voluntary return.
|  | Achieved |  | Initiated but not complete | Strategic Roadmap for Voluntary Repatriation drafted and shared to all relavant stakeholders including the Burmese government, EAGs and refugees representatives. | No assistance for returnees so far. Few number of returnees are believed to be seasonal or go-see visits only.
Source:
UNHCR and Government and project data, annually. TBBC annual reports.
| Impact Indicator 5 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015
| Number of maternal deaths reported in hospitals/health centres by TBAs in the past year. | Planned | 61 | 64 | 49 | 33
|  | Achieved |  | 13 | 17 | 10
Source: This relates to HPA in Kachin/northern Shan only
|  |  | Hospital / health centre project staff. | records collected by the | local health authorities in | conjunction with HPA
OUTCOME | Outcome Indicator 1 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015 | Assumptions • RTG Ministry of Interior continues to grant NGO partners access to refugee camps. • Good cooperation between health agencies. • Security situation in camps remains stable. • Dramatic reductions in other donors’ contributions to TBBC do not undermine its ability to meet the basic needs of refugees. • Other donors contribute extra support to community-based organisations providing assistance to IDPs. • Refugees and IDPs remain largely isolated from the effects of the global economic downturn.
Meet more of the basic humanitarian needs of Burmese refugees and displaced and persons in conflict-affected border areas in Burma; and equip them with the knowledge and skills for return and reintegration to Burma. | Percentage of births attended by skilled health personnel (doctors, nurses, midwives or trained AMW). | Planned | 22.47% | 25.5% | 26.9% | 29.3%
|  | Achieved |  | 18% | 22.4% | 10.83%
Source:
HPA's household annual surveys
| Outcome Indicator2 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015
| Children under 5 acute malnutrition rates in refugee and IDP camps. | Planned | 2% across 9 refugee camps: WHO 2005 Growth Standards (2011 Nutrition Surveys) | annual: <5% | annual: <5%. Nutrition surveys data available early 2014. | annual: <5%
|  | Achieved |  |  | 2.1% | 2.1% (wasting), 35.1% (stunting rate) in refugees
Source:
Nutrition Surveys (biennial), TBBC IDP Survey, TBBC SE Burma Programme reports (annual)
| Outcome Indicator 3 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015
| Number of people in communities affected by conflict and displacement benefiting from community-based humanitarian relief. | Planned | 0 | 58446 | 63200 | 70000
|  | Achieved |  | FLD = 37434, KDN = | FLD: 41810 | FLD: 46,470
Source:
Village profile (PRA records), project records, mid-term evaluation and end of project evaluation.
| Outcome Indicator 4 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015
| Number of businesses established following entrepreneurial development including female businesses supported by the programme. | Planned | 478 businesses | 200 | 200 | 1100 (accumulative)
|  | Achieved |  | 556 | 540 | 1064
Source:
TBBC bi-annual programme report, Entrepreneurship Development, Grant, Savings & Loans Project (EDGSLP) Monitoring System Data (annual).
| Outcome Indicator 5 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015
| Percentage of refugee communities members report overall satisfaction with Legal Assistance Centre project activities. | Planned | 0% (pending development of community accountability scorecards) | 60% | 70% | 80%
|  | Achieved |  | 93% | 100% | 85.1%
Source:
IRC LAC 's Annual assessment on protection, access to justice and rule of law with sampled refugee camp population by LAC.
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
| 25854578 |  | 0 | TBC | 25854578 | 100%
INPUTS (HR) | DFID (FTEs)
50% FTE Humanitarian Coordinator (Bangkok). 50% Programme Officer (Bangkok). 20% Evaluation Adviser (DFID Vietnam). 20% Economic Adviser (DFID Burma). 20% Senior Governance Adviser (DFID Burma)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015 | Assumption
Effective delivery of food and relief items and other means to enable refugees / IDPs to sustain a basic livelihood for voluntary durable solutions. | Number of displaced persons (in Thailand and eastern Burma) have access to food in camps. | Planned | 139,771 refugees (69,459 F, 70,312 M) 17,595 IDPs (8,719 F; 8,876 M) (April 2012) | 139,000 (68,945 F; 70,055 M) refugees in 9 camps 17,000 in IDP (8,415 F, 8,585 M) camps and resettlement sites | Remaining caseloads in camps | Remaining caseloads in camps | • Donor commitment to funding. • Partners continue to be able to access IDP communities. • Sufficient commodities available in market place. • Royal Thai Government allow appropriate levels of independence for aid agencies to operate.. • Other donors contribute extra support to community-based organisations providing assistance to IDPs. - Cross border access maintained for aid agencies.
|  | Achieved |  | 127,038 (F: 63915, M: 63123)/ IDP: 133,396 | Refugees;119,000, IDP: 12,639 | 104,316 ( with F=50% as of December 2015)/ IDPs (inside (12,307)/outside (25,955) camps in SE): 38,262 persons
Source:
Monthly Population Report (MPR), Monthly Monitoring Report (MMR), Nutrition Surveys, TBBC SE Burma / Myanmar Annual Programme Report, TBBC Bi-annual Programme Report.
| Output Indicator 1.2 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015
| Number of HH benefiting from livelihood in-kind grants (e.g. pig banks, cow bank, solar lighting, homestead garden and vermi-composting). | Planned | 0 | 370 HHs benefitting from livelihood in-kind grants | 5,660 HHs benefitting from livelihood in-kind grants | 6,812 HHs benefitting from livelihood in-kind grants
|  | Achieved |  | 4,843 HH benefitting from livelihood in-kind grants | 6,092 HH benefitting from livelihood in-kind grants | 7,692 HH benefitting from livelihood in-kind grants
Source:
FLD and KND's Delivery Reports, Quarterly Reports and End of Year Report
| Output Indicator 1.3 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015
| Number of vulnerable people suffering livelihood shocks in SE Burma that receive cash equivalent to 3 months supply of rice. | Planned | 451093 (2006-2012) | 45,000 people in SE Burma (22,500 F, 22,500 M) | 45,000 people in SE Burma (22,500 F, 22,500 M) | 135,000 people in SE Burma (67,500 F, 67,500 M) - Accumulative
|  | Achieved |  | 42173 | 29000
Source:
| Output Indicator 1.4 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015 | Assumption
| Number of stipend workers and project participants receiving certificates to support efforts to secure future employment. | Planned | 0 | 650 current stipend staff (250 F; 350 M) 1000 participants (450 F, 550 M) | 650 stipend staff (325 F, 325 M) 1000 participants (500 F, 500 M) | 1950 stipend staff (900 F, 1050 M) 3000 participants (1450 F, 1550 M) | Continued engagement of the Burmese government, Ministry of Interior and Ministry of Justice in developing any guidance on refugees and their return; Political and social conditions in Burma are progressive and positive for voluntary return.
|  | Achieved |  | 650 (357 F: 293 M) project participants | 2,966 stipend workers and camp-based participants, 650 participants (357 F; 293 M)
Source: Stipend staff regular records, Activity participant regular records, TBBC programme reports (biannual)
| Output Indicator 1.5 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015
| Number of refugee community members who have received information on Myanmar legal framework relevant to potential refugee and IDP return. (male/female) | Planned | 0 | 7000 all 5 camps (cumulative) | 7500 all 5 camps (cumulative) | 8000 all 5 camps (cumulative)
|  | Achieved |  | 0 | 8,780 participants from all 5 camps | 6922 (results as of June 2015)
Source:
Community dissemination activity records (regular) by LAC.
| Output Indicator 1.6 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015
| Number of participants (including camp residents, refugee representatives and CBO partners) in trainings on diverse topics with emphasis on capacities needed for return. | Planned | 6,557 participants (2,871 F, 3,686 M) in camp-based capacity building trainings 47 CBO partner staff trained (2011) | 6,600 (3,000 F, 3,600 M) participants in camp based training participants 48 CBO participants | 6,700 (3,350 F; 3,350 M) camp based training participants 50 CBO participants | 20,100 (9,700 F; 10,400 M) camp based training participants 50 CBO participants
|  | Achieved |  | 4,657 (1948 F: 2709 M) / 132 CBP partner staff | 6,188 camp based training participants (82.51% of the 2014 milestone)/ 132 CBO participants (71 women) Over 100%
Source:
IMPACT WEIGHTING (%) |  | TBBC Southeast Burma/Myanmar Programme Report (Annual) Camp Management Support Programme Capacity Building Records |  |  |  |  | RISK RATING
15% |  | TBBC bi-annual programme report, TBBC SE Burma / Myanmar annual programme report, Request summaries / Financial records. |  |  |  |  | Low
| DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
| 1692605 |  | 0 | 19291507.5 | 20984112.5 | 8.066%
INPUTS (HR) | DFID (FTEs)
INPUTS (HR) | DFID (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015 | Assumptions
Effective delivery of needs-based humanitarian assistance to people in communities in Burma affected by displacement and conflict. | Number of people directly assisted by food security programmes (via village-based community mechanisms (e.g. rice banks). (DFID Standard Indicator) | Planned | 0 | 10352 (9690 + 662) HHs in 142 (132 + 10) villages | 11632 (10352 + 1280) HHs in 158 (142 + 16) villages | 12912 (11632 + 1280) HHs in 174 (158 + 16) villages | • No major changes in the political situation affecting border areas. • Partners continue to be able to access IDP communities. • Reliable data can be collected on support to IDPs. • Collection of new baseline data on vulnerable populations. • Other donors contribute extra support to community-based organisations providing assistance to IDPs.
|  | Achieved |  | Data not available | 8,003 (6,137 HHs -STC FLD) in 138 villages, 1,866 HHs - AAM KDN) | 9,191 (FLD - 7128, KDN - 2,063)
Source:
FLD and KDN's Delivery Report, Quarterly Reports and Rice Bank End Year Report
| Output Indicator 2.2 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015
| Number of people with sustainable access to an improved sanitation facility as a result of DFID support (cumulative). (DFID Standard Indicator) | Planned | HPA 29,369 | HPA 32,919 | HPA 37,394 | HPA 38,762
|  | Achieved |  | HPA 32,769 | HPA 37,784 | HPA 44,307
Source:
HPA and KDN's Work records (annual). Note KDN funded via CA ends in July 2014.
| Output Indicator 2.3 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015
| Number of households provided with new/improved drinking water sources. (DFID Standard Indicator) | Planned | - 40 communities in target 60 communities (AAM/KDN) '- 10,352 (9,690+662) HHs from 142 villages (132+10) provided with improved drinking water sources (STC FLD) - 1,282 (HPA) | - 60 communities in target 90 communities (AAM/KDN) '- 11,632 (10,352+1,280) HHs in 158 (142+16) villages provided with improved drinking water (STC FLD) - 1,397 (HPA) | - 60 communities in target 90 communities (AAM/KDN) '- 12,912 (11,632+1,280) HHs in 174 (158+16) from 174 (158+16) villages provided with improved drinking water sources (STC FLD) - 1,817 (HPA) | - 3464 (HPA), FLD - 80% of 153 Villages | to reflect both AAM/KDN and STC/FLD
|  | Achieved |  | 2,272 (HPA) | 8,128 HHs in 138 villages (STC FLD) HPA - 2,998 AA/KDN not started | HPA - 4229, KDN - 7,058, FLD - 8,682
Source:
FLD, HPA, KDN Work records and project reports from community organisations (annual).
DFID (FTEs)
New | Output Indicator 2.4 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015
| Number of communities are able to prioritise, plan and implement community action points | Planned | 0 | 30 communities in the 60 target areas are able to prioritised, plan and implement community action points | 70 communities in the 90 target areas are able to prioritised, plan and implement community action points | 70 communities in the 90 target areas are able to prioritised, plan and implement community action points
|  | Achieved |  | N/A | N/A
Source:
KDN and FLD ' participatory reviews and monitoring visit reports, programme reports, end of project evaluation report.
IMPACT WEIGHTING (%) | [6 empty] | RISK RATING
25% | [6 empty] | High
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
| 6605075 | (40% TBBC+ 100%FLD+ 100%KND+ 100%Shan+ 100%HMSF) | 0 | TBC | 6605075 | 100%
INPUTS (HR) | DFID (FTEs)
50% FTE Humanitarian Coordinator (Bangkok). 50% Programme Officer (Bangkok). 20% Evaluation Adviser (DFID Vietnam). 20% Economic Adviser (DFID Burma). 20% Senior Governance Adviser (DFID Burma)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015 | Assumption
Improved health awareness and access to basic health facilities and services in the programme communities. | Full immunization coverage of children under two years old in the programme communities. | Planned | 25.82% | 42% | 45.8% | 49.9% | • Local Medical Officers are cooperative ; -No major external shortage/problems in medical and health supplies • Access to all sites continues • Baselines can be collected • There is sufficient M&E capacity to collect HH surveys
|  | Achieved |  | 19.22% | 33.1% | 16.35%
Source:
Work records of TBAs and health facilities collected by HPA project staff. Annual household surveys.
| Output Indicator 3.2 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015
| Number of pregnant women who receive at least 4 antenatal care visits as a results of DFID funding in the programme communities. | Planned | 2210 | 4910 | 8020 | 8563
|  | Achieved |  | 4864 | 9290 | 13306
Source:
HPA 's Work records of TBAs and health facilities collected by HPA project staff.
| Output Indicator 3.3 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015
| Percentage of population aware of key messages related to personal hygiene, health and environmental sanitation in the project villages. | Planned | 27.56% | 37.4% | 44.84% | 44.4%
|  | Achieved |  | 4,864 (99% achieved) | 22.7% | Data survey could not be conducted during the period.
Source:
HPA's Household surveys by project implementers, annually.
| Output Indicator 3.4 |  | Baseline 2014 | Milestone 2013 | Milestone 2014 | Target 2015
| Correct Knowledge of malaria prevention and treatment | Planned |  |  |  | 36.4%
|  | Achieved | 35.4% | N/A | N/A | Data survey to be conducted
Source:
HPA project progress report (annual).
| Output Indicator 3.5 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015
| Percentage of children under 5 years old treated with ORS after diarrhoea episode in last 14 days in programme villages. | Planned | 21.99% | 23.54% | 28.04% | 27.9%
|  | Achieved |  | 9.02% | 35.5% | 4.7%
Source:
Baseline: HPA's Household survey in February 2012. Milestone 1: Estimate based on observation and records of TBAs, MWs and VHC. Milestone 2: Household survey in June 2014. Target: Household survey in June 2014.
| Output Indicator 3.6 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015 | Assumption
| Number of patients treated (registered) for TB | Planned | Displaced (73; 36% female) Refugee (98; 38% female) | Displaced (125-175) Refugee (210-270) 30-40% female | Displaced (280-340) Refugee (470-600) 30-40% female | Displaced (450-550) Refugee (730-930) 30-40% female | -Caseload of TB, including MDR and XDR strains can be effectively managed by SMRU’s TB clinic. -Continued support for the programme by Thai and Burmese local authorities
|  | Achieved |  | Displaced 136 (36.8% f) Refugee: 155 (38% F) | Displaced 322 (37.9% F), refugees: 308 (35.7% F) | Displaced 446 (38% F), refugees: 381 (38% F)
Source
Annual TB reports (PU-AMI/SMRU)
| Output Indicator 3.7 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015 | Assumption
| Total no. cases treated at Mae Tao Clinic and Pa Hite Clinic in medical inpatient & outpatient, RH, surgical, eye and dental departments (excludes acupuncture) - (male/female) | Planned | 103372 | 108541 | 113968 | 119666 | Pharmacy audits are up to date, orders sent to Crown Agents on time, deliveries arrive on time, correct stock supplied, staff dispense correct medication, pharmacy procedures are adhered to and regularly updated
|  | Achieved |  | 58260 | Female = 81,033, Male = 46,011 (total = 118,628) | 43,483 (Female = 26,716 or 61%)
Source
MTC's 6-monthly report
IMPACT WEIGHTING (%) | [6 empty] | RISK RATING
30% | [6 empty] | Risk: Medium
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
| 7000000 | (HPA, MTC, TTBI) | 0 | 9714690 | 16714690 | 41.88%
INPUTS (HR) | DFID (FTEs)
50% FTE Humanitarian Coordinator (Bangkok). 50% Programme Officer (Bangkok). 5% Evaluation Adviser (DFID Vietnam). 5% Economic Adviser (DFID Burma). 10?% Senior Governance Adviser (DFID Burma)
OUTPUT 4 | Output Indicator 4.1 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015 | Assumptions
Refugee communities have increased opportunities to access justice, protection and good governance from accountable refugee leadership and local authorities. | Percentage of all appropriate serious crimes reported to the camp justice committee or LAC that are successfully referred (with client consent) to the Thai justice system. | Planned | 93% appropriate serious crimes camps reported in 5 camps | 95% appropriate serious crimes reported in 5 camps | 98% appropriate serious crimes reported in 5 camps | 100% appropriate serious crimes reported in 5 camps | • Enabling environment prevails • Appropriate policies and practices supported by the Government of Myanmar and other stakeholders - Cooperation by local authorities (both in Thailand and in Burma) • Central level engagement continues to be possible ; • RTG Ministry of Interior continues to grant IRC access to refugee camps along the Thai-Burma border. • Continued willingness of Thai government justice system to take on cases from refugee camps. • Security situation in camps remains stable. • Significant numbers of trained paralegals do not apply for resettlement to third countries (these are currently selected from individuals with no resettlement plans). • Continued engagement of the Ministry of Interior and Ministry of Justice in the development of guidelines.
|  | Achieved |  | 100% (39/39) appropriate serious crime reported in 5 camps | 100% (33/33) of appropriate serious crimes reported (17 female cases and 16 male). | 100% (28/28) of appropriate serious crimes (5 or 17.86% were female and 23 or 82.14% were male cases) have been reported.
Source:
IRC LAC database and annual reports.
| Output Indicator 4.2 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015
| Percentage of local authorities, refugee community leadership and members, and civil society demonstrate improved knowledge and skills in mediation, conflict and dispute resolution, administration of justice and good governance principles. | Planned | 41% | 50% | 60% | 70%
|  | Achieved |  | 72.57% (426/584) | 65.41% (658/1,006) | 65.52% (325/496)
Source:
IRC LAC's Annual assessment on protection, access to justice and rule of law with sampled refugee camp population.
| Output Indicator 4.3 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015
| Number of refugee community members (male and female) receive high quality, tailored counselling, referral and follow up services. | Planned | 291 clients in original camps and 78 in newer camps receive legal counselling, referral and follow up services. | 300 Clients in original camps and 120 in newer camps receive legal counselling, referral and follow up services. | 300 Clients in original camps in and 150 in newer camps receive legal counselling, referral and follow up services. | 300 Client in original camps and 170 in newer camps receive legal counselling, referral and follow up services.
|  | Achieved |  | 199 clients in original camps and 100 clients in new camps | 259 clients (83 female and 176 male) in original camps and 108 clients (58 female and 50 male) in newer camps (82% of 2014 | 183 clients (83 females)
Source:
LAC database and annual reports
| Output Indicator 4.4 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015
| Percentage of gender-based violence and child protection cases reported to IRC receive coordinated and comprehensive support services. | Planned | 0% - no written protocol between agencies outside / inside camps | 70% of cases | 85% of cases | 95% of cases
|  | Achieved |  | 100 | 100 | 100% (37/37)
Source:
LAC database, case checklist, annually.
INPUTS (HR) | DFID (FTEs)
IMPACT WEIGHTING (%)
10%
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
| 2013876 | 100% LAC | 0 | 1370089 | 3383965 | 59.51% | Risk: Medium
INPUTS (HR) | DFID (FTEs)
50% FTE Humanitarian Coordinator (Bangkok). 50% Programme Officer (Bangkok). 20% Evaluation Adviser (DFID Vietnam). 20% Economic Adviser (DFID Burma). 20% Senior Governance Adviser (DFID Burma)
OUTPUT 5 | Output Indicator 5.1 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015 | Assumption
Greater capacity and engagement on the peace process for women | A timely joint funding mechanism in place to support the peace process and address inter-communal violence work in Burma. | Planned | 0 | The fund framework formulated and agreed with all key partners. | Liason offices in ceasefire areas established and operational. | Pilot projects well underway and scaled up. | Government continues to welcome donors' support to the peace keeping process. - The political and economic environment in Burma does not get worse. -Consultations with key partners of the peace keeping and recovery process including with local communities is supported by the Govenrment.
|  | Achieved |  | Delayed | The Peace Support Fund is fully up and running and has begun dispersing grants in support of the peace process and to address inter-communal violence. Liaison Offices in ceasefire areas are established and operational, though UK funding was not required for this initial phase.
Source:
The fund management office reports, annually.
| Output indicator 5.2 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015
| a. Number of women who have been trained in order to build their capacity for engagement on the peace process b. Number of women who have directly engaged in the official peace dialogue / ceasefire process | Planned | 0 | 2 measures in place | 0 | 4 measures.
|  | Achieved |  |  | Decision was made not to progress with this type of interventions in the light of increased need to directly support peace process initiatives.
Source:
The fund management office reports, annually.
| Output Indicator 5.3 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015
| Number of initiatives supporting the peace process and/or addressing inter-communal violence. | Planned | 0 | 6 | 9 | 21
|  | Achieved |  | 9 (TBC) | 7 (TBC), The Peace Support Fund is fully up and running and has agreed funding for 5 initiatives (Oct 2014), has rejected 9 proposals and 13 are currently being appraised
Source:
TBC Bi-annual report and NIS annual report
IMPACT WEIGHTING (%) | [6 empty] | RISK RATING
15% | [6 empty] | High
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
| 4500000 | 100% Peace Support Fund contributed by DFID | 0 | TBC | 4500000 | 100%
INPUTS (HR) | DFID (FTEs) | a
50% FTE Humanitarian Coordinator (Bangkok). 50% Programme Officer (Bangkok). 20% Evaluation Adviser (DFID Vietnam). 20% Economic Adviser (DFID Burma). 20% Senior Governance Adviser (DFID Burma)
OUTPUT 6 | Output Indicator 6.1 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015 | Assumption
Optimal fund management results in generated evidence utilised to inform policy, funding, and programming decisions; and improved fiduciary risk management. | Availability of an M&E framework by each subproject to collect data and evidence on sub-project activities which include tools for collecting feedback from refugees and displaced people. | Planned | NA | The framework formulated and agreed with all key partners. | annual reports generated from the framework | Final report on M&E and project results. | • Government enables access for implementation and monitoring • Implementing partners have capacity to effectively monitor their programmes
|  | Achieved |  | Yes | Yes | To postpone until end of cost-extension phase
Source:
Programme M&E report (Annual).
| Output indicator 6.2 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015
| Availability of accurate, up-to-date information on refugee and IDP populations to stakeholders (UNHCR, agencies, CBOs in Thailand and Burma). | Planned | 12 monthly updates | 12 updates reflecting monthly population changes. | 12 updates reflecting monthly population changes. | 12 updates reflecting monthly population changes.
|  | Achieved |  | Yes | Yes | Yes
Source:
Monthly population report; TBC monthly Population maps.
| Output Indicator 6.3 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015
| Number of refugee camps using information technology (laptops) to complete Ration Distribution Register (RDR) at food distributions. | Planned | 1 camp piloting IT. Draft IT strategy developed. | 2 camps piloting IT. Review of IT use and strategy. | 4 camps piloting IT. | 9 Camps use computers for RDR data.
|  | Achieved |  | 5 camps | 5 camps | 5 camps
Source:
Post-distribution monitoring surveys, staff reports, TBC programme reports.
| Output Indicator 6.4 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015
| Availability of an evaluation framework for the programme which includes a repeat of the VFM evaluation. | Planned | NA | A framework developed. Start baseline data collection. | Mid-term review evaluation. | VFM evaluation and possible an evaluation of impact.
|  | Achieved |  | Yes | Complete | To postpone until end of cost-extension phase
Source:
Programme annual monitoring reports.
IMPACT WEIGHTING (%) | [6 empty] | RISK RATING
5% | [6 empty] | High
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
| 2350416 | 100% of DFID funds for M&E and fiduciary risk | 0 | TBC | 2350416 | 100%
INPUTS (HR) | DFID (FTEs)
50% FTE Humanitarian Coordinator (Bangkok). 50% Programme Officer (Bangkok). 20% Evaluation Adviser (DFID Vietnam). 20% Economic Adviser (DFID Burma). 20% Senior Governance Adviser (DFID Burma)
Footnotes:
Impact Indicator 1- Data source: | Annual targets are based on mortality rates for East Asia & Pacific region. An increase to twice the target (16 per 1000) would indicate a significant public health emergency.
Purpose Indicator 1 - Data source: | Annual targets are based on mortality rates for East Asia & Pacific region. An increase to twice the target (14 per 1000) would indicate a significant public health emergency.
Target for indicator 7.5: the target will be defined and agreed by partners after the project has been approved.

## Cost-extension phase
Project Name | Assistance to Refugees and Internally Displaced People 2012-2016
Impact | Impact Indicator 1 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015 | Target 2016
Improve the quality of life and reduce the vulnerability of refugees and displaced persons along Burma’s border, including preparation for their voluntary return. | Under 5 mortality rate (U5MR) in Burmese refugee camps in Thailand. (DFID standard outcome indicator) | Planned | 4/1000 | annual: <8/1000 | annual: 8 </1000 | annual: 8</1000 | annual <4/1000
|  | Achieved |  | To be assessed | To be assessed
Source:
Baseline data was from The Border Consortium's bi-annual programme report for mortality rates. UNESCAP's 2011 statistical yearbook for Asia and the Pacific.
| Impact Indicator 2 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015 | Target 2016
| Percentage of surveyed refugee community members express satisfaction with justice and protection system. | Planned | Satisfaction: 68% | 75% | 78% | 78% | 78%
|  | Achieved |  | 71.7% | 74.35%
Source:
Baseline: IRC LAC Assessment on Protection, Access to Justice and the Rule of Law in camps. Y2: random sampling Y3: Repeat Assessment and Project Evaluation. Collected by IRC Legal Assistance Centre Staff and External Evaluator. Note: Sex disaggregated targets will be developed in the first 3 months of the project.
| Impact Indicator 3 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015 | Target 2016
| Percentage of women in refugee camp management. (Camp Committees, security and other stipend positions). | Planned | 33% | 35% | 40% | 45% | 45%
|  | Achieved |  | 35% | 40% | 38%
Source:
The Border Consortium's bi-annual programme report.
| Impact Indicator 4 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015 | Target 2016
| Number of displaced people who opt for voluntary return to eastern Burma. | Planned |  |  |  |  | 30,000 returnees to Burma as documented by the monthly population records are assisted. (cumulative)
|  | Achieved |  |  |  |  | 0
Source:
UNHCR and Government and project data, annually. TBBC annual reports.
| Impact Indicator 4 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015 | Target 2016
| Number of maternal deaths reported in hospitals/health centres in targeted areas of Kachin/Shan by TBAs in the past year. | Planned | 61 | 64 | 49 | 33 | 22
|  | Achieved |  | 13 | 17 | 10 | 14
Source:
Hospital / health centre project staff. records collected by the local health authorities in conjunction with HPA
OUTCOME | Outcome Indicator 1 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015 | Target 2016 | Assumptions
Meet more of the basic humanitarian needs of Burmese refugees and displaced and persons in conflict-affected border areas in Burma; and equip them with the knowledge and skills for return and reintegration to Burma. | Percentage of births attended by skilled health personnel in targeted areas of Kachin/Shan (doctors, nurses, midwives or trained AMW). | Planned | 22.47% | 25.5% | 26.9% | 29.3% | 32.1% | • RTG Ministry of Interior continues to grant NGO partners access to refugee camps. • Good cooperation between health agencies. • Security situation in camps remains stable. • Dramatic reductions in other donors’ contributions to TBC do not undermine its ability to meet the basic needs of refugees. • Other donors contribute extra support to community-based organisations providing assistance to IDPs. • Refugees and IDPs remain largely isolated from the effects of the global economic downturn.
|  | Achieved |  | 18% | 22.39% | 19.7% | 19.01%
Source:
HPA's household annual surveys
| Outcome Indicator2 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015 | Target 2016
| Children under 5 acute malnutrition rates in refugee and IDP camps. | Planned | 2% across 9 refugee camps: WHO 2005 Growth Standards (2011 Nutrition Surveys) | annual: <5% | annual: <5%. Nutrition surveys data available early 2014. | Under 5% in refugee and under 3% in IDP camps/beneficiaries in SE Burma/Myanmar | Under 5% in refugee and under 3% in IDP camps/beneficiaries in SE Burma/Myanmar
|  | Achieved |  | 2.1% | 2.1% | 2.1% (wasting), 35.1% (stunting rate) in refugees
Source:
Nutrition Surveys (biennial), TBC IDP Survey, TBC SE Burma Programme reports (annual)
| Outcome Indicator 3 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015 | Target 2016
| Number of people in communities affected by conflict and displacement benefiting from community-based humanitarian relief. | Planned | 0 | 58446 | 63200 | 70000 | To be negotiated
Achieved
Source:
Village profile (PRA records), project records, mid-term evaluation and end of project evaluation.
| Outcome Indicator 4 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015 | Target 2016
| Number of businesses established following entrepreneurial development including female businesses supported by the programme. | Planned | 478 businesses | 200 | 200 | 600 | 670
|  | Achieved |  | 556 | 540 (F=435) | 1064 | 160 (as of May 2016)
Source:
TBC bi-annual programme report, Entrepreneurship Development, Grant, Savings & Loans Project (EDGSLP) Monitoring System Data (annual).
| Outcome Indicator 5 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015 | Target 2016
| Number of returnees assisted with cash transfers at the point of departure from refugee camps. This indicator will be deleted as the activity of cash transfer will no longer exist (decision as of July 2016). | Planned | 0% |  |  |  | 15,000 (annual)
Achieved
Source:
TBC bi-annual programme report, Entrepreneurship Development, Grant, Savings & Loans Project (EDGSLP) Monitoring System Data (annual).
| Outcome Indicator 6 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015 | Target 2016
| Percentage of refugee communities members report overall satisfaction with Legal Assistance Centre project activities. | Planned | 0% (pending development of community accountability scorecards) | 60% | 65% | 65% | 65%
|  | Achieved |  | 97.1% | 100% |  | 99.86% (5773/5781)
Source:
IRC LAC 's Annual assessment on protection, access to justice and rule of law with sampled refugee camp population by LAC.
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
| 9570000 |  | 0 | 0 | 9570000 | 100%
INPUTS (HR) | DFID (FTEs)
40% Humanitarian Adviser (Burma), 45% Programme Officer (Bangkok). 5% Evaluation Adviser (DFID Vietnam). 5% Economic Adviser (DFID Burma). 5% Senior Governance Adviser (DFID Burma)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015 | Target 2016 | Assumption
Effective delivery of food and relief items and other means to enable refugees / IDPs to sustain a basic livelihood for voluntary durable solutions. | Number of displaced persons (in Thailand, eastern Burma and Kachin) have access to food or cash assistance in camps or as initial support to returning populations.* | Planned | 139,771 refugees (69,459 F, 70,312 M) 17,595 IDPs (8,719 F; 8,876 M) (April 2012) | 139,000 (68,945 F; 70,055 M) refugees in 9 camps 17,000 in IDP (8,415 F, 8,585 M) camps and resettlement sites | Remaining caseloads in camps | Remaining caseloads in camps at 110,000 persons | Remaining caseloads in Thai/Burma border camps at 90,000. Support to 30,000 returnees. In Kachin - 11,000 IDPs | • Donor commitment to funding. • Partners continue to be able to access IDP communities. • Sufficient commodities available in market place. • Royal Thai Government allow appropriate levels of independence for aid agencies to operate.. • Other donors contribute extra support to community-based organisations providing assistance to IDPs. - Cross border access maintained for aid agencies.
|  | Achieved |  | 127,038 (F: 63915, M: 63123)/ IDP: 133,396 | 120112 (as of July 14), IDP: 12791 | 104,316 ( with F=50% as of December 2015)/ IDPs - In (12,307)/outside (25,955) camps in SE): 44,302 persons | 103,762 ( with F=50% or 52,543 as of August 2016)/ IDPs - 9,107 (female: 4,442)/displaced outside the camp in SE): ??persons In Kachin - 8,800 IDPs
Source:
Monthly Population Report (MPR), Monthly Monitoring Report (MMR), Nutrition Surveys, TBC SE Burma / Myanmar Annual Programme Report, TBC Bi-annual Programme Report. * Wording amended in Year 4 to include Kachin
| Output Indicator 1.2 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015 | Target 2016
| Number of HH benefiting from livelihood in-kind grants (e.g. pig banks, cow bank, solar lighting, homestead garden and vermi-composting). | Planned | 0 | 370 HHs benefitting from livelihood in-kind grants | 660 HHs benefitting from livelihood in-kind grants | 900HHs benefitting from livelihood in-kind grants
|  | Achieved |  | Data disaggregated on yearly basis is not available. Only the achievements to date data are available | 2,851 HH benefitting from livelihood in-kind grants
Source:
FLD and KND's Delivery Reports, Quarterly Reports and End of Year Report
| Output Indicator 1.3 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015 | Target 2016
| Number of vulnerable people suffering livelihood shocks in SE Burma that receive cash equivalent to 3 months supply of rice or assisted through rehabilitation initiatives (to improve livelihood, economic opportunities and social protection). | Planned | 451093 (2006-2012) | 45,000 people in SE Burma (22,500 F, 22,500 M) | 45,000 people in SE Burma (22,500 F, 22,500 M) | 20,000 people in SE Burma (annual) | 120,000 people in SE Burma
|  | Achieved |  | 42173 | 29000 | 53000
Source:
TBC's Bi-annual Programme Report
| Output Indicator 1.4 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015 | Target 2016 | Assumption
| Number of stipend work jobs created (temporary, part-time, and full time), including for women and vulnerable population groups. | Planned | 2485 |  |  |  | 3,600 (cumulative) | Continued engagement of the Burmese government, Ministry of Interior and Ministry of Justice in developing any guidance on refugees and their return; Political and social conditions in Burma are progressive and positive for voluntary return.
Achieved
Source:
Stipend staff regular records, Activity participant regular records, TBC programme reports (biannual)
| Output Indicator 1.5 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015 | Target 2016
| Number of refugee community members who have received information on Myanmar legal framework relevant to potential refugee and IDP return. (male/female) | Planned | 0 | 7000 all 5 camps (cumulative) | 7500 all 5 camps (cumulative) | 8000 all 5 camps (cumulative) | 5000 in all 5 camps (annual)
|  | Achieved |  | 0 | 28% (as of May 2014) | 6512 | 4,573 (as of May 2016)
Source:
Community dissemination activity records (regular) by LAC.
IMPACT WEIGHTING (%) | Output Indicator 1.6 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015 | Target 2016
15% | Number of diverse trainings that participants engage in (including camp residents, refugee representatives and CBO partners) with emphasis on capacities needed for return. | Planned |  |  |  |  | Camp-based participants engaged in 730 trainings (cumulative)
Achieved
|  |  | Source: |  |  |  |  | RISK RATING
|  |  | IRC LAC Programme Narrative report |  |  |  |  | Low
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
| 1855670 | (TBC, HPA, FLD,KDN) | 0 | 19291507.5 | 21147177.5 |  | 9%(TBC)
INPUTS (HR) | DFID (FTEs)
40% Humanitarian Adviser (Burma), 45% Programme Officer (Bangkok). 5% Evaluation Adviser (DFID Vietnam). 5% Economic Adviser (DFID Burma). 5% Senior Governance Adviser (DFID Burma)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015 | Target 2016 | Assumptions
Effective delivery of needs-based humanitarian assistance to people in communities in Burma affected by displacement and conflict. | Number of people directly assisted by food security programmes (via village-based community mechanisms (e.g. rice banks). (DFID Standard Indicator) | Planned | 0 |  |  |  | Needs negotiating with partners | • No major changes in the political situation affecting border areas. • Partners continue to be able to access IDP communities. • Reliable data can be collected on support to IDPs. • Collection of new baseline data on vulnerable populations. • Other donors contribute extra support to community-based organisations providing assistance to IDPs.
Achieved
Source:
FLD and KDN's Delivery Report, Quarterly Reports and Rice Bank End Year Report, HPA progress report
| Output Indicator 2.2 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015 | Target 2016
| Number of people with sustainable access to an improved sanitation facility as a result of DFID support (cumulative). (DFID Standard Indicator) | Planned | 29369 | 32919 | 37394 | 38762 | 45432
|  | Achieved |  | 32769 | 37784 | 44307 | 44445
Source:
HPA Work records (annual) - Humanitarian and health
| Output Indicator 2.3 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015 | Target 2016
| Number of households provided with new/improved drinking water sources. (DFID Standard Indicator) | Planned | - 40 communities in target 60 communities (AAM/KDN) '- 10,352 (9,690+662) HHs from 142 villages (132+10) provided with improved drinking water sources (STC FLD) - 1,282 HHs (1.53%) (HPA) | - 60 communities in target 90 communities (AAM/KDN) '- 11,632 (10,352+1,280) HHs in 158 (142+16) villages provided with improved drinking water (STC FLD) - 1,397 HHs (HPA) | - 60 communities in target 90 communities (AAM/KDN) '- 12,912 (11,632+1,280) HHs in 174 (158+16) from 174 (158+16) villages provided with improved drinking water sources (STC FLD) - 1,817 HHs (HPA) | - 60 communities in target 90 communities (AAM/KDN) '- 12,912 (11,632+1,280) HHs in 174 (158+16) from 174 (158+16) villages provided with improved drinking water sources (STC FLD) - 3,464 HHs (HPA) | BPHWT 1. Gravity flow = 9,000 (W-4,900 & M-4,100) 2. Shallow well = 1,750 (W-965 & M-785) (annual) - 4,924 HHs (HPA)
|  | Achieved |  | - 2,272 HHs (HPA) | 5,192 HHs (STC FLD) in 138 villages 1,866 HHs (AAM KDN) 2,998 HHs (HPA) | - 4,229 HHs (HPA) | - 4,545 HHs (HPA)
Source:
FLD, HPA, KDN, BPHWT Work records and project reports from community organisations (annual).
IMPACT WEIGHTING (%) | Output Indicator 2.4 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015 | Target 2016
25% | Number of communities are able to prioritise, plan and implement community action points | Planned | 0 |  |  | 70 communities in the 90 target areas are able to prioritised, plan and implement community action points | Needs negotiating with partners
Achieved
|  |  | Source: |  |  |  |  | RISK RATING
|  |  | KDN and FLD ' participatory reviews and monitoring visit reports, programme reports, end of project evaluation report. |  |  |  |  | High
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
| 802392 | (100%FLD+ 100%KND) | 0 | 0 | 802392 | 100%
INPUTS (HR) | DFID (FTEs)
40% Humanitarian Adviser (Burma), 45% Programme Officer (Bangkok). 5% Evaluation Adviser (DFID Vietnam). 5% Economic Adviser (DFID Burma). 5% Senior Governance Adviser (DFID Burma)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015 | Target 2016 | Assumption
Improved health awareness and access to basic health facilities and services in the programme communities. | Full immunization coverage of children under two years old in the programme communities. | Planned | 25.82% | 42.3% | 45.8% | 49.9% | 52% | • Local Medical Officers are cooperative ; -No major external shortage/problems in medical and health supplies • Access to all sites continues • Baselines can be collected • There is sufficient M&E capacity to collect HH surveys
|  | Achieved |  | 19.22% | Not yet available | 34.4% | 29.5%
Source:
Baseline: HPA's Household survey in February 2012. Milestone 1: Estimate based on observation and records of TBAs, MWs and VHC. Milestone 2: Household survey in June 2014. Target: Household survey in June 2014.
| Output Indicator 3.2 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015 | Target 2016
| Number of pregnant women who receive at least 4 antenatal care visits as a results of DFID funding in the programme communities. | Planned | 2210 | 4910 | 8020 | 8563 | 9413
|  | Achieved |  | 4864 | Not yet available | 13306 | 14228
Source:
HPA 's Work records of TBAs and health facilities collected by HPA project staff.
| Output Indicator 3.3 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015 | Target 2016
| Percentage of population aware of key messages related to personal hygiene, health and environmental sanitation in the project villages. | Planned | 27.56% |  |  | 44.4% | 48.7%
|  | Achieved |  |  |  |  | 32.1%
Source:
Baseline: HPA's Household survey in February 2012. Milestone 1: Estimate based on observation and records of TBAs, MWs and VHC. Milestone 2: Household survey in June 2014. Target: Household survey in June 2014.
| Output Indicator 3.4 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015 | Target 2016
| Correct Knowledge of malaria prevention and treatment | Planned |  |  |  | 36.4% | 38.1%
|  | Achieved |  |  |  |  | Data not available yet
Source:
HPA's work records
| Output Indicator 3.5 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015 | Target 2016
| Percentage of children under 5 years old treated with ORS after diarrhoea episode in last 14 days in programme villages. | Planned | 21.99% | 23.54% | 28.04% | 27.9% | 30.4%
|  | Achieved |  | 9.02% | Not yet available | 16.32% | 34.03%
Source:
Baseline: HPA's Household survey in February 2012. Milestone 1: Estimate based on observation and records of TBAs, MWs and VHC. Milestone 2: Household survey in June 2014. Target: Household survey in June 2014.
| Output Indicator 3.6 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015 | Target 2016 | Assumption
| Number of patients treated (registered) for TB | Planned | Displaced (73; 36% female) Refugee (98; 38% female) | Displaced (125-175) Refugee (210-270) 30-40% female | Displaced (280-340) Refugee (470-600) 30-40% female | Displaced (450-550) Refugee (730-930) 30-40% female | Displaced (380-440) Refugee (150-200) 30-40% female | -Caseload of TB, including MDR and XDR strains can be effectively managed by SMRU’s TB clinic. -Continued support for the programme by Thai and Burmese local authorities
|  | Achieved |  |  | Displaced 322 (37.9% F), refugees: 308 (35.7% F) | Displaced 446 (38% F), refugees: 381 (38% F)
Source:
Annual TB reports (PU-AMI/SMRU)
IMPACT WEIGHTING (%) | Output Indicator 3.7 |  | Baseline 2012 | Milestone 2013 | Milestone 2014 | Target 2015 | Target 2016 | Assumption
30% | Total number of displaced people receiving access to primary healthcare (male/female) through Mae Tao Clinic and Pa Hite. | Planned | 100,557 (MTC) |  |  |  | 42,000 (MTC, Female 60%) | Pharmacy audits are up to date, orders sent to Crown Agents on time, deliveries arrive on time, correct stock supplied, staff dispense correct medication, pharmacy procedures are adhered to and regularly updated. Access is not blocked by conflicts in Kachin.
|  | Achieved |  |  |  |  | 39,217 (total female = 26,993) as of 31 May 2016
Source:
MTC's 6-monthly report/ HPA's progresss report
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%) |  | RISK RATING
| 4173741 | (100%HPA)(100%TTBI)(100% MTC) | 0 | 0 | 4173741 | 100% |  | Risk: Medium
INPUTS (HR) | DFID (FTEs)
40% Humanitarian Adviser (Burma), 45% Programme Officer (Bangkok). 5% Evaluation Adviser (DFID Vietnam). 5% Economic Adviser (DFID Burma). 5% Senior Governance Adviser (DFID Burma)
OUTPUT 4 | Output Indicator 4.1 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015 | Target 2016 | Assumptions
Refugee communities have increased opportunities to access justice, protection and good governance from accountable refugee leadership and local authorities. | Percentage of all appropriate serious crimes reported to the camp justice committee or LAC that are successfully referred (with client consent) to the Thai justice system. | Planned | 93% appropriate serious crimes camps reported in 5 camps | 95% appropriate serious crimes reported in 5 camps | 98% appropriate serious crimes reported in 5 camps | 95 % appropriate serious crimes reported in 5 camps | 95 % appropriate serious crimes reported in 5 camps | • Enabling environment prevails • Appropriate policies and practices supported by the Government of Myanmar and other stakeholders - Cooperation by local authorities (both in Thailand and in Burma) • Central level engagement continues to be possible ; • RTG Ministry of Interior continues to grant IRC access to refugee camps along the Thai-Burma border. • Continued willingness of Thai government justice system to take on cases from refugee camps. • Security situation in camps remains stable. • Significant numbers of trained paralegals do not apply for resettlement to third countries (these are currently selected from individuals with no resettlement plans). • Continued engagement of the Ministry of Interior and Ministry of Justice in the development of guidelines.
|  | Achieved |  | 100% (39/39) appropriate serious crime reported in 5 camps | 100% (33/33) of appropriate serious crimes reported (17 female cases and 16 male).
Source:
IRC LAC database and annual reports.
| Output Indicator 4.2 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015 | Target 2016
| Percentage of local authorities, refugee community leadership and members, and civil society demonstrate improved knowledge and skills in mediation, conflict and dispute resolution, administration of justice and good governance principles. | Planned | 41% | 50% | 60% | 70% | 70%
|  | Achieved |  | 72.57% (426/584) | 65.41% (658/1,006) (109.01% of the 2014 milestone)
Source:
IRC LAC's Annual assessment on protection, access to justice and rule of law with sampled refugee camp population.
| Output Indicator 4.3 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015 | Target 2016
| Number of refugee community members (male and female) receive high quality, tailored counselling, referral and follow up services. | Planned | 291 clients in original camps and 78 in newer camps receive legal counselling, referral and follow up services. | 300 Clients in original camps and 120 in newer camps receive legal counselling, referral and follow up services. | 300 Clients in original camps in and 150 in newer camps receive legal counselling, referral and follow up services. | 300 Client in original camps and 170 in newer camps receive legal counselling, referral and follow up services. | 200 Client in 5 camps
|  | Achieved |  | 199 clients in original camps and 100 clients in new camps | 259 clients (83 female and 176 male) in original camps and 108 clients (58 female and 50 male) in newer camps (82% of 2014
Source:
LAC database and annual reports
IMPACT WEIGHTING (%) | Output Indicator 4.4 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015 | Target 2016
10% | Percentage of gender-based violence and child protection cases reported to IRC receive coordinated and comprehensive support services. | Planned | 0% - no written protocol between agencies outside / inside camps | 70% of cases | 85% of cases | 95% of cases | 95% of cases
|  | Achieved |  | 90% | 100%
|  |  | Source: |  |  |  |  | RISK RATING
|  |  | LAC database, case checklist, annually. |  |  |  |  | Medium
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
| 678000 | (100% LAC) | 0 | 46311 | 724311 | 93.61%
INPUTS (HR) | DFID (FTEs)
40% Humanitarian Adviser (Burma), 45% Programme Officer (Bangkok). 5% Evaluation Adviser (DFID Vietnam). 5% Economic Adviser (DFID Burma). 5% Senior Governance Adviser (DFID Burma)
OUTPUT 5 | Output Indicator 5.1 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015 | Target 2016 | Assumption
Greater capacity and engagement on the peace process for women | Number of initiatives supporting the peace process and/or addressing inter-communal violence. | Planned | 0 | 6 | 9 | 21 | 27 | Government continues to welcome donors' support to the peace keeping process.
|  | Achieved |  |  | 4
Source:
TBC Bi-annual report
IMPACT WEIGHTING (%)
15%
RISK RATING
High
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
| 4500000 | 100% Peace Support Fund contributed by DFID | 0 | TBC | 4500000
INPUTS (HR) | DFID (FTEs)
40% Humanitarian Adviser (Burma), 45% Programme Officer (Bangkok). 5% Evaluation Adviser (DFID Vietnam). 5% Economic Adviser (DFID Burma). 5% Senior Governance Adviser (DFID Burma)
OUTPUT 5 | Output Indicator 5.1 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015 | Target 2016 | Assumption
Optimal fund management results in generated evidence utilised to inform policy, funding, and programming decisions; and improved fiduciary risk management. | Availability of an M&E framework by each subproject to collect data and evidence on sub-project activities which include tools for collecting feedback from refugees and displaced people. | Planned | NA | The framework formulated and agreed with all key partners. | annual reports generated from the framework | annual reports generated from the framework | Final report on M&E and project results. | • Government enables access for implementation and monitoring • Implementing partners have capacity to effectively monitor their programmes
|  | Achieved |  | Yes | Yes | Yes
Source:
Programme M&E report (Annual).
| Output indicator 5.2 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015 | Target 2016
| Availability of accurate, up-to-date information on refugee and IDP populations to stakeholders (UNHCR, agencies, CBOs in Thailand and Burma). | Planned | 12 monthly updates | 12 updates reflecting monthly population changes. | 12 updates reflecting monthly population changes. | 12 updates reflecting monthly population changes. | 12 updates reflecting monthly population changes.
|  | Achieved |  | Yes | Yes | Yes
Source:
Monthly population report; TBC monthly Population maps.
| Output Indicator 5.3 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015 | Target 2016
| Number of refugee camps using information technology (laptops) to complete Ration Distribution Register (RDR) at food distributions. | Planned | 1 camp piloting IT. Draft IT strategy developed. | 2 camps piloting IT. Review of IT use and strategy. | 4 camps piloting IT. | 9 Camps use computers for RDR data. | 9 Camps use computers for RDR data.
|  | Achieved |  | 5 camps | 5 camps | 5 camps
Source:
Post-distribution monitoring surveys, staff reports, TBC programme reports.
IMPACT WEIGHTING (%) | Output Indicator 5.4 |  | Baseline 2011 | Milestone 2013 | Milestone 2014 | Target 2015 | Target 2016
5% | Availability of an evaluation framework for the programme which includes a repeat of the VFM evaluation. | Planned | NA | A framework developed. Start baseline data collection. | Mid-term review evaluation. | Move target to 2016 for final impact evaluation | VFM evaluation and a possible evaluation of impact.
|  | Achieved |  | Yes | Complete | To be completed by end of Year 2016
|  |  | Source: |  |  |  |  | RISK RATING
|  |  | Programme annual monitoring reports. |  |  |  |  | High
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%) | DFID SHARE (%)
| 250000 | 100% of DFID funds for M&E and fiduciary risk | 0 | 0 | 250000 |  | 100%
INPUTS (HR) | DFID (FTEs)
40% Humanitarian Adviser (Burma), 45% Programme Officer (Bangkok). 5% Evaluation Adviser (DFID Vietnam). 5% Economic Adviser (DFID Burma). 5% Senior Governance Adviser (DFID Burma)
Footnotes:
Impact Indicator 1- Data source: | Annual targets are based on mortality rates for East Asia & Pacific region. An increase to twice the target (16 per 1000) would indicate a significant public health emergency.
Purpose Indicator 1 - Data source: | Annual targets are based on mortality rates for East Asia & Pacific region. An increase to twice the target (14 per 1000) would indicate a significant public health emergency.
Target for indicator 7.5: the target will be defined and agreed by partners after the project has been approved.