DFID BUSINESS CASE
‘UK Aid Direct ’ Phase II of the Global Poverty Action Fund (GPAF)
ARIES Project: 202035

Civil Society Department / August 2014

# Table of Contents

Section 1:	Intervention Summary	4
Section 2:	Strategic Case	9
Section 3:	Appraisal Case	14
Section 4:	Commercial Case	28
Section 5:	Financial Case	30
Section 6:	Management Case	34

Annex A	Logframe
Annex B	UK Aid Direct stakeholders and communications approach
Annex C	Submission: Refreshing the Global Poverty Action Fund (GPAF) - agreed by the Secretary of State on 16 May 2014

# List of Figures and Tables
Figure 1: UK Aid Direct results	8
Table 1: Resource Implications of Round 1	19
Table 2: Estimated beneficiaries from Round 1	19
Figure 2: UK Aid Direct Theory of Change diagram	24
Table 3: Cost per beneficiary from GPAF	26
Table 4: Risk Matrix for UK Aid Direct	38

# Key supporting documents
GPAF Mid Term Evaluation Report, April 2014	Quest no: 4522916
GPAF Fund Manager Annual Report 2013/14	Quest no: 4615379
GPAF Fund Manager Quarterly Report, 1 April – 30 June 2014	Quest no: 4615375
GPAF Fund Manager’s Quarterly Report, 1 January – 31 March 2014	Quest no: 4522937
GPAF Portfolio Analysis and Update, June 2014	Quest no: 4615393
GPAF Refresh: Defining a Future Learning Strategy, 2 April 2014	Quest no: 4461575
GPAF Annual Review August 2013	Quest no: 4358755
GPAF ‘One Year On’ Review	Quest no: 3532950

# Abbreviations and Acronyms
BOND	UK membership body for organisations working in international development
BF	Beneficiary feedback
CHASE	Conflict, Humanitarian and Security Department (DFID)
CGI	Common Ground Initiative
CN	Concept note
CPB	Cost per beneficiary
CSCF	Civil Society Challenge Fund
CSD	Civil Society Department (DFID)
CSO	Civil Society Organisation
DALYS	Disability adjusted life years
DD	Due diligence
DFID	UK Department for International Development
FM	Fund Manager
FY	Financial Year
GPEDC	Global Partnership for Effective Development Co-operation
GPAF	Global Poverty Action Fund
HDI	Human Development Index
IATI	International Aid Transparency Initiative
ICAI	Independent Commission on Aid Impact
M&E	Monitoring and Evaluation
MDGs	Millennium Development Goals
MTE	Mid Term Evaluation of the GPAF (Coffey, April 2014)
NFPs	Not for Profit organisations
NIDOS	Network of International Development Organisations in Scotland
NPV	Net present value
OJEU	Official Journal of the European Union
PCD	Procurement and Commercial Department (DFID)
PL	Proposal
SRO	Senior Responsible Official
SRP	Structural Reform Plan
VFM	Value for money

# Section 1: Intervention Summary

Title: UK Aid Direct: Phase II of the Global Poverty Action Fund

What support will the UK provide?
As UK Aid Direct the UK will establish and finance a flexible medium-term programme of support to small and medium sized national and international Civil Society Organisations (CSOs) to reduce poverty through service delivery, livelihoods, empowerment, accountability and peace, security and justice.

The UK will provide minimum resources of £150 million over the next five years. Specific allocations by year have not been set, and with Ministerial agreement, there is scope for UK Aid Direct to absorb additional funds. In doing so, the UK will help deliver important development results, establish an on-going commitment to the role of civil society in poverty reduction, establish a medium-term and flexible facility for providing finance to civil society and generate evidence and learning for wider use in development.

UK Aid Direct is designed to be an adaptive, demand-led, fund with the ability to respond to UK development priorities in the context of a rapidly changing world and within a robust and value for money management mechanism that fully meets the UK’s requirement for managing public finances. It will follow closely the strategic direction set for DFID by Ministers through the Better Delivery agenda, combining flexibility, adaptiveness and judgement with sound management of public money and high-quality programme management.

UK Aid Direct will operate using an annual strategic investment decision cycle that will determine, with Ministerial guidance and approval, key investment decisions for the UK’s work with civil society. These may include thematic areas for concentration and results achievement, managing varying volumes of financing, opportunities for action, modalities for providing finance and geographical emphases.

The flexibility of the annual strategic investment decision cycle will be paired with the strong programme management and financial capability necessary to manage UK funds effectively and efficiently. UK Aid Direct will also provide capacity building skills to respond to CSO’s requirements to deliver poverty reduction and build capability, evidence, communications and learning skills and flexibility in decision-making and approach to respond to changing needs, contexts and priorities.

UK Aid Direct continues and extends the impact and reach of the Global Poverty Action Fund (GPAF) established in 2010. UK Aid Direct will incorporate and extend the high-quality programme management, emphasis on value for money and learning and evidence that has been central to the GPAF.

1. UK Aid Direct will focus strongly on communications including raising awareness of the fund among a broader range of eligible organisations; improving the grantee experience; and widening outreach and the knowledge of the benefits of development funding with Parliamentarians and the UK public.
2. UK Aid Direct will invest in and generate high-quality learning and evidence, working closely with other parts of DFID, to widen the impact of DFID investment in civil society and to contribute to DFID’s portfolio of interventions on policy and learning.

In order to continue the momentum achieved by GPAF the first funding round for UK Aid Direct will take place in September 2014, with a total amount of £30 million. This will use the existing structure established under GPAF but immediately introduce the enhanced communications and outreach elements of UK Aid Direct.

For the purposes of the analysis in the appraisal case and to demonstrate potential impact, the Business Case assessed what results would be delivered from this first competitive funding round a year starting in September 2014[1]. Economic analysis and results information for future investment decisions will be integrated within the choices proposed to Ministers at annual strategic investment decision points.
[1] The date of the first funding round will depend on approval of the Business Case

The September round of UK Aid Direct will follow GPAF in using (i) ‘impact’ grants for UK and international organisations working on medium/large scale poverty reduction programmes; and (ii) ‘community partnership’ grants for UK based CSOs with an annual income of less than £1 million, to support initiatives at the community level. UK Aid Direct will aim to allocate at least 10% of the available funds to small CSOs through community partnership grants. As above, the adaptive nature of UK Aid Direct means that future funding rounds may offer different opportunities and will not be fully determined at this stage and so have not been appraised or assessed within this business case.

As there are future choices to be made, to determine the potential of UK Aid Direct, following this Business Case, an extended Delivery Plan, setting out in more detail the choices for UK Aid Direct will be prepared.

Why is UK support required?
The UK Government is committed to halving the numbers of people living in poverty by 2015 through the achievement of the MDGs. This commitment is the central focus of the Department for International Development’s (DFID) work as set out in its Business Plan[2] and Structural Reform Plan (SRP), 2012-2015[3]. The UK is actively participating in the post-2015 process and UN Open Working Group to establish a new set of Sustainable Development Goals to be attained by 2030[4] and will be equally committed to achieving those goals.
[2] DFID (31 May 2012) Business Plan 2012-2015
[3] DFID (27 July 2010) Structural Reform Plan
[4] Open Working Group (2014) Zero Draft Proposed Goals and Targets on Sustainable Development for the Post 2015 Development Agenda

In meeting its commitments DFID recognises the contribution that civil society has to make to ‘finishing the job’ on the MDGs and achieving any new sustainable development goals by:
- reaching poor and marginalised people;
- helping poor people set standards for their lives and demanding that they be met;
- providing basic services and livelihoods in places that the government or private sector have not reached[5].
  [5] Gaventa, J and Barrett, G (2010) ‘So what difference does it make? Mapping the outcomes of citizen engagement’ IDS Research Summary of IDS Working Paper 347, Brighton IDS

CSOs are able to build relationships, trust and legitimacy, through their grass-roots knowledge of needs in developing countries. This is crucial part of the open societies required for tacking poverty and its underlying causes and creating economic growth and development. CSOs play an important role in delivering development assistance on fragile and conflict affected countries and regions. CSOs will remain a key part of the overall portfolio of action necessary to achieve poverty reduction. However, they also need to respond to changes in their contexts, which is why UK Aid will be adaptive in design, and to learn and use evidence, which is why UK Aid Direct will focus on evidence and learning.

Experience from GPAF shows that small CSOs are particularly well placed to learn local power structures and adapt activities to ensure effective delivery. They significantly add to the richness and diversity of development both in the UK and in the developing countries. They are often innovative, have strong links to the communities in which they operate, adopt nuanced approaches to meet the specific needs of people or organisations and have high levels of beneficiary accountability. This enhances the delivery of results and helps ensure sustainability. UK Aid Direct will allow all these qualities to be applied across DFID priorities.

GPAF has demonstrated success in reaching organisations that have not previously received DFID funding or that are small (54% of total grantees and 80% of current Community Partnership grant holders[6]) and 38% of grant holders are small organisations with less than a £1 million annual income. There are limited funding opportunities for these organisations elsewhere.
[6] GPAF Portfolio Analysis June 2014

At the High Level Forum, all donors and governments committed ‘to work with CSOs to provide an enabling environment[7] that maximises their contributions to development’[8]. UK Aid is a direct response to forming part of that enabling environment by providing financing and support to civil society organisations
[7] According to the Open Forum an “enabling environment” is the political and policy context created by governments, official donors and other development actors that affect the ways CSOs may carry out their work. “Enabling standards” are a set of inter-related good practices by donors and governments – in the legal, regulatory, fiscal, informational, political, and cultural areas – that support the capacity of CSO development actors to engage in development processes in a sustained and effective manner.
[8] Open Forum for CSO Development Effectiveness (30 June 2011) The Siem Reap CSO Consensus on The International Framework for CSO Development Effectiveness

What are the expected results?
The intended impact of UK Aid Direct will be to support the achievement of the MDGs and post-2015 sustainable development goals, through financing civil society programmes in the following areas;

1. Increasing access to services by specific groups – often those who are marginalised or discriminated against[9]; and, providers’ lack of capacity to deliver services in areas such as, but not confined to: WASH[10], health[11], education[12], finance[13], and sustainable livelihoods[14];
  [9] http://www.ohchr.org/Documents/Issues/Minorities/UNDPMarginalisedMinorities.pdf
  [10] http://www.unep.org/dewa/vitalwater/article63.html, 2008
  [11] Peters, DH et al. 2008, Poverty and access to health care in developing countries Ann N Y Acad Sci. 2008;1136:161-71. Epub 2007 Oct 22
  [12] Shari Krishnaratne, Howard White and Ella Carpenter (2013) Quality education for all children?, 3ie Working Paper
  [13] Beck, Thorsten, Asli Demirgüç-Kunt, and Ross Levine, 2007. “Finance, Inequality and the Poor,” Journal of Economic Growth, 12(1)
  [14] Awaiting advice
2. Secondly the fund will seek to enable citizens to overcome the barriers to the ability to demand access to such services by citizens and civil society, coupled with the lack of knowledge of rights to services[15];
  [15] Harry Jones et al. (2012) Knowledge, Policy and Power in International Development: A Practical Guide, Policy Press
3. Changing social attitudes and approaches that result in problematic situations for certain groups e.g. FGM, early marriage, and social discrimination; and
4. Increasing economic empowerment which includes access to credit, business knowledge, access to markets; and policies or lack of policies which impact on groups and create or are the result of barriers and legislation[16].
  [16] http://www.unwomen.org/ru

The focus and management arrangements for future operation of UK Aid Direct will be agreed with Ministers. The specific nature of the results from investment decisions using the modality established in UK Aid Direct will be discussed and agreed with Ministers in advance.

UK Aid Direct will employ at the onset, but not be limited to, a challenge fund mechanism in order to generate the best value proposals that support small and medium-sized CSOs, including small UK based organisations and non-traditional partners such as diaspora and faith-based groups, and strengthens their capacity to help deliver the MDGs and sustainable development.

The principles for UK Aid Direct were outlined in a submission to the Secretary of State. The Secretary of State supported the development of the second phase of the GPAF. She agreed that that the design should consider flexible funding rounds to support key priorities, that funding would continue to fund to target a range of CSOs across a breadth of policy areas, small organisation should continue to be supported and that the fund should be renamed to convey the purpose to potential applicants.

# Figure 1: UK Aid Direct results
# Section 2: Strategic Case

Why is civil society important to poverty reduction and to DFID?
With less than a year to go, achieving the Millennium Development Goals’ MDGs by 2015 remains a challenge. Progress towards the goals varies across countries and even if the MDGs were to be fully achieved, much more would still be required to eradicate poverty globally and ‘leave no one behind’

The UK Government is committed to the achievement of the MDGs and developing and delivering against a set of sustainable development goals for ‘post-2015’. A strong international and local civil society is vital for supporting the achievement of MDGs and the post-2015 goals.

The Zero Draft of Open Working Group for the post-2015 framework highlighted that ‘sustainable development can only be achieved with a broad alliance of people, governments, civil society and the private sector, all working together’[17]. The recent High-Level Meeting of the Global Partnership for Effective Development Co-operation (GPEDC) in April 2014, reinforced the importance of CSOs in the achievement of inclusive and sustainable development results; ‘Civil society organisations play an important role in enabling people to claim their rights, in promoting rights-based approaches, in shaping development policies and partnerships, and in overseeing their implementation’.[18]
[17] Open Working Group (2014) Zero Draft Proposed Goals and Targets on Sustainable Development for the Post2015 Development Agenda
[18] Mexico High Level Meeting Communiqué (16 April 2014) First High-Level Meeting of the Global Partnership for Effective Development Co-operation: Building Towards an Inclusive Post-2015 Development Agenda

CSOs are shaping their own practices for effectiveness, as part of building an enabling environment. Through the Open Forum for CSO Development Effectiveness, established following Accra, international CSOs have established a framework of principles that defines effective CSO development practice and elaborates the minimum standards for an enabling environment for CSOs. The eight Istanbul Principles for CSO Development Effectiveness[19] reflect a commitment to take pro-active actions to improve and be fully accountable for their development practices. This is vital given that globally, the number of international non-governmental organisations increased from 6,000 in 1990 to 50,000 in 2006[20] and in 2011, CSOs managed 10% of all official aid flows.
[19] Open Forum for CSO Development Effectiveness (29 September 2010) Istanbul CSO Development Effectiveness Principles
[20] Yearbook of International Organisations

DFID recognises that CSOs play the important role in reaching poor people and marginalised communities in places that the government or private sectors have not reached. They do so through their ability to build relationships, trust and legitimacy, through their grass-roots knowledge of needs in developing countries and through their responsiveness. This is crucial part of creating the open societies required for tacking poverty and its underlying causes and creating economic growth and development. They can build strategic alliances with government and private sector in so doing.

As development seeks to better reach those that are systematically left behind, discriminated against and locked into poverty, in particular women and girls, disabled people, LGBT groups and others, working through civil society remains an important approach. CSOs offer the potential of reaching the most excluded people in ways that others cannot but doing so can be expensive, requires strong legitimacy and relationships, and the skills to adequately target populations.

DFID works with over 500 international and UK CSOs and has direct or indirect links with many more CSOs in developing countries. It is currently estimated that 16% of all DFID financing flows through civil society organisations. DFID has five broad objectives for its work with civil society:
- Provide goods and services to the poor, particularly the hard to reach
- Help people in developing countries hold governments and others to account and influence decisions that affect poor people’s lives
- Support poor people to do things for themselves
- Build support for development by encouraging UK citizens
- Build and maintain the capacity and space for an active civil society.

DFID uses a variety of funds to support CSOs. Presently, under the Programme Partnership Arrangements (PPAs)[21], funding is unrestricted allowing organisations to support a wide range of activities and give flexibility that is valued by the sector. There are also a number of specific challenge funds and direct accountable grants, through a range of Departments, including country offices. CSD has been streamlining its instruments for directly financing civil society organisations. UK Aid Direct will compliment other funding mechanisms and ensure that smaller CSOs have an opportunity to access DFID funding.
[21] Through Programme Partnership Arrangements with 41 CSOs https://www.gov.uk/programme-partnership-arrangements-ppas

It is crucial to use the learning and evaluations of the current GPAF in decision making on UK Aid Direct. It is also important to generate and strengthen the evidence and learning gathered through UK Aid Direct on the international development impact that can be delivered through CSOs and how they can make a distinct contribution to DFID’s and global objectives. This is will be funded by UK Aid Direct.

UK Aid Direct will build on the momentum and success of the GPAF
UK Aid Direct will build on the successes achieved within the GPAF and enhance its reach and communications. Taking on the architecture and approaches of GPAF gives confidence for effective functioning of UK Aid Direct.

The Global Poverty Action Fund (GPAF) was launched in October 2010 with the aim of reducing poverty and achieving the MDGs through the provision of basic services by CSOs. Funding of £120 million (£40 million a year between 2010 and 2013 including fund management and evaluation costs) was agreed. 140 projects are currently being supported, reaching more than 11 million poor people across 31 countries.

GPAF invites proposals for projects lasting up to three years and operating in any of DFID’s 28 focal countries or in one of the bottom 50 UN Human Development Index (HDI) countries.

An additional £20 million was approved by the Secretary of State for a specific ‘Jobs and Livelihoods’ thematic round in late 2013 for which proposals are currently being assessed and grants will be awarded later this year. It is still too early to make any firm conclusion on the impact of this thematic round. However, it is clear that thematic rounds offer some advantages in terms of focusing activities on a specific sector or area and their impact can be more easily measured.

The total original GPAF budget of £120 million is now fully committed and all GPAF projects (including those due to be awarded under the latest funding round focused on Jobs and Livelihoods) will end by 2017/18.

Key statistics: the GPAF so far[22]
[22] GPAF Portfolio Analysis June 2014
- 162 grants awarded to date, working in 36 countries
- 140 projects currently in implementation
- 5 projects completed
- 96 projects funded through the ‘impact’ window
- 66 projects funded through the ‘innovation/community partnership’ window
- £99.4 million DFID funding currently committed (DFID has committed £141.2 m overall)
- 66% of projects scoring A or A+ in 2014
- Match funding means a total budget of £159.79 million (£60.39 m matched funding leveraged)
- 96% of projects IATI compliant

The recent DFID Annual Review in August 2014 scores the programme as ‘A – Outputs meet expectations’[23]. It concluded that the 130 grants to 110 CSOs at that point in time, had delivered direct positive changes[24] to over 10.8 million poor people in over 30 countries. Overall 66% of projects have scored A or A+ in 2014.[25]The latest information from the Fund Manager on the performance ratings of all current GPAF projects from the 2014 Annual Reports shows an increase in the number of projects meeting and moderately exceeding expectations.
[23] The latest Annual Review is due at the end of August 2014 and is currently on going
[24] A direct positive change is defined as the women, men, girls and boys who will have a measurable net benefit attributable to the GPAF supported intervention.
[25] GPAF Fund Manager’s Quarterly Report 1 April – 30 June 2014

The fund has reached a diverse range of organisations in terms of geographic location, organisational income size and type. A number of grants are agreed on the basis of matched funding and in this way the DFID investment of £99.4 million to date has leveraged additional funding taking the total budget for GPAF projects to £159.79 million.

The independent Mid-Term Evaluation (MTE) of the GPAF, undertaken by Coffey, reviewed the 33 projects that had completed 12 months of implementation by the start of May 2013. This sample was ‘deemed large enough to evaluate the progress of the fund and identify areas for improvement to enhance the performance of the fund in its later stages’.[26] Field verification visits were also undertaken to four of the sampled projects to understand the extent to which the Annual Report was fair and representative of the project’s performance and test if it was corroborated by beneficiary feedback.
[26] Coffey (April 2014) Global Poverty Action Fund Mid-Term Evaluation Report, p. i

The MTE concluded that the GPAF was successful in its objective of addressing the MDGs and supporting diverse projects across a range of sectors that reduced poverty and had the greatest impact on the poor and marginalised. It found that projects were already delivering results effectively and grants awarded under the ‘impact’ window were providing benefits at scale for poor and marginalised people.

The MTE also found that the fund is effective at reaching target beneficiaries. At the mid-term stage, the 33 projects included were delivering benefits to 1,827,728 people (48% of the total lifetime target of these projects).[27] The MTE suggested that the capacity of GPAF projects to reach their target populations was enhanced by the range of actors and partners with which they work, a key characteristic of how CSOs operate. For example, the MTE highlighted a Samaritan’s Purse project that was able to identify and develop relationships with the members of the community that held power over household decision making through ‘Lead Grandmother’ groups, to deliver behaviour change in a maternal health project.[28] Small CSOs are particularly well placed to learn local power structures and adapt activities to ensure effective delivery.
[27] Coffey (April 2014) Global Poverty Action Fund Mid-Term Evaluation Report, p. ii
[28] Coffey (April 2014) Global Poverty Action Fund Mid-Term Evaluation Report, p. 23

Furthermore, the MTE assessed the sustainability strategies of the GPAF projects as ‘well developed’ and recognises that there has been considerable work by grant holders in this area. Ten of the grantees in the sample had leveraged both in-kind and financial contributions that represent an additional 12% (£2,713,383) above the total budget for the respective projects. In addition to leveraging additional funds, organisations are also working with others to ensure the future of projects. The MTE highlights the success of one CSO to secure funding to replicate the model used in its GPAF project in other districts (not targeted by the GPAF project), as well as how other organisations are building relationships with local governments and other actors to fund and take over projects after the GPAF grants is complete.

The Fund Manager produces a large amount of learning through quarterly and annual reports. A recent workshop on a ‘Future Learning Strategy for the GPAF’, based on a learning visit to Civil Society Challenge Fund (CSCF) and GPAF projects in Uganda, discussed how the experiences of both the CSCF and the GPAF could inform the development of UK Aid Direct as the next phase of funding for CSOs and will inform the development of the extended delivery plan.

However, there remains relatively limited evidence of the role of Civil Society and the best funding mechanisms for different sized CSOs. This further emphasises the need to continue to learn from existing GPAF projects and to ensure that UK Aid Direct is designed in a way that it specifically generates, adapts and responds to further evidence and learning.

Impact and Outcome that we expect to achieve through UK Aid Direct

The Impact is a decline in poverty through the achievement of the MDGs and sustainable development goals in the post-2015 framework.

The outcomes are:
1. The achievement of the outcomes of all projects funded by UK Aid Direct in the areas of service delivery, empowerment and accountability, changing social attitudes and economic empowerment;
2. Effective civil society organisations.

Precise indicators and outputs will be evaluated and agreed through annual strategic investment decisions for UK Aid Direct made by Ministers.

A programme that learns and responds
UK Aid Direct will be operating in a rapidly changing world and changing priorities in response. The ability of the fund manager to manage and respond flexibly to change and to generate and use learning in response will be an important feature for UK Aid Direct.

UK Aid Direct will focus on increased communications to increase awareness of the fund among a broader range of eligible organisations; improve the grantee experience; and improve outreach and knowledge of the benefits of development funding with Parliamentarians and the UK public.

Gender Equality Impact Statement
Achieving the MDGs and eventually getting to zero poverty requires better progress for everyone living in persistent poverty. Extreme poverty is increasingly concentrated in population groups that face specific barriers and discrimination. Women and girls tend to be at higher risk of being trapped in poverty, being over represented amongst the poor and suffering from abuse, violence and discrimination. Gender inequality is a key characteristic of poverty.

UK Aid Direct will generate and build better evidence and better understanding of the different needs of, and the impact of interventions on, men, women, girls and boys and on the relationships between them. Such features will include: promoting gender sensitive project methodologies and analytical tools amongst grant holders, improving baseline socio-economic data, capacity-building to grant holders, embedding gender in due diligence processes and promoting gender skills and competences among grantee staff and partners.

Drawing from findings from the GPAF UK Aid Direct will encourage a wider diversity of gender mainstreaming activities through the design, budgeting, staffing and delivery of activities.UK Aid Direct will seek to strengthen further GPAF’s efforts to target women and girls, to improve upon GPAF’s overall approach to gender analysis at the project level and to ensure that women and girls are able to equally access the benefits of the projects. All projects are expected to demonstrate how they will address gender and consider the impact of any planned interventions on the lives of women and girls. They are expected to show this through proposals, logframe reporting, annual reports and evaluations.
# Section 3: Appraisal Case

What are the feasible options that address the need set out in the Strategic case?

Three feasible options were considered for UK Aid Direct:

Option 1 – ‘Business as usual’. Extend the GPAF for three years based on the current funding level of £120m and existing model.

Option 2 – ‘UK Aid Direct’. Build on GPAF to launch UK Aid Direct over five years, building on the strengths of the GPAF with an increased focus on flexibility, communications and evidence.

Option 3 – ‘Do nothing option’. Allow the GPAF to end now with no further funding rounds, closing the principal DFID challenge fund for CSOs. The final grants will conclude in 2017. This option provides the counterfactual approach.

Option 2 ‘UK Aid Direct’ is the preferred option. This option addresses the Secretary of State’s desire to build on the success of the GPAF, integrate a flexible approach including to better respond to UK priorities and enhance communications to increase the impact of the finance. This option integrates an adaptive model of rolling investment decisions that will enable the fund to respond flexibly and adapt to evidence and learning.

An appraisal of these options was submitted as part of the Business Case to QAU and was assessed a category 2 (broad recommendations). The revisions subsequently made to the business case are in recognition of the three main recommendations. As set out in the intervention summary, the extended delivery plan will bring to conclusion future management choices.

Key design questions
Two sets of design questions were considered, the first relating to the establishment of the facility for DFID financing civil society in the medium-term, the second to the strategic choices and investment decisions for deploying that facility. The analysis of these questions is outlined below. To maintain the adaptive nature of the fund all the conclusions drawn are indicative and allow space for the fund to respond to differing needs and differing times.

There are a number of additional questions that will be explored through the development of the extended delivery plan and annual strategic investment decisions including:
  1. How to drive innovation
  2. What is the right balance between types of grants, including impact and community partnership grants
  3. Eligibility criteria for organisations
  4. Geographic focus
  5. The overall risk appetite for investment decisions
  6. Duration of grants and the most effective and responsive way of managing the application process

Should UK Aid Direct be managed in-house or by an external contractor?
It is not in DFID’s strategic interest to manage UK Aid Direct in-house. This is for the following reasons:
- The commercial value that DFID is able to gain through a competitive tendering process.
- The greater efficiency that a fund manager is able to gain through specialisation and focus on the single task of managing the fund.
- A Fund Manager’s ability to respond flexibly to surges in activities and quickly access experts with the right skill set. The nature of project management is that there are periods of the year that are resource intense. An external fund manager is able to more efficiently accommodate this change in workload. This is also an advantage for UK Aid’s adaptive approach and will be built into the terms of reference for the fund manager.
- A number of practical issues around bringing the programme in house (DFID would likely have to recruit and/or train staff for the roles, an increased burden on other sections of DFID such as those involved in processing payments etc.)
- Additional services provided by the fund manager. For example, broader engagement with the sector through BOND and other CSO membership organisations; participation in the DFID pilot on beneficiary feedback; wider learning and research such as collaboration with University of Bath for knowledge sharing.

Contracting out the fund management is the most efficient way of running the programme day to day. It will also ensure that we have the standing facility and capacity to respond to changes and the flexible and adaptive nature of UK Aid Direct.

How effective are challenge funds? Experience of GPAF
Challenge Funds have been widely used by governments and donors to finance international development programmes. Competition is the key feature intended to drive quality. There is relatively little evidence to demonstrate when a challenge fund is likely to work better than alternate funding mechanisms, however, a recent paper produced by the University of Bath in collaboration with Triple Line Consulting reviewed challenge funds and found that they are most frequently used to:
- stimulate innovative responses to complex problems to which there is no standard solution – such as how to reach marginalised people
- stimulate responses to a problem that need to be tailored to a specific context – to tap into local knowledge and creative capacity
- to engage with smaller less well known organisations
- grant holders benefit from a mechanism that supports capacity building and promotion of best practice
- strengthen performance management, institutional learning and accountability
- to build flexibility into funding portfolios in a way that can accommodate uncertainty and variability in funding availability
- to reconcile flexibility with achieving economies of scale in management of related activities[29]
  [29] Practice Brief One: What is a challenge fund and when should it be used? TripleLine and University of Bath, March 2014

The GPAF fund has demonstrated that that a demand-led, competitive fund structured to respond to key issues is an appropriate way to support the sector. Previous GPAF rounds 2011-14 have funded on average 5% of applications. A flexible, competitive fund ensures:
  1. The right organisations are selected to reach target populations, and are supported to enhance and build the capacity of civil society organisations in country, (and also in the UK and internationally) and to contribute to the achievement of UK Aid Direct’s goals.
  2. Through competition and assessment, DFID is able to select those civil society organisations that are more likely to be able to deliver sustainable outcomes because the organisations have demonstrated that they have the appropriate mix of skills, knowledge, experience, relationships, and the capacity to deliver and to use DFID money appropriately.

It is important for UK Aid Direct to continue GPAF’s role in building evidence on the impact of challenge funds as a mechanism to support CSOs and deliver development impact. This will be part of the evaluation plan. Experience and lessons learned from working with the GPAF Fund Manager and other Fund Managers across DFID, including information generated by the recent BOND Survey of DFID grantees, is applied to the UK Aid Direct.

How should investment decisions be structured? Should funding windows be managed by theme?
UK Aid Direct will feature a rolling programme of annual strategic investment choices. Each year, a proposal which will further assess current UK policy priorities, resource availability, evidence and learning, value for money and results will be sent to Ministers for approval.

The recent end of programme review of the Governance and Transparency Fund (GTF) recommended that ‘the design of global funds should be guided by ease of portfolio management to measure and assess results quantitatively and qualitatively using thematic windows’[30]. This is in order to obtain the benefits of a focused set of outcomes across the portfolio, support learning and the economy, efficiency and effectiveness of the fund.
[30] Governance and Transparency Fund, End of Programme Review, Coffey, April 2014

There are a number of reasons why thematic windows could be an effective option for UK Aid investment decisions:
Projects can be more efficiently compared
- The fund can respond to UK or other development policy priorities or changes in context
- Like for like projects will be judged against each other
- Standardised metrics can be used to report outcomes.

Conversely, thematic rounds could increase the risk of a lack of high quality proposals as the fund becomes specialised, although this can be mitigated through effective communication and ensuring the theme is not too narrow. It is too early to conclude on the benefits and lessons from the first thematic funding window under the GPAF (grants have not yet been awarded). This knowledge will be used in determining UK Aid Direct design and investment decisions.

However, other options could present themselves as legitimate investment decisions for using UK Aid Direct, including geographical focus or more rapid response activities.

How should funding to small organisations be managed?
In GPAF there have been separate funding windows for small organisations accounting for 10% of the programme budget, designed to reflect the reach small CSOs can have and to ensure that organisations that do not traditionally get funding from DFID are able to access DFID resources.

Maintaining 10% of funding levels to small organisations is the preferred approach for UK Aid Direct. However, creating a target within streamlined windows open to organisations of all sizes and actively encouraging small organisations to apply in order to reach the 10% is a preferred option. UK Aid Direct will only fund projects that represent good value for money irrespective of size but will aim to ensure at least 10% of funding goes to small organisations. This increases the flexibility of the fund to respond to the source of the strongest proposals, in keeping with the demand led nature of the challenge fund.

How should we determine and manage overall financing for UK Aid Direct?
As an adaptive programme UK Aid Direct will need to make on-going choices on resources and priorities that deal with uncertainties and opportunities. It will do this through annual strategic investment choices. At the same time UK Aid Direct requires a degree of certainty and a minimum amount to be a credible international programme and to achieve value for money in its delivery. Reviewing CSD’s project based financing to civil society organisations, we asses that it is currently running at an average of £30 million per year. This business case proposes to maintain this amount, which over five years, totals £150 million.

For its first round in September 2014 an allocation of £30 million continues the momentum of GPAF. Going forward investment decisions will vary according to the evidence of success, priority areas for intervention, results sought, policy choices and the resource environment within DFID. UK Aid Direct could disburse significantly more or less in any given year of operation or choose to channel other sources of funding for civil society. The management capacity of the fund manager of UK Aid Direct will be built to manage this flexibility.

How will UK Aid Direct work?
To ensure that there is continuity of funding to the sector, a first new funding round is proposed in autumn 2014 based on the existing GPAF design. This funding round will provide both ‘Impact’ and ‘Community Partnership’ grants up to a value of up to £30 million and invite proposals for projects that will focus on poverty reduction and contribute towards the achievement of the Millennium Development Goals (MDGs). 10% of the funding available will be allocated to small CSOs through community partnership grants.

This Business Case sets out illustrative results UK Aid Direct expected from this first round, but these will need to be refined once proposals are clear and within the approval process.

In parallel to the first funding round under UK Aid Direct, an extended delivery plan for the fund will be developed which will focus on the management and financial choices for establishing the capacity and value for money in a fund manager.

For the first rounds, UK Aid Direct will continue to use a two stages approach of (i) concept note and (ii) full proposal. Concept notes and full proposals will be assessed against published criteria by the Fund Manager and quality assured by DFID staff. The process for future funding rounds will be agreed through the Delivery Plan. Final approval of all funding decisions will remain with the Secretary of State.

For the first round of UK Aid Direct grants will be awarded for a period of up to three years from the start of each individual project. Within the extended delivery plan and within the context of investment decisions this will be reviewed. The current GPAF appraisal framework will be used, reviewed and adapted over the lifetime of UK Aid Direct. This framework has been developed according to the GPAF experience to date and best practice.

Applications will provide a clear description of measurable change and the number of people (beneficiaries) who will experience that result. Proposals must have considered the support of the relevant local government agencies, organisation of beneficiaries, effective stakeholder engagement and coordination, risk management, lessons from past experience and have developed a logframe.

We plan to develop a set of systematic VfM measures to enable a greater degree of impartial VfM assessment and these will be presented in the Delivery Plan and annual investment decision process.

Evidence for the first funding round of UK Aid Direct
This business case proposes a minimum funding commitment of £150m over 5 years, but with an immediate round of £30m for ‘finishing the job’ on the MDGs and overall poverty reduction. The flexibility of the fund, enabling it to be responsive, will create significant impact in priority areas as they emerge and ensure the role small and medium sized CSOs play in development is aligned to DFID wide priorities.

Table 1: Resource Implications of Round 1
	2014/15	2015/16	2016/17	2017/18	2018/19	TOTAL
Project Funding		6,097,889	9,146,833	9,146,833	3,048,944	27,440,500
Project Assessment	516,075					516,075
Fund Management		376,888	565,332	565,332	188,444	1,695,996
Evaluation		28,300	42,450	42,450	14,150	127,349
Due Diligence	220,080					220,080
Total Admin Costs	736,155	405,188	607,782	607,782	202,594	2,559,500
Resource Commitment	736,155	6,503,077	9,754,615	9,754,615	3,251,538	30,000,000
DFID Resource Cost	46,603	94,127	95,058	63,999	48,474	299,787
GRAND TOTAL	782,758	6,597,204	9,849,673	9,818,614	3,300,013	30,299,787
Real Terms	782,758	6,467,847	9,467,198	9,252,299	3,300,013	28,487,357
Present Value	782,758	5,879,861	7,824,131	6,951,389	3,300,013	23,955,394

As can be seen, an up-front commitment of £30m is estimated to result in £27.4m being allocated to projects lasting 3 years spanning four financial years.

Given the funding mechanism remains the same, our best estimation of projects funded under the first round of UK Aid Direct is previous years of GPAF funding. Assuming the same cost per beneficiary (CPB) of previous projects and the same sector breakdown, the expected reach of this first round of UK Aid Direct is set out in table 2:

Table 2: Estimated Beneficiaries from Round 1
Row Labels	Proportion of funding	Estimated Budget (£)	CPB	Estimated beneficiaries
Agriculture	13.6%	3,740,411	34.7	107,696
CSO capacity	9.2%	2,519,626	9.5	264,469
Disability	4.5%	1,222,098	208.5	5,861
Education	13.6%	3,723,269	39.0	95,577
Environment	2.9%	788,319	9.0	87,209
Health	18.5%	5,070,181	5.9	855,574
Income generation	7.5%	2,061,562	38.1	54,093
MCH	20.0%	5,490,297	12.4	441,527
WASH	10.3%	2,824,737	16.3	173,678
Grand Total	100.0%	27,440,500	13.2	2,085,684

As can be seen this £30m commitment is expected to reach more than 2 million people over 3 years. As only five projects have been completed under GPAF so there is insufficient information for a detailed assessment of impact.

Communications, outreach and evidence
UK Aid Direct will feature an enhanced focus on communications, outreach and evidence – this is reflected within the logframe and the theory of change. This reinforces the importance of communicating to all stakeholders, including the UK public, the objectives and achievements of the fund and ensuring that a broader range of eligible organisations are aware of the opportunity. The proposed approach to stakeholders and communications, which was developed with colleagues in Communications Division, is attached as Annex B.

DFID Digital Services colleagues have designed and launched a streamlined and intuitive, digital ‘Funding Finder’ on the DFID website. This feature will act as a signpost to the UK Aid Direct and increase its visibility to a wider pool of applicants.

Outreach to other influential figures and stakeholders is also important and through UK Aid Direct we will make a particular effort to raise the awareness of Parliamentarians of the Fund and where organisations in their constituency are benefitting from DFID funding. The communications plan outlines an initiative to write to MPs informing them of each call for proposals so that they can make their constituents aware of the opportunity and also requesting organisations that receive funding to inform their local MP and communicate how they are using the grant.

GPAF and UK Aid Direct projects are also a source of positive news. They include some of the most innovative and effective programmes funded by DFID and can showcase the benefits of development funding. The media strategy developed for the GPAF will continue and be regularly reviewed, working closely with Press Office to ensure maximum benefit. Information about all projects will be made available on the DFID website. This includes a targeted approach to announce individual projects and create a bank of good news stories for national, regional and specialist media, which can also be used as stand-alone press releases, or included as case studies in wider communications, such as speeches and online features.

B. What is the likely impact (positive and negative) on climate change and environment for each feasible option?
Under UK Aid Direct there is the opportunity to support CSOs to enhance their understanding of the links between the natural environment, livelihoods, poverty and growth and to reinforce the environmental screening of successful CSOs. The Fund Manager will ask grant holders to conduct their own climate change/environmental opportunities/risks assessment, and to consider how risks will be mitigated or how opportunities could be developed. The Fund Manager’s experience of environmental and climate change screening and safeguards will be assessed as part of the competitive selection process in order to ensure that they are able to impart the necessary capacity building and support for GPAF applicants and grantees.

The fund offers an opportunity to contribute to MDG7 which is one of the most off-track MDGs. Additional opportunities are through funding projects that contribute to climate change adaptation and resilience. Under the focus on Empowerment and Accountability funding can be made available for strengthening community action to manage natural resources, demand better services, justice and security and better management of local government.

Significant opportunities could also be offered through a direct thematic window focussing on natural resource management, building resilience to environmental and climatic shocks and enhancing natural resource governance and/or through mainstreaming an improved understanding of the links between environment and well-being.

C. If any, what are the likely major impacts on social development?
Impacts will depend on the structures and systems employed in managing UK Aid Direct and in the investment choices made within the programme. On the latter, an ‘inclusive development’ theme would provide the opportunity to make funding available to those harder to reach groups (e.g. women and girls suffering from gender based violence) and harder to measure changes (e.g. empowerment). It would allow for CSOs who are experts in these areas, who are able to share learning, or test and use new and innovative approaches.

GPAF has shown that ‘the capacity of grantees to identify the relative level of poverty and marginalisation among their target groups has been constrained by a lack of socio-economic baseline research and analysis. Instead, target groups are often assumed as being poor or marginalised because of where they live’.[31] The targeting of poor and marginalised groups will be strengthened in UK Aid Direct.
[31] Coffey (April 2014) Global Poverty Action Fund Mid-Term Evaluation Report, p.12

DFID and the fund manager will seek ways to ensure that grantees conduct proportionate baseline and periodic research to review possible changes in the characteristics of target and beneficiary groups. This support could include, as suggested by the MTE, providing best practice guidance on how to conduct baseline research and on how to commission external research that is proportionate and cost-effective.

As with targeting specific groups of beneficiaries, GPAF has performed less well on gender equality. The MTE found design, implementation and reporting of gender responsive activities was through a focus on gender equality through logframe indicators rather than through an understanding of broader gender mainstreaming. As a result, the GPAF performs well against evaluation framework indicators that relate directly to project design, whilst the portfolio is relatively weak in being able to evidence effects on gender mainstreaming. The MTE concluded that this reflected a relative lack of familiarity and/or a lack of investment in gender-sensitive project methodologies. The Fund Manager and CSD will develop specific guidance for applicants on gender mainstreaming. This will need prioritising, alongside support on targeting and strong socio economic baselines.

The selection of the fund manager for UK Aid Direct will take into account the need for sufficient expertise in gender issues to appraise, guide and support applications in proactively mainstreaming gender and reach girls and women.

A focus on Empowerment & Accountability through investment decisions and specific thematic windows may be appropriate. Funded projects that focus primarily on empowerment and accountability will require more adaptive and innovative approaches to programme management, and to monitoring and evaluation than to date. Again the capacity of the fund manager to successfully manage this approach will be tested within procurement.

Linking to and potentially expanding the GPAF pilots on Beneficiary Feedback (BF) will be an important source of learning in tracking hard to measure change and leading to greater empowerment and sustainability. As DFID develops its knowledge on this through the GPAF Beneficiary Feedback pilots, wider FCPD pilots, and Better Programme Delivery, CSD and the Fund Manager should consider how best to share this learning with grantees and provide support in assessing how best to gather feedback, for what purposes and at what cost.

The monitoring and evaluation plans established under UK Aid Direct will test core assumptions around the link between characteristics unique to CSOs and certain types of development results (e.g. empowerment, reaching excluded groups). These findings will be an essential source of evidence to CSD and to DFID in considering the best ways to fund and support work on such themes and will be reflected in investment decisions for UK Aid Direct.

D. For fragile and conflict affected countries, what are the likely major impacts on conflict and fragility, if any?
A large number of the current GPAF projects are delivering effective development interventions in fragile and conflicted affected countries. 116 projects/provisional awards, out of a total of 146, are operating in countries which DFID considers to be fragile and conflict affected.[32]
[32] Afghanistan; Bangladesh; Burma; CAR; DR Congo; Ethiopia; Haiti; Kenya; Liberia; Malawi; Nepal; Nigeria; OPT [no GPAF projects]; Pakistan; Rwanda; Sierra Leone; Somalia; Sudan; South Sudan; Tajikistan; Uganda; Yemen [no GPAF projects]; Zimbabwe.

In the GPAF, the Fund Manager applies specific criteria to assess projects working in fragile and/or conflict affected environments. This includes a ‘do-no-harm’ approach. The Fund Manager also ensures the appropriate identification and management of risks related to the proposed projects’ dependency on support from government agencies in fragile states. Grant holders report the effects of working in fragile/conflict countries in the Annual Review. They also identify any unintended outcomes from project implementation.

CSD is working with DFID’s Conflict, Humanitarian and Security Department (CHASE) and DFID country offices to improve the assessment of projects in fragile or conflict affected states. Additional questions will be embedded into the assessment framework for UK Aid Direct to capture:
- Evidence that the project is seeking to avoid harm (e.g. not fuelling/creating conflict)
- Evidence that the project is also making a contribution to peace and stability.

E. Theory of Change
The UK Aid Direct theory of change is set out diagrammatically in Figure 2.

UK Aid Direct’s theory of change states that by creating a demand-led fund DFID can respond to the appetite in the sector for, and ability to respond to, calls for proposals in the identified areas. By responding to this demand DFID can support organisations whose work will, ultimately and by creating change for beneficiaries, contribute to meeting the MDGs/NDF. However, the results chain is a long one and as a result, challenging particularly at the outcome to impact level.

The theory of change states that organisations and partners will achieve their outcomes and change for beneficiaries through improvements in access, knowledge, empowerment and accountability. An enhanced and increasingly active civil society will contribute to increased and sustainable human potential for change and progress in target countries and support the MDGs/NDF. This confidence is supported by early evidence from the GPAF mid-term evaluation that shows that individual projects are achieving their output and outcomes. The umbrella evaluation framework which encompasses both UK Aid Direct and the Programme Partnership Arrangements will ensure that the latter aspect of the theory of change will be robustly assessed.

The GPAF fund has demonstrated that that a demand-led, competitive fund structured to respond to key issues is an appropriate way to support the sector. Previous GPAF rounds 2011-14 have funded on average 5% of applications. A flexible, competitive fund ensures:
- The right organisations are selected to reach target populations, and are supported to enhance and build the capacity of civil society organisations in country, (and also in the UK and internationally) and to contribute to the achievement of UK Aid Direct’s goals. Through competition and assessment, DFID is able to select those civil society organisations that are more likely to be able to deliver sustainable outcomes because the organisations have demonstrated that they have the appropriate mix of skills, knowledge, experience, relationships, and the capacity to deliver and to use DFID money appropriately.
- The breadth of assets and skills embedded in civil society are acknowledged.
- That investment choices can include thematic windows, identified in clear response to emerging development issues or key DFID priorities. Broad approaches across themes and countries allow a wider range of approaches, ensure accessibility for the wider civil society sector. [33]
  [33] This approach was trialled in the 2013/14 through the ‘jobs and livelihoods’ window.

Any fund such as UK Aid Direct is underpinned by an efficient programme management approach which guides and monitors activities. Activities include the establishment of the fund mechanism and the day-to-day running of the fund.

The outcome level is measured through the achievement by grantee organisations of their outcome goals via the DFID annual review scoring system. Milestones are individually set at levels appropriate to a window. As for outputs this approach allows for DFID to tailor monitoring process to acknowledge and accommodate challenging or innovative funding windows.

Figure 2: UK Aid Direct: Theory of Change diagram

At the impact level UK Aid Direct will contribute to a decline in poverty though support to the achievement of the Millennium Development Goals and the New Development Framework and their indicators are used to monitor change.

F. What measures can be used to monitor Value for Money for the intervention?

Value for Money is at the core of UK Aid Direct and will build on the work done under GPAF to date. DFID will ensure VfM at 4 levels:
1. That the VfM potential of UK Aid Direct’s flexibility is maximised
2. VfM of the fund manager
3. VfM at project selection
4. VfM through the life of projects

Below is our vision for value for money in each of these areas. Whilst inevitably implementation will depend on certain key strategic decisions, this gives an indication of how VfM will be approached in UK Aid Direct.

VfM through the flexible nature of the fund
UK Aid Direct will respond to key priorities and where there is a need for DFID funding that can best be satisfied by centrally managed CSO programming. This has a number of advantages when driving VfM:
- Instead of locking down decisions upfront, whilst evidence is still emerging, options at key investment decision points will be presented to the SoS with a fuller picture of what works and what doesn’t.
- Areas (geographical, sector, type of CSO etc) where small and medium sized CSOs can add value to DFID priorities in future rounds are not known today. By creating fund that responds to the current situation, resources can be directed in a way that “maximises the impact of each pound spent to improve poor people’s lives”[34] in each round, rather than assuming what represents VfM today is what represents VfM in 3 years’ time.
  [34] DFID’s Approach to Value for Money (VfM) July 2011
- Adaptive funding enables scale up when the marginal benefit is highest and down when the marginal benefit is less so
- Annual delivery plans will enable a greater focus on VfM that is relevant to each strategic funding decision. This will include an appropriate economic appraisal.

Whilst flexibility can be an asset for VfM there are certain fundamental VfM principles that will be at the core of all decisions made in UK Aid Direct:
- The decision of which CSOs to fund will always be made on the basis of VfM. Assessment of proposals, whilst dependant on the nature and scope of the funding mechanism, will incorporate VfM metrics to inform decision making.
- The fund manager will be selected by competitive tender. The ToRs for this will include an increased emphasis on ensuring and measuring VfM across the life of UK Aid Direct and the successful bidder will be expected respond positively to strategic decisions made by DFID and the SoS in maintaining this drive for VfM.
- As GPAF projects draw to a close there will be increasing evidence on impact of projects delivered through small and medium sized organisations. This evidence of what worked will provide the basis of future strategic and funding decisions as well as how VfM can be best achieved.
- Throughout the life of projects VfM will be driven through proactive monitoring of projects by the fund manager and regular oversight from CSD. This will be fundamental to ensuring the vision of the fund is delivered.

VfM of the fund manager
The management of UK Aid Direct will be tendered through a competitive process. To ensure value for money is being achieved throughout the length of the contract DFID’s Civil Society Department will proactively manage the contract (continual contract management), drawing on lessons learnt from the GPAF, the Civil Society Challenge Fund as well as wider DFID experiences.

VfM at the project selection stage
All applications will be evaluated against value for money as a core part of the application process. They are assessed both on the value for money of the management arrangements (economy), their impact on poverty (effectiveness and efficiency) and the relative balance of these (i.e. are we achieving a high level of poverty reduction for every pound spent). Value for money is also a ‘mainstreamed criteria’ which means it is assessed throughout the application, in parallel to the other assessment criteria.

Building on the increased emphasis on VfM in the GPAF, specific VfM metrics will be a core part of selection criteria (the choice of metrics will be determined by that is most appropriate for the funding). The use of these metrics will aim to increase the level of VfM evidence and improve decision making, rather than to form the basis of project selection. This is because projects funded through a challenge fund are too diverse in nature for this kind of comparison to be meaningful on its own. It can, however, increase the evidence base for making a more informed VfM judgement.

For example, drawing on data from the GPAF, we have a reasonable dataset on cost per beneficiary against which new proposals and projects can be benchmarked. These figures are updated after each funding round, therefore the dataset becomes a more reliable source to benchmark against. Data from the current rounds are presented in table 3 below:

Table 3: Cost per beneficiary from GPAF
Sector	Number of Projects	Percentage of Beneficiaries	Average no. of Beneficiaries per Project	Average CPB
Agriculture	22	5.2%	17,194	34.73
CSO capacity	14	12.7%	66,351	9.53
Disability	8	0.3%	2,573	208.51
Education	20	4.6%	16,785	38.96
Environment	5	4.2%	61,262	9.04
Health	29	41.0%	103,624	5.93
Income generation	15	2.6%	12,666	38.11
WASH	11	8.3%	55,457	16.26
MCH	17	21.2%	91,224	12.43
Grand Total	141	100%	51,955	13.16

Driving VfM throughout the life of a project
Once grants have been awarded, individual projects will be required to submit an annual review each year for the lifetime of the project. The annual review will capture key cost ratios such as admin to programme spend, cost per unit of office space, cost per unit of travel and number of staff per £X of programme spend. Grantees should also demonstrate how they are achieving value for money through their own business processes, such as procurement and internal cost management.

Annual reviews will also report against the agreed log frame indicators, which should enable some form of cost-effectiveness measure to be calculated. Before the first annual review, a set of VfM measures will be incorporated into the logframe to enable VfM to be better tracked at the programme level as well as the project level.

An addition to annual reviews the fund manager is expected to proactively manage grants and escalate projects that may not be representing VfM to DFID. In order to achieve this, the fund manager will be expected to assign risk ratings to projects to ensure those with the greatest potential to go off track are monitored closely. In the past DFID has been prepared to close early projects that are under performing and representing poor VfM and this willingness will continue.

The fund manager is also expected to develop VfM ratings for projects which go beyond annual report scores (which tend to be largely output driven) and some way to assessing to what extent the project is maximising “the impact of each pound spent to improve poor people’s lives”[35].
[35] DFID’s Approach to Value for Money (VfM) July 2011

By combining these three measures (annual reviews, risk ratings and VfM ratings) a comprehensive VfM assessment of projects can be made and both DFID and the fund manager can respond accordingly.

G. Summary Value for Money Statement
Although it is not possible to accurately predict the total benefits that will arise under UK Aid Direct, the highly competitive selection process ensures that grants are only awarded to grantees who can demonstrate the results they will achieve with DFID funding. Value for money is continually assessed throughout the selection process and within the subsequent M&E process.

UK Aid Direct also enables DFID to drive value for money through investment decisions and thematic windows. By comparing projects on a similar theme standard metrics can be developed to increase ease of comparison.

# Section 4: Commercial Case

Procurement/commercial requirements for intervention
UK Aid Direct will have a high level of ambition for achieving value for money in selection and on-going management of the fund manager and in programme interventions. This requires further work which will be set out in detail in the delivery plan.

The UK Aid Direct Fund Manager will be directly contracted through a competitive ‘Official Journal of the European Union’ (OJEU) procurement exercise. We plan a formal Early Market Engagement event which will further broaden potential market interest and a Prior Information Notice (PIN) will be issued to advise any interested organisations of the opportunity and a supplier information session will be held to ensure that the requirements are clearly understood.

Procuring a fund manager with the capacity and capability to respond quickly to the adaptive and flexible nature of UK Aid Direct is critical to the success of the model and to delivering the expected results. An indicative list of activities to be undertaken by the contractor is outlined below – this will be further refined in the extended delivery plan :
- Manage the call for proposal for funding rounds
- Assess all applications and make recommendations to DFID
- Prepare and put in place all grant or contractual arrangements for successful applicants
- Undertake any required due diligence checks on all organisations receiving grants to manage risk and ensure close fiduciary control (Due diligence assessments of GPAF grant holders are currently managed through a separate contract with KPMG which ends in November 2014. Future due diligence requirements for grants awarded under UK Aid Direct, will be brought into the Terms of Reference for the new Fund Manager)
- On-going monitoring of output and financial tracking including verification through spot checks, ensure compliance
- Conduct annual reviews and project quality assurance visits
- Portfolio analysis and risk management
- Grant management of all existing GPAF grants (approx. 197)
- Financial Management – checking and verifying expenditure claims, disbursement, review audited accounts, monthly financial forecasting and monitoring against yearly accounts
- Outreach activities
- Monitoring and Learning (Evaluation will be procured separately to the Fund Manager)

The first call for proposals will be announced shortly after the business case is approved. It is proposed to amend the current GPAF Fund Manager contract (and extend until August 2015) to cover the activities involved in issuing the call for proposals and assessing the concept notes and full proposals under the first round of the new UK Aid Direct. This will ensure continuity between GPAF and UK Aid Direct. The contract amendment will also include activities and commitments to ensure a comprehensive handover between the existing and newly appointed Fund Managers.

The proposed amendment and extension to the existing GPAF Fund Manager’s contract has been agreed with colleagues in Procurement Department (PCD) as a viable way forward to ensure the delivery of existing GPAF projects and new calls for proposals until the OJEU competition can be completed. Where external expertise is required for monitoring and evaluation work, DFID framework agreements or short-terms contracts will be utilised.

How does the intervention design use competition to drive commercial advantage for DFID?
In early market engagement, in setting out a detailed delivery plan, in setting points for investment decisions which will incorporate reviewing of value for money provided by the Fund Manager and opportunities for mid-course corrections UK Aid Direct will seek to be responsive to commercial discipline, understanding cost drivers and achieving value for money.

How do we expect the market place will respond to this opportunity?
UK Aid Direct will be DFID’s central and medium-term funding mechanism for small and medium sized civil society organisations. It will be high profile and will attract significant interest and bids. There are a wide range of technically suitable organisations capable of managing the UK Aid Direct. We expect the number of interested organisations submitting proposals to drive up the quality of proposals and ensure good value for money. The competition that appointed the GPAF Fund Manager received four bids and a competition for a similar fund in 2010 attracted 6 bidders.

What are the key cost elements that affect overall price? How is value added and how will we measure and improve this?
Key cost drivers for supplier for this programme relate to fund management and monitoring and evaluation costs. The cost drivers include Supplier’s staff, its administrative costs, procurement costs, direct fund management costs, and overall management overhead charges. Credible VFM will be delivered through early market engagement and by global competition. CSD will work with PCD colleagues to benchmark the proposed costs of programme with similar fund manager type contracts let by DFID. The Terms of Reference will set the requirement for the manager to set out year on year efficiency plan to demonstrate ongoing commitment to reduce its management costs over the life of the contract. Bids will be judged against the value for money criteria of economy, efficiency and effectiveness.

Economy – fees, daily rates, overheads etc. and unit costs of specific inputs. For example; comparison with current costs, and those for other Fund Manager contracts. Costs of accommodation, travel, and other expenses will be included in the commercial evaluation. In consultation with PCD, consideration will be given to requesting a breakdown of supplier overhead costs, including profit in the commercial bids.

Efficiency – number of days and or/staff required to deliver outputs, the inclusion of recommendations, which would improve the delivery of outputs or reduce fiduciary risks etc.; and,

Effectiveness – elements of the proposals that would improve the overall impact of local technical capacity or introducing better management practices into the sector as whole.
Management fees being charged will be included in the commercial evaluation to ensure these costs are at an appropriate level for the programme and will be formally benchmarked against other similar fund disbursement programmes.

The preference is for all payments to be made in arrears based on the achievement of the agreed outputs. However, the nature of working with small organisations with a limited income means that some will not be able to operate on an arrears basis. DFID guidelines allow for CSO’s to claim in advance if justifiable. Any organisation wishing to claim in advance will be required to provide written justification during the grant award process and before a grant arrangement is signed.

Approval for an advance funding process for managed grant costs was agreed by HMT for the GPAF contract. A continuation of this arrangement would be requested for UK Aid Direct. If the Fund Manager had to borrow sufficient resources to cover this pre-financing, there would be a significant cost to the taxpayer in terms of bank charges. HMT approval for an advanced funding process would create a potential saving to the tax payer of around £3million.

E. How will the contract be structured and how will contract & supplier performance be managed through the life of the intervention?
CSD will follow DFID’s best practice guidance for managing supplier performance as set out in the newly agreed Smart Rules. Key Performance Indicators will be included in the contract Terms of Reference and used to measure supplier performance throughout the contract duration. Regular supplier meetings to discuss results, value for money and performance will take place with the CSD staff responsible for managing UK Aid Direct. Outputs from these discussions will also inform the Annual Review.

The Fund Manager will also submit monthly accounting reports to DFID. This will enable DFID to make key decisions regarding the direction of the programme, to ensure efficiency levels are maintained and effective delivery against outputs achieved.

# Section 5: Financial Case

A. Who are the recipients of all proposed payments?
The majority of the funding agreed for UK Aid Direct will be used as grants payments to small and medium/large civil society organisations following a competitive process. Fund management and monitoring and evaluation costs will also be paid out of the total budget of £150 million. These will be procured through competitive processes under EU Directives and are expected to be no more than a maximum 8% of the total budget.

B. Is the required funding available through current resource allocation or via a bid from contingency? Will it be funded through capital/programme/admin?
UK Aid Direct will be entirely funded from programme funds. It is possible that UK Aid Direct may identify and offer opportunities for capital resource expenditure and this will be tested at investment decision points.

In the current resource environment for DFID, UK Aid Direct offers the opportunity for some certainty over an overall resource envelope but for decisions to taken at regular points within the programme that bring together evidence, resource availability and ambition form results.

How will funds be paid out?
DFID will transfer grant money to the Fund Manager to pay the grant holders. The Fund Manager will be required to open an account solely for the UK Aid Direct grant payments. In order to keep account balances low, on a monthly basis the Fund Manager will provide DFID with a list of all claims received that month from fund recipients and a total figure for that month. This list would detail all of the actual expenditure being accounted for and the amount of advance funding requested for each on every individual programme.

DFID will put in place an agreement with the contracted Fund Manager that they would ensure that all payments transferred by DFID into the project account would be passed on to the organisations running the successful bids. The agreement with the Fund Manager would also stipulate that any interest accrued on this account would be used to offset any bank charges. Any interest over and above charges will be the property of HMT. However we do not expect to have any significant interest as funds are being released just in time.

HMT approval for an advance funding process for managed grant costs would reduce barriers to entry for small organisations that would be unable to pre-finance fund disbursement to project recipients. This would increase the number of potential bidders. The lack of an advance funding option has been challenged by suppliers as a barrier to small organisations bidding for DFID business and not aligned with the Action Plan for Small and Medium Enterprises published by the Cabinet Office. UK Aid Direct will review this at investment decision points.

What is the profile of estimated costs? How will you work to ensure accurate forecasting?
Civil Society Department (CSD) will ensure accurate forecasting through developing a strong working relationship with the Fund Manager, enabling effective engagement on programme issues including financial management issues. The Fund Manager will submit quarterly financial statements and a more detailed annual financial and narrative progress report which will also include an assessment of risks associated with delivery. These reports will clearly indicate realistic projection of spend for the current financial year broken down by quarter on all major budget category lines.

The Fund Manager will provide financial forecasts to DFID on a monthly basis. Forecasts should be accurate to within 1%. This is ensured by including accurate forecasting as a Key Performance Indicator for the Fund Manager.

CSD will rigorously reconcile these forecasts against: (i) relevant data on ARIES; (ii) work plans and budget; (iii) previous quarterly reports; and (iv) previous disbursements and past spending trend. Any discrepancies will be quickly raised with the Fund Administrator and necessary changes to forecasts will be agreed.

What is the assessment of financial risk and fraud?
Financial risk and risk of fraud is considered to be medium to low. This judgement is based on the types of projects and organisations funded in GPAF. 162 grants have been awarded since the GPAF began and there have been 3 allegations of fraud through misappropriation of funds to date. Only 1 has proved to include DFID money (approx. £2000) which was repaid by the grantee. One allegation proved to be false and one allegation is currently being investigated (approx. £16k) and again we expect that if the allegation proves correct we will recover the money from the grantee.

The financial risk and that of fraud will be different for the different components. For the Fund Manager, we assess the risk to be low as the preferred bidders will be subjected to a full pre-contract due diligence process. There is a higher financial risk and of fraud when providing grants to CSOs and their partners. Fraud and financial risk and mitigation measures (including phased payments) are assessed for each application during the GPAF competition. CSOs named in receipt of the grant will be subject to full due diligence and again the level of risk at this level is low.

At implementation level these CSOs will be working with a range of partners in different environments, some of these will be challenging including in fragile states and areas of post-conflict. We will be asking all recipients of grants to set out how they plan to manage and mitigate these risks, and what action they will take if any fraud is discovered.

In addition to grant holder mitigation measures CSD has put in place a number of measures to tackle the risk of fraud and corruption in the difficult environments in which we work. The comprehensive risk management strategy includes an annual audit of 15% of the projects, project visits to grants assessed as medium and high risk and proactive management support. A sample of grants will be selected on a quarterly basis for financial spot checks and audits. A stratified approach is taken, ranging from additional desk-based verification to physical visits to the Implementing Partners. Currently, this process is overseen and managed by a member of the GPAF Internal Audit team at Crown Agents. The internal auditor will select projects to be audited on the basis of:
- Size of grant (stratified sample to include small and large grants)
- Complexity of project delivery or project structure
- Known concerns on the part of the Fund Manager
At the same time, a certain proportion of projects will be chosen at random to ensure that there is monitoring control over the whole portfolio of projects. Any project can be chosen in any period of the project life cycle. If level 1 checks raise concerns, level 2 checks can be undertaken. In some cases, serious concerns may lead directly to a level 3 or level 4. Some projects will also be selected randomly for checks at levels 2, 3 or 4.

The currently agreed risk management strategy means that instances of actual or alleged fraud result in immediate action in line with DFID’s ‘zero tolerance’ on the misuse of public funds. The Fund Manager and CSD work closely with DFID’s Counter-Fraud and Whistleblowing Unit (CFWU), which reviews and advises how to address each case of alleged fraud, to decide the best approach on a case by case basis.

To mitigate against the risk of grantees under reporting instances of fraud, CSD and the Fund Manager will deliver the following under UK Aid Direct:
- Due diligence reviews assess organisational capacity to follow grant management procedures and report risk to DFID prior to grant confirmation
- Clear guidance on project reporting provided
- Creates an environment where projects know they can be audited/visited at any time
- Demand higher standards of detailed reporting on results (including case studies), financial reporting, value for money reporting
- Sampled in country visits are carried out by the FM, contracted local consultants and financial consultants
- Independent evaluations contracted by grant holder to verify results at the end of the project
- Good quality and regular communication between UK-based grant holders and implementing partners including translation of documentation and reporting. Regular visits to the project by the grant holder
- Remove risk through project closure where pro-active management and other strategies are insufficient to reduce the risk.

F. How will expenditure be monitored, reported and accounted for?

Grant level
Each organisation provisionally approved for a grant by the Secretary of State must then undergo a due diligence check before the grant is confirmed. These pre-grant due diligence procedures aim to ensure value-for-money by identifying potential risks and capacity building opportunities around governance, management and capacity within the partner CSOs. Pre-grant due diligence helps to reduce the risk of diverted funding and establishes an environment of accountability and transparency. The pre-grant due diligence assesses capacity to manage the proposed level of DFID support in the following areas:

- Governance: The focus on governance considers how the CSO is administered, its risk management processes and its ability to comply with key legislation such as the Bribery Act 2010. Key policies and procedures are also assessed, including those covering child protection, environmental risk management and conflict of interests.
- Financial Capacity: The financial focus includes assessing the financial position and stability of the organisation and its ability to effectively and efficiently manage the proposed level of DFID support.
- Operational Capacity: The operational capacity considers whether the organisation has the resources and systems in place to deliver the proposed outcomes.
- Value for Money and Results: In addition, the due diligence process assesses the organisation’s approach to value for money and its ability to measure and report the results of DFID’s grant.

If a due diligence finding highlights as unmanageably high risk for DFID the grant offer is withdrawn. Examples of where this happened in GPAF, include weak financial controls that could not be remedied and inappropriate or insufficient response to prior incidents of fraud within an organisation. Wherever possible DFID looks to put in place remedial actions that will allow the grant to go ahead. Once the grants are agreed all grant holders are required to submit audited accounts annually for review.

In making grant payments the FM is required to thoroughly check grant holder expenditure claims. This includes verification through requesting the supporting documentation for a random 15% of claims each quarter.

# Section 6: Management Case

A. What are the Management Arrangements for implementing the intervention?

Delivery of UK Aid Direct
The detailed management choices and arrangements for the transition period and selection of fund manager will be set out in the extended delivery plan for this programme which will retain at a minimum the assurance level established under GPAF, but seek to enhance this. The competitive procurement process under EU Directives will ensure that the appointed Fund Manager has the systems, process and staffing at an appropriate level to successfully manage the funding provided.

The extended delivery plan will build on this Business Case to address all key outstanding questions in the ‘ten key delivery questions’ under Better Delivery Guidance and set out below. Work will be focused on those with followed by an asterisk. In particular, it will focus on achieving value for money and commercial best practice in selection and on-going management by DFID of the fund manager, in managing the transition between GPAF and UK Aid Direct and in addressing risk and value in the operation of UK Aid Direct.

The Ten Delivery Questions: Better Programme Management
- Does the programme deliver UK government international development policy?
- Does the programme suit the local context and is it flexibly responding and adapting to changes, opportunities and citizen feedback?*
- Is there sufficient understanding of the evidence and, where there isn’t, are we developing and sharing evidence and learning incrementally?*
- Is the programme delivering our vision and does it continue to be good value for money?*
- Do we understand delivery risks, including the risk of fraud? Are they consistent with the risk appetite within which the programme is operating and are we able to mitigate these appropriately through the life of the project? Is it clear when to escalate issues to senior managers or ministers?*
- Do we know who else is working in this area and is there space for further, more effective collaboration or complementarity?
- How do we determine and measure success? How do we know the programme is working? Are we engaging beneficiaries in monitoring processes?*
- Are we clear on roles and responsibilities and do we have the right skills to provide programme leadership and management throughout the life of the programme?
- Is the timeframe realistic? Does it take account of lead in times and experience of previous projects?
- Have we set clear conditions for project partners? Are we tracking recommendations from annual reviews and performance improvement measures?

A CSD Team Leader will have lead responsibility for this work and will report to identified Senior Responsible Official (SRO). The DFID staffing resources required (set through on-going assessment of GPAF management requirements in the first two years of operation) would be:
1. Three CSD staff with clear roles and responsibilities - A2 Team Leader (70%); a B1 Programme Manager (70%); a B2 Programme Officer (70%)
2. The Head of CSD would chair the Advisory Panel and provide general advice and approval where required (10%)
3. DFID country offices, relevant policy teams and CHASE are asked to review shortlisted proposals during the competition process twice a year (using 10% cadre time)
4. The Secretary of State takes the final funding decision for all investment decisions using UK Aid Direct, including resource amounts, thematic windows and approval of grants.

Fund Manager contract management:
DFID’s CSD team will be responsible for procuring and managing the Fund Manager contract. This will include writing terms of reference and running the OJEU process with DFID’s Procurement and Commercial Department (PCD). Once the supplier is appointed, contract management includes setting out DFID’s expectations; bi-weekly meetings; quarterly performance reviews and review of risk management process; monthly financial reports; six monthly reports from the FM; annual review by DFID and annual portfolio analysis; annual survey of grant holders against Fund Manager performance; quality assurance of Fund Manager correspondence with grant holders.

Assessment of applications
At each funding round, DFID will set the eligibility criteria, approve the detailed guidelines, application forms and timeline, as well as setting the funding ceiling. The Fund Manager will set the appraisal methodology (based on criteria), produce guidelines and application form. They will communicate information about the funding round, provide applicants with detailed feedback and additional support to organisations new to DFID funding, including workshops on logframes, setting budgets and the application process.

There will be two stages to the application process:
1. Concept note – organisations submit a short concept note. The Fund Manager will assess the concept notes and DFID will agree which should be invited to move to full proposals.
2. Full proposal – shortlisted organisations will be invited to submit a full elaborated proposal. These are assessed by the Fund Manager with recommendations which are quality assured by a DFID team including county office and policy staff. The final decision on funding awards rests with the Secretary of State who will agree provisional grant awards.

Within the on-going management of UK Aid Direct and in the context of rolling investment decisions we will build further evidence and learning on the process and effectiveness of assessment, against issues such as speed of responsiveness, policy choices and risk management. If the evidence suggests a case for change then this will be considered.

Due Diligence of potential grant holders
Due diligence of potential grant holders for UK Aid Direct will be the responsibility of the Fund Manager (replacing the KPMG contract used for GPAF organisations). Assessment will follow the standards set out in the DFID Due Diligence framework. Each assessment will provide recommendations on whether the potential grant holder has the capacity to manage DFID funds for their intended purpose and whether any changes should be out in place prior to DFID funding commencing or in the early stages of funding. If an organisation has previously undergone a DFID due diligence check then any future checks should be proportionate.

The DFID team will review the recommendations and follow up on any points that need further clarification and decide whether to accept them. Decisions are risk-based. DFID has a low risk appetite for financial instability or weak financial controls. However, as far as possible organisations with critical findings are given time bound opportunities to address weaknesses.

Grant Arrangement
The Fund Manager will negotiate and agree budgets with grant holders; advise on and agree monitoring frameworks including logframe and baselines; produce grant agreements (GA) for DFID signature with standard clauses and conditions plus any arising from the due diligence process. The wording of the GA will be reviewed at each round to ensure that is accurate and up to date. The DFID team quality assures each before signing.

Grantees will liaise directly with the Fund Manager and provide quarterly reports on actual and planned expenditure. They will report on progress against results frameworks annually. For projects that present a high risk, partners will be required to report more frequently.

Where grant holders use implementing partners they are required to have a Memorandum of Understanding between them that incorporates all the conditions in the DFID grant. This increases DFID’s reach and assurance throughout the funding chain.

Grant management
The Fund Manager will lead on the day to day management of the grants including:
1. Assessing annual reports and independent evaluations and providing feedback
2. In year project monitoring including quality assurance visits
3. Ensuring compliance with grant arrangement
4. Annual portfolio analysis
5. Oversight of risk management process that is both embedded in day to day work and reviewed at a quarterly management meeting between DFID and FM
6. Ensuring the correct and proper close of projects in line with approved plans
7. Agree any budget revisions throughout the life of the project for all approved grants based on an established criteria
8. Issuing of revised grant arrangements for DFID signature
9. Checking, verifying and authorising expenditure claims for fiduciary oversight
10. Disbursement of project funds on a quarterly basis
11. Review grantee annual audited accounts
12. Monthly financial forecasting
13. Reviewing and verify payments against end of year financial statement.

As part of outreach activities, the Fund Manager will ensure regular updates and messages are communicated to MPs and the public and address any media queries.

The Fund Manager will be responsible for all project closure activities, following DFID procedures, including for disposal of assets.

GPAF and other funds have highlighted the importance of proactive in-year project monitoring. The manager will apply a proactive management approach and closely monitor poor performing or at risk projects. Early action will be taken to put in place performance improvement plans that are monitored through engagement with the grant holder and where needed through in-country project visits. DFID maintains oversight in-year project monitoring through bi-weekly progress meetings with the Fund Manager. Where a project is consistently performing poorly, DFID and the Fund Manager will take a decision to either suspend funding until the required action has been completed or close the project. The capacity to do this will be an important part of the selection criteria for UK Aid Direct’s fund manager.

B. What are the risks and how these will be managed?
This is a medium to low risk level programme. The risk matrix below outlines the key risk to the programme and the probability and impact of them occurring. The addition of a portfolio risk management approach under UK Aid Direct will allow a more comprehensive management of risk across the entire set of projects. This will be explored and undertaken through the delivery plan and assessed at annual strategic investment decision points. Ministers may wish to adjust risk appetite within areas of UK Aid Direct in order to reach particular policy or results objectives.

The Fund Manager, together with DFID, implements a comprehensive risk management strategy for the fund. This provides oversight of all aspects of the grant portfolio (technical and financial) and is reviewed quarterly. A proactive management tool, known as ‘PMON’, records all projects deemed to demonstrate a higher risk on a register. This register is discussed with DFID at fortnightly meetings and ensures that these projects are provided additional oversight and support until issues are resolved.

In addition, quarterly audits of 15% of the portfolio are undertaken to mitigate fraud risk. Projects that have been classified as medium and high risk are more likely to receive project visits. Learning and evidence from GPAF and UK Aid Direct will be used to review audit frequency and this can be subject to change, depending on business need.

Table 4: Risk Matrix for UK Aid Direct
(Note this will be further articulated within the extended Delivery Plan and will integral to investment decisions points).

Risk	Probability	Impact	Mitigation
The competitive application process could prove to be an inefficient aid delivery mechanism and not generate the most appropriate projects to help meet the MDGs and Post-2015 Framework	Low	Medium	The rigorous application and assessment processes ensures that the strongest applications, which best contribute to development goals, are selected. / There is also considerable outreach undertaken to ensure organisations across the UK are aware of the grant making strategy and application process. / Value for money is ensured through a two stage process whereby weaker applications are weeded out at concept note stage
There is an insufficient pool of organisations that can deliver high quality development interventions	Low	Medium	Phase one of the GPAF has had a large number of quality proposals / An organisation with an inability to deliver would not be funded. / Capacity building and support to grant recipients will be part of the fund manager’s role
Projects do not deliver results	Low	High	The fund manager will conduct regular project monitoring and requires annual narrative, data and financial reporting from grantees / All organisations will be assessed on their ability to deliver in the due diligence process / All projects will be subject to normal DFID business rules including Annual Reviews, Logframes etc…
Results from relatively low-value projects could prove unsustainable	Medium	Medium	Project selection will consider sustainability of the proposal in the assessment process / Due Diligence will provide a level of assurance on the sustainability of each project selected
Fraud and misuse of DFID resources	Medium	High	The fund manager undertakes regular project monitoring. Any suspected or alleged misuse of funds is thoroughly investigated by the fund management staff and/or an independent forensic audit team. / All organisations receiving DFID funding will be subject to due diligence to ensure the risk of fraud is low.
A small number of the countries are fragile or conflict affected. Increased insecurity could disrupt project implementation or project itself could increase insecurity.	Medium	High	DFID and the fund manager undertake regular monitoring of projects and, where necessary, projects can be suspended until the situation in-country improves.
Under performance of the fund manager	Low	Medium	The contract will be awarded through competitive tender ensuring it is awarded to a high performing organisation. / The fund manager will be subject to the normal DFID business rules including Annual Reviews, Logframes etc… / Regular meetings and conversations will be conducted between DFID and the fund manager to ensure high performance.

C. How will progress and results be monitored, measured and evaluated?
DFID has a clear ambition to secure maximum value for money in aid through rigorous independent evaluation and an unremitting focus on results. The work within GPAF and UK Aid Direct contributes to strengthening the evidence base for why we should work through Civil Society partners, their contribution to international development goal and the modalities for achieving results, including challenge funds.

CSD is putting in place a department-wide theory of change and corresponding evaluation, learning and evidence strategy. The strategy aims to embed high quality and strategic understanding about CSD’s area of work across DFID and the civil society sector. This holistic strategy will ensure that CSD is working across a common framework, and can support DFID and the sector efficiently and coherently. The Strategy will:
- Develop a theory of change for civil society in conjunction with partners;
- Review the assumptions and evidence base for the theory of change;
- Develop evaluation and learning strategies for CSD funding;
- Identify key evaluation questions to answer DFID and Sector learning needs;
- Define what robust evidence looks like and seek to embed data collection standards in CSD managed projects.

Investment decision points within UK Aid Direct will review and consider:
1. cumulative results from GPAF and UK Aid Direct financing to date
2. results anticipated from proposals moving into implementation
3. the results ambition and implications of future policy and resource choices

The Fund Manager will report to DFID on progress towards achieving targets in the programme logframe (Annex A).

Monitoring
Monitoring at both the fund and project level will provide understanding and assurance that each is being delivered according to agreed expectations. In addition, data collected through the monitoring process will be used to answer evaluation and learning questions.

At the Fund level, monitoring will take place through:
1. An annual report to DFID on progress towards the programme logframe targets, as well as reporting quarterly and six-monthly on progress and risks.
2. An annual portfolio analysis on themes, issues and learning across the fund. This analysis will guide the focus on the evaluation and learning strategy as well as feed into wider learning for DFID and the sector.
3. DFID will produce an Annual Review using the standard DFID format.

UK Aid Direct will feature monitoring systems at the individual project level including:
1. Each grant holder collecting baseline data and develop an approved (by the Fund Manager) logframe in the DFID format in the first three months of the project before receiving finance. Grant holders are required to disaggregate data by gender and other marginalised groups.
2. Grant holders notifying the Fund Manager if the project and the logframe need to be altered. Logframes may be revised in response to changing contexts and/or learning within a project.
3. Grant holders submitting an Annual Report with progress measured against the logframe and to provide a project score and setting out their risks, assumptions and their approach to obtaining value for money. The Fund Manager will review the reports and scores to ensure a clear story on progress, results, and that projects are on track. If an Annual Report is either not of a sufficient quality or raises performance concerns the project will be closely monitored. Either remedial action will be taken or the project will be closed (see above for detail).
4. At the end of the project grant holders are required to submit a Project Completion Report with a project score, in line with the DFID template and scoring. The Fund Manager will review the reports and scores to ensure there is a clear results story.
5. Grant holders are required to either commission or be part of an independent evaluation. Any evaluation will in part verify grant holder self-reporting of impact. It should also add to the evidence base around the programme theory of change. Evaluations must be proportionate.
6. Both the Annual Report and Project Completion reports require beneficiary feedback to be collected. In addition, seven current GPAF projects are taking part in a DFID pilot programme to test approached to collection beneficiary feedback and integrating it into project management decision making. This is a three year pilot ending in March 2016. Findings from the pilots will inform beneficiary feedback requirements under UK Aid Direct.

In addition, the Fund Manager is required to make spot check visits (estimated at present to be about 15 % of the portfolio) to projects throughout the year. Visits are determined in part on a risk basis (if financial or narrative reporting raises concerns) and partly on a random basis (to strengthen the relationship between the FM and the grant holders). Visits will be done using local consultants and focusing on multiple-projects in the same area where possible.

Evaluation
UK Aid Direct recognises the relatively limited evidence of the role of Civil Society and the best funding mechanisms for different sized CSOs. UK Aid Direct will invest in and generate high-quality learning and evidence for wider use in development, working closely with other parts of DFID, to widen the impact of DFID investment in civil society and to contribute to DFID’s portfolio of interventions on policy and learning.

The extended delivery plan will explore opportunities for innovation and efficiency in evaluation, including thematic or regional evaluations across a range of UK Aid Direct projects. It will also consider how to work with other parts of DFID, such as Research and Evidence Division, and externally, to generate a body evidence on the impact of the fund over time. Regular strategic decisions will consider whether support should be offered specifically to build research and evidence against the overall objectives of UK Aid Direct.

Evaluations are likely to consider questions related to: the added value of centrally funded CSO projects rather than funding from country offices; the optimum characteristics of competitive challenge fund type arrangements; the extent to which UK Aid Direct contributes to building capacity in funded organisations; the extent to which investing in smaller organisations represents value for money; and the advantages and disadvantages of “open” and thematic funding rounds.

The GPAF is subject to an independent evaluation being carried out by Coffey (already contracted to undertake evaluation of the GPAF and PPAs). The next planned evaluation under this contract is the end of programme evaluation in 2016. Prior to this date, we will work with Coffey to refresh the current evaluation plan for the GPAF ensure that we continue to learn from existing GPAF projects and that UK Aid Direct can adapt and respond to further evidence and learning.

GPAF is also part of a DFID-wide pilot to test approaches to collecting beneficiary feedback. This three year pilot is due to end in 2015. Lessons from the pilot will be incorporated in to GPAF and UK Aid Direct to improve engagement with beneficiaries. In the meantime all projects are required to ensure participation of beneficiaries at all stages of the project (see Appraisal Case).

Logframe
The quest number for the logframe for this intervention is 4530891. This is the overall logframe for UK Aid Direct as a DFID programme. Each individual grant will have a separate logframe that will be assessed at application stage and agreed before the grant award.