Annual Review

Title: Security & Risk Management in Hostile Environments
Programme Value: £1,819,617		Review Date: August 2016
Programme Code: 203978	Start Date: July 2013	End Date: March 2018

Summary of Programme Performance

Year	2015	2016
Programme Score	A	A
Risk Rating	Minor	Minor

The Security and Risk Management in Hostile Environments project promotes improved NGO safety and security by strengthening NGOs’ security management practices (through the European Interagency Security Forum) and by developing accessible, effective safety and security training (through RedR).

This annual review covers the progress of both organisations in the reporting period.

Summary of progress

RedR

The Mission Ready online security training, developed by RedR and its partner DTS, is a cost-effective method of reaching a wide audience, equipping users with the knowledge and skills to asses and manage their own security. The target of Mission Ready is intended to be primarily field-based national staff unable to attend face to face security training because of financial, visa or other restrictions.

During the reporting period the first Mission Ready module, Field Security Management, went live and has proven to be a well-developed online course utilising gaming technology to promote interactive learning. While there is work still to do on improving impact evaluations and developing a marketing strategy to ensure future sustainability, Mission Ready is on target to meet its predicted number of active users and is offered in 4 languages (Arabic, English, French and Spanish).

The second Mission Ready module, Remote Security Management, has also been developed during the reporting period and is due to be launched in August / September 2016.

European Interagency Security Forum (EISF)
EISF has continued to grow in size and quality as an organisation. In the reporting period it increased its membership to 83 organisations and demonstrated high levels of member engagement – 93% of members used EISF products and services and the Berlin forum had the highest ever member attendance. Levels of engagement via the website exceeded all milestones, demonstrating EISF’s relevance to the NGO security sector.

EISF has engaged specialists and organisations on a gratis basis, ensuring high quality products and events at low cost. It has also supported the development of country-specific NGO security fora in the UK, France, Spain and Switzerland and regionally in the Middle East and North Africa (MENA) and West Africa.

EISF may require DFID support to engage with other European donors and expand its governmental donor base beyond DFID (UK), OFDA (US) and FDFA (Swiss).

Key Lessons and Recommendations for RedR, EISF and DFID

RedR
- The CHASE OT Security Adviser should remain on the RedR Mission Ready Steering Committee.
- RedR should continue develop an app and offline versions of Mission Ready to enable access in locations with poor internet.
- RedR should develop its marketing approach to ensure maximum uptake of Mission Ready in the sector, ahead of DFID funding ending in 2018.
- DFID should to continue explore the possibility of further co-funding to RedR to support the development of an interactive module on Protection training.
- DFID should continue to explore the possibility of providing further funding to RedR to allow it to expand security training to UNDP for security focal points working in humanitarian emergencies through the new Specialist Services Business Case.
- DFID should promote uptake of the course internally for use by its staff.

EISF
EISF should aim to expand its donor base and secure funding from other European donors. DFID should play a role in advocating with these donors on EISF’s behalf where requested.
- EISF should do more to promote its activities on social media and consider reviving the area of the EISF website where members can exchange information.
- EISF should collaborate with relevant organisations to help raise the profile of NGO humanitarian security at external events.
- EISF should consider how its model could be replicated to build the capacity of southern based NGOs in security risk management.
- EISF should update its Security to Go guide with new sections on sexual violence and human resource management.

Other Recommendations and Actions

New Specialist Services Business Case
Attacks against humanitarian aid workers persist and it remains a highly dangerous profession. It is therefore recommended that funding from the new Specialists Services Business Case should be earmarked for projects that contribute to improved security risk management amongst national and international humanitarian organisations. It is anticipated that when the Specialist Services Business Case has been approved this Security & Risk Project will close and the activities currently supported will be transferred to the new business case.

INGO Safety Office (INSO)
INSO is a specialised and respected INGO that has now been operational for 5 years. Through its country programmes INSO provides: analytical reports based on its network of analysts (many of whom are in inaccessible locations, including Syria); informed humanitarian access advice to NGOs; raw data (enabling NGOs to make their own spatial and temporal analyses); regular in-country security briefings for NGOs; in-country security coordination mechanisms for the aid sector; bespoke services to NGOs (e.g., crisis management, capacity building training, site assessments) and advocacy with national and sub-national authorities on behalf of the humanitarian community. INSO is the only NGO working operationally on the safety and security of humanitarian and development organisations across multiple conflict-affected countries.

DFID provided £594,000 to INSO between 2014 – 2015 for institutional support and scale up of its then 5 country programmes and for the development of a sustainable funding strategy. INSO has subsequently secured €1m a year over 3 years from MINBUZA (the Dutch government), increased to 10 country programmes and successfully sought in-country funding for these. INSO is now seeking to further consolidate its country programmes and strengthen the organisation.

DFID should consider providing new funding to INSO from the new Specialist Services Business Case as part of its broader support to improve the safety of aid workers working in humanitarian emergencies. DFID should coordinate its support with MINBUZA and other governmental donors to ensure a strategic approach.

National Organisations and Staff
National staff are at far greater risk of injury, kidnap or death in the course of their work, either as independent operators or as implementers for INGOs. However, they may lack the resources or capacity to implement the same standards of security risk management as international organisations.

DFID should consider what new support it can provide to build the capacity of local organisations in security and risk management, possibly through the new localisation Business Case (yet to be written).

Logframe(s)
Update logframe(s).

A. Introduction and Context

DevTracker Link to Business Case:	4609266

Period of review July 2015 – July 2016

Humanitarian aid workers continue to face high levels of risk. In the 12 months from August 2015 to July 2016 in the course of their work:

- 82 national and 2 international staff were killed;
- 40 national and 8 international staff were kidnapped;
- 71 national and 12 international staff were wounded.

Countries of greatest risk for aid workers are currently South Sudan, Afghanistan, Central African Republic, Democratic Republic of Congo, Sudan, Yemen, Somalia and Syria. (Source: Aid Worker Security Database)

Such statistics are likely to be an underrepresentation of the reality: they are compiled from open sources where incidents affecting international staff are disproportionately reported, while access constraints in places such as Somalia, Syria and Yemen prevent accurate data collection.

National staff continue to represent the highest figures for death, injury and kidnap due to their number, their exposure and the fact that capacity building support in security management from donor INGOs to national partners may not always be provided (although there are examples of successful support initiatives to be found, including ICRC’s Safer Access project).

This project supports NGO Safety and Security in two ways:

(i) Accessible and effective training: A NGO-led partnership between RedR and Digital Training Solutions (DTS) has developed an innovative approach to humanitarian security training using interactive gaming software to improve knowledge retention through immersive learning. It complements existing face-to-face training, but as e-learning is able to reach more users at lower cost. It helps teach key skills, such as raising the awareness of personal security, preparedness and planning, security management, personal risk assessments, and travel security. DFID is jointly supporting the project with OFDA (US government), providing £260,000 to support the design and build phase of the training programme, with basic operation and maintenance support for a further three years. RedR has developed a price banding structure for users to help ensure the financial sustainability of the project.

(ii) Improved NGO security management and awareness: The European Interagency Security Forum (EISF) is an independent network of security focal points representing European-based humanitarian INGOs. EISF promotes stronger security management among its members working in conflict and disaster-affected countries. DFID had previously provided £150,000 to EISF and in April 2016, agreed to further extend its support by an additional £100,000 over 2 years.

In addition, DFID has provided funding to:

(iii) Recognise the risk faced by humanitarian aid workers: In recognition of the risks faced by humanitarian workers, DFID is contributing £61,000 through the Overseas Development Institute (ODI) towards the establishment of Humanitarian Aid Worker Memorial in London and annual memorial services held in Westminster Abbey.

## B: PERFORMANCE AND CONCLUSIONS

Annual outcome assessment

RedR MISSION READY:
Outcome	Safety and security of humanitarian actors is increased as a result of take up of Mission Ready
Indicator(s)	Milestones	Progress
1. Number of active users of Mission Ready	500 (1 year after launch)	282 active users 8 months after launch
2. Evident change in knowledge of Mission Ready users	Analysis component tool indicates 80% of users who complete the course increase knowledge (1 year after launch)	89% of user who complete the course increase knowledge

Mission Ready 1 (‘Field Security Management’) was launched in October 2015 and is a well-developed online course utilising technology to promote interactive learning. More than 50% of the ‘500 active users’ milestone had been met by June 2016. However, measuring impact is difficult as the 3-month impact survey returned only 8 responses. While 89% of respondents reported an increase in knowledge, the sample size is too small to be conclusive. Evidence of the impact of the training will become clearer as more users complete the course and fill in the M&E questionnaires.

Each individual user will typically complete the course only once. Therefore RedR’s marketing strategies need to be developed and implemented by the newly appointed Marketing and Communications Coordinator to ensure sustainability through proactive marketing to new users.

EUROPEAN INTERAGENCY SECURITY FORUM:
Outcome 1	Security Risk Management improved across the humanitarian sector through stronger relationships and greater trust
Indicator(s)	Milestones	Progress
1. % of EISF members who utilise EISF services	80% of members utilise EISF services, with a 5% growth in membership per year	93% of members utilised EISF services, with a growth rate of 6% (5 new organisations)
2. Number of stakeholders and external experts who facilitate at EISF events	At least 10 external experts facilitate at EISF events	27 external experts have facilitated EISF events
Outcome 2	Knowledge and experience on humanitarian security risk management is shared using EISF platform
Indicator(s)	Milestones	Progress
3. % of EISF members who utilise EISF website	70% of members utilise EISF website, with a 5% growth in membership per year	75% of members in 2016 member Survey stated they “often find information / resources they need on EISF website”
4. Number of visits to EISF website and number of documents downloaded per month	At least 3,000 visits and 600 document downloads	157,467 page views and 23,118 website users. 10,674 document downloads
Outcome 3	Integrated security risk management skills and knowledge improved
Indicator(s)	Milestones	Progress
5. Number of workshops / learning events organised by EISF per year	4 workshops / learning events	6 learning events
6. Number of articles tackling gaps in SRM implementation produced by EISF per year	2 articles tackling gaps in SRM implementation produced by EISF	2 articles

EISF continues to develop steadily. Its role in fostering strong relationships between humanitarian organisations is evidenced by 5 new members joining during the reporting period, with 83 organisations now full or associate members. Levels of trust are indicated by 93% of members utilising EISF services and the ability of the organisation to attract high levels of participation by external experts at EISF events. The relevance of EISF is indicated by 100% of members who completed the 2016 survey stating that EISF strengthened their approach to security risk management (with the caveat that 43% of members completed the survey). The EISF platform has proved a key repository for information on humanitarian security risk management, evidenced by web page views, users and document downloads well exceeding original milestones. These outcomes indicate that EISF is a well-utilised and valued platform for humanitarian organisations to manage safety and security risks in emergency settings.

Overall output score and description

MISSION READY:

Output 1: An innovative online security training system is available to the humanitarian sector through 6 interactive film based scenarios – A Output Met Expectations
Output 2: A series of high quality learning programmes to support the scenarios is available to the humanitarian sector including documentaries, expert interviews and written content – A Output Met Expectations

EUROPEAN INTERAGENCY SECURITY FORUM

Output 1: Members actively engage with each other and the EISF Secretariat and the relationships amongst security risk management stakeholders expanded and strengthened – A Output Met Expectations
Output 2: Members actively engage with each other and the EISF Secretariat and the relationships amongst security risk management stakeholders expanded and strengthened – B
Output 3: Capacity of Members of security risk management is improved and horizons broadened, EISF Secretariat identifies skills gaps in security risk management and develops means to address them, and practical tools and guides produced to fill skill gaps in humanitarian security – A+

Has the logframe been updated since the last review?
We have agreed a new logframe with EISF for the period of extension funding. RedR are proposing some changes to their logframe which will be discussed and agreed with them following completion of the Annual Review.

## C: DETAILED OUTPUT SCORING

MISSION READY: INNOVATION IN HUMANITARIAN SECURITY TRAINING

DFID is providing £260,000 to RedR between October 2014 and September 2018, in partnership with Digital training Solutions (DTS), to develop the Mission Ready training. Using training simulation exercises and online resources, the courses are designed to benefit humanitarian workers working in insecure environments, particularly national staff that are often at the front line of a response. Using gaming technology, Mission Ready challenges the learner to answer real time questions in realistic interactive video scenarios. The highly immersive training is designed to improve knowledge retention through active engagement.

Output Title	An innovative online security training system is available to the humanitarian sector through 6 interactive film based scenarios
Output number per LF		1	Output Score	A
Risk:		Moderate	Impact weighting (%):	25%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress

1.1. Number of scenarios made available to the humanitarian sector	2 (6 months)	6 interactive scenarios are now available in 4 languages
1.2 Participant feedback on quality, relevance and usefulness of online scenarios	Average participant score from 500 participants across all 3 factors is higher than 4 out of 5 (1 year after launch)	Average score 4.2 out of 5 (from 62 evaluations) 9 months after launch

Output Title	A series of high quality learning programmes to support the scenarios is available to the humanitarian sector including documentaries, expert interviews and written content
Output number per LF		2	Output Score	A
Risk:		Moderate	Impact weighting (%):	25%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
2.1 % of proposed programme learning tools made available to humanitarian sector	25% ( 6 months)	Achieved
2.2 Participant feedback quality, relevance and usefulness of additional online learning tools	Average participant score from 500 participants across all 3 factors is higher than 4/5 (1 yr. after launch)	4.5

Key Points
The first course (Field Security Management) was launched mid October 2015, and has issued 718 licences between launch in October 2015 and June 2016. Six interactive scenarios are designed to be innovative user friendly and engaging. Development involved the filming of 7 documentaries in Kenya at the Humanitarian and Peace Support School near Nairobi, accompanied by written content, quizzes, voiceover and visuals. The second course (Remote Security Management) is due to go live in August / September 2016, initially in English. Four interactive scenarios have been shot at the MOD’s training centre in Norfolk and DTS offices in Manchester.

RedR and DTS regularly meet face to face, or via Skype, to oversee development of the platform, with DTS submitting bi-monthly progress updates to RedR. A Steering Committee, of which DFID is a member, oversees project development and took part in user testing of the system. As the platform has developed it has become clear there were a number of functions, such as collecting user data, linking it to survey monkey for monitoring and evaluation purposes, and linking it to a payment method that had not been budgeted for. DFID agreed to changes in the budget to accommodate this. The project has proved useful organisational learning experience for RedR on how to develop a technology / information management based platform.

Marketing activities have included four launch events aimed at NGOs and the humanitarian security sector in London, Pakistan, and two in Nairobi. More than 100 people from humanitarian organisations, networks and local government attended. RedR also promoted the platform at the European Interagency Security Forum (EISF) in Berlin in September 2015, and in May recruited Marketing and Communications Officer, who will dedicate half their time to increasing the visibility of Mission Ready. The platform was also presented at the World Humanitarian Summit at a panel discussion side event, further helping to raise its profile. A promotional video has been filmed for circulation at events and conferences, and there is now a Mission Ready information page on the RedR website.

The main difficulty encountered for the project was streaming the video in locations with limited or slow internet speeds. To overcome this DTS has developed two versions of the game, with high and low resolution video options. A downloadable app is also being developed that will allow users to undertake the training offline, thereby increasing access in areas with poor internet connectivity. This is currently undergoing user testing and is set to go live at the beginning of August. Further testing is also being carried out on different platforms, including desktops, laptops, iPad and phones. RedR also experienced unexpected difficulties with the payment system, which has meant it now gives access to both courses automatically, but with a 60% increase in the price from $5 to $8.

When users access the training they are required to give comprehensive user data information which is collected and then stored. Once the training has been completed users are then required to undertake immediate impact evaluations, with follow up evaluations after 3 and 12 months. These also include a line manager, when one is provided. In May, RedR have reviewed the survey questions to increase the likelihood of completion. Post-game reports are also automatically produced at the end of each game; giving the user a description of their choices and an explanation of why (or not) their choices were correct given the scenario and context. RedR have made available to users “Knowledge Point”, an online resource that provides free and fast expert advice to humanitarian aid workers, and allows them to contact a network of over 100 technical experts with any follow up questions they may have on the training

Generally feedback on the platform has been positive. As well as the licences that have already been purchased, RedR has supplied free licences to 7 organisations (Handicap International, Action Contre Le Faim, World Vision Kenya, Metrography, CARE Canada, UNDSS, Humanitarian Innovation Fund, and Oxfam Horn, East and Central Africa), to test out the platform before placing bulk purchases. RedR are generally encouraging organisations to buy bundles of training for their staff by providing discounts for multiple purchases.

RedR submitted funding applications to ECHO and the Humanitarian Innovation Fund (HIF) to develop a module on Protection using the same successful methodology. Unfortunately both applications have been unsuccessful, but this is an area that is a priority for DFID and we should be open to co-funding this module if RedR is able to secure funding from another source. Success of the module will depend on the quality of the Steering Group overseeing content development. The focus of the training also needs further clarification to ensure it fills a gap in knowledge and does not replicate existing protection material.

RedR has also been in discussion with UNDP who are keen use Mission Ready to train their security focal points. We have consulted with colleagues in DFID responsible for UNDP funding but unfortunately the current proposal does not fit strategically with their funding streams. It also does not fit with HRG’s approved Business Case which is focussed specifically on support to NGO humanitarian aid workers. DFID should, however, explore if support could be provided through the new Specialist Services Business Case, which is due to be written in the autumn, particularly if the training would benefit staff working in highly insecure areas likely to have a humanitarian caseload.

Summary of responses to issues raised in previous annual reviews (where relevant)

1. DFID continue with the next tranche of funding for Mission Ready – COMPLETE
2. DFID remains on Steering Committee and be part of initial testing – PARTIALLY COMPLETE

EUROPEAN INTERAGENCY SECURITY FORUM

EISF is an independent network of security focal points representing European based humanitarian NGOs operating internationally. EISF is committed to improving the safety and security of staff and programmes, strengthening risk management to allow greater access to crisis-affected populations. The EISF Secretariat works in collaboration with its members to produce original research, arrange biannual forum meetings and workshops to facilitate information sharing between members and the wider humanitarian community. At the end of the July EISF had an active membership of 83 full and associate members.

Output Title	Members actively engage with each other and the EISF Secretariat and the relationships amongst security risk management stakeholders are expanded and strengthened
Output number per LF		1	Output Score	A
Risk:		Minor	Impact weighting (%):	10%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
1.1 % of EISF members who positively engage with EISF	60% attendance at EISF forums, with members scoring 4 out of 5 for quality and relevance, and 50% participate in at least 1 additional event per year	62% of Members attended at least 1 forum; 38% of organisations attended one or more workshops; EISF forum scored 3.5 out of 4 for quality and relevance
1.2 Number of country coordination events held per year	4 country coordination events	5: UK x 2; France; Spain and Switzerland
1.3 Number of stakeholders and external experts who support EISF research projects	At least one sector expert included in EISF Research working groups	11

Key Points

Over the reporting period EISF held forums in Berlin in September 2015 and Brussels in March 2016. The Forums are EISF’s primary mechanism for fostering relationships and improving trust amongst humanitarian security risk practitioners. The forums allow members to exchange information and good practice and to also engage with external stakeholders. The event in Berlin was attended by the most participants since EISF’s inception, with 49 representatives from 42 member and associate member organisations. Expert external facilitators and contributors attended, including DFID and OCHA. The focus of the September forum was on training and building trust throughout the humanitarian security sector. The March forum included external speakers from Aegis, UNDSS and Mott MacDonald, and focussed on operating in MENA.

The EISF Secretariat supported and attended 2 security focal point co-ordination meetings in the UK for British NGOs, with the Executive Coordinator also supporting the re-activation of the French security coordination group and supporting and advising the Spanish Access Working group. A meeting was held with Swiss NGOs. The Executive Coordinator also facilitated a coordination meeting for regional Security Focal Points in Amman, helping establish the MENA Regional Security Forum, and met with regional Security Focal Points in West Africa to share experience and raise awareness.

A working group made up of EISF members, external experts and an EISF Researchers is established to oversee every EISF publication. Eleven sector experts took part in 4 EISF research working groups. This approach helps ensure publications are grounded in operational practice and experience and benefit from fresh perspectives. The diverse membership of the working groups helps strengthen engagement in the network and builds relationships across the sector.

Output Title	Members actively share information and respond to requests, EISF website and social media is an up to date resource for humanitarian security issues, and EISF ensures the global debate on humanitarian security issues considers the needs of EISF members
Output number per LF		2	Output Score	B
Risk:		Minor	Impact weighting (%):	30%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
2.1 Number of members updates circulated per year	24 EISF updates circulated	20 updates
2.2 Number of external vacancies and training events added to the EISF website per month	At least 20 external notifications added per month	12 events and training listings per month on average, plus job vacancies
2.3 Number of original papers and translations produced per year	1 paper, 2 short research reports and at least 1 translation per year	2 new full papers initiated; 2 new short research reports
2.4 Number of EISF blogs produced per month	At least 3 blogs produced each month (36 total)	16 blogs plus 1 per month on status of EISF research
2.5 Number of external events and working groups that EISF participates in	EISF participates in 8 external and 2 working groups	5 external events and 5 external working groups

During the reporting period 20 updates were circulated by the EISF Secretariat informing members about security sector events, publications, and topical news pieces. The updates help encourage debate between members in the network and allow the Secretariat to give notification of upcoming event and publications.

EISF’s website is managed by the Secretariat to provide a knowledge sharing resource for members and users. On average, 12 events and training listings were added per month during the reporting period, as well as job vacancies. The vacancies section of the website is the most visited area and, anecdotally, it has been reported that vacancies posted on the EISF website increase both the quality and quantity of applicants for security roles in NGOs.

EISF is recognised for its original research papers which helps bring new thinking into the sector, share good practice and learn lessons. Research priorities are chosen by members. EISF was without a full-time Research Adviser for 7 months during the reporting period which unfortunately has impacted negatively on the number of new papers and guides produced. Two new papers were initiated - on the Review of the NRC Ruling and Implications for Duty of Care (due to be published in September 2016), and Managing Security Staff with Diverse Profiles.

EISF produced 16 blogs over the reporting period, with content provided by the Secretariat and by external experts. These ae intended to provoke thought and debate on humanitarian risk management across the sector. In addition, 1 blog per month was produced on the status of the EISF research programme.

EISF participated in 5 external working groups, as well as 5 external events during the reporting period. Sector working groups included: (i) BOND Working Group on the Impact of Counterterrorism Law on Humanitarian Work; (ii) Saving Lives Together Oversight Committee; (iii) IASC Task Team; (iv) UK NGO Military Contact Group; and (v) Institute of Risk Management Charity Special Interest Group.

External events included: (i) Presentation at the publication of Communications Technology and Humanitarian Delivery at 36th Forum on the Working Group for Emergency Telecommunications in Dubai; (ii) Presentation at the Communications Technology and Humanitarian Delivery paper at the University of Oxford; (iii) Saving Lives and Staying Alive MSF Crash Book Launch; (iv) Quaynote Conference; and (v) World Humanitarian Summit.

Unfortunately EISF efforts to raise the profile of security at the World Humanitarian Summit pre-summit workshops and high level roundtables were relatively unsuccessful. EISF did, however, manage to galvanise support from other security bodies and stakeholders at the Security & Wellbeing stand for: (i) Core commitment 3: Commit to ensure populations in need receive timely and unimpeded humanitarian assistance; and (ii) Core commitment 4: Commit to redouble efforts to respect and protect humanitarian and health care workers and facilities against attacks, threats or other violent acts that prevent them from fulfilling their exclusively humanitarian function.

Output Title	Capacity of members for security risk management is improved and horizons broadened, EISF Secretariat identifies skills gaps in security risk management and develops means to address them, and practical tools and guides produced to fill skill gaps in humanitarian security
Output number per LF		3	Output Score	A+
Risk:		Minor	Impact weighting (%):	10%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
3.1 Number of external stakeholders participating in EISF forums	3 external stakeholders participating in EISF Forums	19 external stakeholders
3.2 Number of capacity building events facilitated by EISF	3 capacity building events participated in and / or organised by EISF	4 capacity building events
3.3 Number of guides and tools produced by EISF	At least 2 guides or translations produced per year	1 new guide and 1 translation

A total of 19 external stakeholders participated in the EISF forums held in Berlin and Brussels over the reporting period. External speakers are invited to help encourage EISF members to reflect on their own approaches to risk management and gain insight into how risk is managed in other sectors. The inclusion of external speakers in the forums also helps build relationships between professions and allows the Secretariat reach out to high profile academics and experts.

The EISF Secretariat organised 4 capacity building events during the reporting period:

(i) Risk Assessment Training of Trainers workshop, hosted by Medecin Sans Frontier (MSF) in Amsterdam, to provide global and regional security focal points with the skills needed to identify staff learning needs on performing risk assessments;

(ii) Humanitarian Operation in Conflict Zones: from risk aversion to risk management – a joint round table event with MSF UK and Humanitarian Practice Network (HPN) to discuss the difficulties of effective risk management in high risk contexts;

(iii) Inclusion and Security of LGBTI Aid Workers – a joint workshop with RedR exploring the current practices and growing concerns about international development and humanitarian organisations’ approach to the inclusion of LBGT humanitarian workers, safely and without discrimination;

(iv) Operating in Conflict Environments – where Humanitarian Outcomes presented the finding of their Secure Access in Volatile Environments project.

EISF also organised 2 webinars on Applying Serious Gaming to Human Security and Security Risk Management and Aid Worker Wellbeing.

During the reporting period EISF published one new guide, “Security to Go: A Risk Management Toolkit for Humanitarian Aid Agencies”, a simple, easy to use guide for non-security experts to quickly set up basic safety, security and risk management systems in new contexts or in rapid onset emergency situations. The guide remains EISF’s most popular publication and work is underway to add modules to it on sexual violence and human resource management. EISF are also working with Translators Without Borders to translate it into Spanish. The Secretariat have translated the guide “Opening an Office” in to French. Work is also currently underway, on a pro bono basis, to update the EISF Abduction Management Guide and make it into a practical guide. Publication is expected later this year.

Summary of responses to issues raised in previous annual reviews (where relevant)

1. DFID to consider further support for EISF over 2015-17 period. COMPLETE

2. EISF to explore further use of innovative technology and social media to allow for widest audience participation. EISF Research Adviser has developed a social media plan to raise awareness on humanitarian security risk management issues but due to staff shortages the Secretariat have been unable to develop and implement a full communications plan. Consistent measuring of EISF social media activities has commenced over the last 3 months and indicates increasing engagement.

MEMORIAL FOR HUMANITARIAN AID WORKERS

Key Points

There has been good progress over the reporting period to establish a humanitarian memorial in central London. The decision to move the location of the memorial from Westminster Abbey meant the Steering Committee had to identify an alternative venue. After consultation with local stakeholders and Lambeth Council, the Coin Street Neighbourhood Centre has been chosen as the preferred location.

The Steering Committee have also successfully secured a contract with the Contemporary Arts Society to project manage the commissioning of an artist and the design process. From a long list of eight, an internationally renowned artist has been selected to design a fitting memorial.

In addition to the contribution made by DFID, fundraising for the memorial is actively underway. The Steering Committee is reaching out to their personal contacts, and High Net Worth individuals are also being approached. A Just Giving page has also been set up which had raised just under £100,000 of the £300,000 target at the time of writing.

The 2016 memorial event will be held at Westminster Abbey on 18 August. Some 160 people have RVSPd. DFID’s Minister of State will represent DFID and say a few words, with other senior DFID officials also in attendance. It is expected there will be some media coverage. The launch event for the memorial itself at the Coin Street Neighbourhood Centre will take place sometime during 2017. DFID funding for this part of the project ends on 30 September 2016.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance

RedR

Mission Ready online training is more cost effective than face-to-face training, and therefore should be able to reach many more users than conventional training methods. It is currently on track to reach up to 500 users this year. Given this, it should also be more attractive to national staff working in insecure environments, who are the primary target audience. Value for money can be further maximised by bulk buying licenses (Save the Children has bulk-purchased over 100 licences in the last six months). The built in user surveys also allow for low cost monitoring and evaluation, and measuring the impact of the training.

RedR has achieved project cost savings by: sharing resources with RedR Kenya to provide staff support to DTS during filming; negotiating discounts with HPSS training facility for accommodation and facilities; using existing relationships to secure documentary interviews for free; sourcing multiple quotes to obtain the most competitive price for translation into French and Arabic, and using in-house language skills to translate into Spanish.

EISF
EISF’s membership is growing, which indicates that the organisation is providing a valued and useful resource. Members are required to pay a membership fee, which goes someway to reducing the organisation’s reliance on donor funding and improves sustainability. EISF’s main costs are staff costs and these have been lower than expected over the reporting year due to staff turnover and vacancies. This has not affected delivery. EISF members provide meeting venues for free, with sector experts also often providing pro bono peer review of research and other technical support. For example, the “Operating in Conflict Environments” workshop held in May was hosted in Paris by the French Red Cross and expert input for the “Abduction Management” guide was provided by Aegis pro bono.

Assessment of whether the programme continues to represent value for money

The project is judged to still offer value for money. With attacks against humanitarian aid workers continuing it remains a highly dangerous profession. DFID’s relatively small investment in this area is valuable and helps strengthen humanitarian delivery and efficiency overall in high risk environments. DFID should explore what further support it can offer, particularly to improve the safety and security of national organisations and staff, who are often in the greatest danger.

Quality of financial management

Both organisations are demonstrating good quality financial management. RedR requested moving some funds between budget lines as the project developed and it became clear some functions such as collecting user data or linking to a payment method had not been budgeted for. RedR submitted its latest financial report alongside its narrative report for this annual review, and the bulk of DFID’s support to RedR has now been disbursed. EISF’s first payment for the extension period is due in September 2016, payable in arrears.

E: RISK

Overall risk rating: Minor

The overall risk of the project is considered minor. Whilst the objective of the project is to improve the safety and security of humanitarian aid workers who often work in highly dangerous situations, risk to the successful delivery of the project is considered low. Much of the work to create the Mission Ready online training platform is being done in the UK, minimising the risk to project delivery, though RedR will need to develop an effective marketing strategy to ensure ongoing uptake of the courses. Similarly, most of EISF’s activities are undertaken in the UK and/or Europe. Should it attempt to do more directly with national organisations in the future the risk rating for that component of work could increase.

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe

All projects remain on track for delivery against their planned timeframes.
- The next humanitarian memorial event is due to be held in Westminster Abbey on 18 August 2016 and good progress has been made by the Steering Committee to identify an artist to design the memorial itself. DFID support for the humanitarian memorial component with ODI ends on 30 September 2016.
- DFID support to RedR continues until 31 March 2018. Initial contracting delays have now been overcome, and with the design and build phase of the project now complete DFID support is for ongoing operation and maintenance of the platform. The second course will go live in August / September 2016.
- DFID agreed a further 2 years support to EISF from 1 April 2016, and progress largely remains as expected against agreed milestones.

Performance of partnership (s)

RedR report that several partnerships were strengthened over the year. In particular the partnership with DTS has developed as the two organisations have worked closely to develop the training platform. In addition, RedR has developed relationships with its two donors. Also, RedR were able to take advantage of DFID’s contacts with the British Council in Kenya to launch the platform in Nairobi.

Asset monitoring and control

Whilst the project does not produce any physical or capital assets, DFID has been granted a free licence for the Mission Ready online training platform which we will consider making available to the rest of the organisation.

G: CONDITIONALITY

Update on partnership principles (if relevant) Not applicable

H: MONITORING & EVALUATION

Monitoring progress throughout the review period

The training has been designed in way that captures comprehensive monitoring and evaluation information as users complete the course. RedR are currently re-evaluating the impact surveys to improve response rates.

EISF evaluation forms have been updated by training experts to incorporate practice change questions as well as learning questions. Event participants are sent follow up questions to complete at 3 and 6 month intervals to assess change in practice as a result of EISF events. The Secretariat conducted a survey of members and non-members in February 2016 to inform the strategic direction of EISF Steering Group. At the next forum in September EISF will discuss with its membership how to improve impact monitoring.