Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Building a Reliable Investment Climate in Kenya
Programme Value: £15.3M		Review Date: March 2016
Programme Code: 203348	Start Date: 19 March 2013	End Date: 31 March 2017

Summary of Programme Performance
Year	2014	2015	2016
Programme Score	A	A	A+
Risk Rating	Medium	Medium	Moderate

Summary of progress and lessons learnt since last review
This review is less intensive; the WBG KICP II Mid Term Review is running in parallel, the report of which is expected to provide an assessment of the design, implementation, value for money and results accomplished by the programme when compared to the planned targets. The project is also due for a Project Completion Review in the next reporting cycle.

The delivery of the project’s outputs is on track with an average score of an ‘A+’ Outputs exceed expectations’.

Below is a summary of the results:

Output 1: Reformed regulatory environment (A+):
Significant progress was made leading to Kenya being highlighted as one of the global top 3 reformers by the World Bank, and an extraordinary change in the Ease of Doing Business Ranking of 26 points from 134 to 108 was achieved. In Kenya’s second and third cities, launch of the Mombasa and Kisumu County E-Business Permit and E-Construction permit systems respectively helped to speed processes, significantly increase revenue collection and reduce corruption. The Mombasa e-business system had generated revenue amounting to about Ksh 250M by mid-February 2016 while the Kisumu e-Construction system attracted an average of Ksh 7M collections by the same period.

Output 2: Effective competition (A+): Transaction advisors finalized feasibility studies and PPP transaction plans for six selected early mover transactions. The Special Economic Zones Act 2015 which had been lagging for four years was enacted, and regulations drafted. Work with the Competition Commission took off, generating two cartel enquiries and 11 submissions on anti-competitive practices and policy.

Output 3: Effective environment for public private partnerships - PPPs (A+):
PPP sector strategies for the road, rail, ports, airport, water, energy, health and education sectors, as well as for county PPPs, were developed then discussed with the relevant line ministries and contracting authorities. Significant progress was made on a number of national PPPs with the market, including the KU hostel, Independent Power Producer and five other projects expected to be closed by the end of the feasibility stage. Four roads and highway PPPs and the (Mombasa) Nyali Bridge and Kisumu Port revitalisation were at end of the transaction appraisal cycle and one PPP was let.

Output 4: Strengthened demand and evidence base for investment climate reform (A):
Kenya Private Sector Alliance (KEPSA) has made significant progress in redefining the changes required to create a more effective environment for investment and presenting the collective policy views of the private sector to the public and to the government of Kenya (GoK). KEPSA has ‘hosted’ two Presidential Round Tables (RTs) and a Deputy President (RT) among numerous other advocacy events at which investment policy challenges have been debated; actions agreed, prioritised and acceded to by the President, Deputy President, Cabinet Secretaries and other senior GoK officers publicly.
DFID is supporting the Kenya Agribusiness and AgroIndustry Alliance (KAAA) in rebranding itself to deliver value to its members and lead on reforms in the agricultural/agroprocessing sector in its bid to achieve financial sustainability and strengthen its institutional capacity, working with the World Bank.

Summary of recommendations for the next year

The BRICK programme completes early in 2017. During the next months, after the production of the WBG Mid Term Review report, the focus should be on working with stakeholders to generate a concrete plan for future reforms.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-203348/documents/
DevTracker Link to Log frame:	http://devtracker.dfid.gov.uk/projects/GB-1-203348/documents/

Outline of the programme

The UK Government is providing £15.3 million to contribute to poverty reduction by improving the environment for businesses and economic development in Kenya. BRICK reflects the Prime Minister’s Golden Thread and G8 narrative on economic growth and institutional reform. BRICK is a four year programme approved in 2013 and is aimed at delivering the following outputs:

1. Regulatory reforms: Improved business environment through reduction in burdensome red tape that prevents Kenyan businesses from rapidly industrialising and growing to their full potential at both the national and county levels (30%)
2. Effective competition among and between firms in markets that are essential for the growth of the agribusiness sector and increased opportunities for the poor (30%)
3. Supportive environment for the private sector to participate in provision of infrastructure, such as energy and transport, which are needed for employment and growth through public private partnerships (30%).
4. Strengthened demand and evidence base for investment climate reform in Kenya (10%)

The rationale for the support is to bridge the existing capacity gaps in the Government of Kenya in designing and managing modern reform processes, and in procuring world class reform advisers. The programme is expected to result in effective transfer of skills and knowledge on reforms in both the national and sub-national levels of government in Kenya.

Most of BRICK’s funding, £12.45M, is channeled through the International Finance Corporation (IFC) Kenya Investment Climate Programme (KICP II) for the benefit of their Kenya partners who include quasi-government bodies, regulatory agencies and selected units within government (both at national and county level). The Dutch government contributes 20% of the IFC KICP II project funding. BRICK’s support to KEPSA is currently valued at £2 million to support the strategy formulation and implementation aimed at improving its capacity to execute its advocacy mandate and support it to financial sustainability. DFID has also recently approved funding worth £0.2 million to support the institutional strengthening of KAAA for a period of twelve months.

BRICK contributes to the Kenya Operational Plan (OP) vision of “stimulating growth, led by the private sector and with a focus on job creation; and improving service delivery. The following are some of the programme’s expected results:
1. reduction in regulatory burdens and red tape on private sector and businesses by about $20 million annually over the life of the programme
2. reducing the number of days relating to starting a business, registering property and getting an electricity connection from, respectively, 32, 73 and 146 to 20, 30 and 60 days
3. improve the quality of environmental regulation (measured by a World Bank index) by 10%
4. reduce by 50% the number of procedures to register a small business in Kenyan cities, namely, Nairobi, Mombasa and Kisumu

The programme is also expected to contribute to a number of transformative reforms in the sector, including:
1. reformed regulatory environment at national and sub-national level, improving conditions for business and demonstrating how new County Governments can support local business
2. effective competition policies in sectors that also help the growth of small businesses and increase welfare of participating poor consumers who pay high prices for basic food stuff
3. conducive environment for PPPs, especially in infrastructure and export competitiveness

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

Outcome indicator	2015 Planned	2015 Actual	Extent met	2016 Target
Compliance cost savings to private sector (direct and indirect)	0	0	Met	0 / ($87m 2019)
Number of investment climate Doing Business reforms implemented at national (N) and county (C) levels (cumulative)	N:1 C:10	N: 3 C:0	Partly Met	N:4 C:11
Private sector investment generated ($m, cumulative)	0	0	Met	$30m / ($220m 2019)
Number of sectors showing improved performance	1	1	Met	4
Number of PSD champions created in government	M:0 F:0	M:0 F:0	Met	10
Increase in revenue generated from tax	0	0	Met	$10 million
Proportion of KEPSA’s financial sustainability target that is achieved (%)	0	0	Met	70%

There is still insufficient evidence as yet to comment with confidence on progress towards the Outcome targets, since it is too soon to see the anticipated change in the Outcome indicators. The theory of change was updated in 2015, but continues to require further evidence before adjustments to Outcomes can be made. However, in reviewing the key risks to the Outcomes identified and confirmed last year (see Risk section), it is clear that valid for the last AR to press for the development of coalitions for change to push for changes, including the enactment of laws (SEZ - approved and warehouse receipts - under review)) and the implementation of regulations (seeds - redrafted, PPP - well underway), reforms (Doing Business now significantly progressed), manufacturing action plans (now agreed) and business processes (Single Window – implemented and operational). Output 4, which facilitates the use of KEPSA and reform champions for such coalitions, made a significant contribution to the series of significant and impactful changes; through incorporating observations made in DFID’s Inclusive Growth Diagnostic that reforms can make faster headway if perceived to be in the firm interests of political elites. This is post-hoc evidence and justification for the approach of the programme and the core thinking of the DFID IGD on reform.

Current evidence on each of the Outcome indicators is as follows:
- Compliance cost savings: generated by regulatory reforms, competition policy, trade logistics and taxation; now generating some evidence of savings (see VfM section).
- Investment climate reforms: significant enhancement this year, 3rd best global Ease of Doing Business (EoDB) reformer.
- Private sector investment: generated by PPPs, agribusiness, renewable energy, SEZ and investment policy. Investment has already come in through the KU hostel PPP, with five others close to market. The target may be met if there is one further investor.
- Sector showing improved performance: achieving systemic change is difficult and takes time; the project should lead to these changes by 2019, but discussion about the parameters of the change to be expected should now take place.
- PSD champions: there is now evidence of the effect of these processes, and they should be underpinned.
- KEPSA’s financial sustainability: KEPSA’s target is to increase non-donor funding from 20% of its budget to 80%. This will require a change in culture which will take time. It may be too ambitious to have this as a target for 2016/17. KEPSA has assessed itself to have achieved 46% of this target, this will be analysed by the financial strategy development consultancy they have procured set to commence in May 2016. Further discussions between KEPSA and DFID on this target is necessary.

Overall output score and description
The output score is A+ ‘Outputs exceed expectation’. This is based on the following:
- Output 1: Reformed regulatory environment (A+): WBG have provided practical support to GoK in setting its agenda for improving Kenya’s Doing Business indicators, resulting in Kenya being cited as the 3rd top global reformer this year and significant uplift to 108 on the EoDB index.
- Output 2: Effective competition (A+): Transaction advisors finalized feasibility and transaction plans for six transactions; one transaction completed. Work with the Competition Commission generated two cartel enquiries and 11 submissions on anti-competitive practices. The Special Economic Zones Act 2015 was enacted.
- Output 3: Effective environment for public private partnerships (A+): Significant changes were made to legislation and policy, with a significant range of regulations and sector PPP plans finalised.
- Output 4: Strengthened demand and evidence base for investment climate reform (A): KEPSA capacity to manage its advocacy mandate was significantly enhanced, with sector and theme change plans and staff objectives reflecting these, and a revenue/charging strategy under development. The project’s investment climate diagnostics work performed well.

Key lessons
The most significant lesson for DFID is the confirmation from post-hoc evidence of the need for coalitions of reform champions to be supported to embed reform processes. This has provided justification for the approach of the programme and the core thinking laid out in the DFID IGD on reform, and further justifies the more intense and continual use of political economy e.g. forces for change and analysis. The use of KEPSA and latterly KAAA as animators for reform coalitions, made significant change contributions. Reforms can make faster headway if these techniques are deployed.

Key actions
- Overarching recommendation to develop a four year business environment reform plan to underpin dialogue on DFID economic development support priorities in the context of DFIDs new Economic Development Strategy; due in summer 2016.
- Revision of the logframe to include the 2016 Compliance cost savings indicator once the IFC MTR is concluded and methodology on the computation of this agreed.

Has the logframe been updated since the last review?
The Logframe was updated and approved in December 2015 as part of the 2015 AR recommendations to incorporate new work on business taxation and investment policy; addition of gender sensitive indicators and improvements in the capture of some of the project activities to make them realistic.
## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Reformed regulatory environment
Output number per LF		Output 1	Output Score	A
Risk:		Minor	Impact weighting (%):	30%
Risk revised since last AR?		Y/N	Impact weighting % revised since last AR?	Y/N

Indicator(s)	Milestones	Progress
1.1 Capacity score of the Doing Business Unit of MoIED	3	Achieved: 3 (refer to output text)
1.2 Number of web-based regulatory portals developed and fully transactional on Construction Permits (CP) Single Business Permits (BP),Investment Portals (IP) and e-citizen portal (e-CP)	CP:2 BP:2 IP:1	Achieved: / CP:2 BP:2 IP:1 e-CP:1
1.3 Number of county officers satisfactorily trained (disaggregated by gender)	85	Achieved: T:78 M:48 F:30 / Note that this does not account for training of the 5 County facing officers now also based in the national treasury PPP unit.
1.4 Number of reform memoranda drafted	0	Achieved : 0
1.5 Percentage of transactions of top 15 government agencies using the KNESWS for permit application	70	Achieved : 100
1.6 Number of policies recommended for improvement or elimination	0	Achieved: 1 / - An Investment Policy was drafted but due to institutional changes, undergoing redraft / - A detailed report on regulatory obstacles was prepared that has identified policies with recommendations for improvement.
1.7 Percentage of key counterparts reporting satisfied or very satisfied with BRICK assistance	70%	100% Wider counterpart testing took place in the World Bank project review process which is due to report in mid-April. Of those, the review reported all were satisfied, and the DFID team leader spoke to several counterparts, of which nearly all were satisfied or very satisfied, but often seeking more technical assistance beyond the available.

Key Points
Component 1: National regulatory reform. Progress against indicators: Kenya’s performance against EoDB indicators remained a significant priority for GoK, with the Ministry for Industrialisation and Enterprise Development (MoIED), now renamed Ministry of Industry, Investment and Trade (MoIIT) mandate to lead the agenda extended with additional resources brought on board from WBG. The 2014 Doing Business action plan endorsed by the Deputy President was implemented although the unit was understaffed at points in the year. The project team provided technical assistance to the Ease of Doing Business Unit (EDBU) and government technical working groups which resulted in Kenya moving up to position 108 from 134 and being publicly congratulated as the third-top global reformer in the (globally disseminated) Doing Business 2016 report. The official launch to disseminate the Doing Business 2016 report in Kenya was officiated by the Deputy President, six Cabinet Secretaries and the private sector. Sample specific reforms results were: Registering property was made easier due to improved electronic document management and the use of unified registration forms; the number of days it takes to register a property was reduced from 72 to 61 and the number of procedures needed to get electricity was reduced from six to four. In relation to starting a business, the number of days needed to stamp a memorandum was reduced from five days to one. Client satisfaction – MoIED: Although MoIED was ‘Satisfied’ with support from WBG and its quality, they continued to note an apparent lag in support due to main experts working on a number of other countries. The WBG disagree on this, it is possible the perceptions reflect the fact that WBG staff and consultants work using a remote management model rather than being embedded.
Other progress: The project team provided ongoing technical assistance to the National Payments Digitization Taskforce as it digitized and rolled out the e-citizen portal. Uptake of the portal has grown, with an additional 20 services now automated, including immigration, the National Transport and Safety Authority, and business registration. A renewed driving licence can be applied for and received electronically the same day. The portal now has 1.5 million registered users handling an average of 8,000 transactions daily.

Component 2: County regulatory reform
Progress against indicators: Mombasa and Kisumu: The programme conducted the Mombasa e-single business permit (e-SBP) and Kisumu e-construction permit (e-CP) systems’ user acceptance testing (UAT); obtained sign-off from the County governments; conducted media and business community reform sensitization workshops and officially launched these at public events hosted by the respective county Governors, private sector users and donors. Nyeri – the Nyeri e-SBP and investment promotion (IP) systems’ UAT were signed-off; and capacity building and strategy formulation workshops conducted for 12 IP unit officials.
Machakos and Kiambu - counties were re-engaged and work plans were developed for the Machakos IP portal and Kiambu e-CP system. Nairobi - after the county indicated its readiness to begin reform implementation, the project team re-started work on automating the planning system and upgrading the construction permit system; the delays experienced indicated some resistance to change.
Subnational Doing Business: The project team finalized the recruitment of coordinating entities to facilitate data collection in each of the selected indicator areas in the 11 selected counties. The questionnaires for data collection in the counties was prepared and launched by distributing questionnaires to both official and private sector contributors. Data has been gathered and collated but results are not yet analysed for public dissemination. Client satisfaction – County governments: The MTR consultants reported that both the county and national government offices were highly complementary of the engagement of the BRICK project assistance, citing inadequate IT systems as a challenge at both levels; compounded by multi-agency involvement at the national level and public awareness gaps at the county level.

Other progress: Embedding and sustaining this work requires engagement with the Council of Governors; this started in the latter part of the reporting period.

Component 3: Trade logistics
Progress against indicators: Implementation has begun for the last remaining modules relating to declaration of imports and exports. Of all the modules, these are the most complex because they comprise several customs regimes. The transit and export regimes are currently being tested and will likely go live in April 2016.The testing of the import regime (used for customs clearance of imported goods) is however behind schedule, because the integration of the Kenya Revenue Authority (KRA) and Kenya Trade Network Agency (KenTrade) systems has not been completed; mainly due to administrative delays in the implementation of a new Customs IT system at KRA (due to legal action, now concluded). However, KenTrade and KRA have agreed to begin testing and piloting the remaining customs regimes in March 2016, and to complete testing by June 2016.
Single Window - Previous delays have firmly been tackled following the government’s directive in July 2015 instructing the business community to use the Electronic Single Window (eSW) for import/export transactions. The eSW activity has increased substantially, with 12 agencies achieving 100% import and export permits’ processing through the system. The eSW usage statistics show that the processing of import declaration forms increased from 48,920 during the period Jan to June to 128,038 in July to December 2015, an increase of 162 percent; the number of manifests processed increased by 776 percent, from 117 to 1,025; and the number of import and export permits processed increased by 173 percent, from 74,961 to 204,668 During the same period payments collected by government agencies through the eSW’s e-payment system increased over 29 percent, from Ksh 267 million to Ksh 345 million. This is a clear indication that both the e-payment and eSW systems are now operational.
Component 4: Business Taxation
Progress against indicators: indicators are not in the logframe since this component has just started;
the project however progressed well during the reporting period . The project team provided capacity development in transfer pricing, underpinning developments in the extractives sector, and three draft laws were submitted to government for discussion: transfer pricing legislation, transfer pricing regulations, and advance pricing agreement legislation and related rules.

Summary of responses to issues raised in previous annual reviews
- Agreements were finalised to serve as frameworks in undertaking e planned county activities. The PCR and development of the next phase should reflect on effective ways scaling up this work , if appropriate.
- Clarify with the Registrar General’s Office whether business registration can be done at county level: DFID suggests the decentralisation of some services to cities that can serve sub-regions e.g. Mombasa, Kisumu and Nakuru.

Recommendations
- National regulatory reform: DFID to discuss with the WBG after the WBG KICP II MTR is published, to discuss focused national priorities for the next four year phase.
- County regulatory reform: DFID to visit Mombasa and one other pilot county to review the automated systems and how they have affected business.
- Trade logistics: DFID to ensure TMEA is aware and coordinate with IFC on the single window/KNESWS project.

Recommendations
In view of potential future programming that is under discussion, consider realistic targets to aim for over the next four years and articulate a roadmap from changes to business investment and performance, linking this to investment policy.

Output Title	Effective competition
Output number per LF		Output 2	Output Score	A+
Risk:		Moderate	Impact weighting (%):	30%
Risk revised since last AR?		Y/N	Impact weighting % revised since last AR?	Y/N

Indicator(s)	Milestones	Progress
2.1 Number of industrial sector action plans that meet quality criteria and are adopted by GoK (cumulative)	3	Achieved: 3 - A full Kenya Industrial Transformation Programme was also published (with McKinsey) with a series of advice notes
2.2 Number of short-term tourism initiatives completed (cumulative)	1	Achieved: 1 – / NB macroeconomic sector study is underway to measure the footprint and impact of tourism
2.3 Number of laws and regulations drafted to support agribusiness (cumulative)	2	Achieved : 3 - WRS redraft, Seeds redraft (EAC reg. compliance) Pyrethrum.
2.4 Number of farmers reached (disaggregated by Gender)	0	Achieved: T:2000 F:654 M:1,346
2.6 Number of laws and regulations drafted to increase market competition (cumulative)	5	4 - Engagement at the Competition Commission is strong; assistance on two cartel investigations and 11 separate submissions on competition, will lead to a further reforms.
2.7 Percentage of key counterparts reporting satisfied or very satisfied with BRICK assistance (MoIED, MoEAACT, MoA, CAK)	Satisfied	100% Satisfied.

Key Points
Component 5: Manufacturing, Tourism & Innovation
Progress against indicators:
GoK’s industrialisation roadmap was finalised and published with help from McKinsey Consultants alongside sector action plans and implementation roadmaps in 4 key sectors, and cross cutting advice notes on e.g. SEZ’s. The Industrial Transformation programme’ was launched publicly and presented to development partners; and from this several direct support requests were presented to Development Partners (DPs). With assistance from the DFID SITA programme, the Geneva ITC action plans were also developed for two sub sectors. The project has funded a macroeconomic study of the reach and contribution of tourism which is ongoing, in preparation of future sector development discussions .

Component 6: Agribusiness
Revised the draft Warehouse Receipt System (WRS) bill, which will now be deliberated by fisheries and private sector stakeholders; Facilitated a three-day workshop for members of the Departmental Committee on Agriculture, Livestock and Co-operatives; Conducted capacity building for WRS practitioners from parliament, national and county governments, and the private sector; Facilitated a WRS learning visit to India involving visits to the regulator, banks, WRS operators, collateral managers, and a commodities exchange; to promote WRS awareness (and thus future scale-up), partnered with the Media Council of Kenya to conduct a WRS development dialogue explaining the benefits of WRS (this was targeted at farmers, operators, financial institutions, insurance companies, traders, etc.); Concluded the WRS Impact study, which confirmed the proof of concept.
Facilitated value-chain prioritization, in partnership with KAAA (cotton/textiles, potatoes and horticulture emerged as the value chains of largest potential for Kenya); Developed the value-chain action plans to be implemented through the Kenya Agribusiness Public-Private Dialogue (PPD) Platform, and provided ongoing support toward the platform’s establishment; Reviewed the draft seed regulations; and Supported the harmonization of the draft seed regulations to align with EAC and COMESA standards.
Pyrethrum regulations were completed, a decision was however taken to discontinue working in the sector. Competition from Australia is seen as too significant to be overcome.
Component 7: Competition Policy
Working with the Competition Authority of Kenya (CAK), the project team developed and launched an independent report on dismantling regulatory barriers to competition. In response, the National Treasury committed to address the recommendations in the 2016 budget; a plan was drafted for the 2016 assistance to the Authority.
Other Detail: A report on legal advisory services for the preparation of a concurrency framework for competition law enforcement in the communications sector with the Communications Authority and CAK was prepared and submitted, and subsequently discussed. Technical assistance was provided to CAK on two major cartel investigations. The project team supported the Competition Authority of Kenya to develop the special compliance program, which aims to create a mechanism through which the Authority would receive submissions from business associations in the financial and agriculture sectors (thus providing relative anonymity and credibility) to identify actions that are likely to facilitate cartels. This was effective and a total of 11 submissions were received and analysed. Final recommendations on practices to be stopped will be published in 2016. A report on the ex-ante impact of Competition Authority of Kenya’s decision on investment and consumer savings was completed.
Comments on the draft leniency program were submitted to the Competition Authority of Kenya, and the project team commenced the public consultation on it and competition regulations.
Working with the authority the project team completed the assessment of the spectrum policy and provided recommendations to the Communications Authority on 4G spectrum allocation, and drafted the spectrum regulations in telecoms sector and provided training on competition in Telecoms to 57 participants, including operators, law firms, the officials from the Communications Authority and CAK . The project team submitted comments on the draft radiofrequency, interconnection, competition, licensing and dispute resolution regulations to the Communications Authority. The project team provided technical assistance to prevent the elimination of the Communication Authority’s power to control dominant telecom operators considered in the amendments of the ICT Act approved by the statute law (Miscellaneous Amendments Act).
Component 8: Investment Policy
The investment policy framework was drafted in mid 2015; the preparation however suffered from two institutional related changes - the preparation of the parastatal reform report late in 2014 and the reorganisation of several GoK Ministries in late 2015. These have caused uncertainty over the role of KenInvest and linked brand marketing bodies in tourism, trade and related areas. In early 2016 the decision was taken to place KenInvest under a new PS of Trade in the MoIED (now MoIIT) and the policy development cycle will now recommence. In the year, Oxford Intelligence undertook diagnostic research and produced a body of draft documents on the foreign direct investment environment, investor entry, incentives and retention. The Oxford Intelligence team subsequently presented their findings to senior government officials and Business Membership Organization staff, including the cabinet secretary, permanent secretary; senior staff from the Ministry of East African Affairs, Commerce and Tourism (MoEAACT); the National Investment Policy task force, and various private sector representatives. The project seconded a consultant embedded within the Kenya Investment Authority (KenInvest) to help draft the National Investment Policy and report on progress. Support was provided for Kenya’s flagship international investment conference (the Kenya International Investment Conference, or KIICO), leading on topics to do with the textile, apparel and leather subsectors. This involved establishing a public-private sector-focused investment support team, led by the Ministry of Industrialization and Enterprise Development and coordinated by KenInvest staff. The project also recruited support and coordinated the efforts of the (USAID) East African Trade and Investment Hub.

Summary of responses to issues raised in previous annual reviews (where relevant)
It was agreed in previous reviews not to scale up work on tourism. This is in the process of being reconsidered for future work under a broader marketing banner following a study analysing the macroeconomic reach and contribution of the sector which is underway.
Recommendations
Tourism may have capacity to alleviate poverty in remote and low income areas and regions in Kenya. A view should be taken on further support to the sector following the publication of the MTR. Engagement with non-state investors, travel agencies, charter and other flight market, and global market makers should be the determining driver. Public sector views should be determined at County level, not solely national.

None, or only extremely limited work, should continue on any Investment Policy related work. WBG should withdraw from this until a commitment is provided from the Presidency or Cabinet Secretary MoIIT to complete institutional reform on KenInvest and related bodies, and to empower KenInnvest to implement its remit.

Output Title	Effective environment for public private partnerships
Output number per LF		Output 3	Output Score	A+
Risk:		Moderate	Impact weighting (%):	30%
Risk revised since last AR?		Y/N	Impact weighting % revised since last AR?	Y/N

Indicator(s)	Milestones	Progress
3.1 Number of PPP regulations (R) and Fiscal Commitment and Contingent Liability (FCCL) frameworks (F) drafted through adequate consultation (cumulative)	R:2 F:1	Achieved: R:2 F:1 / National and County regulations drafted; and the County regulations and the FCCL approved.
3.2 Number of GoK officials satisfactorily trained in the PPP Unit (disaggregated by gender)	14	Achieved: 14; NB an additional several county facing officers recruited/commenced training in the latter part of the year.
3.3 Number of PPP transaction feasibility studies at national (N) and county (C) level completed and approved by PPP Committee	N:4 C:0	Achieved: N:4 C:0
3.4 Number of project concept notes for County PPPs finalized and approved by PPP committee	5	Achieved: 5 / - 60 EOIs drafted, 5 cleared by the PPP committee
3.5 Number of laws, regulations and e-portals drafted to support renewable energy (cumulative)	3	Achieved: 3 Energy Policy, Energy Bill, Net metering regulations
3.6 Number of laws (L), regulations (R), site feasibility reports (F), market demand reports (M), developer requests for proposals (D) and investment targeting strategies (I) drafted to support investments in SEZs (cumulative)	L:1 R:0 F:0 M:0 D:0 I:0	Achieved:L:1 R:0 F:0 M:0 D:0 I:0 / SEZ regulations
3.7 Capacity score of the SEZ Authority.	1	Achieved: 0 SEZ regulations were drafted and discussions commenced on the role of EPZ and/or SEZ authority.
3.8 Percentage of key counterparts reporting satisfied or very satisfied with BRICK assistance.	Satisfied	100% Satisfied. National PPP counterparts are very satisfied, county demand is very high. There is frustration at Treasury, for insisting on its fiscal authority over county PPP’s and forcing the pace to follow the regulatory framework.

Key Points
There are general challenges with bringing projects to close; with the county PPPs being slower paced than national PPPs hitherto.

Component 9: Public Private Partnerships (PPPs)
Following an extensive review, the transaction advisors finalized feasibility studies and PPP transaction plans for a first six transactions – four road and highway PPPs, the Nyali Bridge and Kisumu Port projects. For the four road-sector projects, this involved harmonizing various approaches to developing Kenya’s road network, such as technical standards and the tolling regime. Transaction advisors for university hostel PPPs for five universities commenced work in September 2015, and contract negotiations with transaction advisors for a geothermal electricity generation project are about to be finalized. The procurement process for transaction advisors for two multipurpose dam PPPs was agreed to be cancelled since the chance of attracting private sector financing was considered low and IFC is exploring other options for implementing these projects. The project finished a comprehensive assessment of public-private partnerships in Kenya (a World Bank study titled Realizing Public-Private Partnership Opportunities) and presented it to government decision makers in October 2015. PPP sector strategies for the road, rail, ports, airport, water, energy, health and education sectors, as well as for county PPPs, were developed then discussed with the relevant line ministries and contracting authorities. The process of updating and consolidating the project pipeline is still ongoing. The cabinet secretary for the National Treasury approved the guidelines for the Fiscal Commitment & Contingent Liability (FCCL) risk management framework in November 2015, the team submitted them to the attorney general’s office for endorsement and gazetting. Operational guidelines for a project facilitation fund were finalized in August 2015, approved by the cabinet secretary for the National Treasury in November 2015, and submitted to the attorney general’s office for endorsement and gazetting. The implementation of a modular PPP training program, targeting all stakeholders and contracting authorities, began in September 2015; approximately 120 government officials participated in the first three training modules. The Public-Private Partnership Unit, with IFPPP funding, recruited a communications firm to develop and implement a public awareness campaign on PPPs and, more specifically, on the government’s toll-road policy. Parliament’s enactment of the national PPP guidelines is still outstanding, and the county PPP guidelines are awaiting the attorney general’s endorsement for gazetting. The project team finalized a detailed PPP manual, and publication is imminent. Governments in the region (Ghana, Nigeria, for example) have indicated they consider Kenya to be well ahead in Africa on this path and in the case of Ghana have made a visit to review progress here.
Component 10: Renewable Energy
The team provided significant input to the drafting of primary and secondary energy legislation. The project completed the major outputs most likely to lead to enacted policies and legislation in the near future, including the drafting of at least three laws/policies, though only one of these laws has been passed thus far, with the others still pending parliamentary approvals (the energy policy and the energy bill), which are due in 2016; and the net metering regulation, which has already been adopted by parliament(Net metering regulations allow for the self-supply of electricity by residents and commercial establishments that often includes selling back excess power to the grid).
he project is also expected to contribute to policy making for mini-grids in response to the recommendations of the off-grid market assessment completed in September 2015.As part of this component, the project contributed to the upfront work needed under the World Bank Group's Scaling Solar Initiative, which with support from IFC advisory teams is expected to lead to the competitive tenders of some 50-100 megawatts of solar power. Under the project, the standardized request for qualification, request-for-proposal, implementation agreement and power purchase agreement documents were finalized. Outcome results were reported for the “number of recommended laws or regulations enacted or adopted” indicator, which was 1 rather than 3. Administrative procedures were improved by the online renewable energy portal which facilitated the accessibility of information to potential renewable energy investors in Kenya. These activities led to tea and sugar companies carrying out technical studies and expressing interest to invest in small hydro plant. Between the renewable energy portal’s launch in October 2013 and June 2015 the online facility reported 138,691 page views. The portal registered a total of 27,871 users from October 1, 2012 to June 16, 2015, and 33.7 percent returned to the website. From this it is evident that the portal has up-to-date and useful information that encourages previous users to return to check for current updates.

Component 11: Special Economic Zones (SEZs)
The SEZ Act, 2015, came into operation on 15 December 2015. The project team assisted GoK in drafting 11 related regulations to operationalize the Act: Kenya Designation Regulation; Kenya Registration and Licensing Regulation; Kenya Labour Regulation; Kenya Environmental Regulation; Kenya Land use Regulation; Kenya Administrative Regulation; Kenya SEZ Authority Regulation; Kenya Developer/Operator Regulation; Kenya Tax Regulation; Kenya Expatriate Entry Regulation and Kenya Dispute Resolution Regulation.

It also drafted the Administrative Procedures Order, which will guide the operations of the SEZ Authority once it is established; Participated in an investment promotion visit to Japan, including a seminar with leaders from more than 100 top Japanese companies; and Initiated the procurement of a firm to design the Kenya SEZ communications strategy.

Summary of responses to issues raised in previous annual reviews (where relevant)
It is clear there is still a political economy issue of a significant proportion around SEZs and Dongo Kundu in particular.

Recommendations
Japanese and Chinese investments should be complimentary in developing countries. Opportunities to create synergies should be explored quickly for the good of Kenyan industrial development. The WBG must play a role.

Continued support to PPP law and regulations will be beneficial in further enabling the PPP operational environment. A greater emphasis needs to be placed on getting projects to the financial market and market testing and getting to financial close.

Output Title	Strengthened demand and evidence base for investment climate reform
Output number per LF		Output 4	Output Score	A
Risk:		Minor	Impact weighting (%):	10%
Risk revised since last AR?		Y/N	Impact weighting % revised since last AR?	Y/N

Indicator(s)	Milestones	Progress
4.1 Number of GoK officials satisfactorily trained on private sector development (disaggregated by gender)	0	Achieved: M:0 F:0
4.2 Extent that a Change Management Plan is drafted and implemented to help make KEPSA 'fit for purpose'	Plan approved by KEPSA Board & at least 50% implemented	Part Achieved - a development plan was approved by the KEPSA Board in 2015. Implementation is underway, and action plans for all departments are scheduled to be completed in May.
4.3 Number of BRICK components for which private sector inputs have been received through adequate consultation	7	Achieved: 7
4.4 Number of Investment Climate reports produced (P), formally launched (L) and rated as Satisfactory on average by targeted GoK agencies (S)	P:7 L:4 S:4	Achieved: P:7 L:5 S:4

Key Points
KEPSA continue to lead and proactively manage Public and Private Dialogue efforts in strengthening the demand for reforms.

Component 12: Private Sector Development (PSD) Champions
During the review period, the reform champion’s programme was in abeyance pending evidence of reform progress. This has now been evidenced and consideration is being given to the more comprehensive approach to champions.

Component 13: KEPSA (and KAAA)
KEPSA made a significant early start in the reform process and over the last year has made a significant leap forward in capability and reach, hosting two Presidential RTs and a DP RT among numerous other events at which investment policy challenges have been debated, actions agreed, prioritised and acceded to by the President, Deputy President, CS’s and other senior GoK officers publicly. There is evidence of action. On corruption For example, there were 186 court cases for corruption by December 2015, whilst there had been none a year before. Operationally, progress is demonstrated by the recruitment and start of an effective Deputy CEO in an exemplary process, other top recruitments were finalised in 2015, and the increased capability of the new senior management team, demonstrated in competent management of business in the month long absence of the CEO early in 2016. DFID is also supporting economist posts via the WBG to enable top quality economic analysis to be driven by members.
KEPSA has not yet made enough headway in sufficiently sustaining and increasing the fiscal independence from donor funding that is essential for a top, national, mature, BINGO, globally benchmarked, as it was identified in the 2014 strategy, against for example the UK CBI, and the Singapore Chamber. This will be underpinned in 2016 by a focused revenue strategy development and implementation consultancy; this is essential because it will support KEPSA efforts to engage the Presidency and Government, Parliament and others and underpins championing of reforms that the WBG and the business community prioritises.
In parallel a significant effort has been made to engage and build the capacity of KAAA specifically on agroprocessing investment and export. This is essential to develop a PPD platform on agribusiness. With the support of the WBG, the project has facilitated value-chain prioritization in partnership with KAAA (cotton/textiles, potatoes and horticulture emerged as the value chains of largest potential for Kenya); and developed the value-chain action plans to be implemented through the Kenya Agribusiness Public-Private Dialogue (PPD) Platform, and provided ongoing support toward the platform’s establishment.

Component 14: Investment Climate Diagnostics
A single integrated review report on diagnostics was prepared which identified a series of significant obstacles to a much improved investment climate and included policies and recommendations for change. A number of individual policy reform reports were prepared in the year including: the overarching Regulatory obstacles/impacts to competition; Textile and Apparel; Leather and leather products and Furniture. The results of the Informality study and Manufacturing competitiveness study that were undertaken previously were carried forward into the project work with counterparts.

Summary of responses to issues raised in previous annual reviews (where relevant)

Include a capacity building component across the programme which was done in the form of the PSD Champions component. GoK has also made a formal request for capacity building support through the Trade and Private Sector Donor Group (TPSG), currently under review.

Recommendations
- Close working between the WBG, MoIED and TPSDG to guide the proper articulation and implementation of action plans stemming value chain strategies in support of the Government’s Industrial Transformation programme.
- Continued private sector participation in the relevant reforms capable of improving the business environment and leading to increased economic growth through the various PPD platforms KEPSA and KAAA lead on.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance
The composition of the IFC costs is identical to the cost analysis in the 2015 AR: consultants 35%; staff 34%; travel 13%; and administrative fees and expenses 9%. The current breakdown of the budget by the different programme components is as follows: county regulatory reform 12%; PPPs 13%; agribusiness 10%; trade logistics 10%; manufacturing, tourism and innovation 11%; SEZs 4%; KEPSA 10%; KAAA 1%; PSD champions 3%; business taxation 2%; investment policy 6%; competition policy 6%; renewable energy 5%; national regulatory reform 4%; investment diagnostics 1% investment diagnostics 1% and 1% unallocated.

The WBG is following a number of good practices that demonstrate their effectiveness. Firstly, wherever possible they require GoK contributions as a sign of commitment to ensure sustainability. For instance, for process automations, they have required equipment and personnel inputs from the Counties before committing any support and have only provided assistance to GoK agencies that have demonstrated sufficient demand for assistance. Secondly, they have been proactive in engaging parliamentary committees in expediting the recent passing of the SEZ and Warehouse Receipts Bills.

We currently lack information on the IFC practices to promote Efficiency; this will be captured in the KICP II MTR report currently underway.

VfM performance compared to the original VfM proposition in the business case
The VfM indicators that can be applied to the programme are the following:
- Economy: one of the WBG’s biggest inputs is consultants, and so benchmarking of their consultancy fees would be appropriate. Their commercial rules preclude them from sharing with DFID the actual fees they are paying. In 2015, they preliminarily agreed to share their fee bands, although this has not been possible. This lack of transparency remains a cause for concern, with DFID unable to fully assess the value for money of the programme.
- Efficiency: WBG are charging a 5% trust fund administration fee, which is in line with DFID guidance. The budget agreed in the DFID-IFC MoU charges 10.5% of each component to programme management and supervision. However, WBG have to date not been willing to report on what this has been spent on, and so it is not possible to benchmark BRICK’s administrative costs against other projects. As above, this poses a risk in terms of being unable to fully assess the value for money of the programme.
- Cost effectiveness: two measures may be used here:
  - Cost per compliance cost savings: the planned DFID-funded ‘Value for Money in Investment Climate Report’ by IFC can be used to compare the regulatory reform, competition policy and trade logistics components, since planned compliance cost savings have been estimated for each, and actual savings will be gathered.
  - Investment leverage ratio: the ratio of donor funding to private investment generated. This can be used to compare the PPP, renewable energy and SEZ components, since planned investment generated has been estimated for each, and actual investment generated will be gathered.
- Economic return: for some components, cost benefit analysis can be conducted. These are:
  - Trade logistics: there have been recent changes in the methodology used in the analysis of the Doing Business Reports for measuring time to import and export as well as the documents used in import and export of cargo; hence there is no comparable data to be used in measuring the impact of the trade logistics component. The IFC team is exploring a set of new indicators for which baseline data is available or can be collected to apply in the analysis. Structural changes have also been experienced by KenInvest, the most recent being the move to MoIED which has presented the agency with both operational changes and uncertainties.
  - Competition policy: The Competition Authority estimated that the removal of restrictive product market regulations in Kenya’s service sectors such as professional services and electricity would result in an increase of GDP growth by at least 0.39 percentage points (equivalent to US$218 million in the first year) compared to a situation with no reforms. The Competition Authority estimated the following impacts of a number of their recent decisions (this is not an exhaustive list); Price fixing in insurance (decision in April 2015): Annual public sector savings of Ksh 100 million (US$ 1.0 million); Price fixing in supermarket retail (July 2014): annual consumer savings of $2m; Advocacy action in agribusiness (June 2013): Increased incomes to green leaf tea farmers of $0.7m per annum. While full attribution of results to the BRICK programme is unlikely (the initial complaint to CAK was in October 2012, prior to the commencement of BRICK), even if a small proportion of the above savings are attributable, this would still represent a high return, given that the costs of this component is only $1m..
  - Warehouse Receipts and County regulatory reform: the baseline report launched in November 2015 could inform the cost-benefit analysis for the agribusiness component.

Assessment of whether the programme continues to represent value for money

The project is likely to continue representing value for money but needs further analysis:
- Results: The programme is on track with the delivery of outputs, with the project scoring an average ‘A’ score in this AR. Progress against its Outcomes is harder to judge and will require greater attention to the political economy. A number of programmes saw delays in their implementation due to an initial failure to understand the barriers to, and drivers of change as well as reluctance from local agencies to implement reform. While most of these issues have now been overcome, including identifying more suitable change agents where initial reluctance to reform was encountered, this has resulted in a delay to the delivery of outcomes.
- Costs: remain on track (see Financial management below).
- Risks: remain Moderate (see Risks below).
- Theory of Change: this needs to be further analysed to check its validity (see M&E below).
- VfM practices: these appear good for Economy and Effectiveness, but it would be good to learn more about how WBG are promoting Efficiency.
- VfM measures: As reported in the 2015 AR, the full analysis of this is yet to be done, but initial evidence emerging (such as on consumer savings from the Competition Policy component) suggests the potential for very high returns.

Quality of financial management
The delivery of the project is on track. £11.8M of the project funds have been spent to date, representing 77% of the project value. The balance, £3.5M is projected to be spent by December 2016; ahead of the project closure in March 2017. IFC’s spending has been good, but could be improved. We continue to work closely with IFC to promptly obtain spending updates and address any difficulties envisaged. KEPSA procured and installed a new finance system, following a due diligence recommendation by DFID. The system has resulted in financial monitoring improvements, leading to better and clearer reporting by KEPSA to DFID.  The KEPSA component continues to show a high absorption rate, as DFID continues its support. DFID assesses KEPSA as having adequate and capable finance staff, able to deliver the level of support and reporting required. At the point of the Annual review, KEPSA had just gone through an institutional audit and the outcome of the audit was not yet available. DFID recommends that KEPSA provides details of the Management Letter and the audit report immediately the audit is finalised. DFID channels KAAA funding through KEPSA; which is a financial risk mitigation arrangement. A recent spot check on KAAA recommended the recruitment of an auditor to discharge financial assurance functions in compliance with the statutes. DFID also reviewed KAAA’s financial reports; they reflected under-budgeting signalling further fund requirements for KAAA in the future. DFID, working with KEPSA, should urgently review the sustainability of KAAA’s funding and the factors driving the under budgeting issues raised.

Date of last narrative financial report	8 March 2016
Date of last audited annual statement	15 May 2015

Recommendation
- KEPSA to share with DFID the Management Letter and the audit report as soon as the audit is finalised.
- DFID to review the sustainability of KAAA funding and factors driving under budgeting issues raised

E: RISK (½ page)

Overall risk rating: Moderate

Overview of programme risk
The current version of the BRICK live risk matrix is attached in the Annexes. The key risks to achieving the Outcomes are given as follows:
- Political support and reform champions: GoK commitment to improving the business environment continues to rise, providing an opportunity to assist Kenya to address some of the key constraints quickly if we are opportunistic. WBG and DFID should continue to be more politically savvy to ensure this support, building coalitions of change that includes not just the private sector facilitated by KEPSA, but also sections of the political and business elite, whose interests are potentially aligned, and the media and general public.
- The selection of PPP projects for political and not technical reasons remains a risk; close working between the WBG, PPP unit, procuring government departments and the private sector would help to minimise this. Also, the quality of county proposals is still of concern and a lot of capacity building may be required.

The key programme-level risks to achieving the Outputs are as follows:
- Election campaigns: this has the potential of delaying most projects with GoK; continuous environmental scanning, political economy discussions between the WBG, DFID and other donors; and appropriate project adjustments when needed would help to mitigate against this.
- Poor coordination between components: with such a large number of components across two organisations, the risk of missing potential synergies continues to exist. Having a shared high-level Theory of Change that shows how all the components are linked may help in tackling this risk (see M&E section).
- Fraud & corruption: this remains minor; proper checks and balances including audit, due diligence assessments and spot checks have been built into the programme’s management to mitigate risks.

The key risks to each individual Output are covered under the Issues for each Output above.
In order to be useful for project management, the risks should be based on explicit analysis of progress towards Output and Outcome targets.

Outstanding actions from risk assessment
- The adoption of quarterly management meetings between DFID and WBG to review management issues, risks and results, stakeholder engagement (including GoK) and any other issues pertinent to the delivery of the programme.
- DFID to meet with component leads to explicitly review risks to non-achievement of Output milestones for 2016.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
The delivery of the project is on track. £11.8M of the project funds have been spent to date, representing 77% of the project value. The balance, £3.5M is projected to be spent by December 2016; ahead of the project closure in March 2017. There is however room to improve the implementing partner absorption rates/financial forecasting by ensuring they apply realism in activity signalling; recognising their environmental delivery challenges, especially those whose delivery is dependent on traditionally bureaucratic government systems.

Performance of partnership (s)

The WBG has strong working relationships with counterparts, largely GoK, and continue to attract unprecedented demand levels from GoK, especially on the recently launched Industrial Transformation Program aimed at stimulating Kenya’s industrial sector. Counterparts are generally satisfied with the WBG TA support, timeliness is however occasionally cited as an issue resulting from WBG procurement processes and staff serving multiple countries and programmes. Staffing issues were raised in the 2015 AR, discussions have since taken place and actions agreed between DFID and WBG on how to improve this.

KEPSA concluded its balanced scorecard development process which involved its entire staff and helped in aligning general departmental and staff performance goals to the organisation’s business strategy. KEPSA has recently procured a consultant to help in the development and successful implementation of a revenue generation strategy to aid it in achieving financial sustainability as DFID prepares to exit its support to core expenditure lines; the consultancy starts in May 2016. DFID is supporting the Kenya Agribusiness and Agro Industry Alliance (KAAA) via KEPSA to establish its secretariat and develop revenue generation strategies aimed at financial independence. These partnership and engagement bodies are essential for the sustainability of the wider goals of the programme, underpinning the relationship nexus between the business investment cycle, policy cycle, the political cycle, and political economy for the reform process.

Asset monitoring and control
Asset monitoring and control within the project is governed by the respective DFID MoUs with IFC and KEPSA; and between KEPSA and KAAA. KAAA and KEPSA have filed their asset registers with DFID and incorporate reporting on any changes in their respective project reporting.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

The delivery of BRICK programme results is not through government systems and hence DFID Kenya judged that the PPs did not apply in the detailed management and monitoring of this programme.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation
The programme’s log frame was updated in December 2015 as follows;

Various pieces of research have either been commissioned by WBG or are about to be:
- Agribusiness: a study on the effects of a warehouse receipts system on farmers’ incomes – baseline report was launched and disseminated.
- Business registration: a study on the effects of changing business registration rules on job creation.
- Trade logistics: a study baselining the cargo clearance process at the Port and does a cost-benefit analysis of the Single Window.
- Competition policy: A report on the economic impact of recent CAK reforms was launched.

There is a significant lag to the Outcome results, with WBG citing many of them occurring in 2019 despite the project finishing in March 2017. As mentioned in the 2015 AR, there is a strong case for a follow-up study of the project around 2018. Plans for this could be made now as part of a review of the Wealth Creation portfolio. The July-December 2015 KICP II project progress report mentions a reduction in the number of days it takes to register a property from 72 to 61, the number of procedures needed to get electricity from 6 to 4 and the number of days needed to stamp a memorandum (to start a business) from 5 to 1.

Monitoring progress throughout the review period
Nearly all of the indicators in DFID’s revised logframe are taken from WBG’s results framework; to minimise transaction costs and maximise accountability. The 2015 AR recommended a change in the timing of DFID Annual Reviews from March to September; this was however not effected due to the delay in conducting the KICP II MTR which was to provide an independent judgement on the project’s performance.

The six monthly Progress Reports on the project produced by the IFC donor coordination team provide a summary of what has been achieved, the issues and next steps. However, the timing of their availability remains to be a concern as it reduces on its usefulness in tracking results.

Recommendations
- WBG and DFID to review ToC diagrams.
- Make plans for a follow-up study on the project outcomes around 2018.