Project Completion Review - Top Sheet

This Top Sheet captures the headlines on the programme performances performance over the course of its lifetime. Teams should attach summary sheets from each annual review over the life of the programme.

Review Date:	August 2016

Title: / Maternal and Neonatal Health Human Resource Capacity Building
Programme Code: / Aries 202945	Start Date: 1/1/12	End Date: 31/5/16 ( no cost extension)

Summary of Programme Performance

Year	Jan 13	Jan 14	Jan 15	Jan 16	Aug 16
Programme Score	A	A+	A+	A	A+
Risk Rating	Low	Low	Low	Low	Low

Financial Position

Original Programme Value	£15,862,730
Extensions/ amendments	October 2015: Approved no cost extension from 31/12/15 to 31/5/16
Log-frame revisions (with dates)	Revised log frame: / January 2013- Developed an overall logframe combining information for all 11 target countries ( and a separate one for each country) / January 2015- Updated outcome and output indicators as per agreed DFID AR 2014 recommendations / December 2015 - Updated outcome and output indicators as per agreed DFID AR 2015 recommendations to reflect changes in the environment during implementation and practical considerations around data collection and availability.
Total programme spend	DFID Head Office £ £15,862,751

Follow up actions suggested for LSTM and partners following closure
The LSTM team has worked hard with local partners to ensure sustainability of this programme. So far, 6 out of the 11 countries have secured ongoing funding (Kenya, Malawi, South Africa, Nigeria, Tanzania and India) for all or part of the work (see full table in output 1). Kenya and South Africa have funds in place for national coverage of the model.

In addition, the following actions could be considered:

- LSTM to continue marketing and expanding the MiH training package in a franchising model.
- LSTM to continue advocacy to local and international partners to encourage uptake and adoption of this model of emergency obstetric and neonatal care training as national policy.
- All partners to advocate for an Internationally agreed classification system for stillbirths.
- LSTM to ensure local mechanisms are in place to verify that training quality assurance is ongoing
- All partners to consider continuing and expanding this model of UK volunteers delivering high quality and cost effective training. There is a need for a global coordinating centre to carry out this work.
- All partners to advocate for regular patient satisfaction monitoring.
- All partners to consider introducing near miss audits as well as maternal death audits. Perinatal death audits have been successful in South Africa as they measure stillbirths as well as neonatal deaths and could be considered in other settings.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-202945/documents
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-202945/documents

Outline of programme and what it has achieved

Context
The ‘Making it Happen’ (MiH) programme aims to reduce maternal and newborn mortality and morbidity by improving the quality of maternal care provided. The programme achieved this primarily by providing training in emergency obstetric and neonatal care (EmONC) to teams of health workers attending deliveries in health facilities.

The programme comprised three intervention packages:
1) Delivering a ‘skills and drills’ emergency obstetric and neonatal care (EmONC) training package that comprised 1) a short (max 3-5 days) multi-disciplinary training (nurses, midwives, doctors and specialists train as a team); 2) training of critical numbers (80% or more) of health care workers providing maternity care in or close to health care facilities; and 3) using expert UK volunteers to build in-country capacity. The emphasis was on developing confidence and skills in appropriately identifying and managing maternal and neonatal emergencies through hand-on training.

2) In phase 2: Strengthening data collection and use. Developing a data workshop package (1 day) that helped health care providers to better collect, understand and use routine data on maternal and newborn healthcare provision and health outcomes (in all countries except India and South Africa. India’s MiH was a different model to the others and South Africa had its own data collection system in place).

3) In phase 2: Strengthening quality improvement methodology. Developing and delivering a comprehensive workshop package (2 workshops, three days each) to strengthen quality improvement methodologies (maternal and perinatal death audit and standards based audit) at health care facility level (implemented in 4 countries - Malawi, Kenya, Zimbabwe and Sierra Leone).

In its first phase (2009-12), the MiH programme operated in 5 countries (Kenya, Zimbabwe, Sierra Leone, India and Bangladesh). The programme applied evidence-based training, using proven adult education techniques, together with improved mentoring/supervision and data management. The results showed improved technical knowledge and skills among trainees, positive effects in terms of effective medical and midwifery team work and improved care of uncomplicated and complicated births.

Following this success, all 5 participating countries requested a scale-up of MiH. An additional 6 countries (South Africa, Malawi, Pakistan, Ghana, Nigeria, and Tanzania) declared their interest in and were selected to develop MiH within their own contexts. Additional support to supervision and mentoring was not part of Phase 2 due to the increased costs, no clear evidence that it improved outcomes in Phase 1 and the difficulties of measuring the impact.

MiH Phase 2 has been delivered in 11 countries: eight in Sub-Saharan Africa (Kenya, Tanzania, Malawi, Zimbabwe, Republic of South Africa, Sierra Leone, Ghana and Nigeria) and three in Asia (India, Bangladesh and Pakistan). At the request of the Government of India, MiH there has focused on the development of a new RMNCH curriculum and training methodology and the setting up of 5 central national ‘Centre of Excellence’ skills labs which will serve as training sites for State level roll-out.

The UK provided up to £15.8 million over 4.5 years from January 2012 to May 2016 for this programme (no-cost extension approved in October 2015). The Centre for Maternal and Newborn Health (CMNH) at the Liverpool School of Tropical Medicine (LSTM) serves as the global coordinating centre for MiH but works in close partnership with the Ministries of Health, UN technical agencies and professional organisations in all countries.

Expected Results:

In its entirety the project was expected to produce the following results:
•	9,586 maternal lives saved
•	191,720 maternal disabilities avoided
•	10,490 newborn lives saved
•	12,690 stillbirths averted.

Furthermore they expected to build capacity locally by training over 17,000 healthcare workers in EmONC and 1,025 national ‘Master Trainers’ who are able to continue providing training beyond the programme. Facilities are split into those that deliver Comprehensive EmONC (CEmONC) and those that deliver Basic EmONC[1] (BEmONC). CEmONC facilities tend to be at a higer level but also see more complicated cases and sicker women in general.
[1] Emergency Obstetric and Newborn Care (EmONC) includes two levels 1) Basic EmONC with 7 signal functions (parenteral antibiotics, oxytocics and anti-convulsants; manual removal of a retained placenta; removal of retained products of conception (e.g.by manual vacuum aspiration (MVA)); assisted vaginal delivery (AVD- ventouse delivery) and neonatal resuscitation with bag and mask, and, 2) Comprehensive EmONC with 9 signal functions – all 7 above, plus, blood transfusion and Caesarean Section.

The overarching aim was to reduce maternal and neonatal mortality and morbidity within individual countries and working towards achieving Millennium Development Goals (MDG) 4 and 5.

Key Achievements:

Increased capacity of healthcare providers to provide Emergency Obstetric and Newborn Care:

- 18,598 healthcare providers trained in EmONC with 83.7% of healthcare providers demonstrating improved knowledge and 99.2% improved skills
- 1,681 Master Trainers available; 20 Skills labs and 274 training rooms equipped.
- The efficient use of highly qualified UK volunteers was a successful model.

Increased availability of EmONC:

307 healthcare facilities were followed up quarterly (155 designated to provide Comprehensive EmONC and 152 Basic EmONC).
- 69% of healthcare facilities increased the availability of EmONC by 12 months after the MiH Programme started and there was a 123% increase in healthcare facilities able to provide all the required components (signal functions) of EmONC
- Assisted vaginal delivery (ventouse/vacuum delivery – AVD) was only available in 48% of healthcare facilities at the start of the programme and increased to 69%. This result is particularly hard to achieve as instrumental deliveries are a difficult skill to obtain.
- Neonatal resuscitation was available at 87% of healthcare facilities and increased to 98% by 12 months.
- At BEmONC level ‘hard to achieve’ signal functions; assisted vaginal delivery (AVD) increased from 28% to 52% and manual vacuum aspiration for retained products of conception (MVA) increased from 54% to 69% illustrating that it is possible for BEmONC designated health care facilities to provide all 7 signal functions.

Increased accountability for results and quality of care (Zimbabwe, Sierra Leone and Malawi)
- 84 healthcare facilities were followed up quarterly (42 designated to provide Comprehensive EmONC and 42 Basic EmONC)
- 1,487 healthcare providers trained to better collect and use data
- 665 healthcare providers completed the Quality Improvement workshops and worked together to improve maternal and perinatal death audit (review) at their healthcare facility and to introduce standards-based audit.

100% of health care facilties had conducted maternal death audit and perinatal audit and standards-based audit in last 6 months; 81% of healthcare facilities reviewed 80% or more of maternal deaths by 6 months and all participating health care facilities had evidence of action taken as a result of undertaking audit.
Mothers and newborns lives were saved – changing the lives of women and girls
- The programme was focused on services for women and girls and, by increasing access to safe delivery, will have transformed the lives of many.
- Across 963 healthcare facilities in the MiH implementation countries, during the life-time of the programme:

  - 273,510 more women attended for delivery at a healthcare facility and 16,946 more women were recognised to need and received emergency obstetric care.
  - An estimated 6,763 stillbirths were avoided, 1,452 mothers’ lives saved and 4,946 newborn lives were saved i.e. 13,161 lives saved in total.

The numbers of lives saved is much lower than those stated in the business case but is consistent with predictions made by the MiH team throughout phase 2. The business case modelling was based on the Phase 1 of the programme that was only in 5 countries and was very intensive – this model was not exactly repeated in Phase 2 in actual implementation. In addition, some of the countries included in the business case analysis implemented vastly different models e.g. at the request of the government, India set up centres of excellence skills labs in the end and did not implement the more ‘classic’ MIH model. Due to the high population, the initial business case had a large contribution of lives saved predicted from India which did therefore not materialise.

The business case modelling was, however, based on a predicted 25% reduction in maternal case fatatlity rates, which was met in 9 out of 10 countries where this was measured (see outcomes section).

Lives saved estimations are also complicated as women in this progamme received EmONC early and therefore did not even become obstetric near misses in terms of death and therefore may not have featured as a ‘life saved’. Similarly, the babies of these women were also saved as, if their mothers had died, the babies would have died in the majority of cases.

Given all the above, the original projections were overestimations and the programme did achieve the predicted reductions in case fatality rate in most countries.

Lasting and sustained impact on the local health workforce training
300 UK volunteers provided the initial training in countries but this was gradually replaced by local master trainers. Currently all 11 countries are able to provide the course ( 3 countries fully independently and the remaining 8 requiring only quality assurance oversight from LSTM)

Key Challenges:

Strengthening maternity services within exiting health system challenges
MiH was a targeted intervention to improve maternity care by training healthcare workers but had limited available funds to improve equipment and supply availability and quality within facilities. Greater collaboration with local and international partners to ensure a co-ordinated, holistic improvement in maternity services would have maximised the benefits of this programme.

Demand side factors; the impact of wider influences on women’s’ choice of birthplace
The MiH targeted health facilities and increased women’s confidence in delivering at these facilities but the programme had only a limited influence on birthplace choices. There could have been greater coordination with local partners to tackle social, physical and economic barriers to accessing maternity healthcare. This would also have ensured that those hardest to reach also benefited from the interventions and that no one was left behind.

Health workforce capacity issues
High turnover of staff in certain areas has meant that training courses are needed more regularly. and an effort to quantify the minimal percentage of staff that should be skilled up in EmONC was recognised. Even more engagement with ministries of health and other policy makers is needed to avoid turnover of trained staff and to ensure facilities have adequate numbers of members trained in EmONC.

Data collection and monitoring systems
Interim analysis has shown that data on neonatal death before discharge is not routinely collected at health facility level and stillbirths even less so. The sample size for this and the reliability of data to monitor this indicator is thus inadequate. Proxy indicators and alternative methods to capture the data were therefore created.

Start Up Time
Starting up took much longer than expected with long negotiations with governments and other stakeholders. This was particularly the case in India. The results in terms of ownership and sustainability have paid off.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Overall Outcome Assessment :
A – outcomes met expectations. Although not all outcomes were fully achieved, the reduction in case fatatlity rates and the other achievements are significant, deserving the A score. Of particular note is that case fatality reduced to zero in BEmONC facilities and reduced by the taerget 25% in 9 out of 10 countries.

Indicator	Target	Achievement and explanation
Outcome Indicator 1: Number of women attending at participating health facility for delivery	Increased by an average of 15% at 6 months and 20% at 12 months after commencement of interventions, compared to baseline, across all target health care facilities.	Partially achieved / Increased in 6 out of 9 countries – (not assessed in RSA and India) / Observed increases were higher at BEmONC level (21.3% increases at 6 and 20.7% at 12 months) than at CEmONC level (15.2% at 6 and 11.2% at 12 months). / The increase was highest in countries where overall % SBA was lowest (Bangladesh overall 15.5% increase with a 44% SBA coverage in 2015 and Pakistan 14.5% increase with a 52% SBA in 2015) and lowest where overall % SBA coverage already high (Malawi overall increase of 4.7% with SBA coverage at 87% in 2015). Similarly in Zimbabwe - the MiH target health care were the 5 largest in Zimbabwe (tertiary and secondary level) with no change in number of women attending ( 0.1% increase). / In Sierra Leone the Ebola epidemic led to an overall decrease of 12.6% in women attending for delivery at target healthcare facilities. / In Nigeria a 3.5% decrease was noted which is less than the overall country decrease in SBA between 2012 and 2015 of 8.0%.
Outcome Indicator 2: Maternal Case Fatality Rate for direct obstetric complications (CFR)	Reduced by an average of 25% in participating health care facilities, at 12 months	Achieved / Overall the target of 25% reduction in CFR was met in 9 out of 10 countries at CEmONC or BEmONC level (not assessed in India, reduction in RSA was 13.3% assessed as MMR) – the highest reduction (100%) was seen at BEmONC level in 7 out of 9 countries with no maternal deaths at 6 or 12 months compared to baseline – this was most likely as a result of better recognition, management and referral to a higher level facility when needed. / The mean decrease in CFR overall was 25.7% (from 2.26 to 1.68 – includes RSA). At CEmONC level the CFR decreased by 36.3% (from 2.79 to 1.78; excludes RSA where assessed as aggregate only) and at BEmONC level the decrease was 70.4% (from 3.24 to 0.96; excludes RSA where assessed as aggregate only). The three most frequent complications were obstetric haemorrhage, eclampsia and sepsis; the recognition and management of which is part of the EmONC training.
Outcome Indicator 3: Facility level stillbirth rate	Reduced by an average of 10% in participating health care facilities, at 12 months after commencement of interventions, compared to baseline. (target revised from 15% previously)	Partially achieved / Stillbirth rates were reduced in 10 out of 10 countries with a mean reduction of 6.2%. (not assessed in India) / Reduction was greater at CEmONC level (7.0%) than at BEmONC level (2.4%). However SB rates remain generally higher at CEmONC level (35.9 per 1000 births) compared to BEmONC level (14.3 per 1000 births) at 12 months post interventions. / A 10% or greater reduction was observed at CEmONC level in Malawi (22.1% reduction), Nigeria (13.5% reduction), Sierra Leone (22.4% reduction) and at BEmONC level in Bangladesh (18,2% reduction),Ghana (21.9% reduction),Nigeria (13.8% reduction) and Sierra Leone (19.1% reduction).
Outcome Indicator 4: Facility level newborn death before discharge rate.	Reduce by an average of 15% in participating health care facilities, at 12 months after commencement of interventions, compared to baseline	Not achieved / The newborn death before discharge rate (per 1000 births) is higher in CEmONC level healthcare facilities (17.5/1000) compared to BEmONC level facilities (2.5/1000). At 12 months there was an overall reduction of 10.0% across 307 heath care facilities for which data was obtained (compared to 3/12 at which data collection was commenced) / As the information on newborn deaths is not readily available in registers. this indicator was developed for the first time by the MiH programme by subtracting live births from numbers of babies discharged alive (which itself is burdened with recording issues), and is methodologically volatile (e.g. it does not take into account referrals). A proxy indicator (output 1.5) related to babies admitted for asphyxia was created in absence of reliable data on neonatal death rates.

Output Score and Description
The overall output Score was A- the project met expectations
A  Output 1: Increased healthcare provider capacity to provide EmONC
A  Output 2: Increased availability of EmONC for mothers and babies
A  Output 3: Strengthened accountability for results with increased transparency
A+  Output 4: Strengthened capacity to sustain improvements in MNH service delivery
A++  Output 5: Evidence generated by programme disseminated in order to inform national, regional and global agendas

Lessons Learnt
Using volunteer health care professionals from the UK is highly cost-effective and, with coordinated centralised support, results in demonstrable benefits for both the recipient countries and the volunteers and their working environment back in the UK. This model can be marketed as a ‘franchise’ training – LSTM has already had some success with this approach in Sri Lanka.

Sustainable gains are made if there is a strong partnership with and commitment from the Ministry of Health and where there is regular feedback by the programme to a steering group led by the respective government departments.

The outcome and output indicators developed for MiH Phase 2 (11 countries) were largely based on those obtained during Phase 1 (4 countries). With scale up and with countries moving to a quality assurance model and less external expertise there has been some dilution of effect.

The MiH programme shows that short ‘skills and drills’ EmONC training significantly improves skills and knowledge among all cadres designated as skilled birth attendants in all MiH countries.

The MiH model of training multidisciplinary teams of healthcare providers working in the maternity areas together (as opposed to individuals and individual cadres separately) is accepted and highly effective with regard to motivating and building effective teams, delegation and task shifting with better organisation of care and a more systematic approach to assessing women who require care.

The MiH programme has demonstrated the effectiveness of a phased approach to the introduction, implementation and scale up of ‘skills and drills ‘ type in-service training, initially using volunteer trainers (based in the UK), building capacity in-country of Master Trainers and skills laboratories/rooms and subsequently moving on to a not for profit franchising quality assured model.

A ‘catalytic’ but focused approach to building capacity of existing healthcare providers has led to measurable health system strengthening as a result of the programme including increased availability of EmONC signal functions, improved availability and use of labour ward and theatre registers and improved use of routine data for maternal and newborn health.

A multi-country approach and comparison is feasible, strengthening the collection and use of routine MNH data including for monitoring and evaluation of effectiveness of the programme over time.

Quality Improvement using audit methodology is an effective and catalytic intervention complementary to EmONC training which needs to be strengthened more widely especially alongside efforts to strengthen the collection and use of data.

The stillbirth rates in many health care facilities, especially at high volume CEmONC level, remain high and renewed efforts are needed to address this. MiH provides one of the largest global data bases of the causes of and factors contributing to stillbirths with 1307 stillbirths audited in Kenya, Malawi, Sierra Leone and Zimbabwe. 40.3% of all stillbirths recorded were fresh stillbirths. The partograph had been used in only 37% of cases. Cause of death was maternal factors (22.1%), intrapartum (18.5%) placental (15.1%), fetal (6.4%), umbilical (6.5%), uterus (5.2%), amniotic fluid (3.7%) and trauma (0.7%). The MiH training focused on Emergency Obstetric Care and less on Skilled Birth Attendance. Future programmes may need to include a renewed focus on birth care, use of the partograph and fetal monitoring at least to prevent fresh still births. The MiH programme had limited equipment funds and more will be needed in future programmes to ensure fetal heart rate monitoring equipment (hand held simple Doppler) can be provided. For intrauterine death a renewed focus on content and quality of antenatal care is required.

Future programmes should additionally have a dedicated component focused on early newborn care, care packages and criteria for newborn care units particularly at CEmONC level facilities.

A renewed emphasis is needed on improving data for newborn health and newborn health outcomes at health facility level.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Increased health provider capacity to provide Emergency Obstetric and Newborn Care (EmONC)
Output number per LF		1	Output Score	A
Risk:		Low	Impact weighting (%):	25%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
1.1 Number of in-service health care workers trained in EmONC	15,000	Exceeded. 18,598
1.2 Number of pre-service health care workers trained in EmONC	2,000	Exceeded. 2,274
1.3 Percent of health workers (both pre-service and in-service) demonstrating improvement in EmONC knowledge and skills at completion of training	80%	Exceeded. / (Across all 11 countries – includes India and RSA) / 83.7% of health care providers increased knowledge. / 99.2% of healthcare providers increased skills
1.4 ‘Number of women recognised to need and receiving Emergency Obstetric Care	15% increase / disaggregated by the type of complication / and / as a proportion of number of total deliveries (women requiring EmONC/women delivering at facility)	Partly met / 5 out of 9 countries show an overall increase ranging from 5.4% to 33.7% with a mean increase of 17.9% / Across all countries a mean increase of 15.0% at BEmONC level and 5.1% at CEmONC level. / As a proportion of total deliveries the proportion of women receiving EmONC at CEmONC level remained stable at 9.0% and at BEmONC level this increased by 6.2% at 12 months. / This indicator is linked to the incidence of obstetric complications – see output 1.6.
1.5 Percentage of babies referred to Newborn Care Unit for birth asphyxia (for facilities that have a NBU)	In target facilities with NBU, reduce % babies admitted to NBU with birth asphyxia (of all babies admitted to NBU) by 25% at 12 months post commencement of intervention compared to baseline	Not met / At the beginning of programme it was noted that this indicator was not routinely collected in most health care facilities. There is also a lack of criteria with regard to what constitutes a NBU across the various settings. Data were available to compare 12 months vs 6 months for 54 CEmONC level health care facilities across 6 of the 9 countries (not assessed in RSA or India) / 5 of 6 countries showed a reduction in % babies admitted for asphyxia ranging from 7.2% to 44.0% with mean reduction of 21.7%.
1.6 / Percentage reduction in key obstetric complications	Reduction in incidence of key obstetric complications / by 50% at 12 months	Partly met / Disaggregated by type of complication – for Haemorrhage there was an increase of 7.6% in the number of cases recognised and treated, (38.8% increase at BEmONC level with many more cases recognised and documented and 3.9% increase at CEmONC level where cases werer largely already well documented and recognised); for Sepsis there was a 7.2% decrease overall with a 31.0% decrease at BEmONC level and 5.6% decrease at CEmONC level); for Eclampsia there was a 10.2% increase overall but 16.7% increase at CEMONC level and 23.7% decrease at BEmONC level with evidence of earlier referral from BEMONC to CEMONC level . The number of cases of Rupture of Uterus at BEmONC level decreased by 60% but increased by 66% at CEmONC level.

Key Points
The results exceeded expectation in 3 out of the 5 indicators. Two indicators, 1.4 and 1.6, targets were partially met and disaggregation of the data showed areas where significant progress was made such as haemorrhage(the biggest cause of maternal death) in BEmONC centres. It is noted output 1.5 was not met, largely because data collection systems for newborns are so weak. The programme did try and improve these systems with varied impact.
- The overall increase in the number of women recognised to need and receiving EmONC is encouraging. It is likely that at CEmONC levels that almost the maximum number of women requiring EmONC are going to the facilities, with an overall 9.0% of all women attending for delivery requiring EmONC. The increase at BEmONC level is noteworthy and particularly encouraging suggesting both better access to and improved recognition of women who require EmONC.
- Disaggregation by type of complication is helpful – sepsis and rupture of uterus if diagnosed early are likely to be preventable – a marked reduction in sepsis and in number of cases of rupture of uterus at BEmONC level suggests this has occurred.
- With an overall improvement in recognition and recording of women requiring EmONC at BEmONC level, there is also some indication of better referral from BEmONC to CEmONC level but further studies would be needed to confirm this.
- Output 1.5 relies on data from a relatively small number of facilities and this indicator continues to be problematic as this data is still not routinely collected in many settings. MiH was instrumental in strengthening data for this indicator but more attention to routine data to capture newborn health is needed in future programmes.

Summary of responses to issues raised in previous annual reviews (where relevant)
1. LSTM to ensure that the project completion review contains data on the new output indicators 1.4 and 1.6. This has been done.
2. LSTM to continue with its sustainability/transition plan for each country. CMNH-LSTM have continued work on this. An updated table for individual countries post 2015 is provided below.

Country	Post 2015 status/ plan
Ghana	Strong national faculty in place; support from Ghana Health Service; Further funding being sought
Kenya	Funding in place for National coverage of EmONC Training until March 2019. (DFID Kenya)
Malawi	Funding in place until Dec 2016 with additional request for funding to expand coverage post 2016. (UNICEF Malawi)
Nigeria	Funding in place until Dec 2017 (Johnson and Johnson)
Sierra Leone	EmONC training continues with UNICEF funding until September 2016. Funding request as part of consortium submitted for additional 16 months expanded EmONC training programme.
South Africa	Training model adopted at national level. Funding for full national scale up received from EU to DOH RSA and implementation underway.
Tanzania	Funding in place until February 2018 for EmONC training in 2 regions. (UNICEF Tanzania)
Zimbabwe	Strong national faculty in place; 5 skills labs operational. Further funding being sought.
Bangladesh	Franchising agreements for local NGO (Centre for Injury Prevention Research Bangladesh) and, Bangladesh College of Physicians in place – further funding being sought
India	5 Skills Labs operational, supported by Government of India. (Contract for Quality Assurance of Skills Lab expected via WHO India).
Pakistan	Central Government has requested extension in Punjab and KPK provinces using mobile skills labs. Proposal developed and further funding being sought

Recommendations for future programmes
1. Future programmes should continue to document change in practice and outcomes disaggregated by type of complication to be able to identify what additionally is required to recognise and efficiently manage each type of complication at both BEmONC and CEmONC levels.
2. Referral patterns could be better documented
3. Better data to assess newborn care practice and outcomes is urgently needed.
4. Continue marketing the programme package in a ‘franchise’ model.

Output Title	Increased availability of EmONC for mothers and babies
Output number per LF		2	Output Score	A
Risk:		Low	Impact weighting (%):	20%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
2.1 Number of health care facilities with staff trained in EmONC / a) number of Comprehensive EmONC facilities and / b) number of Basic EmONC facilities	1904 healthcare facilities identified to receive EmONC training at planning and baseline stage during the course of the MiH programme.	Exceeded / Healthcare providers in 2,038 healthcare facilities received EmONC training
2.2 Number of health care facilities with increased number of EmONC signal functions available.	75% of health facilities that do not perform all signal functions (appropriate for their level) at baseline demonstrate an increase in the number of signal functions available, measured 12 months after commencement of interventions.	Partly met / In all countries signal functions increased. In 5 out of 9 countries 75% or more of facilities increased signal functions. / Of the 307 health care facilities followed up to 12 months, 77% (236/307) needed to increase signal functions. 69.1% of these facilities had increased the number of signal functions available at 12 months (69.3% at CEmONC level and 68.9% at BEMONC level)
2.3 Number of facilities providing a) ALL Basic EmONC signal functions and b) ALL Comprehensive EmONC signal functions	a) Increase by 10% number of fully functional BEmONC healthcare facilities and b) increase by 25% number of fully functional CEmONC healthcare facilities.	Exceeded / Of the 307 healthcare facilities followed up at 12 months, 23.1% (71/307) were fully functional at baseline. / At 12 month follow-up, 158 (51.5%) facilities were fully functional. (increase by 123% overall; 259% increase for BEmONC and 80% increase for CEmONC) Targets met in all countries

Key Points
The results of this output exceeded targets in outputs 2.1 and 2.3. The target for output 2.2 were partially met as the target was reached in more than half of the countries and steady progress has been noted from 2013.

- There has been a significant improvement in the availability of signal functions, at both BEmONC and CEmONC levels. This was challenging in particular as lack of equipment was the limiting factor in 70% of cases of non-availability of any signal function and the programme had limited influence over this.
- Specifically of note is the increase in ‘hard to achieve’ signal functions; assisted vaginal delivery (AVD) or ventouse extraction increased overall from 48% to 69% (43.8% increase) and manual vacuum aspiration (MVA) for retained products of conception increased overall from 76% to 84% (10.5% increase)
- There have been suggestions that it is not feasible to expect all BEmONC designated healthcare facilities to provide all 7 signal functions. Among BEmONC 135 out of 152 needed to improve – only 11% were fully functional. At 12 months 93 out of 135 had improved (68.9%). At BEmONC level availability of Manual Vacuum Aspiration increased from 54% to 69% and for AVD 28% to 52% illustrating that improvement at BEmONC level is feasible.
Shortages of skilled staff have been highlighted as a limiting factor especially with regard to ensuring 24/7 availability of EmONC. The MiH programme trained 84.6% of all staff working in the maternity area across all target health care facilities (82.2% at CEmONC and 87.1% at BEmONC level).

Summary of responses to issues raised in previous annual reviews (where relevant)
LSTM to disseminate their findings on improvements to services as well as the challenges to all MNCH stakeholders in countries through technical working groups and other available forums, including the Human Resources groups in countries. This could be in addition to planned dissemination through in-country steering groups if feasible. Regular attendance at in-country Technical Working Groups to ensure feedback on programme performance was included throughout the programme, with in-country staff attending such meetings on a quarterly basis in most countries. All dissemination meetings were completed with broad groups of stakeholders invited and attending in each country and also at international dissemination meetings.

Recommendations for future programmes
1. For expansion or development of the programme in new countries, in addition to training of health care providers, additional emphasis and budget should be placed on equipment needs.
2. In future programmes, staff rotational practices (and how these can be amended) should be taken into account to ensure optimal benefit of EMONC in-service training is achieved. For example ensuring that induction protocols include EmONC training prior to starting a maternity rotation.
3. Explore options with other donors or funding modalities to ensure consistent availability and quality of essential supplies.

Output Title	Strengthened accountability for results with increased transparency
Output number per LF		3	Output Score	A
Risk:		Low	Impact weighting (%):	15%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
3.1 Number of facilities with established a) labour ward register b) theatre register c) postnatal discharge register	100% of healthcare facilities have labour ward registers in place, 100% have theatre registers in place, and 75% have postnatal discharge registers in place.	Met a) Labour ward register: 100% of facilities had labour ward registers in place. b) Theatre register: 100% of facilities have a theatre register in place. c) Postnatal discharge register: 100% of facilities have a postnatal register
3.2 Number of health workers and managers trained in the collection, aggregation and use of routine data to inform practice	1150 will be implemented in all countries except India and RSA	Exceeded / 1487 trained
3.3 Number of health facilities with a Quality Improvement Committee in place	100% of QI participating healthcare facilities	Partly met / Increased in all countries; 100% target met in Zimbabwe and Sierra Leone, Increased by 46.2% in Kenya to 86.4% and by 200% in Malawi to 66.7%.
3.4 Number of health care providers trained in quality improvement methodology, including audit and death reviews	610 from Malawi, Kenya, Sierra Leone and Zimbabwe	Exceeded / 665 trained
3.5 Number of facilities that conducted maternal, perinatal or stillbirth audit within past 6 months	80% of QI participating healthcare facilities.	Exceeded / 100% of health care facilties had conducted Maternal death audit and Perinatal or Stillbirth audit and standards based audit in last 6 months / This represents a 71.4% increase in nuber of health care faciliteis conducting maternal death audit, 173% increase for perinatal death audit and 73.3% increase for standards based audit – at 12 months compared to baseline.
3.6 Number of facilities in which a maternal death review was conducted for >80% of maternal deaths occurring in the preceding 6 months	80% of QI participating healthcare facilities.	Met / 81% of healthcare facilities reviewed 80% or more of maternal deaths by 6 months.
3.7 Number of facilities with documented evidence of action taken as a result of maternal death, perinatal death or still birth audit or standards-based audit.	100% of QI participating healthcare facilities	Met / All participating health care facilities have evidence of action taken as a result of undertaking audit. / This was either as a results of Maternal death audit (79.2%) or perinatal death audit (85%) or standards-based audit (96%)
3.8 Number of facilities assessing patient experience of maternal and newborn healthcare provided.	80% of Making it Happen target healthcare facilities.	Partly met / This target was met in Kenya and Malawi. / In Sierra Leone this was not possible because of the Ebola epidemic and in Zimbabwe the MiH programme was not permitted to suport this activity with prolonged ethical concerns being raised at national level.

Key Points
Most output targets were either met or exceeded expectations. Output 3.3 was only partially met but the progress since the last annual review was noted. Furthermore the contextual factors beyond the programme’s control surrounding output 3.8 were taken into account when exploring why it was only partially met.

- The MiH programme served to highlight that although maternal death audit is widely conducted, there are generally delays in carrying out these reviews e.g. at 12 months 76.5% of participating healthcare facilities had audited more than 80% of all maternal deaths that had occurred. This is largely becuase of administartive delays and delays in comissioning revew meetings by district or national level teams.
- MiH attempted to bring in new aspects of quality improvement including what should be considered as routine patient satisfaction surveys – this was challenging in all countries as formal mechanisms for this are not in place.
- Analysis of cause of maternal death shows that up to 80% still continue to be direct maternal deaths and as a results of haemorrhage, eclampsia and sepsis. The application of the International Disease Classification applied to Maternal Mortality, has helped in all settings to provide more accurate information on cause of death.
- Analysis of cause of stillbirth shows that the leading causes are maternal (22%), intrapartum (18.5%) and placental (15.1%) (Aggregate data for Kenya, Malawi, Sierra Leone and Zimbabwe). The lack of an internationally agreed case classification system continues to be a problem and MiH used the Relevant Code of Death classification as this was found to be the most applicable in low and middle income settings.
- Analysis of patient experience from Malawi and Kenya show that mean score for overall quality of care is at 83%; and particular aspects of care (care received, healthcare provider and facility) all score 90%. At CEmONC level, the mean score is 77% overall, and the individual aspects of care (care received, healthcare provider and facility) are all at 90%. At BEmONC level, the mean score is at 75% overall, while the individual aspects score the following: care received at 80%, healthcare provider at 80% and facility 70%.

Summary of responses to issues raised in previous annual reviews (where relevant)
1. MiH focus these last months of the programme on sustaining the gains made in this output i.e. capacity building and institutionalising audits and death reviews. Although progress has been made, the data and challenges are presented above.
2. MiH to recommend a way forward to consult patients on their perceptions of care. The latest progress on this is presented above – embedding patient surveys met with some resistance.

Recommendations for future programmes
1. Improving quality of care using audit methodology is acceptable, easily understood by healthcare providers and supporting this will build on existing mechanisms and structures already in place. Audit leads to identification of priority areas that require action and healthcare providers are able to take effective action and demonstrate change.
2. Formalising the process of maternal audits into hospital protocols including specifying the timing within which they should be undertaken is key to ensuring lessons learnt are not lost. In the future consider expanding the audits to include near miss cases (as in South Africa) as well as maternal deaths. This may be a useful avenue to explore in countries where investigation of maternal deaths is sensitive and learning from near miss cases can result in more open discussions on quality of care improvement and as there are many more near misses than deaths.
3. Ensuring that feedback from clients (women who attend healthcare facilities for birth and/or when they require emergency obstetric care) is obtained and regularly reviewed by health care providers is still novel in many settings and will require high level ‘buy in’.

Output Title	Strengthened capacity to sustain improvements in MNH service delivery
Output number per LF		4	Output Score	A+
Risk:		Low	Impact weighting (%):	20%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones 2015	Progress
4.1 Number of Facilitators (or Master Trainers) able to deliver in-service EmONC training	1025	Exceeded / 1681
4.2 Number of pre-service tutors trained in EmONC	286	Exceeded / 328
4.3 Number of countries able to run EmONC in service health worker training: / a) with external QA support from global coordination centre at LSTM b) independently	a) 5 countries able to run training with QA from global coordinating centre at LSTM. / b) 6 countries able to run EmONC training independently.	Exceeded / 3 countries (Malawi, Sierra / Leone, Tanzania) / 8 countries (Bangladesh, / Ghana, India, Kenya, Nigeria, RSA, Tanzania, Zimbabwe)
4.4 Number of countries able to run EmONC training as part of pre-service health worker training / a) with external QA support from LSTM and / b) independently	a) Pre-service training supported in 3 countries with QA from global coordinating centre at LSTM. / b) At the end of Programme, 3 countries able to provide EmONC training as part of preservice training independently.	Exceeded / a) 4 (Medical interns: Kenya and Republic of South Africa, Midwives: Zimbabwe and Kenya, MCH aides: Sierra Leone) / b) 3 (MCH Aides and Midwifery: Sierra Leone, Bangladesh, Medical interns: Republic of South Africa)
4.5 Number of new / a) skills laboratories or / b) training rooms equipped for EmONC training.	a) 20 Skills Laboratories (full equipment set) / b) 239 Skills Rooms (part equipment set)	Exceeded / a) 20 / b) 269
4.6 Number of countries where in country stakeholder group for MNCH meets regularly (minimum every 6 months)	Stakeholder group meets regularly in all 11 MiH2 countries.	Met / All countries met regularly

Key Points
- The programme has exceeded its targets in terms of countries being able to run EmONC training independently or with quality assurance support from CMNH-LSTM – this is a significant achievement. The training is being scaled up nationally in Kenya and South Africa. In 2015 quality of training by national master trainers was assessed in Malawi, India, Kenya and Nigeria.
- There is scope for further support from LSTM in countries where expansion is being planned or requested (National expansion - India, RSA, Kenya, Ghana and Sierra Leone;m regional expansion – Tanzania, Pakistan, Nigeria and Malawi). Quality assurance and (not-for –profit) franchising models for this are now available pending funding.
- As part of the programme transition, additional instruction on the optimal organisation and use of skills labs was provided in each country to national Master Trainers. Skills labs are placed centrally in larger hospitals and training institutions to allow multidisciplinary teams to practice their skills. In India, 5 skills labs have been developed and operationalised as National Centres of Excellence for all of India. LSTM has developed a clear plan for the future purpose and utilisation of the labs with the Government of India including providing ongoing quality assurance, funded by WHO. Mobile skills labs have been requested by Pakistan.

Summary of responses to issues raised in previous annual reviews (where relevant)
1. LSTM to identify clear transition plans for the training, skills labs and rooms with all countries – this is particularly relevant for India but also Nigeria. Included above. Setting up and managing skills labs was the focus in India and MiH contributed to national guidelines for this as well as disseminated a paper to all State Governments and partners as requested by the government and DFID India. Additionally this was discussed during all dissemination meetings and disseminated via peer reviewed publications.
2. LSTM to pursue further funding options for India to ensure sustainability of the skills labs there. As above – Government of India is funding the labs with QA support from LSTM, funded by WHO.
3. LSTM to document the success and challenges of the skills rooms and labs as part of the broader dissemination. This was done.

Recommendations for future programmes
There is a need for a Global Coordinating Centre to:
- Sustain the continuation and scale up of the competency based EmONC training in those countries that have participated to the Making it Happen Programme;
- Promote the adoption of the MIH EmONC training in new countries, and provide technical assistance to pilot and introduce the training;
- Offer quality assurance and technical assistance to partners during the implementation and scale up of the training;
- Continue providing evidence of what works, what does not work, where and why with regards to EmONC, through the implementation and dissemination of high quality research.

CMNH-LSTM is ideally suited to take on this role having developed the capacity to do so and international recognition and network needed ensure scale up of good practice as demonstrated and developed under the MiH programme.

Output Title	Evidence generated by programme disseminated in order to inform national, regional and global agenda for MNH
Output number per LF		5	Output Score	A++
Risk:		Low	Impact weighting (%):	20%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones 2015	Progress
5.1 Number of a) national and b) international level meeting at which evidence arising from programme information on MiH is disseminated	Annual target: In each participating country, at least 1 annual meeting used to disseminate programme results (11 in total). At international level, at least 2 meetings used to disseminate results.	Exceeded / 11 national dissemination events held (1 per country) plus 5 international conferences attended in Rome and Canada (FIGO), RSA (Still-birth Alliance), UK and India (RCOG International Meetings). Contribution to WHO working groups and two multi-country meetings organised in Liverpool. Additionally a separate DFID event was held in London which included DFID UK and In-country advisors
5.2 Number of a) quarterly reports and b) information bulletins	a) 16 b) 13	Exceeded / a) Quarterly reports: 16 / b) Information bulletins: 14
5.3 Number of peer reviewed publications on evidence arising from programme	6	Exceeded / Peer reviewed: 30 / Non-peer reviewed: 5 / (See Annex 1 for full list)

Key Points
- Dissemination of lessons learnt has formed a key output of the MiH programme. This has been appreciated by the internationally community with the MiH programme recognised to be one of the largest multi-country programmes focusing on implementation, operations research and health systems strengthening with a strong focus on measuring ‘what works where and why’.
- The final findings from the programme were disseminated both in-country and internationally through a mix of presentations, printed summary material and information on the CMNH and DFID websites.
- All meetings have been very well attended and highly participatory. For example; in Ghana the steering committee has brought together regularly Directors of Health in the 3 regions supported to discuss implementation progress, challenges and solutions. The RMNCH technical working group of Ghana Health Services has redesigned all RMNCH in-service training programmes using the MiH approach and methodology. In Kenya, dissemination of best practices and standards for conducting MiH training interventions has resulted in improved quality of training nationally, a revision of the national EmONC training curriculum and a demand for further pre-service training support. Through the training, more efficient equipment for assisted vaginal delivery (KIWI Omni cup) has been added to the national hospital equipment list. Through the steering group meetings and other dissemination meetings in Nigeria, the MOH has fully accepted the short competency based EmONC training and has requested national scale up.
- A final three day International Conference on Maternal and Newborn Health was hosted by CMNH on 24-26 May 2016. It provided a platform to share the final results from the MiH programme with delegates and allowed the opportunity to discuss the future direction of the programme and offer views on the programmatic implementation challenges.
- DFID dissemination event: A key stakeholder dissemination event was held for DFID staff on 8th June that showcased the final results and had presentations from Ghana and Kenya on the impact of the programme in their countries.

Summary of responses to issues raised in previous annual reviews (where relevant)
LSTM focus on the final dissemination event/s as well as final dissemination materials. Whilst published papers are important, it is imperative that the lessons learnt and good practice messages get to policy makers and implementers – materials should be tailored for these audiences as well. The focus in the last 6-9 months has been on dissemination events and materials. Short promotional leaflets ( summary as well as country specific information) on final results of MiH shared with all steering groups, MOH in each country, DFID and other in-country partners, potential and existing funders through dissemination meetings, email, website etc. Promotional films from Africa and Asia on website.

Recommendations for future programmes
The dissemination activities under MiH have included academic papers as well as shorter materials adapted to the audience. This mixed approach has been well received and ensures high quality evidence gets translated into practice. Future programmes can use this approach.
- Build the capacity of local partners to conduct and publish research
- Consider developing a series of policy briefs that summarise the findings from the research. These could be made widely available with clear recommendations on delivering EmNOC training within developing contexts.
- Publishing case studies of implementation successes could be showcased e.g. Kenya where the programme has been scaled up nationally.
- Produce specific marketing tools to promote the franchising model.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance
At the end of the programme, £15,862,751 has been spent on the programme with accurate forecasting and minimal variance. Overall, and as per previous years, the main costs continue to be: central management and coordination; monitoring, evaluation and research; dissemination; implementation costs (in-country and UK). These are the same across all of the 11 countries with some small proportional differences between countries arising from local conditions and differing models of delivery. A breakdown of the proportion being spent in each area is given below. Whilst the actual spend against original budget within central management, monitoring, evaluation and research and dissemination shows very minimal variance, one point of note is that overall there has been lower than expected UK implementation costs and a higher proportion of in country implementation costs, which has been a very positive trend across the life of the programme.

In-country cost drivers
Accommodation and Subsistence (for participants, facilitators and in-country staff) in delivery of all programme activity (EOC training, M&E and dissemination) was the largest cost driver in the programme. National salaries and workshop costs (venue hire, catering and refreshments for EmONC training and Data and Quality Improvement workshops) were also significant. The ratio of these drivers varied across countries, as can be seen below comparing Bangladesh, where accommodation and subsistence is lower than the average and national salaries are the most significant cost driver; and Kenya, where accommodation and subsistence is higher than the average, but national salaries and workshop costs lower than the average.
All Countries Bangladesh Kenya

VfM performance compared to the original VfM proposition in the business case

Economy has been achieved in MiH via cost reduction, with examples such as:
- Remote contact methods (data collection by phone and email) employed in Pakistan and Sierra Leone to reduce travel costs
- Continued liaison with suppliers to ensure best prices and economies of scale for training equipment
- Investing in printers of appropriate quality in country offices to reduce the amount of paperwork printed and shipped from the UK for use in training courses
- Procurement- bulk-buying of equipment at preferential rates
- Revision of out-of-pocket expenses policy for UK staff and volunteers
- Standard Operating Procedures
- Tracker format allows for scrutinising of all transactions from ledger
- Countries increasingly used district-based people to collect M&E data rather than sending out centrally-based staff
- Use of Skype rather than teleconferencing, and Cherry Call facility allowing cheaper international calls
- Fast tracking transition to Quality Assurance (QA) model in the Nigeria training; resulting in courses run entirely by Nigerian facilitators and greatly reduced travel costs from the UK
- Annual review of country work plans in order to fully realise all synergies with other funders’ programmes, and thereby maximise savings (e.g. on travel and dissemination costs)
- Annual budgeting and sub-contracting across all countries

Efficiency: In comparison to current models of training in place locally that happen to be longer and more didactic, MiH is shorter (3days) and a more hands on, using training mannequins to practice skills and avoiding waiting for real patients. It was, therefore, cheaper to run, incurred less opportunity costs for staff (including time away from clinical care) and led to significant achievements against outputs. A total of 5,950 volunteering days were provided by UK- based facilitators to deliver and quality assure the EmONC – all gave their time free of charge. Prior to MiH, in all participating countries, EmONC training was provided only by paid consultants and training was a minimum of 2 weeks up to three months. Trainings were usually not multidisciplinary, mainly didactic and provided by a single facilitator with limited or no evidence of effectiveness. Moving to a 3-5 day highly participatory and effective model is clearly value for money. Volunteering demonstrably not only benefitted the recipient countries and healthcare providers but also the volunteers themselves who felt re-energised when working back in the NHS in the UK. At a cost of £500 per day for these experienced consultant obstetricians, midwives and anaesthetists – this has saved the programme and estimated £2.975 million in technical assistance/consultancy fees.

The graph below shows the changing ratio of national to UK facilitators across all countries throughout the programme. The aggregated picture is that by year 2 of the programme, there was enough expertise in countries for an average of only 3 facilitators from the UK to attend the trainings compared with the model’s target of 4. Not only did this lead to increased sustainability of the training but also contributed to efficiency with less international travel.

Average number of National and UK Facilitators per EmONC Course
(All Countries)

Effectiveness: The original estimation of lives saved by this project seems to have been a gross overestimation and, if these are taken as targets, the programme was not as effective as expected. Using other parameters, however, the programme is highly cost effective. Previous annual reviews have showed that the average cost of the training per trainee is £200, which is cheaper than other trainings of this type.

Cost effectiveness studies from Kenya, Bangladesh and Sierra Leone from 2013 indicate that the cost per maternal and stillborn life saved of 3-5 day EmONC training is between £527.19 and £846.99. Even with the overestimation discussed previously, this works out cheaper than predictions of approx. £1052 per life saved (maternal, newborn and stillbirths). This translates into cost per life-year averted of £10.96-£14.99. The ranges indicate that cost –effectiveness varied on context but overall it is considered highly cost-effective in all three countries (using WHO thresholds).

In the Republic of South Africa where a 2 or 3 day training package was used (depending on level of health facility and health care provider) the estimated cost per maternal life saved is £3000. This included programme costs.

Assessment of whether the programme represented value for money
As highlighted throughout the programme and annual reviews, MiH represented value for money due to low cost training, high rates of scale up, strong local capacity building and demonstrated results.

Quality of financial management during programme
Throughout the MiH programme there was continuous improvement of project management systems to ensure efficiency of the programme. Examples included the quarterly tracking and forecasting of budgets; the scrutinising of each cost item incurred (taken from the financial ledgers); quarterly spot-checks of audit trails for spend items; annual financial reviews of partner’s financial systems, policies and procedures; LSTM’s institutional Due Diligence questionnaire; and, Standard Operating Procedures for in-country offices which set out the minimum requirements expected for financial and administrative processes related to LSTM programmes, and best practice where appropriate. Quarterly management meeting were held between LSTM and DFID to assess progress, identify problems and risks and to keep the programme on course against logframe objectives.

Two cases of financial mismanagement in two countries (Kenya and Zimbabwe) were identified and dealt with swiftly by LSTM in 2014.

Date of last narrative financial report	31 December 2015
Date of last audited annual statement	Up to 31 July 2015

E: RISK (½ page)

Quality of risk management over the life of the programme
A risk management strategy was developed in 2015 with an updated comprehensive Risk Register completed for each country and reviewed monthly as part of the Programme Management Board meetings. The risk matrix for the programme is copied below with mitigating actions outlined:
Risk	Action taken to mitigate risk and update
Lack of interest and/or ownership by national government, professional associations, development partners or other stakeholders	Detailed country level plans were developed in consultation with governments and stakeholders in all countries. In almost all cases, this risk did not materialise and ownership of the programme was very good. Challenges of ownership continued in some countries for example Nigeria.
Insufficient equipment and supplies to provide EmONC services	This was highlighted in previous Annual Review. Insufficient budget was available to mitigate against this risk.
Inadequate record keeping and reporting at facility level to monitor and evaluate programme	Although huge improvements have been made, certain areas remain very weak such as the registering around newborns.
Failure to build sustainability and ensure benefits beyond the immediate lifespan of the programme	Through the building up of master trainers and the use of local institutions and organisations, this risk has been largely mitigated. Sustainability is much higher in countries that had two phases of the programme rather than one. Phase 2 of MiH did not focus on the ongoing mentoring and supervision of trainees, limiting sustainability. As stated in the outputs, many countries are able to run the training independently and some have taken this model up for national roll out.
Weak in-country financial management and misuse of programme funds	Two countries have experienced issues with in-country financial management – both instances have been successfully dealt with by LSTM. LSTM has continually improved systems and monitoring of in-country partners.
Insufficient management capacity within LSTM to administer project with risk of: 1) / Delayed collation of monitoring data and delayed production of progress reports; 2) Less attention to strengthening accountability and improvements in quality of care; 3) Less attention to the generation of peer-reviewed publications/presentations to disseminate evidence and influence MNH policy and strategy beyond the project countries	LSTM has been able to collate data and generate timely progress reports. Some delays experienced were beyond the programme’s control for example in Sierra Leone due to the Ebola epidemic. / The quality of care component of the programme has been implemented in a limited number of facilities, showing some interesting results. The number has been less than expected due to delays in Malawi and Sierra Leone. / Many published, peer reviewed presentations and publications have been produced and a series of in-country and UK dissemination events were held.
Insufficient funding to deliver project results while meeting partner government expectations	Additional funding has been sought and given in a number of countries meaning the programme will continue in some places beyond DFID funding.
Indicators do not represent the real picture for example more referrals of complicated cases can reflect as an underachievement	Outcome and output indicators have been revised to adjust for these anomalies.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
The programme, tracked through key performance indicators, delivered most activities on the ground on time. Some delays were experienced in India due to a change in the implementation focus requested by the government and the extent of consultation requested and required before the skills lab design and content was approved and construction could start. Similarly extensive stakeholder input was received into the design and development of the training curriculum and content of manuals for both participants and master trainers. Implementation delays were experienced in Sierra Leone due to the Ebola crisis. Quality improvement activities were not possible in Malawi due to the roll out of WHO’s Maternal Death Surveillance Review system and this meant fewer facilities than anticipated were involved in the quality improvement work which now builds on the national launch of MDSR in Malawi.

A no-cost extension was granted for the programme to complete all activities and to collate, clean and analyse the large amount of data.

Performance of partnership (s)
The programme has managed to achieve very good, close working relationships with all government ministries as well as local implementing partners, often large respected local institutions. This was apparent during all field visits with a high degree of respect for the work of LSTM and the relationships built up. Local ownership was so high in South Africa that many were unaware of the backstopping being provided by LSTM. The programme was guided by an external advisory group and had 6 weekly meetings with DFID.

Asset disposal and value obtained by DFID
An updated asset register was sent to DFID in May 2016 with agreement that all equipment could be gifted to the host organisation to continue to be used in the field of improving maternal & newborn health. An official letter, checked by DFID, has been sent to parties concerned. See Annex 2 for the full list.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation
An initial project appraisal of the MiH programme (ARIES ref number 200421) was undertaken in September 2011 of 5 countries the programme was taking place in with a view of designing the second phase of MiH. This suggested the inclusion of an evaluation component and expansion of delivering training in broader quality improvement interventions; both of which were incorporated into Phase 2.

No significant programmatic changes were required as a result of DFID annual reviews since 2012. The theory of change assumptions proposed in the business case has held view and this is reflected in the fact that many of the outputs were met or exceeded expectations.

Furthermore the recommendations including changes to log frame were followed through sufficiently including efforts to improve data collection mechanisms.

Monitoring progress throughout the programme
Within the MiH programme there is a monitoring and evaluation framework of the training impact.
This comprised of 5 levels-
Level 1: Healthcare provider reaction
Level 2: Change in knowledge and skills
Level 3: Behaviour change
Level 4: Change in outcome indicators
Level 5: Process evaluation

Annual reviews were undertaken yearly from 2012. Their overall rating was favourable with scores of either an A or an A+.
The programme has had strong interest and support from local partners who have engaged with the MiH team throughout the process.
There have been regular field visits undertaken by LSTM. DFID staff has also reported on South Africa, Nigeria, Malawi, Kenya and Zimbabwe; the findings from these visits were incorporated into the relevant annual reviews and this report.
Ongoing tracking of progress was monitored through quarterly reports, country reports and meetings between LSTM and DFID programme managers.
A final dissemination event was held in DFID where representatives from Ghana spoke about the programme and the data was presented. This was attended by a large number of DFID advisers and other partners. Findings from this event were also incorporated into this review.

Positive feedback was received by various stakeholders. Beneficiary feedback includes:
- Health Care Provider, Malawi “The knowledge and skills that I gained during the training helps me to detect and diagnose obstetric emergencies and act promptly. I have been able to conduct assisted vaginal deliveries, manage shoulder dystocia and many other obstetric complications with less difficulty.”
- UK Volunteer “MiH has helped re-shape the mentality of health workers…that maternal death is not an inevitable consequence of pregnancy and labour. The training has assisted team working and empowered workers to speak up about substandard practice and to be confident about how they themselves practice.”
- NGO Partner, Bangladesh “The skills based, short nature of the course, compared to much longer theoretical courses available in country, is very attractive to healthcare providers in Bangladesh.”
- Ministry of Health, Kenya “MiH is the best thing that has ever happened to Kenya in MNH. It is highly valued and has succeeded in demystifying MNH.”
- Ministry of Health, Tanzania “We own this programme. We would like to scale this up to other areas so that we can work towards the new global targets of ending preventable maternal deaths in Tanzania”
- Reproductive Health Coordinator “In my region alone over 400 health care providers were trained in the (CMNH-LSTM) EmONC training package of which 90% are still in post”
DFID In-country “CMNH-LSTM are really well known for working in partnership with the MOH and all partners – this has been noted and is very much appreciated – also unlike others – CMNH-LSTM has taken sustainability into account from the start of the programme and not just at the end - Well Done! – this is really a great programme - Keep saving lives!”

ANNEX 1: Publications

2016
Ameh CA, Kerr R, Madaj B, Mdegela M, Kana T, Jones SA, Lambert J, Dickinson F, White S and van den Broek N (2016) Knowledge and skills of healthcare providers in sub-Saharan Africa and Asia after competency based training in Emergency Obstetric and Newborn Care. PLoS, (In Press)

Jones S, Gopalakrishnan S, Ameh CA, White S and van den Broek N (2016) Women and babies are dying but not of Ebola - The effects of the Ebola Virus epidemic in Sierra Leone on the availability, uptake and outcomes of maternal and newborn health services in Sierra Leone BMJ Global Health,(In Press).

Jones SA, Sam B, Bull F, James M, Ameh CA and van den Broek NR (2016) 'Strengthening pre-service training for skilled birth attendance An evaluation of the maternal and child health aide training programme in Sierra Leone', Nurse Education Today, vol. 41, no. 2016, pp. 24-29. doi: 10.1016/j.nedt.2016.03.018 Available from: http://www.sciencedirect.com/science/article/pii/S0260691716001246

2015
Ameh CA and van den Broek N (2015) 'Making It Happen: Training health-care providers in emergency obstetric and newborn care', Best Practice & Research Clinical Obstetrics & Gynaecology, vol. 29, no. 2015, pp. 1077-1097. doi: 10.1016/j.bpobgyn.2015.03.019 Available at: http://www.bestpracticeobgyn.com/article/S1521-6934(15)00066-8/pdf

Banke-Thomas AO, Madaj B, Ameh C and van den Broek N (2015) 'Social Return on Investment (SROI) methodology to account for value for money of public health interventions: a systematic review', BMC Public Health, vol. 15, pp. 582. doi: 10.1186/s12889-015-1935-7 Available from: http://www.biomedcentral.com/1471-2458/15/582

Jones S, Ameh CA, Gopalakrishnan S, Sam B, Bull F, Labicane RR, Dabo F and van den Broek N (2015) 'Building capacity for skilled birth attendance: An evaluation of the Maternal and Child Health Aides training programme in Sierra Leone', Midwifery, vol. 31, no. 2015, pp. 1186-1192 doi: 10.1016/j.midw.2015.09.011 Available from: http://www.sciencedirect.com/science/article/pii/S0266613815002570

Jones S, Lambert J and van den Broek N (2015) 'Sustaining change: introducing emergency obstetric and neonatal care education into the pre-service curriculum', Essentially MIDRS, vol. 6, no. 4, pp. 7-11.

Pattinson RC, Makin JD, Pillay Y, van den Broek N and Moodley J (2015) 'Basic and comprehensive emergency obstetric and neonatal care in 12 South African health districts', South African Medical Journal, vol. 105, no. 4, pp. 256-260. doi: 10.7196/samj.9181 Available from: http://hmpg.co.za/index.php/samj/article/view/2660

Utz B, Kana T and van den Broek N (2015) 'Practical aspects of setting up obstetric skills laboratories - A literature review and proposed model', Midwifery, vol. 31, no. 4, pp. 400-408. doi: 10.1016/j.midw.2014.11.010 Available from: http://www.midwiferyjournal.com/article/S0266-6138(14)00292-7/pdf

Utz B, Zafar S, Arshad N, Kana T, Gopalakrishnan S and van den Broek N (2015) 'Status of Emergency Obstetric Care in four districts in Punjab, Pakistan - Results of an EOC Baseline Assessment', Journal of the Pakistan Medical Association, vol. 65, no. 5, pp. 1-6. Available from: http://www.jpma.org.pk/full_article_text.php?article_id=7342

2014
Ameh CA, Adegoke A, Pattinson R and van den Broek N (2014) 'Using the new ICD-MM classification system for attribution of cause of maternal death-a pilot study', BJOG: An International Journal of Obstetrics & Gynaecology, vol. 121, no. S4, pp. 32-40. doi: 10.1111/1471-0528.12987 Available at: http://onlinelibrary.wiley.com/doi/10.1111/1471-0528.12987/full

Aminu M, Unkels R, Mdegela M, Utz B, Adaji S and van den Broek N (2014) 'Causes of and factors associated with stillbirth in low- and middle-income countries: a systematic literature review', BJOG: An International Journal of Obstetrics & Gynaecology, vol. 121, no. S4, pp. 141-53. doi: 10.1111/1471-0528.12995 Available at: http://onlinelibrary.wiley.com/doi/10.1111/1471-0528.12995/full

Aminu M, Utz B, Halim A and van de Broek N (2014) 'Reasons for performing a caesarean section in public hospitals in rural Bangladesh', BMC Pregnancy and Childbirth, vol. 14, no. pp. 130. doi: 10.1186/1471-2393-14-130 Available at: http://www.biomedcentral.com/content/pdf/1471-2393-14-130.pdf

Halim A, Utz B, Biswas A, Rahman F and van den Broek N (2014) 'Cause of and contributing factors to maternal deaths; a cross-sectional study using verbal autopsy in four districts in Bangladesh', BJOG: An International Journal of Obstetrics & Gynaecology, vol. 121, no. S4, pp. 86-94. doi: 10.1111/1471-0528.13010 Available at: http://onlinelibrary.wiley.com/doi/10.1111/1471-0528.13010/pdf

O'Donnell E, Utz B, Khonje D and van den Broek N (2014) ''At the right time, in the right way, with the right resources': perceptions of the quality of care provided during childbirth in Malawi', BMC Pregnancy and Childbirth, vol. 14, no. pp. 248. doi: 10.1186/1471-2393-14-248 Available at: http://www.biomedcentral.com/1471-2393/14/248

Owolabi H, Ameh C, Bar-Zeev S, Adaji S, Kachale F and van den Broek N (2014) 'Establishing cause of maternal death in Malawi via facility-based review and application of the ICD-MM classification', BJOG: An International Journal of Obstetrics & Gynaecology, vol. 121, no. S4, pp. 95-101. doi: 10.1111/1471-0528.12998 Available at: http://onlinelibrary.wiley.com/doi/10.1111/1471-0528.12998/full

van den Broek N, Lewis G and Mathai M (2014) 'Guest editors' choice', BJOG: An International Journal of Obstetrics & Gynaecology, vol. 121, no. S4, pp. 2-3. doi: 10.1111/1471-0528.13011 Available at: http://onlinelibrary.wiley.com/doi/10.1111/1471-0528.13011/abstract

2013
Adegoke AA, Mani S, Abubakar A and van den Broek N (2013) 'Capacity building of skilled birth attendants: A review of pre-service education curricula', Midwifery, vol. 29, no. 7, pp. e64-e72. doi: 10.1016/j.midw.2012.08.009 Available at: http://www.sciencedirect.com/science/article/pii/S0266613812001611

Utz B, Siddiqui G, Adegoke A and van den Broek N (2013) 'Definitions and roles of a skilled birth attendant: a mapping exercise from four South-Asian countries', Acta Obstetricia et Gynecologica Scandinavica, vol. 92, no. 9, pp. 1063-9. doi: 10.1111/aogs.12166 Available at: http://onlinelibrary.wiley.com/doi/10.1111/aogs.12166/full

2012
Adegoke A, Utz B, Msuya S and van den Broek N (2012) 'Skilled Birth Attendants: Who is who? A Descriptive Study of Definitions and Roles from Nine Sub Saharan African Countries', PLoS ONE, vol. 7, no. 7, pp. e40220. doi: 10.1371/journal.pone.0040220 Available at: http://www.plosone.org/article/info%3Adoi%2F10.1371%2Fjournal.pone.0040220

Ameh CA, Msuya S, Hofman J, Raven J, Mathai M and van den Broek N. (2012) 'Status of Emergency Obstetric Care in Six Developing Countries Five Years before the MDG Targets for Maternal and Newborn Health', PLoS ONE, vol. 7, no. 12, pp. e49938. doi: 10.1371/journal.pone.0049938 Available at: http://www.ploscollections.org/article/info%3Adoi%2F10.1371%2Fjournal.pone.0049938

Raven J, Tolhurst R, Tang S and van den Broek N (2012) 'What is quality in maternal and neonatal health care?', Midwifery, vol. 28, no. 5, pp. e676-e683., doi: 10.1016/j.midw.2011.09.003 Available at: http://www.sciencedirect.com/science/article/pii/S0266613811001367

Policy Documents, Manuals

World Health Organization (2016) Making every baby count: audit and review of stillbirths and neonatal deaths: Audit and review of stillbirths and neonatal deaths, World Health Organization, vol. World Health Organization, Available from: http://apps.who.int/iris/bitstream/10665/249523/1/9789241511223-eng.pdf

Adaji S, Aminu M, Dewez JE, Mgawadere F and van den Broek N (2015) Improving Quality of Care for Mothers and Babies. The Global Library of Women's Medicine, Carlisle.

Dewez JE and van den Broek N (2015) Daksh Skill Lab for RMNCH+A Services: Training Manual for Facilitators. Government of India, New Delhi.

Dewez JE and van den Broek N (2015) Daksh Skills Lab for RMNCH+A Services: Training Manual for Participants. Government of India, New Delhi.

Kana T, Lutton M and van den Broek N (2015) "Skill and Drills" Training in Reproductive, Maternal and Newborn Health: Mannequins and other teaching equipment, learning objectives by subject area and timetables for implementation. The Global Library of Women's Medicine, Carlisle.

Madaj B and van den Broek N (2015) Making it Happen with Data: Strengthening the collection and use of data for maternal and newborn health. The Global Library of Women's Medicine, Carlisle.

Ameh C and van den Broek N (2014) Chapter 29: Strategies to improve global maternal and neonatal health, in B. Magowan, P. Owen and A. Thomson (eds), Clinical Obstetrics and Gynecology, edn, vol. Elsevier, London, pp. 229-38.

van den Broek N and Ameh CA (2013) Chapter 16: Maternal and Newborn Health, in A. J. Magill and G. W. Hunter (eds), Hunter's Tropical Medicine and Emerging Infectious Disease, edn, vol. Saunders/Elsevier, London; New York, pp. 135-40.

ANNEX 2: Value and location of asset disposal

Total Purchase Value (£)	Facility Name	Location / User	Responsible person
5520	CAI (Child Advocacy International)	Islamabad, Pakistan	CAI, Pakistan
5520	Ridge Hospital	Accra, Ghana	Cape Coast University
5520	Tamale School of Nursing	Tamale, Ghana	Cape Coast University
5520	Cape Coast University	Cape Coast, Ghana	Cape Coast University
5520	Secondi Takoradi School of Nursing	Takoradi, Ghana	Cape Coast University
5520	CIPRB	Dhaka, Bangladesh	CIPRB
5520	OGSB	Dhaka, Bangladesh	CIPRB
5816	BCPS	Dhaka, Bangladesh	CIPRB
5520	Kibaha COTC	Kibaha, Tanzania	KCMUC, Tanzania
5520	Murgwaza School of Midwifery	Ngara, Tanzania	KCMUC, Tanzania
5816	Ndolage School of Midwifery	Ndolage, Tanzania	KCMUC, Tanzania
16560	LSTM	Liverpool	LSTM
5520	School of Midwifery	Gwagwalada, Nigeria	LSTM Nigeria
5520	School of Midwifery	Minna, Nigeria	LSTM Nigeria
5520	Nyeri KMTC	Nyeri, Kenya	LSTM, Kenya
5520	Bugoma KMTC	Bugoma, Kenya	LSTM, Kenya
5520	Kakamega KMTC	Kakamega, Kenya	LSTM, Kenya
5520	Homabay KMTC	Homabay, Kenya	LSTM, Kenya
5520	Thika KMTC	Kiambu, Kenya	LSTM, Kenya
5816	Kisumu KMTC	Kisumu, Kenya	LSTM, Kenya
5520	St Lukes College of Nursing and Midwifery	Zomba, Malawi	LSTM, Malawi
5520	Mulanje Mission College of Nursing	Mulanje, Malawi	LSTM, Malawi
5520	Malawi College of Health Sciences (MCHS)	Blantyre, Malawi	LSTM, Malawi
5520	Safdarjung Hospital	New Delhi, India	Skills Lab representative
5520	TNAI	New Delhi, India	Skills Lab representative
5520	NIHFW	New Delhi, India	Skills Lab representative
5520	Jamia Hamdard University	New Delhi, India	Skills Lab representative
5520	Lady Harding Medical College	New Delhi, India	Skills Lab representative
5520	Mpilo Hospital	Bulowayo, Zimbabwe	University of Zimbabwe
5520	Parirenyatwa Hospital	Harare, Zimbabwe	University of Zimbabwe
5520	Harare Central Hospital	Harare, Zimbabwe	University of Zimbabwe
35550	N/A	LSTM, Zimbabwe	University of Zimbabwe

Smart Guide

The Programme Completion Report is the opportunity to reflect on the entire programme, its performance, achievements, and lessons and how learning will be shared to inform future programming.

The Programme Completion Report assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with headline information on the programme and any follow up actions
Introduction and Context
Briefly outline the programme, results achieved and contribution to the overall Operational Plan and DFID’s international development objectives. Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Outcome Assessment / Brief assessment of whether the programme achieved the Outcome
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessment
Key points
Summary of response to issues raised in previous annual reviews (where relevant)
Recommendations for future programmes
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case. Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme represented value for money? / Overall view on whether the programme was good value for money
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Quality of risk management over the life of the programme. How were risks managed, the degree to which they were realised and/or mitigated.
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / Could DFID be a more effective partner
Asset disposal and value obtained by DFID / How were assets managed throughout the programme? How have they been (or will they be) disposed to get maximum value?
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the programme / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc.) / The Annual Review process