Annual Review - Summary Sheet

Title: Work in Freedom Programme
Programme Value: £10.5m		Review Date: July 2016
Programme Code: 203857	Start Date: July 2013	End Date: December 2018

Summary of Programme Performance
Year	2013-2014	2014-15	2015 (July)	2016
Programme Score	A	A	A	A
Risk Rating	Medium	Medium	Medium	Moderate

Summary of progress and lessons learnt since last review

Work in Freedom is DFID’s main programme directly tackling modern slavery and human trafficking, and contributes to the UK’s Modern Slavery Strategy and the Prime Minister’s commitment to tackle modern slavery.

In the past year, the programme has made good progress across all five main outputs. In excess of 200,000 beneficiaries have been reached, surpassing targets for this year, and surpassing overall programme targets for reaching women in their communities, before they potentially migrate. Specific results achieved include:

- Over 170,000 women have benefited from training to help them make informed migration decisions, reducing their risk of being trafficked from India, Nepal and Bangladesh;
- Over 200 recruitment representatives have been trained on fair recruitment in Nepal, India and Lebanon, and international guidelines have been drafted;
- Over 29,000 workers have been organised in migrants’ destination areas to help them better access services, provide peer support and lobby for improved working conditions; and
- Policy recommendations and technical assistance have informed new legislation to regulate recruitment agents in India, and advocate against discriminatory migration bans on women in Nepal.

Research activities are well underway - by both the London School of Hygiene and Tropical Medicine (LSHTM) and the ILO – and are yielding results. We now know more about the prevalence of migration and trafficking in the programme’s target communities, how people are recruited and on attitudes and levels of awareness of exploitation amongst employers and recruiters.

Teams have aimed to address most issues identified in the previous DFID Annual Review, in particular:
1. Improving quality assurance of community level interventions (though more work is still needed);
2. Developing strategies for each of the workstreams/outputs;
3. Increasing attention to work in the garment sector; and
4. Improving communications, for example producing 2-pagers and country briefs (but more work is needed over the coming year as new research from the programme becomes available).

While the programme has made good progress, a number of challenges remain, such as devising strategies to change the norms of informal recruiters who can increase women’s vulnerability to exploitation. Risks include the potential impact of worsening regional instability or conflict and a lack of political support in certain source and destination areas for tackling this issue. Management issues include the need to extend contracting through to the end of the programme and the need to improve communication and coordination between the programmes’ sub-contracted partners.

Summary of recommendations for the next year

ILO to prioritise programme scope - in particular building on the programme’s comprehensive law and policy strategy to identify targeted areas to focus action, by sector and country.
ILO and LSHTM to improve communications – updating the Communications and Research Uptake Strategy and delivering increased, targeted activities over the coming year.
ILO and LSHTM to build stronger, more systematic links between research results and programme intervention design/revisions, and document these to capture how the programme is adapting and learning (so that the design of similar, multi-dimensional programmes in future can benefit from the experience of delivering Work in Freedom).
ILO to continue to improve quality assurance and consistency of activities at community level.
ILO to revise the Fair Recruitment strategy, activity and emphasis of this programme, in particular taking account of ways to address informal recruiters and understand feasibilities of reducing fee charging to workers.
ILO, DFID, and LSHTM to finalise revised logframe and Theory of Change – taking into account lessons learnt to date.
ILO to strengthen management of the programme, particularly:
  1. strengthen partnerships and finalise contracts to the end of the programme;
  1. improve coordination between sub-contracted delivery partners to build understanding of objectives and activities under each workstream, and how the overall programme adds up to a whole.
  1. Strengthen links between ILO Geneva and ILO Delhi on fair recruitment and communications.

A. Introduction and Context

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/3893486.odt
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/4346622.xlsx

    (All published information on Work in Freedom: https://devtracker.dfid.gov.uk/projects/GB-1-203857)

Outline of the programme
The UK is providing £10.5 million from 2013–2018 to the ILO and the LSHTM to help prevent the trafficking of women and girls from South Asia into the domestic and garment sectors, and to support women’s economic empowerment by helping them to migrate safely to decent jobs. The programme targets specific, known trafficking routes, where women and girls from Bangladesh, India and Nepal are trafficked internally within South Asia and to the Middle East (Jordan and Lebanon). It supports interventions across the ‘trafficking chain’: building capability of women at source and destination, strengthening standards of recruitment agencies and employers, supporting policy development and enforcement, and building better evidence.

The original impact of the programme is reduced incidence of trafficking of women and girls within and from India, Bangladesh and Nepal, into the domestic and garment sectors, through economic, social, and legal empowerment. This is being revised to focus on the reduction of vulnerability of women and girls to trafficking and exploitation to better reflect the theory of change of the programme and more measurable indicators. The outcome is that women are empowered to make informed migration decisions and an enabling environment is created for their safe migration into decent work.

Context
Human trafficking is an internationally recognised crime and a human rights violation. To date, international efforts on trafficking have focussed largely on sexual exploitation whereas labour trafficking, which is far more prevalent, has been comparatively neglected. In addition to judicial efforts which seek to catch and convict traffickers, more needs to be done to: prevent trafficking and labour exploitation before it occurs; protect vulnerable groups (especially women and girls); and promote migrants workers’ rights to dignity, fair wages and decent working conditions.

Over half of trafficking and forced labour victims come from the Asia Pacific and Middle Eastern regions (11.7 million of an estimated 21 million worldwide). Approximately 4 million originate from Bangladesh, India and Nepal[1].  An estimated 600,000 trafficking victims are in the Gulf States and Middle East, with a significant proportion of workers migrating from South Asia to work in the domestic and textile sectors. Evidence shows that women and girls from South Asia are particularly vulnerable; low levels of education leave many with precarious and poorly paid jobs at the lowest end of the labour market.
[1] ILO Global Estimate on Forced Labour (using regional level data), 2012.

Labour migration has the potential to lift people out of poverty, particularly women who lack economic opportunities at home. This programme seeks to interrupt the cycle of abuse and exploitation for the most vulnerable women workers and girls, and demonstrate an alternative model for migrant women’s social and economic empowerment. As part of this, it works with multiple stakeholders to shift incentives for recruitment and with employers to have more responsible business practices.

Detailed data on the numbers of people in South Asia and the Middle East migrating (particularly women and girls) and falling victim to trafficking is limited. A multi-sector approach and stronger evidence base are needed to measure the scale and nature of the problem, and what works to prevent it.

The Work in Freedom (WiF) programme contributes to the UK Aid objective of tackling extreme poverty and helping the world’s most vulnerable. It delivers on DFID’s Strategic Vision for Girls and Women in two priority areas - economically empowering girls and women, and allowing them to live free from violence. The programme responds to priorities in the Asia Regional Business Plan, and contributes to the UK Modern Slavery Act and Strategy, and regional programming on migration.

The programme operates in regions that are subject to instability. Over the past year, the programme’s destination countries of Jordan and Lebanon have continued to experience large inflows of refugees from Syria in the wake of the Syrian conflict. The extent to which this will affect labour markets, opportunities and/or conditions for migrant workers from Nepal, Bangladesh and India remains unclear and we continue to monitor the situations. (See Section E on Risks for more).

## B: PERFORMANCE AND CONCLUSIONS

Annual outcome assessment
The programme is on track to achieve the intended outcome of “women are empowered to make informed migration decisions and an enabling environment is created for their safe migration into decent work”. The external Advisory Board reports that, particularly over the past year, the programme is making substantive contributions. Their assessment is that by the time of its completion, ‘that Work in Freedom will have played an important role in increasing our collective understanding of how exploitation in its areas of focus actually occurs and how it can be effectively addressed.”

Good progress has been made against outcome level indicators in the past year, for example:
- 170,000 people have been helped to enhance their knowledge and skills (Outcome Indicator 1; no milestone);
- New benchmarks have been developed to allow recruitment agencies to develop business practices in line with fair recruitment standards (Outcome Indicator 2);
- 4 new or revised legal or policy initiatives have been developed that help to protect the rights of women migrant workers including new draft domestic workers legislation, regulation of placement agencies, and domestic workers sectors skills policy in India; reduction of age ban of women migrant workers in Nepal (Outcome Indicator 4; milestone 3);
- 10 reports or papers have been published that can contribute to helping policy makers and practiioners improve the effectiveness of their work in this field (e.g. ILO guidelines for overseas employment of domestic workers; LSHTM Research Briefing Notes offering initial findings from surveys in Nepal and India) (Outcome Indicator 5; milestone is 2 papers submitted to journal- but was not possible given delay in start of research activities due to delay in programme start up.)

Some outcome indicators intentionally do not have interim milestones, for example Outcome Indicator 3 on number of women whose rights are defended or upheld at destination (this has not yet been measured). The programme logframe, including outcome indicators and milestones, is currently being revised to better reflect the programme, and ensure appropriate and measurable milestones are in place.

There is good potential for the programme to influence global advocacy on forced labour and reduce vulnerability to human trafficking and forced labour of women migrant workers over the long term. However, a strong focused approach to interventions is required, with emphasis on consolidating and communicating lessons learned in order to achieve impact at scale.

Overall output score and description: A

The programme has made good progress across all of the outputs, and scores an A.

Results achieved over the past year include:
Output 1: Cumulatively, over 210,000 women, girls and their families in India, Bangladesh and Nepal have benefitted from outreach on how to make informed migration decisions;
- Output 2: 275 staff of recruitment agencies have been engaged to improve understanding of fair recruitment practices;
- Output 3: At least 10 policies relating to labour rights have been targeted to improve protection of women migrant workers;
Output 4: Over 29,000 workers have been organised in migrants’ destination areas to help them better access services, provide peer support and lobby for improved working conditions; and
Output 5: New and better evidence is being generated on forced labour and trafficking of women and girls within and from South Asia and on effective preventive measures.

ILO and LSHTM have reported this year on results achieved in March 2016, which aligns with their reporting cycles and sub-contracted reporting. The current logframe milestones fall in December. This annual review therefore provides the targets for both December 2015 and December 2016, and provides an assessment of progress towards the latter, based on results reported in annual reports, and other evidence up to and including July 2016.

Gender
The programme directly targets women as beneficiaries at source and destination, recognising that they are particularly vulnerable to trafficking, exploitation and abuse. However, to do this, the programme also targets husbands, fathers, and families at source, as they are often involved in decision making about whether or not, or how, a woman may migrate. At destination, the programme reaches both men and women, who access resources available at the migrant resource centres. Initial research results from Nepal and India also give data on both male and female migrants, their destinations, and factors affecting their experience. More results are expected after indepth analysis by December. The programme is also aiming to understand how women’s social, economic and political empowerment may decrease their vulnerability to trafficking; and how the programme may contribute to those changes.

Key lessons learned include:
- Context matters. Differing approaches are needed for each sector and location, and also need to take into account poverty, gender, disaster/conflict – and the capacity of local delivery partners. A one size fits all approach will not work.
- Community level interventions, such as pre-departure training, should be tailored to the particular needs of local women, and are not sufficient on their own. (To be more effective, outreach must be joined up with other local services, and be complemented by work with recruiters, government and employers);
- Interventions focusing on systemic policy changes are important to reducing vulnerability to forced labour with potential for further reach than targeted activities if policies are implemented.
- Tackling recruitment needs to take into account the informality of recruitment agents (often members of the community or known to families), complementing activities targeting registered agents.
- Migration bans by source country governments can be counter-productive and encourage women to take risky and expensive methods to reach their destination.

Key actions
Key recommendations are listed on the summary sheet above. ILO and LSHTM should respond in writing on plans to address recommendations by 15 September 2016.

Has the logframe been updated since the last review?
The logframe is in the process of being updated, but has not yet been finalised (so this review reports against the previously approved version). The logframe is being updated to: refine impact and outcome indicators and milestones to ensure they are measurable and reflect latest lessons emerging from the programme; ensure that milestones are in line with the annual reporting and review period; and ensure data against indicators can be collected.

## C: DETAILED OUTPUT SCORING

Output Title	Potential women migrant workers and their families have increased knowledge and awareness, information and skills that will help them make informed decisions on migration.
Output number per LF		1	Output Score	A+
Risk:		Moderate	Impact weighting (%):	30
Risk revised since last AR?		Revised from ‘medium’ to reflect DFID’s new risk categories.	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones (Dec 2015)	Milestones (Dec 2016)	Progress / (Mar 2016)
1.1 No. of potential women migrant workers, girls and their families who benefit from outreach activities (courtyard meetings, street dramas etc.) on how to make informed migration decisions.	60,000 (20,000 Nepal, 20,000 India, 20,000 Bangladesh) / Contracts in place for community based interventions in Bangladesh	50,000 (17,000 Nepal, 17,000 India, 16,000 Bangladesh)	Targets exceeded: / 211,400 additional women, girls and families have benefitted since the last annual review.
1.2 No. of women and girls who benefit from pre-decision orientation (1,5-2 hour counselling, 2 and/or 7 day pre-decision programmes).	25,000 (8500 Nepal, 8500 India, 8000 Bangladesh)	25,000 (8500 Nepal, 8500 India, 8000 Bangladesh)	Targets exceeded: / 170,600 received pre decision orientation since the last annual review.
1.3 No. of women who receive vocational skills training for local or overseas employment out of which at least 75% have certificate.	3000 (1000 India, 2000 Nepal); / In India and Nepal curriculum for Domestic Worker training course is revised; / At least one Training of Trainers held in each country.	4000 (2000 India and 2000 Nepal)	Partly achieved / - 1,166 women have been skilled / - Political factors in India and Nepal delayed governments launching the new curricula, affecting reach. ILO mitigated this by delivering training through others in India. Curricula amendments now completed in Nepal & Bangladesh, and expected later this year in India. Training of Trainers held in Nepal; will occur in Bangladesh in 2016/17.
1.4 Master trainers, peer educators, social mobilizers/community leaders have an increased understanding on issues related to gender, migration and trafficking	GAATW refresher training held and at least 60% of participants with increased knowledge on issues related to gender, migration and trafficking.	At the country-level, WiF community based organizations have one meeting a year to discuss common objectives, lessons learned etc.	Partly achieved / 450 master trainers/peer educators received training. Training methods ensured that all participants gained a better understanding on issues related to gender, migration and trafficking. Changed plans in research and evaluation meant that proposed indicator could not be measured.

Key Points
This output primarily reaches women and girls, families and communities with safe migration messages in source communities. Through peer educators, the project makes door to door visits and holds educational sessions with potential woman migrant workers.

This output scores A+. The bulk of work and spending in this output is on community outreach activities (outputs 1.1 and 1.2), where targets for the whole programme have been exceeded. Strong partnerships and work by partners has led to greater reach than originally expected. Output 1.3 is off track due to domestic political factors outside ILO’s control, but ILO has made promising progress given circumstances.

ILO and partners have made good progress on in-depth ‘pre-decision’ trainings, and more tailoring of training to suit communities (responding to recommendations in last year’s annual review). Partners report, anecdotally, that the activities are leading more people to take protective measures (e.g. registering travel with authorities, etc), and reduce cases of ‘missing’ migrants. Slow progress on output 1.3 has been due to political factors delaying the setup of the Domestic Work Sector Skills Council in India. However training is now occurring, and ILO will be providing technical assistance to the Council to strengthen the curriculum. Training in Nepal was held up by a Nepali administrative ban on foreign employment of domestic workers. ‘Master trainers’ and peer educators have been trained, but the original milestone cannot be assessed as research plans to gather this data were changed. The revised logframe will reflect more appropriate and measurable milestones.

A significant challenge is that partners delivering community level activities in Nepal, Bangladesh and India deliver consistent and high quality interventions while also responding to local needs. ILO should continue to focus on quality assurance mechanisms, such as programme design, monitoring and coordination between partners. Partners have also reported a desire for projects to be longer, in order to deliver more sustainable outreach, and to be better coordinated with other services and needs in the area (for example linking to social benefits or employment/skills services).

Summary of responses to issues raised in previous annual reviews
1. ILO has continued to streamline and focus activities via strategic partnerships, improving efficiency.
2. ILO improved quality assurance and consistency of activities, and this should remain an area of focus. Lessons from community interventions were reviewed with partners in July 2016, with positive feedback from the Advisory Board.
3. The programme developed skilling opportunities for garment migrant workers.

Areas that still require consideration:
1. ILO should clarify explicitly how the programme engages with men and boys to help make safer migration decisions for women.
2. ILO needs to clarify contract duration with community and local partners (see Section F)
3. ILO should consider how it will communicate key results and tools (after testing is completed) with government and NGO actors to scale up successful activities.

Recommendations
1. ILO should continue to improve quality assurance and consistency of activities at community level – ongoing.
2. ILO should communicate clearly the key lessons emerging from community activities – to all programme partners at community level, to enable them to act on them, and in time to wider partners working in this area – by January 2017.

Output Title	Recruitment agencies adopt recruitment practices based on international standards and are subject to improved monitoring and enforcement.
Output number per LF		2	Output Score	A
Risk:		Moderate	Impact weighting (%):	15
Risk revised since last AR?		Revised from ‘medium’ to reflect DFID’s new risk categories.	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones (Dec 2015)	Milestones (Dec 2016)	Progress (Mar 2016)
2.1 Number of recruitment representatives that benefit from ILO and partner training on Fair Recruitment.	Consultations on recruitment baseline held in four target countries. 45 recruitment representatives trained (15 Nepal, 15 India, 15 Lebanon).	Ciett adopts revised code of conduct. 100 Recruitment representatives trained (15 Jordan; 30 Nepal; 30 India; 25 Lebanon.	Targets exceeded / - 275 recruitment representatives reached / - Ciett code of conduct revised / - Consultations on recruitment baselines held
2.2 Number of specific enforcement measures taken by state authorities to ensure compliance by recruitment agencies in source and/or destination countries.	Capacity building for Governments on how to better regulate recruitment / 20 enforcement measures taken.	25 (cumulative)	Partly achieved / - 20 (cumulative)

Key Points
This output scores A. Training targets have been exceeded. ILO has provided technical support to governments in Nepal and India to improve effectiveness and accountability of recruitment regulation and initiated dialogue in Lebanon and Jordan. Four innovative recruitment practices are being tested to assess replicability. Draft Fair Recruitment Guidelines have been developed, which are due to be published later this year and set out clearly the ways in which agencies can demonstrate ethical recruitment practices.

In Nepal, there has been progress from the Government in reducing fees (Free ticket free visa policy), with employers paying instead, thereby releasing the worker from substantive debt. There is also increased interest from brands in the UK to tackling issues of fair recruitment and slavery in their supply chains, and Work in Freedom have been delivering some successful advocacy work with UK businesses on this, for example hosting an event attended by over 100 business representatives and stakeholders in June 2016.

However, some challenges remain, in particular the informality of the recruitment sector, (which includes sub agents, family or local community members). For example, the programme has documented in parts of India, only 5% of migrant domestic workers were employed through a formal or informal recruitment intermediary (forthcoming), the remaining portion of which are recruited through word of mouth and personal connections. .

In addition, there is mixed response on the principle of employers, not workers, paying recruitment fees. Recruiters see few incentives to change their current business model.. Experience from the programme suggests that successful approaches to achieve this change over time include raising awareness of the impacts on migrant workers, government regulating against this, demand from businesses and employers and showing recruitment agents that there are long term business benefits).

Given the informality of part of the recruitment chain, the programme should consider how to balance activities to reach the formal sector as well as informal agents. There is also a need for more understanding of the efficacy of a ‘no fees’ approach. ILO and partners should consider reviewing the current fair recruitment workstream strategy , and we recommend these questions form part of the planned Mid-Term Review.

Summary of response to issues raised in previous annual review/s:
ILO has acted on the recommendations from DFID’s last annual review in particular producing a detailed strategy, improving coordination between partners working on this output and agreeing to adapt targets in future logframes to reflect lessons learnt.

Recommendations
ILO to make recommendations to DFID on the future strategy, activity and emphasis of this output – by January 2017.

Output Title	Women migrant workers in domestic work and garment sectors enjoy better collective representation and support services and employers have greater knowledge of workers' rights.
Output number per LF		3	Output Score	A
Risk:		Moderate	Impact weighting (%):	15
Risk revised since last AR?		Revised from ‘medium’ to reflect DFID’s new risk categories.	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones / (Dec 2015)	Milestone / (Dec 2016)	Progress / (Mar 2016)
3.1 Number of women migrant workers in domestic work and garment sector who are organised.	One regional training on how to organize domestic workers held; 2100 workers organized (1800 India; 300 Lebanon)	2200 workers organized (1800 India; 200 Lebanon; 200 Jordan) / [annual, not cumulative]	Achieved. / 29,300 reached, surpassing the cumulative target for 5 years (8,500). 21,000 female domestic workers in India, 7,800 garment workers (5,640 female, 2,160 male) in Jordan unionised. Exploration for support for domestic workers in Jordan and Lebanon underway. Regional learning workshop with domestic worker organisations held.
3.2 Number of women workers and/or their employers who access information and/or get improved support through associated services provided by NGOs, Governments and Trade Unions (including new technology component).	5500 (2000 Lebanon; 1500 Jordan; 2000 India) / [annual, not cumulative]	5500 (2000 Lebanon; 1500 Jordan; 2000 India) / [annual, not cumulative]	Partly achieved / 51,300 reached. Overall targets for five years (16,000) were surpassed in Jordan and India. Work in Lebanon in process. In India, 21,000 women trade union members gather weekly. In Jordan, 31,000 migrant workers (19,000 female; 13,000 male) accessed resource centres for support.

3.3 Proportion of employers of domestic and garment workers with new knowledge and understanding of migrant workers' rights and fair recruitment practices.	i) Sensitization Campaign for employers of domestic work launched and codes of conduct developed for employers of domestic workers in Lebanon and India. (ii) Direct capacity building with employers of garment workers and brands on recruitment practices in Jordan.	200,000 employers of domestic workers reached through sensitization campaign in India and Lebanon; 50 employers and brands of garment workers attend ILO workshops on fair recruitment practices	Partly Achieved/ / - Sentisiation campaigns underway in Lebanon based on results of employers survey. / - In Jordan, three consultations held with FSI in garment sector. WiF participated at the Buyer’s Forum of Better Work in 2015 and 2016. Over 100 business reps and stakeholders attended a Work in Freedom/Institute of Human Rights and Business business forum in July 2016. (See Output 2). / - Numbers of persons reached by advocacy campaigns not yet assessed.

Key Points
Overall, excellent progress has been made towards all of these indicators, with some overall targets for the programme surpassed (organisation of workers, workers accessing services), particularly in India, and Jordan. However, more difficulties have been faced in Lebanon in the domestic workers sector. This output scores an A.

The number of domestic workers unionised in India has already exceeded overall targets, and women workers we met in Delhi reported positive benefits from the union in soliciting increased wages and day off from employers, support from peers, and support for accessing justice for victims of sexual abuse. However, a challenge still exists on how best to reach stay-in workers.. In Jordan, garment workers were enrolled in unions through the workers’ centre. Work in Lebanon is still under exploration.

A large success for this objective has been the expansion and operation of the Al-Hassan Workers Centre in Jordan. This workers centre is in one of the main industrial zones and is jointly funded by Work in Freedom, Swiss Development Corporation, and workers’ contributions. This centre has reached 31,000 migrant workers, supporting them to have access to information and resources, and to have mutual support and exchanges with others. An independent study conducted by Columbia School of International and Public Affairs documented impact of the centre on workers, including improved self-esteem and self-dignity; increased skills (and willingness to invest finances to achieve this); and space for expressing personal and cultural identity. However, issues such as psychosocial or legal support, and gender based violence (GBV) were not raised or discussed. The Centre should explore how to provide necessary information and support services to resource centre users. The World Bank and European Union are considering scaling up this model in the Qualifying Industrial Zones (QIZs), in particular for support to Syrian and other refugee workers. The programme is currently exploring the viability of workers centres for garment workers in India. Other services which are being piloted include a mobile phone component to provide SMS based professional rights and career counselling services for migrant garment workers, through a partnership with Gram Tarang (through Oniondev-Gram Vani).

Advocacy campaigns in Lebanon and Jordan included billboards and media spots targeting issues that emerged from the employer surveys (e.g. workers seen as unclean or not bright). The India campaign should be launched once employers’ survey is finalised. Good progress has been made on reaching business actors for strengthening socially and ethically responsible business practices, and links closely with Objective 2 on fair recruitment.

DFID earlier in the year raised questions as to whether migrant workers in Lebanon or Jordan may be affected by the compacts developed with these countries as part of the Syria Conference in February 2016. Initial monitoring suggests that South Asian migrant garment and domestic workers have not yet been displaced due to low numbers of Syrians and employers signing up to these schemes in these sectors. However, ILO and partners should continue to monitor and assess this.

The establishment of national programme officers in Lebanon and Jordan (at 50% each) has facilitated progress on this objective, and was reported favourably by international partners working. DFID has not yet visited the field sites in Lebanon or Jordan, and should make a visit in the near future.

Summary of responses to issues raised in previous annual reviews (where relevant)

Good progress has been made on two of the three issues raised in the previous review. ILO has developed a ‘worker organising’ strategy analysis issues at destination and way forward.

Activities using mobile phone technology have been identified, although the programme should clarify if more or other efforts could be integrated, through for example the workers centres or other means and in particular to reach live in workers.

On the third issue regarding clarification of contracts with delivery partners, clarification of work and partnerships to end of programme needs to be established.

Recommendations
1. ILO should aim to integrate further support and referral services in approaches at destination, including legal or access to justice, psychosocial counselling and services for victims of gender based violence. It should also explore how to more effectively reach live-in workers.
2. ILO should clarify what additional mobile phone innovations may be considered in the programme.
3. ILO needs to clarify contracts with delivery partners for this component.
4. ILO and DFID to revise logframe indicators and milestones (as per other outputs), in part as progress has already exceeded expectations.

Output Title	Policy makers have knowledge on legal and policy reform processes to better protect migrant workers' rights.
Output number per LF		4	Output Score	A
Risk:		Moderate	Impact weighting (%):	10
Risk revised since last AR?		Revised from ‘medium’ to reflect DFID’s new risk categories.	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones (Dec 2015)	Milestone / (Dec 2016)	Progress / (Mar 2016)
4.1 No. of labour and other law enforcement officers trained under WiF programme who have increased knowledge on labour and criminal laws relating to trafficking prevention	400 (700 cumulative)	400 (1100 cumulative)	Partly achieved, but agreed with ILO. / 160 (280 cumulative) / This indicator was discontinued after last year’s annual review following recommendations by the Advisory Board and DFID. A new indicator is now included in the revised logframe currently being finalised and approved. Despite this, 100 law enforcement and immigration officials were trained in Bangladesh in November 2015, and a training manual was produced. And 60 Indian law enforcement officials were trained in May 2015.
4.2 No. of recommendations, orders, and notifications made to improve policies or programmes.	2 South Asia	2 South Asia (4 Cumulative) / and 2 Middle East	Achieved / 3 policy briefs and 3 studies were produced. ILO has provided technical assistance to the governments of Nepal, India and Bangladesh in particular, across various trafficking and migration related policy and regulatory reforms. At least 10 policies were targeted at source, and further policies at destination will be targeted in 2016.

There has been good progress on this output. The first indicator is off track, yet only due to changes of approach agreed subsequent to last year’s review. Reoriented activities are on track. The second indicator is on track, and there are indications that it has successfully influenced positive policy change, such as the Nepal age ban legislation. Overall, this justifies a scoring of “A”.

Key Points
.

Following recommendations from the Advisory Board and discussion with DFID, the component led by UN Office on Drugs and Crime (UNODC) on training labour and law enforcement officers (output 4.1) was shifted to develop policy materials to achieve further impact.  There had been questions on how appropriate and scalable the training and advocacy events were. As a result, UNODC is focusing on policy influencing strategies including policy papers and round table discussions. Over the past year, UNODC’s policy papers and research have been quite broad..  More clarity is needed to refine the focus, objectives and extended impact of this work.

For Output 4.2, ILO and partners focused on influencing the Governments of India and Nepal to assist migrant workers to have appropriate knowledge, and remove discriminatory bans on women’s migration. Targets were met, however, more work is needed in Bangladesh, Lebanon and Jordan. Achievements inlcude:
In India, ILO has provided technical assistance to the national and state governments for example on new draft Domestic Workers Policy, Placement Agencies Regulation bill in Jharkhand. Suggestions to the Delhi Government on social protection which were taken on board, and a policy brief on domestic work in India was used by the Joint Secretary, Ministry of Labour and Employment while sharing views with workshop participants (including trade unions and academics) in April 2016.
- In Nepal, ILO provided inputs to the Foreign Employment Act, advocating for reducing the age ban on female migrant domestic workers and providing new guidelines on overseas domestic work. ILO produced a policy paper and brief on the harmful effects of the age ban which helped inform discussion. The age ban was subsequently reduced (from 30 to 24 years of age), although it is difficult to measure the extent of ILO influence in this. In destination sites: In Jordan, ILO is preparing inputs to the Ministry of Justice for its Anti-Trafficking Law and Action Plan, and to the Ministry of Labour on managing shelters or resource centres for migrant domestic workers. In Lebanon, WIF is scoping various measures to explore alternaitves to the sponsorship system, including a study on the introduction of an insurance system for employers of domestic workers, which could reduce incidence of workers being held against their will.
- Regionally, ILO and partners influenced the development tof the SAARC (South Asia Association for Regional Cooperation) plan of action for migration, due to be discussed at the annual SAARC meetings later this year..\ A regional policy brief on Women’s Mobility and Domestic Work was developed and shared with partners in January 2016.

While the team should be congratulated for a comprehensive and wide understanding of the relevant laws and policies, moving forward the programme needs to prioritise specific areas of work in order to achieve impact, and avoid the danger of efforts being dispersed too widely. Plans are now to focus on: domestic worker protection (new domestic worker and anti-trafficking policy) and rights of overseas garment workers in India; the age ban and Foreign Employment Act in Nepal; migration policy in Lebanon (the sponsorship system and insurance scheme for employers); and the anti-trafficking policy in Jordan.  The law and policy strategy will need to be revised to reflect this, and how evidence products and work with partners and advocacy networks will help achieve this.

The law and policy output is important for the programme to achieve extended impact. To reflect this, DFID proposes increasing the weighting of this output to 15% in future.

Similar to other output areas, ILO needs to better inform partners of the overall picture of Work in Freedom’s activities for this objective, and better facilitate networking between partners.

Summary of responses to issues raised in previous annual review/s:
The team have done further work on analysing the Theories of Change and assumptions behind interventions in this output area. There has been significant change to output targets to reflect improved understanding and effectiveness surrounding how to best influence policy and legal frameworks. Strong progress has been made in developing greater influencing capacity among relevant organisations, and in developing policy briefs and studies in the area to influence policy makers and law enforcement officials.

Recommendations
1. ILO should finalise the policy influencing and law enforcement strategy for this workstream, with a clear prioritisation of effort - by 15 September 2016.
2. ILO to clarify with UNODC the focus and impact of revised programme activities and ensure interventions deliver the most effective outcomes - by 15 September 2016.
3. ILO and DFID to increase the weighting for this output from 10% to 15% to reflect the potential to achieve extended impact.

Output Title	New and better evidence is available on labour trafficking of women & girls within and from South Asia and on effective preventive measures.
Output number per LF		5	Output Score	A
Risk:		Moderate	Impact weighting (%):	20
Risk revised since last AR?		Revised from ‘medium’ to reflect DFID’s new risk categories.	Impact weighting % revised since last AR?	No

Indicator(s)	Milestone / (Dec 2015)	Milestone / (Dec 2016)	Progress / (Mar 2016)
5.1 No. and quality of research papers published on topics including labour migration from south Asia to Middle East and within India, recruitment and employer attitudes and behaviour.	One qualitative baseline study on recruitment published; Quantitative baseline studies on employers of domestic workers in Jordan, Lebanon and India published; One quantitative baseline study on employers of garment workers in Jordan published. One border survey completed in Nepal.	No milestone was given as no study was anticipated at this time.	Mostly achieved Qualitative 5 studies published: report on age ban in Nepal, Indian domestic workers experience, law and policy baseline in Jordan, and employer surveys in India and Jordan. Law and policy baseline in Lebanon planned for release in September 2016. / As reported last year, plans for the border survey were dropped due to methodological limitations.
5.2 Three mixed-methods studies strengthen the evidence base on forced labour, trafficking prevention and safe migration.	Baseline survey (India) and Nepal cross-sectional survey and baseline qualitative data collection completed	Follow-up study of Nepalese female migrants; process data collection	Achieved: / Cross-sectional surveys were completed in Nepal. Initial rounds of qualitative data collection in India and Bangladesh, and full qualitative data completed in Nepal. Round two qualitative studies have commenced in Bangladesh. Formative research paper on Nepal drafted.
5.3 New, evidence-informed conceptual framework, indicators, methodologies and study instruments inform research and programming for trafficking prevention / safe migration.	Process data protocols; analysis plans (qual, quant).	Endline protocols (1), survey instruments (2), survey data analysis plans (3)	Achieved: / Research and evaluation protocols for all three country studies have been completed and ethics approved. Survey instruments designed in India and Nepal. Data analysis plans completed and underway.

5.4 Research results communicated to various stakeholders to foster improved policies, programming, research and academic knowledge on safe migration, labour trafficking and effective trafficking prevention tools.	Policy Briefs (1 - 3); Local summary baseline and case series reports; Submission of preliminary findings to academic conferences, workshops, and seminars / (Strategy for research uptake and dissemination – Milestone 2014)	Policy briefs on interim results (1-3); Presentations at academic conferences, workshops, and seminars; Submission of findings and journals	Achieved: / Communication 2 pager and 4 pager on the overall and country focused LSHTM led research and evaluation produced. Draft policy briefs on preliminary results from India and Nepal produced. Conference papers on conceptualisation and measurement of forced labour and trafficking have been presented. / Research uptake draft strategy produced but under revision to have joint comms strategy for programme.

Key Points

Good progress has been made on most milestones under this output, with plans to achieve full milestones by end of year, resulting in an overall score of A.

Indicator 5.1 refers to ILO activities under this output. ILO produced a research strategy detailing key themes, existing papers, gap analysis and planned future studies. Five studies were completed during this review as outlined above.

Indicators 5.2 and 5.3 refer to the LSHTM component of the programme to conduct research and evaluation in Nepal, India and Bangladesh. This work is on track to reach milestones.

In Nepal, LSHTM and partner Centre for the Study of Labour and Mobility (CESLAM) at Social Science Baha completed surveys and qualitative interviews of prospective migrants (500 women) and returnees (300 women). Howeveer, there were challenges in reaching women migrants in the longitudinal study as planned contact details are no longer in use. The team are following up with ILO and contacts in source communities in efforts to find alternate contacts. Preliminary results suggest at least 1/3 of households in study have at least one member working internationally and women were more likely to have migrated multiple times. Research paper has been drafted and undergoing revision. Reports expected in September.

In India, LSHTM work with partner Centre for Women and Development Studies (CWDS) and ILO implementing partners SEWA in Odisha. Census data collection was completed by Jan 2016 (4,600 individuals); First round of semi-structured interviews and interviews with policy makers have taken place.. Preliminary findings suggest 45% households had at least one member who migrated; 12% intended to migrate in next 12 months; and labour migration is less prevalent amongst the poorest and the wealthiest household quartiles. Reports are expected by December 2016.

In Bangladesh, LSHTM are working with the partner Drishti Research Institute. The first round of qualitative interviews have been completed with 40 women, including 8 returnees.

In country research partners rated on-the-ground relationships and partnerships with LSHTM country focused staff as excellent.

Indicator 5.4 relates to communication plans and materials. LSTHM developed very useful and easy to read 2 pager and 4 pagers.. ILO should seek to use a similar model for its communication materials.

The team shared draft policy briefs. More detailed findings will emerge between September and December 2016 after analysis. LSHTM should update these briefs at this time.

LSHTM and ILO are working to revise the research impact strategy.

The Advisory Board highlighted the need to ensure research findings inform the programme to ensure ‘real time’ research and evaluation, and that interim findings can help the programme adjust or refine as necessary. In order to systematise this, DFID, ILO and LSHTM will discuss research findings at quarterly meetings and the implications for programme activities. Discussions will also take place at national levels with partners.

Summary of response to issues raised in previous annual review/s:

LSHTM has made stronger articulation of the overall research and evaluation narrative in the evaluation protocol and 2 and 4 pagers. Policy briefs and research reports should continue to do this so that lessons across the programme (as opposed to only country specific findings) are also understood.

While a draft research uptake strategy has been completed, ILO and LSHTM need to do to make it an integrated research uptake and communications strategy. This should include thought to how findings may be used to influence priority policies targeted.

DFID, ILO and LSHTM have all been slow to finalise the logframe, in part because of changes suggested by the mid-term evaluation and challenges in identifying meaningful and measurable impact indicators. It is in final stages of revision and should be completed by 15 August 2016.

Recommendations
1. ILO and LSHTM, with support from DFID, to ensure stronger links between research findings and informing programme intervention design or revisions through quarterly discussions, and country specific discussions with partners. Any associated changes in design should be documented.
2. ILO and LSHTM to revise research uptake and communications strategy by 15 September 2016.
3. ILO to strengthen communication materials for programme, and LSHTM to include updated findings in policy briefs and communication tools.
4. ILO, LSHTM and DFID to finalise revised logframe by 15 August 2016.
5. ILO to produce revised Theory of Change diagram and short narrative by 15 September 2016.

Output Title	Work in Freedom is initiated and managed effectively, in line with DFID, ILO and LSHTM rules and procedures for aid effectiveness and financial management.
Output number per LF		6	Output Score	B
Risk:		Moderate	Impact weighting (%):	10
Risk revised since last AR?		Revised from ‘medium’ to reflect DFID’s new risk categories.	Impact weighting % revised since last AR?	No

* to be revised to 1 meeting per year in updated Logframe.
Indicator(s)	Milestones / (Dec 2015)	Milestones / (Dec 2016)	Progress / (Mar 2016)
6.1 Work in Freedom Programme is approved and launched by Ministers; DFID partnerships established with ILO & LSHTM, and effective internal programme management and oversight arrangements are put in place.	Annual Review (Feb 15) & logframe revised; Independent Mid-Term Review (Oct 15). Quarterly update meetings with DFID, ILO & LSHTM; DFID monthly partner meetings & regular updates with country offices	MTR recommendations implemented and light touch Annual Review (Feb 16). Ongoing quarterly update meetings with DFID, ILO and LSHTM; DFID monthly partner meetings and regular updates with country offices	Partly achieved / - Mid Term Review (MTR) evaluation due to begin in summer 2016, after being delayed to first conduct an evaluability assessment (which completed early 2016). Programme delivery is not affected. / - Regular meetings continue, though not always monthly.
6.2 Strategic value of the Work in Freedom programme and approach is recognised by relevant governments and key stakeholders through effective partnerships and evidence-based policy dialogue. Capacity is built for multi-stakeholder integrated and evidence-based programming to improve long-term prevention policies and programmes.	ILO holds regular partnership meetings with relevant government authorities and key stakeholders to update on progress. LSHTM regularly shares research insights with international and local partners.	ILO holds regular partnership meetings with relevant government authorities and key stakeholders to update on progress. LSHTM regularly shares research insights with international and local partners.	Partly achieved / - Strong interest in programme continues from wide range of stakeholders, and ILO and LSHTM continue to engage in relevant fora. / - New LSHTM and ILO comms products. / - Few research results available yet to share widely
6.3 Governance arrangements and advisory bodies are established and operate to ensure robust oversight of the programme. The quality and impact of the Work in Freedom programme is enhanced by external anti-trafficking and evaluation expertise.	Advisory Group meetings (tbd); Impact Evaluation Group meetings (tbd)	Advisory Group meetings (tbd); Impact Evaluation Group meetings (tbd)	Achieved / - Advisory Board meeting held July 2016, and Board members attended WiF regional event in Bangkok in February 2016. / - Evaluation Group met in February 2016
6.4 International and UK communications and influencing strategy is established, including UK key stakeholder engagement and public media initiatives to improve long-term impact and effectiveness of anti-trafficking prevention and labour migration programmes based on robust evidence.	Two UK stakeholder meetings (tbd); Media coverage (tbd); media and communications strategy developed by ILO & DFID	Two UK stakeholder meetings (tbd)*; Media coverage (tbd);	Partly achieved / - Successful UK stakeholder meeting held July 2016 / - Communications and Research Uptake Strategy developed / - New comms products, media and blog pieces published by partners[2]
[2] E.g.: http://blogs.lshtm.ac.uk/samegroup/projects-2/swift/; http://news.trust.org//item/20151017091705-90rgy/; http://migratingoutofpoverty.blogspot.co.uk/2016/03/trafficking-of-women-chasing-away-our.html

Key Points
This output scores B because while the programme continues to be well-managed, the majority of the recommendations from last year’s Annual Review have not been sufficiently addressed, and some of the targets (above) are off track.

Programme governance: The revised governance arrangements agreed in 2015 are working well and this was validated by a successful series of annual meetings in London in July 2016.

ILO programme management and staffing: Questionnaires sent to a sample of ILO partners indicate an average rating of 4 (‘good’) for ILO programme management (on a scale of 1-5). There is however evidence of difficulties with one or two partners related mostly to reporting requirements and delayed payments. The ILO has increased staffing over the past year, with new programme leads in Jordan and Lebanon, a technical officer based in Geneva providing some time towards the ILO’s research elements of the programme, and a new M&E officer planned. These are welcome additions to the ILO team, to reduce the very heavy workload of the Chief Technical Adviser (CTA). Over the coming year, it will be important for ILO to put in place stronger communications links between its work in Geneva and Delhi on fair recruitment and finances.

ILO programme coordination: ILO has made good progress in addressing previous issues around communication between ILO and LSHTM. More work is needed to continue this as discussed in Output 5. ILO should also increase efforts to build better understanding and coordination between the sub-contracted delivery partners – something partners have flagged again this year as an issue preventing them from creating synergies across the programme.

Programme scope: A dominant theme of the previous (2015) Annual Review was that the scope of the programme is broad and that more focus is required. ILO has made some promising progress on this, but it continues to be a concern, and Work in Freedom remains a complex programme to deliver. It will be important in particular for ILO to prioritise activities under Output 4 (Law and Policy reform), assessing which legal and/or policy activities are likely to achieve most significant impact.

Contracting: Many contracts have recently ended, or are due to come to a close in the near future. ILO will need to strengthen partnerships and quickly finalise contracts through to the end programme. To drive greater transparency of the flow of funding, DFID has agreed with ILO and LSHTM for a delivery chain map to be produced detailing in one place how much funding is supplied to each partner.

CommunicationsThe programme needs a coordinated communications and research uptake strategy to ensure findings and lessons reach external and internal audiences. A draft strategy is in place but now needs to be updated with more detailed action plans, and partners must move to implementing it over the coming months.

Summary of response to issues raised in previous annual review/s:
The August 2015 DFID Annual review recommended that ILO strengthens collaboration and co-operation between partners; streamlines programme scope; plans for longer term contracting and develops a communications strategy. Partial progress has been made in all of these areas, but it is clear from the evidence highlighted above that a considerable amount of more work is needed.

Recommendations

1. DFID to finalise delivery chain map based on inputs from ILO and LSHTM - by 15 September 2016.
2. ILO and LSHTM to develop a more detailed Communications and Research Uptake Strategy, with clear communication plans, which are appropriately resourced and events calendar with key research milestones (incl publication targets for new papers) and more regular updates to the Advisory Board - by 30 September 2016.
3. ILO to strengthen partnerships and finalise contracts to the end of the programme – by December 2016.
4. ILO to further review programme scope to assess whether better prioritisation of activities is required, in particular on Output 4 (laws and policies) – by October 2016.
5. ILO to improve communication and coordination between sub-contracted delivery partners to build understanding of objectives, plans, and partner activities under each workstream – and how the overall programme adds up to a whole – by December 2016.  ILO to build stronger links between ILO Geneva and ILO Delhi work on fair recruitment and finances – by October 2016.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance
The Work in Freedom programme has a total approved spend of £10.5 million. Its main spending instruments are a MoU with the International Labour Organisation for £8.3 million, and a contract with the London School of Hygiene and Tropical Medicine for £2.1 million. There is also a small independent evaluation component of £40,000. The main ILO component is split into programme deliverables in South Asia and the Middle East, for which the budget of approx. £6.5m is held and managed in ILO New Delhi, and research knowledge and technical support functions of the programme, for which a the budget of approx. £1.5m is held and managed in the ILO HQ in Geneva.

VfM performance compared to the original VfM proposition in the business case

Value for money appears strong in most areas, but in can be improved in others – see below.

Economy
ILO remains a good value for money partner to deliver this work. ILO’s 11% charge is competitive - ILO usually charge 13%, and partners such as World Bank, IFC and GIZ charge 7-15%. ILO was engaged because of their position as well-connected, global leaders in this field. This has proven useful; ILO’s networks and its tripartite structure (involving government, business and worker representation) have helped to effectively engage a wide range of partners. ILO has selected sub contracted partners according to ILO procurement guidelines that we judge to be rigorous, and thus likely to promote economy and efficiency. ILO has also facilitated linkages and lesson learning between key partners.

Research by the London School of Hygiene and Tropical Medicine is relatively costly, representing 15% of the total budget. It was justified by the ambitious, quasi-experimental analysis of numerous interventions, providing the potential to greatly advance understanding of this issue, and have a significant impact on future programmes and policies. Halfway through the programme, we are beginning to see lessons emerge from this research, with these lessons already informing programming and policies within WIF and across DFID. A number of conference papers have been presented, and a research uptake strategy is underway. Future VFM assessments should consider whether research has achieved goals of both identifying lessons and disseminating this understanding.

Efficiency
A number of output indicators have exceeded milestones significantly. Strategic partnerships and careful planning enabled WIF to notably surpass its targets for community engagement. Additionally, partnering funds from WIF with workers’ contributions and Swiss Development Corporation funds assisted in the expansion and operation of the successful Al-Hassan Workers Centre in Jordan. This strategic management across the programme is helping to deliver good value for money outcomes.

ILO engages a large number of partners (approximately 35) to deliver interventions. As a central purpose of the programme is to learn and disseminate lessons, engaging multiple partners is a way of engaging a wide range of expertise, diversifying intervention approaches, and disseminating lessons learned. However, some partners have expressed concern that project duration was too short to be effective. The number of partners also contributes to a high administrative load on ILO, which may be a contributing factor behind some partners reporting that they do not feel sufficiently connected with other organisations, or do not have a strong understanding of the wider programme. The mid-term evaluation should consider the advantages and disadvantages of these numbers of partners, and if and how these might be reduced moving forward. This should be a future consideration in the vfm analysis.

Effectiveness
In 2015, efficiency and effectiveness of the sensitisation of law enforcement officials was recognised as low. The workstream was discontinued and resources re-orientated toward influencing policy change via roundtables and policy papers. The latter was judged to have the potential to contribute to wider, long-term change, for example by promoting substantive changes to legislation, rather than educating a small portion of the people who may interpret such legislation.

Cost-effectiveness
WIF initiatives have directly reached a large number of people who have received a range of information aimed at reducing their vulnerability to trafficking, and improving their welfare in destination areas. Additionally, Work in Freedom is making strong progress toward its goal of improving understanding of effective interventions in the area of trafficking and safer migration. This could be transformative in improving development approaches regarding an issue which affects millions of people.

Assessment of whether the programme continues to represent value for money
Overall VFM remains strong, but there is room for more work.
Recommendations:
1. ILO to assess the extent to which large numbers of sub-contracted partners are minimising programme effectiveness.
2. ILO to work with DFID and LSHTM to develop stronger VFM indicators that can be reported on in future annual reviews.
Quality of financial management
ILO financial reporting is adequate and in line with their own global standards but ideally we would like to see more details of specific transactions. Requests for funds (which are disbursed roughly bi-annually) are accompanied by financial overviews which indicate allocations, commitments and actual expenditure against single budget lines. DFID also receives annual summaries of expenditure which are set against single budget lines but which are not broken down in any detail. This gives DFID some assurance that payments are not being made in advance of need, but the absence of detailed expenditure breakdowns means it is not possible to ascertain whether expenditure is fully meeting DFID’s Value for Money (VfM) standards.

ILO has rigorous financial management arrangements in place for sub-contracted partners: however there continue to be complaints from some partners regarding the complexity or quantity of required reporting, and of perceived delays in reimbursement. ILO due diligence procedures for the selection of partners is assessed as rigorous. The Facilitated Procedure (under ILO Implementation Agreements) includes an assessment of the implementing agent’s capacity to meet ILO financial control and reporting requirements. When a project submits a request for an implementation agreement, they must attest that an ILO Finance Officer has reviewed previous audit reports and financial statements and that it has been determined that the proposed implementing agent has the institutional capacity to meet the ILO’s financial control requirements. In addition the implementing agents have to get written authorisation and approval from the ILO before they themselves do any sub-contracting, and the terms of any subcontract must be in conformity with the implementation agreement with the ILO[3]. This should help to reduce the fiduciary risk of any long and complex delivery chain.
[3] Details provided by ILO Procurement Bureau to DFID ART on 15 July 2016

Disbursement of funds to LSHTM is milestone based. This appears to be proceeding well: the LSHTM Annual Progress Report up to March 2016 indicates that some 52% of funds are undisbursed which is a healthy financial profile for the two year remainder of the programme, implying that funds have not been disbursed in advance of need.

Date of last narrative financial report	June 2016
Date of last audited annual statement	2014 ( received Dec 2015)

E: RISK

Overall risk rating:	Moderate
(on the scale: minor/moderate/major/severe)

Overview of programme risk
The Work in Freedom programme has an overarching Risk Register in place, which is managed by DFID and captures the key, high level, programme-wide risks to delivery.More detailed risks are contained within separate ILO and LSHTM risk registers for their respective components of work. Key risks are reviewed formally by DFID, ILO and LSHTM every 6 months. In addition, ILO and LSHTM are expected to monitor risks on an ongoing basis and report any significant new or increased risks to DFID immediately.

The key risks (including those that have emerged over the past year) include:

Political risks:

1. [Major risk] Regional political instability or conflict mean Work in Freedom is not able to deliver programme activities as planned. This is an increasing risk in Bangladesh (with regard to increased extremist events). Mitigation plans for this include building in flexibility to programme activities so they can be adapted as required to ensure results can continue to be delivered through alternative means.
2. [Moderate risk] Government support wanes in countries where the programme operates, potentially resulting in activities being unable to operate or unlikely to achieve impact. This is an emerging concern in India and Lebanon that partners are tracking closely and actively mitigating against, for example by engaging in regular dialogue with government officials and ministers.
3. [Minor risk] New ministerial priorities affect how the programme is able to be delivered. This is judged to be low probability.

Economic risks:

[Major risk] Currency fluctuations affect the extent to which partners can deliver the intended activities and results. Mitigation measures include revising activities and budget lines as needed to minimise risk, in line with guidance.

Delivery risks:

[Moderate risk] Work in Freedom’s research and evidence work does not deliver the intended results, or is not communicated effectively to the audiences who are able to use it. Mitigation actions include close working between ILO and LSHTM, and a focus on delivering a high quality Research Update and Communications Strategy.

The other risks remain broadly unchanged from those reported in the previous annual review, and so are not repeated here. The ILO’s management capacity of fraud and corruption remain strong.

Outstanding actions from risk assessment
ILO and LSHTM to revise their respective risk registers, and mitigation strategies to be reviewed at the next 6-monthly programme management meeting with DFID.

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe
The ILO component of the programme (203857-101) is mostly on track and, in some respects, is ahead of the curve (for instance ILO reports that targets have been surpassed on two of five indicators for Output 1). The LSHTM component (203857-102) is also on track and has met agreed milestones for this reporting period.

Performance of partnerships
A sample of questionnaire responses from key sub-contracted partners indicates an average rating of ‘Good’ (4) for the quality of partnership with the ILO (this is on a five point range from Unsatisfactory to Excellent). However a few key points have emerged from the questionnaire survey:
- Financial approval processes are cumbersome even for relatively small grants. This can delay start-up or extension of a contract;
- Reporting to ILO can also be cumbersome with four reporting periods and the submission of full supporting documentation with every report. This can sometimes lead to slow disbursement of funds and partners having to cover themselves financially for periods of time. Recommendation: ILO to consider scope for reducing to six monthly reporting.
- Some confusion over which ILO office is responsible for taking the lead on particular contracts.

Questionnaire responses from LSHTM partners are generally very positive on the programme management relationship.

One emerging theme has been the need to improve dialogue between the different sub contracted partners under the ILO programme so that good practice is exchanged and lessons learned. The ILO has committed to organising a Partners Meeting (possibly following finalisation of the delayed Mid Term Review) in the next reporting period.

Asset monitoring and control
Both LSHTM and ILO have asset inventories in place. LSHTM have not created any assets under this programme in excess of £1,000 in value but a few of ther sub contracted partners have and inventories have been received, and there are only a few such assets registered by ILO. DFID has notindependently verified these assets.

G: CONDITIONALITY

Update on partnership principles (if relevant)

N/A

H: MONITORING & EVALUATION

Evidence and evaluation

Evidence on ‘what works’ to prevent trafficking is scant. There have been a number of global contributions to improving this evidence base in the past year, including an evidence review by LSHTM and the Freedom Fund on of community based interventions to tackle trafficking, economics of forced labour[4],and a range of papers from Harvard University[5]and the Journal of Human Trafficking.[6]
[4] Juliette Faure, ‘Forced Labour: Does it Make Economic Sense’, UNU/SIPA Junior Research Felowship Paper Series (United Nations University), 2016.
[5] Including Bhabha Donger, ‘Is this protection? Analyzing India’s approach to the rescue and reintegration of children trafficked for labor exploitation’, March 2016, and Jewel Gausman et. al., ‘When we raise our voice: The challenge of eradicating labour exploitation, an evaluation of a community empowerment invervention in Uttar Pradesh, India’, March 2016
[6] Routledge, published quarterly, established in 2015.

The Work in Freedom programme is beginning to contribute to improving the broader evidence base, including on the risks and factors associated migration decision-making, and how interventions affect the ability of women to migrate more safely. In July 2016, DFID hosted a seminar with over 70 practitioners which presented some emerging lessons from programme, and we expect further, substantive research and findings to be published over the coming two years.

Given that the interventions are complex, across multiple sites and working with different target groups, it is difficult in the time frame of this programme to quantify whether or not these interventions will lead to prevention of trafficking. However, it will generate evidence on how interventions influence women’s attitudes and pre-departure decision-making. And it will generate evidence on women’s social, economic and political empowerment and how this affects their ability to safely migrate. As a result, the programme’s impact statement focuses on reducing vulnerability to trafficking and exploitation, rather than reducing trafficking.

ILO commissioned an Independent Evaluability Assessment, received in December 2015. DFID was part of the steering group for this evaluation. The Assessment provided recommendations on the logframe and theory of change, which have subsequently informed considerable changes. This has informed recent revisions of the logframe and theory of change, thus strengthening the programme’s overall coherence. These changes are close to finalisation.

To further improve monitoring and evaluation of the programme, ILO is currently recruiting a Technical Officer who will work closely with National Programme Coordinators across all five countries. ILO is also commissioning the external mid-term evaluation to take place in August-November 2016. This will be an important opportunity to take stock of what has been achieved, and recalibrate efforts to ensure optimal effectiveness in the remaining two years of the programme. These activities are necessary as Work in Freedom is well positioned to contribute to global understanding of migration, and how best to reduce vulnerability to trafficking and exploitation.

Monitoring progress throughout the review period

The programme has had strong monitoring throughout the review period (see Output 6).  ILO has established agreements and good reporting systems with implementing partners. DFID, ILO and LSHTM have regular discussions throughout the year. And DFID staff continue have again this year visited ILO offices in the region to discuss progress.

------------------------------------
This annual review has been conducted by DFID’s Asia Regional Team, in particular the Policy and Partnerships Manager, Senior Social Development Adviser; Graduate Placement Policy Officer and Programme Manager, with input from the Asia Regional Team Results Officer and the Social Development Adviser and Economic Adviser in DFID Nepal. It has drawn on the Programme’s External Advisory Board, the Management Committee meetings held in London in July 2016; annual reports from ILO and LSHTM, a range of programme documentation, interim progress updates by ILO and LSHTM; Delhi field visit and questionnaires and interviews with global, national and local partners.

------------------------------------