Project Completion Review - Top Sheet

Review Date:	15 July – 5 August 2016

Title: Climate Research and Information Services in South Asia
Programme Code: 202125	Start Date: September 2010	End Date: May 2016

Summary of Programme Performance

Year	2011	2012	2013	2014	2015	2016
Programme Score	A+	B	B	A	A	A
Risk Rating	Medium	Medium	Medium	Medium	High	Major

Financial Position

Original Programme Value	Value: £1,500,000.00 / Submission and Project Memorandum dated: 20.08.2010 / Quest number: 2748106, 2739626 / Time Period: 2010-2013
Extensions/ amendments	Amendment 1 / Submission for costed extension dated: 12.08.2011 / Quest numbers: / Submission: 3170823 / Business Case: 3717461 / Time period extended to March 2015 / Value: increased to £2,600,000.00 / Amendment 2 / Submission for no cost extension dated: 10.3.2014 / Quest no: 4395732 / Time period extended to September 2015 / Amendment 3 / Submission for no cost extension dated: 7.8.2015 / Quest no: 5095680 / Time period extended to May 2016
Log-frame revisions (with dates)	Original : Quest no. 2739630 dt. August 2010 / Revision 1 : Quest no. 3170813 dt. August 2011 / Revision 2 : Quest no. 3855794 dt February 2013 / Revision 3 : Quest no. 4783824 dt. June 2014 / Revision 4: Quest no.5295345dt October 2015
Total programme spend	£ 2,517,430
Unspent Balance	£ 82,570

Follow up actions required following closure

1. Continue to track results of the programme, particularly instances of policy impact, at least for the next two years. It is likely that some of the papers that have been submitted to journals or are under preparation will be published during the course of the year, and South Asia Research Hub (SARH) should keep a record of these to capture the results of the programme fully. (Action: Senior Responsibility Owner (SRO))
2. Share broad lessons emerging from the programme (such as challenges of regional coordination in climate research and issues of presentation of complex scientific findings in a language accessible to policymakers) more widely within DFID, for example, by presenting these in the next Climate and Environment Cadre PDC.(Action: SRO)
3. Consider including a dissemination/ outreach budget in future business cases to allow for cross-project dissemination. Individual projects would normally build in dissemination in their budgets; however, pooling results across projects and presenting these to relevant audiences would need a higher level of coordination and additional funds. (Action: SARH)
4. Share lessons on capacity building across Research and Evidence Division (RED) that writeshops may not provide an effective mechanism for supporting publication by Southern researchers, when the core barrier is the quality of the primary data (Action: SRO).

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-202125/documents
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-202125/documents

South Asia, as a geographical region, holds about a quarter of the world’s population on about 3% of the world’s land area. South Asia remains home to a large number of people living in extreme poverty and about a quarter of the population live below the international poverty line ($ 1.25/ day). The region is also particularly vulnerable to the impacts of climate change; it is well accepted that these impacts are felt disproportionately by poor and disadvantaged groups, including women and children. This calls for a strong and coherent policy response at the regional level, but this is critically dependant on the availability of robust and reliable evidence.

The IPCC (Inter-governmental Panel on Climate Change) 4th Assessment Report observed that there was insufficient data and lack of agreement on prediction of climate change in South Asia. Also, while there are numerous research studies across sectors impacted by climate change, it is often difficult to develop a coherent evidence base around impacts due to the absence of a unified research agenda. This leads to duplication of effort and adoption of research methods that are not mutually comparable, making policy response particularly challenging.

In this context, DFID South Asia Research Hub (SARH) provided £2.6million over five years (2011-2016) to support the development of ‘more coordinated and higher quality climate research and information services’ in South Asia under the Climate Research and Information Services in South Asia (CRISSA) programme. The UK was in a unique position to support this as it provides significant funding to climate research and action in South Asia and has strong relationships with partner Governments, other donors, and the broader scientific community.

Outline of programme and what it has achieved

The CRISSA programme funded a suite of research studies in critical areas of climate science for South Asia. The expected outcome was to facilitate ‘a more coordinated and coherent approach to (climate) research’ by addressing key climate challenges that were regional in nature, and in the process, enhancing coordination among climate researchers and making available stronger evidence on key climate issues to regional policymakers. The following major studies were funded:

- Operational Research to Support Mainstreaming of Integrated Flood Management under Climate Change (jointly with Asian Development Bank)
- Climate Change and Conflict (Strengthening the response to climate variability)
- Climate Change Adaptation (to floods) in the Indus basin of Pakistan
- Calibrating below and above Snowline Precipitation as Inputs to Mountain Hydrology Models
- Groundwater Resilience to Climate change and Abstraction in the Indo-Gangetic Basin
- Scoping Green Growth Challenges and Opportunities in South Asia
- Glacier monitoring in the Himalayas using Unmanned Airborne Vehicles (UAVs)

In addition, a scoping paper on user needs for climate information (‘expert framing paper’) was commissioned at the start of the programme to scope out specific activities and a major regional consultation was organised to disseminate findings at the programme end. Under the programme, a special issue of the journal Climate and Development was also supported. The issue included a collection of articles on climate adaptation in the South Asian context. A workshop on SWAT (Soil and Water Assessment Tool) and a ‘Spring School’ for young researchers were also partially supported; these focussed on adaptation to changing water resources and was a part of a larger research programme (HighNoon) funded by the European Commission.

The capacity building component of the programme was reshaped from a focus of writing workshops (which failed to produce tangible results as it was evident that the primary problem was the quality of the primary data (or source data) rather than the inability of researchers to write for scientific journals) to collaborative arrangements between northern and southern researchers.

Achievements over DFID’s funding Cycle of the Programme

Key achievements of the programme are highlighted below:

- The programme has yielded high quality outputs, as evidenced by several peer reviewed publications. A total of 19 peer reviewed papers on climate science themes have been published. 11 peer reviewed papers have been published/ submitted under joint authorship of South Asian researchers. Three have South Asians as lead authors demonstrating their capacity built under this programme.
- The programme has also made strong impact at the policy level. Evidence generated from at least three projects (on ground water resilience, flood management and glacier monitoring) have received strong buy-in from policy makers in the region. In one case (flood management), the concerned ministry of the Government of India is currently acting on the recommendations to revise guidelines for implementing bodies at the state level.
- The programme has made significant contribution towards enhanced research collaboration and dialogue among researchers and research users. Three multi-country projects based on collaborative arrangements among northern and southern institutions were successfully completed. All single country projects had strong regional significance and similar collaboration. Three studies have been implemented in conjunction with a multilateral donor (ADB) or an intergovernmental organisation (ICIMOD). Active dialogue among international/ regional researchers and policymakers in a workshop for dissemination of key research findings.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Overall Outcome Assessment

Overall the programme outcome was achieved. CRISSA made a valuable contribution towards the facilitation of a coordinated and coherent regional approach to climate research in South Asia through generation of high quality research carried out through multi-country and multi-donor collaboration. In addition, participation and lesson sharing by policy makers and researchers during a regional consultation workshop held in April 2016 in New Delhi and dissemination of individual projects to regional stakeholders have enhanced coordination and coherence across the region. Research outputs and policy products were presented in various international forums such as International Glaciological Society (IGS) Symposium on Glaciology in High Mountain Asia (HMA) in Kathmandu.

The achievements against outcome indicators are presented below::
Outcome Indicator	Target	Status
Level of duplication of research efforts	Regional research priorities discussed among national and international donors	A regional consultation was held in April 2016 that included panel discussions among key donors (Asian Development Bank, Norwegian Embassy, IDRC, Swiss Agency for Development Cooperation) and policymakers. Several regional research priorities were discussed in the panels (such as responses to climate stress and community based adaptation). These emerged from the key findings of CRISSA funded research, however the broader challenges of research coordination were also discussed. In addition, at least four CRISSA projects organised targeted dissemination that involved some regional donors. / Through the scoping paper, the research outputs and the dissemination activities, CRISSA has been able to address several niche areas of climate research as well as broader issues of collaboration and coordination. By presenting results strategically to policymakers, donors and other stakeholders, CRISSA has been able to strongly articulate both research priorities (both thematic and geographical) and associated challenges. It is expected that these will be taken on board at least by some of the donors/ policymakers that CRISSA reached out to.

Improved evidence base available to decision makers from jointly funded research and high quality evidence reviews	Key research and reviews produced that are disseminated and discussed with decision-makers	CRISSA projects generated high quality evidence; 19 peer reviewed papers have been published. There was significant representation of decision-makers in project steering groups, advisory boards and consultations who have routinely fed back on policy relevance of the findings. Six policy briefs have been developed, and policy-relevant summaries of projects completed have also prepared as part of technical outputs. These have been strategically disseminated by project partners and by SARH among relevant stakeholders. / Some key outputs have already directly influenced policy. For example, the Government of India plans to revise flood management guidelines based on CRISSA funded research.

Output Score and Description

The overall output assessment is A: outputs met expectations.

Output description	Assessment
Coordination with research funders	A
Quality of evidence base available for policy makers and programme managers	A
Capacity of south Asian climate community to produce high-quality and influential research	B

At the level of outputs, the highlights have been the following:

Established coordination with research funders in the South Asia region especially with ADB and ICIMOD and support to four multi-country research projects.
- High quality evidence generation on key climate vulnerabilities such as flooding and groundwater resilience to support decision makers towards making better informed policy decisions.
- Support to a first of its kind study on climate change impact on debris covered glaciers using Unmanned Airborne Vehicles (UAV). This approach in future has the potential to bridge the gap between field-based studies (hampered by accessibility problems) and satellite remote sensing (hampered by coarse resolution and clouds) to assess impact of climate change on glaciers.
- Strengthened capacity of South Asian researchers evidenced by joint authorship (with researchers based in UK/ Europe) of 11 papers on climate science published/ submitted.

Lessons and how these have been shared

The key findings at the level of individual research projects have been documented in technical reports, policy briefs, journal articles and sometimes, through blogs. Multiple outputs (targeted at multiple audiences) have been helpful. In particular, the use of policy relevant material – either policy briefs or summary sections on policy implications – have helped convey messages in a language accessible to policymakers. The CRISSA framing paper was shared with regional donors at the beginning of the programme, and a summary of all final outputs was also shared among donors and policymakers.

Lessons have also been shared at the programme level (across individual projects) through a programme-end workshop; this event saw significant donor participation and close interaction with policymakers. Key issues of research coordination, communication and implementation challenges were discussed with reference to the individual projects but also in relation with the broader climate agenda in the region.

CRISSA engaged with various DFID country offices throughout the programme. Specifically, DFID India (Energy, Climate and Growth Unit) (ECGU) and the Asia Regional Team (ART) participated in several Annual Reviews and this PCR, and linkages were drawn between CRISSA outputs and the Climate Proofing Growth and Development - Climate Change Innovation Programme (CPGD-CCIP) programme of DFID India, wherever this was possible. Strong linkages (both in terms of the theme and the geographical focus) exist between CRISSA supported research on flood management and DFID India supported work on flood forecasting models, and a joint presentation was made at the CRISSA dissemination event. Sharing of lessons across HMG was advanced, and outputs were shared with Research Councils of India UK (RCUK) and the Science and Innovation Network (SIN). While this was useful and helped the outreach of the programme, the engagement could have been more strategic and should have been consistently pursued throughout the programme cycle rather than being done towards the beginning and the end of the programme.

A key lesson has been the reinforcement of the need to engage with various levels of stakeholders (including those outside the academic community) at various points of the project cycle. While research teams would normally engage with their peer community in dissemination of their work, there may not sufficient academic incentive in all cases to engage equally with policy makers; therefore there is a need to develop targeted policy-relevant material for broader outreach, especially in the context of publicly funded research that intends to generate outputs in the nature of regional/ global public goods.

Engagement of key decision makers and implementation agencies at appropriate levels during the research process is critical for validating research outputs. For example, the study on flood management gained significantly from inputs from relevant agencies at various intermediate stages, especially on issues of implications of the research outputs on key institutional mechanisms for management of floods and mitigating losses. While this was a useful process and should enhance uptake, it also caused some implementation delays due to procedural issues at the government end. It would be useful to factor these into future project timelines, especially when delays in approval of outputs could impact implementation schedules.

At the design stage of CRISSA, a capacity building component (through writing workshops or ‘writeshops’) was also included in the programme. Under this component, a workshop was organised to help South Asian researchers to convert their research into peer reviewed papers. However this component was dropped midway through the programme (in 2013) based on the recommendation of an Annual Review. The workshop did not yield tangible results in terms of papers getting accepted and published in peer reviewed journals. It was evident that the issue was primarily with the quality of the primary data (or source data) rather than the inability of researchers to write for scientific journals. In the remaining years, the programme instead focussed on embedded capacity building through collaborative arrangements among northern and southern researchers. This has led to much greater success with several southern researchers taking advantage of collaborative (often multi-country) research teams to jointly author papers for prominent journals..

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Coordination with research funders
Output number per LF		1	Output Score	A
Risk:		Major	Impact weighting (%):	20
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Enhanced multi-country coordination in climate research (in the CRISSA context)	Enhanced multi-country inputs in climate research (May 2016)	Achieved. Three multi-country projects supported in collaboration with donors and inter-governmental bodies (such as ADB and ICIMOD). All other projects have strong regional significance. All projects involve collaboration between southern and northern institutions/researchers.
Increased sharing of research outputs among funders	Research outputs and policy briefs formally shared in an appropriate forum (May 2016)	Achieved. Research outputs of 9 projects have been shared through workshops, publications and web based video platforms such as Youtube. A regional dissemination event was organized in April 2016 to disseminate findings of all the projects funded under CRISSA.

Key Points

National governments in South Asia consider climate change as one of the key risks to their development goals. This has led to the creation of numerous institutions (both national and regional) that fund and carry out climate research. While this seriousness among countries and availability of a range of research institutions provide opportunities for research coordination, they also present significant challenges in terms of developing common research approaches that would allow the comparability of results. CRISSA facilitated multi-country coordination by working with regional research funders and inter-governmental bodies, especially with ADB and ICIMOD. It also identified climate issues with high national and regional impacts to facilitate multi-country engagement. The project on climate change and ground water resilience in the Indo-Gangetic Basin, for example, involved collaboration with partners in India, Bangladesh, Nepal and Pakistan. The project on calibrating precipitation as inputs to mountain hydrology models, though undertaken in a single country (Nepal), had strong regional relevance with a potential contribution to improving regional capacity for accurate modelling of precipitation. Similarly, the project on integrated flood management in India, though not multi-country in scope, has much regional significance as the issues of flood management are similar in most other South Asian countries.

Key examples of project-level sharing include the following:

13 conference presentations have been made based on the outputs of the groundwater resilience study, including at the NERC/ GoI Changing Water Cycle Programme in Bengaluru in 2015

In March 2015 ICIMOD organised the International Glaciological Society (IGS) International Symposium on Glaciology in High Mountain Asia (HMA) (www.icimod.org/igs2015) in Kathmandu. The study outputs of the CRISSA project on glacier monitoring was presented at this prestigious symposium. The study team also worked with Science Media to create a professional documentary based on the project. This has generated significant media attention and the film has been viewed over 2,000 times on Youtube alone. It has been screened at multiple regional international events including the CRISSA dissemination meeting. The documentary can be viewed at http://youtu.be/xTLgpd4Wyxw.

A regional consultation on CRISSA outputs was organised as a programme-end dissemination activity. About 70 participants joined this event (New Delhi, 7-8 April 2016). The participants represented the academic, policymaker and donor communities of the South Asian region. All CRISSA project leads presented key findings. Cross-cutting issues were discussed in panels for donors and policymakers. Links were explored with DFID India, RCUK, ART and the ESPA (Ecosystem Services for Poverty Alleviation) programme in a panel dedicated to cross-HMG linkages.

Output Title	Quality of evidence base available for policy makers and programme managers
Output number per LF		2	Output Score	A
Risk:		Moderate	Impact weighting (%):	50
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Evidence on the needs of users with regard to climate information	WRI evidence review disseminated (2014)	Achieved. The CRISSA framing paper was discussed extensively with climate research users at the beginning of the programme and was subsequently disseminated widely.
Rigorous research findings available on key topics on policy and programming importance	All projects completed, and reports and journal papers prepared (2015)	Achieved. All projects have produced detailed technical reports. 19 peer reviewed papers have already been published and 13 more papers have been submitted.

Key Points

19 peer-reviewed papers were published by programme partners and several more have been submitted or are under development. Almost all publications are open access, and have also been shared on R4D.

Peer reviewed papers provide evidence of the high quality of outputs generated through CRISSA projects. Many of these papers are in high impact journals. For example, the paper ‘Modelling glacier change in the Everest region, Nepal Himalaya’ was published in the open access journal The Cryosphere with an IF (Impact Factor) of 4.374. In this paper, a glacier mass balance and ice redistribution model was applied to examine the sensitivity of glaciers (in the Everest region of Nepal) to climate change. This is just one instance where CRISSA has generated high quality research in a niche area, aligning with larger regional research programmes (in this case, ICIMOD’s research on cryosphere issues).

CRISSA also made significant efforts to ensure that evidence generated supports policy and decision makers at different levels. In this context, various research outputs were converted into policy briefs and shared with stakeholders through various platforms ranging from stakeholder consultation workshops to web based applications.

Some examples of policy level impacts and major academic outreach are noted below:

The groundwater resilience study resulted in a policy advisory titled ‘The Bengal Deep Groundwater Statement: Deep Groundwater in Bangladesh: a vital source of water’ with joint authorship by individuals from Dhaka University, Bangladesh University of Engineering & Technology (BUET), University College London, IIT Kharagpur, Bangladesh Water Development Board and British Geological Survey for delivery to Water Resources Planning Organisation (WARPO) of the Ministry of Water Resources and Policy Support Unit (PSU) of the Ministry of Local Government, Rural Development & Cooperatives, Government of Bangladesh.

The glaciers of the Himalayan region were a notable ‘blank spot’ in the 2007 IPCC report, and while some research had been conducted in time for the 2013 IPCC report, there had not been a scientific symposium focused specifically on the glaciers of the region. With an innovative conference format that included less formality and more time for discussions, synthesis and networking opportunities, the International Glaciology Society Symposium (2015) had a major impact on both the science of glaciology in the region, and on the way scientific symposia should operate. The forthcoming papers of the Annals of Glaciology (related to glaciology) will ensure that the region receives greater scientific attention and scrutiny. CRISSA projects contributed majorly to the scientific outputs of the event and enabled wide ranging regional participation in the event.

Project material and results from the groundwater study have been included in MSc-level university teaching modules prepared for six universities in Pakistan (www.pakistanuniversitywaternetwork.org) and in a short course on conjunctive water management for water managers in Sindh, Pakistan. Project results have also been included within the Sindh Irrigation Sector Strategy.

The report of the integrated flood management study findings will directly feed into climate resilience programmes of DFID India which also focuses on Bihar and Odisha (the two states covered by the CRISSA study). Ongoing programmes such as Climate Proofing Growth and Development - Climate Change Innovation Programme (CPGD-CCIP) and Infrastructure for Climate Resilient Growth (ICRG) focus on improving resilience of the poorest to impacts of climate change by supporting state governments to integrate climate in their planning and build climate resilient infrastructure such as embankments. The report provides useful recommendations on structural and non-structural flood mitigation measures which could be used as evidence to frame policy recommendations to state governments to tackle climate change. Observations in the report such as strengthening flood forecasting, early warning and community preparedness have great relevance for ongoing programmes on climate resilience such as the forthcoming climate services programme of ART.

The Ministry of Water Resources, River Development and Ganga Rejuvenation, Government of India and various other government agencies were active participants of the research process for the integrated flood management study and have provided key inputs at various stages. Notably, two journal papers emerging from this work are co-authored by the research team and senior government officials. The Government of India plans to revise flood management guidelines based on some of the recommendations of this study.

Output Title	Capacity of South Asian climate community to produce high-quality and influential research
Output number per LF		3	Output Score	B
Risk:		Major	Impact weighting (%):	30
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Number of papers on climate science published in high impact journals with South Asian lead or sole authors	10 papers published or accepted (2020)	On track for 2020 / So far three papers have been published with South Asian lead researchers and at least three under preparation will have South Asian researchers as Lead Authors. In addition eight papers already published or accepted are under joint authorship of South Asian researchers. . We expect that South Asian researchers would lead on several more publications over the next four years, and this can be reasonably attributed to the capacity built during the CRISSA programme.

Key points

This output is difficult to score as the target indicator date (2020) is beyond the formal end of the project. Currently three papers have been published with South Asian lead authors with several more in preparation. In addition the project has developed a strong portfolio of collaborative papers – which demonstrate progress against the outcome objective, although not the specific logframe indicator. Several CRISSA projects were multi-country with collaborative arrangements with/among South Asia institutions. All project outputs were jointly authored - with South Asian authors taking the lead in situations where the output is built on case-studies from the region. As many as 8 papers (published/ submitted) are under joint authorship of South Asian researchers.

As the indicator has not been met yet, we have scored this output as B in this PCR, but given current progress, we expect that the target will be exceeded by the milestone date. There is a clear positive trend suggesting that South Asian researchers gain from the collaborations in CRISSA in terms enhancing their capacity to publish.

The capacity-building objective was better achieved through this route (collaborative research) rather than through writing workshops (‘writeshops’, as in the original logframe) which presupposed that the constraints (for development of peer-reviewed material) relate to lack of writing skills rather than the quality of research itself. As mentioned earlier, the programme design was modified (‘writeshops’ were dropped) to reflect this change in 2013 based on an Annual Review recommendation.

The bibliographic reference for the final report of the groundwater resilience is as below:

MacDonald AM, Bonsor HC, Taylor R, Shamsudduha M, Burgess WG, Ahmed KM, Mukherjee A, Zahid A,Lapworth D, Gopal K, Rao MS, Moench M, Bricker SH, Yadav SK, Satyal Y, Smith L, Dixit A, Bell R, van Steenbergen F, Basharat M, Gohar MS, Tucker J, Calow RC and Maurice L. 2010. Groundwater resources in the Indo‐Gangetic Basin: resilience to climate change and abstraction. British Geological Survey Open Report, OR/15/047, 63pp.

This itself reflects the nature of collaboration. The technical report (after DFID and external review) was sent back to all authors for a sign-off before being submitted as a final version. This is healthy practice as this ensures that all authors take (individual and collective) ownership of the final product.

Several projects have helped enhance research capacity by facilitating participation in conferences or by enabling students to get academic degrees based on CRISSA supported work. In one instance (the precipitation study), the funds budgeted for a final workshop was used to support regional students to attend an international conference on glaciology. From 1 March to 6 March 2015, about 250 scientists, researchers, and students met in Kathmandu for this high impact symposium. This was an opportunity to present research findings at a prestigious conference while exposing regional scholars to high quality scientific research. The project on Pakistan floods enabled two students to obtain their Masters degree based on dissertations drawing from the work supported by CRISSA.

CRISSA supported a special issue of the Climate and Development journal, focussing on the theme of climate adaptation. 17 of the 37 authors of papers in this issue were from the South Asian region.

Summary of responses to issues raised in previous annual reviews

Issue 1

SARH should develop and implement a dissemination and outreach strategy for the programme beyond project-level efforts being taken by research teams.

Response

SARH engaged expert research uptake support to design an outreach strategy for the programme. Based on the recommendations, a programme-end dissemination event was organised, and several policy briefs/ project summaries were shared with a range of stakeholders, including donors and policymakers. A list of upcoming conferences in the region was also prepared, and project partners presented their work in at least two of these.

Issue 2

SARH should continue to monitor uptake since policy level impacts are rarely achieved during the project lifetime.

Response

SARH does this on a routine basis and updates a results database at regular intervals. The reporting format has been modified to explicitly include impacts.

Issue 3

SARH should maintain close contact with relevant DFID / FCO teams like ECGU and ART to explore thematic linkages.

Response

This was actively done in the final year in the programme. ECGU and ART were involved in Annual Reviews and a cross-HMG panel (ECGU, ART, RCUK) explored these linkages in the CRISSA dissemination event. This is further being followed up through discussions with these teams.

Issue 4

The delivery mode of capacity building component is to be changed since writing workshops did not generate the desired outputs.

Response

The activity focusing on writing workshops was replaced midway through the programme with efforts were to encourage research teams to develop collaborative arrangements with Southern partners. Emphasis was placed on joint authorship of research outputs. In many cases, Southern partners were successful in getting their work published in top journals (as lead or second authors).

Recommendations for future programmes

Multi country studies greatly enhance regional learning. Future programmes could use CRISSA examples to design research that is undertaken in several countries using a common conceptual framework. Results could then be presented both at the level of a regional synthesis and at the level country specific case studies. Equally, for single country studies, issues of regional significance could be explored at the outset.

Policymakers should be involved from the inception stage of studies, wherever possible, to maximise impact. If feasible, they should co-produce outputs and jointly author research papers. At the least, research projects should have Steering Boards where policymakers are represented.

Strategic collaboration with DFID country and regional programme teams and cross-HMG departments such as RCUK and SIN (Science and Innovation Network) will ensure effective internal cross learning and utilization of evidence generated through research programmes.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

Since this was an umbrella programme out of which a number of individual studies were commissioned, cost drivers varied across studies. Researchers’ fees (against technical inputs), project expenses (travel, field work etc.) and assets procured for specific studies were some of the common drivers affecting costs across all studies.

Unforeseen occurrences have impacted costs in isolated cases. The massive earthquake in Nepal (April 2015) impacted the project on ‘Glacier Monitoring in the Himalayas using UAVs’ which had to be given a costed extension of 6 months since fieldwork was delayed due to lack of access to the field sites. Re-planning of field work incurred additional costs that were covered from programme funds.

Budget proposals for all individual studies were thoroughly reviewed to keep the costs in check. DFID procedures for approvals and extensions were strictly adhered to. It was ensured that DFID approval was taken for the appointment of all international and national consultants on agreed rates. There was a good match between researchers’ expertise/experience and quoted fee rates on each of the studies commissioned. Procurement clauses covering international good practice were built into the supplier/grantee contracts and MoUs. Payments for most studies were results-based with clearly defined outputs and delivery timelines.

VfM performance compared to the original VfM proposition in the business case

The original VfM proposition meant to assess VfM through measuring the quality of outputs and their influence (through pathways to impact).

Economy

A total of 10 activities and a dissemination event have been funded under this programme with a spend of £2.5 million (approximately), well within its original allocation of £2.6 million. The programme has demonstrated strong VfM through constantly focusing on strengthening its procurement and financial management systems.

Different funding mechanisms were used for the commissioning of the studies based on procurement rules and principles: 6 studies were commissioned through Accountable Grants while contracting was used as the funding mechanism for 3 studies. One study was funded through a Memorandum of Understanding.

All contracts were issued following competitive procedures with due consideration to cost issues either by the Procurement and Commercial Department (PCD), RED’s Procurement Team or South Asia Research Hub’s (SARH) Departmental Procurement Officers (DPO). Contracts issued were output-based with a number of well-defined intermediate milestones/ deliverables, and payments were linked with these. In case of grants with input-based arrangements, narrative reports were requested from partners along with financial reports.

The capacity building component through ‘writeshops’ (writing workshops) was discontinued in 2013 based on discussion with the implementing partner and a previous AR recommendation. This decision to close an ineffective intervention reflected VfM considerations; building of capacity to do high-quality research and publish in peer reviewed journals is better achieved through collaborative research arrangements than by participation in workshops of short duration.

Efficiency

The programme has yielded high quality outputs as evidenced by a large number of papers (19) published in peer-reviewed journals. For research projects, ratios of inputs to outputs are hard to determine; however it is evident that there has been significant addition to the knowledge base on key climate issues and clearly enhanced capacity of South Asian researchers to contribute to ambitious multi-country research projects.

Effectiveness

The programme has been able to generate broader discussion around research coherence and coordination based on the outputs of the studies that have been funded. The multi-country studies have served as examples of how strong research collaborations can be achieved, and have been able to identify and address some of the specific implementation challenges such as sharing of cross-border data. Programme level dissemination through a workshop has proved to be an effective way of reaching out to regional decision makers and exploring cross-project linkages.

Several projects have successfully leveraged additional funds or developed links with broader programmes to maximise impact. In the flood management study, the inputs of the economist and legal/ institutional experts were funded through a supplementary contract, with funds made available from ADB’s Regional Department for Sustainable Development. The precipitation study aligned well with the Cryospheric Monitoring Programme (CMP) that ICIMOD presently conducts. Research proposed by the Norwegian Water and Energy Resources Directorate (NVE) complements the precipitation study with additional sensors to be installed near Langtang Valley in Nepal. In one instance (glacier monitoring), CRISSA funded only the maintenance of existing equipment and costs of field campaigns (and associated data analysis) since the research partner had already secured funding separately for core costs.

Assessment of whether the programme represented value for money

The programme represented good value for money, producing high quality outputs. Local partners also have, in general, placed a high value of the benefits of the collaborative arrangements, and have suggested that this is a cost-effective in situ capacity building process.

The team had to issue cost as well as no-cost extensions to the CRISSA programme, and there is evidence (emails and other correspondence) of clear approval processes for these extensions. A key recommendation from the last annual review was to disseminate CRISSA results to a range of stakeholders. A regional consultation at the programme-end involving the leads of all major research studies and donors/ policy-makers was a cost-effective way of achieving this, when compared with costs of organising separate (project-level) events for donors/policy makers at various locations.

Quality of financial management during programme

All spending was closely monitored and forecasts regularly updated on ARIES. Information on ARIES was accurately inputted and updated. All payments were made only after outputs underwent the mandatory quality assurance process by SARH’s technical advisers. Learning from experience in implementing this programme, the team improved processes around procurement, budgeting and forecasting and managing finances and delivery. All contracts had output-based payments to maximise value for money (VfM). For Accountable Grants/MoUs, the team ensured payments were released in arrears upon receiving detailed progress and financial reports including updated projections for future. These reports followed the templates developed by SARH.

The project officers kept track of the forecasts and payments for each project and followed up with the suppliers for invoices and reports keeping the Technical Lead informed, ensuring that any issues linked to potential slippages were identified and resolved early on. In cases where delays were expected, their impact on budget and timelines was gauged and managed accordingly.

Date of last narrative financial report	This is an umbrella programme with many projects. Financial reports were received on time for projects in which partners were required to submit them.
Date of last audited annual statement	This is an umbrella programme with many projects. Audited annual statements have been received on time for projects in which partners were required to submit them.

E: RISK (½ page)

Quality of risk management over the life of the programme

CRISSA was a regional programme and achieving research coherence at the regional level presented special challenges, given the rapidly changing nature of geo-politics in the South Asian region. Even at the level of collaboration across research partners, issues of data access and sharing routinely emerged and needed to be tackled with the appropriate level of sensitivity. The use of specialised equipment such as UAV based sensors often attracted government regulations due to valid security concerns. These risks were managed reasonably well throughout the programme by involving government officials in Steering Groups, and allowing due time for government clearance processes, though occasionally this affected overall delivery schedules for individual activities.

There was a risk around effective dissemination, given the logistic challenges of organising regional events. This risk was managed by the use of Skype and other video conferencing tools to bring in regional participants who were unable to travel.

Achievement of policy impact is contingent on adequate receptivity of policymakers to research findings. This is not within the control of the programme; levels of receptivity vary widely across the region. Moreover, as senior officials complete their tenure and move on, much of the institutional memory gets lost. The programme did try to engage with technical agencies directly to mitigate this risk, often jointly with DFID Country Office counterparts; however this was challenging and often logistically unfeasible. The programme-end dissemination event however did succeed in bringing together regional policymakers, and several of them showed strong interest in the study findings.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

The CRISSA programme was originally approved for £1.5 million until March 2013. In 2011 a costed extension of £1.1m was approved to cover the costs of commissioning policy-relevant research and the end date was extended to March 2015. The programme was given a 6 month no cost extension extending the end date to September 2015 to allow the programme to facilitate the successful completion of two high impact projects and an opportunity to engage more effectively with donors and policy makers, based on the technical outputs of the funded projects. Following an earthquake in Nepal in April 2015, a further no-cost extension was granted in August 2015 to extend the programme end date from September 2015 to May 2016 to allow for the completion of an earthquake-impacted activity and some delays in sourcing official government data. The programme extension was also meant to facilitate completion of the planned dissemination activities including the conduct of a programme end workshop.
Though the programme team has closely monitored timely delivery of outputs, a number of studies had to be given time and cost extensions which in most cases, were due to reasons beyond the control of the programme team and partners. The study on glacier monitoring using Unmanned Airborne Vehicles (UAVs) was affected by the massive earthquake in Nepal (April 2015). The project was to conclude in September 2015, but a field campaign in May 2015 had to be rescheduled to October 2015 when the affected area (Langtang) was accessible again. DFID agreed to extend the end date to January 2016 to allow for planned activities to be completed, and also to fund additional costs incurred by the project on account of postponement and re-planning of the field campaign.

The flood management study was initially extended from April 2015 to October 2015 to account for delays in sourcing official government data. The delays were procedural in nature and largely beyond control of the project team. Another reason for the extension was the additional time spent by ADB to arrange supplementary funding of certain activities within the initial scope of the project. Given the benefits of leveraging additional funds, DFID agreed to allow time to complete these activities and integrate these into the final technical report. The study was further extended to December 2015 to allow for reasonable time for review at the Government of India end. The setting of dates for high level steering group meetings at the government level is beyond the control of the project team although every effort was made to request these meetings within the project completion dates.

Performance of partnership(s)

There has not been any issue with contracts and partnerships, except the need to grant time extensions based on reasonable requests from partners.

SARH has learnt from its past experiences and has applied lessons to improve management of its programmes and communication with partners. The team has developed an information pack for all new suppliers which informs them about DFID’s expectations from partners (like inputs for corporate and financial returns, annual reviews etc.). This also provides useful information about DFID policies, standards and practices. (e.g. value for money, use of the UK aid logo, guidance on transparency).

Asset disposal and value obtained by DFID

Asset registers were periodically shared by partners as part of the reporting requirements. Physical monitoring and spot checks of existing assets (mostly high precision scientific instruments) have not been possible as they are located in remote places; however, their precise locations (geo-coordinates) have been reported by partners in relevant cases.

As part of groundwater resilience project (concluded July 2015) , BGS purchased monitoring instruments including 16 automatic groundwater water-level recorders, 4 automatic water salinity recorders and 4 recorders for barometric pressure. These are located at monitoring points in India (Punjab) and Bangladesh. BGS proposed that these recorders be kept in-situ to continue gathering data on water-level fluctuations and water quality trends in the Bist Doab in Punjab, India, and in southern Bangladesh.  Reliable, high frequency information on groundwater level or salinity variations is sparse within South Asia, and these recorders would continue to provide highly useful information.  The recorders have no value if they were removed and are therefore best left in situ. Data from the recorders will need to be however downloaded every year, and this will be undertaken by National Institute of Hydrology (NIH) in Roorkee, India and the University of Dhaka, Bangladesh – both project partners of BGS.  There are no additional maintenance costs. The individual recorders are disposable and used only until the internal batteries run out. The recordings will be databased by BGS, who will provide a small budget to do this, and eventually stored in the National Geoscience Data Centre.  Data will also be available to NIH and University of Dhaka for other researchers working in the area. The on-going presence of the local partners and the fact that the data will be made available to other researchers means we can be sure that further value can be got out of these assets.

Based on this justification, the assets were handed over to BGS following the approval by Team Leader, SARH of a submission from the SRO.

G: CONDITIONALITY (½ page)

Partnership principles assessment

Not applicable. The programme has not funded any government partner.
H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

No formal evaluation is planned. The dissemination event at the end of the programme solicited feedback from a range of regional stakeholders though they were not asked to evaluate the programme. Some key feedback points were the need to engage with policymakers from the inception stage, the need to communicate results in a language accessible to non-academics and the need to provide actionable recommendations at various geographical scales.

The programme played an important role in enhancing the evidence base on a few niche areas of climate science. The need to fund good quality research to support climate action continues to be felt. In specific, issues that have direct operational relevance (like flood management in the face of climate change) remain priorities for research. The programme points to the need to design regional studies that analyse a set of issues through the lens of country priorities. Regional synthesis remains significant, but it is equally important to contextualise results to countries since several climate action decisions are taken at the level of national governments.

Monitoring progress throughout the programme

Progress has been tightly monitored throughout the programme. Several field visits were undertaken during the programme and all outputs were reviewed internally. All project partners were asked to provide an annual update (even after closure, as project results such as publications or policy responses may follow sometime after closure). Inputs were sought telephonically at the time of all Annual Reviews.

This PCR is based on desk review of all project outputs and the inputs received during the programme-end dissemination event. It has been prepared by Aloke Barnwal (Climate and Environment Adviser, ECGU, DFID India) and Anuradha Rajan (Assistant Programme Officer, SARH) with inputs from Anirban Ganguly, the SRO for the programme. The PCR has been reviewed by Jean-Marion Aitken, Head, South Asia Research Hub, DFID.
Smart Guide

The Programme Completion Report is the opportunity to reflect on the entire programme, its performance, achievements, lessons and how learning will be shared to inform future programming.

The Programme Completion Report assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with headline information on the programme and any follow up actions
Introduction and Context
Briefly outline the programme, results achieved and contribution to the overall Operational Plan and DFID’s international development objectives. Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Outcome Assessment / Brief assessment of whether the programme achieved the Outcome
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessment
Key points
Summary of response to issues raised in previous annual reviews (where relevant)
Recommendations for future programmes
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case. Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme represented value for money? / Overall view on whether the programme was good value for money
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Quality of risk management over the life of the programme. How were risks managed, the degree to which they were realised and/or mitigated.
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / Could DFID be a more effective partner
Asset disposal and value obtained by DFID / How were assets managed throughout the programme? How have they been (or will they be) disposed to get maximum value?
G: Conditionality
Partnership principles assessment / For programmes where we have decided to use the PPs for management and monitoring, PCRs should generally include an assessment of commitment to the PPs, including any concerns that have occurred over the year, the partner government’s response, and details of any response by us. Teams should refer to the DFID guidance on reviewing projects.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the programme / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process