Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Mining Sector Reform Project
Programme Value: £643,632		Review Date: July 2015 to August 2016
Programme Code: 105 844	Start Date: 19/10/2011	End Date: 01/03/2017

Summary of Programme Performance
Year	2012	2013	2014	2015	2016
Programme Score	C	B	B	A	A+
Risk Rating	High	High	High	Low	Minor

Summary of progress and lessons learnt since last review

The Carter Centre has exceeded expectations set for the period. The accountable grant has advanced faster and achieved more than we anticipated by this point – and we are happy that if this can be sustained the project will make a really valuable contribution to improving governance in the DRC mining sector. It is for this reason that we are awarding the project an A+.

It must be remembered that this result is not comparable with previous scores, especially those before 2015, as this review covers a greatly changed and reduced portfolio. In particular, the score and risk rating between 2012 and 2014 were driven by the World Bank trustfunds, ProMines, which we exited.

Response to recommendations from 2015 Annual Review the main recommendations for the coming year are as follows:

Progress against recommendations for last year

Recommendation	Progress and comments
Develop a new Business Case for the mining sector, in line with DFID’s current policies, and bring both future potential work with the Carter Centre and civil society, and the potential follow-up from KEIDI under it;	We have begun the process of writing a new business case and we intend a new project to be in place before the closure of this project.
Close the existing programme by the end of the Carter Centre Phase 2 Accountable Grant;	This will happen at the end of the accountable grant in in March 2017
Continue to monitor the cost effectiveness of the Carter Centre Accountable Grant and consider ways of reducing transaction costs;	The Carter Centre has worked to monitor and improve its cost effectiveness and the results of this work are presented in the value for money section. We will look to conduct a fuller value for money assessment on the accountable grant during the project completion report.
Link mining sector programming more systematically to other DFID DRC and centrally managed programmes, particularly on governance, gender, environment and peace and stability in Eastern DRC;	This process will be important to the next extractives business case currently under development.
Actively monitor manage the risks to mining sector programming stemming from the broader environment, in particular national elections and decoupage	This is an ongoing process within DFID DRC

Summary of recommendations for the next year

1) Review the logframe for the Carter Centre Accountable Grant to ensure that it sets the right level of ambition. New tools were developed for the logframe to monitor progress and it is sensible that the effectiveness and ambition of these indicators is revisited following the completion of this review.

2) Visit Carter Centre downstream partners as an integral part of the project completion report process. Interaction with the civil society partners is a crucial method for assessing the progress of the accountable grant, outside of monitoring through the logframe. It is important that this is included in the project completion report to ensure feedback from the target organisations is a central part of this final review.

3) Close the existing programme at the end of the Carter Centre Phase 2 Accountable Grant. In March 2017 the existing extractives programme will come to an end with the closure of the accountable grant. It is important that this is closed responsibly and lessons learned from the project fully documented.

4) Develop a new Business Case for the mining sector. For the UK to continue its contribution in helping harness the extractives sector for the development of the DRC, we will propose a new business case setting out a new programme to replace the one closing.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/4145425.doc
DevTracker Link to Log frame:

As with last years’ annual review, the context in which this project is operating has not substantially changed since the original business case, however the project is radically reduced to that set out in the business case. The mining sector remains the most important source of revenue for the DRC and arguably the most important sector in the economy. The project has radically changed based on our decision in 2014 to exit the ProMines component of the project due to our concerns about the World Bank’s ability to successfully deliver results.

We have continued to provide support to an accountable grant to The Carter Centre, which works with civil society to increase accountability and transparency in DRC’s industrial mining sector. This remaining component is the subject of this annual review.

Context

The extractives sector is the engine of the DRC economy. The Congo contains around 45% of the world’s cobalt reserves, 65-80% of its coltan reserves, 3% of its copper reserves and around 25% of industrial diamonds. Its gold deposits remain underexplored, but are believed to be vast. Hydrocarbon resources are also considered substantial, although the DRC currently only produces 22,000 barrels per day.

Mining in the DRC takes two distinct forms: industrial mining, and artisanal and small scale mining. Industrial mining provides the vast majority of formal production and tax revenues. It is a capital intensive industry employing only 85,000 people directly. Artisanal mining is vital for the country. Over 10 million people (equivalent to roughly 15% of the DRC’s population) depend on the sector directly or indirectly for their livelihoods.

Governance problems undermine the functioning of the sector and its contribution to inclusive growth. Rent-seeking, corruption, insufficient institutional capacity, a lack of credible information on mining sector assets, and a weak policy, legal and regulatory framework have all contributed to the dysfunctional administration of the sectors. The state owned enterprises – in particular Gecamines – are a major issue. The potential impact of state mining revenues on both growth and inclusion - through job creation and fiscal transfers - has been massively reduced by leakage. The systematic undervaluation of the DRC’s assets is estimated to have cost the state around $1.36bn in revenues in 2011 - double the combined annual budget for health and education.

DFID’s changing extractives portfolio

To help address these issues in 2011 DFID DRC launched the Mining Sector Reform Programme. The largest component of this was ProMines, a £27 million World Bank-managed single donor trust fund for the ‘Growth with Governance in the Minerals Sector’. The project met some success, for example it: supported a proposed revision of the Mining Code; conducted a strategic environmental and social assessment of the mining sector; carried out an institutional audit of mining sector institutions, which has been useful by other donors, the government and civil society; and drafted a new strategy for SAESSCAM (an agency supposed to support small scale artisanal miners). The project however failed to make sufficient progress and given its performance issues, outlined in the last two annual reviews, in 2014, DFID DRC made the decision to exit the trust fund, having committed £9 million. This decision was taken to protect British taxpayer money and ensure that it was well spent, rather than a strategic decision about the importance of intervening in the sector.

The Carter Centre Accountable Grant

From October 2013 to January 2015, DFID funded a first accountable grant with The Carter Centre. This was a separate component under the Mining Sector Reform Programme. The project worked with civil society on advocacy for transparency to increase the Government of DRC and mining companies’ compliance with their information disclosure obligations, including, but not limited to, those found in: the Extractive Industries Transparency Index (EITI) Standard, the new Mining Code and Mining Regulation, ministerial decrees, contracts and conventions, corporate governance laws and international standards and best practices.

This project made good progress, producing two main deliverables: an analysis report of the legal and normative framework governing mining information, and; the Transparency Index, a measure of the scope and quality of information available for mining projects in the DRC. It also made a wider contribution improving the capacity of civil society organisations in the sector and helping improve the overall EITI process in the country.

Phase 2 of the accountable grant was agreed in September 2015 to continue to increase transparency in the DRC mining sector, following the success in helping the DRC becoming compliant with EITI requirements. The overarching impact of this second accountable grant is that the governance of mining sector revenues improves, and investment of these revenues is more responsible, sustainable and equitable. To contribute to this, the project aims to support civil society in contributing to improved EITI implementation in the DRC as well as to use EITI data for more effective advocacy.

The project has three outcomes:

1. Congolese civil society partners, including civil society organisations (CSOs) that advocate for the empowerment of women and girls, are able to effectively monitor, and advocate for improvements to, EITI-DRC processes and reporting.
2. Congolese civil society partners are able to effectively research and analyse revenue impacts and use their analysis to advocate for improved fiscal governance of key mining projects/companies.
3. Congolese civil society partners are able to effectively utilize EITI-DRC data and other sources for advocacy to address sector-wide fiscal governance challenges.

With civil society further empowered to substantively participate in the EITI process, to analyse revenues generated by the mining sector, and to advocate for fiscal governance improvements, they can influence reforms to improve accountability of mining sector revenues and ensure the sector better contributes to the DRC’s development.

## B: PERFORMANCE AND CONCLUSIONS

Annual outcome assessment

The accountable grant has three outcomes. Progress against all three of these outcomes to date has been positive.

Outcome 1: Congolese civil society partners, including CSOs that advocate for the empowerment of women and girls, are able to effectively monitor, and advocate for improvements to, EITI-DRC processes and reporting:
1. Number of partner civil society recommendations taken into account in final EITI-DRC reports and improved EITI-DRC process.
2. Cumulative number of EITI contributions (e.g. memos, revenue estimates, etc.) from civil society teams receiving TCC’s technical support that achieve a quality of at least 50%.

Outcome 2: Congolese civil society partners are able to effectively research and analyse revenue impacts and use their analysis to advocate for improved fiscal governance of key mining projects/companies.
Quality of civil society teams’ case study interim deliverables.

Outcome 3: Congolese civil society partners are able to effectively utilize EITI-DRC data and other sources for advocacy to address sector-wide fiscal governance challenges:
Cumulative number of interim deliverables on using the data and associated advocacy from civil society teams receiving TCC’s technical support that achieve a quality of at least 50%.

Outcomes one and two are being delivered through support to four civil society organisations: ADDH[1] and IBGDH[2] in Kolwezi, and COSCCET[3] and DEDQ,[4] who are collaborating in Lubumbashi (for outcome two) and Sakania (for outcome one).
[1] Action pour la Défense des Droits Humains
[2] Initiative Bonne Gouvernance et Droits Humains
[3] Comité de Suivi pour la Contribution des Communautés et Eglises à la Transformation Humaine
[4] Détectives Experts pour les Droits au Quotidien

For outcome one, the Carter Centre provides hands-on workshops and technical support to these organisations to work with broader civil society to make substantive contributions to the EITI process that meet strict quality standards. It was expected at this stage they would have been able to support these organisations to make two such contributions, and hoped that they could achieve eight across the entire grant period. They have greatly exceeded this milestone, having already achieved seven contributions submitted to the national EITI Technical Secretariat and Executive Committee, a number of which have been raised at meetings of the Executive Committee. These contributions provide analyses of the final 2014 EITI-DRC report, recommendations for the scoping of companies and fiscal flows to be included in the 2015 report, and assessments of the impact of the new 2016 EITI Standard on EITI implementation in the DRC. Importantly, the workshops supported by the Carter Centre have given a voice to civil society in the important mining hubs of Kolwezi and Sakania in the national EITI-DRC Multistakeholder Group for the first time. Feedback from the national Technical Secretariat has thus far been positive, and national civil society delegates to the Executive Committee have praised the partner organizations for their efforts and echoed many of their concerns. The extra work undertaken that has exceeded that anticipated in the logframe has involved contributions that were not planned, but that the Carter Centre deemed sufficiently important to merit additional activities and has sought to find cost-savings elsewhere to ensure their implementation. These have included follow-up on past recommendations not yet taken into account (3) and ensuring that partners were trained on the new EITI standard (2016) which was not contemplated when the project began.

For outcome two all four CSOs are conducting analysis on the financial flows of different mining operations: ADDH and IBGDH are studying two Glencore subsidiaries in Kolwezi (Kamoto Copper Company (KCC) and Mutanda Mining (MuMi) respectively), whilst COSCCET and DEDQ are studying Eurasian Resources Group subsidiary Frontier Mining in Sakania. Progress against this is tracked through monitoring the quality of the interim deliverables on the road to the final report. Progress has been good on this component, although quality dipped below that which was anticipated in the last quarter. This quality assessment, however, is based on only one deliverable produced in the quarter. Several more complicated deliverables will be submitted in quarter three, as the research teams have now begun the work on the heart of their revenue analyses: their estimations and verifications of specific revenue flows. It is anticipated that the ADDH, IBGDH and COSCCET-DEDQ teams’ will finalise their draft deliverables in quarter three and that scores will increase, despite data limitations and the complexity of the work being undertaken. Meanwhile, each of the three research teams continues to revise their earlier draft deliverables with guidance from The Carter Centre in order to continue to improve these building blocks for their final reports.

Outcome three is being delivered by two more established civil society operators: the Kinshasa office of OCEAN,[5] who is a Publish What You Pay network member (with its headquarters in Kisangani) with substantial experience in natural resource governance; and the Bunia-based CSO network CDC,[6] whose Carter Centre-supported EITI work since 2014 has led CDC’s Permanent Secretary Jimmy Munguriek Ufoy to be elected as a civil society delegate to the national EITI Executive Committee. OCEAN is drafting a framework to govern mining companies’ social expenditure declarations in EITI reports and advocating for improved community investments by mining companies via legal reform and improved practice. CDC is advocating for both improved transparency around state owned mining companies, with a particular interest in Sokimo, and improved enforcement of the revenue sharing arrangements between different levels of the Congolese government. For the latter, the organisation’s particular focus is on the mining royalty to the state, which according to law should be divided between the central government (60%), the province (25%) and the locality (15%), although this division is not respected in practice. By this stage it was hoped that the two organisations would have collectively completed 14 interim deliverables– either data analysis or advocacy work – whose first drafts were of a significant level of quality. Progress against this outcome has exceeded expectations, and 18 high quality interim deliverables have been produced. Since the project began, OCEAN and CDC have become the leading civil society advocates on their selected issues, and their efforts have been recognized at the national level. For example, OCEAN’s framework for social expenditures has become the baseline for discussion amongst the EITI Multistakeholder Group; CDC’s push to improve state-owned company transparency in EITI has been identified on a short-list of priorities that must be addressed prior to EITI validation; and CDC has actively built support for improved revenue-sharing of mining royalties amongst government officials in Ituri and Kinshasa and provincial assembly members in Bunia.
[5] Organisation Congolaise des Ecologistes et Amis de la Nature
[6] Cadre de Concertation de la Société Civile de l’Ituri Sur Les Ressources Naturelles

Overall output score and description

Based on the Carter Centre logframe, the overall output score is A+ as they have exceeded expectations on all indicators.

Key lessons

Working with partners

Civil society partners have made huge progress and capacity has been increasing. The teams have however, struggled with the most difficult concepts in the later modules. The Carter Centre has reacted to this and built in extensive review periods during workshops.

There has also been a problem ensuring that some of the most active civil society participants are available to attend workshops. After identifying this challenge, Carter Centre staff discussed ways to motivate active participation, including encouraging particular participants to take the lead in more of the exercises, or to explain challenging concepts to peers. At the same time, the Centre encouraged the research teams to work to schedule separate recap sessions with any team members who are unable to attend certain workshops.

Key actions

It is important to validate the final project completion report with beneficiary feedback. To ensure this the process of the report should involve visits and discussion with participating civil society organisations.

Carter Centre staff have worked with its partners to encourage the participation of women in project research teams and trainings. As a result, women regularly make up 20-40% of activity participants.

Has the logframe been updated since the last review?

The logframe has been completely revised in January 2016 to only cover the current phase of the Carter Centre’s accountable grant.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Congolese civil society, including women and CSOs that advocate for the empowerment of women and girls, is trained and is able produce contributions on EITI reporting and processes in the DRC.
Output number per LF		1	Output Score	A++
Risk:		Moderate	Impact weighting (%):	33
Risk revised since last AR?		N	Impact weighting % revised since last AR?	Y

Indicator(s)	Milestones	Progress
Percentage of men and women of civil society organizations that have increased their knowledge on the EITI process and reporting at least 10%.	25% per quarter	Q1 – 70% Q2 – 47%
Overall level of satisfaction among men and women of civil society organizations participating in TCC-led workshops held on monitoring and advocating for improvements to EITI-DRC processes and reporting.	25% per quarter	Q1 – 82% Q2 – 73%
Cumulative number of contributions by groups of members of civil society developed for use in advocacy with key targets of the EITI-DRC process	2	7

Key Points

Through activities contributing to these outputs the Carter Centre has supported the CSO’s ability to monitor and advocate for improvements in the EITI process. Three indicators were set to monitor this output.

Firstly, pre and post tests were administered to participants for EITI trainings to ensure that at least 25% of participants increased their knowledge by at least 10%. This indicator was exceeded in both quarters with 75% of participants increasing their knowledge in quarter one and 47% in quarter two.

The second indicator asked participants their level of satisfaction in training, with an expectation of at least 25% of participants reporting themselves as happy with the training. The Carter Centre also exceeded this expectation recording 82% satisfaction in the first quarter and 73% in the second.

Most importantly for this output, the Carter Centre supported civil society to develop contributions to help shape the local and national EITI process. Whilst it was initially hoped that organisations would be by this stage able to make two contributions – they have already made 7. These memos have included recommendations on improvements needed to move toward the newly revised 2016 international EITI Standard and a memo that has been praised by the national Executive Committee of the EITI advocating for public information on those who solicit mining titles. All of these contributions are publicly accessible on the Carter Centre-run CongoMines.org online mining sector document library and information portal.

Summary of responses to issues raised in previous annual reviews (where relevant)

None

Recommendations

New monitoring and evaluation tools were developed for the logframe to effectively monitor the Carter Centre progress. As these were new tools it was difficult to realistically set reaching objectives, and we feel the ambition needs to be increased for the remainder of the accountable grant.
Output Title	Congolese civil society partners, including women and representatives of CSOs that advocate for the empowerment of women and girls, are trained on mining sector revenue flows and their impacts.
Output number per LF		2	Output Score	A+
Risk:		Moderate	Impact weighting (%):	33
Risk revised since last AR?		N	Impact weighting % revised since last AR?	Y

Indicator(s)	Milestones	Progress
Percentage of men and women of civil society organizations that have increased their knowledge on mining sector revenue analysis in at least 10%.	30% per quarter	Q1 – 67% Q2 – 83%
Satisfaction with TCC-led workshops held on mining sector revenue analysis.	Q1 – 30% Q2 – 40%	Q1 – 87% Q2 – 88%
Cumulative number of interim deliverables completed toward the final revenues impact case study.	0	0

Key Points

For output two, four CSOs are conducting analysis on the financial flows of three different mining operations: ADDH and IBGDH are studying two Glencore subsidiaries in Kolwezi (Kamoto Copper Company (KCC) and Mutanda Mining (MuMi) respectively), whilst COSCCET and DEDQ are collaborating to study Eurasian Resources Group subsidiary Frontier Mining in Sakania. This not only creates an analysis of the financial flows of these companies, but increases the partners’ understanding of revenue flows and payments more broadly as they develop knowledge and skills that can then be applied to future work on mining governance. Training is conducted through a series of eight modules which serves as a step-by-step guide to revenues analysis. Each module links to hands-on tasks that generate components of a final mining project case study.

The first indicator tracks the technical progress that partners are making, with an expectation that at least 30% of participants would substantively increase their ability to understand extractive revenue flows. The Carter Centre has greatly exceeded this with 67% increasing their knowledge in the first quarter and 83 in the second.

The second indicator tracks partners’ satisfaction in the delivered training. Again the Carter Centre greatly exceeded expectations. A monitoring visit by DFID to Kolwezi confirmed the enthusiasm, appreciation and the amount learned by civil society partners.

It is not yet possible to comment on the final indicator as final reports will be delivered at the end of the accountable grant. The Carter Centre, however, reports that these are on track, and it does not foresee problems. The partners are currently at the phase in the modules where they will produce the core of the overall revenue analysis projects: the estimation and verification (where possible) of specific fiscal and parafiscal revenue flows to the state and state-owned companies.

Summary of responses to issues raised in previous annual reviews (where relevant)

None

Recommendations

New monitoring and evaluation tools were developed for the logframe to effectively monitor the Carter Centre progress. We need to ensure that these are set at the appropriate level and we are setting an appropriate level of ambition.
Output Title	Congolese civil society partners, including women and representatives of CSOs that advocate for the empowerment of women and girls, develop interim deliverables for an advocacy strategy.
Output number per LF		3	Output Score	A+
Risk:		Moderate	Impact weighting (%):	34
Risk revised since last AR?		N	Impact weighting % revised since last AR?	Y

Indicator(s)	Milestones	Progress
Percentage of men and women of civil society organizations that have increased their knowledge on data utilisation and advocacy at least 10%.	30% per quarter	Q1 – 100% Q2 – 88%
Overall level of satisfaction with TCC-led workshops held on data utilisation and advocacy.	Q1 – 30% Q2 – 40%	Q1 – 75% Q2 – 75%
Cumulative number of deliverables developed for using EITI-DRC data analysis in the implementation of the advocacy strategy.	23	24

Key Points

Through output three the Carter Centre is supporting two more established civil society operators - Ocean and CDC to do more systematically important analysis of the mining sector. OCEAN is drafting a framework to govern mining companies’ social expenditure declarations in EITI reports and advocating for improved community investments by mining companies. Mining companies are required by their governing frameworks to make social expenditures. Companies often misreport and mislabel certain payments as social expenditures, such as labelling social security payments or relocated residents as social payments, whereas this label should only mark investments in social, human, or community development. CDC is working to ensuring enforcement of the law governing the federal sharing of mining royalties to the state; and assuring the publication of revenues, revenue allocations and uses, and financial statements of SOKIMO and other state-owned mining companies.

The Carter Centre has worked with these partners to design and implement their advocacy campaign, including by leading training modules on advocacy and the provision of adapted technical support for any necessary analysis of the selected issues. Carter Centre assistance has included: in-depth discussions on intended advocacy initiatives and objectives; an evaluation of the partners’ advocacy skills and knowledge of revenue flows and EITI; an evaluation of policy gaps and the identification of objectives to address those gaps; data collection and fact-checking; the definition of an advocacy message and strategy; and support implementing the final implementation of that strategy.

Again all indicators on the support that the Carter Centre has provided have exceeded expectations, with participants making greater than expected progress (indicator one) and being very satisfied with the support (indicator two). Partners have to date marginally exceeded the amount of work we would have expected them to be able to achieve, due largely to CDC’s quick start in the first half of 2016. Highlighted outputs include the development of advocacy strategies, draft governmental decrees for the publication of financial statements and the creation of sustainable development plans, advocacy memos, and presentations to multistakeholder groups.

Summary of responses to issues raised in previous annual reviews (where relevant)

None

Recommendations
None
## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance
The most significant cost drivers for the project are staff salaries, consultant fees, travel, and meetings. These costs represent the bulk of project activities as the Carter Centre’s work focuses on technical support to civil society partners, both in-person and at a distance, as well as on in-depth engagement on key extractive sector issues. Staff are in constant contact with partners, providing instruction and guidance, reviewing activity plans and deliverables, and discussing strategies. While this support is the key driver of cost in the form of salaries and missions, it is also the most significant driver of project performance. In conjunction with the enthusiasm of partners, having the right staff is essential for the project to deliver.

VfM performance compared to the original VfM proposition in the business case
The Carter Centre ensures value for money by focusing on the economy, efficiency, effectiveness, and equity of its interventions. This includes the continuous review and assessment of mission costs, reducing costs where possible; regular oversight for civil society partners, particularly with regard to spending; using existing tools and skills to implement project activities, thus saving time and money; limiting administrative overhead as much as possible; systematically involving women in project activities; and working closely with partners and civil society more broadly to develop the skills and environment necessary to ensure that the project achieves its full impact and that that impact is sustainable. In particular:
- Carter Centre staff regularly review mission costs (meetings and travel). This has led the Centre to identify ways to save costs on travel (combining meetings, lengthening a single mission to avoid multiple missions, etc.) and to update its budget appropriately on a quarterly basis.
- The Centre recently took part in the Birches Group NGO Local Pay salary review of national staff in the DRC. These results will allow The Carter Centre to further ensure that staff salaries are in line with other international organizations operating in DRC.
- The Centre’s sub-grantee selection process included a rigorous assessment of organizations’ technical and organizational capacity, and Centre staff worked closely with selected partners to develop practical and efficient project budgets. In addition, one of the partners and some of the members of other partners have worked with The Carter Centre previously and thus had baseline knowledge of the Centre’s sub-grant policies and procedures, limiting the time needed for onboarding.
- The project relies largely on previously developed training modules (the Revenues Analysis Training Modules and advocacy training modules), which has resulted in staff time and resources saved.

Assessment of whether the programme continues to represent value for money
The project continues to represent value for money. Resources have been used efficiently to provide hands-on support to civil society partners and participate in key discussions on extractive sector governance. Civil society partners have experienced a number of successes already, including the addition of their focus issues to the EITI agenda (social expenditures, payments to state-owned companies, royalties paid to the provinces, etc.). In addition, VfM has been secured through the Centre’s reliance on existing tools, relationships, and technical expertise to implement and support project activities and its assiduous management of project resources.

Quality of financial management
The Carter Centre quarterly financial reports are timely and the staff is available for any questions and clarifications. The financial report narrative could benefit from some analysis on value for money and some comparisons. While some costs have shifted over the course of the project, The Carter Centre anticipates that it will complete project objectives within the scope of the original budget. Staff continuously update the project activity plan, anticipating and adjusting costs as necessary. In addition, cooperation between the Centre’s finance staff in headquarters and field offices has led to enhancements and improvements to financial tracking, reporting, and analysis.

Date of last narrative financial report	30 July 2016
Date of last audited annual statement	31 March 2016

E: RISK (½ page)

Overall risk rating: Minor

Overview of programme risk

Delivery risk – minor - The delivery risk to the programme is minor as the programme is progressing well and exceeding expectations with limited time left until the end of the accountable grant.

Fiduciary risk – minor - A Due Diligence Assessment was undertaken in August 2013 and a refresh to this was also undertaken by DFID DRC’s Governance Team (prior to agree an Accountable Grant with TCC for an elections programme) in May 2015, with the involvement of the Economic Development Team. It is judged from these assessments that The Carter Centre has the capacity and capability to deliver UK aid successfully through the implementation of this programme.

The Carter Centre carried out detailed due diligence assessments on its downstream partners and has conducted substantial financial training to ensure that they are capable of administering DFID funds.

Security risk – moderate – The political cycle in the DRC means that there is increased tension across the country – especially in areas of Carter Centre operations. The arrest warrant issued for Moïse Katumbi in May, for example, and the associated protests saw tension rise in Lubumbashi. To mitigate this risk TCC’s local security advisor works with TCC staff as well as international, national, and local stakeholders to provide ongoing assessments of the security situation and updates plans accordingly. These plans include considerations for provincial travel, contact with embassies and consulates, evacuation routes, relocation of national staff, etc. Based on feedback from the Security Advisor, for example, TCC have closed the Lubumbashi and Kinshasa offices on a handful of occasions to avoid the possibility that staff would be caught in the protests, as well as limiting staff movements in Kolwezi.

Outstanding actions from risk assessment

None

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

On track

Performance of partnership (s)

The partnership with the Carter Centre has been really productive. The team has been very engaged and willing to work with DFID on a range of issues, going beyond the remit of the accountable grant. Outputs are being delivered on time and are to date exceeding expectations. The Carter Centre are responsive to demands and keep DFID informed of developments. This is especially welcomed given that the core project team is based in Lubumbashi, not Kinshasa.

Asset monitoring and control

There are no assets related to the Carter Centre accountable grant.

The Carter Centre, however, kept DFID informed on a loss of assets (new laptop) earlier this year although it’s not related to the DFID funds. The action the Carter Centre took, investigations and introducing way to better secure assets (laptop locks) was appropriate.

G: CONDITIONALITY

Update on partnership principles (if relevant)

None

H: MONITORING & EVALUATION

Evidence and evaluation

Evidence for this annual review has been gathered from:
- Reporting from the Carter Centre
- Discussion and feedback from the Carter Centre
- A field visit to Lubumbashi in February 2016
- Discussions with key stakeholders

Monitoring progress throughout the review period

In addition to quarterly reporting, catch up meetings were held with the project team on a regular basis whenever they were in Kinshasa alongside periodic phone calls. In February 2016 the SRO made a field visit to meet with TCC team and the downstream partners. This provided downstream partners to provide direct feedback on the support from the Carter Centre – which was overwhelmingly positive. The SRO has also discussed the perception of the Carter Centre’s work with key stakeholders in both Kinshasa and Lubumbashi and this has been widely praised.

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. The Aid Management Platform (AMP) and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
A: Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Output Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on AMP as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Minor/Moderate/Major/Severe / Enter: Minor, Moderate, Major or Severe / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on AMP as part of loading the Annual Review for approval). / Where the Risk for this Output has been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section E Risk
Key points
Summary of response to programme issues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D: Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of financial management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E: Risk
Overall Risk Rating: Minor/Moderate/Major/Severe / Enter Minor, Moderate, Major or Severe, taken from the overall Output risk score entered in AMP
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Detail the key risks that affect the successful delivery of the expected results and mitigating actions. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix etc. / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc.) / The Annual Review process