ADDENDUM TO BUSINESS CASE INCLUDING FOR BRIDGE FUNDING AND SCALE-UP COST EXTENSIONS

SUMMARY INFORMATION
Project Name	Somalia Stability Fund II
Country or region targeted	Somalia
Type of cost extension (if applicable)	Cost and time extension
Original project budget	£80 million (£35million DFID funds)
Original project start and end dates	October 2016 - March 2020
Cost extension value (if applicable)	£10million (of other donor Funds)
New project end date (if applicable)	31 December 2020
Business Case Quest Document No.	5445968

INFORMATION
What is the project’s purpose?
The Somalia Stability Fund II (SSF II) is a multi-donor fund working towards a peaceful, secure, and stable Somalia. At outcome level it aims to enhance government legitimacy and reduce political and communal conflict, through the following four outputs (i) fault-lines for political conflict are identified and appropriately addressed; (ii) popular participation in governance is enhanced, particularly for women and excluded communities; (iii) government visibility and community engagement is enhanced; and (iv) community vulnerability to conflict is reduced. / SSF puts a strong emphasis on high quality analysis, flexible and adaptive programming, government ownership and visibility and ensuring a politically informed approach. SSF also aspires to inform wider policy and programming by disseminating and sharing its analysis and learning with government and with the wider international community. / SSF II followed on from the successful implementation of SSF I, which was implemented from 2013 to 2016. SSF II started in November 2016 and is currently contracted to run through to March 2020. The total budget ceiling for the second phase set out in the DFID-ASI contract is £62.7million, of which £55million is Core Fund (CF) and £7.7million is the Fund Manager (FM) fees and expenses, implemented by Adam Smith International. However, the business case anticipated an increasing project budget of up to £80 million, dependent on commitments from other donors. The FM budget is equivalent to 14% of the Core Fund budget and provides technical assistance and operational support to manage the Fund and implement investments to enhance stability in Somalia. The Core Fund provides capital to fund the investments in Somalia. / There are seven donors to the Fund including the UK, EU, Germany, Netherlands, Norway Sweden and Denmark. Phase II builds on a very successful first phase. The Fund is recognised as a key instrument, quick to respond to opportunities on the ground across Somalia. The SSF is present and has access in each of the Federal Member States in the context of a fragile and insecure operating environment. It maintains excellent relations with key stakeholders including the Government of Somalia, multilaterals including the UN and World Bank, key donors who also contribute to the Fund, the wider International community as well as partners and direct beneficiaries of the Fund. SSF has performed well in challenging circumstances, operating with a politically smart and careful approach.
What is the objective of the cost extension or other changes?
To allow the programme to accept additional funding from the six other donors to the Fund. The Business Case sets out an anticipated funding envelope of up to £80 million. This is comprised of £35million of DFID funds along with additional donor contributions. Commitments from other donors have now reached £74 million, with additional commitments anticipated. A cost and time extension is therefore being sought to enable the Fund to receive and spend donor commitments of up to £90 million. This budget increase was anticipated at business case design stage; however, the exact amount of additional funds was unknown at the time. In practice, the success of SSF has led to increased interest from its existing and new donors, with several contributing additional funds as SSF II has progressed. This in turn has led to an increase in the overall budget and size of the Fund. The Fund is expected to have spent the £62.7 million ceiling by July 2019. / The submission also recommends a time extension until December 2020, rather than the existing end date of March 2020. The second phase of the programme has seen a revised strategy with a much stronger link to the programme pipeline. This has resulted in many new activities being programmed across a range of outputs. The time extension will be critical to allow for the gains to be realised from the new programming that has recently come on board. In addition, the time extension will factor in the evolving political and security situation, including a recent break in federal government and member state relations and upcoming state-level electoral cycles, which has the potential to delay project activities on the ground. Extra funds are expected from the Netherlands, Sweden, Denmark, and Norway in line with other donors’ planning cycles. A time extension would allow the Fund to better manage these contextual uncertainties and scale up additional areas of support as identified by ongoing analysis. / This cost and time extension will allow for gains to existing UK investment – including additional results and impact as a result of other donor funding. In addition, owing to the timelines for the spending review, we current face the risk of a gap in funding (owing to approval timelines). This extension would allow us to continue to provide support while design and approval of the next phase is completed. This would also allow for better complementarity with other programmes in the Governance and Security portfolio. For example, an upcoming design mission will explore the possibility of merging existing DFID programme on justice and policing with SSF III. / DFID is the lead donor and contract manager on behalf of the other donors and therefore a business case addendum and subsequently a contract amendment are needed to extend this limit (and to avoid losing the additional funds). / This addendum seeks two sets of approvals. The first is for the Business case amendment which is within the delegated authority of the DFID Somalia Head of Office. The second is approval to proceed with a contract amendment (for additional donor funds). This will need to be approved by PCD and Ministers as it exceeds the £1million threshold.
What is the additional and total support the UK will provide?
There is no additional cost to DFID for this work above the £35 million approved in the original business case. The cost and time amendment will be funded from other donors’ contributions. / The business case estimated additional donor contributions to bring the total size of the fund to £80 million. Additional Funds committed by donors to date have brought the overall size of the fund to £74M. We estimated that additional contributions by Netherlands, Sweden, Denmark, and Norway would bring the total size of the Fund to between £80M and £90M. / An estimated £120K from the original £35 million approved DFID contribution to the Stability Fund, will be used in the extension period to support the Secretariat Office (SO) costs. DFID has seconded an A1 staff member to lead the SO (responsible for strategy and programming oversight). This is a programme funded post-paid by DFID (consisting of salary and costs associated at post). / We are requesting this addendum as DFID is the lead donor and contract manager on behalf of other donors.
What are the expected results?
The additional funds from donors will contribute to the SSF II outcome of enhancing State legitimacy and reducing political and communal conflict. In the results framework these qualitative targets are classified by the following indicators: / Indicator 2: Status of communal conflicts / Indicator 3: Status of political conflicts / Indicator 4: Government legitimacy / The additional funds will allow the Fund to increase the number of investments, across the range of outputs in several districts. This could help SSF to: / Support up to 3-4 new stabilisation districts, in line with FGS/FMS priorities which are currently under preparation, in support of outputs 2, 3 and 4 in the results framework, dependent on access and security conditions. / Support first tier priorities under the AMISOM Transition Plan, for example the clearance of the road between Mogadishu and Baidoa, dependent on access and security conditions and the activities of other partners. / Engage on 2-3 additional key contentious issues contributing to conflict, under output 1, in line with the contextual analysis / Continue its support to reconciliation in Merka, Lower Shabelle, one of the most intractable conflicts facing Somalia today, following the beginning of a mediation process between elders over the past several months. (output 1) / Expand support to women’s empowerment to include a media component, to complement planned leadership training, coalition-building and advocacy support at the district and FMS level. (output 2) / Expand support to regional assemblies, to better meet capacity needs identified through a recent design mission, including support to a women’s caucus. (output 2) / Support the federal government and member states to better coordinate and deliver progress on key transitional tasks, subject to plans of other donors. (output 1) / Extend economic development work in districts where pipeline work is performing well; and initiate complementary work on reconciliation and political engagement where needed. (output 3 and 1) / These aims are subject to the proposed work meeting the SSF criteria for engagement, particularly regarding the ever-changing security situation in Somalia. The below table summarises the increase in results that could be achieved with the budget uplift. / Indicator Current 2019 Target Target with a potential 64% budget uplift / 2.2: Total number of women, youth and minorities supported by SSF to improve their participation in governance Women 529 868 / Men 265 435 / Number of Investments 80 128 / 3.1: Total number of men and women who have benefitted from socio-economic opportunities in partnership with government (i.e. district, FMS, and FGS). Women 1,474,011 1,724,011 / Men 1,474,011 1,724,011 / This increase in programme funds will require a proportionate increase in SSF resources – people and services – to deliver the additional investments. The Fund Manager’s commercial bid for SSF II committed to a highly efficient costing for the Fund Manager, equating to 14% of the Core Fund budget, which is expected to continue with the uplift.
What is the approach to implementation?
ASI was competitively selected to deliver the fund management and technical assistance for the Somalia Stability Fund II, through the restricted procedure of the OJEU tender process. The contract was signed in November 2016 and is a hybrid output-based contract. Supplier fee payments are made subject to achievement of specific predefined milestones, while disbursement to downstream partners (core fund) is made in accordance with satisfactory implementation of agreed work plans between the supplier and downstream partners. / ASI have performed well on Key Performance Indicators and assessment of their performance in both phase I and phase II of the programme has been satisfactory. They have responded well to the changes in delivery requirements between the first and second phases. They continue to be one of the few private sector providers with the presence, reach and access on the ground in Somalia given the ongoing security concerns and associated risks and duty of care limitations faced by other service providers. We are proposing to maintain the current approach to implementation and therefore requesting a cost and time extension to the existing contract with ASI (subject to PCD approval). / The DFID team (SRO & Programme manager) as well as the Secretariat office jointly oversee the day to day activities of the Fund Manager ASI. In addition, SSF holds quarterly strategic meetings with the Joint Donor Committee to ensure Secretariat and FM are on track to deliver against agreed performance criteria and results targets. / We have considered the market options available for delivery. For the reasons stated above as well as the time required to build relationships, infrastructure and mobilise presence on the ground across federal member states, a cost and time extension to the current contract provides the best VfM in this instance. ASI and SSF maintain an excellent reputation on the ground in Somalia which allows them continued access and presence on the ground. The team has invested a lot of time and resources since the start of phase I (since 2012), to become fully operational and ensure efficient delivery through proactive management of risks, downstream partners and in developing an in-depth understanding of the context across the country. / ASI’s commercial tender for SSF II committed to a highly efficient cost for the Fund Manager to be 14% of the Core Fund budget, up to the £62.7m total budget ceiling. Accordingly, as the CF budget increases the FM budget also needs to increase. The current FM cost of 14% is lean, providing excellent VfM especially considering that the Fund continues to invest strategically, remains flexible and adaptive and has enough resources to provide these investments in an effective and compliant manner. / We have carefully engaged the Fund Manager to ensure VfM from the proposed increase in Fund Management fees. The Fund Manager has identified economies of scale and savings that can be made from expenses. Expenses previously made up 40% of the FM budget, but are now at a proposed 33% of the FM budget. The savings realised mean proportionally we’re able to utilise more FM budget for technical expertise to deliver an increased demand for technical assistance and increased portfolio.
Describe any key changes to the original business case including the theory of change or new evidence from ongoing monitoring, evaluation or learning work?
The SSF II theory of change is still in line with that articulated in the business case but it has been substantially unpacked and expanded. The original theory of change had two key steps: 1) a link to the first priority articulated under DFID Somalia’s CPRD: to strengthen political settlements, along with accountable governance, security and local reconciliation, to create more stable, legitimate, inclusive and effective federal states and institutions; and 2) an emphasis on how the Fund works in order to deliver change, i.e. by being agile and responsive, making decisions based on high quality analysis, taking managed risks and being innovative. / The following SSF theory of change diagram, last updated in April 2018, explicitly captures these two steps, captured under outputs (what) and principles (how) below: / This change is in part in response to an independent evaluation of SSF, completed in August 2016, which identified several recommendations to strengthen delivery under phase II. This included a requirement that programming should be informed by an updated strategy and theory of change, which identify more accurately how benefits will be realised and the associated assumptions and risks. Assumptions have been captured in an updated results framework, attached at Annex A. The evaluation further recommended that SSF ensure a clear line of sight from the updated theory of change to SSF investments/programme activities. Accordingly, the theory of change is actively used to shape investment decisions and SSF reports quarterly to donors on the ‘strategic fit’ of the portfolio. / The Evaluation also recommended that SSF produce and update periodically a macro conflict analysis. In line with this, the second phase of the programme places greater importance on the use of analysis. The updated strategy is based on macro level conflict analysis which provides for a better understanding of the political, security and conflict dynamics at the national and Federal Member State level. SSF also conducts quarterly monitoring of the context based on agreed scenarios, to keep its analysis up to date and to inform new investment decisions and risk management. Assumptions are reviewed and tested periodically in line with the flexible and adaptive programming approach. The Fund now has a knowledge management and learning unit to ensure this approach is embedded at all levels of the Fund. The state level scenarios allow for more nuanced understanding of the dynamics at the local level to inform the development of new programme activities and to iterate existing programming. As a result of the strategy and accompanying analysis, SSF has a clearer set of objectives as well as clarity on its role vis a vis other actors working in the stabilisation space in Somalia. / In its second phase SSF has shifted to become a more structured and strategic instrument that more clearly responds to the needs and priorities of its donors, and more strategically targets investments to directly tackle a prioritised selection of the major ‘fault lines’ in Somalia. / Importantly, SSF has also demonstrated its capacity as a learning instrument. Conflict sensitivity has been enhanced through the introduction of gendered district context assessments which provide crucial information to guide design and implementation of projects; government ownership and visibility has been ensured through a strict no-branding policy and associated support to government communications; and SSF has held numerous learning events to share its analysis and advocate for a more joined-up approach across stabilisation partners and donors, informed by shared analysis of the issues.
[note] These numbers are projections and may change subject to further analysis and research on the potential new activities that the Fund will carry implement.