Annual Review - Summary Sheet

Title: : Improving the way knowledge on forests is understood and used internationally (KNOWFOR)
Programme Value: £37,686,887		Review Date: 19 August 2016
Programme Code: 203034	Start Date: July 2012	End Date: September 2017

Summary of Programme Performance
Year	2013	2014	2015	2016
Programme Score	B	A	A+	A
Risk Rating	Low	Low	Low	Minor

Summary of progress and lessons learnt since last review
June 2015-July 206 has been a year of continued progress towards the outcome for KNOWFOR partners. The cost extension period started in January 2016. Partners are adjusting to new targets.

KNOWFOR partners have had notable success influencing policy and practice, both externally and within their own organisations. KNOWFOR has been instrumental in bridging the gap between global dialogue in Forest Landscape Restoration (FLR) and its mainstreaming into national, regional and international plans. Restoration of degraded forest land is now firmly embedded in both the Paris Climate Change Agreement and the Sustainable Development Goals. IUCN is working with its partners to support implementation of the Bonn Challenge[1] and Nationally Determined Contributions[2]. PROFOR has played a pivotal role in developing the World Bank’s new 2016-20 Forest Action Plan. CIFOR’s research into the causes of fire and haze and options for prevention has formed the basis for new programming by Government of Indonesia to invest in fire prevention. CIFOR’s influential Global Landscape Forum Investment Case held in London in June 2016 continues to bring together diverse stakeholders to progress thinking on how to unlock investment for sustainable land use.
[1] The Bonn Challenge is a global aspiration to restore 150 million ha of deforested and degraded lands by 2020 and 350 million ha by 2030
[2] These are the post 2020 pledges made by countries on actions they will take to mitigate climate change under the terms of the Paris Climate Change Agreement

All three partners have made progress in gender integration by strengthening internal systems. The objective of the cost extension to “bed down” principles of good Design, Monitoring, Evaluation and Learning (DMEL), and to extend this to more of each partner’s work is being met.

A survey carried out in May 2016 with over 200 client organisations provides an encouraging snapshot of user perceptions. Over 80% of respondents accessing KNOWFOR partner information regarded it as very high or high quality and 68% believed that information was influential to their work.

All 5 key recommendations from the 2015 annual review have been taken forward:
The logframe has been revised; the International Climate Fund’s Monitoring Evaluation and Learning Programme is familiar with the KNOWFOR approach and has joined the Community of Practice; the partner-led evaluation starts next month; value for money analysis has started; and discussion is ongoing with international partners on harmonising DMEL systems.

Summary of recommendations for the next year
1. This will be the final annual review. Project Completion will take place after the partner led evaluation by December 2017. To maximise learning opportunities, DFID to develop a timetable for key themes, products/processes and opportunities between now and end of programme, by December 2016. This should include an exploration of VfM experience in other DFID knowledge programmes with a view to developing lesson learning and good practice guidance.
2. A further review of the logframe is needed given the 100% achievement of output 2 and ease of achievement of milestones in output 1. Should include a reassessment of whether better indicators can be found (DFID with partners).
3. DFID to explore options for taking forward key policy themes via integration into other DFID programmes (e.g. restoration with resilience, disaster risk and agriculture) by December 2016.
A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/3717343.odt / http://iati.dfid.gov.uk/iati_documents/5054232.odt
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/5437234.xlsx

Outline of the programme
The KNOWFOR programme aims to increase the value and impact of forest knowledge. The programme builds on existing research and knowledge, and focusses on knowledge uptake, seeking to improve the way existing and emerging themes in international forest knowledge are understood, communicated and used to inform policy and practice. To deliver the objectives of the programme DFID works through three main partners:
- Programme on Forests (PROFOR) a quasi-independent think tank located within the World Bank Group (WBG).
- Centre for International Forestry Research (CIFOR) an internationally renowned research centre and member of the Consortium Group on International Agricultural Research (CGIAR).
- International Union for Conservation of Nature (IUCN) which hosts the Global Partnership on Forest Landscape Restoration within its Global Forests and Climate Change Programme (GFCCP).
KNOWFOR provides high quality original and synthesised knowledge products for a wide range of audiences in the forest and land use sectors and addresses the disjuncture between the supply and uptake of knowledge. KNOWFOR places strong emphasis on the enabling conditions and systems required to ensure that knowledge is useful, relevant, timely, and understood by its intended audience, enabling assessment of the extent of knowledge use, influence over decisions, and ultimately, the change it intends to bring about. The main justification for the cost extension to the programme (to October 2017) was to ensure that early progress made on this was fully embedded within the partner institutions.
Expected results by the end of the programme (October 2017) are:
IMPACT: Poverty reduction, biodiversity conservation and protection of climate and other ecosystem services through improved management of forests and trees.
OUTCOME: Policymakers/practitioners in developing countries are equipped[3] with strategic knowledge, comparable evidence, reliable tools and systematic analysis on forests, trees and climate
[3] KNOWFOR is using “equipped” in relation to policy makers and practitioners having access to key forest-related knowledge and information. It is recognised that to be effective, such knowledge and information should be tailored based on the skills, capacity, and broader enabling environment of intended audiences. This “interface” will be the focus of more attention under the cost extension.
Context
This reporting year has seen two significant global agreements to which KNOWFOR partners have made contributions. The Sustainable Development Goals, recognising the need to address degradation as well as protect existing terrestrial resources; and the UN Framework Convention on Climate Change (UNFCCC) Paris Agreement which also made explicit the important role of forests and land use in climate mitigation and adaptation. These agreements will shape the work of KNOWFOR partners for years to come. Additionally, important contextual developments that have affected partners and programme delivery include:

PROFOR: A new Director joined PROFOR in September 2015; the third since KNOWFOR began. The transition has been smooth and the new Director is building positively on the work of his predecessors, investing in improved knowledge management to enable better alignment with major forestry trust funds such as the Forest Carbon Partnership Facility (FCPF), The Forest Investment Programme (FIP), The Global Environment Facility (GEF) and the Bio-Carbon Fund (BioCF). This will afford more customised and targeted dissemination of PROFOR analysis and tools for use by these major international funds, funded by the UK, and will ensure much greater coordinated effort than currently exists.

CIFOR: Core funding to the CGIAR from DFID and other donors is being replaced by more targeted funding. CIFOR has had a significant budget shortfall in the 2015-16 period; though work prioritised under KNOWFOR has not been affected. This has coincided with a restructuring process within the CGIAR Council and Board and the development of the next round of research funding proposals known as the Consortium Research Programmes (CRPs) for the period 2017-22.

IUCN: Because of the overwhelming demand for the application of the KNOWFOR supported methodology for assessing forest landscape restoration options, IUCN has recruited a full time coordinator to engage with 23 countries.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment
The KNOWFOR outcome seeks to demonstrate that policymakers and practitioners are “equipped” with the right knowledge and tools to make effective decisions. KNOWFOR partners have worked hard to demonstrate the extent to which the knowledge they produce has been influential. A new outcome indicator helps to evidence the progress through outcome stories. These illustrate specific examples in detail capturing how the issue was identified, by whom, how the knowledge has been used and whether there are early signs of influence resulting in any changed behaviours.

The outcome level milestones for this reporting period are:

75% (PROFOR and IUCN) and 85% (CIFOR) of activities funded under KNOWFOR are rated as meeting or exceeding expectation in the uptake rubric (a set of criteria to assess evidence of the extent to which knowledge produced has reached intended audiences and been influential)

Outcome stories which demonstrate the “equipping” of policy makers and practitioners for key themes relevant to each partner (3 from IUCN, 8 from CIFOR, 4 from PROFOR)

These represent a substantial increase on the targets set last year, which reflect the progress being made by KNOWFOR partners to change from knowledge product output to outcome and impact focussed knowledge organisations. The examples of success in uptake and influence also reflect the maturity of some of the knowledge streams and/or their political relevance over the reporting period.

Summary of progress against outcome indicators:
All partners are now extending the use of improved approaches to knowledge design, monitoring, evaluation and learning (DMEL) in their activities beyond those funded by KNOWFOR. This was one of the key objectives of the cost extension. This is a significant achievement and bodes well for the sustained improvement that we wish to see in knowledge organisations. All partners have met or exceeded the milestone against the rubric (outcome indicator 1) and for outcome stories (outcome indicator 2).

PROFOR: of the 17 project activities concluded in 2015 12 exceeded and 2 met expectations (82%) therefore exceeding the 75% target. Three project activities however did not meet expectations, mainly due to delayed outreach.

PROFOR knowledge and analytical work helped shape the World Bank Group Forest Action Plan FY16-20 (FAP), notably influencing the FAP in areas related to forest-smart investments, governance, and monitoring and evaluation. Ongoing PROFOR inputs will also be fundamental to its implementation - specifically related to forest-smart investments. This is because PROFOR’s portfolio is developed in close collaboration with regional management, leadership teams and country partners to ensure activities are driven by client country demand. PROFOR activities are implemented by WBG Task Team Leaders (TTLs), which enables strategic thinking and action for the targeted dissemination of knowledge products in-country, and assures that activities are aligned with ongoing policy dialogue and are supported by the Country Partnership Framework. This also aligns PROFOR knowledge closely with potential WBG operations, allowing this knowledge to frequently shape the operation and influence policies and dialogue with external stakeholders.

CIFOR, 85% of the “mature” sub-projects achieving expectations (67% above expectations); eight outcome stories and two outcome assessments have been produced
CIFOR’s research and political economy analysis around the causes of fire and what preventative measures can be taken has been hugely influential again this year. The Indonesian Peatland Restoration Agency (BRG) uses the canal blocking techniques, developed by KNOWFOR’s Fire and Haze project, to promote community based efforts on rewetting peatland. Additionally, the Indonesian National Board for Disaster Management (BNPB) uses CIFOR's research to help explain fire causes. The Ministry of Environment and Forestry based its proposal to the World Bank for a loan of UD200 million to work on fire prevention, on CIFOR’s research. The research has helped raise the profile of and concern for fire management and prevention by the Government of Indonesia. The close engagement of CIFOR with the international community in Jakarta, including the UK Climate Change Unit and UK embassy, further enhanced the political visibility of this work.

IUCN has been able to reach the majority of planned target audiences for 2016 and equipped them with the knowledge and tools needed to commit to, plan and initiate forest landscape restoration (FLR) projects

IUCN, supported by KNOWFOR evidence and tools, has made great strides with advancing the Bonn Challenge. The Restoration Opportunities Assessment Methodology (ROAM)[4] developed with support from KNOWFOR, is now being applied in 23 countries (12 funded directly by KNOWFOR) to support the national and sub-national level assessment of restoration planning and guide implementation. The application of ROAM is demand driven, guided by what countries need to fulfil national and international commitments (Bonn Challenge and Intended Nationally Determined Commitments under the Climate Change Convention). By engaging a wide range of stakeholders, the ROAM process builds ownership and ensures uptake of its results. The assessments provide evidence on how to prioritise areas for restoration, how to identify the most appropriate actions and how to cost these. Unanticipated boundary partners have also been engaged. Asia Pulp and Paper[5] is the first private sector company to announce its commitment to the Bonn Challenge, but other private sector companies like Kingfisher, The Body Shop, and Kimberly-Clarke are interested in exploring how forest landscape restoration could contribute to their sustainability goals.
[4] http://www.iucn.org/content/roam-around-world
[5] https://www.asiapulppaper.com/news-media/press-releases/asia-pulp-papers-commitment-support-protection-and-restoration-indonesian-forest-landscape-accepted-bonn-challenge

A survey of KNOWFOR partner “clients” sought views on the quality and usefulness of the KNOWFOR partner’s knowledge products. Over 200 client organisations or boundary partners representing government, researchers, practitioners, private sector and international organisations responded. Over 80% of respondents accessing KNOWFOR partner information regarded it as very high or high quality and 68% believed that information was influential to their work (an increase of 26% on the 2013 survey).

Overall output score and description
The overall output score is A based on the following scores and weighting:

Output 1 Generating and translating knowledge for action (40%) A
Output 2 partner systems (20%) A+
Output 3 partner collaboration (20%) A
Output 4 Design, Monitoring, Evaluation and Learning influence (DMEL)(20%) A

Key lessons
KNOWFOR funding is not restricted to the generation of knowledge but also to ensuring it is effectively designed and communicated, and that “old” knowledge is refreshed for new audiences. This flexibility has allowed partners to seize important opportunities when demand for certain types of information has been high (e.g. as momentum developed quickly, IUCN was able to capitalise on growing interest from countries and the private sector to join the Bonn Challenge pledge on forest restoration and provide those countries with tailored evidence for their decision making needs at short notice. CIFOR was able to make use of KNOWFOR rapid response funds to turn years of high quality research into influential policy briefing, practical advice and facilitation to address Indonesia’s fire and haze crisis). Flexible funding and adaptive management facilitated this positive opportunism and is an essential part of knowledge generating programmes.

Experience from CIFOR in tackling sensitive or entrenched issues shows that engaging strategically and working in partnership with local institutions and actors is key. They are agents of influence, and in the eyes of local decision makers, have greater legitimacy than “outsiders”, however qualified.

Having a dedicated budget line AND team for gender helps to ensure that gender is rooted in the organisation and integrated across thematic work (CIFOR’s experience).

The highly trans-disciplinary nature of working on landscapes, even within the same organisation, let alone across organisations, takes time to develop. CIFOR, as part of the CGIAR network has developed strong working relationships with other research entities and organisations to carry out integrated research on landscapes. PROFOR has developed new partnerships within the World Bank to bring interactions between forests, agriculture, energy etc. into their analysis and therefore, through joint analysis, starting to break down entrenched investment silos.

Theory based approaches to research/project design are proving to be very relevant to a wide range of partners working on complex landscape and land use related activities. However, organizations have had to respond and adapt with improved organizational skills and capacity, systems, and culture change to take on the theory based and DMEL approaches promoted by KNOWFOR. The changes take time.

Key actions
Further adjustments to the logframe are required. Based on the performance of partners for some targets (notably relating to social media), which have been comfortably exceeded, there is a need to set more challenging targets and/or review whether more nuanced indicators can better capture some of the outputs. DFID should work with partners to make the changes to the logframe by October 2016.

Ensure that adequate attention is focused on lesson learning from both the outcome stories and the process of the partner-led evaluation. This should include learning from those activities which have gone less well, in spite of enhanced DMEL. Partners should ensure lesson learning from less successful activities is also documented.

All partners have received DFID lines but continue to highlight concerns regarding exchange rates and what this might mean for delivery on programme outputs and outcomes. Continue to monitor the situation and assess progress working closely with partners to track implications for delivery. In line with new guidance, engage with a DFID Commercial Adviser should any action be required.

With the programme due to come to an end in October 2017 – it will be important to review where and how important knowledge themes such as landscape restoration might be taken forward to further translate concepts into practical action. Opportunities may exist to integrate restoration more systematically into some of DFID’s programing on resilience, agriculture, disaster risk preparedness. This should be explored by DFID by December 2016.

On VfM DFID should explore opportunities to join forces with other knowledge related programmes to explore the difficult issue of assessing value for money. Many programmes are grappling with this challenge and it would make sense to draw on experience and lessons from other similar programmes. The KNOWFOR MEL budget line has sufficient resources to support this.

Has the logframe been updated since the last review? Yes, to take account of a previous recommendation to ensure milestones were more ambitious, gender focussed, and relevant to the cost extension’s objective (e.g. to ensure that the mainstreaming of DMEL was captured and that “knowledge translation” was taken into account).

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Partners draw on tested approaches and shared learning to create and translate knowledge for action, taking into consideration the needs of women and girls
Output number per LF		1	Output Score	A
Risk:		Minor	Impact weighting (%):	40
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator	Milestones- / June 2016 Target	Progress
1.1 No. of products and range of categories (of which at least 25% either explicitly respond to the specific needs of women and girls or generates sex differentiated gender relevant knowledge)	PROFOR: 90 / CIFOR: 65 / IUCN: 38	PROFOR: 117 knowledge products have been produced, exceeding the quantitative target, based on 32 projects delivered in 2015. Of these 32, only 14 were considered ‘gender relevant’ by the responsible leads. / CIFOR 91 knowledge and communication products during this period of which 34 are specifically gender responsive. These range from peer reviewed journal articles to TV interviews. / IUCN 42 targeted knowledge products ranging from policy briefs, peer review journals, to web and social media materials, on themes such as how FLR can contribute to enhancing food security, livelihoods benefits and ensuring gender responsive restoration planning and implementation Indicator score: A (two out of three partners exceeded the targets significantly, one did not meet gender targets)
1.2 - No. and range of KNOWFOR supported engagement process/events (workshops, forums, meetings, trainings etc.) including gender disaggregated data on participants and evidence of engagement processes that were gender responsive	PROFOR: 80 (> 25% of the participants will be women) / CIFOR: 60 (> 25% of the participants will be women) / IUCN: 17 (30% women)	PROFOR: 95 engagement processes /events, exceeding the target of 80 but failing to ensure that data collected was sex disaggregated. Only 13% were women. It is not clear how many events were gender responsive. / CIFOR: 124 events. CIFOR has reached 5,830 participants of which 36% are women but it is not clear how many events were gender responsive / IUCN: 28 capacity building activities, engagement processes/events, and international events for dissemination, transfer of knowledge and capacity-building on tools and methodologies. 40% female participation and 4 were specified as Gender responsive / Indicator score: B – reporting not providing sufficient information on gender responsiveness to fully meet criteria
1.3 No. and type of products accessed (downloads, distributed etc.)	PROFOR: 7 (5 co-published with partners). Social media reached 50,000. / CIFOR: 1000 downloads, 5000 hardcopies, 80,000 page views / IUCN: 500 downloads, 900 page views, 15 blogs; 7000 material distributions, 500 video views, 1000 twitter followers/ 100,000 impressions, 300 facebook likes /4000 reach	PROFOR: 9 - published 4 books and 5 working papers. In addition, there were 7 co-published Partnership Publications, including those produced in collaboration with the World Bank, FAO, CIFOR, and The Forest Dialogue. PROFOR’s social media presence has seen tremendous growth in 2015, surpassing the 50,000 target.to 55,000 / CIFOR has exceeded its milestone. It has a very active outreach programme and shares knowledge products through Forest News, Twitter, Facebook, YouTube and other online channels: 53,000 downloads, 640,000+ page views, 9,000+ hardcopies of documents were distributed / IUCN: 3,243 downloads, 27 blogs/web stories, 6,700 page views, 6,140 copies of printed material and 2,352 USB-distributed (8,492 in total), 5,050 views on You Tube, 3,479 new followers and 430,900 impressions, 597 facebook likes and audience of 26,800 reached / Indicator score: A+ target exceeded
1.4 - No. of narrative descriptions of good practice examples of creating processes and/or products that identified and delivered on audience specific information needs including at least one example that delivered on the needs of women or girls	PROFOR / 3 / CIFOR / 3 / IUCN / 3	PROFOR met this milestone through 1). ICT in forest governance application – phase II; 2). Institutional analysis and landscape level planning guidelines for watershed development in India; 3). Turkey forest villages: socioeconomic study to better understand the causes of out-migration, forest dependence and poverty / CIFOR met this milestone through 1). tailoring dialogue processes to specific audiences, including women and girls in the areas of fire and haze in Indonesia; the role of forests in Food Security in Ethiopia for example / IUCN has achieved this milestone through 1).Putting Restoration Opportunity Assessment Methodology (ROAM) into practice; 2). Mainstreaming gender considerations in FLR planning and implementation; 3.) Supporting DRC and Burundi in developing a roadmap for the implementation of the Bonn Challenge commitments / Indicator score: A target met

Key Points
This output focuses on the products and engagement processes that partners develop, how they communicate them, and the extent to which they are tailored to or engage with key audiences in doing so. Targets have been exceeded for some indicators, substantially in the case of online presence. This reflects in part how difficult it is to predict targets for online presence, and demonstrates that what is topical or “in the news” can generate enormous interest and therefore demand for information. Some examples of knowledge translated for action:

The CIFOR-organised “Global Landscape Forum Investment Case”[6] event in London in June 2016 was an opportunity for all KNOWFOR partners to showcase their work and tailor messaging to a financial services and private corporations audience. The event brought together leaders from the financial services industry, the corporate sector, government and academia to explore the role of private finance in enhancing livelihoods and landscapes across the globe. Participants included high-level decision makers from Standard Chartered, HSBC, BNP Paribas, The Body Shop and Kingfisher. Chris Botsford, CEO of ADM Capital reflected: “I think it’s been a great Forum. And I think what’s really positive about it is they’ve got a lot of people from different angles looking at problems. And so you put the problem on the table and you’ve got a lot of different people giving a lot of insight and coming up with some really interesting solutions. And in five years people will say, gosh, that was really the starting point, right here at CIFOR.”
[6] GLF The investment case 2016
IUCN made optimal use of targeted outreach with compelling blogs, videos and other web based materials on International Women’s Day (March 8), International Forest Day (March 21) and World Water day (March 22) achieving a higher than expected on-line and social media presence. The video titled ‘Equipping Uganda for restoration: Radio and apps for Reforesting Landscapes[7]’ was chosen as a winner of the Global landscape Forum 2015 Partner Video Award.
[7] https://www.youtube.com/watch?v=ZsmunU87Dgg

PROFOR’s outreach activities took forward the Turn Down The Heat III report which explores ecosystem shifts and impacts as a result of climate change. They organised a very successful side event for Latin American countries capitalising on the infrastructure of the Massive Open Online Course (MOOC) under UNESCOs Our Common Future Under Climate Change conference pre-Paris[8]. Feedback indicates an increased sense of empowerment amongst civil society organisations to engage and an increase in networking amongst Latin American organisations.
[8] see http://www.worldbank.org/en/events/2015/05/27/training-on-carbon-balance-appraisal-of-agriculture-forestry-and-land-use). TDTH III (LAC) Presentation at : “Our Common Future Under Climate Change” (7-10 JULY 2015 Paris, France)
At the request of the Ethiopian Ministry of Agriculture and Natural resources, CIFOR provided a forest nutrition expert to formulate recommendations for the inclusion of nutrition-sensitive interventions in the Ministry of Environment, Forestry Development and Climate Change as part of the government’s second national nutrition programme that is focused on a multi-sectoral approach. This advice was built on CIFOR’s growing body of evidence on the importance of forests for dietary diversification and nutritional outcomes.
Summary of responses to issues raised in previous annual reviews (where relevant)
Ambition was raised for the targets relating to this output. Despite this some have been easily surpassed although the quality of supporting evidence is good. There has also been some difficulty in fully reporting on all aspects of the indicators, mainly the degree of gender responsiveness. This appears to be due to systems not capturing this information adequately under work streams started pre-DMEL, rather than the products, events and process not being gender responsive. Given the achievement under Output 2, which includes fundamental criteria on gender, we will expect to see the gender responsiveness dimension to indicator reporting under this output improved across all partners as all these new work streams mature.

Recommendations
A comprehensive review by DFID and partners of the indicators under this output is required as soon as possible to raise the level of ambition beyond numbers of products and or processes and follow up to ensure that measures are in place and working to adequately track gender responsiveness.

Output Title	All partner activities have an explicit, evidence based logic and assumptions that can be tested to facilitate learning
Output number per LF		2	Output Score	A+
Risk:		Minor	Impact weighting (%):	20
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator	Milestones / June 2016 Target	Progress
2.1 - KNOWFOR is rated as ‘Meeting expectations’ or ‘Above expectations’ in the ‘Enabling’ rubric (rubric includes criteria such as whether project planning included identification of next users and knowledge pathways and the differentiated needs of women and girls).	PROFOR / 60% of projects will meet or be above expectations in the design rubric / CIFOR / 100% projects meet the expectations in project planning rubrics / IUCN / 100%	PROFOR has exceeded this milestone. All new Concept Notes met expectations and PROFOR staff worked with project leads to ensure all criteria are addressed in all Concept Notes developed since late 2015. / CIFOR has met this milestone fully. All projects implement the DMEL framework;.irrespective of funding source. / IUCN has met this milestone for the first time by ensuring that all relevant projects initiated under different result areas addressed the criteria. The thematic areas to which the rubric was applied included application of ROAM, development of knowledge products and tools for gender-responsive FLR, Green growth and FLR, Enhancing food security through FLR, Raising awareness about benefits of FLR and sustained outreach and advocacy effort / Indicator score: A+ fully met ahead of time

Key Points
This output was developed with partners at the first annual review of KNOWFOR. It has been a critical foundational output to ensure that all work supported by KNOWFOR applies the principles of sound design (engaging with audiences and potential stakeholders early on), that outreach and communication is built into the proposed activities from the beginning, that gender is fully considered, and knowledge uptake pathways clearly set out.
All partners have for the first time this year met the target fully and earlier than expected in the case of PROFOR. This is a significant achievement and suggests that programme partners and others they work with are seeing the benefits of using KNOWFOR systems.

Recommendation
Given the early 100% achievement of the end of programme target, a decision on how to proceed with this output should be taken by DFID with partners by October 2016.

Output Title	Improved collaboration across KNOW-FOR partners
Output number per LF		3	Output Score	A
Risk:		Moderate	Impact weighting (%):	20
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator	Milestones- June 2016	Progress
3.1 - No. of instances and narrative description of when partners collaborated to develop shared understanding, products or influence external actors on appropriate DMEL approaches	6	Partners achieved their target. Partners worked closely on a range of initiatives that shared lessons and enhanced their own understandings through the KNOWFOR community of practice, built on joint work to develop products to reach internal and external audiences and shared lessons with external audiences at two international conferences. / Indicator score: A target met
3.2 - No. of instances and narrative description of when partners collaborated to develop shared understandings, products or influence external actors on gender responsive practice	4	The KNOWFOR partnership has given a platform for the gender teams within these three organizations to collaborate on joint knowledge products and policy engagements. 8 instances in total have been reported. This has prompted an upsurge in collaboration between World Bank forest trust funds which is to be welcomed. / Indicator score: A+ target exceeded
3.3 - No. of instances and narrative description of when partners collaborated to develop shared understandings, products or influence external actors on forest landscape restoration	6	KNOWFOR partners have collaborated on 6 occasions. They have promoted FLR-related initiatives in two geographies: Brazil and the Mozambique. The focus has been on the application of ROAM, strengthening governance, making the business case to farmers, developing a mobile tool, organising a regional conference on FLR in the Miombo region, and promoting sustainable charcoal production. Indicator score: A target met
3.4 - No. of DFID initiated information requests relating to topics of operational, strategic or political interest responded to by partners. These requests may include briefing, outcomes stories, case-studies etc.	Provision for up to / PROFOR:3 responses, CIFOR:4 responses, IUCN:3 responses	PROFOR – no requests reported / CIFOR received 2 requests - / Fire and Haze rapid response project in close collaboration with the UKCCU in Indonesia and Summaries of research findings on Miombo woodlands and charcoal production in support of the development of a DFID business case / IUCN received 1 request: Gender integration in forest landscape restoration case study / Indicator score: B Demand led and therefore targets only indicative. Indicator not well framed.

Key Points
This output was developed at the first annual review in 2013 to encourage more collaborative working and co-learning on a number of themes (DMEL in knowledge programmes, Gender and forests, landscape restoration). This was done with a view to demonstrating that the collective efforts of three partners working on common issues, harnessing their institutional comparative advantages, could maximise value for money, bring added value to the advancement of certain knowledge areas and extend the outreach to different audiences, in a way that would not happen if they worked in isolation. For example, CIFORs research is critical to provide credible evidence to influence decision takers, IUCN draws on the research to improve practical guidance for users, and PROFOR leverages this collective effort to influence and direct additional financing via World Bank activities. Although still early to assess whether this hypothesis holds, the partner led evaluation has included questions to explore this.

Collaboration between potential competitors for resources has taken time, but has taken off this year with some important progress being made under indicators 3.1-3.3.
DMEL Partners continue to work jointly, and with other interested parties through the KNOWFOR supported Knowledge into action community of practice (CoP). In February 2016 Partners presented a session entitled “What is effective aid in a research for development context? Using theory-based approaches for designing, implementing and evaluating research for development programmes” at the Australian National University Aid Policy conference. In July 2016 CoP members presented their experience and lessons learnt on research to impact at the Evidence on Trial Durham conference.
In 2015 KNOWFOR partners undertook a study to assess which factors helped or hindered successful uptake of new DMEL approaches. Results from the study showed that investments have already led to improved understanding and practice changes among activity managers. Continued work and investment is needed to translate these early achievements into sustained and ingrained DMEL practices; the justification for the cost extension[9].
[9] http://www.iucn.org/news/knowledge-forests-ensuring-learning-start-finish
Gender: A cross partner gender working group has been formed to take work forward within partner organisations, but also to engage with other partners. For example, the group met in the World Bank with representatives from agriculture, natural resources, the gender cross cutting group, the Forest Carbon Partnership Facility (FCPF) and Forest Investment Programme (FIP) to explore how to get the most out of the new World Bank Gender Strategy and ensure improved gender integration within forest sector and landscape activities. The FCPF’s gender team then took the synthesis of knowledge from the KNOWFOR Gender Working Group seminar, presenting it at the 21st annual FCPF Participants Meeting in May 2016 in Washington DC. At a dedicated gender session, forests, agriculture and climate change specialists from over 30 participating FCPF countries discussed gender and REDD+ issues, examples and progress.  The outcome was a summary of at least 10 specific gender-responsive actions that REDD+ country teams can take forward.

Restoration: The partners have selected two geographies to collaborate on landscape restoration. These are in Brazil and the Miombo woodlands of Mozambique. In Mozambique PROFOR and IUCN prepared a common proposal to support landscape planning and testing of the restoration opportunities assessment methods developed with KNOWFOR support. The test phase was so successful that the World Bank’s IDA financed MozLandscape Project will support the scale up of ROAM at the provincial level. At the same time, the Forest Investment Programme in Mozambique (MozFIP) is also considering the same for the remaining provinces. The findings from the first test phase were presented at a Miombo conference held in Mozambique in July 2016 (funded by IUCN and PROFOR). Additionally, CIFOR has collaborated with the World Bank’s MoZFIP team to provide guidance on sustainable charcoal. As part of the same collaboration, PROFOR also supported the financial assessment of forest concessions, which will determine how Mozambique shapes its strategy on concession management; supported by MozFIP. This work provides an excellent example of how the collaborative working by the three partners, each working to their strengths, has shaped substantial investments, including in the FIP, to which the UK is a major contributor.

In Brazil, IUCN and PROFOR have worked with State Authorities in Sao Paulo to demonstrate the economic benefits of different forest restoration models to farmers which is crucial to help them comply with the new forest code and diversify their sources of income. Given this is a national requirement; the potential uptake of this work is very significant. A mobile app is also being developed to help extension agents disseminate the models and test the willingness of farmers to implement them.

Recommendation

Indicator 3.4 was developed at the end of the last reporting year to capture requests that were being generated by DFID at the time, requesting tailored information. Since this is responsive to demand from DFID it has been difficult to meet the indicative targets. The B scoring for this indicator is therefore not a reflection of poor performance. In its current form, this indicator does not generate sufficient information of quality to merit continuation. DFID, in consultation with partners, should review this by October 2016.

Output Title	KNOWFOR partner organisations have the systems, culture and expertise for effective design, monitoring, evaluation and learning and influence practice of internal colleagues and programmes
Output number per LF		4	Output Score	A
Risk:		Moderate	Impact weighting (%):	20
Risk revised since last AR?		New Output	Impact weighting % revised since last AR?	New

Indicator	Milestones / June 2016	Progress
4.1 - No. and narrative descriptions of partner organisation work that has been influenced by KNOWFOR DMEL approaches	PROFOR: 4 (note: WAVES Partnership Programme; PMEH Programme; Korean Green Growth; External and Corporate Relations (ECR)) / CIFOR has fully mainstreamed the DMEL. Process in all KNOWFOR work and 6 examples outside KNOWFOR use theory based approaches and are recorded in outcome stories / IUCN: 5 non KNOWFOR initiatives influenced directly by KNOWFOR learning	PROFOR has met this milestone by influencing other WB Trust Funds to follow the DMEL approach. There are possibilities of further influence of DMEL approaches in other programmes managed by the Bank. / CIFOR – Milestone achieved. Inception meetings have been done for all the new KNOWFOR sub-projects. A number of non-KNOWFOR funded projects have adopted KNOWFOR tools. 6 outcome stories from activities outside KNOWFOR funding have been completed. / IUCN has met this milestone - 5 projects/programmes not funded by KNOWFOR within IUCN influenced by KNOWFOR DMEL approach. / Indicator score: A target met
4.2 - Evidenced narrative of attainment against jointly developed organisational DMEL performance expectations	Evidenced narrative demonstrating the following agreed criteria for DMEL performance: / Enabling environments: incentives to promote use of DMEL system, use of DMEL outputs in planning, increased investment in DMEL / Internal practice changes: Generic tools adapted and refined, systematic use of monitoring tools, , evaluative data informs project management, comfort with learning from failure / Influence DMEL practices of partners: Share implementation lessons with other donors and practitioners, influence DMEL practices of partners	PROFOR has made significant progress in raising awareness about DMEL, and in influencing practice among many project leads in the Bank. Achieved primarily through a systematic overhaul of its project cycle templates which now focus much more on DMEL relevant issues, such as a clear theory of change, the demand and audience for the intended activity, and the dissemination plan, etc. In addition, PROFOR staff have helped Task Team Leaders (TTLs) develop their concept notes, particularly in articulating a ToC and indicators to track influence and impacts. TTLs have become increasingly convinced about the value of paying attention to DMEL issues, and PROFOR believes that the opportunity provided by KNOWFOR has started to influence a change in the right direction. / CIFOR has created a very strong enabling environment, including in the new 2016-2025 strategy to promote the use of DMEL in all CIFOR projects. CIFOR has also created 2 new teams to allow a better control on how projects are funded, designed and run ensuring crucial issues like DMEL, Gender, Communication and Engagement are considered and funded. The KNOWFOR DMEL framework, approaches and tools have also been used in CIFOR’s phase II of the FTA research proposal, representing partial or complete adoption by core partners (ICRAF, Biodiversity, CATIE, CIRAD, Tropenbos International and INBAR). / IUCN - IUCN has made significant progress towards attainment of jointly developed organisational DMEL performance expectations. Examples have been provided to evidence that IUCN has successfully met all aspects of this milestone. / Indicator Score: A target met

Key points
This is a new output designed to capture the objectives of the Cost Extension. It focuses on the extent to which the improved processes for knowledge design, management, monitoring, evaluation and learning have influenced the working practices of the partner institutions beyond what is directly financed by KNOWFOR. For long term sustainability and to maximise value for money in research and knowledge provision, it is important that these processes are embedded within the institutions.
Steady progress is being made although this varies between partners. CIFOR has embraced the approach strongly, facilitated by the fact that it is aligned with a drive within the CGIAR to improve on the same elements covered by the KNOWFOR DMEL approach. The major success story for CIFOR is the mainstreaming of DMEL approaches across the new CGIAR Forests Trees and Agroforestry (FTA) research strategy, which covers 3 CGIAR research institutions and a further 4 external partners. The research programme is worth a potential $450 million dollars.

PROFOR’s adoption of the improved approach has been noted by the advisory board for bringing value to PROFOR’s work. This is significant since it is a multi-donor trust fund where the introduction of non-Bank systems is not usual. Since access to funding and approval of project concepts now requires compliance with DMEL principles, the incentives are clear. PROFOR has made progress in challenging the mind set of Task Team Leaders given this is not a requirement elsewhere in the Bank. Those that have been through the process see its merit, particularly noting the difference it makes to exposure and uptake.

PROFOR staff were requested to provide guidance in the design of monitoring and evaluation frameworks for four Trust Funds in the Bank. These included: Energy Sector Management Assistance (ESMAP); The Korean Green Growth Programme; Pollutions Management and Environmental Health (PMEH); and the Wealth Accounting and Valuation of Ecosystem Services (WAVES). Three of these are DFID funded. KNOWFOR DMEL has therefore influenced practices beyond PROFOR, in programmes which will run until 2020 and beyond.

IUCN has worked on improving audience identification and targeting across their forest portfolio through social media network analysis. They commissioned work which found:: Social media managers can use social media network maps and reports to gain a “situational awareness” of a set of topics that could be too large to master by manually reading all the streams of tweet and messages. With a weekly or daily map and report (depending on the speed of the conversation) a social media team can gain an overview in minutes that would otherwise take hours of reading messages. Network metrics take social media managers beyond follower count to better gain insight into the size, shape, structure and dynamics of social media topic stream.”

The findings from the report have been adopted by IUCN’s Global Forests and Climate Change knowledge and outreach team. As a result of this work, they are increasingly targeting “mayors”[10] within IUCN’s Twitter network with tailored content to reach as many key people as possible with their messaging.
[10] Mayors are those people in a network with the highest “centrality”. They are in the “middle” of the network and may be the people with the greatest influence or power to be heard in the conversation.

Recommendations
As part of the consultation with external stakeholders in the partner led evaluation, ensure that examples cited here are contacted and explored.

Encourage more discussion and reporting around where mainstreaming DMEL has failed or where there has been resistance to change and why.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

The reputation and pre-eminence of the three partner institutions were the primary drivers for their selection as KNOWFOR partners. Overhead and administrative costs, however, particularly of CIFOR, were identified as key cost drivers.
CIFOR, partly due to its operating location, has the highest management costs amongst the partners. CIFOR committed to reducing its overhead costs from a high of 29% in 2009 to 15% by 2015. CIFOR has successfully exceeded this target and now reports that overhead costs are 14% which is quite an achievement given exchange rate losses and resource constraints this year and reductions for a second year running of core funding due to CGIAR governance transition. CIFOR continues to see demand for its research grow at unprecedented levels and it is currently placed 3rd out of the 15 CGIAR centres in terms of most visible and cited research institutes.
CIFOR has adopted a risk management strategy which includes a framework which identifies, evaluates and prioritises risks and opportunities across the organisation, develops risk mitigation strategies which balance benefits with costs, monitors the implementation of these strategies and periodically reports to its Board on results.  Most of the identified risks to CIFOR operations are as a result of the 2014 and 2015 budget cuts and the CGIAR governance transition which is currently underway.  CIFOR has mitigated any impact on science quality by adjusting operations (e.g. saving of $150k on travel costs within the last 12 months by creating an internal travel broker position (recycling an existing member of staff). A bilateral programme such as KNOWFOR is likely to be shielded from internal cuts, but should these begin to have a significant effect on key cross cutting support functions, this would be cause for concern. We will monitor the situation over the remaining lifetime of the programme.
CIFOR has been awarded its “7 pillar assessments” from the European Commission (EC) which confirms efficiency and effectiveness in its procurement, sub-contracting procedure etc. CIFOR also continues to negotiate low overhead rates from partner institutions with which it collaborates.
IUCN has continued to demonstrate that KNOWFOR’s support to its work on FLR represents good VFM for the UK government. The investment in the ROAM methodology has far out performed expectations with 23 countries now actively using the methodology to help design and implement their restoration objectives. IUCN has trained 150 people from 25 countries and created champions who are now able to support ROAM training in their own languages, regions and countries. Overhead and administration costs remain reasonable at 8% given the global reach of the work.
PROFOR can demonstrate VfM through different levels:
- Economy – by tapping into technical networks of the World Bank to build dialogue with clients at the country level. Leveraging technical networks and expertise from other sectors within the WB e.g. energy, agriculture etc, leveraging co-financing from several partners.
- Efficiency – by producing outputs of the required quality at the lowest cost through pre-established quality review processes at the Bank which seek to maximise productivity and ensure overheads remain low at 5%. Making use of new large scale online fora to get their messages out to large audiences.
- Effectiveness – PROFOR activities have a high rate of influence, with two national policy reforms and 30 World Bank operations influenced in this reporting period.
VfM performance compared to the original VfM proposition in the business case
In addition to the VfM measures identified in the Business Case, the following examples demonstrate the significant leveraging contributions made by the programme, in terms of both influence and investment.
The CGIAR’s new $450+ million research proposal on Forests Tress and Agroforestry, led by CIFOR, presents significant potential value for money if approved. It has been heavily influenced by KNOWFOR adopting a fully integrated approach to improved DMEL across all partners involved. Based on the hypothesis that better DMEL results in better targeted knowledge with more uptake and impact, this will be a significant value for money contribution from KNOWFOR.

A CIFOR project on bushmeat in Central Africa co-funded by KNOWFOR, USAID and a FAO/GEF project –developed the evidence to convince the European Commission and the Secretariat of the African, Caribbean and Pacific States to invest 45 million Euros in a new “Wildmeat” programme.

Co-financing for the PROFOR portfolio in 2015 (out of a total value of $9.9 million) was $6.8 million and every $1 invested by PROFOR leverages $25 in World Bank forestry project investments. This leveraging ratio is based on the value of the forestry components of 15 World Bank investment projects active in 2015 that were directly influenced by PROFOR. This has increased from $1 leveraging $8 in 2012.

IUCN were awarded a $54 million grant for a new forest restoration project under the Global Environment Fund. Much of the analysis that went into the programme design was generated under the KNOWFOR programme, and DMEL principles are fully embedded. This programme will help to take forward implementation in 10 countries.

By investing in new approaches in DMEL, KNOWFOR partners have improved understanding about knowledge uptake in the forestry sector and ultimately influenced how knowledge programmes are designed and managed. The Theory of Change for improved DMEL suggests that implementation of new approaches is leading to more effective knowledge uptake projects being designed, implemented, monitored and learned from. This continues to be tracked over the remainder of the programme. Given the common challenge to all of DFID’s knowledge programmes, in developing VfM metrics, the programme should consider how to compare learning across other DFID programmes.
Assessment of whether the programme continues to represent value for money
The KNOWFOR programme continues to represent value for money, and is making a demonstrated impact on the way in which organisations operating in the forestry sector deal with and plan for the uptake and results evaluation of knowledge products. The mainstreaming of KNOWFOR’s DMEL approach in the CGIAR FTA research proposal worth $450 million (including likely UK finance) will ensure that the research carried out follows best practice principles and should therefore, in line with KNOWFOR’s theory of change, result in uptake and impact.
Quality of financial management

Date of last narrative financial report	PROFOR: Due by October 2016 / CIFOR: 31 December 2015 / IUCN: 31 December 2015
Date of last audited annual statement	PROFOR: 30 June 2015 (2016 report due soon) / CIFOR: 31 December 2015 / IUCN: 31 December 2015

CIFOR has passed the European Commission’s Seven Pillars Assessment on its internal control and accounting systems. This is an independent external audit and sets out rules and procedures for providing financing from EU funds through grants, procurement and financial instruments and Sub-Delegation

CIFOR has shown resilience and management adaptability to ensure that budget cuts are managed well, and they have not affected the delivery of KNOWFOR outputs. In the most recent audit report it states that CIFOR is still financially stable and within CGIAR recommended guidelines for level of cash reserve.

E: RISK (½ page)

Overall risk rating: Minor

Overview of programme risk
Knowledge programmes are difficult to assess for impact, and therefore carry inherent risks; however, progress on embedding a robust DMEL approach is helping to ensure that the programme delivers on its objectives and focuses on uptake. The achievement of output 2 is a good indication of progress being made in mitigating this risk.
Partners have expressed concern that the poor exchange rate for the GBP against the USD may affect some deliverables. We have agreed that we will review this situation periodically to assess whether any revisions will be required, and note recent guidance that any adjustment would be discussed first with a DFID commercial adviser.
There is a risk that the long term sustainability of the systemic changes underway in partner organisations may be undermined should institutional resource constraints, beyond KNOWFOR, affect the ability of partners to sustain cross cutting systems such as DMEL. It is expected however, that the benefits of improved DMEL are becoming more apparent and are considered sufficiently good value for money to survive any cuts.
Fiduciary risk in the programme is low. No financial losses have been reported. Audits have been carried out on all programme partners and these are clear and unqualified.
Outstanding actions from risk assessment
This programme pre-dates due diligence guidance and requirements; however, as the KNOWFOR partners are reputable international organisations with well-established financial systems, and two are administered through World Bank managed Multi Donor Trust Funds, significant risks from poor institutional capacity to manage DFID funds is low. With the approval of the cost extension a light touch due diligence exercise for the IUCN was undertaken during the reporting year. No areas of concern were uncovered.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
The programme is on track when assessed against the logframe.

Performance of partnership (s)
DFID continues to have a good working relationship with all three programme partners. The past year has seen increased collaboration between the three partners, both on individual events and research initiatives, and in the continued development and embedding of the DMEL approach. KNOWFOR has been crucial in fostering this collaboration and new way of working between the partners, and the partners now engage in regular meetings and discussions on opportunities for joint work without the convening support of DFID.
Partners have also actively engaged in the planning stages of the upcoming partner-led evaluation of KNOWFOR and their continued engagement will be monitored and any learning from the process documented at the end of the evaluation.
Asset monitoring and control N/A

G: CONDITIONALITY (½ page)
Update on partnership principles (if relevant): N/A:

H: MONITORING & EVALUATION (½ page)

Evidence and Evaluation
There are characteristic challenges in monitoring and evaluating knowledge programmes (e.g. issues of attribution, lengthy timeframe in seeing impact of investments, topicality of issues can impact on their visibility). The DMEL approach is helping to combat some of these challenges in an innovative way.
Partners have worked collaboratively on this approach as set out in outputs 3 and 4. To enable this change, partner internal systems have been adapted/improved and through use, changes in individual practice are being observed with staff and partner training also playing a key role in the successful implementation of the approach.
An improved uptake theory of change to ensure that knowledge products are designed well and implemented more effectively and are able to generate evidence-based lessons to share with the sector has been developed. DMEL is also helping KNOWFOR partners to actively address gender issues and ensure that gender is a key consideration in the knowledge produced.
Clear Horizon continues to provide high quality support to partners on the application of DMEL and will also play a critical role in supporting partners and coordinating inputs across the partner-led evaluation process.
KNOWFOR partners are now able to assess progress at the intermediate outcome and impact levels using tools such as episode studies, outcome stories, performance story reporting etc. This will continue to be developed over the remaining period of the programme and form a key part of the evidence for use under the partner-led evaluation.
The partner-led evaluation of KNOWFOR starts in September 2016. Procurement of an external critical friend to accompany and quality assure the process is currently under way. This is not an evaluation approach commonly used in DFID, so we will ensure that progress is shared through the KNOWFOR community of practice, and other parts of DFID. The terms of reference for this work include the requirement to capture lessons about the partner-led process as well as about the quality of the partner-led evaluation, and the work itself.

Monitoring progress throughout the review period
DFID holds regular on-going meetings with all partners to address key issues including tracking of programme milestones. A technical meeting was held with all partners in January 2016 to set priorities for the cost extension period. During this visit, DFID took the opportunity of engaging in field visits to meet collaborating partners and understand first-hand the impact of research on the ground. An evidence gathering and planning meeting with all three partners was held in July in preparation for this annual review and to finalise plans for the evaluation. DFID attended the PROFOR annual advisory board meeting in April 2016 which provided information on progress against PROFOR deliverables, including updates on financial situation, and views from other donors.
This annual review has been led by DFID in collaboration with all KNOWFOR partners who provided comprehensive individual reports and supporting evidence to inform the annual review.