Project Completion Review - Top Sheet

This Top Sheet captures the headlines on the programmes performance over the course of its lifetime. Teams should attach summary sheets from each annual review over the life of the programme.

Review Date:	August 2016

Title: Providing humanitarian assistance to disaster affected population of Gorno Badakhshan Autonomous Oblast in Tajikistan
Programme Code:	Start Date: 14/09/2015	End Date: 30/06/2016
If programme was closed >1 month early please describe in a few words why.	n/a

Summary of Programme Performance

Year	2016
Programme Score	A
Risk Rating	Minor

Financial Position

Original Programme Value	£94,780
Extensions/ amendments	No cost extension only
Log-frame revisions (with dates)
Total programme spend	£94,870

Follow up actions required following closure
N/a

A. Introduction and Context (1 page)

DevTracker Link to Intervention Summary :	https://devtracker.dfid.gov.uk/projects/GB-1-205136/documents
DevTracker Link to Log frame:

Outline of programme and what it has achieved
FOCUS implemented the humanitarian project as part of the disaster relief efforts in Gorno Badakhshan Autonomous Oblast (GBAO) following severe mudflows in July 2015. These mudflows in various areas of GBAO resulted in loss of human lives, internally displaced families, and paralyzed critical infrastructure. In Barsem village, the debris flow filled up water channels and blocked the Gund River and formed a lake that inundated additional areas including residential houses and posed significant risk for communities downstream. The Government of Tajikistan appealed for financial and technical support from the international community. The project implemented both humanitarian relief and post-disaster interventions to mitigate the risk and impact of future disasters. Both disaster and post-disaster efforts were mainly focused in Shugnan district, the most affected area in GBAO.

During the first hours following the mudflows and floods, the affected population were in need of life-saving humanitarian items. FOCUS instantly dispatched the locally available emergency stocks which decreased the amount of existing emergency stockpiles. DFID’s support enabled FOCUS to restock its emergency stockpiles and be well prepared for any future humanitarian disaster response. DFID’s fund also supported the bathymetric survey by international experts of the newly formed lake in Barsem village to identify possible risks and mitigation actions. Based on the findings from this bathymetric survey, DFID funded the construction of mitigation structures to reduce risks and impact of future floods and mudflows.

In total, DFID’s support benefited 9,807 individuals, including 4,707 women and 565 vulnerable people (including female headed households, pregnant women, people living with disability and old people). It provided emergency relief to affected people and reduced people’s vulnerability to future natural disasters.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Overall Outcome Assessment
DFID’s support benefited 9,807 individuals in GBAO affected by mudflows and floods, including 4,707 women and 565 vulnerable people (including female headed households, pregnant women, people living with disability and old people). Funds were used to purchase non-food items and pre-position emergency stockpiles for 100 families, including all-weather family tents, mattresses and blankets. These stockpiles are a critical component of disaster preparedness activities and will meet the immediate emergency needs of any future crisis-affected people including women, girls, children, elderly and handicapped.

A bathymetric assessment was carried out for the ‘artifical’ lake that was created in Barsem village as a result of Gund River blockage by the debris flow. The assessment concluded that this lake had accumulated almost 3 million cubic meters of water and the blockage caused by debris’ prone to collapse. The potential risk of collapse posed a significant risk for approximately 1,300 households in 20 villages living downstream (including households in GBAO administrative center – Khorog town). Based on this assessment, mitigation measures were taken through the construction of a debris diverting wall and clearance of the stream channel from sediments in Barsem villages. This significantly reduced future hazard risks for over 200 households or 1,413 people (50% women; 14% children; 17% elderly) living in Barsem village and other villages downstream.

The below table provides a breakdown of the beneficiaries by key activity.

Table 1: Number and groups of beneficiaries covered through project

	Beneficiaries
Activities	Households	Population	Women	Vulnerable groups[1]
Stockpile replenishment	100	594	257	98
Bathymetric assessment	1,300	7,800	3,744
Constructing debris diverting wall	208	1,413	706	467
Clearing of debris flow stream channel
Total:	1,608	9,807	4,707	565
[1] Pregnant women, persons with disabilities, single female headed households, older persons, children

Output Score and Description

Output description	Impact weight	Risk	Score	Indicator number and whether targets are on-track
Output 1: Emergency stockpiles are replenished and accessible in Shugnan district	40	Minor	A	1.1 A - Achieved / 1.2 A - Achieved
Output 2: A Bathymetric survey is conducted for the newly formed Barsem Lake	20	Minor	A	2.1 A - Achieved
Output 3: Stream channel is cleaned and diverting dam is constructed in Barsem village	40	Moderate	A	3.1 A - Achieved

Lessons and how these have been shared
- FOCUS worked closely with the local government and local communities. It coordinated closely with the regional and local government to ensure that any disaster response and rehabilitation efforts were complementary. Through working with the communities, FOCUS ensured their contribution in kind (labour) to the mitigation works. This has created a strong ownership and communities’ commitment to maintain the structures in the future.
- Emergency stockpiles should cater humanitarian needs in both summer and winter conditions. In 2015, GBAO was affected by mudflows and floods during the summer, followed by an earthquake in the winter, December 2015. These disaster events showed that non-food items should cater to the basic needs in winter as well as summer time. For example, following the earthquake, FOCUS has tested the procurement and use of all weather tents and traditional tents (yurts).
- Careful consideration should be given to the type and quality of emergency non-food items to address the specific needs of the most vulnerable people, i.e. people living with disability, pregnant women, children and elder people, such as the composition and quality of hygiene kits for women and young infants.
- FOCUS indicated the need to increase the stockpile-per-family ratio and bring it to at least, and ideally above 5% of total households in the province. The recent disasters showed that the 3% ratio as recommended by the internationally recognised Sphere standards[2] was insufficient to address the number of affected people given their high level of vulnerability to various natural disasters in the region.
  [2] Sphere was initiated in 1997 by a group of humanitarian non-governmental organisations (NGOs) and the International Red Cross and Red Crescent Movement. Their aim was to improve the quality of emergency response and to be held accountable for them. Sphere framed a Humanitarian Charter and identified a set of core and minimum standards in key life-saving sectors which are reflected in the Sphere Handbook: water supply, sanitation and hygiene promotion; food security and nutrition; shelter, settlement and non-food items; and health action.
- FOCUS is currently exploring options the use of Unmanned Aerial Vehicle (UAV) in emergency assessments and bathymetric surveys. This technology, although costly, would enhance possibilities for conducting assessments in more remote and less accessible areas
- FOCUS demonstrated their ability and commitment to adaptive programming by adjusting implementation to emerging needs and ensuring complementarity with other donor and government interventions. It showed the importance of strong coordination of emergency and disaster efforts with government and donors.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Emergency stockpiles are replenished and accessible in Shugnan district
Output number per LF		1	Output Score	A
Risk:		Minor	Impact weighting (%):	40%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Target June 2016	Achieved June 2016	Score
Output indictor 1.1: Number of families with access to emergency stockpiles	100	100	A
Output Indictaor 1.2: Number of storage facilities for stockpile items	2	2	A

Key Points

Following the mudflows and floods in July and August 2015, FOCUS released its emergency stockpiles across GBAO to help affected people meet their urgent humanitarian needs. The stockpiles in the critical locations were exhausted and required replenishment. DFID’s funds were used to competitively procure new non-food stockpiles for 100 families, including tents, blankets etc. To provide best possible value for money, FOCUS started an open and competitive tender. During the tendering process it became clear that local Tajik suppliers could not deliver quality emergency family tents. The order for 100 all-weather family tents was placed with a Pakistan-based company specialized in manufacturing tents and shelters, blankets, relief supplies. The products and services of this company comply with internationally accepted standards. FOCUS had used their services in the past.

All items for the emergency stockpile were purchased and delivered to FOCUS office in Khorog town. The stockpiles’ items are stored in FOCUS emergency warehouse in Khorog and also pre-positioned in key locations across GBAO. These stocks are usually released in the event of emergency or disaster. FOCUS provided a detailed list and status of the items purchased as part of the humanitarian assistance project as part of the final progress and financial project report.

Summary of responses to issues raised in previous annual reviews (where relevant) –
N/A

Recommendations for future programmes
- Emergency stockpiles should cater humanitarian needs in both summer and winter conditions. In 2015, GBAO was affected by mudflows and floods during the summer, followed by an earthquake in the winter, December 2015. These disaster events showed that stockpile contents should be upgraded with items that can appropriately cater to the basic needs of affected individuals in winter as well as summer time. Tents should be larger, ventilated and be comfortable in hot as well as cold, more extreme weather conditions.
- Emergency stockpiles should address the specific needs of the most vulnerable people, i.e. people living with disability, pregnant women, elder people. FOCUS is aware and has already procured items that are specifically relevant for vulnerable groups but has identified ways to further improve their response to address their specific needs, such as hygiene kits for women and young infants.
- FOCUS indicated the need to increase the stockpile-per-family ratio and bring it to at least 5% of total households in the province. The recent disasters showed that the 3% ratio as recommended by the internationally recognised Sphere standards was insufficient to address the number of affected people given their high level of vulnerability to various natural disasters in the region.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	A Bathymetric survey conducted for the newly formed Barsem Lake
Output number per LF		2	Output Score	A
Risk:		Minor	Impact weighting (%):	20%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Target June 2016	Achieved June 2016	Score
Output indictor 2.1: Bathymetric survey report completed	Bathymetric survey report completed	Report completed	A

Key Points
The mudflows resulted in large volumes of debris blocking the natural flow of the Gund river which runs through Barsem village. As a result, an artificial lake was formed in Barsem village flooding significant part of the village and posing significant risks to villages located downstream in case of a sudden burst of the blockage/dam. A barthymetric survey was needed to assess the situation and identify possible risks and mitigation actions. Using the programme budget, two international experts from the Moscow State University (MSU) were hired to assess the water volume of this new lake formed as a result of blockage of Gund River flow. It was the first time in Tajikistan that an indepth barthymetric survey was carried out using advanced technologies, such as an echo-sounder. Aside from identifying the volume of the newly formed lake (around 3 million m3 as of the day of the survey), the experts from the MSU checked the dynamics of the water level, the surface of the lake (378 thousand m2 as of the day of the survey). A detailed report and map of the lake was produced as a result of the survey. Copies of the report with map were presented to the partners from the regional government of GBAO.

Summary of responses to issues raised in previous annual reviews (where relevant)
N/A

Recommendations for future programmes
- There are around 130 remote mountaineous lakes in GBAO that are not properly assessed. These lakes pose risks to the communities living downstream. More detailed volumetric assessments and surveys would help identify potentially dangerous lakes. This information could feed into FOCUS’s disaster management and preparedness work across GBAO.
- Conducting bathymetric surveys with advanced technology like Unmanned Aerial Vehicle (UAV) would enhance possibilities in more remote and less accessible areas. FOCUS is currently exporing this option.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Stream channel is cleaned and diverting dam is constructed in Barsem village
Output number per LF		3	Output Score	A
Risk:		Moderate	Impact weighting (%):	40%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Target June 2016	Achieved June 2016	Score
Output Indicator 3.1: Number of households are protected from the threat of debris flow	200	208	A – Target met

Key Points
The amount of debris brought down by mudflows filled up the stream channel in Barsem village and significantly reduced its capacity to carry any future loads of debris and sediments. There was a high risk of significant damage and loss of life in the event of future floods and mudflows. The bathymetric survey concluded that a potential outbreak would pose significant risk for approximately 1,300 households in 20 villages living downstream (including households in GBAO administrative center – Khorog town).

The rehabilitation of irrigation channels was funded by the World Bank (WB), and therefore no longer covered by DFID funds as initially intended. Based on this assessment, DFID instead funded the mitigation measures including the construction of a debris diverting wall and clearance of the stream channel from sediments in Barsem village. In case of future mudflows, the debris flow will be diverted away and will significantly reduce the risk of damage and loss of human life. The Government of Tajikistan constructed an additional water channel to gradually release water from the lake and avoid further major accumulation of the water.

The nature of mitigation works required the use of heavy-duty machinery and specialised engineering expertise. Through a competitive tender, FOCUS outsourced the mitigation work to two licensed contractors, a Limited Liability Company “Panj” and a private entrepreneur “Sobir Alimamadov”. Both contractors have their own heavy machinery (excavators, bulldozers, heavy trucks) and are specialized in engineering, roads clearance, rivers and channels clearance and excavation works and riverbank reinforcement works. Community members contributed in kind through labour and helped with the construction of the retainment wall near their houses. This ensured the community’s commitment and ownership to maintain the wall with minor repairs within the means they have. Due to cold weather and frost, the mitigation works could not be finished by end of December 2015. The activities had to be postponed and resumed in the spring of 2016 and were finished by June 2016.

The cleaning took place in two phases. During the first phase, which began in 2015, 400 meters of the channel was cleaned. The second phase started in March 2016 and involved cleaning the upper reaches of the channel (135 meters). A retaining wall was built on both banks of debris stream channel to protect the houses located on both sides of the channel. On the right bank the diverting wall is 200 meters long, 4 meters high, and 3.8 meters wide. On the left bank the wall is 100 meters long, 4 meters high, and 3.7 meters wide. The cleaned stream channel is now around 5 meters deep and 15 meters wide. The cleaning increased the carrying capacity of the stream channel and reduced the potential for flood damage to the residential areas. The diverting wall helps in prevention of erosion of the banks, which was posing a direct threat for 3 households. These mitigation measures have significantly reduced future hazard risks for over 200 households or 1,413 people (50% women; 14% children; 17% elderly) living in Barsem village and other villages downstream.

Summary of responses to issues raised in previous annual reviews (where relevant)
N/A

Recommendations for future programmes
- Close consultation with the government and community engagement is critical when identifying the risks and mitigation measure and implementation of mitigation measures. In this case, a range of complementary mitigation measures were taken including construction of a new water channel from Barsem lake for gradual release, the debris diversion channel and rehabilitation of irrigation channels.
- Explore mitigation approaches taken in similar contexts in other countries. Mitigation measures could include fairly simple infrastructure yet good quality requiring limited maintenance.
- Need for adaptive programming to adjust implementation to an evolving context. In close consultation with DFID, FOCUS changed some of the initial planned interventions in response to emerging needs and opportunities while ensuring complementarity to other interventions covered by the World Bank. It showed the importance of strong donor coordination of emergency and disaster efforts to ensure complementarity of interventions.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance
The cost of the construction materials and machineries, procurement of stockpile items were the main cost drivers of this project.

VfM performance compared to the original VfM proposition in the business case
The overall Value for Money was not be affected by the no-cost extension of the project. Due to prolonged freezing temperaturs during the winter season, the clearing of the stream channel in Barsem village had to be stopped for almost three months and resumed in March 2016.

Assessment of whether the programme represented value for money
The project represented Value for Money through competitive procurement of construction materials, stockpile items and construction company. The order for 100 all-weather family tents was placed with a Pakistan–based private company specialised in manufacturing relief supplies and global warehouse services. The products and services of the company comply with internationally accepted standards.

FOCUS contracted two licensed suppliers for the implementation of the mitigation works. Both contractors are specialised in engineering, road clearing, excavation work, riverbank reinforcement works and use their own heavy machinery. Through the competitive procurement, FOCUS ensured that the quality of products and services met the required standards respresenting value for money.

FOCUS worked closely with the local government and local communities. It coordinates closely with the local government to ensure that any disaster response and rehabilitation efforts are complementary. Through working with the communities, FOCUS ensured their contribution in kind (labour) to the mitigation works. This has created a strong ownership and communities’ commitment to maintain the structures in the future.

Quality of financial management during programme
FOCUS submitted a detailed financial report on July 15, 2016 along with the final progress report after the project completion. The quality of financial report met required standards. While the overall budget expenditure was within the total allocated budget, two budget lines showed a larger spend than previously estimated. These larger expenditures were fully justified given the specific nature of the disaster response. First, high quality and professional flood lights were required to monitor the perimeter of the flooded Barses lake at night time. These professional searchlights will also be important for future emergency responses including search and rescue, evacuation, and perimeter monitoring during floods and critical water levels. Second, a high quality, special inflatable emergency tent was procured to be used for emergency response teams. This light weight tent can be used in various geographic and climatic conditions and is easy to set up. It was and will be used as a mobile Emergency Operation Centre (EOC) by various disaster reponse stakeholders, including Government and NGOs, to operate and coordinate disaster response operations.

Date of last narrative financial report	15/07/2016
Date of last audited annual statement	n/a

E: RISK (½ page)

Quality of risk management over the life of the programme

Overall risk rating: Minor

Overview of programme risk
FOCUS is a trusted and effective implementing partner with a strong expertise in emergency response and preparednes. From March 2009 until October 2014, DFID provided support to FOCUS. Independent Audits found FOCUS management and financial systems robust. The main programme risk was bad weather affecting programme implementation which indeed happened. The onset of the winter delayed the finalisation of output 3 within the initial timeframe. A no-cost extension of 6 months allowed the completion of output 3 as well. The programme can be closed with all outputs having been met.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
The programme delivered against the planned budget but did not deliver against the planned timeframe. Originally the programme was approved for four months period from September 2015 to December 2015. Due to the cold weather and continued frost, the mitigation works could not be completed before December 2015. The activities were postponed and resumed in the spring of 2016. The project received a no-cost extension and all activies were finished by 30 June 2016.

Performance of partnership (s)
N/A

Asset disposal and value obtained by DFID
A range of assets were purchased including non-food items, inflatable light-weight tents, winterised tents and other equipment needed to support the emergency response. All items were purchased through a competitive procurement process in line with FOCUS procurement guidelines. All items have been handed over to FOCUS at programme closure and will be used for future emergencies. Three assets had a value of above £1,000 including a generator (£4,530), an emergency rescue boat (£3,840) and 2 cargo containers (£1,272 each). The generator and emergency rescue boat are stored in FOCUS’s premises and will be used for future emergencies. The cargo containers have been placed in local communities and and are used as store emergency stockpiles such as matrasses, tents, blanket etc, only to be opened in case of emergencies.

G: CONDITIONALITY (½ page)

Partnership principles assessment
The UK does not have a formal partnership principles agreement with either the Tajik government. However, DFID Central Asia does monitor government commitment to the principles and uses the findings of this assessment to determine how and where to direct UK Aid.

Based on the latest review of the principles for both countries, undertaken in February 2016, DFID does not provide financial aid directly to government although some of our programmes with International Financial Institutions and third parties provide technical assistance and other support subject to rigorous financial controls.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation
No new evidence has been identified that has implications for this project.

Monitoring progress throughout the programme
DFID and the FOCUS programme team had regular communications over phone, email and face-to-face meetings. This supported adaptive programme management to respond quickly to evolving developments. For example, DFID’s support initially also included the rehabilitation of irrigation channels damaged by the mudflows. Given the findings of the bathymetric survey and willingness of World Bank to fund the rehabilitation of these irrigation channels, DFID and FOCUS jointly agreed on construction of mitigation measures to reduce future risks and impact of disasters. Part of the funds were also used for the procurement of high-quality all weather tents.

From 25-28 April 2016, the DFID Livelihoods Adviser and the Programme Manager conducted a monitoring visit to the project sites to see progress made and learn about FOCUS work and the particular challenges faced by the communities prone to regular disasters such as avalanches, mudflows, floods, and earth quakes. During the visit, the construction of debris flow diverting structure and the clearing of debris pathway were still onoing. The visit showed the tremendous scale of the undertaking, progress made and huge commitment shown by the FOCUS team and the local community.
Smart Guide
The Programme Completion Review is the opportunity to reflect on the entire programme, its performance, achievements, lessons and how learning will be shared to inform future programming.

The Programme Completion Report assesses and rates outputs using the following rating scale. The Aid Management Platform (AMP) and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with headline information on the programme and any follow up actions / Early closure is likely to be summed up by issues such as ‘poor performance by partners’ and/or ‘major changes in operating environment’
A: Introduction and Context
Briefly outline the programme, results achieved and contribution to the overall Operational Plan and DFID’s international development objectives. Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Outcome Assessment / Brief assessment of whether the programme achieved the Outcome
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Output Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on AMPas part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Minor/Moderate/Major/Severe / Enter: Minor, Moderate, Major or Severe / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on AMP as part of loading the Annual Review for approval). / Where the Risk for this Output has been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section E Risk
Key points
Summary of response to issues raised in previous annual reviews (where relevant)
Recommendations for future programmes
Repeat above for each Output.
D: Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case. Performance against vfm measures and any trigger points that were identified to track through the programme / If programme was closed >1 month early please describe in a few words why, what savings were made, as well as what money was spent.
Assessment of whether the programme represented value for money? / Overall view on whether the programme was good value for money
Quality of Financial Management during programme / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E: Risk
Quality of risk management over the life of the programme. / How were risks managed, the degree to which they were realised and/or mitigated? / Did any risks materialised throught the duration of the programme which were not forseen? What where they and how was this managed? / What lessons have been learned?
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / Could DFID be a more effective partner
Asset disposal and value obtained by DFID / How were assets managed throughout the programme? How have they been (or will they be) disposed to get maximum value?
G: Conditionality
Partnership principles assessment / For programmes where we have decided to use the PPs for management and monitoring, PCRs should generally include an assessment of commitment to the PPs, including any concerns that have occurred over the year, the partner government’s response, and details of any response by us. Teams should refer to the DFID guidance on reviewing projects.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the programme / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review and PCR process