Annual Review – post April 2019

Title: Political Settlements Research Programme (PSRP)
Programme Value £ (full life): £6,541,250		Review Date: 1 April 2020
Programme Code: 204326	Start Date: 01/04/2014	End Date: 29/03/2021

Summary of Programme Performance
Year	2015	2016	2017	2018	2019	2020
Programme Score	A	A	A+	A+	A+	A+
Risk Rating	Medium	Moderate	Moderate	Moderate	Moderate	Minor

DevTracker Link to Business Case:	Business Case
DevTracker Link to Log frame:	Logframe

A. Summary and Overview (1-2 pages)

Description of programme (1/2 page)

The Political Settlements Research Programme (PSRP), led by Edinburgh University, is a DFID-funded Research Programme Consortium (RPC). The research explores how donors can shape ‘political settlements’ - the rules that regulate the access of elites to resources and power – to reduce poverty and reduce the risk of conflict. PSRP has established a database of over 1,800 peace agreements which, together with research from the programme, is informing the content, choice and targeting of interventions to reduce the risk of conflict and broker peace, by donors, diplomats, and civil actors, in fragile and conflict-affected states (FCAS).
PSRP had an original budget of £4.4m over four years (2015-19). Based on the PSRP consortium’s strong performance, and very high demand for further research and policy engagement, DFID funded a time and cost extension of £2.2m for 2 years (2019-2021).
PSRP focusses on three broad themes:
1. How different types of political settlement emerge, and which actors, institutions, resources, and practices shape them;
2. How political settlements can be improved by internally-driven initiatives (i.e. by directly involved parties), including the impact of gender-inclusive processes and rule of law institutions;
3. How, and with what interventions, external actors can change political settlements.
The research is explicitly comparative and uses a mix of qualitative and quantitative methods, with substantial field work. Research to date has focussed on Afghanistan, the Democratic Republic of Congo (DRC); East Timor; Ethiopia (Ogaden); Liberia; Nepal; Nigeria; Philippines; Sierra Leone; and Somalia, with comparison with less fragile settings: Colombia and Northern Ireland.
Following a competitive procurement process a consortium led by University of Edinburgh was contracted to implement the programme. The consortium was reduced in size as part of the extension. It currently includes: Edinburgh University, Conciliation Resources, Austrian Study Centre for Peace and Conflict Resolution and International IDEA.

Summary supporting narrative for the overall score in this review (1/2 page)
A+ (Output and performance exceeds expectations). PSRP has exceeded the targets set out in the logframe: publications including peer reviewed journal articles (Output 1), uptake through events and social media (Output 2) and engagement of southern researchers in the programme (Output 3). Impact from the research programme has been detailed through case studies and feedback provided by PSRP and verified by DFID. This is summarised below.
UK Policy influence:
UK Conflict Policy: Edinburgh University researchers have worked closely with HMG teams to make the case for a longer term, evidence-based, approach to conflict resolution in countries that are high priorities for the National Security Committee (NSC) and for DFID, such as Afghanistan, Somalia, The Sudans and Yemen.
PSRP research is informing the ‘Integrated Review of Defence, Diplomacy and Development’ and new DFID programming on ‘Conflict, Security and Justice’. PSRP research is heavily cited in the ‘UK Government’s Approach to Stabilisation’ published in 2019. PSRP publications this year are summarised in Output 1 and listed in full in Annex A.
[note] https://www.gov.uk/government/publications/the-uk-governments-approach-to-stabilisation-a-guide-for-policy-makers-and-practitioners
Key publications this year, drawn on by DFID/FCO teams, are.
  - Transitional administrations/governance e.g. Sudan, Zimbabwe and Lebanon.
  - Response to Civil Protest (draft), e.g. China/Hong Kong, Lebanon and Iraq.
  - Peace Implementation Mechanisms, e.g. Sudan, S. Sudan and Zimbabwe.
  - Interstate Agreements e.g. Syria, Yemen, Afghanistan and Libya.
UK Country Policy: PSRP researchers have provided advice to senior officials (ambassadors, DFID heads of office and their teams) working on peace processes during times of crisis - a service for which there is growing demand. PSRP ran sessions this year with FCO/DFID Somalia, Sudan, South Sudan, Kenya, Yemen, China, Lebanon, and several sessions at the DFID-convened Conflict and Stability Research event in Nairobi, November 2019.
Rapid Response’ and ‘Futures Research’. Demand for the ‘futures research’ has been high among country teams. These go beyond PSRP’s ‘rapid responses’ to questions raised by teams, with research on topics likely to be at the forefront of future peace efforts e.g. electoral reform options in Somalia. PSRP has also produced papers responding to country teams on: civic protests, use of ‘backchannels’ in peace processes, implementation mechanisms and Trust Funds. Feedback from all teams was that PSRP’s service was fast, relevant and of higher calibre than other knowledge services available to DFID advisers and FCO country experts and researchers [?], enabling DFID and FCO to review clear options against comparative examples at critical moments in a political transition. This advice enabled teams to make decisions on how their programmes should adapt to political changes and allowed HMG officials to propose options to negotiators and mediators.
International Policy influence: engagement with the staff of international organisations:
Multilateral Policy on Peace Processes: PSRP has built further on its engagement with the UN (particularly UN/World Bank Conflict Prevention Study. ). This year PSRP:
[note] United Nations; World Bank. 2018. Pathways for Peace: Inclusive Approaches to Preventing Violent Conflict. Washington, DC: World Bank. © World Bank. https://openknowledge.worldbank.org/handle/10986/28337 License: CC BY 3.0 IGO.”
[note] World Bank (2011) ‘World Development report on conflict’ https://siteresources.worldbank.org/INTWDRS/Resources/WDR2011_Full_Text.pdf
- Presented research to the Organisation for Security and Cooperation in Europe (OSCE) which then drew on PSRP to draft a paper on transitional financing mechanisms.
- Presented research to the Economic Community of West African States (ECOWAS) contributing to discussions on conflict resolution in Nigeria and the wider region.
- Was cited in UN documents on UN Security Council Resolution 1325 regarding women, peace and security. These drew on PSRP’s published reports on women and peace processes, and current PSRP data (2019).
- Continues to support the UN as it re-orientates its approach under the UN Secretary General’s ‘Sustaining Peace Agenda’. As key UN institutions for political affairs and peacekeeping are merged at headquarters level, PSRP has commissioned research to help them consider how country operations should respond to interim transitions to supplement, and oriented its interim transitions project to answer questions from the field, and circulated a draft paper exploring options for UN support to Sudan which will be further developed in 2020 through planned PSRP visits to Khartoum (travel permitting).
Operational Support to Peace Processes: PSRP researchers have directly supported civic actors engaging in peace processes in Libya, Yemen, Syria, Columbia, Ethiopia and South Sudan.
- Yemen: ongoing support to office of the UN Mediator and to Yemeni civil society actors through the ‘Yemini Voices Platform’, and translated several research papers into Arabic, as requested by Yemeni actors.
- Ethiopia: helped parties to resolve longstanding tensions in Ogaden region. Conciliation Resources continues to provide support following an agreement reached in 2019 (see last AR).
- Sudan/s: supports Sudanese and South Sudanese civil society actors in their respective processes.
- Provided technical and research expertise to discussions on electoral design relating to Somalia.
- Africa: events in Nairobi and London for over 60 African representatives from over 12 countries to discuss how local peace agreements are negotiated, and their contribution to local and national peace. These, with the local agreements database developed by PSRP, make an important contribution to an area of peace-making often overlooked by the international community.
Recommendations for the year ahead (1/2 page)
In its final year, PSRP should focus on uptake, and ensuring that its legacy sustains beyond DFID funding.
Finalising the research.
1. PSRP to complete all research projects (e.g. particularly on ‘local agreements’). with outputs published on the website or shared in draft with DFID by March 2021
2. PSRP to continue ‘rapid response’ support to HMG until March 2021.
3. PSRP to develop short ‘Futures Research’ papers for each country on key conflicts which combine: analysis of the agreements reached to date, unresolved or contentious issues, the positions or red lines taken by key parties, any key points from country specific analysis conducted by PSRP to date, and any factors likely to affect future progress. These to be finalised by March 2021.
Uptake.
1. PSRP to deliver at least one major research uptake event with HMG in London, and ideally with UN and other international actors (either combined in London, or in the US/Europe) by March 2021. Alternative online events will be considered by DFID if Coronavirus makes these unfeasible.
2. PSRP to provide podcasts to accompany key research publications e.g. on elections, constitutions, ceasefires, amnesties, inclusion, implementation mechanisms, intra-state agreements, transitional governance, responding to civil unrest, sequencing of peace processes and the role of women in peace making, by April 2021.
3. Final versions of the top facts and infographics to be shared with DFID by March 2021.
4. PSRP to provide DFID with 1 page outlining options on how its ‘peace tech’ initiative could enable support to peace processes and research uptake during the coronavirus outbreak by April 2020.
Responsible closure for the last year
DFID funding to PSRP is due to end on 31st March 2021. PSRP should ensure responsible closure by: ensuring the sustainability of the database and website, seeking alternative funding, managing staffing implications and by focussing on targeted uptake to ensure the research developed is fully utilised. PSRP to provide short summary of closure plan to DFID by September 2020.
Update logframe
PSRP to draft and DFID to agree revised logframe reflecting focus on research uptake, by June 2020.

## B: DETAILED OUTPUT SCORING (suggest 1 page per output)

Output Title	High quality, relevant, timely and reliable research delivered on political settlements
Output number per LF		1	Output Score	A+
Impact weighting (%):		40%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
1.1 Number of high quality, policy relevant, new evidence on peace and political processes published (e.g. articles published in peer reviewed journals).	4 articles, book chapters or report in peer reviewed outlets	Exceeded: 7 journal articles this year.
1.2 New datasets capable of supporting ongoing research	New local peace agreements database produced.	Exceeded: / Local Agreements Database created, plus 3rd major update of PAX database. PAX Database has been updated.
1.3 Number of high quality policy relevant publications, (e.g. number of policy briefs, working papers and blogs).	4 briefing papers, 5 blogs, 3 rapid reaction briefs.	Exceeded: / 13 briefing papers, / 7 Rapid Reaction Briefs / 5 Blogs.

Provide supporting narrative for the score

PSRP has exceeded publication targets, delivering high quality journal articles (1.1) and producing a wide range of policy relevant publications (1.3). These include papers on: Transitional governance, implementation arrangements, and women’s contribution to peace making. This is particularly impressive given that the research programme, now in the first year of the extension, is working on half the budget of previous years.
PSRP and DFID asses policy relevance in two ways. Research gaps or trends are identified by understanding new peace process data which has not received scholarly attention (including PSRP’s data), and ongoing contact with international and national organisations involved in peace processes such as the UN’s Standby Mediation Network, or the various Networks of Women’s Mediators, or dilemmas from parties seeking to broker peace are learnt from joint analysis from those in the field. We also jointly assess opportunities for research to inform pressing peace negotiations through direct requests from those involved. This year demand has been particularly high in the Sudans and Somalia. PSRP’s publication reach is impressive, with citations in academic research, broadsheet and online media and demonstrated uptake among senior mediators (See Output 2).
1.1	PSRP exceeded the target for Journal articles published this year and has consistently published around 7 journal articles per year. It largely publishes in specialist human rights and peacebuilding journals. Publications are listed with web links in Annex A.
1.2	PSRP exceeded the target for new datasets, updating the peace agreements database (the third version since its launch in 2018). This raises the number of agreements in the database to 1824, an increase in 300 from the 1509 included in 2018. PSRP remains the only global dataset of peace agreements and processes that can be searched by specific provisions and key words with comprehensiveness and functionality across all stages of a peace process, and this helps to sustain high use.
PSRP’s new database on local agreements has also been developed this year. It currently includes 242 agreements from 19 countries, likely to rise to 250 once additional agreements are added from Central African Republic and South Sudan. Data includes (a) geo-referencing of agreements (b) background information on their relationship to national level processes (c) and translation of agreements where possible. PSRP has, for example, either translated or found translations for 24 local Yemeni Agreements and 65 local Syrian agreements. The collection and translation of agreements has been time intensive. Several agreements are ‘cross border’ e.g. Ethiopia-Kenya, and some conflicts have multiple conflicts within them. The PSRP consortium’s work on this has also drawn attention to, and informed, a vital but often overlooked part of global practice.
1.3	PSRP exceeded the target for policy-relevant papers. Highlights this year are outlined in the table below. These papers, together with earlier published work, now make PSRP’s collection the ‘go-to’ reference point for HMG policy makers working on peace processes. They are being used by Ambassadors and their teams working on all priority ongoing conflicts.
This year’s paper on how disability is included in peace agreements is an important addition to the PSRP collection on inclusion, and to DFID’s wider commitments on disability.
PSRP policy papers on women and peace-making continue to have impact at the UN and to contribute to the UK’s National Action Plan on UN Security Council Resolution 1325 regarding Women Peace and Security.
Table 1: Highlights from publications produced by PSRP this year (full list and links provided in Annex A)
Date	Type	Description
Aug / 2019	Policy Paper	Interstate Agreements for Solving Intrastate Conflicts. The paper outlines how agreements between multiple states are made to resolve conflict within third party states (in contrast to inter-state agreements dealing with conflict between the two states signing the agreement). This is particularly relevant to countries where major regional powers are involved either as direct conflict actors (as in Syria), or geopolitical underwriters of either the conflict or the peace process. There are 2 patterns to these agreements. / - When multiple states in a region agree to convene a process (e.g. Great Lakes for DRC, ECOWAS for Liberia, ASEAN and other states for Cambodia) / - When bilateral agreements involve neighbouring states, or those that are close to a conflict affected country or have historic ties with the conflict. (e.g. UK-Ireland, Israel-Jordan, Armenia-Azerbaijan- Russia over Nagorno Karabakh) / The incentives for regional agreements tend to include: self-interest (e.g. regional stability), to raise the reputational cost of non-compliance for the domestic parties, to provide alternative ways to legalise agreements as treaties, to deal with multiple levels of the conflict and peace process together, to promotes specific norms recognised at the regional level, as a mechanism of innovative regional brokerage. ) / http://www.politicalsettlements.org/publications-database/interstate-agreements-to-end-intrastate-conflicts/
Oct 2019	Policy Paper	Implementation Provisions. A peace agreement signals the end of one process but the beginning of another difficult implementation process which can break down at any point for decades afterwards. Implementation can include monitoring, verification and sometimes enforcement mechanisms. Implementation can be undertaken by protagonists, civil society, government entities, international actors or a hybrid of these. The paper sets out when and how peace agreements provide mechanisms for their own implementation. / http://www.politicalsettlements.org/publications-database/how-peace-agreements-provide-for-implementation/
September / 2019	Policy Paper	Trust Funds (2 reports), are a means to improve equitable distribution of political, economic, and legal power and create or restructure institutions to improve governance of a state or sub-state entity. They are a popular approach to consolidating post agreement arrangements though their effectiveness depends on how they are designed. When well-designed they can catalyse optimism for peace, assist implementation of specific peace agreement provisions, enable the allocation of resources to sub-state regions, incentivise parties to abide by the agreement or to continue negotiations on unresolved issues. While they tend to be managed by an international body their focus is on implementation by domestic entities, stressing the importance of addressing domestic interests. They can often be impeded by the absorption capacity of domestic institutions that have often been damaged during conflict. / Report 1 sets out the ways in which peace negotiations provide for trust funds / http://www.politicalsettlements.org/wp-content/uploads/2019/08/Trust-Funds-Report-Digital.pdf / Report 2 sets out the sequencing of stabilisation and reconstruction tasks that trust funds should ideally address and illustrates with the ‘smart’ trust fund mechanisms used to implement the peace agreement in Northern Ireland. / http://www.politicalsettlements.org/wp-content/uploads/2019/08/Spotlight-MDTF-NI-Digital-2.pdf
Sept / 2019	Policy Report	Transitional Governance. Temporary governance arrangements put in place to manage transitions from conflict/crisis whereby transitional authorities introduce a wholesale constitutional transformation with the intention to bring peace and stability. These have been a major feature of most crises/conflicts this decade: Sudan (2019), Libya (2011), Tunisia (2011), Nepal (2006), Iraq (2004), Somalia (2004), Afghanistan (2002). Transition concerns the transformation of a state’s regime e.g. ‘the institutional structure of the state and government’ based on legal instruments or texts with a temporary constitutional status. They can include domestic intra-state agreements, reference to international agreements, interim or transitional constitutions or other provisions. The report sets out the key features of interim governance, using a comprehensive set of examples: / international legalisation of the transition / how they establish the length of the ‘interim’ period / how they limit the functions of the interim government / how they provide for inclusion / how they provide for transitional justice / http://www.politicalsettlements.org/wp-content/uploads/2019/09/Interim-Transitions-Report-DIGITAL.pdf

Lessons identified this year, and recommendations for the year ahead linked to this output

This year DFID and PSRP kept the log frame indicators at the same level of ambition as previous years although the amount of DFID funding has halved, due to the extension starting last year. PSRP was still able to exceed its publication targets, largely because of the time delay for journal articles (submitted last year), to reach publication.

Recommendation: Amend the Log frame indicator to reflect the focus on uptake in the final year.

Output Title	Evidence of stakeholder uptake and research engagement.
Output number per LF		2	Output Score	A+
Impact weighting (%):		30%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
2.1 Number of tailored sessions run for key stakeholders (including DFID). Number of people reached by presentations and workshops.	2 tailored sessions, and 100 people directly addressed	Exceeded: / 5 tailored sessions provided this year.
2.2 PSRP Research taken up and referenced elsewhere (cumulative totals)	15 peer-reviewed articles cite PSRP work (not authored by PSRP)	Exceeded: / 19 articles cited (this year) / 41 articles cited (cumulative.)
2.3 Number of stakeholders engaging with research and policy products through website, media and publication downloads	Upward trend in website hits on PSRP website and PA-X website. At least 10% of PA-X website hits from global South.	Substantially exceeded: / 43,875 website hits (1 Mar 2019-29 Feb 2020) which is a 24% increase over last year (30,736 last year). / Over 2000 followers on twitter. / 3 papers had 1000 + downloads. / 1 paper had 500+ downloads / 10% website hits from global south.

Briefly describe the output and provide supporting narrative for the score
PSRP has exceeded the output by: (2.1) delivering a range of tailored briefing sessions and events for policy makers, (2.2) through citation of PSRP research and data by academics and in online and broad sheet media and through (2.3) their growing, though specialist, following on social media.
  1. PSRP exceeded the target for events run this year. Highlights include:
- Local Agreements. PSRP ran 2 major events on local peace agreements in London (covering MENA and Asia) and in Nairobi (covering Africa). The workshops examined the processes, and contents, of local peace agreements and included mediators and negotiators from over 19 countries, in addition to international institutions such as the UN.
- Horn of Africa Conflict Research Event. PSRP presented research to HMG representatives from across the Horn of Africa in Nov 2019 at the third annual RED-convened Conflict and Peace Research Event in Nairobi. The event informed strategy and programming and was commended by three Ambassadors, and the head of DFID Somalia. The sessions helped DFID South Sudan review its approach following efforts to extend a ceasefire; helped DFID Somalia review its theory of change and options for support for electoral reform, and supported DFID Kenya and the joint donor group in Nairobi to consider options for peaceful elections in 2022.
- ECOWAS. PSRP presented PA-x Data to the Economic Community of West Africa States (ECOWAS), Nigerian Institutions and west African negotiators working on farmer-herder conflict.
- OSCE. PSRP presented to the Organisation for Security Cooperation in Europe (OSCE) and provided data on transitional funding mechanisms to support an OSCE study,
- Northern Ireland Office. PSRP briefed the Director of the UK’s Northern Ireland Office (NIO) at a time when the power sharing arrangement had broken down and the ‘devolved executive and assembly’ had been unable to meet for 2 years. PSRP shared information on power sharing, civil society involvement in peace processes and funding modalities. A new power-sharing arrangement was reached in April 2019 and PSRP research is subsequently informing the NIO’s new strategy. PSRP research published last year on the links between paramilitarism and domestic violence has informed NI police and probation service’s operational practice and training for new recruits.
- Social Unrest. PSRP provided advice to HMG teams working on Lebanon, China/Hong Kong, and Middle East, and a tailored research paper to outline mechanisms for responding to civil unrest (e.g. through National Dialogue, amnesties and commissions of inquiry). This built on similar briefings provided last year to HMG’s Zimbabwe and Sudan teams. The paper was also welcomed by the UN’s Department for Political and Peacebuilding Affairs.
Additional PRSP hosted events include:
  - Convening women mediators from around the globe.
  - Several briefings to DFID/FCO Sudan.
  - Edinburgh Dialogues, which focussed this year on transitional governance, including specific sessions on Sudan and South Sudan.
1.2	PSRP exceeded the target for citations. 19 PSRP publications have been cited by other academics this year. Researchers are also drawing directly on PSRP data from the online database to provide analysis of peace processes. This indicates the credibility that PSRP’s quantitative and qualitative PSRP data is building within the academic community; and the value for money (VfM) achieved by DFID’s investment through research beyond PSRP.
For example, Miller and Blake’s paper ‘Envisioning a Comprehensive peace agreement for Afghanistan’ cites PSRP outputs and draws on the comparative data to provide a vision for political accommodation in Afghanistan, including new political and security arrangements, their risks. and potential roles for external actors. The paper builds on workshops that the FCO convened last year with Laurel Miller and PSRP Director Christine Bell and Associate Alexander Ramsbotham, which discussed potential components of a settlement. A deal was then reached between the Taliban and the US Government this year to begin US troop withdrawals (notably apparently drawing language on ‘violence reduction’ from PSRP research). The deal is considered a pre-requisite for a wider process between Afghan parties.
https://www.rand.org/pubs/research_reports/RR2937.html
Analysis of civil wars and peace processes in the 90s by Johansson also draws on the PSRP Data, alongside the Uppsala Conflict Data, to provide an overview of 103 armed conflicts. This finds that provisions on ceasefires, development, and rebel inclusion were the three most common provisions in the 696 civil war peace agreements reviewed. http://www.diva-portal.org/smash/get/diva2:1272935/FULLTEXT01.pdf

PSRP’s data on Women Peace and Security has been particularly drawn on. Berry and Rana cite PSRP research in their analysis of the obstacles to peace in women’s lives after war, and how women overcome these to support reconciliation.
PSRP’s work continues to attract media coverage. The Times and the Scotsman picked up PSRP research this year on the inclusion of women’s rights in peace agreements (see box for article in The Times on 5 March 2019).

1.3	PSRP has exceeded targets for social media uptake this year. PSRP had 43,875 website hits (1 Mar 2019-29 Feb 2020) a 24% increase from the same dates last year. 30,736 hits were registered last year, for slightly different dates. 10% of hits come from the global south, with South Sudan being the fourth highest location for PSRP web users, behind the US, UK and Canada.

PSRP has 2466 twitter followers (as of 04/03/202), an increase of 27% from last year. Twitter impressions range from 15,000 to 89,000 per month, with most months registering between 20– 30,000.

Christine Bell was ranked by SSRN (a top social science repository) within the top 10% of authors based on views and downloads of their publications.

Lessons identified this year, and recommendations for the year ahead linked to this output

PSRP has seen year on year growth of its uptake targets. In the final year of the programme PSRP should focus on disseminating the completed research now published. The following should be delivered by May 2021:
- At least one major UK based event and possibly additional events in the US and Europe.
- Podcasts of the messages from its key publications.
- Ensuring the sustainability of its website and database beyond DFID funding.

Output Title	Enhanced research capacity, particularly in global south
Output number per LF		3	Output Score	A+
Impact weighting (%):		30%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
3.1 Number of Southern-based researchers involved in research projects, as evidenced by their active engagement, e.g. through co-authorship and/or presentations at events.	2 projects involving 5 Southern-based researchers.	Target exceeded: The local agreements events in Nairobi and London involved presentations from 60 participants from the Global south. 43 southern researchers have co-authored PSRP publications.
3.2 New peace-tech capacity tools for complex problems in FCAS tested and disseminated where effective	2 peace-tech innovations implemented and tested with policy and practice audience with feedback.	Target exceeded: PSRP Peace tech innovations include: / - a mobile app on gender in peace agreements. / - interactive infographics. / - a pilot study of perceptions of peace in social media implemented with partners in Nairobi and Kenyan researchers.

Provide supporting narrative for the score

3.1	PSRP exceeded the target on involvement of southern researchers in PSRP projects. This year 60 southern researchers and/or practitioners presented at 2 events (London, Nairobi) exploring the process and content of local peace agreements.
PSRP exceeded the target for southern researcher participation in PSRP research. 43 southern researchers co-published PSRP publications during phase 1 of the project which included significant field work. A further 39 played key roles in field research with their roles noted in PSRP research publications. Phase 2, in the extension, focuses on research drawing on the peace agreements database with limited field work. The involvement of southern researchers this year has largely been to support research on local agreements and in research uptake. Having collated 282 local agreements on the database PSRP involved southern researchers, peacemakers and mediators in reviewing the local agreements collated and in developing the research on how the agreements were designed and their impact.  The Nairobi Local Agreements event involved 80% southern participants. Southern researchers also presented at several uptake events this year.

  1. Target exceeded on Peace Tech tools tested and disseminated

  - A mobile app on gender in peace agreements is in development with UNWOMEN. It is currently undergoing final testing and will be launched in 2020.

  - Interactive infographics illustrating key facts from PSRP’s database have been published and distributed in February 2020. These are already being used by HMG officials in the FCO, DFID and Cabinet Office and by UN and civic actors in varying country contexts.
http://www.politicalsettlements.org/2020/02/28/new-interactive-infographics-now-live/

  - A pilot study examining perceptions of peace in social media has been implemented with partners in Nairobi, involving Kenyan researchers. PSRP plans to publish this in 2020 and is exploring options to extend to other contexts.

Lessons identified this year, and recommendations for the year ahead linked to this output

PSRP’s peace tech innovations have been well received and they are seeking funding to develop more comprehensive platforms for reaching civic actors in a range of contexts. PSRP will provide a full report on the options for further innovation to DFID by April 2020. This will include options for continuing uptake and supporting civic actors engaged in peace processes during the COVID-19 outbreak.

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES (1-2 pages)

Summarise the programme’s theory of change and any major changes in the past year (1/2 page)

PSRP’s original contract, and subsequent extension, are based on a standard theory of change for DFID research programmes. This same ToC is reflected in the PSRP log frame:

- PSRP’s research strategy identifies priority research questions and research themes that will contribute to the evidence base for policy makers and other interest groups, including DFID and its partners.
- The PSRP consortium designs and delivers a portfolio of research projects (with fieldwork in specific settings and with appropriate methods and analysis) to deliver this new evidence. (Output 1)
- Throughout the research cycle, PSRP engages with policy makers to ensure that the research products are relevant and useable. (Output 2)
- PSRP produces a range of research outputs tailored to different audiences and actively disseminates these, including through publication, online media and events. (Output 2).
- Where required, PSRP builds capacity with research partners in order to deliver the research to expected quality and on time (Output 3.)

PSRP’s intended outcome is ‘Increased knowledge and uptake by policy makers of evidence-based policies and programmes for achieving open and inclusive, non-violent political settlements’. This is measured through outcome case studies and through feedback from policy makers.
Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead (1/2 page)

PSRP has exceeded expected outcomes and impact over the 5 years of the programme: Phase 1 (2015- 2019) and the first year of Phase 2 (2019-2021). PSRP has also exceeded output targets.
PSRP has delivered a series of high-profile outcome case studies, showing how PSRP’s research has informed peace and political processes in Somalia, the Ogaden region of Ethiopia, The Sudans, and in Yemen.
Having updated the peace agreements database this year PSRP has also now collated a significant repository of local agreements, filling important global gaps in research.
PSRP has drawn on this data to deliver a legacy of high-quality research and policy guidance with over 20 publications on key elements of peace processes and exploring how these are implemented in practice in particular geographies. PSRP publications cover arrangements for sharing of power, territory, economic resources, business interests and military institutions and for including minorities and supporting the role of women. PSRP has also met high demand for expert advice and evidence from UK officials, partners at the UN, and national peacebuilders and mediators working to end complex conflicts.
Ministers agreed to extend the programme in August 2018. This is a high preforming programme and progress to date suggests that PSRP will deliver all expected outputs during the 2-year extension.
Based on this performance and high demand for PSRP’s expert advice drawing on the unique data collated, DFID will consider future options for how similar research and services can be sustained after the end of the current contract.
Explain major changes to the logframe in the past year (1/2 page)
No changes have been made this year.
Describe any planned changes to the logframe as a result of this review (1/2 page)
The log frame indicators will be updated to reflect the completion of research and the focus on uptake and dissemination in the final year.

## D: VALUE FOR MONEY (1-2 pages)

Assess VfM compared to the proposition in the Business Case, based on the past year (1 page)
PSRP continues to be a high performing research programme that bridges the divide between academic research and practitioners’ operational needs. PSRP continues to deliver good value for money (VfM) across all indicators, with a focus on high quality while limiting costs.
This is a milestone based contract with expenses paid quarterly in arrears, based on actual costs. DFID retains 5% of each payment; the retained amount is then paid in the following quarter providing all performance criteria have been met.
In this reporting period delivery and performance remained on track and the 5% retention was paid in full in each subsequent quarter. Full details of key cost drivers are set out in Section 4 of the contract.
Key cost drivers include staffing, research uptake, and travel costs. In this reporting period, programme delivery and performance remain on track, continuing to meet agreed targets and expected standards.
Examples of VfM are listed below under DFID’s “4 Es” framework.

Economy
- PSRP travel costs are often covered by organisations inviting PSRP to present at events. PSRP maximise the value of these trips, by conducting additional briefings and outreach to new stakeholders in these countries. This expands dissemination networks, increases the value added of each trip, and reduces the environmental impact.
- PSRP’s development of ‘Peace Tech’ platforms for promoting their research in creative ways (e.g. infographics) and to new audiences (e.g. through the Yemeni voices initiative) reduces the transaction costs of PSRP staff engaging with users face to face. This also reduces time incurred in meetings and related travel costs. PSRP continues to use phone and video conferencing where feasible to reduce the time and travel costs of the core team.
- PSRP continues to collaborate with the British Academy, working this year on a joint workshop in London and a joint publication on Local Agreements. The BA subsequently provided a London venue for the event and has provided academic support to the project.

Efficiency
- PSRP has made efficient use of its resources by partnering with other organisations, to increase reach of the programme and reduce overheads. Examples include: an event with UNWOMEN for ’Women Constitution Makers’ and an event with ‘Social Change Initiative’ on media and conflict resolution. The latter has led to PSRP developing a report/policy on the topic.
- PSRP has added value through expanding its research dissemination networks: within UK government; by reaching new regional organisations such as the OSCE and ECOWAS (see output 2); and through establishing a network of 60 local researchers and practitioners involved in local peace agreements. This extended reach further increases the likelihood of PSRP informing the practice of peace making and enhances the ‘value added’ of the programme.

Effectiveness
- PSRP has demonstrated more than thirty cases where research has influenced and shaped national and international policy development, illustrated in Output 2 and feedback provided in Annex A. PSRP’s contribution to global peace is hard to quantify but DFID’s investment is likely to be worthwhile if the prospects of peace are improved or the length of a conflict is reduced as a result of their evidence and expertise. The examples provided by PSRP to date would appear to more than justify DFID’s investment.
- PSRP data is now being used by a wide range of academics and practitioners, leading to substantive publications and value added from the DFID investment beyond the PSRP programme (See Output 2 for details).
Equity
- Collaboration with Southern based researchers has expanded this year through PSRP’s work on local peace agreements and through their ‘PeaceTech’ engagements with researchers and practioners in Yemen, Syria, and the Horn of Africa (Output 3).
- PSRP is drafting a joint paper on local agreements with the British Academy which will include contributions from Southern-based colleagues involved in the workshops conducted this year.
- PSRP’s publication on disability in peace agreements and several articles on the role of women in peace making are important contributions to DFID’s equity commitments.

Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio (1 page)
PSRP consistently performs well on VfM. It has established systems to ensure VFM through the project cycle. This includes the use of financial accounting systems which use stringent controls over monitoring of expenditures, and link payments to delivery of outputs by partners. Edinburgh University monitors the budget as the research develops to ensure the programme achieves outputs on time and within budget.
PSRP has attracted additional funding to extend their work into new areas. Examples include:
- Partnership with UN Women led to a £34,029 contribution between April and December 2019;
- PSRP won £40,000 from the Global Challenges Research Fund during April 2019.
- The British Academy has provided a venue and support for a Joint Analysis Workshop in London and a joint paper.
- The United States Institute of Peace has provided $500,000 to PSRP’s partner ASPR for a project on local perceptions of the peace process in South Sudan.
- Based on the knowledge and networks developed in the PRSP, International IDEA funded and organised an additional PSRP event at University of Edinburgh on the role of women in constitution building, which will provide the foundations for a peer network of women constitution building in the future’. This was attended by women constitution makers from around 15 countries

PSRP has delivered the same number of publications as in previous years while operating on half the annual budget since the extension began.
The increased use of PSRP data by other academics also provides significant value for money benefits to the DFID investment because the data is now enabling research outside the PSRP programme.

E: RISK (½ to 1 page)

Overview of programme risk (noting the rating from p.1) and mitigation
Overall risk rating: Minor
The overall programme risk is assessed as minor as PSRP completes the first year of the extension and enters the final year of the programme. The risk rating was assessed as major in phase 1 of the programme to reflect duty of care and operational risks for field research in conflict affected settings. The risk assessment is reduced to minor in the final year of the programme to reflect the focus on uptake and completing research based on the peace agreements database. Researchers funded in the final year of the programme are largely based in Edinburgh.
The main risk this year is ‘failure to provide a broadly applicable evidence base to inform policy’. The risk of this is low given the solid evidence base already established by PSRP. PSRP has also established good working relations with HMG and the UN, particularly following the publication of the PA-X database. The programme has delivered its core outputs and provided in-time advice to HMG and UN institutions.
PSRP advice to those involved in peace processes is extremely sensitive as participants and observers do not want it to be known that they are seeking advice. PSRP manages this risk by protecting the confidentiality of those that seek advice.
There is a possible risk to programme delivery in the event that key UoE programme personnel begin to leave the programme as it nears its end.
PSRP has managed COVID-19 risks well to date. The programmes use of technology to support peace processes helped them adapt to the restrictions in place. One event in London was cancelled with minimal cost to DFID as they had secured a free venue. All other future events will be conducted by Zoom.
PSRP has a detailed risk assessment which has been discussed with DFID throughout the year.

Update on partnership principles [[if relevant. If it’s not – delete this section, but only having read the text in the Smart Guide at the end]] (1/2 page)

Not Relevant

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE (1-2 pages)

Performance of partners and DFID, notably on commercial, and financial issues (1-2 pages)
This is a performance-based contract with expenses paid quarterly in arrears, based on actual costs. DFID retains 5% of each payment; with this retained amount then paid the following quarter providing all performance criteria have been met. To date, no funds have been withheld and the full 5% retention was paid in each subsequent quarter. PSRP has robust financial monitoring processes in place.
Overall expenditure to date as £5,100,998 against a contract budget of £6,541,250.
For the review period, actual expenditure is expected to be £237,382. The programme underspend is 9%. Under DFID’s 10% variance target.
The programme expects to attain a full spend over its duration.

Figures in £	Q1 Apr-Jun 19	Q2 Jul-Sep 19	Q3 Oct-Dec19	Q4 Jan-Mar 20	Yr 1 2019/20 Total
Forecast	£263,767	£227,266	£290,289	£339,342
Actual	£210,353	£227,846	£308,475	£287,392 (forecast)	1,034,066*actual plus revised forecast figure
% spend of forecast	80%	100.%	106%	85%	92%

Financial management is covered in quarterly meetings, and expenditure and forecasts remain generally on track. Quarterly financial reports have outlined the operational challenges experienced by the programme but despite these, expenditure has remained close to that forecast. Invoicing has been timely, good quality, and backed up with quarterly reports verifying progress against key performance indicators and outputs.
A breakdown of actual expenditure across all programme components has been provided for the period as well as a full summary of the actual and forecast expenditure by programme partner.
PSRP have confirmed there are no physical assets associated with the contract.
Date of last narrative financial report(s)	31/01/2020
Date of last audited annual statement (s)	NA

G: MONITORING, EVIDENCE & LEARNING (1-2 pages)

Monitoring (1/2 page)
DFID and PSRP have formal quarterly meetings to discuss and monitor overall progress and communicate monthly on routine business. PSRP submitted their Annual review and quarterly reports on time. Quarterly reports are detailed and rigorous for a programme of this size.
This annual review was carried out during February and March 2020 by DFID Senior Conflict Advisor and a Project Manager. Substantive feedback was also received from FCO Research Analysts and DFID Advisers. PSRP’s Annual Board Meeting was held in November 2019.
The DFID review team conducted a desk-based review of key documents, including a detailed report of the programme’s performance over the review period submitted by the partners. Key research and communication outputs were also reviewed. The review team consulted with downstream partners included in the programme and with key policy audiences (e.g. the UN and HMG officials) to verify feedback provided by PSRP.
DFID and PSRP held a meeting to discuss annual performance in March 2020. The Annual Review report was shared with PSRP in March 2020. Recommendations will be followed up at subsequent project meetings. An evaluation has not been included in this programme. Given the nature of the research and the relatively small size of the programme, an evaluation was not considered to offer sufficient VFM over rigorous monitoring.

Evidence (1/2 page)

Qualitative feedback has been provided by policy audiences alongside data on quantitative targets for this AR. Monitoring is targeted at the specialist policy audiences working on peace processes who are the main consumers of PSRP research. Their feedback has been used over the last year to refine the research questions and to specify the focus of policy briefs.
Demand for research on political settlements is variable, and subject to fluctuating conflict cycles and international attention. Ongoing peace and political processes can take 20 years or more to reach conclusion. PSRP’s work to inform ongoing processes is therefore best reviewed through feedback from those involved in the processes rather than concrete signs of progress in contexts where an end to conflict may be some way off (e.g. Syria, Yemen and South Sudan).
PSRP’s work on Columbia last year demonstrates the value that research can provide when the political conditions for a positive milestone emerge. While we would expect these outcomes to contribute towards reduced discrimination, fragility, deaths in conflict, and violent homicide rates (PSRP programme impact indicators), it is clear that direct attribution and measurability are unlikely during the timeframes of this research programme
Learning (1/2 page)
PSRP continues to adapt its approach to research uptake and engagement with DFID country teams. This year they have produced a paper on learning from their engagement with DFID Somalia on elections system design. This will inform the uptake approach in the final year,
Progress on recommendations from previous reviews (1/2 page)
Recommendation: PSRP and DFID will add new log frame targets on publication numbers and website hits, to reflect the reduced intensity of DFID expenditure in the 2 -year extension.
The log frame targets were kept consistent with last year’s targets. Although the budget has halved since Phase 1, PSRP has delivered the same number of publications and output targets as in previous years, demonstrating particularly good VfM. The log frame targets for the final year of the programme will need to be amended to reflect the focus on uptake, rather than research delivery.

Annex A: List of Publications this year

Q	Project	Type	Delivery
1	Cross- project	Data	PA-X Peace agreements database and dataset – qualitative output, Version 2
1	Cross- / project	Data	PA-X Peace agreements database and dataset – quantitative output, / Version 2
1	Cross- / project	Data	PA-X Peace agreements database and dataset – corpus of texts for / computer-based text analysis, Version 2
1	Cross- project	Infographic	Political Power-Sharing (English version, Arabic version forthcoming). Available here: http://www.politicalsettlements.org/wp- / content/uploads/2019/06/GJA_Political_Power_Sharing.pdf
1	Cross- project	Infographic	Economic Power-Sharing (English version, Arabic version forthcoming). / Available here: http://www.politicalsettlements.org/wp- content/uploads/2019/06/GJA_Economic_Power_Sharing.pdf
1	Cross- project	Infographic	Territorial Power-Sharing (English version, Arabic version forthcoming). Available here: http://www.politicalsettlements.org/wp- / content/uploads/2019/06/GJA_Territorial_Power_Sharing.pdf
1	Cross- project	Infographic	Military Power-Sharing (English version, Arabic version forthcoming). Available here: http://www.politicalsettlements.org/wp- / content/uploads/2019/06/GJA_Military_Power_Sharing.pdf
1	Cross- project	Infographic	Transitional Justice (English version, Arabic version forthcoming). Available here: http://www.politicalsettlements.org/wp- / content/uploads/2019/06/GJA_Transitional_Justice.pdf
1	Cross- project	Infographic	Amnesties (English version, Arabic version forthcoming). Available here: http://www.politicalsettlements.org/wp- / content/uploads/2019/06/GJA_Amnesties.pdf
1	1.1	Journal Article	Robert Forster (2019). Twenty Years After Ottawa: ‘Unpacking’ Mine Action in Peace Agreements. Journal of Peacebuilding and Development. Available here: http://www.politicalsettlements.org/wp- content/uploads/2019/05/20190404_Mine_Action_Forster_Accepted_Man / uscript_Pre_Print.pdf
1	5	PSRP / Spotlight	Jan Pospisil (2019). ‘Sudan’s Enduring Transition: Evolving Arrangements after the Fall of Bashir’. Available here: / http://www.politicalsettlements.org/wp-content/uploads/2019/05/PA-X- Spotlight-Sudan-Digital.pdf
1	Phase I, Pillar 2	Journal Article	Patrycja Stys, Judith Verweijen et al (2019). ‘Brokering between (not so) overt and (not so) covert networks in conflict zones’. Global Crime. / Available here: http://www.politicalsettlements.org/wp- content/uploads/2019/06/Brokering-between-not-so-overt-and-not-so- covert-networks-in-conflict-zones.pdf
1	Phase I, Pillar 6	Report	Julia Bello Schünemann (2019). Sudan and South Sudan: Violence Trajectories after Peace Agreements (ISS PSRP report). Institute for Security Studies. Available here: http://www.politicalsettlements.org/wp- content/uploads/2019/03/EAR-Trajectories-of-violence-ISS-March- / 2019.pdf
02	1.1	PA-X Spotlight	Robert Forster and Christine Bell, ‘Gender Mainstreaming in Ceasefires: Comparative Data and Examples’
02	1.1	PA-X Spotlight	Laura Wise, ‘Humanitarian Assistance and Gender Perspectives in Peace Agreements’
02	1.2	PA-X Spotlight	Christine Bell and Robert Forster­, ‘Re-invigorating Stalled Peace / Negotiations: Challenges and Opportunities for Women’s Inclusion’
02	1.2	Animated Video	Animated video to accompany the PA-X Spotlight by Bell and Forster, ‘Re-invigorating Stalled Peace Negotiations’
02	1.2	PA-X Spotlight	Christine Bell and Robert Forster, ‘Women and the Renegotiation / of Transitional Governance Arrangements’
02	1.2	PA-X Spotlight	Robert Forster, ‘A Gender Analysis of Peace Agreements and Transitional Documents in Libya, 2011-2018’
02	2	PA-X Spotlight	Laura Wise, Robert Forster, and Christine Bell, ‘Local Peace Processes: Opportunities and Challenges for Women’s Engagement’
02	2	PA-X Report	Kathryn Nash, ‘Interstate Agreements to End Intrastate Conflicts’
02	2	PA-X Report	Sean Molloy, ‘Peace Agreements and Trust Funds’
02	2	Infographic	Peace processes (English)
02	2	Infographic	Peace processes (Arabic)
02	1.2	Infographic	Transitional Justice (English)
02	1.2	Infographic	Military Power-sharing (English)
02	1.2	Infographic	Economic Power-sharing (English)
02	1.2	Infographic	Political Power-sharing (English)
02		Story	Harriet Cornell, ‘Introducing our ‘Stories’ Feature’
02	1.2	Story	Susan McKay, ‘Gender Perspectives in Peace Processes’
02	4	Story	Ronald Kerr, ‘Data for Peace: Charting 30 years of human ingenuity in ending conflict’
02	1.2	Policy Brief	Rebecca Sutton, ‘Who is a Civilian? Perceptions of ‘Civilianness’ in the Central African Republic’
02	3.3	PSRP Spotlight	Avila Kilmurray, ‘Trust Funds in Fragile and Conflict-affected States: Lessons from Northern Ireland’
02	1.2	PA-X Report	Emmanuel de Groof, ‘The Features of Transitional Governance Today’
03	1.2	PA-X Report	Sean Molloy and Christine Bell, ‘How Peace Agreements Provide for Implementation’
03		Journal Article	Aisling Swaine, ‘Re-shaping How Political Settlements Engage with Conflict-Related Violence Against Women’, Feminists@Law 9 (1)
03		Journal Article	Corina Lacatus and Kathryn Nash, ‘Peace Agreements and the Institutionalisation of Human Rights: a Multi-level Analysis’, International Journal of Human Rights 23 (1)
03		Research Memo	Alex de Waal, Alan Boswell, David Deng, Rachel Ibreck, Matthew Benson, and Jan Pospisil, ‘South Sudan: The Politics of Delay’
03		Policy Paper	Amanda Cats-Baril, ‘Moving Beyond Transitions to Transformation: Interactions between Transitional Justice and Constitution-Building’