Business Case

Summary Sheet

Title: Support to the refugee response in Tanzania.
Project Purpose: / To provide humanitarian assistance to refugees living in the camps in Western Tanzania.
Programme Value: £15M		Country/ Region: Tanzania
Project Code:	Start Date: July 2016	End Date: July 2017
Overall programme risk rating:	Minor
Quest Number:

Intervention Summary (2 Pages)

What support will the UK provide?
The UK will provide a further £15m to support refugees in Tanzania who have fled political crisis in Burundi. This brings the total funds to the current response in Tanzania to £29.25m since April 2015.

What are the main programme activities?
DFID will support the provision of basic services to the refugee population in camps and host communities in western Tanzania. Activities include: WASH, camp management, shelter construction, education, protection and provision of food. DFID will also support the development of increased self-reliance through the funding of livelihoods and environment activities and support to host communities.

Why is UK support required?
In April 2015 President Nkurunziza announced his intention to run for a third term, which many saw as a contravention of the constitution and against the spirit of the Arusha peace accords. The decision led to generally peaceful demonstrations particularly by students. On the 13th May there was an attempted coup and thereafter the police cracked down hard on opposition. Hundreds of opposition, or suspected opposition, particularly young men have been arrested with the United Nations Office for Human Rights (UNOHR) reporting that over 400 people have been killed and hundreds have disappeared.

As a result of the political instability, Burundians began to flee the country most stating that they have been intimidated by Imbonerakure (the youth militia of the ruling party CNDD-FDD). By May 2016 there were over 265,000 Burundian refugees in surrounding countries with over 140,000 in Tanzania, with 70 people still arriving on a daily basis – down from a peak of over 150 per day during 2015. The crisis continues unresolved and could easily get worse.

In Tanzania the refugees are living in 3 camps and, due to Tanzania’s encampment policy, the refugees are totally dependent on aid for their survival. The response has been complicated by weaknesses in overall leadership, under-funding, and long lead times on securing necessary approvals from the Government of Tanzania on the allocation of land for additional camps which resulted in over-crowding. The regional refugee response plan which covered the humanitarian needs of refugees in Tanzania for 2015 was only 37% funded and the 2016 appeal in Tanzania for $174 million is currently only 38% funded (http://data.unhcr.org/burundi/regional.php).

This means there are still considerable gaps in coverage, and refugees continue to arrive on a daily basis. Work remains to be done on ensuring water and sanitation provision, effective coordination, the construction of semi-permanent shelter to replace tents or emergency plastic sheeting shelters and classrooms and protection. It is also important to consider the likely protracted nature of the refugees and the need to start to support refugees to become more self-reliant through developing livelihoods activities to enable refugees to be less dependent on aid and to ensure better overall health and well-being. DFID was the second largest humanitarian donor in Tanzania in 2015, and DFID is also the second largest bilateral donor in Tanzania and is well placed to support the crisis and influence a more sustainable response strategy which tackles the likely prolonged nature of the displacement. The ongoing crisis means a further influx is still possible so preparedness is also important.

What are the expected results?

The programme will improve the quality of life and reduce the vulnerability of the refugee population. Results include:

UNHCR
£5m will make a 10% contribution to UNHCR’s specific funding needs of $75m (£53M) (UNHCR RRRP 2016 Quest re:5489331) to target up to 170,000 refugees Western Tanzania. £4.5M will be un-earmarked to allow UNHCR to prioritise services according to need. UNHCR will ensure there is adequate protection for refugees, water and sanitation, health care, essential non-food items, education and semi-permanent shelter for the refugee population. £0.5M will be earmarked for the environment and for the host community. The funding will contribute to the achievement of UNHCR’s 2016 targets which include, for example:
- 100% primary aged children enrolled in primary education
- Crude mortality rate of less than 1 per 10,000 per day.
- Under-5 mortality rate of less than 2 per 10,000 per day.
- 15 litres of clean drinking water per day.
- Global Acute Malnutrition of less than 10% in refugee population and Severe Acute Malnutrition prevalence of less than 2% in under 5 population.
- 1 Latrine for 20 persons

WFP: £4m will contribute 10% to WFP’s funding needs of $50m (£35m) in 2016 (Quest Ref: 548937). £4m will buy:
6 weeks months of dry food ration (Maize, pulses (beans, peas, split peas or lentils), salt, oil, CSB (fortified food: Corn Soya Blend or micronutrient powder) for 200,000 people.

Oxfam: £1.5m will deliver
- Upgrading of water system in Nyarugusu camp.
- Installation of a gravity water system in the host community of Kumuhasha.
- 1500 family latrines and 750 bathing shelters in Nyarugusu and Nduta.
- Hygiene promotion activities, WASH committees.
- Leadership training for women to encourage greater involvement of women in decision-making in the camp and the management of community facilities.
- 1500 dignity Kits, 20,000 jerry cans.
- 3500 households will receive unconditional cash grants or vouchers, to enable households to invest in livelihoods activities, to assist households to diversify their diets and to reduce the need to adopt risky livelihoods practices.
- 50 groups for income generation activities or food production will be formed and supported.
- Collaborate with UNHCR on a pilot for bio-mass fuel.

DRC: £2m will deliver a number of activities contributing to effective camp management and community management systems:
- 23 community services workers to support camp management systems in 3 camps.(50% Nyarugusu)
- 1 office set up in Nyarugusu/Kasulu to support a Tanzanian NGO Tanzania Water and Environmental Sanitation (TWESA) and logistical supply
- 5 specific trainings provided to partner staff (TWESA)
- 150 solar street lamps provided
- 6 help desks for community feedback.
- 1 cross-camp information management system (in collaboration with UNHCR).
- 1 Camp Coordination and Camp Management (CCCM) staff and 1 refugee leadership camp exchange/learning event organized
- 10 community meeting halls across 3 camps for supporting refugee self-management initiatives
- 1 community-based protection network set up (Nyarugusu and support to networks in the other camps.
- 80 school buildings (classrooms, dorms, admin blocks, WASH blocks), 1250 desks.
- 70 small business grants provided to community groups/self-made cooperatives (NB the cooperative idea came from the community themselves, so supporting that seems feasible with good monitoring and support/training)
- 5230 households supported with agricultural supplies and technical training (2 camps + host)

UN Staffing Support: £0.2m
- One Cash transfer expert for WFP
- One Sustainable livelihoods adviser for UNHCR.

Monitoring and Evaluation £0.1m:
CHASE/OT DFID Humanitarian Adviser.

Contingency: £2.2m
£2.2m of contingency will be kept back as contingency for the 4th camp and/or emergency preparedness to respond to a surge in new arrivals.

A minimum of £0.5 of the funding will directly contribute to environmental projects and projects for the host communities.

How does the project fit with the country programme or department’s strategic objectives set out in the Operational Plan?

The project meets UK commitments to leading the response to humanitarian emergencies, and is in line with DFID Tanzania Business Plan. The programme aims to go beyond direct service provision and contribute towards resilience within the refugee population, it will include the consideration of women’s and girl’s needs, piloting longer-term solutions to reduce reliance on humanitarian assistance and developing innovative solutions to protracted crisis, and will contribute to initiatives to reduce carbon emissions. This Business Case is one of two DFID Tanzania BCs dealing with refugee issues in Tanzania. A second BC for around £38m is also being developed that will be for three years and will have a more comprehensive focus on refugee populations and on promoting self-reliance.

What are the key risks to the success of the programme?

The key risks to the success of the programme relate to having sufficient land, water and financial resources to accommodate current and further influxes of refugees. DFID will work to mitigate risks through assisting UNHCR to advocate with the Government of Tanzania and the donor community.

A more detailed risk analysis can be found in the management section.

Strategic Case

Context and Need:

In April 2015 President Nkurunziza announced his intention to run for a third term, which many saw as in contravention of the constitution and against the spirit of the terms of the Arusha peace accords. The decision led to generally peaceful demonstrations particularly by students. On the 13 May there was an attempted coup and thereafter the police have cracked down hard on the opposition. Hundreds of opposition or suspected opposition, particularly young men, have been arrested. UNOHR report over 400 people have been killed and hundreds have disappeared.

As a result of the political instability Burundians began to flee the country, most stating that they had been intimidated by Imbonerakure (the youth militia of the ruling party CNDD-FDD). By May 2016 there were over 265,000 Burundian refugees in the region with over 140,000 in Tanzania with 70 people still arriving on a daily basis – down from over 150 per day during 2015.

In Tanzania the refugees are living in 3 camps and due to Tanzania’s encampment policy the refugees are totally dependent on aid for their survival. The response has been complicated by limited preparedness, staff capacity, underfunding and long lead times on the allocation of land which led to over-crowding.

In May 2015 a multi-agency Regional Refugee Response Plan and Appeal was launched which was subsequently updated in August for a total of $307m for up to 320,000 refugees. Tanzania required a total of $154m for up to 150,000; by the end of 2015 the appeal in Tanzania was 37% funded. DFID Tanzania gave £14.25m ($20m) i.e. 13% of the appeal. Out of this £9.05m went to UNHCR, £1.5m to WFP, £2.15 to Oxfam (for WASH) and £1.15m IOM (for refugee transportation) and £0.4 for advisory deployments.

There are still urgent needs to be met for the current population, and a further large-scale influx remains possible. Work remains to be done on ensuring water supply and sanitation, effective coordination, the construction of semi-permanent shelter to replace tents, construction of classrooms and camp management systems to aid coordination and ensure camps are managed safely and securely for refugees. There is also a need to consider the likely protracted nature of the crisis and the need to start to support refugees to become more self-reliant through developing livelihood activities to enable refugees to be less dependent on aid and to ensure better overall health and well-being. Action must also be taken to ensure the local host communities are not negatively impacted by the presence of the refugees, such as promoting trade between the local community and refugees, managing the environment and natural resources and where possible host communities and refugees can benefit from improvements to infrastructure.

Status of funding for the Appeal:

The appeal for 2016 is for $174m (£124m) as of June 2016 was 38% funded. Though better than last year, the lack of land provided for in the initial response has resulted in the need to provide nearly double the resources as new land was eventually allocated and refugees have been and continue to be transferred from Nyarugusu to the new sites. It has also been decided that approximately 50,000 Burundians will remain in Nyarugusu and therefore facilities need to be upgraded.

Key contributions by Donor to Burundi Refugee Crisis in Tanzania for 2016 / As of June 2016: Total required $174m (£124m), $67m (£48m) received, 39% funded
Donor	Amount	Agency	Comments
US (Bureau of population, refugees & Migration) / US (Food for Peace programme)	$14.9M / $ 3.9M / $15M	UNHCR ($11m) / NGOs / WFP
ECHO	$13.6M	UNHCR ($9.8m) / WFP ($1.4m) / NGOs ($2.4m)
CERF	$10.9M	UN Agencies
Canada	$2.6M	UNHCR ($1.5m) / WFP($0.3m)
France	$1.1M	WFP ($0.8m) / NGOs ($0.3m)
Sweden	$1.3M	NGOs

The current situation in the camps and possible areas for support:

UNHCR lead the response and are working with a mix of operational (non-UNHCR partners) and implementing partners (funded by UNHCR) to deliver basic services and protection to the refugee population. There are currently 3 camps: Nyarugusu, which hosts a total population of 130,000 (65,000 Congolese refugees who fled DRC in the late 1990’s and 65,000 Burundians), Nduta, (55,000 Burundians) and Mtendeli, (20,000 Burundians). The expansion of the Mtendeli and a possible 4th camp are dependent on finding a supply of water.

WASH: DFID have been supporting Oxfam to install permanent/sustainable water infrastructure in 2 camps (Nyarugusu and Nduta) and a borehole in a third camp (Mtendeli). Nyarugusu camp from the beginning of the crisis was deemed by the Government of Tanzania (GoT) as a temporary camp for Burundians – it is now clear with the lack of water in other locations that 50-60,000 Burundians will remain and therefore there is a need to ensure a permanent supply system throughout the camp. In Nduta there is a need for a borehole to provide backup to the current river extraction system. MSF Holland, through their own funds, are setting up a water system in Mtendeli and along with Oxfam and Tanganyika Christian Refugee Service (TCRS) are in the process of drilling further boreholes to find additional water with the support of UNHCR. A 4th camp is planned and if water is found, provision for further water systems could be part of the contingency funding.

Sanitation and Hygiene promotion: the Sphere Standard of 20 persons per latrine has been achieved, however, emergency latrines need to be replaced as they are full, and ideally if funds are available each household needs their own latrine to enable better levels of hygiene and maintenance. Hygiene promotion activities must continue in order to reduce the risk of the outbreak of water related disease. Core relief items, particularly the availability of household water storage containers remains below standard.

Camp Management: Effective camp management is an essential foundation for delivering other services to refugees effectively. DRC are camp managers for Nduta and Mtendeli. Nyarugusu, (with over 130,000 refugees is one of the largest camps in the world), is managed by a Tanzanian NGO, Tanzania Water and Environmental Sanitation (TWESA), who have little experience in camp management. UNHCR need to adapt their support to match the size and complexity of Nyarugusu camp. By putting in place a more effective camp management system refugees in Nyarugusu will be better protected and receive more efficient services. Camp Management also includes developing community based approaches to help refugees manage the camp, and help ensure better safety, security and accountability. Systems are being developed in Nduta and Mtendeli but Nyarugusu currently has no such systems.

Protection: Child protection and Sexual and Gender Based Violence (SGBV) is coordinated by UNHCR and many elements are delivered by NGOs However there are gaps in the provision of a safe and secure environment for adults; refugees have reported being harassed and some have been accused of political activity. The GoT has set up a detention centre for refugees thought to be involved in political activity. Work still needs to be done to ensure that systems are in place to address refugee fears and suspected political activity.

SGBV: The International Refugee Committee (IRC) is implementing SGBV services in all 3 camps with support from the US Bureau of Population, Refugees and Migrants (BPRM) and through UNHCR. Reports of rape and sexual violence have mainly been during flight. Without appropriate protection mechanisms in place, it can be expected that incidents of SGBV in the camps will increase over time. Gender inequality leading to domestic violence in Burundi is high and there is already considerable evidence that alcohol consumption in the camps is exacerbating the violence. SGBV services can benefit from more resources but there is a greater need to implement other activities to reduce the risk of SGBV – livelihoods activities, for example, will reduce boredom and reduce arguments over money. Reducing the need for women to wander far from camps to find firewood would also reduce risk.

Education: with over 60% of the refugee population being under 18 years old, there are over 80,000 school age children in the camps. The GoT has insisted on permanent structures for classrooms which has created delays in the construction of classrooms as the cost of the 1000 classrooms ideally required is way above existing or likely funding. UNHCR and agencies are lobbying for semi-permanent structures to bring down the overall budgets. Children are being taught on a double shift system which will also reduce the number of classrooms required.

Shelter: All refugees have been moved out of the sub-standard mass shelters, however refugees are now living in emergency plastic sheeting shelters or tents which urgently need replacing. The strategy moving forward is to work with the refugees to build over 28,000 mud brick houses at a cost of $350 per shelter.

Health: Health indicators are above international refugee standards, but there are many concerns over the capacity of the Tanzanian Red Cross (TRCS) to cope with the scale of the need, particularly if there was an outbreak of disease. The International Federation of the Red Cross are supporting TRCS with capacity building and some funds and TRCS will receive funding from BPRM. There have also been delays with drug supply. MSF SWISS and Holland are present and for the time-being provide a backstop to any potential outbreaks.

Self-reliance/Livelihoods: DFID is working on a 3 year business case that will follow on from this humanitarian business case to support the development of self-reliant activities and reduce the dependence on aid thereby enabling refugees to live with greater well-being and dignity. Such activities should indirectly lead to a reduction in risk of incidents of SGBV and risky/anti-social behaviour, as women will not have to adopt risky behaviour (e.g. prostitution) to earn money or get additional food, they can buy firewood instead of walking long distances to collect it, there will be more money in the households which will reduce domestic disputes over resources and working men are less likely to get bored and find anti-social activities to engage in. Two NGOs have already started livelihoods activities and DFID want to maintain momentum with these initiatives until they can be scaled up in the multi-year BC and integrated into UNHCR self-reliance strategy. Despite the encampment policy it is possible for the refugees to develop some livelihoods opportunities and the demonstration of the benefits of livelihoods for both refugees and host populations will help build the case for easing the encampment policy.

Food/Cash transfers: Before the arrival of Burundian refugees in 2015 WFP had undertaken research and was planning to move to cash transfers for the Congolese refugees. The Burundian influx put these plans on hold but is important that the plans for cash are revived and implemented. Cash will enable greater freedom of choice, nutritional diversity and aid the local economy. Cash transfers should help build a case for greater freedom of movement for refugees as the benefits for the economy in Kigoma region become clear. A DFID cash adviser visited the camps (Feb 2016) to assess next steps and found there to be considerable research and information available, gaps remained in knowledge of the market, the supply chain and modalities for cash transfers however these issues could be solved fairly easily and the programme could be phased in over the next year, at least for the Congolese.

Host communities and the environment: the environment is a key concern for the Government, especially destruction of forests, and greater efforts need to be made to manage natural resources (see below). Though the camps are isolated it is important to address key concerns of the host community and to ensure their livelihoods do not suffer from the presence of the refugees. Maintaining social cohesion is also essential for the continued acceptance of the refugees in Tanzania.

UNHCR and Coordination: the coordination of the response in 2015 initially suffered as the local capacity and systems to deal with a large rapid influx of refugees were not in place. But over time UNHCR has built its capacity considerably, it has recently conducted a review of coordination structures, and improvements in the coordination structure are being implemented. However there are still improvements that can be made and UN agencies, NGOs and the Government still need to improve collaborative working in the response, strategic planning, information sharing and reporting.

Gender & Equality Act.
Burundi is one of the world’s poorest countries and ranks as one of the lowest in terms of gender equality - men dominate the household though women are more often ultimately responsible for providing food for the family. Refugee camps can present an opportunity to address some imbalances ensuring women are given a voice and are represented in governance structures. Girls can be targeted to ensure they attend school. DFID will ensure that partners address the needs of women and girls and that of vulnerable groups, including young men are who have been the target of much of the political violence in Burundi.

48.7% of the refugee population are women, 51.3% are men, and 57% are under 18 years old. In the crisis it is young men who have been the target of much of the violence, arrests and detention. A feature of the camps is a higher than normal proportion of single young men who have fled the violence. Young men have also been targeted for recruitment into the Imbonerakure and other rebel groups and families report fleeing to avoid recruitment. Women have been victims of sexual violence in Burundi and women have often had to flee with their children without the support of the husbands to reduce the risk of being targeted or arrested during flight.

In the camps women and girls without an adult male can be vulnerable to exploitation by other men, particularly where they live without the usual support mechanisms of a community. Reports by IRC highlight that women and girls have been the target of sexual assault outside the camp when looking for firewood. Firewood is not only collected for the household but it is also one way to earn money.

1. Some of the mechanisms intended to mainstream gender in their interventions, have in fact served to reinforce gender divisions. Women are deemed the heads of household for food distribution by UNHCR and WFP, a measure which was introduced in 2013 after the last Burundians returned to Burundi. This has caused some dissatisfaction amongst the male refugees as they feel emasculated and feel they are not given the same opportunities to women. Women are often the target of other interventions in the camp such as NFI or small cash distributions which has been given to reduce the need to collect firewood. (See article: www.fmreview.org/solutions/weima).
2. Young men report being targeted by Burundi Government supporters (these reports are unsubstantiated) who have infiltrated the camps and are also the target of arrests by Tanzanian police. Young men have also been arrested as suspected rebels when they leave the camp looking for work.
3. DFID will be funding DRC to improve camp management practices, which includes community based protection mechanisms and helpdesks to improve community based security and reporting of incidents. DFID is also funding livelihoods interventions, a proportion of which will focus on women to reduce the need of women to adopt risky livelihoods practices such as prostitution and collecting firewood. Through Oxfam and UNHCR, DFID will be funding a briquette manufacturing pilot as an alternative to firewood. DFID is also funding an additional 150 street lights in in the camp.

Public Sector Equality Duty
In this BC DFID Tanzania will be partnering large international organisations which have policies on all forms of discrimination. All partners will be asked to demonstrate that policies are in place and all efforts are taken to ensure principles are followed within in the organisation and within the activities implement.

Within the refugee population, those with a disability or other particular needs are targeted systematically though ‘Persons with Special Needs’ (PSNs) programmes. Help Age is the UNHCR implementing partner for PSN support, and is responsible for identifying all people with some form of additional need (disabled, chronically ill and elderly) and ensures they have the appropriate additional support such as appropriate non–food Items, cash payments and transport services.

Care is also taken to ensure those from minority groups and ethnicities are given support. The majority of refugees are Hutu with a minority of Tutsi; attention is given to potential issues which may arise between ethnicities however so far issues have not arisen. Albinos have been targeted in Tanzania as part of witchcraft practices, after one attempted kidnapping refugee families with albino children are being accommodated nearer to police posts.

Reducing environmental impact and increasing social cohesion
A key concern of the Government is that refugees consume a large amount of fire wood. UNHCR now has an environmental strategy and have set up one nursery and set aside funding for 300,000 trees. Fuel efficient stoves have already been distributed by UNHCR, Oxfam and World Vision and work continues on assisting refugees to build their own stoves from clay. UNHCR and Oxfam are looking at options for briquette making programmes to reduce firewood consumption. UNHCR through local NGOs is also working with local communities and authorities on sustainable forest management.

The presence of refugees is also a potential cause of tension, as local populations see refugees receiving goods and services that they also struggle to purchase. With the camps being isolated there have so far been few cohesion issues. However in Mtendeli there are continued negotiations on land and there are increasing concerns that water will be an area of contention in the dry season.

The El Nino 2015-16 did not affect the camps significantly, heavy rains were experienced but there was nothing exceptional. Parts of the camps did flood – but this was mainly due to the use of marginal land as an emergency measure due to overcrowding – site planners are re-organising camps to avoid flood prone areas and construction of drainage is an essential component of camp planning. Reduced rainfall/drought is a potential risk particularly in Nduta where water is taken from a river – water consumption will need to be managed particularly when brick making scales up. Drought in Tanzania could result in higher food prices however this is not predicted to be an issue in 2016.

Compliance with the Terrorism Act
DFID will adopt a risk based approach to ensure compliance with the Terrorism Act throughout programme delivery. This will be done through identifying areas where that may present greater risk. UNHCR, WFP and IOM have made sufficient progress since 2013 MAR to addressing the issues in its financial and risk management to minimise the opportunity for aid funds and resources being misused or diverted to support terrorist activity. Due diligence assessment that includes checks on counter terrorism finance will be carried out to all beneficiary INGOs and recommendations will be provided on the specific areas of concern. Moreover, delivery chain risk mapping covering the entire programme will be carried out (based on existing delivery chain maps for the previous funding), updated regularly and appropriate records kept as part of the delivery plan.

## Appraisal Case

Why Should DFID intervene?

Humanitarian response is a core element in DFID’s UK Aid Strategy , DFID Tanzania is the 2nd largest bilateral donor in Tanzania, and DFID Tanzania was the 2nd largest humanitarian donor after the US in response to the crisis in 2015. The number of refugees continues to rise, a quick return seems unlikely, and a year on much of the emergency camp infrastructure needs upgrading to permanent or semi-permanent – water systems, latrines, shelters, schools and health facilities all require investment. The failure to identify a 4th camp means overcrowding will remain a problem. Basic services need to be maintained and expanded to meet the needs of the rising refugee population. DFID is well placed to influence and promote a more effective response to the current crisis both with UNHCR and the Government of Tanzania.

DFID Tanzania has a long-term strategy to influence both the GoT and UNHCR to develop solutions to protracted displacement. DFID Tanzania’s approach is in line with DFID’s global commitments on protracted displacement and the Wilton Park principles. By continuing to support the immediate needs DFID can more actively influence overall strategy and planning.

The counterfactual: do nothing?

Doing nothing would carry a high risk of reducing the welfare of the vulnerable refugee population in Tanzania and harming DFID’s reputation as a significant humanitarian donor. DFID funding was critical to ensuring that the needs of both long-term Congolese refugees and the recent influx of Burundian refugees were met in 2015 and is likely to be so in 2016.

Burundi is not a high-profile humanitarian crisis and it is unlikely that other donors would be able to fill in the gap left by DFID. UK Humanitarian Policy commits the UK to provide aid where needs are greatest. If DFID support was stopped it would have a negative impact on the most vulnerable refugees in Tanzania who currently rely on humanitarian aid.

Not supporting refugees will result in the health and welfare of the refugee population deteriorating, if health indicators fall DFID may be required to intervene and the cost of such an emergency intervention would be significantly higher. Developing good structure and systems now should reduce risk and costs in the long term.

Additionally, when funds are limited, lifesaving interventions are naturally given priority over longer-term support. By withdrawing from or scaling back funding, DFID would weaken efforts to develop solutions to the protracted displacement and impact DFID’s ability to engage with the Government on its policy on refugees.

How should DFID intervene?

The strategic case outlines the current status of the refugee response and areas of highest needs, it is clear that nearly all areas of the response need support and therefore DFID Tanzania will make a 10% contribution to UNHCR’ s appeal to enable UNHCR to prioritise as it sees fit given the needs as they develop. There are however also a number of key areas where DFID will target specific support:

WASH: The provision of WASH and particularly the development of water infrastructure is essential to the response. By funding WASH directly DFID can ensure that a good quality system is installed which can be maintained with limited input over the coming years-achieving improved value for money over current temporary solutions. Through the provision of family latrines and hygiene promotion activities DFID will be able to contribute to improved hygiene in the camps and enable refugees to manage their hygiene more effectively thus reducing the risk of an outbreak of water-related disease. DFID will fund an NGO to carry out this work directly. The reasons will be explained below.

Camp Management in Nyarugusu – the problems with camp management in Nyarugusu has resulted in one of the largest refugee camps in the world without important camp management systems such as an address system in place and with inadequate community management structures. DFID will fund an NGO directly to ensure camp management services in Nyarugusu are improved with the aim of supporting all agencies in the camp to work more effectively for the refugee population.

Protection and Community services: ensuring a camp has an effective community-led management structure is fundamental for ensuring safety and security in the camp – it will also help community cohesion and support communities in the camp to take greater responsibility in managing their areas of the camp. DFID will support these services by funding an NGO directly in order to ensure better safety and security in the camp, which will include funds for street lighting in key areas of the camps.

Education: The key need within education is classrooms and the scale of the need is vast. DFID will contribute to the construction of classrooms. DFID will fund an NGO directly to construct classrooms to boost the speed of construction.

Self-reliance and livelihoods: DFID is in the process of developing a multi-year business case which will improve self-reliance in the refugee population through a livelihoods approach, and work with the GoT to ease encampment policies in Tanzania. Livelihood activities will also contribute to helping to reduce the risk of SGBV through reducing the need of women to undertake risky practices to earn money, and engaging men in work to reduce boredom and the risk of engaging in anti-social activities. Two NGOs have already started support to livelihoods and DFID will support these initiatives so that they can scale up and be refined in the coming years – ultimately contributing to DFID’s strategic aim of moving the refugee population towards greater self-reliance and reduce protection concerns. DFID will also support UNHCR directly with funding a staff member to develop a strategy for self-reliance.

Environment: This is key area of concern for Tanzania; DFID will provide support for environment projects such as tree planting, fuel efficient stove production/training and help start-up briquette initiatives. Water consumption will need to be manged by WASH actors, as brick making scales up for shelter construction.

Host community needs will be taken into consideration; DFID will ensure that 5-10% of funds will directly or indirectly support host communities.

Food to Cash Transfers: DFID only contribute 10% of the overall food need in the camps, ultimately DFID wants to support WFP to move to cash-based approaches however, there is clearly a need to coordinate with other donors to ensure that there is enough funding. DFID will look at supporting WFP by providing an adviser to enable planning and implementation to get underway as well as funding for food or cash depending on the speed of implementation.

Capacity support to UN : DFID has allocated specific funding to ensure UN agencies have key staff to support the development of key programme areas – Sustainable Livelihoods Adviser for UNHCR and Cash Transfer Manager for WFP.

Contingency: With the continued influx, the potential for a surge in new arrivals and the need for a 4th camp – DFID TZ will keep £2.2m in reserve. .

Delivery Options:

There are 3 delivery options:

1. Contract private sector organisations
2. Put all funds into UN agency appeals,
3. A mixture of funding UN agency appeals and accountable grants with NGOs

A. Private sector: There is currently no private sector organisation directly implementing the response. The private sector is involved in supplying goods and services to NGOs and UN agencies. As there is currently no presence and therefore no operational experience in this area, it is not viable to consider the private sector as an option for direct delivery in an on-going response at this time.

B. UN Agencies: In 2015, DFID supported UNHCR, WFP and IOM. These agencies have global mandates to respond in key areas: food/cash, protection/basic services and transportation. UNHCR also has the mandate and capacity to coordinate the response and to liaise and advocate for refugees with the government. Though there are issues with these large UN agencies, as shown in the MAR, they play an essential role in the humanitarian system. However, DFIDT has found that these agencies are not always able to have the flexibility to try innovative approaches as their priorities are to address the most urgent needs and capacity can be patchy. WFP, for example, despite repeated requests has not progressed far in finding alternatives to food aid (though the 2015 influx did delay plans). NGOs who work on a much smaller scale have been able to innovate quickly - within months of start-up they have distributed cash in the camps and are looking at ways to supplement income and enable dietary diversification. UNHCR initially struggled to build its capacity to lead and coordinate the response which has caused delays and frustrations amongst implementing and operational partners. For example, UNHCR do not have expertise in procurement of technical equipment such as water pumps – which caused delays when working with WASH partners.

C. UN Agencies and NGOs (recommended): DFID have globally agreed to fund UN agencies and as mandated organisations it is important to support them to fulfil their mandates. But DFID Tanzania sees an added advantage in also funding NGOs directly to ensure the delivery of certain key resources and to promote innovation. For example, DFID has previously funded one NGO - Oxfam - to deliver WASH as Oxfam was present in country and had the capacity to scale up and procure quickly. By funding directly Oxfam were able to have sufficient funds upfront to buy equipment and plan more effectively, and DFID were able to ensure key infrastructure was delivered within a reasonable time period. Within the current response it is the NGOs who are able to be innovative; with non-UNHCR funding NGOs have started up livelihoods activities, undertaken cash distributions and rapidly implemented the distribution of fuel efficient stoves. NGOs are also looking for the gaps that UNHCR has not been able to prioritise due to limited funding.

Preferred option and why?

We recommend funding a combination of UN agencies and NGOs. By funding a mixture of UN agencies and NGOs DFID can ensure the main areas of the response are well funded and coordinated, but we can also target key areas we want to see improved or developed. Funding UN Agencies will enable DFID to fund and influence the overall response and ensure key policy areas, such as providing cash as an alternative to food and work on adapting the encampment policy, are actively pursued. Working with NGOs will enable DFID to gain a greater insight into what is happening in the camps but will also help support small-scale innovative approaches which NGOs are better able to implement. Funding NGOs in key areas of the response will help ensure that key gaps that UNHCR is unable to prioritise still receive support.

How will the programme be managed?

The programme will be managed by DFID Tanzania, due to the lack of humanitarian experience in the existing team a Humanitarian Adviser will be recruited.

Costs and Benefits:

The overall cost of the refugee response appeal is $174m (£124m), DFID intends to fund 10% (£12.8m over 9 months) of the overall appeal and maintain £2.2m for contingency. It is unlikely that the appeal will be fully funded so the actual DFID contribution will be considerably higher than 10%. DFID assess that a 10% contribution ensures that DFID is undertaking its burden share and a further £2.2m will be held in contingency.

DFID funding	Agency	Comment
£5m	UNHCR	10% of $74m (£53m)
£4m	WFP	10% of $50m (£36m)
£2.0m	DRC	Focused support for camp management and classroom construction and livelihoods
£1.5m	Oxfam	Focused support for WASH and livelihoods.
£0.2m	UN Staffing support	1* UNHCR for Sustainable Livelihoods Adviser, to develop strategy for multi-year BC. 1* Cash Adviser to accelerate the move from food to cash in the multi-year BC.
£0.1m	M&E	Specialist input for DFIDT on M and E and Humanitarian Adviser.
£2.2m		Contingency

DFID’s burden share will contribute proportionately to the provision of basic services for 140,000 Burundians and indirectly support 65,000 Congolese. The challenge to DFID is to meet basic needs in a way that drives improvements in the cost-efficiency of service provision. It seeks to do this through engagement with UN agencies to ensure better coordination and prioritisation, but funding NGOs separately ensures a focus on some key sectors. DFID is proposing to work through 2 NGOs to provide a) greater efficiency in delivering a permanent water infrastructure and b) better camp management to improve coordination and efficiency in one of the camps where camp management has not been prioritised. Camp management in particular will improve the efficiency of the overall operation by ensuring that community management is in place, leaders are elected, there is an effective address system so that refugees can be located and agencies will receive feedback through helpdesks. A well-installed permanent water system will have long-term benefits and less maintenance costs in the future.

The benefits of the intervention derive from the interventions by the UN agencies and from those delivered by NGOs with direct DFID funding.

This programme will deliver essential services to help ensure the health and welfare of the over 200,000 refugees living in camps in Western Tanzania. It will mean the UN can achieve or maintain some key international benchmarks for refugee welfare such as an under-5 mortality rate (per 1000 population/month) of 0.5 and 2,200 calories per day. By funding livelihoods interventions DFID is setting the scene for a larger scale up of such interventions in the coming multi-year business case, which intends to support the development of greater self-reliance amongst the refugees and help the development the local economy, this will provide refugees not only with an improvement in welfare but provide a sense of purpose and hope for the future for both refugee and host populations, which can be seen as justifying this intervention in itself.

In particular DFID will fund the continuation of small-scale livelihoods activities, implemented by NGOs that will lay the groundwork for the larger multi-year business case which will have a focus on building greater self-reliance for the refugee population. Developing a livelihood will also enable refugees to trade with the host community thus providing some economic benefits to the host community.

Some of the key benefits expected by the programme are:
- A minimum of 70,000 refugees will have access to a permanent supply of clean drinking water, a permanent system will have a longer lifetime and cost less in the longer term to maintain than the current temporary system, and reduce the risk of outbreaks of water-related disease.
- Over 140,000 refugees will live with greater safety and security through community management systems in 3 camps, enabling refugees to feel safe in their communities and be empowered to have more control over their own lives and influence community activities
- 5000 host community members will have access to improved water supply, which will also help reduce the potential for disputes over access to water near Nduta contributing to better social-cohesion.
- Funding 10% of UNHCR budget will help UNHCR maintain the health and welfare of refugees through support to a variety of services in the camp, from shelter construction, provision of the health services and roads and drainage to ensuring the camp is a safe and secure place to live. Not earmarking the funding gives UNHCR the freedom to target highest priority areas.
- 10,000 refugees and 250 host households will benefit from livelihood activities, which will enable refugees to earn an income to buy essentials, improve and diversify their diets thus improving overall health/nutrition status, reduce dependency on aid, promote better mental health as refugees have something to do every day. More money and less boredom will reduce household arguments over money and reduce domestic violence and livelihood activities will help the economy of the camp and local area as refugees and host community can trade.
- 0.5 million trees will be planted to replace trees used in the camp, reduce environmental impact and reduce tension with local authorities.
- Over 5000 children will benefit from 80 schools , enabling children to receive an education protected from the weather, good facilities will increase school attendance and provide an improved working conditions for teachers.

Whilst not a new humanitarian crisis, there is a continued and pressing need to provide additional funding to ensure the basic needs of the existing refugee population and new arrivals are met. The additional £15m funding will help ensure that the existing camps are able to cope with the growing refugee population, primarily by helping to improve overall response efficiency through strengthened camp management, boosting community protection services to help ensure refugees feel safe, improving water and sanitation services to reduce the risk of disease outbreak, the provision of food assistance to maintain good nutritional status and an overall contribution to basic service delivery through UNHCR. These are essential needs and the counterfactual is a heightened risk of disease, poor health and social-cohesion issues with the host community, which could result in Tanzania Government refusing to allow further refugees to cross the border. These benefits have not yet been monetised but there is a clear case to intervene to support the appeal. A key feature of the intervention is to set the scene for a longer-term more developmental intervention: doing so is cost-effective in reducing the need for ongoing humanitarian support.

What measures can be used to assess VfM for the intervention?

All DFID partners are up and running in country and therefore there are no significant set up costs. Both NGOs are UNHCR implementing partners and have prearranged agreements with suppliers. However, 1 year into the response the programming is still operating in an emergency state as infrastructure is still being built, refugees are being transferred from one camp to another, and up to 100 people continue to arrive per day. We will use the period of this BC to start to build better VfM measures. For the purposes of this BC, our VfM objectives will to 1) engage with partners to develop an evidence base that will allow us to determine the cost of key inputs and outputs (e.g. the sphere standard of 20 litres of water per person per day) and then 2) identify measures that will allow us to reduce costs in some key areas of the operation and so reduce costs for certain outputs. We will focus on costs and outputs for food/nutrition, water, and education as these are the highest costs of the overall operation and also where we have a direct funding interest. We will also discuss with partners the possibility of conducting a review of procurement systems to see whether an adjustment to procurement approaches now the main phase of the emergency is over might result in any savings. Once this evidence base is in place, and we have agreed with partners the value of this approach, we will move to a more sophisticated approach to VFM in the multi-year BC and will look to quantify benefits so the cost-effectiveness of different approaches can be compared. In practice, for this BC, this means that DFID will agree with each partner, based in the interventions they are delivering, on metrics to ensure that inputs are purchased at the lowest cost to deliver to quality and on time, that the inputs are effectively achieving the outputs that these are having the desired effect on achieving the outcomes, identify where savings might be made, and seek to achieve savings wherever possible. Given the overall appeal is underfunded, this should then also free up funds to finance underfunded elements of the appeal.

1. Both NGOs have submitted proposals and budgets and have been assessed for cost-efficiency, and effectiveness, The budgets are in sufficient detail to assess some input costs, such as the estimated cost of a semi-permanent latrine, classroom and estimated costs of the installation of water systems, Both agencies are planning to reduce international staff and build capacity of partners. Both agencies work with the same national partner therefore there can be synergy and cost sharing on partner support costs and training which should reduce costs as specific joint activities can be organised. Both are planning to open activities to the host communities and both are planning similar livelihoods activities but are targeting different camps, which demonstrates coordination. Both agencies have provided clear, good quality documentation. However we not yet in a position to be able to assess output costs. The Humanitarian Adviser assesses that proposals and budgets provide a good justification of costs but it is likely that certain costs and activities will need to be adapted during the course of the programme.
2. DFID Tanzania will agree specific metrics for each partner during finalisation of agreements. Indicative VfM metrics that link the costs of each intervention to what is trying to achieve is set out in the table below. This will form the basis for agreements with each partner, who will report on a quarterly basis to the DFID adviser.

Output	Economy	Efficiency	Effectiveness	Responsibility for reporting
Minimum 15 litres water per person/day	Cost of upgrading Nyarugusu water system. Total £95,000, £1.36 per beneficiary based on 70,000 people.	Number of people using the water system. / Average distance from shelter to tapstand? / Who are they (e.g. are any groups excluded? If so, why?)	No outbreak of water related disease.	Oxfam
	Cost of installing water system in host community (Nduta) £45,000	As above	No. of arguments between host community and refugees. / Evidence of water being diverted from river by host.	Oxfam
100% of primary aged children in school/compete year	Cost of building a classroom / $8000 per classroom	No. of classes taught in a classroom. / No. of pupils taught in a classroom.	Proportion of classes cancelled because of not being in a classroom. / Education attainment measures	DRC and UNHCR
2,200 cals per person/per day	Cost per tonnes of food commodity and the cost per HH.	Number of complaints regarding the food distribution?	Nutritional indicators	WFP

 Theory of Change:

DFID provides resources to enable partners to implement the necessary activities and supplies to provide the essential basic services which will improve or maintain the health and welfare of the refugee population.

Funds

DFID Staff (1PM 0.2, 1 HA.

UN advisers *2.

Joint, more effective coordination of planning and response by donors, the UN, GoT and partners.

Partners implement activities to provide basic services.

Increased advocacy with GoT for access to land.

Expansion of livelihood approaches in support of self-reliance possibilities

Beneficiary consultation and feedback to improve the response.

Basic social services are provided and maintained for the refugee population.

Food distribution

Permanent water system installed.

Host community water supply.

Camp and community management systems are in place

Refugees and host benefit from livelihood interventions.

Environmental management activities

Health and welfare of refugees’ population is improved and maintained.

Improved quality of life and reduced vulnerability of refugees, and host communities in Tanzania.

Inputs
Process
Outputs
Outcome
 Impact
VFM

Cost of inputs eg ton of pulses, classroom
Cost of outputs eg 2,200 calories per person, 15 L water/person/day

Assumptions:
Assumptions:
- Government of Tanzania and Ministry of Home Affairs fully support community camp management processes.
- Government provides more land for refugees, especially if there is a new influx
- Government continues to support livelihoods interventions.
- Boreholes produce sufficient water.
- Improved coordination between aid agencies (UN and NGOs) in the response.
- Other donors continue to support the appeal to at least 50% funding

Risks for matrix in Management section.

Commercial Case

Option 3 has been assessed as the recommended option – using a combination of UN and NGOs: The following table outlines the delivery arrangements:

Programme outcomes	Agency	Direct or indirect	Instrument	Amount (million)
Provision of basic services through contribution to appeal	UNHCR	indirect	MOU	£5.00
Food/cash transfers (appeal contribution)	WFP	indirect	MOU	£4.00

WASH, livelihoods	Oxfam	indirect	Accountable Grant	£1.50
Camp management, community services, livelihoods, classrooms	DRC	indirect	Accountable Grant	£2.0
Surge staff	Staffing	direct	MOU	£0.30
Contingency	Contingency			£2.20
	Total			£15.00

Direct Procurement:

£0.3m is proposed for CHASE-OT deployments, through the existing CHASE OT contract:
- £0.1m DFID Humanitarian Adviser to advise and guide programme implementation and a specialist M&E input.
- £0.2m for 6 months for surge staff for UN agencies – Cash Manager for WFP and Sustainable livelihoods Adviser for UNHCR.

Though not in the peak of the emergency there is a need to get staff in place for the key programme areas. Procurement processes particularly within UN agencies are slow and in order to boost key programme areas and accelerate the development of longer term strategies it is important that staff are found quickly. DFID Tanzania will use the CHASE OT roster to rapidly deploy staff into the UN agencies. CHASE has a roster of pre-selected staff and pre-existing frameworks for rapid deployment which have already taken into account DFID requirements for value for money thus enabling us to maximise speed against pre-checked quality standards and considerations.

Indirect Procurement:

Indirect procurement will account for £14.7m (98%) of the total budget.

Market Place:
DFID will not be opening this programme to the market. The programme is supporting an on-going humanitarian response where UN agencies and NGOs are already in operation. DFID has a global agreement to support UN agencies and therefore DFID will fund UNHCR, WFP and IOM (if required as part of contingency funding) in accordance with global agreements. For NGOs DFID Tanzania do not see any advantage in running a competition. This is because UNHCR have already run a tender process and received 26 expressions of interest for 10 sectors, which indicates that there is a limited market, which reflects the isolated location of camps, high set up costs and the number of humanitarian actors operating in Tanzania. For WASH in particular, UNHCR received 5 bids. UNHCR selected Oxfam and 2 national NGOs on the basis of the quality of application, existing presence and operational experience. Of the two agencies not selected one was only offering small scale water treatment and not able to offer a full WASH programme, the other an international NGO was proposing to start up activities and therefore had additional costs and no experience in the region or in Tanzania. Similarly, for camp management, only one international NGO (DRC) and a national NGO applied for camp management. There is no evidence that indicates that a DFID run process would present a different result, and if we did find a partner we would then have to negotiate with UNHCR to accept additional operational partners in key programme areas where they had already selected partners, which will cause confusion and disruption. Therefore DFID Tanzania believes that the NGOs selected for support through this BC are the only viable international NGOs in the sectors of WASH and camp management.

Private sector will be contracted through NGOs for certain activities – e.g. borehole drilling, classroom construction and procurement of relief items.

NGOs: DFID Tanzania intends to fund Oxfam and DRC. Both are UNHCR implementing partners and went through UNHCR’s selection process. Both are the only viable international partners operating in their key sector. Oxfam – WASH and DRC camp management/community protection services. Both NGOs have global experience and have full teams in place to implement the operation with oversight from Regional and Head offices which help ensure that in country team delivers.

Oxfam: has previously been DFID’s WASH partner, and have already installed permanent water infrastructure in the camps. They have the knowledge and experience to rapidly install the necessary systems. By funding them directly Oxfam are assured to have sufficient funds to plan and install the system quickly and efficiently and reduce transaction time with UNHCR as Oxfam will be able to independently procure necessary equipment. Oxfam have already been working with the national NGO TWESA and Oxfam will continue to work with them to build capacity for the long-term sustainability of the response. Oxfam have also been the first agency to implement livelihoods activities in the response and as part of DFID’s long-term strategy for self –reliance we plan to provide small scale funding to keep these activities live – until we can scale up livelihoods through formal completion in the multi-year BC.

DRC: DFID plan to fund DRC due to the need to support better planning and coordination in camps, UNHCR have selected DRC for camp management in Nduta and Mtendeli but choose to keep the nominal national NGO with no real experience of camp management in place in Nyarugusu despite its size, due to lack of funding and due to the fact the UNHCR had expected Nyarugusu to reduce in size. DFID funding will support camp management in Nyarugusu which has a population of 130,000 (who are very likely to remain). As part of camp management DRC are implementing community protection services - a network of community watch people to ensure communication and safety in the camp. UNHCR are only able to pay for the bare essentials and by funding DRC DFID will help to ensure better community safety in the camp. DRC have been constructing classrooms with UNHCR funding which has recently finished. With over 500 classrooms required DFID can boost the number of classrooms by funding directly at a lower cost than through UNHCR as DFID will only pay one set of non-project attributable costs (NPACs). DRC have together with Oxfam been promoting livelihoods interventions and bring a wealth of experience in self-reliance in order to maintain momentum DFID want to provide small scale funding to keep these activities going until the multi-year programming can be implemented.

Both Oxfam and DRC have been selected as the only international partner in their key sectors and enable DFID to support multiple programmes activities without engaging further partners.

DFID will fund the following UN Agencies: UNHCR, WFP and IOM (from contingency only if required) DFID Tanzania has worked with them all previously. UN partners are mandated to respond in humanitarian emergencies and DFID has globally agreed to support these organisations. All 3 have been assessed by DFID in the MAR 2016, with the following summaries:

UNHCR: plays a critical role in helping to deliver UK and international priorities to address the protection and other needs of forcibly displaced persons and stateless people, in fragile and conflict-affected contexts. UNHCR has an important role in strengthening the effectiveness of the overall humanitarian system; it needs to work better with partners involved in the humanitarian response, and adapt so it can partner better with development agencies. Whilst it has made some progress, UNHCR needs to strengthen its accountability and transparency, climate smart programming, and maximise its contribution to Leave No-one Behind.

UNHCR has made progress since the 2013 MAR Update in the way it addresses sexual and gender-based violence as well as in its financial management, risk management, and fraud prevention.
Performance by component scores found UNHCR as follows:
What it does	Very Good
Where it works	Good
How it Delivers	Adequate
Results and Value	Good
Risk and Assurance	Good
Transparency and Accountability	Weak

WFP: is well organised, with robust systems, good organisation of human resources and reliable risk management and fraud detection procedures. WFP at times faces challenges in using the most appropriate interventions (i.e. often cash transfers can be more effective than giving vouchers or distributing food), and in ensuring better outcomes for women and girls systematically. It can prioritise its programming further to obtain value for money, and improve the way it targets and is accountable to the people it helps. WFP has been improving its performance management system in recent years. WFP can improve this further by integrating its management and strategic results frameworks in a single Corporate Results Framework. Performance by component scores found WFP as follows:

What it does	Very Good
Where it works	Good
How it Delivers	Good
Results and Value	Good
Risk and Assurance	Good
Transparency and Accountability	Adequate

IOM’s flexibility has allowed it to operate on a large scale and at speed including in recent migration emergencies. IOM is working towards establishing a portfolio based on needs and humanitarian principles. It has a wide geographical reach in fragile and conflict-affected states and is continuing to invest in its rapid response capacity. IOM must continue to aim for outstanding transparency standards, finding a way to work around the sensitivities of its field. It needs to clarify how value for money can be best achieved and better demonstrate how it incorporates accountability to affected populations in all its programming. IOM has made progress since the 2013 MAR Update in developing frameworks to guide its programmes; however work on results-based programme management needs to go further. Performance by component scores found IOM as follows:

What it does	Very Good
Where it works	Very Good
How it Delivers	Good
Results and Value	Good
Risk and Assurance	Adequate
Transparency and Accountability	Weak

IOM has been included in this business case as a potential contingency planning partner. They have systems in place to respond to the need to transport large numbers of refugees if required . DFID supported them in the 2015. .

Key Cost Drivers:

The main cost drivers for the programme will be food items, construction materials, relief items and water system equipment (pumps, tanks, boreholes, piping). With the isolation of the camps transportation costs are high and increased the cost of supplies and thus the overall operation. Staffing costs also drive costs as there is limited capacity locally therefore staff have had to be recruited internationally or elsewhere in Tanzania and there is limited accommodation resulting in high accommodation costs.

## Financial Case

Who are the main recipients of all proposed Payments?

DFID will provide 5/6 months of funding for UN agencies (end Dec 2016) and 8/9 months of funding NGOs (end of March 2017).

Agency	Amount	Non-project attributable costs (NPAC)
UNHCR	£5.00m	7%
WFP	£4.00m	7%
Oxfam	£1.50m	11.9%
DRC	£1.50m	7%
Staffing	£0.30m	n/a
Contingency	£2.20m	n/a
Total	£15.00m

Costs to be incurred by DFID?

1. £15m between July 2016 and March 2017. No cost will be incurred by third party organisations.
2. DFID will be funding 10% of both UNHCR and WFP Refugee Response appeals in Tanzania. Both UNHCR and WFP charge DFID a 7% NPAC, both will then incur NPAC from downstream partners.

DRC and Oxfam have NPAC agreements with DFID at 7% and 11.9% respectively. By funding both NGOs we save on doubling NPAC provision. i.e. the construction of classroom at £0.5M directly will have an NPAC of 35,000, through UNHCR the overall NPAC 14% would be £70,000.

There is no direct funding of Government.

The programme will be funded through DFID Tanzania programme spending.

Forecasting:
UN agencies will receive funds in lump sum once the MOU is signed (July 2016). NGOs will be paid retrospectively after 3 months c. £1M and 6 months £1m in Oct and February and a final payment of project completion July 2017 c. £1M.

Contingency funding will be allocated according to context, however if not committed by September will be gradually reallocated to within the response.

Financial risk and fraud?

The agencies that DFID fund will undergo the necessary due diligence assessment. In line with the approach agreed by DFID’s Risk and Control Unit.

UNHCR and WFP performed well in the MAR process: (see commercial case). They will not be assessed at country level, but the annual country level audit reports will be referenced.

Due diligence has already been under taken for Oxfam but requires updating in 2016. Oxfam have found fraudulent activity within their current response. Their systems picked up fraudulent activity within a number of procurements. A full investigation was undertaken and at the time of writing management are agreeing actions going forward and action is being taken against a number of staff. DFID Tanzania understood that there is a risk of fraud in Tanzania but that Oxfam’s systems and procedures are in place. Indeed they have picked up irregularities and these systems worked. Oxfam are resolving the gaps in the systems which led to the fraud to reduce future risk.

1. DRC are a new partner in Tanzania but not a new partner to DFID globally. Due Diligence was carried out for DRC for programmes in the Syria Crisis. A Tanzania country level Due Diligence has been carried out and necessary recommendations have been agreed.
2. In compliance with DFID’s zero tolerance policy on fraud we will follow up with agencies where we have reasons to believe that DFID-funded operations or supplies have been lost, damaged or unaccounted for. We will continue to inform partners of this policy.

Monitoring and Evaluation:

All partners will provide financial reports as set out in the MOU and accountable grant agreements. For NGOs this will include interim and final financial reporting. In addition NGOs will submit audit reports and UN agencies certified annual financial statements on an annual basis.

DFID will also undertake periodic monitoring and evaluation during visits to examine value for money and other aspects of the intervention. (see management case)

Management Case
## Management Arrangements

The Senior Responsible Owner (SRO) will be responsible for overall programme delivery and reporting. The SRO will be DFID Tanzania Governance Adviser (30%) who will be supported by a Humanitarian Adviser (100%). The DFID Tanzania Governance Programme Manager (20%) will be supported by 1 Programme Officer (10%) and will supervise the programme management process and ensure corporate compliance.

DFID Tanzania will require ad hoc advisory input from DFID Tanzania Human Investment Team – for WASH, health and nutrition, social protection and gender/SGBV.

DFID will work with key humanitarian donors in Tanzania to have a dialogue with the Government of Tanzania, UN agencies and NGOs on ensuring that the response is well coordinated and that standards are met and key needs prioritised.

DFID will work closely to support UNHCR Tanzania to ensure it implements the Refugee Coordination model and work with them to ensure improved communication and strategic planning. Providing funding for a Sustainable Livelihoods Adviser should assist better long term planning for self-reliance.

All agreements will follow DFID’s template but will annex any additional arrangements, for example specific reporting requirements and preconditions for fund transfers. The agreements will also contain an exit clause allowing a termination of the agreement should partners consistently fail to deliver results, should the needs of the project change or should their financial management worsen.

There are specific groups within refugee population that are likely to face particular obstacles and risks. These include those with disabilities; the elderly; and unaccompanied minors. The need for consideration of the particular needs of these groups will be signalled, along with the need for evidence of gender-appropriate design, in arrangements with UN, other international organisation and NGO partners.

Monitoring and reporting:

The programme will be managed as a whole with a single log frame (Annex 1) as the primary management tool. Each partner will report based on its contribution to the results and will report back to DFID against the log frame targets. NGOs will submit quarterly reports and a Project Completion Report produced within three months of completing the programme and for UN agencies DFID will use their annual multi-donor report and will expect to see regular response sitreps. The programme team will hold programme review meetings with all partners and conduct regular field trips in order to track overall progress and assess risks. All partners will be monitored in terms of Red Cross/NGO code of conduct and attainment of Sphere standards.

Beneficiary feedback will be a key part of monitoring – through talking to refugees and host communities and ensuring the implementing agencies have a system in place to collect and respond to beneficiary feedback.

Evaluation:

This BC does not require an evaluation. A PCR will be completed at the end of the programme to assess overall impact.

## What are the risks and how these will be managed?

DFID T is has developed a delivery chain map of humanitarian partners, which identifies delivery, financial and reputational risk not just with the primary partner, but also down the entire chain to the ultimate beneficiary (Annex 2). This will improve our ability to identify and manage risk.

The overall risk rating of the project is moderate.
Risk	Impact	Likelihood	Mitigation	Residual risk
Weak leadership and Coordination by UNHCR	M	M	Monitoring through regular consultation with other NGOs, other partners and government. / Informal and formal feedback to UNHCR rep on and suggestions on improvements. / Ensure that there is national coordination meeting to solve issues. / Linking up with other DFID COs in the region and HQ as necessary	Major
Situation in Burundi deteriorates rapidly, resulting in a rapid influx of more refugees.	H	M	Lobby for land for more camps. / Ensure that contingency plans are in place. / Lobby for more funding.	Major
Government of Tanzania rapidly forces refugees to return with a peace agreement.	H	M	Embassies and UNHCR engage early with government on conditions for return. / Lobby and advocate with GoT and focus on lessons learnt from previous returns process. / Ensure there is an analysis of which refugees are repeat refugees and support alternative durable solutions.	Moderate
Insufficient funding	H	M	Lobby other donors for increased support particularly if new influx. / Implementing agencies work to prioritise essential services.	Major
Fraud/Theft	M	H	Due diligence, ensure agencies have financial systems in place and are managing them. / Financial reporting	Moderate