Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: / CHASE Urban programme
Programme Value: £3,523,593		Review Date: 27/09/2016
Programme Code: 204273	Start Date: 07/10/2014	End Date: 31/12/2017

Summary of Programme Performance
Year	2015	2016
Programme Score	A	A
Risk Rating	Mid	Moderate

Summary of progress and lessons learnt since last review
The programme continues to perform well. Both parts of the programme – led by the International Institute for Environment and Development (IIED) and the International Rescue Committee (IRC) respectively – are progressing as expected. Some flexibility was required at the beginning on the setting up of the programmes, and both now continue to deliver useful knowledge products, tools and advocacy. There appears to be good synergy between the parts of the programme.

The programme also appears to be increasing interest and participation by others in urban issues. IRC’s role in forming the Global Alliance for Urban Crises at the World Humanitarian Summit is very positive. It will be important to see the Alliance delivering tangible change on approaches to urban crises. IIED has done well to launch three calls for proposals so swiftly and to manage a number of small research grants in limited time and with reasonable management costs.

The relevance of the programme continues, especially as urban crises continue to grow in importance at the centre stage of humanitarian crises, e.g. the Syria crisis, and the role of urban municipalities generally in humanitarian crises. This opens new doors and there is an opportunity to build upon the interest generated.

The programme needs to ensure that lessons learned, tools, etc are turned into results on the ground, and that the programme is able to assess this as much as possible through effective monitoring and evaluation.

Summary of recommendations for the next year
The work on monitoring and evaluation is important and needs to be delivered – it will be useful to see not just what activities have been done, products delivered or advocacy undertaken, but how much they have been accessed, used, etc (to the extent it is possible to attribute), and what impact they have had.

IIED and IRC need to continue to focus on complementarity and build upon all parts of the programme.

IRC have played a big role in the foundation of the Global Alliance for Urban Crises – building on this and developing the Global Alliance should be a priority. While IRC’s advocacy to date has been largely aimed at raising the profile of urban crises, it should become increasingly specific in what practical changes it is calling for in urban humanitarian response.

IRC have requested a 12 month cost extension for their part of the project, taking it up to December 2017, and in line with the IIED end date which DFID should consider. An extension should enable the Global Alliance to be firmly consolidated and institutionalised and ensure its sustainability post 2017.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	Business Case
DevTracker Link to Log frame:	Log Frame

Outline of the programme
This programme responds to the Humanitarian Emergency Response Review’s identification of urban areas as increasingly frequent locations of crises, and the widespread lack of confidence and capability within the humanitarian system to operate in urban environments. The main purpose of the programme is to increase DFID’s, its partners’, and the humanitarian system’s capability to respond to urban crises.

This business case has 2 components. Component 1 is an advocacy and learning partnership with the International Rescue Committee (IRC). Component 2, managed by the International Institute for Environment and Development (IIED), is a capability fund that will make grants to support documentation of and learning from good practice, and the development of practical tools.

Total value of the project is £3.5m over the period October 2014 to December 2017.

Component 1
IRC’s contribution to the programme is an innovative learning and advocacy ‘co-production’ partnership with DFID, in which IRC acts as convenor and catalyst in support of an enabling policy environment for improved response to urban crises by government, humanitarian and development actors. IRC’s contribution to the programme has two outputs:

1. IRC’s advocacy focused output is working to broaden the range of actors involved in responding to urban crises and encourage key stakeholders to develop, review and enhance their policies on urban contexts and their implementation. To this end, IRC is implementing a programme of policy engagement focused on the World Humanitarian Summit (WHS) and Habitat III, both in 2016, as well as contributing to other international forums and conferences.

2. IRC’s learning output is working to improve humanitarian and other actors’ understanding of how crises impact urban contexts and how to programme effectively in towns and cities. With a particular focus on working with local authorities and on cash and livelihoods programming, the partnership will generate evidence-based knowledge products that draw on IRC’s and other organisations’ operational experience in crisis-affected towns and cities, and will disseminate lessons learned and good practice

Component 2
IIED’s contribution to the programme aims to strengthen understanding and improve practice among national and international humanitarian actors, local and national governments, and donors, with regard to approaches to humanitarian response in urban contexts. It seeks to do this by addressing gaps in knowledge, technical capacity and skills in order to provide a better basis on which to prepare for and respond to humanitarian crises in urban areas. The work by IIED has three mutually reinforcing outputs:

1. Coordinating a ‘learning partnership’ of leading international organisations (including NGOs, multilateral agencies, and academic institutions) working in the field of urban humanitarian response, in order to document best practices, generate tools, and develop innovative operational working methods.
2. Managing a ‘learning fund’ and ‘responsive small scale research and documentation fund’ to support innovative thematic and regional research on key issues shaping humanitarian responses in urban areas.
3. Coordinating learning events and networking activities in order to disseminate best practices, discuss policy changes, and build the capacity of key actors. This output also includes an efficient and accountable project- and grant-management process to create and coordinate a Strategic Steering Group (SSG); undertake monitoring, evaluation and learning (MEAL) activities; and disburse funds.
## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

Both programmes are delivering on the Outputs, which are easily quantifiable (e.g. number of knowledge products produced, number of events organised). Outcomes around increasing knowledge and commitment of stakeholders to urban issues are harder to assess, but proxy indicators such as activities undertaken and access of products (e.g. website access) are positive.

Overall output score and description

A – Overall the Urban programme is scored A. All Outputs on both parts of the programme are meeting expectations.

Key lessons

The programme has established IIED and IRC as actors in the Urban humanitarian aid area – and interest in this area of work is generally growing (the project may have contributed to this, or at least galvanised interest) and should continue to grow.

Urban issues are now a core part of IRC’s activities – whereas previously they may have been seen as a separate area, urban issues are now widely considered throughout the organisation.

There has been unexpected and welcome interest from others, such as professional bodies (e.g. the Royal Institute of British Architects).

Key actions

Partners should continue to ensure complementarity between the knowledge and learning products that they are producing or commissioning, so as to minimise overlap in content or proposed audience.

It is important that the project can measure outcomes, such as how the policies of partners are being changed – IRC’s monthly ‘outreach tracker’ is useful, as is IIED’s process tracing and social network analysis.

There is a need to think about sustainability and how to build on the programme’s successes - other donors are considering providing support and this should be encouraged. The potential ‘game-changer’ is the full development of the Global Alliance for Urban Crises.

How to tailor support and outputs to assist local and sub-national governments will be an important issue to keep in view.

Another important issue is dissemination of the findings in the various knowledge products, and ensuring that there is genuine uptake by practitioners.

Has the logframe been updated since the last review?

No.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Advocacy: Key stakeholders are encouraged to develop, review and enhance their policies on urban contexts and better operationalise them
Output number per LF		(IRC) 1	Output Score	A
Risk:		Moderate	Impact weighting (%):	33%
Risk revised since last AR?				Yes, but only because of change in DFID’s grading system	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Number of advocacy products produced with actionable policy recommendations that address how humanitarian, development and urban stakeholders can improve response in urban contexts and disseminated at regional and global advocacy and policy events and through online downloads.	By December 2015: 3 papers / By December 2016: At least 6 advocacy products (papers, reports and briefings) have been published or electronically circulated over the course of 2 years	During the period covered by this Annual Review, the following papers have been prepared, bringing the total number of advocacy products produced by the programme to 6 and achieving the target ahead of schedule: / ‘Urban Crises and the new Urban Agenda” – 4,000 word paper published on the journal ‘Environment and Urbanization (April 2016) / A two-page briefing paper on the same topic was also prepared and circulated at a number of New York events focused on Habitat III / ‘Cities are at the centre of the Syrian refugee crisis – so why are they being ignored?’article for Guardian Cities written in collaboration with IRC’s President and CEO, and appearing under his name. / Additional papers on urban displacement, cash and working with local authorities are planned to be disseminated before December 2016 which we expect will exceed the target.
Number of events at which evidence based advocacy messages are shared (side events, high-level panel events).	By December 2015: 4 events / By December 2016: At least 6 events where advocacy messages are shared	To date the programme has met the target for December 2016, and may exceed it. / During the period covered by the Annual Review 2016 the programme co-hosted or organised the following events, bringing the overall programme total to 10. / WHS Global Consultation side event co-organised by IRC ‘A Global Urban Crises Alliance: Managing Conflict, Disaster, and Displacement in Urban Contexts’ with a breakout group focused on the role of the Alliance and local authorities (October 2015) / Side event at the 32nd International Conference of the Red Cross and Red Crescent Societies, Geneva, December 2015.. / High-level event, ‘City Haven’, on urban displacement. / Member state and UN agency briefing at the UN in Geneva (hosted by OCHA) co-organised by IRC on the importance of the urban humanitarian crises agenda in the lead up to the WHS (February 2016). / Special Session of the World Humanitarian Summit in Istanbul, where IRC and UN-Habitat launched the Global Alliance for Urban Crises. / United Nations Economic and Social Council (ECOSOC) Humanitarian Affairs Segment 2016 side event on Urban Crises and the New Urban Agenda co-organised by DFID, IFRC and ICRC, (June 2016) / Pending a decision by the Conference / Secretariat, IRC will also co-host a networking session with IIED and a side event at Habitat III.
Number of targeted stakeholders (including humanitarian, urban and development) briefed by IRC on the specificities of urban crises and key recommendations.	By December 2015: All Ditchley Park attendees in Group A have had at least 2 follow-up meetings and 30% of Group A have sent representatives to other IRC events. Initial meetings held or other forms of institutional engagement with Group B stakeholders / By December 2016: Engagement maintained with all Group A organisations and follow-ups with Group B. Briefings extended to five additional high-level stakeholders (donors, international multilateral agencies or INGOs)	All Group A stakeholders have had at least 2 follow-up meetings, and 76% have sent representatives to other IRC events (UNHCR, OCHA, UNDP, IFRC, ICRC, IOM, UN-Habitat, World Bank, ECHO, DFID, Danida, SIDA, WFP/FAO food security working group). / IRC have started and maintained communication with 3 additional governments (Germany, Switzerland and the Netherlands). / Institutional systematic engagement has also been maintained with all Group B stakeholders. / Outreach to well beyond 5 additional stakeholders has been achieved through sustained advocacy activities that culminated with the launch of the Global Alliance for Urban Crises. The Alliance now has more than 70 members. This has exposed a large number of new actors, including associations of urban professionals, Member States and municipal authorities, to messages developed by the IRC and other Alliance members on the intersections between urbanisation and humanitarian action

Key Points

The policy and advocacy engagement of the programme over the past year had significant success in delivering on the milestones and being on track to exceed final targets.

IRC’s decision to co-convene the urban expert group for the World Humanitarian Summit (in collaboration with UN Habitat) has multiplied its outreach to humanitarian, development, academic, professional and local government institutions. At the Global Consultation for the WHS in Geneva, October 2015, IRC with UN-Habitat organised and facilitated a side event introducing the Alliance to prospective members and discussing its potential role, and was also involved in a side event on ‘Urban Innovation’.

IRC has since taken on a leading role in the establishment and interim management of the Global Alliance for Urban Crises, which was launched at a Special Session of the WHS in May 2016. With over 70 members, the Alliance has exceeded expectations in terms of reach, and IRC is already in discussions with potential international donors for funding the Alliance activities and Secretariat functions.

Alongside high-level events and formal side events, the Urban Crises programme has also fielded staff for panels and workshops in international fora, including.

- Technical inputs to a workshop session on ‘New ways of working’ at the OCHA Global Humanitarian Policy Forum in December 2015.
- Presenting at a thematic panel on ‘Public Spaces, Informal Settlements and Civic Engagement’, convened as part of the preparations for Habitat III
- The Resilience Week in Barcelona where IRC’s Senior Urban Coordinator participated in a panel discussion on the role of the Global Alliance for Urban Crises and highlighted both gaps and examples of good practices from field operations (March 2016).

The frequency with which IRC and Urban Crises programme staff are requested to speak on panels demonstrates their thought leadership on the issue of humanitarian action in urban areas.

The events to which IRC has contributed, as well as those organised by the IRC to meet programme deliverables, have provided a wide range of opportunities across Europe and the US for outreach, dissemination and amplification of the programme’s messages. They have also contributed to the consolidation of IRC’s engagement with all Group A and B stakeholders.

Summary of responses to issues raised in previous annual reviews (where relevant)

The main recommendation from last year suggested to increase dissemination of advocacy messages with European donor and multilateral agencies based in European capitals. IRC has acted on this recommendation and have scaled-up outreach to European donors, particularly the Directorate-General for European Civil Protection and Humanitarian Aid Operations (ECHO) and Geneva based multilateral representatives. For greater impact, outreach has also been conducted through senior IRC officials when meeting European donors and other agencies. Engagement with the Netherlands, Switzerland and Germany has also been initiated.

Recommendations

While progress on advocacy has been made to date, it will be important for IRC to focus on what specific aspects of today’s policy and practice it wants to change over the remainder of the project and what the operational implications of doing this are.

DFID understands that the conference secretariat for Habitat III rejected IRC’s proposition to organize a side-event. IRC should work on alternative plans that will mitigate the consequences and inform DFID of its intention in that regard.

It will be important for IRC to document and share all the elements that have secured success, and to include them in future programme design.

Output Title	Learning: Humanitarian and other actors supported to have greater understanding of how urban contexts are impacted by crises and how to programme effectively for the urban context.
Output number per LF		(IRC) 2	Output Score	A
Risk:		Moderate	Impact weighting (%):	17%
Risk revised since last AR?		Yes, but only because of change in DFID’s grading system	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Number of knowledge products produced on how urban contexts are impacted by crises and how to programme effectively for the urban context.	By December 2015: / 1 knowledge product produced / By December 2016: At least 3 knowledge products produced based on evidence and lessons learnt from IRC urban programming and other non-IRC urban humanitarian and development programming over life of project.	The programme has progressed on the production of the following knowledge products on track to meet December 2016 target: / Finding Economic Opportunity in Cities: Lessons from IRC’s Cash and Livelihoods Programmes in cities within Lebanon and Jordan which has been first shared with DFID in October 2015. The product focuses on cash and livelihood programming in the urban areas of Lebanon and Jordan. This product has been refined and enhanced during the development of the pieces 2 and 3 described below to ensure consistency of language and design / Urban emergency response in Lesbos, Greece – drafted and currently under design / The right to the city for urban refugees in Dar es Salaam, Tanzania – drafted and currently under design / Systematic literature review on the main drivers of risk and violence in urban areas and strategies to address the protection concerns of forcibly displaced populations – The review will result in a comprehensive summary of what is currently known about the drivers of and solutions to urban violence. / Desk review of existing approaches to strengthening public service delivery in the context of urban displacement – This review will produce a guidance note for humanitarian practitioners seeking to strengthen public service delivery channels.
Number of Regional Practitioner Workshops delivered independently or jointly with IIED on how urban contexts are impacted by crises and to promote exchange of knowledge on how to programme effectively in urban areas.	By December 2015: / 1 Regional Practitioner Workshop delivered by IRC in collaboration with IIED. / By December 2016: / 3 Regional Practitioner Workshops delivered by IRC or jointly with IIED.	The Programme delivered jointly with IIED the following Practitioners’ Workshops: / ‘Meeting needs in a context of protracted urban displacement in the Middle East and North Africa’ (September 2015) / ‘Meeting needs in a context of protracted urban displacement in the Horn and East Africa’ (May 2016) / IRC and IIED are organising the third workshop in Bangkok in November 2016. This workshop will focus on Asian countries, particularly the IRC country offices of Pakistan, Afghanistan, Thailand, and Myanmar and IIED’s partner organisations in Bangladesh.

Key Points

The team is currently finalising 4 products on urban emergency responses in Lesbos, the right to the city of urban refugees in Dar es Salaam, the drivers of and solutions to urban violence, and guidance on strengthening public service delivery channels, respectively. All products are in progress and scheduled to be released by December 2016.

Drawing on lessons from the Practitioners’ Workshop in Istanbul (September 2015), the second Workshop was organised in collaboration with IIED and delivered in Nairobi in May 2016. It focused on meeting public service needs in protracted urban displacement in the Horn and East Africa, and it included over 40 participants from 17 organisations representing practitioners.

Based on the success of the Practitioners’ Workshops in Istanbul and Nairobi, the IRC will deliver a third workshop in Bangkok focusing on Asian countries hosting urban refugees in November 2016. This workshop will include representation from Afghanistan, Pakistan, Burma, Japan, Thailand, the Philippines, and Bangladesh.

IRC has established itself as a thought leader in urban humanitarian response and is well integrated into the international discourse around the topic. The Learning Manager contributed to the report on the Nexus of Urbanization, Violence, and Conflict. With World Vision, and supported by the Active Learning Network for Accountability and Performance in Humanitarian Action (ALNAP), he co-hosted a Urban Thinkers Campus and co-authored the resulting report on resilience for the World Urban Campaign in the lead up to Habitat III. The Learning Manager supported the design of the agenda, delivered a session and participated in a peer-to-peer municipal learning workshop in Amman as well as a Summit on Integrated Development.

Summary of responses to issues raised in previous annual reviews (where relevant)

The main recommendation from last year was around ensuring synergy and complementarity with IIED in the coordination of practitioner workshops as well as drafting and dissemination of knowledge products. IRC and IIED have strengthened their collaboration over the reporting period. IRC ensure that IIED is invited to IRC events and meetings and has the opportunity to input to IRC knowledge products. IIED has offered their online presence and visibility to disseminate common messages. All three Urban Practitioners’ Workshops were co-hosted or plan to be co-hosted by IRC and IIED, and IIED worked together with UCLG and IMPACT to organise a side-event at WHS focusing on the role of municipalities in urban displacement crises. Additionally, IIED has peer reviewed IRC publications generated through the partnership, and vice versa.
The second recommendation was related to the need to fully utilise IRC’s presence in Europe to capitalise on European donors and multi-agencies interest on urban areas and protracted displacement. To address this concern IRC has redoubled efforts in Europe and co-organised several events, including in Barcelona, the Netherlands and Geneva. IRC are working in close synergy with their Brussels and newly opened Berlin office to agree on common messages to be disseminated at a national level with local stakeholders. The sustained engagement with Belgium-based actors has led ECHO to invite IRC to submit a concept for additional funds for the Enhanced Response Capacity opportunity as a follow up from the WHS.

Recommendations

IRC should ensure that its knowledge products have a clear aim and are not duplicating existing guidance. It is also important to mitigate the potential bias of evaluators by using rigorous evidence-based analyses as much as possible. Lessons learnt briefs based on evaluators’ perception may not be considered by other actors as a reliable knowledge base and thereby only have limited influence.

By the end of the project period, IRC should ensure it has reliable and objective methods of measuring the progress of outcome indicator 1 against the final target (especially “50% of Group A stakeholders demonstrate a change in policy and/or practice to reflect the urban context”).

Collaboration with many different actors, from international and national peer organisations, to non-humanitarian NGOs, to municipal governments should continue to be pursued.

Output Title	Effective practices documented, tools generated and innovative operational working methods developed by the learning consortium
Output number per LF		IIED 1	Output Score	A
Risk:		Moderate	Impact weighting (%):	20
Risk revised since last AR?		Yes, but only because of change in DFID’s grading system	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones (by 31/12/2016)	Progress
Number of tools and knowledge products co-produced by more than one consortium partner	At least 3 tools and knowledge products produced (including research papers, briefing papers, advocacy notes, guidebooks) produced by consortium members	On track: Two desk reviews are currently in pre-production from the IRC-led partnership, on urban context analysis and needs assessment. Outputs including blogs and research papers are scheduled from the Habitat for Humanity-led consortium before the end of 2016.
Number of learning events jointly delivered by consortium partners.	At least 2 joint events held, one of which at the World Humanitarian Summit	IIED have focused on internally facing joint events with a focus on M&E. As outputs are only beginning to emerge, IIED will explore opportunities for webinars as a dissemination tool for these.

Key Points

Both Learning Partnerships are now up and running, and are beginning to demonstrate results. Despite some delays in recruitment, each is now being led by a dedicated coordinator who was specifically recruited for this role. The IRC-led partnership had a clearly-defined set of outputs from the outset, consisting of a series of desk reviews, piloting of tools and writing of guidance notes, each led by a different member of the consortium. These activities are underway with the first desk reviews in the process of being copy-edited. IIED have been working closely with IRC on their DFID-funded stream of work, for example organising and participating in joint workshops.

The Habitat for Humanity partnership began with the intention that the outputs and thematic focus areas would emerge through discussions with the country partners involved. The partnership coordinator has made a push to define the activities and thematic focus areas at country level, and ‘accountability to affected populations’ will be the central theme. While progress in this consortium has initially been slower, required strategic and staff support time will be put in to ensure that the consortium achieves its intended outcomes, including actively engaging with the consortium’s review and planning meeting in October.

IIED have involved both partnerships in internal monitoring and evaluation process, which sees the process of working with the partnership as a valuable opportunity to assess a) the ability of this programme of work to influence key actors in the humanitarian sector and feed this back in to activities during the life of the programme; and b) the effectiveness of the Learning Partnership approach as a model to create change in institutions and the sector more broadly. The monitoring and evaluation will apply the methodologies of process tracing and social network analysis. IIED have included representatives from the partnerships in a number of M&E workshops and these have been valuable opportunities to better understand the challenges and advantages of the consortium model, and have fostered a spirit of openness between the different consortium members.

Whilst the focus on joint events has so far been internal, with 6 monthly consortium meetings to catch up, plan activities and discuss M&E, IIED are exploring opportunities for events such as ALNAP webinars to disseminate the findings from the consortium activities. If IIED’s submission for a networking event at Habitat III is successful, they will explore ways of involving the consortium members as they are also part of the Global Alliance for Urban Crises.

Summary of responses to issues raised in previous annual reviews (where relevant)

Last year’s recommendation said that “IIED must take the necessary steps to ensure that the Learning Consortium is inaugurated on a positive note, and in the spirit of true collaboration. This may require further facilitation to ensure the members of the two mini-consortiums are maximising the synergies between their work and making the most of each other’s networks”

The recruitment of coordinators for each Learning Partnership by IRC and Habitat for Humanity respectively enabled a positive fresh start on this. Both coordinators have been very open to collaboration and communication with each other and with IIED, enabling a good working relationship across the board. IIED has arranged regular monthly catch ups with each contact point to stay up to date on activities and plans. The two coordinators have also been very engaged in the monitoring and evaluation process that IIED has initiated.

Recommendations

In next quarterly reports from IIED, DFID would welcome further details on the specific objectives and progress of both consortia (i.e. themes of literature reviews, tools being developed, etc.). Key partnership documents should be annexed.

As IRC is receiving DFID funds both directly and through IIED for work on urban crises, IIED and IRC need to ensure clarity in allocation of activities and outputs to one grant or the other and to report to DFID accordingly. Areas of potential overlap include the production of guidance notes and the organization of events.

Output Title	Innovative thematic and regional research produced through a learning fund and small scale research and documentation fund.
Output number per LF		IIED 2	Output Score	A
Risk:		Moderate	Impact weighting (%):	20
Risk revised since last AR?		Yes, but only because of change in DFID’s grading system	Impact weighting % revised since last AR?	NO

Indicator(s)	Milestones (by 31/12/2016)	Progress
Number of research grants allocated through the learning fund and the small-scale research fund	Second round of 15 research grants allocation	On track: The 3rd round of research grants is in the process of being selected. The first and second call led to six proposals being funded, the third call will fund a further five, totalling 17 research grants in total (see full list below). The fourth round is scheduled for allocation before the end of 2016. Five research grants are ongoing from the small-scale discretionary research fund (see list below).
Number of knowledge products produced from both funds and disseminated at events and through online downloads	10 knowledge products complete and 15 in progress; At least 2,000 total internet downloads and papers disseminated during at least 3 events	On track: From the calls for proposals, 3 working papers, 3 briefing papers and 1 short film have been produced or are in pre-production. It is expected that a further 3-5 papers to be ready by December. / Existing publications were disseminated at the IIED WHS side event, and will also be disseminated at Habitat III and the IRC-IIED workshop to be held in Bangkok in November 2016. / Total downloads: 2034 for the first 6 publications available online on the IIED website, (as at 30 August 2016) and a further 310 downloads from the ALNAP website (Cash and ABA review papers only).
Effective and relevant knowledge products are produced (including products with particular focus on needs of different groups and gender relations)	An assessment by SSG indicates that knowledge products are relevant and being accessed by appropriate stakeholders	This will form part of the agenda at the November 2016 SSG meeting. However, a fuller assessment may not be possible until more outputs emerge

Key Points

Summary of research grants made in call 1 and 2
Study title and region	Status
Call 1 – Local Collaboration
An assessment of collaboration between local and humanitarian actors in Colombia, South Sudan and the Philippines	Pre-production stage
Local government management and response to Syrian refugees transiting in Croatian border towns	Working paper published, Croatian version in production, two briefing papers in English and Croatian in production
La gestion humanitaire des inondations dans une commune de Niamey, Niger (Humanitarian management of floods in a district of Niamey)	Research ongoing
Typhoon Haiyan response in Tacloban, the Philippines	Film online; working paper in pre-production stage, briefing paper in pre-production
The collaboration mechanisms in addressing the Syrian refugee crisis in urban settings in Lebanon	Working paper and briefing paper published
Civilian Protection in Urban Sieges- capacities and practices of first responders: A cross-country analysis in Aleppo, Syria and Gaza, OPT	No-cost extension granted due to situation in Syria. Focus of research now on Syria due to difficulties getting government permission for research in Gaza.
Call 2 – Protection
Implications of humanitarian responses in the long-term: Case of Chennai	Ongoing
Idea Lab for Fostering Protection of Displaced Persons in Urban Areas of Northern Nigeria	Ongoing
Tackling gender based violence in Gaza	Ongoing
Hidden refugees in Egypt	Ongoing
Protecting IDPs in Mogadishu	Ongoing
Non-state forms of protection	Ongoing

Summary of discretionary research grants

Study title and region	Status
Review of area-based approaches	Complete – working paper
Review of cash transfers	Complete – working and briefing paper
For my son (film)	Complete – on HuffPo
Haiti Urban Response: Learning from Community Planning	First draft stage
Water programming in the MENA region	Ongoing
Empowerment outcomes of Urban Humanitarian Responses	Ongoing
Urban planning following humanitarian crises: Supporting local actors to take the lead	Field work in progress
Towards an inclusive urban reconstruction policy development process in Nepal	Field work in progress

IIED has now launched three of its planned four calls for proposals, each with a specific thematic focus which was agreed upon with the input of the Strategic Steering Group. The dissemination of these research calls has been through the ALNAP Urban Community of Practice mailing list, the IIED website and social media, as well as emails to individual contacts. There have been the following response rates:
- Call 1 – local collaboration: 52 proposals received
- Call 2 – protection: 148 proposals received
- Call 3 – local markets: 31 proposals received – (the lower number of proposals submitted may be due to the specificity of the topic).

The fourth call is scheduled for release in late September 2016 and the topic is likely to centre on the nexus between humanitarian response and development – as in each of the previous calls, the precise theme will be developed in association with the strategic steering group.

The latest cumulative download figures for Urban Crises publications on the IIED site are:
Humanitarian responses by local actors: Lessons learned from managing the transit of migrants and refugees through Croatia 12 (uploaded in late August 2016)

Making cash work for cities and towns affected by humanitarian crises (policy briefing) – 269

Annexes: A review of evidence of humanitarian cash transfer programming in urban areas - 141

A review of evidence of humanitarian cash transfer programming in urban areas – 553 (and 69 downloads on ALNAP)

Humanitarian response to urban crises: a review of area-based approaches – 680 (and 241 downloads on ALNAP)

Setting a new research agenda for urban crisis and humanitarian response - 379

Summary of responses to issues raised in previous annual reviews (where relevant)

The last review’s recommendation was: “Partners [IIED and IRC] should ensure complementarity between the knowledge and learning products that they are producing or commissioning, so as to minimise overlap in content or proposed audience”.

In order to avoid any duplication or overlap in research pieces, IIED is maintaining a table of geographical and thematic areas being covered by outputs 1 and 2. This also allows identification of possible complementarities across research activities and also to put in touch research teams working in similar areas or on similar topics. In selecting research proposals from the thematic calls, ensuring geographical representativeness is a criteria.

Recommendations

N/A

Output Title	Best practices disseminated, policy changes discussed and capacity of key actors built through learning events, networking, and effective project management.
Output number per LF		IIED 3	Output Score	A
Risk:		Moderate	Impact weighting (%):	10
Risk revised since last AR?		Yes, but only because of change in DFID’s grading system	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones (by 31/12/2016)	Progress
Number of different types of events organised (webinars, workshops) and number of participants attending the events, with feedback from participants indicating that they plan to make use of workshop content in their work	A further 2 events held including 1 at the World Humanitarian summit; at least 50 people with representation from different sectors attend events and indicate that contents will be used to inform their work.	On track: a joint side event was held at the WHS with IRC, United Cities and Local Governments (UCLG) and IMPACT Initiatives. / An application has been submitted for a Habitat III networking event under the umbrella of the Global Alliance for Urban Crises. / A joint IRC –IIED workshop will be held in November focusing on the Asia region.
Number of events at which research outputs shared	Research outputs shared in at least 3 events	Research outputs including the policy briefings were disseminated at the Nairobi workshop in May 2016 (organised by IRC), at the World Humanitarian Summit, and will be available at the IIED stall and on the IIED publications USB stick at Habitat III in Quito. Additionally, the latest publications will be disseminated at the Bangkok workshop hosted by IRC in November 2016.
Chances of reaching the most relevant people are maximised and information that is most useful to them is shared to them	SSG assessment indicates that relevant contacts are utilising knowledge products	This will be a topic for discussion at the next SSG meeting in November 2016.

Key Points

Following on from the successful joint workshop between IIED and IRC in Istanbul in September 2015, both organisations have endeavoured to include each other in planned events. IIED attended and contributed to the IRC practitioners’ workshop in Kenya in May 2016 (see blog), and similarly IIED will jointly organise with IRC the practitioners’ workshop in Bangkok in November 2016, focusing on the Asia region.

IIED and IRC submitted a joint event proposal for the World Humanitarian Summit, on ‘Integrating Development and Humanitarian Programming in Urban Areas: lessons from local governments and civil society’. The organisers requested that this event be merged with one proposed by IMPACT Initiatives and UCLG, which became a session entitled ‘Perspectives from cities in crisis – the role of local actors’. IIED sponsored the attendance of two civil society representatives from Nepal and Lebanon to act as panellists, alongside city representatives sponsored by UCLG. The session focused on the role of local actors in urban humanitarian response and the possibilities for collaboration with humanitarian agencies. The event was well-attended and kicked off the urban thread of the WHS and was written up as an IIED blog.

IIED has submitted an application for a networking event at HABITAT III in Quito, and is waiting to hear the outcome. The proposed event would be under the umbrella of the Global Alliance for Urban Crises and would enable participation for a number of member organisations. The proposed session focuses on the role that the Global Alliance for Urban Crises can play, as a collaborative multi-stakeholder network of urban and humanitarian practitioners, researchers, and local authority networks, in achieving the commitments of the New Urban Agenda. If approved, this would be an important opportunity to highlight the importance of including consideration of humanitarian action in the urban development, governance and resilience discourse. If the event is not accepted in the formal programme IIED will develop alternative ways of ensuring programme outputs and findings are shared and discussed at the conference.

In terms of dissemination of outputs, IIED will use the planned events above to distribute paper and/or USB copies of the publications produced under this initiative (all publications are included in the IIED Human Settlements USB stick which contains all IIED publications and is updated regularly). IIED are also listed on ALNAP’s Directory (see below).

IIED’s in-house communications team is also exploring opportunities to further disseminate research findings and outputs to a broader audience, including with IRIN. In addition, IIED have taken advantage of key events such as World Humanitarian Day to launch relevant blogs and new publications, while also highlighting these on social media.

Summary of responses to issues raised in previous annual reviews (where relevant)

The previous review recommended that “Partners [IIED and IRC] should ensure a joint web presence that provides details of the Urban Crises Programme as a whole, and provides a platform for outputs from both partners.”

IIED and IRC now have an entry on the ALNAP Directory of Emerging Urban Learning which provides a summary of the initiative as well as links to the latest publications. IIED also has a project-specific website on the IIED site which provides details of the IIED Urban Crises Learning Fund and will also update with the latest publications and blogs.

Recommendations

IRC’s DFID-funded Advocacy and Learning program is currently due to end on 31 December 2016 while the IIED research program will continue through 2017. DFID should consider IRC’s request for a time and cost extension which would bring the IRC project end date in line with IIED’s. An extension should also enable the Global Alliance to be firmly consolidated and institutionalised and ensure its sustainability post 2017. Should this not be approved, IIED and IRC should plan for the earlier conclusion of the IRC grant and ensure that the knowledge generated by the IIED program in 2017 continues to be disseminated and appropriately highlighted to practitioners.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance
As with last year the cost drivers for the IRC element of the project remain predominantly as staffing, travel, events and publications. Almost all IIED costs have been staff, grants (including bank charges) and travel (including meetings). Production costs for outputs have been small to date, as outputs from first round of call for proposals are only just being published, plus a few from discretionary funding.

VfM performance compared to the original VfM proposition in the business case
The original business case notes that IRC has strong internal policies and procedures to monitor and manage delivery and financial risks, most notably fraud, bribery and corruption.
During 2016 the IRC has set up a new Ethics and Compliance Unit and revised the reporting procedures around Fraud, Bribery and Corruption Policy. This was presented to DFID’s Counter Fraud Unit in June 2016. Throughout the same period IRC has had a Commercial Expertise Review around procurement.

The original business case notes that each bid to IIED will be assessed on value for money by the IIED internal fund management board /strategic steering group. This was established at the start of the initiative, consisting of non-IIED humanitarian experts (including DFID staff). The process for assessing proposals is to do an overall shortlist with reserve options, based on criteria specified in the call document. The steering committee’s advice is then taken regarding the selection. Financial considerations include looking at budgets in terms of rate of proportion of staff costs from total and specifically at day rate and number of days, levels of travel costs, amount and justification for any institutional overhead, minimising any miscellaneous or contingency budget lines, and checking overall for a realistic estimate of costs to complete the work intended.

Assessment of whether the programme continues to represent value for money
IRC confirm that all flights and hotels have been booked at charity fares, and have allowed significant savings on flight costs needed to join panels or global events. IRC has also taken advantages of other organisations funding some of the costs needed to deliver the Programme.

The project is meeting expected outputs with the relatively small financial investment. Project outcomes are being contributed to as expected.

Working in close collaboration with IRC’s Units for Governance; Equality, Recovery and Diversity; Protection; Research, Learning and Evaluation; Policy and Advocacy has helped IRC identify the specific needs of the most vulnerable people amongst the Urban Displacement communities, contributing to the project’s equity.

As outlined above IIED follow a competitive process of selecting research proposals. IIED are on track to meet planned deliverables and their dissemination strategy is intended to ensure a broad reach for project outputs.

Quality of financial management
IRC and IIED project finances are being well managed with minimal variance between expected and actual spend. Quarterly financial and narrative reports are provided within good timeframes with any delays being explained and communicated in advance. The process that IIED use to manage budgets, noted above, is helping to manage costs.

IRC Date of last narrative financial report	28 July 2016
IRC Date of last audited annual statement	US FY ending on 30 September 2015
IIED Date of last narrative financial report	August 2016
IIED Date of last audited annual statement	July 2016

E: RISK (½ page)

Overall risk rating: Minor/Moderate/Major/Severe

The previous risk rating medium. Following DFID’s introduction of a four tier risk rating, we judge that the risk rating should be Moderate.

Overview of programme risk

Medium/ Moderate remains the right risk rating. The Programme has been able to establish an effective working relationship with UN Habitat, DFID, ECHO and the wider Humanitarian system that has led to the launch of the Global Alliance for Urban Crises in May 2016 at the World Humanitarian Summit in Istanbul. Thanks to the systematic work of active engagement and participatory inclusion, 70 agencies have already signed up to the Alliance.

A lack of traction in the donor and humanitarian environment remains a residual risk to the Programme.

DFID has a seconded member of staff working for IRC on this programme. While this is achieving great opportunities for closer working between donor and NGO networks on urban issues. This does present a risk of conflict of interest which are being manged, for example through using a separate DFID advisor to review the project and decision making.

This programme of work depends on a considerable amount of pass-through from IIED to other organisations in the Learning Partnership and carrying out research studies through the thematic calls for proposals and discretionary fund. This gives an opportunity to direct support to researchers and organisations who may otherwise find it challenging to secure funds for research on this area, which also means accepting that some grantees may require higher levels of support than others. There is a degree of risk in that some of the contracted researchers/research organisations are unfamiliar to IIED, but IIED have systems in place to manage this.

Outstanding actions from risk assessment

There are no outstanding actions. IRC will continue to work on maintaining traction on urban issues in the donor and humanitarian environment through this project.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

The project is delivering well against the planned timeframe and log frame. As highlighted above, IRC have requested a cost and time extension to bring their grant element of the programme in line with the IIED timeline.

Performance of partnership (s)

The secondment of a DFID member of staff to IRC has allowed for strong collaborative approach, ensuring that relevant parts of both organisations are working well together on urban issues.

IIED and IRC have demonstrated increased closer working throughout the reporting period, as highlighted in the above narrative.

Asset monitoring and control

There are no assets associated with this project.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

N/A

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

The assumptions in the business case theory of change and the IIED/IRC joint theory of change still hold. The main change since the start of the programme is the creation of the Global Alliance for Urban Crises, which has the potential to act as a conduit for channelling the knowledge generated to the ground, through changes in the approaches and policies of the organisations involved, and to act as a mouthpiece for all organisations seeking more effective approaches to urban humanitarian response.

A monitoring and evaluation process has started to be implemented with a focus on the Learning Partnership, with the intention of using the findings to implement any necessary changes in the project’s approaches and ways of working. The M&E focus is twofold: looking at the influence of the learning partnership on the ways of working of humanitarian actors in urban contexts (i.e. effectiveness) and what the implications are for the ways of working for IIED in managing a consortium model. The M&E process will use both social network analysis and process tracing, and will involve the participation of actors in the two Learning Partnerships.

Monitoring progress throughout the review period

This annual review was conducted by DFID’s project team consisting of the Senior Responsible Officer, Programme Manager and lead advisor. IRC and IIED provided written assessments, which were used alongside quarterly reports and face to face meetings with both organisations.

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. The Aid Management Platform (AMP) and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
A: Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Output Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on AMP as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Minor/Moderate/Major/Severe / Enter: Minor, Moderate, Major or Severe / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on AMP as part of loading the Annual Review for approval). / Where the Risk for this Output has been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section E Risk
Key points
Summary of response to programme issues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D: Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of financial management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E: Risk
Overall Risk Rating: Minor/Moderate/Major/Severe / Enter Minor, Moderate, Major or Severe, taken from the overall Output risk score entered in AMP
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Detail the key risks that affect the successful delivery of the expected results and mitigating actions. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix etc. / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process