Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: South African Partnership for Effective Development Co-operation (SAPEDC)
Programme Value: £5,000,000		Review Date: September 2015
Programme Code: 203622	Start Date: August 2012	End Date: March 2016

Summary of Programme Performance
Year	2013	2014	2015
Programme Score	A	A	A
Risk Rating	Medium	Medium	Medium

Summary of progress and lessons learnt since last review
The South African Partnership for Effective Development Co-operation (SAPEDC) programme has continued to make solid progress over the past 12 months, with good results from the majority of the ten components. Positive relationships have been developed with the Parliamentary Committee for International Relations and Co-operation, and a number of sub-projects have brokered new relationships with other Africa governments. Support given to civil society organisations resulted in significant African youth engagement in the negotiations on the post-2015 development agenda.

Unfortunately there has been little progress in establishing the South African Development Partnerships Agency (SADPA). Work with other parts of government (in South Africa and the region) has also suffered delays, largely due to reasons outside of implementing partners control. In addition some projects started implementation later than originally planned, due to lengthy start up arrangements between DFID Southern Africa (DFIDSA) and project partners.

The benefits of SAPEDC’s flexible funding mechanism were highlighted through DFID’s ability to provide swift support to the South African Department of Health’s Ebola response in Sierra Leone (through the World Health Organisation (WHO)). However, SAPEDC remains an intensive programme to manage given the high number of components.

A significant underspend is forecast. This is partly due to the lack of progress on SADPA, which has reduced planned spending against one of the three outputs, as well as the significant weakening of the South African Rand against the British Pound over the programme period.

Summary of recommendations for the next year
As SAPEDC will end in March 2016 this review makes a limited number of recommendations. Instead it encourages learning lessons from this experience in advance of designing any future programme. In particular, engagement going forward should consider the likely role SADPA will play in the UK’s development partnership with South Africa and the cost effectiveness of the current model, particularly given limited staff resources. Key recommendations are as follows:

Conduct a robust assessment of Value for Money (VfM) during the project completion review (PCR), using the indicators now devised for this programme.
- Ensure project partners are fully aware of, and compliant with, the Gender Act.
- Prioritise increasing the qualitative monitoring of publications and training events delivered by project partners.
- Strengthen the strategic role played by the SAPEDC Steering Committee including in planning for any follow on programmes to SAPEDC.
- Tighten up forecasting and reflect realistic plans and budgets for components which are largely delivering influence and policy
- Revisit the logframe to ensure:
(i) Milestones remain realistic (particularly given the delays to the formalisation of SADPA)
(ii) Sources are up-to-date.
A. Introduction and Context

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-203622/documents
DevTracker Link to Log frame:	http://devtracker.dfid.gov.uk/projects/GB-1-203622/documents

Outline of the programme
The SAPEDC is a £5,000,000 programme running from August 2012 to March 2016, funded under DFIDSA’s Global Development Partnerships Programme (GDPP). SAPEDC is designed to increase the transformational impact of South Africa (SA)’s development co-operation on poverty, under-development and marginalisation in Africa, as well as its contribution to national and global debates on development.

SA’s role as a development actor continues to grow. It is Africa’s most diversified, developed and, until recently, largest economy. SA drives economic growth and jobs, strengthens tax and customs administrations and actively supports conflict mediation and peacebuilding work across the continent. Its public institutions of budget management, revenue collection, public service planning and performance management, and statistical analysis are models for many of its neighbours. SA’s private sector has a presence across Africa and its infrastructure investment is driven by a range of public-private partnerships. SA’s civil society is engaged across the region on issues of transparency, pro-poor policy advocacy, peace and security, health reform, and most recently the post-2015 development agenda. SA academia plays a leading role, notably in driving developmental research.

SA occupies a unique position in international development debates. It is the sole African representative of the G20, a member of the BRICS and current Chair of the G77 and Open Government Partnership (OGP). SA was a pivotal voice throughout the post-2015 negotiations within Africa, the G77 and at the UN. SA’s powerful platform enables it to exert influence on the delivery of the sustainable development goals, and shapes the international systems that will enable their implementation.

This programme contributes to SA’s regional and global development role by working with SA partners to put in place the institutions, skills and knowledge required to implement successful development programmes and policies. SAPEDC initially focused partly on supporting the establishment of SADPA, with the hope of it resulting in a more formal and coherent approach to sharing SA’s expertise and in helping to address regional issues. However, the continuing delays in establishing the Agency means it has not fulfilled this role to date. Instead, over the last 12 months, the programme has shifted to focus on strengthening engagement with the Parliamentary Committee on International Relations and Co-operation in the areas of development diplomacy and oversight, following a direct request for support.

An indirect, but significant result of the programme is intended to be a strengthened development partnership between the UK and SA. This collaboration is expected to increase the results both countries can achieve on development policies and programmes in future.

The overall impact is that SA regional development assistance and global policy influence have a transformational impact on poverty in Africa.

The programme outcome is that SA regional development interventions are selected, designed and managed for maximum results for poor men and women, in line with international best practice.

The programme outputs are:
UK expertise and funding make a significant contribution to the SA Parliament’s oversight of Government development and peacebuilding approaches, and the establishment of the SADPA.

SA-UK programmatic partnerships in Africa result in sharing and improving expertise on approaches to development co-operation on both sides.

SA civil society, academia and think tanks increasingly able to contribute to and constructively shape national and international debate on development issues.
## B: PERFORMANCE AND CONCLUSIONS

Annual outcome assessment

Outcome	South African regional development interventions are selected, designed and managed for maximum results for poor men and women, in line with international best practice.

Indicators	Milestone – September 2015	Progress
Status of progress towards establishment of the South African Development Co-operation Agency as a functional organisation.	Timetable for SADPA bill to Parliament announced	In April 2015 the Minister for International Relations and Co-operation announced plans for the establishment of SADPA in her budgetary address to Parliament. However, no further progress has been made in formalising the Agency and no Bill timetable has been announced.
Number of South African development cooperation initiatives achieving results in other countries with UK support through this programme.	5 (Oct 2014 – Sep 2015)	Five programmes operated in other countries across Africa over the past year. Three are very much in their infancy but all are demonstrating results. / In addition, research and briefing papers developed under SAPEDC components are disseminated across Africa, enhancing knowledge of numerous development policy areas.
Extent to which SAPEDC partners include gender disaggregation within their quarterly reporting.	New guidance for gender disaggregation provided to SAPEDC partners	Gender guidance was not issued to project partners in this reporting year and remains under development. By the end of 2015 DFIDSA plans to issue guidance and hold a training session on the implications of the Gender Act for all project partners.

This past year has seen the establishment of positive relationships with the Parliamentary Committee on International Relations and Co-operation, and good progress on five initiatives delivering results in other African countries. However, given the continuing delays it is highly unlikely that the SADPA Bill will have been approved by Parliament by March 2016.

Overall output score and description
SAPEDC has made good progress against each of the three outputs – meeting milestones for outputs one and two, and exceeding expectations against output three. Taking weightings into account, the overall output score is assessed as an ‘A’.

While output one now focuses on engagement with the Parliamentary Committee on International Relations and Cooperation, it is hoped that by maintaining a focus on development policy momentum behind establishing SADPA may be reinvigorated – enabling some progress before the end of SAPEDC. However, some of project partners have also experienced difficulties in securing DIRCO's engagement in ongoing areas of work.

Three of the five projects under output two – Support to Transitional Justice, Advancing the Transparency and Accountability Agenda through the OGP and Strengthening Customs Systems in East and Southern Africa (Phase 2) – have only recently begun. Subsequently progress is not as advanced as originally planned. However, each project partner has quickly developed relationships with key stakeholders and is working to deliver project outputs by March 2016.

SAPEDC’s strongest performance has been against the third output. This has seen significant engagement by civil society organisations in the post-2015 development agenda, both nationally and internationally. The role played by youth leaders in both the Voice for Africa (Phase 2) and Building Bridges projects has been particularly impressive. Networks established through these projects will outlive them and opportunities given to the youth representatives have already changed the course of their lives. For example, youth representatives with African Monitor were addressing Parliament the day after meeting with the review team in Cape Town.

Key lessons
Project monitoring (progress, financial and risk) was significantly improved following recommendations in the 2014 annual review. However output milestones are largely focused on the number of papers/ events delivered. Monitoring the quality of these interventions would better help assess their impact. Ensuring feedback forms are completed after each event or adding a rating button to product pages, or counting webpage hits may be a simple way to quickly gauge reactions to products.

SAPEDC is brokering new project partners for DFID. Unfortunately a number of these have seen lengthy start-up negotiations, highlighting the difficulties in entering agreements with organisations new to DFID. Smaller organisations commented that they were not set up to meet DFID’s rigorous financial requirements. These partners have urged DFID to be clearer about requirements and expected timeframes from the outset.

Whilst the SAPEDC model has provided a high degree of flexibility and enabled a number of effective pilot projects, the high number of accountable grants means that the management burden on the GDPP in SA remains high. This is unlikely to be a cost effective model going forward. However, it will be important to maintain these close institutional links with South Africa partners in any future model.

Key actions
As highlighted in the summary sheet, the GDPP team should ensure lessons are learnt from this experience in any future programme. This should carefully consider the distinction between overall objectives for DFID’s engagement with Emerging Powers and regional programming priorities, to ensure DFID builds on the success of SAPEDC.

Has the logframe been updated since the last review?
Yes. The logframe was revised in June 2015 to reflect recommendations from the 2014 annual review.

Given the limited time remaining to deliver the programme, no significant changes to the logframe are recommended. However, targets should be reviewed to ensure they are realistic, particularly relating to the establishment of SAPDA, and indicator sources should be revisited before work on the Project Completion Report begins.

## C: DETAILED OUTPUT SCORING

Output Title	UK expertise and funding make a significant contribution to the South African Parliament’s oversight of Government development and peacebuilding approaches and the establishment of the South African Development and Co-operation Agency (SADPA)
Output number per LF		1	Output Score	A
Risk:		Medium	Impact weighting (%):	10
Risk revised since last AR?		No	Impact weighting % revised since last AR?	Yes

Indicator(s)	Milestones	Progress
1.1 Number of briefings and training events provided for the Parliamentary Committee for International Relations and Co-operation.	2 (Oct 2014 – Sept 2015)	IGD hosted a workshop on SA’s draft White Paper on International Relations and Cooperation on 5 November 2014. A summary of these discussions were published on the Parliamentary Monitoring website. In addition, a short report was produced and disseminated to the Committees’ Content Adviser in order to aid discussions with DIRCO on the White Paper. / IGD have also provided inputs to the Committee in advance of discussions on the Annual African Renaissance Fund Report in mid-October 2015.

Key Points
As a result of limited progress on the establishment of SADPA, the 2014 Annual Review concluded that the focus of this output should be on increasing engagement with Parliament and the Parliamentary Committee for International Relations and Co-operation in particular. A no-cost extension was granted to the Institute for Global Dialogue (IGD) in March 2015 to do this work.

Both the Committee Content Adviser and IGD noted the positive relationship established between the two parties. There is a clear demand from the Committee for IGD’s expertise. The products produced have been well received, increasing the Committee’s engagement in discussions with DIRCO. However, a number of planned sessions have been delayed. The nature of Parliamentary business – with, for example only four oversight periods per year; the fluidity of the parliamentary timetable; and, a focus on constituency issues – means it is difficult to agree the timing of interventions.

Summary of responses to issues raised in previous annual reviews
- The SADPA position in DIRCO remains unfilled over the past year and DFID have not received any direct calls to support the establishment of SAPDA. However, DFIDSA continues to engage with DIRCO and stands ready to provide support, if requested.
- Indicators and milestones were reviewed and amended following the 2014 annual review. However, given the continuing delays in establishing SADPA, it is unlikely that the final outcome level milestone will be met by the programme’s end in March 2016.

Recommendations
- Consider qualitative assessments of papers/ training sessions provided by IGD – at present there is no formal system for measuring the impact of either research papers or briefing sessions.
- Revisit the target indicator for this output to ensure it is realistic, given the challenges around holding training events with the parliamentary committee.

Output Title	South African-UK programmatic partnerships in Africa result in sharing and improving expertise on approaches to development cooperation on both sides.
Output number per LF		2	Output Score	A
Risk:		Medium	Impact weighting (%):	50%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	Yes

Indicator(s)	Milestones	Progress
2.1 Contribution of UK-South African partnerships to enhance regional trade and investment in extractives industry.	Case study evidence demonstrates increased national capacities in customs procedures and improved regional coordination on customs reform in at least three countries. The geological survey capacity of key extractives industries is assessed in at least two countries.	Work on strengthening customs systems in East and Southern Africa only began in September 2015 following lengthy start-up negotiations, resulting in only two activities being delivered to date. / The South African Council for Geoscience has carried out scoping studies in order to identify how to strengthen the capacity of the Geological Survey Departments in Malawi and Zambia.
2.2 Contribution of UK-South African partnerships to global health challenges and national health sector policies in other African countries.	Case study evidence demonstrates improved health sector performance as a result of South African assistance in at least one other country.	DFID’s support to South Africa’s Ebola Response (through the WHO) resulted in a stronger response to the disease in Sierra Leone.
2.3 Contribution of UK-South African partnerships to building more open and effective governance institutions and more peaceful societies in and between African countries.	At least two UK-supported, SA-led regional networks of expertise in place on issues of governance, open institutions and peacebuilding.	Work on the ‘Support to Transitional Justice in Africa’ and / ‘Advancing the transparency and accountability agenda through the OGP’ has been slow to commence. Consequently progress is not as advanced as envisaged. However, both programmes are underway and developing regional networks.

Key Points
This output has made positive progress in a number of areas, again demonstrating the regional benefits of effective development partnerships with SA. The flexible nature of SAPEDC allowed DFID to quickly release funds to support SA’s response to the Ebola crisis in West Africa. This delivered a laboratory in Freetown that carried out 25% of all Ebola diagnosis in Sierra Leone during ther period of their support. Malawi and Zambia positively engaged with the Council for Geo-Science (CGS)’s geological mapping and capacity survey work, and both governments appear enthusiastic for further capacity building support.

Other collaborations with the Institute for Justice and Reconciliation (IJR) and the Open Democracy Advice Centre (ODAC) are at an early stage but are showing promise of delivering effective results in support of transitional justice and the OGP in Africa respectively. In some cases, delays resulted from DFID’s due diligence process, where small organisations upscaled their capability significantly in order to meet financial management and reporting requirements, given they had managed only very small budgets in the past.

Summary of responses to issues raised in previous annual reviews
As recommended in the last review, DFIDSA undertook scoping work on potential collaboration with the SA private sector in the region. This remains ongoing to identify interventions which will effectively enhance its developmental impact.

Recommendations
DFIDSA should ensure that any future programmes retain the flexibility to respond to emerging priorities, whilst avoiding the existing management burden of the current programme.

Output Title	South African civil society, academia and think tanks increasingly able to contribute to and constructively shape national and international debate on development issues.
Output number per LF		3	Output Score	A+
Risk:		Low	Impact weighting (%):	40%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	Yes

Indicator(s)	Milestones	Progress
3.1 Number of UK-funded South African civil society-produced papers or events on South African bilateral and trilateral development policies.	10 (Oct 2014 – Sep 2015)	Over 10 papers/ events have been produced by ISS and IGD. These range from “SA’s Engagement with the Private Sector in Post-conflict Reconstruction and Development” to “Trilateral Co-operation Beyond the Nation State”.
3.2 Number of UK-funded South African produced research papers or events on global/regional development policy issues including the post-2015 development agenda, financing for development (FFD) and regional integration.	10 (Oct 2014 – Sep 2015)	Over 10 papers/ events have been produced/ held in this reporting period. These include three high-level events hosted by the University of Cape Town on regional integration; numerous events on post-2015 and FFD held by SALO, African Monitor and IGD in SA and the region; and briefing papers on Structural Economic Transformation and Inclusive Growth by NEPAD, as well as policy briefs and blogs.
3.3 Level of involvement and influence of South African civil society organisations in support of priority issues on the post-2015 development agenda.	Input of South African civil society actors to UN processes recognised positively by DFID post-2015 team. African Monitor providing recognised regional leadership.	African Monitor provided an effective regional leadership role in the final stages of the post-2015 negotiations. The DFID post-2015 team commented that their work, alongside that of the Southern African Liaison Office (SALO), saw civil society constructively shape national and international debate on development issues.

Key Points
The Institute for Security Studies (ISS), the Institute for Global Dialogue (IGD), the University of Cape Town (UCT), NEPAD, African Monitor and the Southern African Liaison Office (SALO) have all actively engaged in the delivery of this output. They have produced high-quality research papers, policy briefs, blogs and events that have reached a wider audience than originally intended. For example, a number of papers produced by ISS have been shared by key UN organisations, including the Department for Peacekeeping Operations.
On the post-2015 agenda, African Monitor and SALO conducted extensive consultation on youth, LGBT and peace and security issues, in both SA and in the region, allowing them to engage directly with DIRCO and other African representatives. African Monitor’s role as secretariat of the African CSO Working Group gave it particular leverage, allowing it to meet with 21 African Ministers at national and regional events, and 11 African Member States at the UN level. However, there appears to have been some duplication of effort under the post-2015 work, with four organisations funded under SAPEDC to contribute to this output.

Summary of responses to issues raised in previous annual reviews
- Following a recommendation in the 2014 annual review, African Monitor and SALO have worked more closely together over the past year on the post-2015 development agenda. Monthly CSO meetings were held with the Government of SA and the civil society voice was amplified.
- Project partners have worked to ensure that products reflect the needs of target audiences. However, in order to maintain an independent voice, not all products have been directly requested.

Recommendations
Future programming should focus on the implementation of the Global Goals and Financing for Development agenda to build on the momentum achieved to date.
## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance
The key cost drivers remain those highlighted in the Business Case. These are primarily related to staffing costs (including advisory, research and policy work), travel costs, events and related expenses. Supplementary drivers include the cost of producing publications and training.

VfM performance compared to the original VfM proposition in the business case
In the business case, VfM was defined by effectiveness, efficiency and economy. As recommended in the last AR, DFIDSA developed a range of metrics to measure VfM at each of these levels.

SAPEDC’s economy was based on the scrutiny of partners’ budgets and processes during the approval process, to ensure consistency with DFID guidelines. Specific metrics identified include scrutiny of procurement policies (especially travel); the balance of delivery partners between NGO, public, and commercial suppliers; any savings achieved through multi-country working; and the delivery against agreed timeframes and budgets. On procurement, the policies of partners have continued to be scrutinised through due diligence processes, and have generally been found to be in line with DFID guidelines. No business class flights are known to have been taken, for example, and DFID’s per diem policy was also consistently applied. Partners’ budgets have been scrutinised prior to approval, with changes frequently required to ensure VfM. Regarding the balance of delivery partners, SAPEDC has used predominately NGO and thinktank/academia providers, as well as two international organisations (WCO and WHO) and one parastatal (CGS). Whilst this mix has been appropriate for the purpose of programme delivery, there has been no competitive tendering of projects. On the issue of multi-country projects, a number of projects (IJR, ODAC, WCO and CGS) have been implemented in several DFID priority countries, representing some administrative savings compared with delivering projects bilaterally. Finally, overall the delivery of project partners has been sufficient to meet the logframe’s outputs; however, a number have also required no-cost extensions to deliver their original workplans, suggesting that some implementers were too ambitious in their original timeframes.

Efficiency was measured by the programme’s ability to “respond flexibly to changing needs and to evidence on which components are performing well”. Additional metrics directed at the beneficiaries’ views were developed to ellicit the extent to which events and publications under SAPEDC met the needs of the relevant audience or ‘customer, although were not applied to all aspects of the programme,’. In terms of its flexibility, SAPEDC performed well, for example providing rapid support to SA’s Ebola response from October 2014. On relevance, the picture has been broadly positive. In the case of the post-2015 engagement projects, the attendance of DIRCO officials at events run by African Monitor and SALO is a good indication of their relevance. However, the lack of a clear interlocutor on SADPA meant that some partners struggled to gain traction with DIRCO on certain development themes, or to tailor products to their requirements. It should also be noted that the low management burden envisaged in the Business Case has not been realised. This is due to a number of factors including the high number of components within the programme, and the realities of a number of partner organisations having little previous experience of working with DFID and therefore being unfamiliar with our requirements.

The effectiveness of the programme was defined by the extent to which activities funded achieved the intended outputs and outcomes. Supplementary indicators focused on the vibrancy, connectivity and effectiveness of networks created, and the contribution of the activities to the development of SAPDA. At output level, activities have met the intended outputs. However, at outcome level, indicators have only been partially achieved. Whilst the target for the number of projects operating in Africa has been met, the dissemination of gender guidance to project partners was delayed to the next reporting year. In addition, as highlighted in the logframe’s assumptions, SAPEDC was not able to influence the timetable on SAPDA in the absence of clear direction from Government. In terms of the networks developed, a number of these (IJR, ODAC and WCO/SARS) remain at an early stage of development. However, UCT’s young leaders’ programme and African Monitor’s work with Youth Monitors has clearly developed self-sustaining networks which have complemented and enhanced the other workstreams.

Assessment of whether the programme continues to represent value for money
Overall the picture on VfM looks positive. SAPEDC’s economy indicators appear to be broadly cost effective; it demonstrated good efficiency by flexibly responding to urgent programming requirements and consulting with many of its customers to develop tailored products; and its activities achieved all of its intended outputs and contributed to some of its outcomes, with some good initial signs of the self-sufficiency of its networks.

Key areas to strengthen VfM for the remainder of the programme cycle as well as any follow on programme include:
- A more competitive process to select project implementers
- Ensuring that the delivery plans of implementing partners are realistic in terms of their timeframes and budgets.
- Designing a more effective management system in any future programme, which retains the ability to design flexible projects whilst reducing the management burden on DFIDSA.
- Prioritising engagement with DIRCO on the future of SADPA, to inform the logframe targets and to ensure that any future programming is well tailored to supporting its development needs.
- Engaging with beneficiaries to gain regular feedback on outcomes and impact.

Quality of financial management
DFIDSA was audited by DFID’s Internal Audit Department (IAD) in March 2015. This audit commended DFIDSA’s overall approach to programme management. However, it noted that “the complex and high number of accountable grants in the portfolio of projects under the SAPEDC creates a particular programme management burden.” IAD observed a few issues relating to programme oversight, all of which have since been addressed by the team.

Narrative and financial reports are generally being submitted on time and to the required standard, although this requires significant and ongoing engagement by the GDPP team with project partners, particularly in the early stages of project implementation. One project partner highlighted an issue with a financial disbursement, where the incorrect amount of funds had been issued due to a currency fluctuation. However, they commended DFIDSA for quickly resolving the issue.

Date of last narrative financial report	Various. Last was October 2015
Date of last audited annual statement	Various. Last was October 2015

E: RISK

Overall risk rating: Medium

Overview of programme risk
The overall risk rating remains unchanged since the last programme review. The risks highlighted in the Business Case remain those most likely to affect delivery, with the risk of a “lack of commitment by the Government of SA” continuing to be particularly important to manage. Whilst the SA Government continues to work with DFID over a range of development areas, delays to the development of SADPA have made a number of project activities more challenging to deliver. In addition, in cases where Government counterparts have limited time or incentives to engage on a particular development theme, project partners can struggle to gain traction.

The 2014 annual review highlighted the risk of implementing partners being unable to fully spend their budgets within the agreed periods due to the SA Rand weakening against the British Pound. This continues to be a major concern for the majority of our partners and a challenge for DFIDSA’s financial oversight.

Outstanding actions from risk assessment
None. Individual risk matrices started to be developed for each programme, but the March 2015 audit deemed the process to be too onerous on partners. Instead, risks are flagged in quarterly reporting and discussed with DFID at regular meetings. Key risks are then escalated internally using DFIDSA’s risk management system.

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe
SAPEDC is currently forecasting a spend of £3,819,032 against the allocated budget of £5,000,000. The programme’s considerable under spend is due to a number of factors, the most significant of these being:
1. Planned activities to support the development of SADPA have not taken place.
2. The weakening of the SA Rand against the British Pound.
3. Start-up negotiations with partners taking longer than expected, causing the time period for project implementation to be reduced.

It is unlikely that SAPEDC will spend the £5,000,000 originally allocated As recommended, DFID and the implementing partners should pay more attention to accurate forecasting for the remainder of the programme. An overall lesson, which has come out of evidence on adaptive and networking approaches, is that engagement with partners and beneficiaries may not require a high value of spend. This, and the high transaction costs this poses for DFID, should be taken into account in any future programming

Performance of partnerships
On the whole our programme partners are performing well. Strong and effective relationships have been built with the range of implementing partners – in both Government and civil society. Partners working to deliver output three welcomed the quarterly meetings between DFID and themselves, identifying them as a positive opportunity to learn lessons from each other. A formal lesson-learning exercise across all partners should be considered as part of the plans for future programming.

The GDPP team works closely with partners to ensure consistency with DFID guidelines and provide oversight of project delivery. This continues to take considerable staff resource. However, DFIDSA’s transparent and collaborative approach to programme management was commended by all partners during the review.

Asset monitoring and control
The programme does not involve the purchase of significant assets. However, some components have involved the purchase of office equipment, particularly laptops. In response to a recommendation in the 2014 annual review, an asset management review was undertaken with our project partners and an asset register has been created. Procedures for the purchase, management and disposal of assets are set out in programme management guidance.
G: CONDITIONALITY

Update on partnership principles
The Partnership Principles (PPs) are not being used as part of the management or monitoring of this programme. South Africa’s Adherence to the PPs is assessed as follows:

A commitment to reducing poverty and achieving the Millennium Development Goals (MDGs)
Summary: South Africa’s progress on the Human Development Index is static. Progress against MDG targets in health and education is positive and progress against HIV related indicators impressive given the scale of the problem. Inequality, slower than expected economic growth, equitable access to public services are major challenges, but remain central to government planning and development strategies.

A commitment to respecting human rights and other international obligations
Summary: Domestic respect for international human rights instruments is delivered through South Africa’s constitution - widely recognised as one of the most progressive in the world, with robust independent accountability mechanisms and the inclusion of both civil and political rights and economic and social rights. The Constitutional Court and independent bodies like the office of the Public Protector have been able to enforce the provisions of the Constitution. The positive framework provides a strong enabling environment although there are still areas of concern in relation to human rights as reflected in responses to South Africa’s Universal Periodic Report to the Human Rights Council.[1]
[1] http://www.ohchr.org/EN/HRBodies/UPR/Pages/Highlights31May2012pm.aspx

Acommitment to strengthening financial management and accountability, and reducing the risk of funds being misused through weak administration or corruption
Summary: There have been many reported and prosecuted incidents of official corruption. South Africa was ranked at 72 of 177 countries in Transparency International’s 2013 Corruption Perceptions Index. Official corruption remains high on the political agenda; South Africa is a global leader on budget transparency with South Africa ranked second globally on the Open Budget Index. The EU and South Africa carried out a PEFA assessment in 2014 and South Africa was again given an ‘A’ rating for its overall public financial management capability.

A ommitment to strengthening domestic accountability
Summary: South Africa is a founding member of the ‘Open Government Partnership’ and its successful bid to become co-chair and then lead chair for the OGP demonstrates a commitment to increasing government accountability and transparency both in South Africa, in the region and globally. This partnership aims to bring together government and civil society to find innovative means to improve accountability despite some tensions between the two in recent years.

H: MONITORING & EVALUATION

Evidence and evaluation
The evidence set out in the Business Case and 2014 annual review continue to support the rationale for this programme. Over the last 12 months, SA’s leading roles in the G20, G77 and as Chair of the OGP have reinforced its significance in shaping development issues on the international stage. Its leading role in the post-2015 development agenda (notably as chair of the G77) means it is likely to continue to be a key player in delivering the Global Goals and in shaping the international systems that will facilitate their implementation. Work undertaken through DFIDSA’s bilateral aid review in 2015 have also underlined the importance of SA as a regional development actor, due to its significant influence on inclusive economic growth in Africa.

Monitoring progress throughout the review period
This annual review was led by a member of the Emerging Powers Team in DFID’s Global Partnerships Department, with support from the GDPP team in DFIDSA. Consultations were held with nine of the eleven implementing partners in Pretoria and Cape Town, as well as a phone interview with the WCO. DFID and HMG staff from SA, Addis Ababa and London were also consulted during the review. The review was quality assured by the DFIDSA Deputy Head and SRO for the SAPEDC programme.

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessment
Key points
Summary of response to programme issues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Output Risk Rating: L/M/H / Enter Low, Medium or High, taken from the overall Output risk score calculated in ARIES
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Review the key risks that affect the successful delivery of the expected results. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process