Type of Review: Annual Review
Project Title: DFID Tanzania
Tanzania Climate Change Institutional Strengthening Programme (TCCISP)
Date started:	April 2011	Date review undertaken: June 2014
## Introduction and Context
What support is the UK providing?
This programme seeks to support the United Republic of Tanzania incl. Zanzibar build the necessary core institutional capacity to respond to climate change. The UK is providing £2.8 million over 4 years from April 2011 to June 2015. This was intended to fund: / a climate change programme adviser, and / a flexible technical assistance fund, to support to institutional strengthening on climate change in Tanzania. / The programme seeks to complement other climate change work currently funded by DFID Tanzania that provides support to civil society and the private sector. / The 2013 mid term review identified the need to increase the programme budget to cover expanding commitments and demands. In December 2013 an additional £800,000 was approved through a cost extension submission, bringing the total budget from £2 million to £2.8 million in flexible funding for technical assistance and programme activities.

What are the expected results?
The expected outcome is that Tanzania is able to access climate finance and use it effectively to support climate change resilience and low carbon sustainable growth. The targets to be achieved by end of project (2015) are that Tanzania has secured $300 million in climate finance (increased from original business case target of $250m) and that at least 50% of Government and Development Partner spending on climate change is in line with the National Climate Change Strategy. / To achieve this outcome, the business case includes the following changes that DFID support is expected to contribute to: / Tanzania has a comprehensive National Climate Change strategy both for URT and Zanzibar. / Tanzania also has a strong policy and institutional framework to plan, budget and deliver for effective use of the climate finance at a national, sector and local level. / Establishment and implementation of an effective national level policy and financing framework with climate change mainstreamed into key sector policies and annual budgeting processes. / Delivery models for climate financing and planning piloted in at least 3 villages/districts by 2015, to enable them to effectively plan and budget for climate change. / Increased number of people, who are better able to cope with the adverse effects of climate change. (Indirect 500,000 people by 2015) / Ministry of Finance and key sector Ministries are engaged and active on the climate change agenda. / Climate Change plans developed in key sector ministries and for key sector investments (such as “green growth” strategy for the Southern Agricultural Growth Corridor for Tanzania and Agriculture Climate Action plan). / 50% of climate change funds in support of National and Zanzibar climate change strategies. International climate finance secured reaches target of USD300m by 2015. / Strengthened data and evidence base for decision-making on climate change spend.

What is the context in which UK support is provided?
Tanzania’s population of 43 million (2012) is expected to rise to 75 million by 2030 and 110 million by 2050. 80% depend on agriculture for (at least some of) their livelihoods. It is estimated that more than 95% of Tanzanians live on less than US$2 a day. The proportion of the total population living in towns or cities will rise from its current 26% to 50% by 2050. / The country aims to achieve a GDP growth rate of 8-10% per annum. Actual rates of growth have been lower (5-6%) over the last decade. During the same period, the percentage of people living below the national poverty line decreased by a modest 5%, from 39% to 34%. / Temperatures are projected to rise by 1 to 3 degrees by 2050, increasing further to between 2.1 to 5.2 degrees by 2100. The economy is not adequately adapted to cope with existing climate risks. Extreme climate events already cause major socio-economic impacts and reduce economic growth. A drought in 2005/6 cost at least 1% of GDP. By 2030, the net economic costs of climate change may reduce GDP by at least 1.5% per year. / The Government plans to transform the country from a predominantly agricultural economy with low productivity to a diversified and semi-industrialised economy with a modern rural sector and high productivity. Future prosperity is being closely linked to un-exploited reserves of hydrocarbons, rare earths and other metals and minerals. To enable increased extraction, the planned industrialisation and expected urbanisation, energy production is increasingly a priority. Unpredictable output levels from the country’s current generation, notable its hydro-electricity plants, also make energy a focus of government attention. Biomass currently accounts for 90% of the nation’s final energy. / Tanzania is currently one of the world’s lowest emitters of greenhouse gases (GHG) at 2.4 tonnes of CO2 equivalent per capita (2007). Deforestation, (before taking account of forest replanting), accounts for 70% of total GHG emissions. Agriculture comprises 23%, mainly through emissions from livestock and soils. / Prior to project start, Tanzania had no coherent national approach to responding to climate change risks. Similarly, while it participated in international negotiations, it had no mechanism in place to channel (existing and planned) large-scale international funding to address national priorities incl. at sector and local level. The level of access to climate finance was limited and amounted to US$50m (£31m) / The need for such additional funding is considerable. In 2012, the Economics of Climate Change outlined the financial requirement for programmes that address both current variability and build resilience to future climate risks was estimated to be US$ 500 million per annum (£312m perannum). By 2030, total additional costs of building resilience and managing climate risks could be as high as US$ 1,500 to US$ 2,000 million a year. (£938m-£1250m per year) / Building on the support provided and experience gained under the Tanzania Cliamte Change Institutional Strengthening Programme (TCCISP), DFID Tanzania has successfully accessed £110m from the UK International Climate Fund (ICF) for programmes in four new areas that have been identified for building resilience: (i) Water security/Agriculture, (ii) Urban resilience (iii) Institutional strengthening, and (iv) Green mini grids. The third area is of particular relevance for the current programme, as the outputs and lessons learned will be the basis for the scoping of this next, larger phase of support. In addition to this DFID Tanzania is in the final stages of approval for a low carbon development business case for scaling investment in green mini grids (off-grid electrification) in Tanzania (£30m) and a recently approved additional round of private sector challenge fund AECF REACT, bringing the total funding under this fund for Tanzania to £8m. The work under TCCISP has been critical in supporting of scale of UK climate finance in Tanzania.

## Section A: Detailed Output Scoring

Output 1: Comprehensive climate change strategy in place, including adaptation and low carbon, with budget allocation and being effectively delivered at sector and district level.
Output 1 score and performance description: A+ Outputs moderately exceeded / Indicator 1.1 National Climate Change strategies (URT and Zanzibar) in place / Milestone: Strategy for Zanzibar developed by end 2013 / RAG Assessment: Green
Progress against expected results: Milestone met and exceeded / Following the 2012 annual review, the Revolutionary Government of Zanzibar (RGOZ) requested assistance to develop its own climate change strategy as their view was that the National Climate Change Strategy did not adequately consider the islands. Support for the Zanzibar Climate Change Strategy (ZCCS) was provided by DFID through UNDP’s climate change mainstreaming programme in Zanzibar. The ZCCS was drafted by a team of international consultants supported by a consultative process in Zanzibar, with strong buy-in and support from the First Vice President’s Office – Division of Environment (which has a focal point for the strategy) and the President’s Office of Finance, Economic Development, and Planning. The Strategy was a key outcome of the support provided by DFID on the Economics of Climate Change in Zanzibar (£150,522 financed under TCCISP), which was also used as an input to the Strategy itself. / The ZCCS was completed by the end of 2013, approved by Cabinet and formally launched by the President of Zanzibar on World Environment Day in June 2014. The President has requested that all relevant sectors mainstream the ZCCS in their operations and budgets, though this remains an unfunded mandate. / The RGOZ has prepared a Terms of Reference for technical assistance to the Division of Environment to develop the Zanzibar climate change strategy investment plan, which would include, streamlining institutional roles and responsibilities for delivering the ZCCS, a monitoring, reporting and verification framework, and developing costed investment plans at the sector and local levels. This investment plan is a deliverable under UNDP’s mainstreaming programme, but does not currently have budget available for its implementation. Zanzibar is on track to prepare an investment plan per the 2014 TCCISP milestone, but this is unlikely to happen before the end of 2014 as the ZCCS was launched mid-2014 and would be at risk given the lack of funding. It is therefore recommended that the logframe is amended to include a more realistic timeframe for this and support for the investment plan is considered under TCCISP. The Planning Commission and Ministry of Finance also requested support on agreeing a way forward on the climate finance modalities and development of capacity for claimte screening of investments and plans. / Indicator 1.2 Climate Change plans developed in sector ministries identified as priorities by URT/Zanzibar and for GOT economic priorities / Milestone: SAGCOT green growth strategy launched and next steps identified by end 2013. Climate change action plan in Agriculture by end 2013. / RAG Assessment: Green / Progress against expected results: Milestone met expectations / Indicator 1.2 was included in the updated logframe after the 2013 annual review due to the emphasis on sector-level planning in the NCCS. The SAGCOT green growth strategy was finalised and formally launched in 2012, but uptake of the document by SAGCOT stakeholders was slow. However the SAGCOT centre id use the document in October 2013 This has since been revived, with the SAGCOT Centre using the strategy to demonstrate that the SAGCOT centre have a strategy for addressing the issues raised in the Strategic Regional Environmental and Social Assessment (SRESA) and that they are promoting green investments. A Green Reference Group has formed, with financial support form the US funded Nature Conservancy, which includes representation of private agribusiness, Development Partners, NGOs and Government, in order to guide how SAGCOT can promote green and socially responsible investments under SAGCOT “green print” as it is known. The SAGCOT centre have also employed a full time programme officer to lead environmental and social issues. / The Agriculture Climate Resilience Plan (ACRP) through the Ministry of Agriculture, Food Security and Cooperatives (MAFC) has been drafted and is currently undergoing stakeholder consultation. The ACRP was drafted through finance to the World Bank via the EFO. The MAFC Environmental Management Unit has led the process and generated strong support within the Ministry, generating awareness among management and committing to Parliament that the Ministry would deliver the ACRP by the end of June 2014. MAFC is planning to convene a meeting with the Ministry’s management team in June to present the ACRP for their endorsement. The EMU has indicated that, while the ACRP is still in draft form, that MAFC is already using the document to leverage funds for climate smart agriculture at regional level thorugh the EAC and also using it to mainstream climate change in sector initiatives (e.g. SAGCOT, Big Results Now, and the negotiations around the Agriculture Sector Development Strategy II basket fund). / The ACRP is nearly finalised but has been delayed beyond the original milestone set for the end of 2013 to allow for internal consultation and approvals. The Ministry of Water has completed a sector climate change action plan as well, so together with the finalisation of the ACRP and progress with the Zanzibar action plan, the 2014 milestone for the completion of two sector plans is on track, as is the 2015 target to have three sector plans in place. / In addition to this PMORALG is developing a metholdogy for mainsteaming climate resilience at municipal level, these tools and methodology will feed into their World Bank supported work on urban, which will be taken to scale with UK ICF funding – see ICF concept note on urban resilience (£20m) approved in April 2014. / Analytical work around implementation of the NCCS and ZCCS is described in more detail in Indicator 1.3. In conclusion from the support provided by TCCISP is that sector action plans to date are ad hoc in nature based on development partner interest and funding, there is a need provide funds to support implementation of sector plans, and clear guidance and methodology for preparing sector plans needs to be developed (incl. clarity on time span, costing methodology). It would be good to consider this as part of any future support on institutional strengthening. / Indicator 1.3 Transparent mechanism for funding Tanzania’s response to Climate Change in support of the national strategy operational / Milestone: Feasibility study on options for financing completed by end of year. / RAG Assessment: Green / Progress against expected results: Milestone met and exceeded / An options paper, prepared by independent consultants (GCAP) contracted through DFID’s resource centre CEIL PEAKS, was finalised in July 2013. This work had already been presented (together with DFID centrally funded ODI’s work on a climate public expenditure review) at a UNDP-sponsored workshop on climate finance in March 2013. As found in the 2013 annual review, while a useful exercise in setting out the options for a climate fund, it did not take a step back and assess whether a dedicated climate fund in the Tanzanian context is indeed the best approach. It was agreed that any assessment of climate finance modalities needs to consider the opportunity cost of establishment (for a fund this can be 2 years and over £2m based on the Rwanda experience), the political economy incl. high level leadership and buy in from Development Partners, who would be willing and/or able to contribute. The MTR/AR recommended that further work be commissioned that would result in a more comprehensive analysis and develop a broader roadmap for support of the NCCS, which moves beyond a single climate fund. Responding to this recommendation, three additional results have been achieved: / A high-level meeting with the PS of Environment, DPS of Ministry of Finance, and Development Partners (UNDP, DFID, World Bank and Norway) was held in Februray 2014, and a task force appointed to chart the way forward for developing a climate finance mechanism. Support for this task force has been provided by UNDP, through DFID support to the climate change mainstreaming programme. / Through the EFO, the World Bank has drafted a policy note that digs deeper into options and considerations for financing the NCCS and ZCCS, which is Tanzania-specific and provides guidance and consideration of a range of possibilities to leverage and manage financial resources for climate change. This builds upon the GCAP climate fund options paper as well as the work done by ODI and DFID London on climate finance modalities, but adds a critical element of the political economy analysis around climate change planning and finance that has to date been lacking in previous technical outputs. A key aspect of this work is to guide the URT to more strategically request and use funds from Development Partners for supporting the NCCS and ZCCS. This report has been drafted and is currently under review by World Bank management and has been peer reviewed by DFID Climate Environment Department (Malcolm Smart), and initial conclusions presented to the government finance task force. This piece was not originally envisaged under the EFO but was undertaken given the opportunity for influence at a high level. / A team of international and local consultants were also contracted under TCCISP to develop a Roadmap to support implementation of the NCCS and ZCCS, based on a request form the government, Vice Presidents Office. The Roadmap analyses current levels of DP finance in Tanzania and prospects to access additional finance, and proposes a practical way forward that would fill critical planning and capacity gaps to deliver on the NCCS and ZCCS, which reflects the current reality on both the donor and government sides. / The key issue going forward is that there a notable departure between the conclusions of the GoT task force ( supported by UNDP) and the conclusions from the World Bank/ DFID study and the Roadmap, which clearly advise that a dedicated fund is only one modality for implementing the NCCS, and a broader approach needs to be taken, whereas the task force is more focused on the design of a single financing mechanism i.e. a fund. The Vice President’s Office is moving ahead with using the national Environmental Trust Fund set out in the Environmental Management Act as this mechanism, yet there is little demonstrated appetite by development partners to contribute to such a fund. In mainland Tanzania, this is likely to be the main government funding mechanism to support the NCCS but will lack the transparency, good governance structures and credibility desired by DPs. The Roadmap concluded that DPs are unlikely to contribute to the ETF, and instead recommended that the URT focus on a more structured approach to implementing strategies, and developing a comprehensive system to track climate finance and effective delivery of results. This would be a lengthy process and require significant investment, outside of the scope of the current TCCISP, but could yield substantial results to improve how climate finance is managed and tracked. / Zanzibar has clearly signalled interest in developing their own financing mechanism separate from that of the Mainland, given the coordination challenges. They are more open in their approach and are potentially interested in developing either a climate fund or a results based financial aid instrument in support of their strategy and investment plan. It is proposed that TCCISP in the next year look at supporting Zanzibar in developing a resource mobilisation plan and as part of that scoping out how such an instrument could work, with a view to financing it under the UK ICF. / While the outcomes of this work are quite positive and should provide guidance to both URT/Mainland and Zanzibar that is much more reflective of the current reality on the ground, it has also resulted in a departure from the original intent of the indicator to develop and operationalize a transparent funding mechanism for climate change. Additionally, the climate finance policy note as well as the Roadmap have recently been finalised and will need to be presented and discussed as part of dialogue with the URT and DPs on climate finance. It is therefore proposed that the indicator is changed to something more short term, to reflect the political economy and reality on the ground. / Output 1 Recommendations / Immediate 14/15 / The 2014 milestone for Indicator 1.1 should be revised to focus on developing an investment plan for the Zanzibar climate strategy, targeted for the end of 2015. / Messages from the Road map and EFO outputs on climate finance need to fed into the dialogue on climate finance with DPs and URT/ Zanzibar. / The output statement on developing a climate finance mechanism may need to be revisited, as it is likely that the preferred mechanism of the government i.e. establishment of a environment/climate fund supported by UNDP; however there are concerns about the transparency and credibility of a such a fund. Review whether the Target for 2015 for Indicator 1.3 is realistic in light of the political econmy and therefore needs to be adjusted – agree appropriate changes and way forward with Results Adviser. / TCCISP to consider supporting ToRs developed by RGOZ for supporting implementation of ZCCS over the coming year. / Long term – input to design of new ICF programmes / Development of the new ICF Business Case on institutional strengthening can draw from the activities under Output 1 over the next year to appraise options for results-based financial aid to Zanzibar and central structured support on development and implementation of sector action plans in implementation of both the NCCS and ZCCS. / Feed in recommendations from Roadmap on climate finance tracking and monitoring into new ICF business case. / Impact Weighting (%): 35% / Revised since last Annual Review? No / Risk: / Revised since last Annual Review? No – still medium to high due to political economy. However as the President is now the chair of the Africa group on climate change, there maybe a window of opportunity to provide high level leadership but unclear if this will be sustained beyond the election.

Output 2: GoT and development partner investments and expenditure is climate smart
Output 2 score and performance description: A+ Outputs moderately exceeded / The purpose of this output is to mainstream climate change across the activities of DFID, other Development Partners and the Government of Tanzania. Output 2, including the milestones and targets, were revised in 2013 after the 2012 annual review found that the output to ensure that all DP and URT spend was climate smart was overly ambitious. / During the period 2013-2014, there is an improved evidence based on government and DP spend on climate change, but also a greater recognition of how complex this analysis is to undertake on an ad hoc basis. A climate public expenditure review done by ODI and University of Dar es Salaam was completed in 2013, which shows trends in government climate spend from 2009 - 2013, and the same methodology was applied to the agriculture sector (discussed below). On the DP side, the annual mapping exercises were deepened through the development of the Roadmap (also discussed below). It is notable that neither exercise clearly developed the criteria for defining what is “climate smart” investment. However, these are first steps in using methodologies to assess and track climate finance, and do provide a firmer basis from which to assess the proportion of climate smart investment by DFID, DPs, and the URT/ Zanzibar. / Indicator 2.1 Proportion of DFID (and development partner) spend that is climate smart / Milestone: New project and programmes screened for CC risks and opportunties - same target for 2014 and 2015. / RAG Assessment: Green / Progress against expected results: Milestone met and exceeded / DFID has effectively mainstreamed climate change screening for new projects and programmes undert its mandatory Climate and Environment Assessment (CEA) and also provides additional inputs and specific outputs on building climate resilience e.g. rural roads. As described in the 2013 annual review, a screening of all programmes including General Budget Support was undertaken in 2012 which identified significant climate risks but also large opportunities for building resilience for example in infrastructure and water resources. Additionally DFID’s Climate and Environment Assessment process for all projects and programmes, which is approved by a climate and environment adviser, effectively screens for risks. / Initiatives to mainstream climate change have increased over the past year as well, which is increasing the level of spend across DFID and DPs that is climate smart. Many of these areas were identified through prior screening processes, and DFID also developed and implemented a Country Poverty Reduction Diagnostic (CPRD) and Resilience strategy in 2013, which further provided the rational for building resilience across the portfolio and £55 million in ICF investment has been identified to mainstream climate change in rural roads, port infrastructure, civil society accountability programme and social protection. The new £110 million in ICF programme funds will contribute to further mainstreaming in water, agriculture and urban. For example the urban resilience ICF programme will build resilience through the World Bank’s $500 million urban portfolio. / The CPRD Resilience pillar and Resilience strategy will provide the building blocks and priorities for the DFID Tanzania operational plan period.
Indicator 2.2 Proportion of GoT budget that is climate smart / Milestone: Screening undertaken in URT by end 2014. All new investments in URT screened by end of 2014 ( as part of Environmental Impact Assessments). / RAG Assessment: Amber / Progress against expected results: Milestone met in terms of the EIA but unclear to what extent all projects are screened effectively / A climate public expenditure review was completed by ODI and University of Dar es Salaam in 2013, and a budget screening for the agriculture (and water sector by GIZ/ODI) was also carried out in 2013 as part of the process to prepare the sector action plan through the EFO. The ODI PER found that the proportion of the budget for climate-relevant activities (as defined in the study) has grown steadily as a proportion of the budget from 2009 – 2013 (4.2% to 6.5%, respectively), which is tied mostly to an increase in development partner funding for climate smart agriculture. While the amounts appears to be substantial, most of the projects are only loosely linked to building climate resilience. The subsequently a further more detailed screening of the Ministry of Agriculture budget was undertaken through the EFO, as part of the sector climate action plan preparation, using the same methodology as the national PER. This came to similar conclusions, but was particularly relevant for the costing of the action plan: because the budget screening was done, the action plan was able to set a target to increase sector climate spend by 22% over the previous year in order to implement the action plan. / This indicator was updated after the 2013 annual review found that Environmental Impact Assessments (EIA) in Tanzania now have to factor in climate change impacts, which should indicate how investments consider climate risks and impacts. As reported in the 2013 annual review, there was some evidence that this process was working as seen in the SAGCOT Strategic Environmental Assessment (SRESA) and Rufiji basin IWRM strategy, both of which considered climate change in scenario planning. However, this will be complicated to assess and determine results since there is no tracking of EIAs and how they consider climate change. How to measure this indicator will need to be considered for the next annual review and the project completion review. / Milestone: Zanzibar also screening investments as part of Mkuza implementation. / RAG Assessment: Green / Progress against expected results: Milestone met and exceeded / Zanzibar specifically requested development of climate screening tools for public investments under the MKUZA II, Zanzibar’s guiding development plan. A rapid screening was done in 2012, and climate risk screening guidelines prepared for government in 2013. The ZCCS includes climate mainstreaming as a strategic priority, which would build on this screening tool and involve the Planning Commission and Division of Environment and include strengthening of screening guidance, wider training across government, and extension to private investment. While it unclear that screening has not been systematically applied to investments yet, the system is in place and with the adoption of the ZCCS it has the backing of the strategy, and with support through the UNDP climate mainstreaming project, and buy-in from government. Zanzibar appears to be on track to meet this milestone going forward, pending additional strengthening to implement screening procedures. Zanzibar requested additional support (25/06) in this area for both the Planning Commission and Finance to set up guidelines, screening tools and capacity in both minisites to undertake this as part of the development of new plans (post Mkuza 2) and investments. This could be considered in the new ICF business case for institutional strengthening. / Output 2 Recommendations / Immediate 14/15 / DFID’s new A2L SAIC climate change adviser should follow up with NEMC and Zanzibar to see how EIA screening and MKUZA II screening are working, and include lessons learned in the new ICF programme. / How “climate smart” investments and expenditures will be assessed in the AR/PCR will need to be defined, as there are now several different tools and studies that have undertaken these types of assessments but there is no standard methodology. Consider defining and assessing the impact of screening tools versus mainstreaming in institutions (e.g. Rural Roads Fund, TASAF, agriculture sector programmes). Assessing climate risks through EIA requires additional guidance as to how the indicator will be assessed and how mitigation measures for identified risks would be built into projects – follow up to see if this is a gap. / Develop ToRs and provide funding under TCCISP to support mainstreaming of ICF funding under rural roads, port, social protection and accountability programme (AcT). / Long term feed into new ICF programmes / New ICF Business Case can consider institutional strengthening for both mainstreaming climate change in the EIA process in Mainland and Zanzibar, as well as implementation of the climate screening tool for planning in Zanzibar / Undertaking ad hoc assessments of climate spend for DPs and URT is costly and the results are inconsistent – a more systematic approach is needed for a credible evidence base. Recommendation from the Roadmap report is to set up a climate finance tracking system consider supporting this under the ICF supported programme. / Impact Weighting (%): 20% / Revised since last Annual Review? No / Risk: / Revised since last Annual Review? No - medium

Output 3: Improved aid effectiveness through a comprehensive framework for development partner support in Tanzania on climate change
Output 3 score and performance description: A Outputs met expectations / Output 3 largely focuses on the performance of Development Partner support to Tanzania on climate change, to more effectively direct climate spend toward alignment with the NCCS. The 2013 review pointed out several challenges with respect to DP performance, including reduced efforts by DPs to harmonize activities, personnel changes within the Development Partners Group on Environment (DPGE), and inconsistencies between DPs on how climate change activities are defined, which makes assessing the levels of DP spend on climate change a challenge. / Coordination on climate change within the DPGE this year has been in flux, with limited secretariat support at the beginning of the year and DFID stepping down as lead on claimte change in January 2013. DFID after 4 and half years has stepped down as lead of the sub-group on climate change, due to capacity constraints. Finland as chair of DPGE is now leading the dialogue on climate change. Ad hoc meetings on climate-specific topics have still been led by DFID e.g. Climate finance, Roadmap and district level climate finance and planning, but climate change issues are now mainly discussed as part of overall DPGE monthly meeting agenda. DFID has provided support to the new secretariat, which has greatly improved coordination and communication between DPs and the URT. However given DFID staff constraints a gap exists in the dialogue between Development Partners/ DPG-E and government on climate change, it is anticipated that this gap will be filled with the recruitment of a new SAIC A2L Climate change advisor (funded under TCCISP) who will lead on the co-ordination and dialogue with government and partners on climate change. Approval for this position was agreed on 13th December, however the funding for this post was only agreed in May 2013 and recruitment is underway. It is anticipated the postholder will be in place by September/October 2014. / The Roadmap and climate finance policy note responded to the challenges found in the last review as well, both to conduct a more detailed assessment of DP climate spend but also to pose recommendations for both the URT and DPs to improve coordination, evidence, and use climate finance more strategically with the specific aim to align with the NCCS and ZCCS. A systematic approach to track climate spend is a major recommendation coming from both, which recognise the reality that DPs are unlikely to develop one coordinated approach to support the NCCS and ZCCS. These still need to be presented and discussed with government and DPs, which is a next step in 2014. / There is evidence that DP coordination on support on climate change is improving at a project level. For example, Tanzania is a pilot country for the Scaling Up Renewable Energy Programme ($50 million), jointly supported by AfDB, IFC and World Bank. Joint programming related to climate change has also been identified in other areas such as water, agriculture urban and energy sectors mainly between DFID, WB and SIDA. / Indicator 3.1 Increased proportion of development partner spend in line with DP CC framework (and National CC strategy) / Milestone: 25% of climate change funds in support of DP framework by 2013 / RAG Assessment: Green / Progress against expected results: Milestone met and exceeded / DP commitments on climate change have increased in the past year, and significant resources are in the pipeline. The Roadmap found DPs commitments total US $245 million, with another $400 million in the pipeline, which is an increase over the findings of $194.5 million in the 2013 mapping. However, most of this increase is due to the omission of Japan’s Fast Start Finance in the DPGE mapping. Though DPs have undertaken annual exercises to map overall environmental spend, including climate change, the Roadmap and climate finance policy note through the EFO confirmed the challenge of doing so, and especially determining how DP spend aligns with the interventions in the NCCS and ZCCS. This was originally envisioned in the Roadmap assignment, but was agreed with the consultants that the scope was too complex and a more modest approach was taken. / Additionally, there is no standard guideline to determine what is “climate spend” and no system for assessing it, so the mapping exercises are likely to remain ad hoc and yield inconsistent results depending on who facilitates the exercise and what DPs contribute. These exercises are sufficient for rough figures on climate spend through the DP environment sector and international climate finance, but inadequate for use as a measure of aid effectiveness. As discussed under Indicator 1.3, the Roadmap recommended development of a comprehensive tracking system of climate interventions more broadly, with a major focus on finance. However this will take considerable support outside of the scope of the current TCCISP and will not be in place for the PCR next year. The Roadmap points out that this system alone cannot assess overall aid effectiveness, but would provide a much stronger and more systematic evidence base from which effectiveness could be analysed. / Output 3 Recommendations / Immediate14/15 / The 2014 milestone should be revised to assess development partner climate-specific funding rather than attempting to map all development partner funding against the NCCS and ZCCS, which would not be feasible especially if not part of a systematic process. / The new A2L SAIC Climate change adviser should lead on reviving coordination on climate change issues between development partners and the government to enhance aid effectiveness on climate finance and programmes. / The climate finance tracking system envisioned in the Roadmap should be discussed among DPs and govertnment to gauge interest and feasibility for improving coordination and ability to deliver results on the strategies / Update the 2014 milestone to agree with Government on a TOR and next steps for developing a system to track and monitor results (effectiveness) of climate finance. / Long term to feed into new ICF programme / Consider how a systematic approach to climate change planning and finance tracking can be supported as part of new ICF institutional strengthening programme building on ToRs for climate finance tracking and reporting. / Impact Weighting (%): 10% / Revised since last Annual Review? Yes / Risk: / Revised since last Annual Review? No – Low to Medium

Output 4: Strengthening the data and evidence base for decision making around climate change spending.
Output 4 score and performance description: A+ Outputs moderately exceeded / This output was dramatically changed in scope after the 2013 annual review. It was originally intended to “Establish an effective M&E framework for climate change in Tanzania”, which was to ensure DFID Tanzania effectively monitored and evaluated its impact on building resilience to and mitigating climate change. This was primarily an internal DFID management function and a responsibility of the management team for the climate change programes ( adviser and programme officer). With the removal of the Climate Change Adviser funding from this project, the elements of this activity that are internal to DFID ceased to be an output. / Instead, this output now focuses on a major gap that has been identified for climate change planning in Tanzania: lack of data and evidence for making informed decisions on climate spend at all levels of government. This was subsequently revised in the logframe, approved in December 2013, with Indicator 4.1 on district climate change planning strengthened and moved from Output 1, Indicator 4.2 added to improve the use of climate change evidence in decision-making, and Indicator 4.3 includes a new activity through a partnership with the UK Met Office to support TMA in improving climate data information and services. / Despite the late addition of this output under the programme, performance in 2013-14 has met key milestones and activities are largely on track to meet targets in the final year of the programme. While in the initial stages, over the next year all three indicators also hold potential to not only strengthen the data and evidence base, but also the process of decision-making itself. Three districts have set up finance mechanisms that await budget allocation and have structures in place for bottom-up adaptation planning to develop a pipeline of fundable projects, there is evidence that analytical work is influencing key policies and plans, and the significant issue of climate data accessibility has a plan in place for improvement that will soon be implemented. / Indicators 4.1 and 4.3 are particularly relevant to be considered for scale up as part of new ICF programmes to be developed over the coming year, to ensure that they build on the existing systems and structures that are being built through the current programme and scaled up appropriately. / Indicator 4.1 District climate change programming funding mechanisms piloted in at least 5 districts that can be taken to scale by end of project / Milestone: Scoping support to vulnerable coastal comunities building on drylands pilot. Implementation in at least 3 districts underway. / RAG Assessment: Green / Progress against expected results: Milestone met and exceeded – coastal work undertaken by WB independent of TCCISP and work in 3 districts exceeding expoectations but issues of scale up and sustianbility need to be addressed / Scoping to vulnerable coastal communities / This is underway, though through a different mechanism than originally intended. This milestone was thought to scale up the IIED programme and methodology to coastal districts, but this has now been done through a World Bank project (with no addititional requirement for support from DFID) to assess vulnerability along the entire coastline of mainland Tanzania and Zanzibar, and prioritise projects for building coastal resilience. It was considered to be cost effective and good value for money to undertake this work through IIED given the high degree of consultation involved in setting up the structures for district-level adaptation planning and finance, transportation costs to bring districts together for collaboration, and that the drylands pilots are not yet fully advanced to draw lessons on the functionality of funding mechanisms for the design of new ones. The pipeline of projects that will come out of the Bank study could be a good basis for future scaling up of climate finance and programming in coastal districts. / Implementation underway in at least 3 districts / DFID is investing in 3 dryland districts in northern Tanzania which have historically been vulnerable to drought (Longido, Monduli and Ngorongoro). This project implemented through IIED/Haki Kazi intends to build adaptation capacity of these areas and responds to the needs and the experiences of communities, particularly following the drought of 2010. / The approach taken is process-orientated, requiring the participation of recipients and beneficiaries; this has taken time to achieve and builds upon previous IIED projects. Key stakeholders such as District officials, PMO-RALG, the VPO, MNRT, TMA, MLFD and local MPs have been consulted and support the initiative. This support is seen as significantly improving the work’s likelihood of success. The model involves district councils, Members of Parliament, project implementers and the communities. The project also provides a direct connection from the grassroots to national level agencies, and builds on exchanges with similar activities in arid and drylands of Northern Kenya. / This work fills a gap in district and community level planning, where communities especially felt they didn’t have a voice despite a national framework for participatory planning. Districts face a challenge in responding to weather-related shocks because the budgeting and planning process is rigid, and funds can not be flexibly used for discretionary purposes (as in the case of drought response). The structures set up under the project address both of these issues: providing a flexible fund that can better be controlled by the district, and ensuring that funds respond to community priorities. This is backed up by a solid fund structure that is legally sound, a decision-making structure from the community up to district decision-makes, sensitization of district and local leaders, and training of facilitators that will lead the community engagement process. IIED/ Haki Kazi has coordinators in each district that work within the district and across the three districts. / The funding mechanism for each of the three districts has been established, budget requests have been submitted to PMO-RALG/Ministry of Finance, and they expect funds to arrive in Quarter 2 or 3 of the 2014/15 financial year from the national budget along the lines of 2 billion shillings per district (with additional funds for Monduli given the need for response to a drought last year). While the initial contribution is expected from MoF, the fund is structured such that contributions can come from outside sources as well incl. climate funds. There is a solid framework for funding decisions, which relies on an evidence base: a legal analysis was done to ensure a fund was feasible, a total economic valuation is nearly completed, and detailed natural resource mapping has been done with local knowledge to understand the resource base and livelihoods patterns. These tools are fully integrated into decision-making around adaptation projects, and developing a pipeline of projects based on the funding envelope. / The project is set to close in September 2014 and IIED/ Haki Kazi envisions a second phase that would deepen the experience in the three districts and expand to 10 more in Tanzania over the next four years. They are planning to sign an MOU with PMO-RALG and develop an operational framework for the programme in June 2014. While the structures are all in place and significant capacity and buy-in exists, it may take time for both government funds and outside funding sources to flow into district finance mechanisms. With the project set to close, there is a risk that the work done to date could lose momentum, and/or that funds will be received but the project will not be able to continue supporting the planning process that is critical to link adaptation finance with the vulnerability and needs of communities.
4.2 Government and donors using improved evidence base for decision-making in climate change response investments / Milestone: Studies feeding into NCCS plans in URT and Zanzibar / RAG Assessment: Green / Progress against expected results: Milestone met / This milestone has been met and exceeded– the Economics of Climate Change studies for Mainland and Zanzibar have fed into the NCCS, ZCCS, and agriculture action plan (which was able to draw from climate projections and costing). Other efforts are also underway that are having an influence on integrating climate change in decision-making: for example the district adaptation project with IIED/ Haki Kazi has strong endorsement and involvement of District Officials and Members of Parliament in each of the three target districts. The sector action plan for agriculture prepared through the EFO, while not yet formally approved, is also being used by the ministry to guide preparation of the updated Agriculture Sector Development Strategy. A ministerial meeting was held on water, energy and agriculture to build economic resilience through water security. / However, meeting the 2015 target under Indicator 4.2 requires updating to reflect changes in resource allocation. This was originally intended to work either i) directly with Climate Parliament in establishing a cross party committee on climate change and renewables or ii) through a UNDP programme of supporting Parliamentary committees. BHC have provided funding to Climate Parliament to provide support in establishing the committee it is therefore felt that additional support in this area is not reuired under TCCISP. Additionally, the annual review has found less demand for sector or geographical briefings on climate change and limited demand from MPs specifically – instead, direct and practical engagement such as that done by IIED/ Haki Kazi is likely to be more effective, as well as linking with BHC funded Climate Parliament initiative on Parliamentary Action for Renewables in East Africa. This would build capacity of legislators through awareness raising, regional networks, and supporting parliamentary action. / 4.3 Improved collection, storage and use of climate data and information / Milestone: Proposal for digitisation of archive climate data / RAG Assessment: Green / Progress against expected results: Milestone met / The UK Met office has drafted a proposal that includes digitisation of TMA’s paper archives of climate data, and the project is moving forward. There has been a slight delay of 1 – 2 months due to contracting issues, but the project has completed the inception phase and a strategy will be developed for carrying out the digitisation and inventory of the archives by September 2014. The digitisation of high priority data will be completed by February 2015, slight after the 2014 milestone (set for end-2014) but this accounts for the delay in contracting. It should be noted that it will not be feasible to digitise the entire archive of climate data; however, TMA will be left with a system and equipped to use it, as well as having a capacity development framework so that the digitisation is sustained. / A foreseeable challenge in meeting the overall indicator is on the improved use of climate data – this is a policy issue beyond the scope of the project but could be considered for support later. Though the project data will be more accessible within TMA, but it is unclear how this will translate to outside users. Currently TMA has a culture of data ownership and see selling data as a key to financial viability, but there is likely a greater opportunity to make climate data more freely available and instead scale up the value chain to offer analyses that can be used as decision-making information by private sector and sector ministires such as agriculture. / Output 4 Recommendations / Immediate 14/15 / Indicator 4.1 should be revised to pilot climate funding mechanisms in three districts, to match the 2015 target. Setting up the structures in two additional districts by 2015 will not be feasible. / Re-orient the 2015 target for Indicator 4.2 toward more practical engagement with decision-makers and integrating climate planning with policy / Extend the IIED/ Haki Kazi drylands work to carry out community planning to have a pipeline of projects for funding through the district finance mechanism, and allow time to leverage additional sources of finance by March 2015. Focus of any extension to IIED/Haki Kazi work should focus on addressing gender, work on ensuring budget allocations under exisiting district level budgets for prioritised activities under district adaptation plans, sharing lessons with TASAF and Zanzibar and addressing issues of scale up and long term sustainability. / Long term feed into new ICF programmes / Consider how future support could establish a long-term mentoring relationship between TMA and the UK Met office / Consider measures at a policy level for making climate data from TMA more accessible to users / The coastal vulnerability and adaptation priority work should be included in the Business Case appraisals for scoping work on both urban resilience and institutional strengthening. / Impact Weighting (%): 35% / Revised since last Annual Review? Yes / Risk: / Revised since last Annual Review? No – medium to high

## Section B: Results and Value for Money.

1. Progress and results
Has the logframe been updated since last review? / Yes, an updated logframe was drafted to accompany the 2013 Annual Review, with revised outputs and indicators, in light of its recommendations. Several indicators were found through the 2012 and 2013 reviews to be overly ambitious, and the indicators were adjusted in light of these recommendations. The revised logical framework was reviewed by the DFID Tanzania results adviser and comments have been incorporated. It was approved in December 2013. / The annual review suggests some minor adjustments to the revised logframe to account for minor discrepancies and scoping issues. These are as follows: / Output 1 / The 2014 milestone for Indicator 1.1 should be revised to focus on developing an investment plan for the Zanzibar climate strategy, targeted for the end of 2015. / Review whether the Target for 2015 for Indicator 1.3 is realistic in light of the political economy and therefore needs to be adjusted – agree appropriate changes and way forward with Results Adviser. / Ouptut 3 / The 2014 milestone 3.1. should be revised to assess development partner climate-specific funding rather than attempting to map all development partner funding against the NCCS and ZCCS, which would not be feasible especially if not part of a systematic process.Update the 3.1 milestone/ target to agree with Government on a TOR and next steps for developing a system to track and monitor results (effectiveness) of climate finance. / Output 4 / Indicator 4.1 should be revised to pilot climate funding mechanisms in three districts, to match the 2015 target. Setting up the structures in two additional districts by 2015 will not be feasible and there is not sufficient budget and time for this. / Re-orient the 2015 target for Indicator 4.2 toward more practical engagement with decision-makers and integrating climate planning with policy / Annex 2 – includes revised logical framework 2014, with the minor changes outlined above. / 1.2 Overall Output Score and Description: / A+ Outputs moderately exceeded - output scoring and risk summary. / 1.3 Direct feedback from beneficiaries / As reported in the 2013 annual review, DFID continues to be seen as a key partner with government (and more broadly with Civil Society, DPs and private sector) on climate change in Tanzania. In particular, its access to and provision of high quality technical expertise is valued. / DFID retains good relations with the Vice Presidents Office in Mainland and the First Vice President’s Office in Zanzibar, who respectively have overall responsibility for the climate change agenda. Key ministries, such as the Ministry of Finance and Planning Commission (Mainland and Zanzibar), Ministry of Agriculture, Food Secuirty and Cooperatives (MAFC), Ministry of Water, Ministry of Energy, and PMO-RALG have been the focus of the engagement over the past year and this should continue, especially as appraising options for new ICF funding moves forward. Engagement with the mainland Planning Commission (POPC) began in 2012 and climate change was of interest to POPC, but this was not sustained. There could be an opportunity to restart this dialogue during preparation of the new ICF business cases as well as during awareness-raising of the TCCISP outputs. / The team met in the district of Longido and the district coordinators from Monduli and Ngorongoro spoke highly of DFID’s support to local adaptation planning and climate finance. They reported strong benefits from capacity building both on climate science as well as planning processes, and IIED/Haki Kazi described this engagement as a genuine partnership between government, NGOs, and local communities where government was driving the process. / There is still a consistent demand for support from Zanzibar, which was evident through the process to develop the ZCCS as well as the subsequent Roadmap process. There was ahigh level meeting held as part of this annual review (25/06) where the Ministry of Finance, Planning and FVPO presented the ZCCS and also identified key areas of support, they also highlighted how the support by DFID to date has helped them get to where they are now. Zanzibar has prepared a TOR for development of an investment plan for their strategy,resource mobilisation plan and identified a clear way forward, but realise the need for technical assistance in the process and have requested this support from DFID over the coming year. TCCISP should consider supporting this over the next year. / In MAFC there is clear ownership and broad buy in of the Agriculture Climate Resilience action plan the process of engagement has been very successful as comparted to for example the water sector, where both the output and process have not been so strong. / The relationships developed under TCCISP will be critical foundation for taking forward the new ICF business cases and this has already been seen in the case of agriculture,water, PMORALG/ urban and Zanzibar. With the engagement of the SAIC A2L climate change adviser it is anticipated that these relationships can be further strengthened at national, sector and local level.
1.4 Summary of overall progress / The programme has met and exceeded expectations, despite the difficult political economy progress it has been made in some critical areas. The overall conclusion is that the pace of change is much slower than initially anticipated in the business case. The programme has capitalised and responded to opportunities such as the request for a roadmap for NCCS and ZCCS implementation, establishment of climate finance task force and leadership shown by Zanzibar, sectors and districts. It has benefitted from changes to the log frame made in 2013 to revise the output indicators and set more realistic indicators, timeframes and targets, taking into consideration the political economy in Tanzania and around climate change, based on receommdnations from the MTR. Achievement under specific outputs has been positive and in some areas has exceeded expectations: progress on planning under Output 1 has exceeded targets, with national, sector, and subnational plans being adopted. The work on climate finance has been positive, yet yielded results that depart from both the intent of the indicator on climate finance and the government’s (VPO) direction. This is not necessarily negative, as the work under this outcome has recommendations for moving forward that are solid but require extensive dialogue with government ( Finance and VPO). Output 2 has yielded good results on developing a baseline for climate spend both by DPs and government, it has also identified a way forward on climate finance tracking, which is relevant not matter which claimte finance mechanism is adopted. Output 3 continues to be a challenge given the move away from aid harmonisation by many development partners and DFID’s limited time to dedicate to harmonizing the approach of DPs – despite this a DPG_E secretariat is in place and has support form Finland and Germany, there is prioritised workplan on climate change and the NCCS and ZCCS provide a framework against which DPs can align and the Roadmap is the first step in mapping this support and greater alignment. The recruitment of the SAIC A2L adviser under this programme, as recommended in the MTR, will help support the delivery of outputs 1-3 in particular through a closer dialogue with government and improved co-ordination of DPs on climate change. A framework for support will take time and resources to establish and co-ordinate. Output 4, which has the most concrete indicators and the largest funding allocation, it is on track to meet all milestones but there is a need to look at future sustainability of systems, structures and processes that have been supported in particular at the district level. / Much of the progress over the past year lies in developing strategies to overcome some of the barriers that were highlighted in the political economy study which was updated in 2013; in particular around the mixed messages around climate finance, lack of high level poltical leadership and the need for the programme to “go with the grain” for example support for Zanzibar, key sectors and districts. Coordination and alignment on climate change are still critical, particularly around climate finance but the Roadmap clearly shows that this can be done more effectively through supporting better planning, information and tracking systems for climate finance. / 1.5 Key challenges / Deciding how to provide support for a climate finance mechanism is a key challenge. The GoT/VPO has signalled its preferred option for a climate finance mechanism is under the Environmental Trust Fund, which most Development Partners (including DFID) would not find to be an acceptable management structure – due to issues of credibility, transparency and governance. / National strategies, sector action plans and district level adaptation planning are in place, but to date the functionality of these plans is unclear. The next step of leveraging resources and then management of those resources will be a key challenge at all levels to demonstrate results and not lose credibility if strategies and plans are not followed by resources. / While there is clearly demand and buy-in from Zanzibar, and now a climate strategy in place, there has been a consistent challenge in providing large-scale support from DPs given this would still be relatively modest compared to the transaction costs given the small size of Zanzibar compared to mainland. / Development Partner coordination will continue to be a challenge, likely more so with the lack of a focal person on climate issues – until the A2L SAIC CC adviser is in place. However the Roadmap offers a framework that fills key gaps with respect to the DP and URT coordination issues.The success of overcoming this challenge lies in large to dialogue and agreement around the Roadmap and next steps for implementation.
1.6 Annual Outcome Assessment / Tanzania is able to access climate finance and is using it to support climate change resilience and low carbon sustainable growth. The end of project (2015) (that Tanzania has secured $300 million in earmarked external finance) has already been exceeded (albeit this earmarking has yet to be reflected in the budget). The process of identifying which priority targets in the National Climate Change Strategy and ZCCS are being met is beginning to be put in place. The target of 500,000 people are better able to cope with climate change ( indirect) will also be largely met the current number of people already reached through the pilots at district level is 425,000.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: / The original budget of the programme is £2 million. But the mid term review conducted in 2013 identified the need to have this budget increased to cover for the programme’s expanding commitments. An additional £800,000 was approved in December 2013 through a cost extension submission, bringing the total budget of the programme to £2.8 million. As of 4 June 2014 the programme’s total spend is £1,899,664, with committed funds of £478,116 and a balance of £422,219. / Comparison of Activities Planned with Actual Expenditure by Output / Component Activity Output Actual Spend 04/06/2014 Commitment Comments / £ % £ / 202534-103 Direct Contract - DPGE Secretariat 3 24,960 100 24,960 Completed / Contract – PEAKS Roadmap to finance CC resilience in Tanzania 3&4 4,065 8 52,470 Time extension to allow for presentation of Roadmap to government / 202534-105 EFO - World Bank for TA climate resilience growth planning in Tanzania 2 120,000 95 126,000 Extension issued in May 2014 with additional £ 26,000 approved. / MoU Contribution Agreement – UNDP on mainstreaming environment and climate change into development planning. 2 133,333 67 200,000 MoU negotiated based on key deliverables and outputs under the UNDAP programme. / 202534-106 Accountable Grant – IIED Promoting climate resilience for dry lands 4 421,961 76 557,167 Request for extension in time and cost to March 2015 / 202534-107 MoU – UKMET Office Capacity development of Tanzania Meteorological Agency (TMA) 4 30,000 10 300,000 Delay in contracting due to lack of clarity on contracting process - MoU / Direct Contract – M&E independant consultancy inputs to annual review 4 0 0 3,601 Completed and invoice submitted / Total 743,319 1,264,198 58% of actual spend is contributed by output 4. / 2.2 Key cost drivers / In 2012 DFID Tanzania climate change adviser were £251,070 until this funding was taken back in house by DFID Tanzania, releasing an additional £324,249 for reprogramming. Also in December 2013 a cost extension of £800,000 was agreed, based on the MTR/AR recommendations. Building on the recommendations of the MTR/AR the project has moved to larger contracts/ agreements with UNDP, IIED/Haki Kazi and UK Met office, the last two both being under output 4, collectively contributing to more than £1m. There was a strong endorsement from the MTR for the work at district level with IIED/Haki Kazi, that this should be supported and further scale up for this work is to be considered over the final year of the programme. The other two MoUs were negotiated based on a clear set of deliverables. The EFO with the World Bank was already in place an additional resources and time has been agreed under for support to the GoT climate finance task force and for the printing, publication and dissemination of the deliverables. Over the past two years only three additional contracts have been let, two direct through a competitive process and one through the PEAKs resource centre. The contract through the PEAKs resource centre was for a group of individual specialised local and international consultants, which was managed by PEAKs and was seen to be more technically appropriate (right skills and experience) and more cost effective ( one contract v 5 seperate contracts and their management) then competing bids from GCAP and two other consultancy firms – neither of which had the right skills and experience. / 2.3 Is the project on-track against original timescale: Yes / Key strategic outputs were notably delayed in the 2013 annual review, but nearly all are on track in the revised logical framework. Several milestones require further adjustment for timing, but after the updated logframe none are expected to have significant delays with the exception of the operational funding mechanism under Indicator 1.3, which is beyond DFID’s direct control.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / No change since last Annual Review. The proposal to undertake a evaluation across the office review/evaluation on climate change is still under consideration, a budget has been allocated under this programme (up to £60,000) for M&E, incl. the evaluation. This would strengthen the evidence base on climate change and feed into future programming post 2015. It will build on the ITAD M&E claimte change work that was undertaken in 2012 that has fed into claimte change results reporting across the office. It has been identified as one of the areas that DFID Tanzania needs to address if it is to achieve “gold status” as part of the country Strategic Climate Programme Review. / 3.2 Where an evaluation is planned what progress has been made? / Under the original business case there was an allocation specifically earmarked for monitoring and evaluation, on the basis that the evidence base for climate change is weak and also to promote lesson learning across the DFID office. An evaluation is planned for 2015 as part of an overall DFID Tanzania Climate Change portfolio evaluation and the PCR. Planning is in the initial stages for this, with initial questions drafted as part of the mid- term review, see Annex 2 and ToRs will be drawn in 2014 in consultation with the Results Adviser.

4. Risk
4.1 Output Risk Rating: Low/Medium/High / Overall risk is medium – Risk table was updated as part of submission for cost extension approval in Decmber 2013 – see Annex 3. It has been further updated to include risks highlighted in annual review discussion on risk around NCCS, ZCCS and investment plans not being implemented due to a lack of allocation of funds from GoT and DPs. This is being addressed at sector level e.g. Agriculture through engagement in the development of ASDP2 and inclusion of the priority investments for the Ag climate action plan; at district levels adaptation plans are being integrated into the local budgeting process and other DP financing at local level moving away from a reliance on national climate fund establishment. / 4.2 Assessment of the risk level / Accurate and updated risk table ensures they are up to date and comprehensive.
Risk of funds not being used as intended / Low risk as majority of funds are directly managed by DFID or other development patners such asUNDP and WB ensuring full control of spend is maintained. The accountable grant through IIED funds being managed by downstream partner Haki Kazi,based in Arusha. Haki Kazi is also funded under AcT and is seen as low risk partner with good financial management systems. This is being monoiotred closely with the AcT programme management team. We are also undertaking an independent audit of our funds under the component, which will include IIED and Haki Kazi. / 4.4 Climate and Environment Risk / High opportunity and Low risk. The overall objective of the programme is about enabling Tanzania to be better placed to manage claimte and environment risks in key economic sectors and ensure these risks do not undermine the achievement of MDGs. As the project is on track, it will have a significant positive impact on enabling Tanzania to be better placed to manage these risks e.g. screening of investments under the Mkuza, community level adaptation planning, mainstreaming in key climate-sensitive sectors. TCCISP is primarily a TA project with UK-based and international inputs, with associated travel-based carbon impacts. Decision-making on when to use inputs takes account of carbon impact. There has been a move over the past year to use local consultants where at all possible.

5. Value for Money
5.1 Performance on VfM measures / VfM (Economy and Efficiency) is monitored by reference to log-frame targets, programme managements costs and delivery of detailed objectives of contracts tendered through the technical assistance fund. / A majority of targets are rated as green, as described in Section A. Highlights from 2013/14 include official launch of the Zanzibar Climate Change Strategy, preparation of a Roadmap for implementation support for the NCCS and ZCCS, the Agriculture Climate Resilience Plan, and the set-up of three district-level climate finance mechanisms. The programme is also on track to achieve its outcomes in terms of leveraging climate finance and number of people better able to cope with the impact of climate change. In the next year we are looking to scope out support for performance based financial aid to Zanzibar against their Climate Change strategy. The lessons from this programme are already feeding into the development of DFID ICF funding going forward, leveraging a potential additional £110m in climate finance for Tanzania. / The following table, attached in Annex 4, outlines how value for money is being delivered over the past year under the existing contracts, ensuring rates, fees and procurement is undertaken in a competitive manner - Accoutnable grants (one), MoU (two), EFO (one) and direct procurement (two) and use of resource centre PEAKs ( one) and the rational for each. In summary: / We have used least cost delivery mechanisms in the majority of cases through direct procurement following open competition to contract - DPGE Secretariat and Annual Review Inputs. The Resource centre ( PEAKS HTSPE) was used for the Roadmap to finance Climate Change resilience in Tanzania; In this case the PEAKs resource centre provided efficiencies; high quality individual local and international consultants have been sourced in a short time and cost-effective manner and technically it was a stronger bid and also avoided any conflict interest with previous work which has been undertaken by GCAP on climate finance. Additional finance, including from development partners, has been successfully raised in the following cases, DP co-ordination on Climate Change, WB for EFO, Norway for SAGCOT green growth and UNDP on mainstreaming environment and climate change into development planning. For example the pooled funding arrangement for TA climate resilience growth planning in Tanzania succeed in reducing transaction by ensuring EFO is leveraging co-financing from WB on climate finance and agriculture. Start-up times have been minimised as far as possible, however the lack of clarity on contracting process with UK Met Office meant some delays. Finally performance based payments for delivery of climate finance in Zanzibar is to be scoped out with a view to piloting the approach. / Annex 4: / Component Activity Type Value Time Frame Value for Money Additional Comments / £ / 202534-103 Contract - DPGE Secretariat Direct recruitment 24,960 2 September 2013 to / 26 December 2013. / Extended to March 2013 – due to cost savings no cost extension agreed. Direct procurement following open competition. Additional funds leveraged from Finland and Germany to continue funding of DPG-E secretariat following initial funding by DFID. No cost extension allowed time for development i) joint DP retreat to agree priorities and work plan and ii) contracting by Finland. Purpose of position is to reduce transaction costs, improve co-ordination and avoid duplication – all contributing to improvements in vfm and improved aid effectiveness. Completed following cost extension. Work plan for DPG-E developed on climate change, NRM and environment. Long term funding for secretariat also secured. / Contract – PEAKS Roadmap to finance CC resilience in Tanzania PEAKS / Resource centre 52,470 15 January 2014 to / 31 August 2014 Contracting through PEAKs following request for proposals from PEAKs and GCAP, who carried out work on climate funds. PEAKs have team of individual consultants with expertise in required areas incl. strong local consultant. Technically a stronger bid and avoids conflict interest with previous work which has been undertaken by GCAP on climate finance. A new perspective on the issues and lessons from DFID Bangladesh on climate finance. PEAKs added value reducing time in DFID managing four individual consultants and contracts. Roadmap developed with through a consultative process and of good quality – used by GoT and DPs to feed into resource mobilisation for NCCS and ZCCS and climate finance readiness. Time extension to allow for presentation of Roadmap to government (mainland and Zanzibar) in August / September at event funded jointly by WB and DFID under EFO. / 202534-105 EFO - World Bank for TA climate resilience growth planning in Tanzania Contribution Arrangement – WB/DFID Externally Financed Operation 126,000 May 2012 / to / 31 September 2014 (request for extension until December 2014) Direct contracting through EFO with WB based n a set of agreed outputs on i) agriculture action plan with MAFC; ii) urban resilience with PMORALG and iii) climate finance modalities. Technical assistance has been provided and there has been flexibility in responding to requests such as technical support to the GoT climate finance task force. This EFO is leveraging co-financing from both WB and UNDP on climate finance and agriculture. The outputs have fed into the development of new ICF programmes £110m for Tanzania – significant return in investment made under EFO. Regular monthly meeting with WB and consultant leading on this work to monitor progress and outputs. Additional funding for publication and joint WB/DFID event to disseminate outputs. Reduction in transaction costs through pooled financing. Extension requested to December 2014 and additional funding sought (up to £32,500) to allow for professional editing of outputs, publication and joint WB/DFID event on climate finance and delivery of NCCS and ZCCS – presentation of TCCISP supported outputs. / CA/MoU – UNDP on mainstreaming environment and climate change into development planning. Contribution Arrangement – MoU between UNDP and DFID 300,000 30 October 2013 to / 30th September 2014 MoU agreed with UNDP for the delivery of specific outputs on support to VPO and Ministry of Finance on climate finance and implementation of NCCS. UNDP have provided quarterly reports and frequent meeting with UNDP on DP co-ordination on climate finance. Funding providing is supporting to GoT task force on climate finance and development of ZCCS. Over ambitious targets and political economy mean targets on setting climate fund will not be achieved. Set management fee does not provide good value for money, also additionality and attribution of DFID funding at times is also unclear. DFID have delegated responsibility for leading on climate finance to UNDP. MoU for DP co-ordination on CC support to GoT still unsigned – UNDP, WB, Norway and DFID. No further support envisaged beyond September 2014. / 202534-106 Accountable Grant – IIED Promoting climate resilience for dry lands AG 557,167 25 June 2013 to / 25 September 2014 Accountable grant with IIED and new local partner Haki Kazi; ( HK are contracted under AcT and considered low risk); project management costs are 11.5 % of total; measures have been taken to reduce rent costs, monitor fuel usage and use assets available from first phase. Issues around scale up, lesson sharing and long term sustainability are main focus of proposed extension in time and cost until March 2015. This AG is the main output responsible for the delivery of results on climate change KPI1 – impact indicator 2. Outputs from this support are feeding into design of new ICF programme and scale up and additional support to be considered as part of appraisal. IIED looking to also leverage additional DP funds form Irish Aid, EU and BMU to start in Jan 2015. Request for extension in time and cost to March 2015 to deliver additional outputs. / 202534-107 MoU – UK Met Office Capacity development of Tanzania Meteorological Agency (TMA) MOU 300,000 20 February 2014 to / 31 May 2015 Limited guidance on contracting other UK government departments – options set out incl. IFUSE – MoU used by other DFID offices in contracting UK Met office for similar work in other DFID countries Afghanistan, China etc – see note on contracting options. / UK Met office can leverage substantial expertise and institutional knowledge in mentoring relationship with TMA. Output on digitising climate data and information will substantially bring down cost of accessing information both in terms of time, transactions and monetary. Market analysis will also make data and information provided more targeted and appropriate. Delay in contracting due to lack of clarity on contracting process with UK Met Office - MoU / Direct – Consultancy inputs to annual review. Direct local contract 3,601 20th May 2014 to 4th July 2014 Local consultant contracted following open competition, request for 10% inputs and request for consultants through PEAKs. Consultant recruited at short notice as 10% input fell through at the last minute. However consultant was technically good, had good understanding of programme and also as based in Tanzania cost was significantly lower. Has delivered good input to Annual review at short notice. DFID Adviser led on outputs relating to EFO to avoid any conflict of interest. Work completed and output delivered on time and good quality. / Total 1,360,597 / Two direct contracts have been offered during this reporting period. DFID contracted two independent consultants after a competitive process. All direct procurement (DPG-E Secretariat, AR consultancy inputs) have been undertaken through a competitive tender providing assurance on management costs and ability to procure high quality inputs based on previous track record of delivery. Costs have been kept to levels comparable to market rate and lower and contracts are being managed effectively. / The use of the resource centre has been used to provide a comparison with direct procurement and in one instance for the Roadmap, where individual consultants were to be hired it was seen to be better value for money, both in terms quality, time and value. In this case the PEAKs resource centre has provided efficiencies. High quality individual local and international consultants have been sourced in a short time and cost-effective manner, however over the past year we have also looked employ consultants directly to reduce the management feee, where are suitable consutlants available – see above. Absorption of DFID programme management staff time in contract management has reduced by approximately 20% since 2011, mainly due to larger contracts and use of MoU with partners such as WB. Action has been undertaken in an isolated case where a contractor did not adhere to guidelines. For instance, this was picked on the accountable grant with the Agricultural Council of Tanzania (ACT), for the SAGCOT green investment framework ( 2012), DFID withheld 10% of payment until reports were delivered in the in the approved formats. / Capacity building and technical assistance has been delivered effectively through pooled funding arrangements with the World Bank EFO, UNDP and Norway (completed). These have been efficient in delivering a number of relatively small programmes, reducing transaction costs and contributing to donor coordination. However there is a risk with UNDP that their plans are overly ambitious and the resources do not match the level of ambition, we are managing this by tying our support to specific outputs and deliverables but this will need to be tacked in the quarterly reports. Also there are issues of attribution of our funds channelled through UNDP.It is unlikely we will use them as a channel for our funds to support Zanzibar and procure the support directly over the coming year. / UK Met Office have been contracted to provide support through an MoU to Tanzanian Met Agency. The MoU has been agreed with clear deliverables, milestones and outputs and is considered good vfm as UK Met office, bring a high level of technical and insitutitional support which would not be provided by an individual or consultancy form – see options appraisal for contracting UK Met Office approved by DFID Head of Office. DFID signed one accountable grant (£0.55m over 15 months) with IIED for promoting adaptation and climate resilience in Northern Tanzania. Due diligence on IIED was undertaken. / In view of overall performance in delivering log frame objectives and achieving economies in programme management, value for money is judged to be good. The effectiveness of the programme in delivering climate resilience and low carbon growth opportunities in Tanzania cannot be assessed reliably, however the underlying theory of change set out in the Business Case remains valid. The programme can be judged as being efficient and effective, it is £2.8m and its mange objective is to leverage climate finance for Tanzania, which has scaled up form USD 50m in 2010 to over USD 200m in 2013/14. / 5.2 Commercial Improvement and Value for Money / See table, attached in Annex 4, which outlines how value for money has been delivered over the past year under the existing contracts, ensuring rates, fees and procurement is undertaken in a competitive manner - Accountable grants (one), MoU (two), EFO (one) and direct procurement (two) and use of resource centre PEAKs (one) and the rational for each. There has been a shift away from using the PEAKs resource centre to direct procurement, in particular where individual consultants are required as there is a now a good understanding of the market and the skills available. Contracts awarded for engaging technical assistance are mutually agreed upon a maximum figure for all costs of undertaking the consultancies. Payment is made after a successful milestone delivery spelled out in terms of reference. / Signing accountable grants with IIED after a successful submission of proposals and budget; and completion of due diligence of external partners (IIED) assessing their resource capacity to manage, implement and deliver the grant. Funds are released based on findings and recommendations. Reports and regular meetings are used as tools for monitoring of progress and performance throughout the life of the grant agreement to ensure a low cost but high value delivery of outputs. / Memorandum of understanding (MoU) has been agreed upon with multilateral organizations such as UNDP and other UK government agencies /departments (UK Met Office). Processes and procedures of the implementing organisation apply. DFID is monitoring progress through regular meeitngs and review of quarterly financial and narrative progress reports, payment is made against agreed milestones and deliverables. N.B. there is no central guidance on contracting other UK government departments, outside of IFUSE, which is only suitable for short term inputs, the MoU was based on precedecent by DFID Afghanistan and China. / 5.3 Role of project partners / This project is implemented through financial support to government, civil society, multinationals and development partners. Project implementation partners show a clear understanding and committment to value for money. DFID will continue to monitor progress of partners commitment to value for money. / 5.4 Does the project still represent Value for Money : Yes / 5.5 If not, what action will you take? / N/A

6. Conditionality
6.1 Update on specific conditions / There are no conditionalities. Partnership principles do not apply as it is not direct financial aid to government.

7. Conclusions and actions
The TCCISP can provide an important function in creating the enabling environment for Tanzania’s response to climate change. It is broadly on track against indicators and milestones. Most of the intended outcome targets remain valid and appropriate and have already been met – it has been agreed not to change them from the original targets set in 2011, even if they will be exceeded. Minor revisions will be needed as outlined in para 1.1. / As the Programme has developed, the flexible nature has been key to respond and adapt to changes in the political environment as well as the international landscape of climate change planning and finance – especially in countries where adaptation is a priority and where low capacity is present, these processes are relatively new and untested. TCCISP has faced some delivery and timing challenges due to changing Government, DP and DFID priorities, but the initial results from 2013/14 and anticipated milestones toward 2015 are yielding progress. Especially given budgetary constraints of URT/Zanzibar and in the DP community, there is a risk that planning processes, institutions and financial structures that are supported through TCCISP will not be sustained given most are prepared without any guarantee of finance. This is not unique to this programme but is indicative of climate change planning more broadly: with significant ICF resources in the pipeline, DFID is well-placed to take the lessons, evidence and partnerships built through TCCISP and scale these up for more transformation and sustainable action. / Key actions are: / DFID needs to decide on allocating the fund balance of £422,000 by September 2014, to ensure they are effectively used. The annual review recommends: / EFO extension to Dec 2014 and additional resources for editing, publication and high level political event and launch – pending review of detailed budget. / Additional support to IIED/ Haki Kazi to address issues of scale up and sustainability and lesson learning with TASAF and Zanzibar: / Support for ZCCS in developing investment plans and resource mobilisation and scoping out results based financial aid against ZCCS; / Support development of ICF concept notes for mainstreaming in social protection, rural roads and port with TMEA. / DFID needs to review the planned outputs, indicators and milestones for the programme and revise the logical framework. Final logical framework for approval by end July 2014 as part of this annual review see Annex 1 / Dialogue with DPs, GoT and Zanzibar is needed on how the climate change Roadmap is taken forward and orgnaised high level event to share lessons and agree way forward on work that has been undertaken by end Dec 2014. / Awareness is needed to highlight the results that have been achieved in support of implementation of the NCCS and ZCCS with decision-makers as well as broader stakeholders.This can be done through both a high-level dialogue and a stakeholder workshop, by end of October 2014. / Agree way foreward with results adviser on Climate Change portfolio wide evaluation and develop Tors on the basis of the Annex 2 – evaluation questions. / Agree timing of PCR and evidence that needs to be collected to assess delivery against Indicators. Consider extension of TCCISP until September 2015 – as UK Met office work is due to finish at end May 2015, allowing time for the PCR to be undertaken. / DFID to support as part of the programme a programme co-ordianator and technical adviser (SAIC Adviser) who will be within the Ministry of Finance/Vice Presidents Office (70%) providing support to government on climate finace and how to structure support to sectors.

8. Review Process
Initial inputs for the review were provided by an independent consultant contracted directly through a competitive process. The Annual Review was undertaken by the consultant and the DFID Cliamte Change and Environment Adivser and with inputs from the programme officer and cross cutting team in DFID –vfm, commercial, results and evaluation, CC&E and social. There was a consultation process as part of this annual review with GoT (VPO and Finance), implementing partners (including IIED/ Haki Kazi and the UK Met Office), sector ministries ( agriculture, water and PMORALG), Zanzibar and Development Partners. / The final annual review was presented to DFID Tanzania at a meeting chaired by Nick Leader, Governance Team Leader on 26th June 2014, where the assessment and scoring were agreed. The final annual review was submitted for approval to Ros Cooper, Acting Head of DFID Tanzania on 27th June 2014. Approved by Ros on 3 July 2014.