Project Completion Review - Top Sheet

This Top Sheet captures the headlines on the programme performances performance over the course of its lifetime. Teams should attach summary sheets from each annual review over the life of the programme.

Review Date:	March 2016

Title: Tanzania Climate Change Institution Strengthening Programme
Programme Code: 202534	Start Date: July 2011	End Date: December 2015

Summary of Programme Performance
Year	2012	2013	2014	2015	2016
Programme Score	A	A+	A+	A	B
Risk Rating	Medium	Medium	Medium	Medium	Medium

Financial Position
Original Programme Value	£ 2,000,000.00
Extensions/ amendments	In December 2013, following the recommendations from the mid-term review, an additional £800,000 was approved, bringing the total budget from £2 million to £2.8 million. / A no–cost extension was approved in December 2014 (to Dec 2015), in order to complete the following outstanding activities: (i) Evaluability Assessment for Tanzania ICF programmes, providing a baseline for our ICF portfolio moving forward; (ii) provide direct support to Zanzibar through UNDP based on a request from the government to support an investment plan for the Zanzibar Climate Change Strategy (ZCCS); and (iii) recruitment of a programme funded SAIC A2 Climate Change programme adviser.
Log-frame revisions (with dates)	The logframe was updated after the 2013 annual review, and had minor adjustments after the 2014 annual review.
Total programme spend	£ 2,752,547.16

Follow up actions required following closure
- The new Assisting Insitutions and Markets for Resilience (AIM 4 Resilience) programme will take into account lessons learned from TCCISP, and follow a problem-driven approach that builds on existing relationships and programming to design an intervention that leads to transformational change in climate change delivery in Tanzania.
- Given the slow progress on taking forward the National Climate Change Strategy (NCCS), and the issue of access to climate finance; it is recommended that AIM 4 Resilience takes this forward as a priority and explore alternative, innovative options to resolve this during the design phase.
- Under TCCISP, an evaluability assessment of DFID’s ICF portfolio in Tanzania was undertaken, which was intended to provide a basis and methodology for developing a baseline and M&E framework for DFID Tanzania’s entire ICF portfolio. Unfortunately, the outcome of the evaluability study was not of the desired quality, and therefore, the propsed Monitoring, Evaluation and Learning (MEL) function under AIM 4 Resilience will take this work forward.
- Drawing on the lessons learnt from TCCISP, AIM 4 Resilience will also support knowledge management and learning across the DFID Tanzania ICF portfolio, focusing on i) performance monitoring and reporting; ii) supporting evaluations; and iii) working with public stakeholders on to support knowledge management and learning. It should also look at creative ways to monitor the programme; for example using a systems or network approach to capture the change effected by this institutional strengthening programme.
A. Introduction and Context (1 page)

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-202534/documents
DevTracker Link to Log frame:

Outline of programme and what it has achieved
The Tanzania Climate Change Institutional Strengthening Programme (TCCISP) was a £2.8 million, 4.5 year (April 2011 to December 2015) programme, aimed at supporting the United Republic of Tanzania (URT) including Zanzibar build core institutional capacity to respond to climate change and leverage climate finance for Tanzania. The programme has complemented other climate change work funded by DFID Tanzania, particularly support to civil society and the private sector. The last annual review was conducted in June 2015[1], at which point, the majority of the activities under the programme had already come to an end.
[1] TCCISP 2015 Annual Review, available on Quest (5036075).

The intended impact of TCCISP was for Tanzania to achieve of its Millennium Development Goals (MDGs) though better management of climate change risks and opportunities. The intended outcome was Tanzania to access climate finance and use it effectively to address climate change and its impact through promoting resilience and low carbon sustainable growth.

The programme consisted of the following components:
Building climate change adaptation and resilience into planning and budgets, including:
- Co-financing with UNDP for mainstreaming of environment and climate change adaptation in the implementation of national policies and development plans. The project is under UNDAP to support institutional strengthening in Vice President’s Office and Ministry of Finance and develop a climate finance mechanism, working in mainland and Zanzibar.
- Technical assistance for for “Climate-Resilient Growth Planning” in Tanzania, in partnership with the World Bank and the Nordic Development Fund.
- Technical support to mainstreaming resilience into work on social protection, rural roads and the port and initial scoping for new International Climate Fund (ICF) programming in Tanzania. As well as funding studies such as the economics of climate change, political economy of climate change, UK REDD Tanzania scoping study, climate screening the National Development Plan and Mkuza and overall monitoring of the programme.
- Promoting adaptation and climate resilience to droughts in the budgeting and planning process in the districts of Longido, Monduli and Ngorongoro in northern Tanzania. Also increasing their capability to manage a devolved ‘climate adaptation fund’ at district level. The project was implemented by the International Institute for Environment and Development (IIED) and Haki Kazi.
- Capacity development for the Tanzania Metrological Agency (TMA) to improve evidence based decision-making based on targeted, appropriate and accessible climate information and data. The UK Met Office supported TMA to make climate data and information more accessible to key climate sensitive sectors and Ministries, such as agriculture and health and to private sector investors in energy and agriculture.
- Green Growth Strategy for the Southern Agricultural Growth Corridor of Tanzania[2].
  [2] SAGCOT Green Growth Strategy, August 2012. Available here: http://www.sagcot.com/uploads/media/SAGCOT_Greenprint.pdf.

TCCISP went some way in supporting the climate change agenda to be embedded into Government planning and decision making, notably through technical analysis that fed into government strategies/plans, such as the National Climate Change Strategy, Zanzibar Climate Change Strategy, Agriculture Climate Resilience Plan, and district adaptation plans for Longido, Monduli and Ngorongoro. The programme has also helped to influence Development Partners to engage more in climate change in Tanzania. However, as DFID Tanzania itself expanded its climate change portfolio during the lifetime of TCCISP (without a corresponding increase in DFID staff capacity), the ability of TCCISP to facilitate leadership and a strong government response to climate change was stretched. As such, while the programme has been effective at producing high quality technical analysis addressing key knowledge gaps and supporting the development of new government strategies on climate change, there has been less successful at driving effective implementation and operationalisation of the strategies. The new AIM 4 Resilience programme[3] will draw on the valuable lessons learnt from TCCISP, leveraging DFID’s early investment, to support the next phase of institutional and market strengthening on climate change, building on what has worked well and learning from what hasn’t.
[3] AIM 4 Resilience Business Case available on DevTracker: https://devtracker.dfid.gov.uk/projects/GB-1-204364/documents.

Some of the key findings from the programme are:

- Activities that support solutions to clear problems with pragmatic technical assistance have delivered the most concrete results and could have a significant impact if brought to scale. Activities such as the work at the district level, engagement with TMA, planning in Zanzibar, and sector planning for agriculture and urbanisation, have had positive feedback from the beneficiary institutions, and direct requests for further engagement. All of these activities have taken the time to establish good working relationships and trust between implementation partners and institutions, but despite time delays this has delivered results and provided some valuable entry points for the next phase of climate change institutional strengthening support.
- Several institutional bottlenecks identified at the onset of TCCISP still persist. These provide clear opportunities for further enegangement and support for future climate change programming. In mainland Tanzania, there is a lack of political will and high level leadership around driving the climate change agenda forward. There is awareness that climate change is a risk that urgently needs to be addressed from the highest levels of government, development partners, and non-state actors. However, the key institutional actors, namely in the Vice President’s Office Department of Environment and Ministry of Finance, that are needed to make decisions, lead on establishing a coordinated effort across government, and taking forward Tanzania’s National Climate Change Strategy, have not managed to do so. The new AIM 4 Resilience programme will try to harness this as an opportunity, and it will continue institutional strengthening with a particular focus on the VPO to remove the bottlenecks.
- Support for planning processes need to be either followed by implementation support or a clearer exit strategy. Sectors and local governments have made significant gains in learning how to plan and take pride in the frameworks they have developed, but still lack the technical ability to leverage resources and take plans forward. AIM 4 Resilience will be taking forward a number of the workstreams initiated by TCCISP, with support for implementation of action plans, strategies, etc.
- There are benefits to programmes with multiple components that can be flexible and responsive to changing political and economic drivers. For example, Zanzibar has strong political will at the highest levels, and good coordination between planning, finance, and environment institutions, however resources to take forward next steps have been lacking. With multiple components under TCCISP, resoucres could be shifted to respond to opportunities. AIM 4 Resilience is being designed in a similar matter, so the programme can quickly adapt and be responsive to opportunities.
- However, these can also require heavy inputs from DFID to manage effectively. The 2013 mid-term review (MTR) suggested that, while a small spending programme, TCCISP’s management and administrative load is high. With a growing trend of reduced administration resources, it is likely that complex, multi-component, multi-delivery partner programmes such as TCCISP, would be hard pressed to be considered value for money.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Overall Outcome Assessment
The intended outcome of the programme was that “Tanzania accesses climate finance and uses it effectively to support climate change resilience and low carbon sustainable growth”. With respect to the outcome indicators and targets, the programme met one of the outcome indicators, but the evidence is insufficient to suggest the second outcome indicator has been met. Therefore, the outcome assessment is B: the programme moderately did not met the intended outcome targets.

Outcome Indicator 1: International climate change funds secured (from multi-lateral and bilateral sources). Target by December 2015: US$300m

Tanzania has been successful at accessing climate finance, with this target exceeded in 2014, as reported in the Juny 2014 Annual Review. It is estimated that climate finance secured is now around US$400m (including DFID’s most recent new ICF commitments in Tanzania). However, this climate finance has not been reflected in the national budget.

Tanzania has a strong pipeline of technical assistance and climate investments available over at least the next five years. Assessing the effectiveness of climate finance in Tanzania, however, remains a challenge. There have been a number of assessments of how much climate finance Tanzania has accessed[4],[5], but there have not be any assessments of the outcomes or impacts from this finance for adaptation or low-carbon growth. Going forward, as the recently appointed Tanzanian Ministers and their Departments settle into their roles, DFID and other Development Partners will need to work closely with the Government to ensure effective use of the climate finance accessed by Tanzania, as well as government’s own spending on climate change, in the absence of investment plans and systems in place to track finance and outcomes of climate spend. Addressing these challenges will be a core focus of the new AIM 4 Resilience programme – particularly in developing effective methodologies to measure and track climate spend.
[4] Climate Finance in Tanzania: what is recorded in the national budget? (2014) Neil Bird, ODI and Pius Yanda, University of Dar es Salaam. Available: http://www.odi.org/publications/8207-climate-finance-tanzania-recorded-national-budget.
[5] Understanding Climate Finance Readiness Needs in Tanzania (2013) GIZ, ODI, Africa Climate Finance Hub. Available: https://www.giz.de/expertise/downloads/giz2013-en-climate-finance-readiness-tanzania.pdf.

Outcome Indicator 2: Government actions are consistent with the Climate Change Strategy in United Republic of Tanzania and Zanzibar. Target by December 2015: More than 50% of Government spending on climate change is clearly consistent with the National Climate Change Strategy.

While a National Climate Change Strategy[6], a Zanzibar Climate Change Strategy[7] and an Agriculture sector action plan[8] have been developed, Government has struggled to implement and operationalise these. The next step to coordinate and align available climate spend with the NCCS remains a challenge. One reason for this bottleneck is securing an agreed approach across Government on where climate finance should be ultimately managed by (Ministry of Finance, Department of Environment, Sector Ministries, etc.). The National Strategy itself does not currently have targets or priorities, and only agriculture sector has to date developed a sector action plan. As such, there is insurfficient evidence available at this time to determine whether 50% of Government spending on climate change is clearly consistent with National Strategy.
[6] Tanzania National Climate Change Strategy (2012). Available: http://tanzania.um.dk/en/~/media/Tanzania/Documents/Environment/TANZANIA%20CLIMATE%20CHANGE%20STRATEGY/TANZANIA%20CLIMATE%20CHANGE%20STRATEGY.pdf.
[7] Zanzibar Climate Change Stategy (2013). Available: http://www.paulwatkiss.co.uk/newimagesanddocs/Zanzibar%20SummaryLR%20draft%20final.pdf.
[8] Tanzania Agriculture Climate Resilience Plan (2014). Available: http://www.kilimo.go.tz/publications/english%20docs/ACRP_TANZANIA_ENDORSED.pdf.

Output Score and Description
The programme output score is assessed as: B – outputs moderately did not expectation. Of the four outputs, two met their targets and two moderately did not met their targets. More detail for each is provided in the output scoring below. In the lifetime of the programme, good progress was made against many of the milestones, especially with respect to more tangible activities such as:

- Development and launch of the National Climate Change Strategy and Zanzibar Climate Change Strategy and Action Plan.
- Establishing district level climate funds in three districts; data rescue in the Tanzanian Metrological Agency; and launching the Agriculture Climate Resilience Plan, Tanzania’s first sector action plan in line with the National Climate Change Strategy.
- Over the lifetime of TCCISP, Tanzania began leveraging significant additional climate finance resources, for example, through DFID ICF support, but also potential forthcoming support from the Green Climate Fund (GCF).

While the majority of the output indicators have been achieved, much of the impact of these achievements is yet to be realised, since implementation of the various strategies and action plans has been slow. Further support is needed to work with government to ensure effective strategy implementation (e.g. of the National Climate Change Strategy, the Agriculture Climate Resilience Plan, etc.) continues, including the development of investment plans; deciding who will manage climate finance; and defining institutional roles and responsibilities. Securing high-level leadership to drive institutional change and drive forward the climate change agenda is still lacking.

Lessons and how these have been shared
Some of the key challenges and lessons learnt from the programme are:

Government buy-in and leadership: TCCISP, as a whole, was not designed in collaboration with the Tanzanian government, but as a result of needs identified through DFID’s own analysis. While Government speaks highly of DFID’s work in this agenda and of a number of the outputs supported by TCCISP, a large number of institutional bottlenecks still persist restricting the impact the programme might have had otherwise. There is awareness that climate change is a risk that urgently needs to be addressed across the government, but there remains low political will, little coordination on roles and responsibilities across Ministeries, and inadequate high-level leadership to drive the climate change agenda forward. The design and implementation of AIM 4 Resilience will need to explore a variety of approaches to fostering this commitment and political will on climate change. This could involve changing the narrative around climate change, particularly reflecting the priorities of the new President and his government, drawing out the opportunities for Tanzania (e.g. significant low carbon energy resources), rather than the negative threats and impacts.

Demand pull versus supply push: Under TCCISP there was (certainly initially) a tendency to provide support for knowledge products. This was particularly important initially since little was known about the impacts of climate change in Tanzania. The 2013 mid-term review (MTR) suggested that the programme had been focusing on the technical aspects of institution building rather than changes in attitudes and behaviours; a more process based approach. While what has been achieved by the programme is significant, it is important that any future programme in this area be designed to balance and respond to demands of partner institution to enhance the chances of success and impact of the programme. The design phase of AIM 4 Resilience will be crucial in indentifying and understanding the relevant demands across the government and other relavant stakeholders.

Highly ambitious in a new area – not a strong theory of change: The MTR assessed TCCISP as being overly ambitious in what it might be able to achieve by the end of the programme. For example, TCCISP envisaged Tanzania moving within two years from having no climate change strategy at all to being able to plan and budget for the response in key line ministries, and that TCCISP’s small £2.8m over 4.5 years could be considered for contributing to associated impacts. These expectations were unrealistically ambitious. One concern, raised in the MTR, was that the theory of change in the original business case could have been strengthened – the logical flow from inputs through outputs to outcomes was not clearly established. In addition, as the original business case makes clear, it also depended upon a series of ‘critical assumptions’, not least political commitment and that ‘GoT is able to absorb the envisaged economic and technical capacity, and that there is continued momentum to pursue the climate change agenda’, which, as described in the first bullet, has not proven to be the case during the lifetime of TCCISP. These important lessons and critical assumptions need to be reviewed in the design phase of AIM 4 Resilience, such that a clear and realistic theory of change underpins the programme from the beginning and that assumptions reflect the reality of the current political context.

Lack of coordination amongst Development Partners: The programme made a lot of effort to coordinate the activities and messages on climate change from the various Development Partners, particularly at the beginning of the programme, when the A2 Climate Change Adviser in DFID Tanzania was considered a Programme Funded Adivser who was to spend 60% of their time on the successful implementation of TCCISP. However, during 2012, to reflect new corporate guidance and build DFID Tanzania’s portfolio of programmes on climate change, this role was no longer funded directly by TCCISP but directed more effort to design and deliver new, ambitious ICF programmes in Tanzania. As such, the strong leadership that DFID had provided to the Development Partners Group on Environment (DPGE), notably the sub-group on climate change, diminised. In addition, other DPs facing their own central corporate priorities have had limited capacity to take on this role. AIM 4 Resilience will revive the climate change sub-group through support to the DPGE Secretariat and a strong DFID role through the new SAIC A2 Climate Change Adviser leading on institutional strengthening on climate change for DFID.

Lack of strong civil society advocacy: The lack of strong civil society advocacy on climate change issues has indirectly impacted on the performance of TCCISP. Without a strong civil society voice holding government accountable, there is less pressure on government to act and show leadership on climate change issues. Climate change was not a campaign issue in the recent elections in October 2015, and has not featured prominently in the new governments priorities. In addition, TCCISP did not have significant advocacy element, as the programme was considered a compliment to another DFID programme on Accountability in Tanzania (AcT). However, lessons learned from the programme could have been more effectively communicated with civil society and AcT partners. The Monitoring, Evaluation and Learning function in AIM 4 Resilience should explore creative ways to capture and share outputs from the programme with a wide audience, including materials for awareness raising and advocacy.

Nascent private sector markets: Finally, participation of the private sector in the climate change agenda in Tanzania has been circumspect. Most activity to date is in the off-grid household solar market. While TCCISP was not set up to encourage or promote private sector involvement in climate change mitigation or adaptation, it has been recognised that there is a wide space for private sector to engage in climate change, for both mitigation and adaptation. AIM 4 Resilience will harness this opportunity to incentivise more private sector investment, through establishing a facility to encourage a variety of private sector players to engage in the agenda. This is likely to also have positive impacts on boosting political will and engagement in the agenda, and could draw on the strong role DFID has been playing on supporting innovation in Tanzania through the Human Development Innovation Fund.

## C: DETAILED OUTPUT SCORING (1 page per output)
Output Title	Comprehensive climate change strategy in place, including adaptation and low carbon, with budget allocation and being effectively delivered at sector and district level
Output number per LF		1	Output Score	B
Risk:		Medium	Impact weighting (%):	35%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicators	Target	Progress
1.1: National climate change strategies (URT and Zanzibar) in place.	Planning and resource mobilisation takes place in accordance with national strategy including priority sectors identified in NCCS and ZCCS.	Target moderately not met. / URT Climate Change Strategy developed in 2012. No Investment Plan or Action Plan has been developed to enable resource mobilisation. / Progress is further ahead in Zanzibar with the Zanzibar Climate Change Strategy and Investment Plan developed in 2015, due to be finalised in 2016. However, resource mobilisation has not begun.
1.2: Climate change plans developed in sector ministries identified as priorities by URT/Zanzibar and for GoT economic priorities.	Three key economic sectors have climate change strategies and action plans in line with climate change strategy (URT and Zanzibar).	Target moderately not met. / SAGCOT Green Growth strategy drafted in 2012 - “Greenprint”. This is currently available on SAGCOT website, as a draft, open to feedback. / One sector climate change strategy was developed in 2014 – the Agriculture Sector Climate Resilience Plan (2014 – 2019) developed. Water Plan is being developed. / World Bank supported much work on urbanisation and climate change – which has led to a new DFID-WB Urban Resilience programme.
1.3: URT and Zanzibar have agreed way forward in mobilisation of climate finance resources for support to NCCS and ZCCS, including choice of transparent climate finance modality.	URT and Zanzibar Governments have agreed roadmap for climate finance and resource mobilisation by mid 2015.	Target moderately not met. / Feasibility study on options for financing was not carried out. / Climate finance mechanisms developed for both mainland and Zanzibar (2015), but not yet formally approved by GoT. / The road map for climate finance and resource mobilisation plan for Zanzibar was drafted (2015), but not yet approved by the VPO and MoF.

Key Points
While there has been progress and support to the development of plans and strategies, none are considered fully operational, and therefore, none of the Output 1 indicator targets for the end of the programme can be considred to have been met. Progress in these areas faces persistent coordination challenges; slow pace of decision making and other factors that lead to institutional inertia. To address these challenges and continue progess and implementation of the strategies and action plans, a high level dialogue and agreement is needed on these matters between VPO, MoF, PO-RALG and other relevant ministries. How to address these challenges by facilitating dialogue and strong relationships between the relevant ministeries will need to be considered by AIM 4 Resilience during the design phase, drawing on the lessons described earlier in this report.

Summary of responses to issues raised in previous annual reviews (where relevant)
As reported in the most recent annual review (June 2015), many of the issues raised in the past reviews have either been responded to during the life of TCCISP or are being taken forward under the new AIM 4 Resilience programme. In particular, AIM 4 Resilience aims to develop a tracking system for climate finance, and provide further support for institutional strengethning to implement of sector and district level action plans, and the Zanzibar climate strategy.

Recommendations for future programmes
- Continuously review timeframes for achievement of output targerts. Often implementation of strategies and action plans takes longer than the drafting of the plans themselves. Be cautious not to be overly ambitious about what can be achieved in terms of implementation within a given timeframe, and ensure output targets reflect the current political context.
- Effective facilitation of dialogue between government institutions is required for emerging and cross-cutting issues, such as climate change. Support for facilitation of dialogue is crucial, particularly identifying and fostering strong relationships between key personnel in Government with diverse remits. This could include convening a high-level meeting to present the findings of the climate finance policy note and chart a way forward on making key decisions.
Where possible, systematising processes for development of action plans could help other sectors to undertake this activity. Lessons should be learnt from the agriculture and water sectors who have undertaken the development of their own climate change action plans.

Output Title	GoT and development partner investments and expenditure is climate smart
Output number per LF		2	Output Score	B
Risk:		Low	Impact weighting (%):	20%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicators	Target	Progress
2.1: Proportion of DFID (and development partner) spend that is climate smart.	Less than 50% of DFID spend is at risk from climate change.	Target moderately not met. / Development of new ‘mainstreamed’ ICF programmes has meant that climate is considered in a broad variety of DFID Tanzania priority areas such as social protection, urbanisation, accountability and governance, rural roads, and agriculture. Other sectors being considered are education and health. In FY 2015/16 climate spend was around 20% of DFID Tanzania entire spend.
2.2: Proportion of GoT budget that is climate smart.	Climate screening of Tanzania’s development strategies (e.g. MKUKUTAII, 5 Year Development Plan and Long-Term Prosperity Plan) and the Government Budget Support (GBS) undertaken in URT by end 2014. / All new investments in URT screened by end of 2015 (as part of Environmental Impact Assessments).	Target modetately not met. / 2014 screening was completed and all new investments should assess climate impacts through ESIA - though unlikely that this happens in practice beyond the very large investments – e.g. mining, energy, etc. / Zanzibar is also believed to be screening investments as part of Mkuza implementation.

Key Points
There is insufficient evidence available to suggest that Output 2 targets have been met. However, positive steps and achievements have been made, such as:
- DFID Tanzania has made significant progress in ensuring spend is climate smart over the past five years. DFID Tanzania has one of the largest (in spend) and broadest (across sectors) climate change portfolio of all DFID bilateral partners.
- A climate public expenditure review was undertaken by ODI in 2013 and described in the 2014 annual review. This analysis showed that climate change activities had grown steadily as a proportion of the national budget from 2009–2013, yet most of these activities, while considered climate smart, are only marginally so.
- In Zanzibar, the Planning Commission has implemented an early climate risk screening system, which is advancing the mainstreaming of climate change into the planning process. This is also consistent with the ZCCS.
- The Environment and Social Impact Assessment (ESIA) is a legal requirement for all bills, policies, plans and programmes that may impact the management, conservation and enhancement of the environment or sustainable natural resources management. However, while ESIAs should screen for climate change, neither the outcome nor impact of this requirement have been assessed. It has been suggested that the focus is often more on large energy, mineral and water related investments, and not all projects receive a thorough ESIA with climate change assessments.

Summary of responses to issues raised in previous annual reviews (where relevant)
During the lifetime of TCCISP, DFID Tanzania built a strong climate change portfolio, covering a number of key sectors, including rural roads, port infrastructure, civil society accountability programme and social protection (responding to a recommendation in the 2014 annual review). However, progress on these programmes has been slower than anticipated due to staff changes in DFID Tanzania during the second half of 2015. Issues relating to the challenges in assessing and evaluating climate spend are to be taken forward under AIM 4 Resilience’s Monitoring, Evaluation and Learning Unit. More details on this are in the Monitoring and Evaluation section of this report (Section H).

Recommendations for future programmes
Ensure programme design includes strong approaches to data collection and results monitoring. A number of indicators for TCCISP have proven difficult to measure and monitor due to inadequate data collection and methodologies for analysis (e.g. what can be assessed as “climate smart” expenditure). As a result, a Monitoring, Evaluation and Learning Unit has been developed as a core component under AIM 4 Resilience.
- Consider meaningful indicators for measuring success against indicators. Ensuring projects screen for climate change through ESIAs is good practice, but its utility as an indicator for climate smart budget spend needs examination.
- While there has been some noteworthy success, more support is needed in both URT and Zanzibar. Additional tools and capacity are needed in the Planning Commission and Department of Environment.

Output Title	Improved aid effectiveness through a comprehensive framework for development partner support in Tanzania on climate change
Output number per LF		3	Output Score	B
Risk:		Medium	Impact weighting (%):	10%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator	Target	Progress
3.1: Increased proportion of Development Partner (DP) spend in line with DP climate change framework (and National CC Strategy)	At least 50% of climate change funds mobilised are in support of NCCS and ZCCS by end 2015.	Target moderately not met. / Previous annual reviews suggest that DP commitments on climate change have increased. However, there is no standard guideline to determine what is “climate spend” and no system for assessing it, so the mapping exercises are likely to remain ad hoc and yield inconsistent results. / DP climate change framework does not exist. Roadmap developed for NCCS but next steps not yet agreed. ZCCS roadmap developed, alongside investment plan (supported through UNDP).

Key Points
Given the lack of accurate data and methodologies to measure this indicator, there is insufficient evidence available to suggest this output target has been met.

The output largely focuses on the performance of Development Partners support to Tanzania on climate change, to more effectively direct climate spend toward alignment with the NCCS and ZCCS. Both the 2013 and 2014 annual reviews highlighted significant challenges in measuring this and delivering results, as it is difficult for DPs to harmonise activities, due to variations in procedures (including central or regional DP programmes) and timeframes. As described previously, DFID was considered the leader of the DPs on climate change at the start of TCCISP (driven by the role of DFID Climate Change Adviser being tied largely to the delivery of the programme), however this set-up changed in 2012 when DFID staff resources were restructured to focus more on expanding DFID’s climate change portfolio of programmes. Leadership and coordination across the DP group then waned.

In addition,the 2015 target that 50% of DP spending on climate change is clearly consistent with the National Strategy was destined to be a challenge in the lead-up to the end of TCCISP, given the national strategy does not yet have targets or priorities, and only one (agriculture) sector to date has developed and published a sector resilience plan. Moreover, this was perhaps an unrealistical assumption that the £2.8m TCCISP programme could influence decisions over 50% of DP’s climate spend. This may have been more appropriate as a outcome indicator, alongside development of methodologies for measuring and monitoring this figure.

Summary of responses to issues raised in previous annual reviews (where relevant)
The recommended improvements on climate change coordination highlighted in the 2014 annaul review, which included: revision of milestone on DP climate funding; reviving climate change coordination among DPs; facilitating the discussion of climate finance tracking system among DPs and government; and discussion on a systematic approach to climate change planning and finance tracking, were not realised in 2015 due to other competing priorities for the DFID Tanzania Climate Change Adviser, who was no longer directly funded under TCCISP, but was shifted to be responsible for designing and delivering a new, large climate change portfolio.

Recommendations for future programmes
- DFID should reclaim its leadership among Development Partners by re-engaging in the Development Partners Group on Environment (DPGE) – this should include reviving the climate change subgroup in the DPGE and developing an annual work programme and priorities for the subgroup. Under AIM 4 Resilience, DFID will provide support to the DPGE secretariat for the around two years.
- More coordination is needed amongst Development Partners and the Government to ensure consistency in the approach to assessing ‘climate spend’. This should start with a marker for international climate finance rather than attempt to track “climate-related” expenditures, which could be inaccurate and overly complex. In tracking dedicated climate finance, the URT and DPs can be in a better position to assess outcomes of finance intended to have additionality for climate resilience. The focus thus far on climate finance has been focused on volume rather than outcomes.

Output Title	Strengthening the data and evidence base for decision making around climate change spending
Output number per LF		4	Output Score	A
Risk:		Medium	Impact weighting (%):	35%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicators	Target	Progress
4.1: District climate change programming funding mechanisms piloted in at least 5 districts that can be taken to scale by end of project	At least 3 districts have demonstrated successful approach supporting climate change response activities and is fed into national level decision-making/evidence on climate finance by end 2014. Long term support identified for scale up by early 2015.	Target met. / IIED have developed climate adaptation plans for three districts (Longido, Monduli and Ngorongoro), and shared lessons on ASALs work with DP and GoT. / Support for scaling up this work to 15 districts has been ringfenced under AIM 4 Resilience.
4.2: Government and donors using improved evidence base for decision-making in climate change response investments	Studies feeding into NCCS plans in URT and into ZCCS for Zanzibar to ensure evidence based planning and decision-making by beg 2015.	Target met. / New DFID programmes have drawn heavily from evidence base developed under TCCISP, such as the political economy and economics of climate change (which fed into development of NCCS). / Study launched and shared with VPO, MoFEA and PoPC. Request form Zanzibar for similar study.
4.3: Improved collection, storage and use of climate data	Accessible digested archive for climate data in place and protocol for use established by 2015 information products developed by TMA for use by two line ministries to support decision making.	Target moderately exceeded. / Climate data has been organised, digitisation is ongoing. / Project is having highly positive impact on efficiency and effectiveness of TMA services. / TMA has engaged with multiple ministeries including Ag, Water and local districts. / Support for scaling up this work has been ringfenced under AIM 4 Resilience and was launched in January 2015.

Key Points
Out of the TCCISP activities, Output 4 has resulted in the most tangible impacts on strengthening the targeted institutions (district, sector, and coordinating government agencies) and has resulted in a number of valuable workstreams to take forward, under AIM 4 Resilience. The positive results under Output 4 demonstrate the value-added of sustained, practical engagement on an individual level with institutions. This has worked very effectively with both the district-level programme on adaptation implemented by IIED and Haki Kazi (Indicator 4.1), as well as the UK Met Office programme with the Tanzania Meteorological Agency (Indicator 4.3). Studies and planning, such as activities undertaken through the World Bank (e.g. on urban resilience), have been time-intensive but achieved strong buy-in from Government in part due to close collaboration and up-front identification of clear entry-points where there was demand.

Summary of responses to issues raised in previous annual reviews (where relevant)
No outstanding issues remained following the most recent annual review in June 2015.

Recommendations for future programmes
While some of the activites undertaken under this output could be considered ad hoc, many have been significantly valuable to raising the profile of climate change in Tanzania across a variety of stakeholders. Future programmes should consider how to have a similar ability to respond to needs and opportunities through support to ad hoc studies or pilot projects. The design phase for AIM 4 Resilience should explore such options.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Aggregate Financial Performance
The original budget of the programme was £2 million, which was increased to £2.8 million after the 2013 annual review recommended additional funds to cover the programme’s expanding commitments. As of March 2016, the programme’s total spend is £2,752,547 with a balance of £47,253.29 representing 98% spend for the duration of the programme.

The remaining balance of £47,253 will cover commitment of approximately £30,000 to pay for the outstanding costs of the ICF portfolio evaluability assessment consultancy (June-July 2015). See Table 1 in Annex 1 for the total budget for each TCCISP component, budget allocation, actual spend, and percentage spend as at 23 March 2016. The contracts active during the past year include accountable grants (1), MoU (2), and EFO (1). All of these are continuations of work in prior years, and no new contracts have been signed.

Since the last annual review in June 2015, all activities under the EFO with the World bank have been completed and the EFO closed. A no-cost extension until May 2015 was granted to IIED/Haki Kazi to continue the district-level work to set up local climate funds and extend the programme to Zanzibar. This has also spent all of its funds and officially closed under TCCISP. Disbursements under the UK Met MoU have been completed and this activity under TCCISP has also closed.

As at 23 March 2016, programme spend is 98% of the total allocated budget. No new contracts have been signed since the last annual review (in June 2015), and the last two pieces of work - the Zanzibar investment plan (through UNDP) and the ICF portfolio evaluability study (contracted by DFID Tanzania directly) – was contracted and completed. The costs for covering the new A2 SAIC Climate Change Adviser, originally covered by TCCISP, has been exhausted and is currently being charged under the new AIM 4 Resilience programme.

Key cost drivers and performance
See Tables 2 and 3 in Annex 1 for summaries of the key cost drivers under TCCISP. Project resources have been largely concentrated in Output 4, at over 50% of total programme spend (Table 3). The largest activity has been support to adaptation in drylands, which combined support to Tanzania Natural Resource Forum (TNRF) early in TCCISP and the IIED work on district-level planning. While the resources have been substantial, these activities have consistently scored well and delivered on milestones in the 2014 and 2015 annual reviews. The UK Met project with TMA is also among the larger costs (£300,000) but has also delivered. Neither of these activities were planned or prioritised in the Business Case, which could be viewed as either a success of having a flexible fund that can be targeted where there is demand and buy-in, or as a reason why other outputs have suffered, as a result of insufficient resources due to directing most to Output 4.

In terms of the type of activities supported (Table 2), most spend on deliverable-based activities (as opposed to administrative expenses) has been concentrated on direct technical assistance (e.g. IIED, UK Met, World Bank EFO, and UNDP). This has been a shift after the mid-term review point in 2013, where more than one third of spend was on technical/analytical work intended to trigger demand from Government. Results from this technical assistance have been mixed: whereas support to the UK Met for TMA has performed well and delivered in a short period of time (about 18 months), the cost is equivalent to the UNDP MoU which has struggled to deliver against milestones (both activities at £300,000). The World Bank EFO was much more modest compared to other engagements of similar duration (£156,000 over approximately 2.25 years), and delivered three large pieces of TA.

VfM performance compared to the original VfM proposition in the business case
VfM (Economy and Efficiency) is monitored by reference to logframe targets, programme management costs and delivery of detailed objectives of contracts tendered through the technical assistance fund. The programme emphasised several VfM principles in the original Business Case to use least cost delivery mechanisms and reduce transaction costs through exploiting existing relationships and pooled funding arrangements with other Development Partners.

The DP funding arrangements with UNDP (MoU) and World Bank (EFO) were intended to reduce transaction costs of direct procurement and improve donor coordination. They have delivered several achievements in line with the logframe including strong technical analysis on climate institutions and finance, and sector planning in the agriculture and urban sectors. However, performance of these arrangements has been mixed. The UNDP MoU has struggled to deliver on support to MoF and VPO to drive implementation of the NCCS. Channeling funds through the World Bank provided questionable value-added, with significant time delays and the EFO proving an inflexible instrument ill-suited to the more flexible TA intended by TCCISP. While having a dedicated coordinator managed by the World Bank allowed for close engagement with Government and other stakeholders, as opposed to a contracting a firm, this also resulted in lack of DFID control over priorities and time management and contributed to time delays.

Efficiency at times has been a challenge. Despite the economy of arrangements such as the MoU and EFO, each requires coordination and management which have been a challenge to keep up with given the number of contracts and limited programme management capacity within DFID. However these are a relatively small proportion of the total budget. The larger activities, for example under Output 4 which represents over one third of the total budget, have concrete outputs and have been met in terms of budget and logframe targets.

The effectiveness of the programme in delivering climate resilience and low carbon growth opportunities in Tanzania cannot be assessed reliably, however the underlying theory of change set out in the Business Case remains valid (with the exception of the area of political will and leadership which received less attention than was needed to support progress). The programme as a whole has supported Tanzania to increase its access to climate finance (with an increase in DP climate funding over the course of the programme). However, the programme’s effectiveness at driving greater accountability on climate finance and making investment decisions remains questionable, and the risks and bottlenecks described in the 2011 Business Case have persisted per the mid-term review and annual reviews, and analytical work financed under TCCISP (i.e. Roadmap, WB Climate Finance Policy Note, Political Economy study).

Assessment of whether the programme continues to represent value for money
TCCISP represented good VfM in terms of leveraging climate finance. In addition to the points above, TCCISP was a modest £2.8 million investment which influenced around £200 million in new UK ICF financing in Tanzania. This also has had positive spillovers at the district level, where climate funds set up in pilot districts will receive national budget resources, as well as other development partner programmes including the World Bank’s US$800 million urban portfolio and the second Agriculture Sector Development Programme (ASDP). While as-yet unquantified, TMA has achieved efficiency gains in providing climate services. As described above, it is too early to determine the effectiveness of this finance to deliver on-the-ground results for Tanzania.

Quality of financial management
Disbursements for the four main activities implemented in 2014/15 (UNDP, World Bank, IIED, and UK Met) have been mixed. Both UNDP and World Bank were slow to disburse, and modifications to the World Bank EFO (time and cost extensions) resulted in a protracted modification to the EFO Legal Agreement between the Bank and DFID. Although, UNDP has also been slow to disburse under the MoU, the additional funds for Zanzibar were disbursed quickly – these were responding to specific demand from Government of Zanzibar. IIED has submitted final narrative and financial report including the audit report. IIED has to reimburse DFID a total of £8,520 (£1,374 – recovery from overpayment during last disbursement; order no. 821520 and £7,146 – unspent fund from completed project; order no. 830350). UNDP still has a balance of around £32,000 (committed funds). UNDP has completed auditing the project in February 2016, but the audit report has not been shared with DFID. Audit report for UK Met also still outstanding – Project team to follow up on the reimbursement from IIED and audit reports from UK Met and UNDP. No financial reports are required under the World Bank EFO.

Date of last narrative financial report	IIED – March 2015
Date of last audited annual statement	IIED – July 2015

E: RISK (½ page)

Quality of risk management over the life of the programme
As TCCISP was delivered through a number of components with different implementing partners, overall programme risks were predominantely managed by DFID Tanzania, notably the Climate Change Adviser and Programme Manager, using a portfolio approach to risk. By supporting multiple implementing partners (including the World Bank and UNDP, as well as consultancies and technical specalists), and a variety of activities (e.g. studies, pilot projects, capacity building), the programme could take on more or less risk depending on how the individual investments were performing. The drawback to this approach however, particularly for TCCISP which supported multiple small contracts with multiple suppliers, is that it requires a lot of time to manage and administer. During the lifetime of TCCISP, DFID Tanzania’s climate and environment portfolio grew exponentially, while staff resources available remained constant. As such, the ability to manage and steer programme resources to minimise risks was constrained. Building on the lessons learnt about the time and effort required to manage this multi-component programme, with multiple suppliers, a diversity of projects, and a diversity of risk; AIM 4 Resilience will be managed by an overarching Management Agent (identified via an OJEU procurement process). This Management Agent will be responsible for managing the four components under AIM 4 Resilience and their associated risks (e.g. financial, intellectual/innovation, management, reporting, etc.), in order to achieve DFID’s objectives for the programme.

Overview of programme risk
The overall risk rating for TCCISP was “medium”. The programme risk table (Annex 2) was updated as part of the submission for cost extension approval in December 2013, and further updated after the June 2014 annual review. However, while the 2014 update was intended to include observations on risk around NCCS, ZCCS and investment plans not being implemented due an apparent lack of political will, with a corresponding lack of allocation of resources from GoT and DPs (adding an additional risk (Risk 4) to the table). Given the challenges of achieving the quantitative outcome targets for the end of the TCCISP programme due to a lack of political will; a crucial lesson for AIM 4 Resilience will be to ensure risks associated with political will; capacity; and engagement and coordination across government actors is reflected effectively in the anticipated milestones and targets withint the logframe.

Finance risks were considered low-medium, since most funds were directly managed by DFID or other development partners (UNDP or World Bank). The accountable grant with IIED was managed by downstream partner Haki Kazi. Haki Kazi is also funded under DFID Tanzania’s Accountabilty in Tanzania (AcT) programme and is seen as a low risk partner with good financial management systems. This is being monitored closely with the AcT programme management team.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
The 2013 mid-term review concluded that the achievements and targets in the logframe were overly ambitious within the timeframe of the programme. Following the review, a number of the logframe targets were revised and updated (and some again in 2014), however, the a number of crucial indicators (with quantitative targets) remained the same, for example the Outcome Indicators. In hindsight, it may have been worthwhile to update these targets after the annual review of 2015, before the completion of this PCR, but this was not undertaken (a number of reasons may explain this, including a complete restructure of the DFID climate change team).

Many of the main activities under TCCISP required time extensions during the course of the 4.5 year programme. Some however, while being slow to start, did deliver their commitments on time, such as IIED/Haki Kazi and UK Met Office/TMA. The most notably delays were encountered under the UNDP project, which has not meet planned timelines. There were some tangible results under this project (e.g. draft National Climate Finance Mechanism framework and coordination and dialogue with DPs) but the key next steps, noably operationalising the Finance Mechanism, were not delivered by the end of the programme. There are a number of reasons for delays, including challenges in aligning the interests of the VPO and MoF on roles and responsibilities of climate finance (addressed in other areas of this report), as well as the project launching one year later than anticipated. This delay in progress has had significant impact on the TCCISP meeting its final targets, particularly Outcome Indicator 2 and Outputs 1 and 3. Additionally, the timing of the Tanzanian elections in October 2015 is likely to have an impact on progress, since governments tend to shift pace and focus in election years and it can be challenge to move forward on contentious issues.

Performance of partnerships
TCCISP was implemented through seven components, a number of which had multiple contracts and delivery partners. As such, a thorough review of all delivery partners is not feasible. Annual reviews throughout the lifetime of the programme indicate that key delivery partners (World Bank, IIED, UK Met Office, TMA, UNDP) demonstrated a clear understanding and commitment to the objectives of the programme and value for money. In addition, many have been making linkages between each other to ensure complementarity and leverage investments already made. For example, IIED and TMA have been in touch about climate data reaching the district level. IIED is also coordinating with UNDP on Zanzibar.
The business case heavily emphasized partnerships with other DPs to reduce transaction costs and harmonise activities, but this has proved more challenging than expected. One reason for this was the decision to move the Climate Change Programme Funded Adviser out of the programme and onto DFID’s Front Line Delivery team, resulting in the Climate Change Adviser shifting focus away from TCCISP only, and onto DFID Tanzania’s wider climate and environment portfolio – including leading on the expansion of DFID Tanzania’s ICF portfolio through designing new climate programmes, supporting mainstreaming of climate change in the wider DFID Tanzania portfolio, such as social protection and accountability. This shift meant DFID could now longer provide the strong leadership and facilitation role in the DPGE on climate change, and no other DP at the time was able to take on this role.
Drawing on assessment in previous annual reviews, implementation delays were due to several factors, including unclear up-front expectations (in the case of the EFO), lack of strong project management by World Bank and UNDP staff given competing demands, and no dedicated in-house teams within World Bank and UNDP (implementation instead largely relied on individuals with competing demands). These risks were not adequately considered in the Business Case or logframe. We are drawing on these lessons for AIM 4 Resilience as we launch the procurement process for the Management Agent.
The partnership with the World Bank through the EFO mechanism, the first between DFID and the Bank in Tanzania, provided some lessons for future EFOs. This is an effective funding mechanism for discrete outputs. The key lessons learnt through this process was that given difficulties in amending the legal agreement; the activities, timeline, and disbursements should be clearly defined up front rather than viewing the EFO as a more flexible instrument.

Asset disposal and value obtained by DFID
The only assets that have been purchased under this project are through IIED/Haki Kazi, these have been documented by IIED and consist of computers and a container used as an office space at Haki Kazi for this programme. No other physical assets have been procured under this programme. The new office space and equipment were observed during Annual review field visit to Arusha in June 2015. It is impractical to remove the container office and the computers are better used by the IIED/Hakikazi, and these will continue to be used as we continue to support this work with IIED under AIM 4 Resilience.

G: CONDITIONALITY (½ page)

Partnership principles assessment
There are no conditionalities. Partnership principles do not apply, as TCCISP is not direct financial aid to government.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation
As highlighted in the MTR, the underlying assessment of the business case, that Tanzania will need institutional capacity and funding to respond to climate change, continues to hold true. Emerging evidence, from Tanzania and globally, is that the pace of climate change and its impact are likely to be at the upper levels of current estimates. The TCCISP funded study on the Economics of Climate Change suggested that climate variability will increase, with increases in temperature, increased uncertain precipitation patterns and intensification of extreme weather events (such as droughts and floods)[9]. The lack of data and limits to climate modelling make detailed forecasting of climate adaptation needs (and their costs) challenging – which is why TCCISP has (and the forthcoming AIM 4 Resilience will) provide support to the Tanzanian Metrological Agency (TMA) to build capacity, data capture and products and services for Tanzanian stakeholders to respond to climate changes. In addition, the lack of information reinforces the need to invest in enabling coherent and effective country level responses, building the capacity of Tanzania to respond to an uncertain future. TCCISP has, through its knowledge products, has contributed to the analysis of the impacts of climate change and the needs of Tanzania in the future.
[9] Watkiss, P. Downing, T., Dyszynski, J., Pye, S. et al (2011). The Economics of Climate Change in the United Republic of Tanzania. Report to Development Partners Group and the UK Department for International Development. Available at: http://economics-of-cc-in-tanzania.org/

However, evidence from the operation of the TCCISP, and documented in the MTR, is that some of the underlying assumptions were overly optimistic – most crucially, political commitment and leadership on climate change. While climate change as a political issue has gained more visibility and traction during the life of the TCCISP, political commitment and leadership across URT has yet to reach the same levels shown within Tanzania’s neighbouring countries. In Zanzibar, progress has been more positive, with the development of the ZCCS Investment Plan and a willingness and leadership by the Zanzibar First Vice President’s Office. Lessons from other countries indicate that the institutional capacities are only put in place when such leadership exists. This is an important lesson for AIM 4 Resilience to recognise and to ensure sufficient attention can be paid to assist the establishment of this leadership, if instituational capacity remains a key objective of the programme.

The MTR reported that Development Partners were less willing to collaborate than had been assumed in the business case, and that this is not a function of the climate change agenda alone and appears to reflect a wider cultural shift among donors. This has resulted in Output 3 being less of a strategic priority (it was reduced to a 10% impact weighting after the MTR).

TCCISP has been contributing to ICF results reporting. The most recent annual report (June 2015) found that the programme has contributed over the last four years to improving the ability of nearly 800,000 people to cope with climate change (KPI1: 100,000 direct and 670,000 indirect), and helped to integrate climate change in planning at the national and sector levels through a comprehensive climate strategies in mainland, Zanzibar, the agriculture sector, and three districts (KPI 13). Institutional knowledge of climate change is still relatively low, but increasing (KPI 14a).

Monitoring progress throughout the programme
Over the duration of the programme, TCCISP has had five annual reviews (scores available at the beginning of this report) and one mid-term review (in 2013) undertaken. The original business case had earmarked an allocation for monitoring and evaluation, on the basis that the evidence base for climate change in Tanzania was weak, particularly at the time of the programme launch, and also to promote lesson learning across the DFID office. Under this M&E allocation, ITAD undertook a study in 2012 to improve monitoring of climate change results across the DFID Tanzania climate portfolio. The mid-term review in 2013 also put together a list of evaluation questions for a potential impact evaluation for the climate change portfolio. In June 2015, DFID commissioned an Evaluability Study to help define and prioritise evaluation in: overall impact and vision of DFID Tanzania’s ICF portfolio; impact of individual CC programmes; interaction between CC programmes and broader enabling environment work; and ensuring learning and evidence. This work (completed in October 2015) will be taken forward under AIM 4 Resilience, which includes a component to establish a Monitoring, Evaluation and Learning Unit which will draw on these reports, findings and assessments to manage the M&E process across DFID Tanzania’s CC portfolio, including supporting capacity of individual programmes on M&E.
Annex 1: Financial and VfM Summaries

Table 1: Budget/Spend by Component as at 23 March 2016

Component/Title	Budget Allocation (£)	Spend (£)	Percentage of allocation spent

202534-101: / Climate Change Institutional Strengthening Programme	251,765.10	269,530.00	107%
202534-102: / Southern Agricultural Growth Corridor of Tanzania – Green Growth Strategy	127,414.31	127,414.31	100%
202534 – 103: / Technical Support to Climate Change Institutional Strengthening Programme	631,073.93	575,447.41	91%
202534-104: / Climate Change Adaptation in Dry Land Projects	295,752.53	295,752.53	100%
202534-105: / Climate Change Adaptation and resilient Growth Planning	462,940.00	461,869.18	99.8%
202534-106: / Promoting Adaptation and Climate resilience Growth through Devolved District Climate Finance	731,053.73	722,533.73	99%
202534 – 107: / Capacity Development of Tanzania Meteorological Agency	300,000.00	300,000.00	100%
Total	2,800,000.00	2,752,547.16	98%

Table 2: Summary of Cost Drivers by Activity

Deliverable-based Activities	Output	Total budget (£)	% total activity budget	% total budget
SAGCOT Secretariat - SAGCOT Green Growth Strategy	1	127,414.30	7%	5%
Contract – PEAKS roadmap to finance CC resilience in Tanzania	3&4	81,537.00	4%	3%
EFO - World Bank for TA climate resilience growth planning in Tanzania	1, 2, 4	156,000.00	8%	6%
MoU Contribution Agreement – UNDP on mainstreaming environment and climate change into development planning. ( Mainland)	1,2	300,000.00	16%	11%
MoU Contribution Agreement – UNDP extending to Zanzibar on mainstreaming environment and climate change into development planning	1	100,000.00	5%	4%
Drylands adaptation planning (IIED + TNRF)	4	852,919.50	44%	30%
MoU – UKMET Office Capacity development of Tanzania Meteorological Agency (TMA)	4	300,000.00	16%	11%
Total Deliverable-based activities		1,917,871.00	100%	68%
Administrative Activities	Output	Total budget	% total admin budget	% total budget
Programme Funded Adviser	1, 2, 3, 4	271,734.00	31%	10%
Direct contract - DPGE secretariat	1, 2, 3, 4	24,960.00	3%	1%
Direct contract - Annual Review 2015	1, 2, 3, 4	6,214.00	1%	0.2%
Other	1, 2, 3, 4	579,221.00	65%	21%
Total administrative activites		882,129.00	100%	32%
Total		Sum of activities	% total
Deliverable-based activities		1,917,871.00	68%
Administrative activities		882,129.00	32%
Total TCCISP budget (deliverables + administrative)		2,800,000.00

Table 3: Summary of Cost Drivers by Output

Deliverable-based Activities	Total budget	% total budget
Output 1 Activities
SAGCOT Secretariat - SAGCOT Green Growth Strategy	127,414
EFO - World Bank for TA climate resilience growth planning in Tanzania	52,000
MoU Contribution Agreement – UNDP on mainstreaming environment and climate change into development planning. ( Mainland)	150,000
MoU Contribution Agreement – UNDP extending to Zanzibar- On mainstreaming environment and climate change into development planning	100,000
Administrative activities	220,532
Total Output 1	649,947	23%
Output 2 Activities
EFO - World Bank for TA climate resilience growth planning in Tanzania	52,000
MoU Contribution Agreement – UNDP on mainstreaming environment and climate change into development planning. ( Mainland)	150,000
Administrative activities	220,532
Total Output 2	422,532	15%
Output 3 Activities
Contract – PEAKS Roadmap to finance CC resilience in Tanzania	40,769
Administrative activities	220,532.29
Total Output 3	261,301	9%
Output 4 Activities
Contract – PEAKS Roadmap to finance CC resilience in Tanzania	40,769
EFO - World Bank for TA climate resilience growth planning in Tanzania	52,000
Drylands adaptation planning (IIED + TNRF)	852,920
MoU – UKMET Office Capacity development of Tanzania Meteorological Agency (TMA)	300,000
Administrative activities	220,532
Total Output 4	1,466,220	52%
Total TCCISP Budget	2,800,000

Annex 2: Risk Table (last updated after 2014 annual review)

Risk Description	Impact on Success / (L,M,H)	Probability of Occurring (L,M,H)	Mitigating Actions	Monitoring Mechanism
Risk 1 / Outcome Level / Output 2	Significant natural disaster or economic crisis will undermine results, remove gains or impede progress. On-going macro-economic and political stability.	High	Medium	Programme focuses on building resilience to deal with climate shocks and may include support to early warning systems. The support is flexible and responsive to changes in circumstances.	WB and IMF reports on the economy. GoT reporting on impact on macro-economic shocks and natural disasters and response required
Risk 2 / Outcome Level / Output 1	Financial mismanagement or corruption. Fiduciary risk assessment is positive.	High	Low	Funds will be disbursed quarterly or on the basis of deliverables/outputs, in arrears, where possible. Funding will be immediately suspended if Annual Independent Audits are late, or there is evidence of corruption. / Low risk as majority of funds are directly managed by DFID or other development partners such as UNDP and WB ensuring full control of spend is maintained. The accountable grant through IIED funds being managed by downstream partner Haki Kazi, based in Arusha.	Part of DFID monthly/quarterly forecasting and annual progress reports. Reports on outputs contracted under TA fund
Risk 3 / Outcome Level/ / Output 1 2 and 3	Lack of political will of GoT to implement new polices and focus on institutional strengthening for CC esp. sector and district level / Political will and leadership on climate change.	High	Medium	GOT have stated that climate change is an important area of work and a priority / The TA fund will be monitored annually and discontinued if there is a major issue of political will.	Minutes from DPG monthly meeting minutes / Follow up political economy study on climate change.
Risk 4 / Output 1 and output 2	Ministry of Finance is willing and able to play a key role on climate finance. International CC finance system does not further strengthen the position system of gatekeepers (VPO) constraining the space for engagement across government and at the local level.	High	Medium	This was key risk highlighted in the 2010 political economy analysis,, the programme builds on recommendations including working closely with sectors and Ministry of Finance and Planning.	Political economy analysis 2010 and update 2013. Feedback from DPs and other partners
Risk 5 / Output 2	Weak capacity in GoT to absorb and manage technical assistance and policy implementation effectively.	High	Medium	Core programme focus is institutional strengthening building on political economy study findings. / The TA fund will be monitored annually and discontinued if there is a major issue of capacity that cannot be adequately addressed by the programme.	Minutes from DPG monthly meetings and Environmental working group meetings.
Risk 6 / Outcome Level /Output 1 and 3	International climate finance is not forthcoming based on agreements in international negotiations and legally binding treaty is not favourable to Tanzania. Development Partners and GoT do not prioritise climate change in their bilateral and multi-lateral funding.	Medium	Low	Tanzania’s engagement in the negotiations and as part of the Africa group is important is support by development partners. More critical will be Tanzania having a credible national climate finance framework – that has good governance structures, can report results and is transparent - and sector based investment plans will also be critical– all of which will be delivered by the programme. Work will also focus on climate finance from GoT budget for NCCS , ZCCS, sector and district financing of adaptation. DFID funded ODI PER work supports this approach.	DPG reports on bilateral and multilateral climate finance – UNDP and GIZ climate finance readiness and DFID funded Roadmap for NCCS and ZCCS. Also some information on / www.climatefundsupdate.org
Risk 8 / Output 4	Data and information is accessible and readily available. Line ministries are interested and use the data.	Medium	Low	UK Met Office has already undertaken a capacity needs assessment of TMA so have a clear picture of the data available. They have also met with sector ministries (agriculture and energy) to assess their needs and use for the data. Accessibility and use of the data will be key objectives of the programme of support.	Review of outputs form TMA to sectors. Feedback from targeted line ministries e.g. agriculture and private sector energy stakeholders.