Business Case

Summary Sheet

Title: Cooperation in International Waters in Africa (CIWA) – Additional Financing to end period of Trust Fund.
Project Purpose: The project will continue to provide support for transboundary water management and development in priority international river basins in Africa to reduce poverty and contribute to sustainable growth and climate resilience
Programme Value: £4.5million			Country/Region: Sub-Saharan Africa (SSA)
Project Code: 200496	Start Date: Dec 2016		End Date: March 2020
Overall programme risk rating:	Moderate
Quest Number:	Business Case
	Annex A	Theory of Change Results Chain
	Annex B	Results Framework
	Annex C	MTR Action Plan

Transboundary Water Management in Sub-Saharan Africa: Cooperation in International Waters in Africa (CIWA) – Additional Financing
Intervention Summary

What support will the UK provide?

£4.5million additional contribution (on top of DFID’s initial contribution of £!0m in 2011 to the current $73m of capital within the Cooperation in International Waters in Africa (CIWA) multi-donor Trust Fund, managed by the World Bank. This will be coupled with strategic engagement and oversight through DFID participation on CIWA Advisory Committee.

What are the expected results?

CIWA is an existing and proven Multi-Donor Trust Fund (MDTF) established by the World Bank and a group of development partners established in 2011. The Trust Fund runs until 2020, and is administered by the World Bank. The initial contribution was made by the UK with subsequent contributions from Denmark, the Netherlands, Norway and Sweden. The CIWA programme aims to support riparian governments to unlock the potential for sustainable and climate resilient growth by addressing constraints to cooperative management and development of international waters. It also leverages the comparative advantage of the programme’s host institution, the World Bank, to bring knowledge and experience of investment in infrastructure, institutions and information systems across the water-related sectors in Africa. The programme is implemented across several priority basins in Sub-Saharan Africa. More details of successes to date are provided in the following sections.

The following results will be realised by combined Trust Fund finances overall:

- $10 billion of investment financing mobilized for implementation of projects influenced by CIWA
- 50 million direct beneficiaries of projects influenced by CIWA
Intermediary results centre around:
- 5 basins with strengthened institutions
- 5 basins with improved analytic tools, data and capacity
- 10 investment opportunities with regional benefits progressed in the project cycle
- 5 basins with improved engagement with civil society, private sector and academia.
The overall aim of the programme is to support countries in priority international river basins in continental Africa to manage their shared water resources (rivers, lakes, and groundwater) for economic development. In an increasingly water-scarce region, the programme will help countries to build water infrastructure, such as water storage reservoirs, irrigation, and water supply systems. It will support countries to monitor and communicate water data (such as water levels) to their neighbouring countries to enable timely flood and drought warnings. And it will build the capacity of the institutions such as River Basin Organisations who are responsible for managing water resources in shared river basins and forging agreements between Member States on how to use them to support economic growth and poverty reduction. This will help these countries avoid the cost of not having enough water (e.g. leading to outages in hydropower production) and of having too much water (e.g. leading to economic losses from flooding).

The programme will contribute to all four pillars of the UK aid strategy, specifically to strengthening resilience (pillar 2), but also to promoting regional stability (pillar 1), reducing poverty (pillar 4) and promoting global prosperity (pillar 3). It will contribute to the Government’s Manifesto Commitments (around water supply and sanitation and climate change), to stability related objectives of UK National Security Committee’s Strategies for regions of Sub Saharan Africa, and to the UK’s climate finance commitment made at the Conference of the Parties in Paris in 2015.

Such results are in the UK’s national interest as they support regional stability and address one of the drivers of economic migration and conflict – increasingly scarce water availability. They support economic development and trade between countries and seek to address chronic vulnerability and reduce the need for future humanitarian assistance caused by floods and drought.

Why is UK support required?

All of Africa’s major waters are transboundary, which complicates countries’ abilities to manage and develop their water resources. Regional action is therefore a necessity. Currently, only ten percent of Africa’s hydropower potential is developed and only five percent of its cultivated land is irrigated. While these water-dependent sectors must be developed, the financial, technical and political complexities of transboundary waters form serious obstacles to achieving the climate-resilient food, energy and water security needed for Africa’s sustainable development. Although Transboundary Rivers can maximise cooperation and manage conflict, the existing international institutions at both regional and River Basin levels remain under-strength and need to perform this task better than they have been. Unless international support is able to help improve the effectiveness of these organisations, tensions between riparian states are likely to exacerbate and not be adequately managed, and critical investment in infrastructure will not be forthcoming. And finally, the impacts of climate change are also already adding an additional and significant stressor on these water resources.

There is strong evidence, as described in the strategic case, that strengthening Information and Institutions provides a platform for cooperation, stakeholder participation and offers the analytic tools, information synthesis and dissemination as evidence base for cooperation. Infrastructure investments can have very significant positive benefits in terms of improved climate resilience and development through action from facilitating agreements, evaluating trade-offs, scoping to feasibility detailed design, and from construction and commissioning to informing ongoing operations and maintenance.

The additional UK contribution, to cover the period until the end of the Trust Fund, is required because CIWA is in urgent need of additional funds, as specified in the Financial Case. DFID’s contribution of £4.5 million is a timely and needed contribution, which would facilitate further pipeline development and secure additional development results in line with CIWA and DFID’s TWM related objectives. Other donors are in earlier stages of the approval processes and funds will only be available later, hence the DFID contribution will be frontloaded, given the urgent need for funds to allow for pipeline advancement The amount is a suitable burden share for DFID compared to other current financiers.

How does the project fit with the country programme or department’s strategic objectives set out in the Business Plan?

Support to CIWA is fully in line with Africa Regional Department’s (ARD) Business Plan and its underlying Regional Inclusive Growth Diagnostic analysis and fits strongly with overall UK development objectives (see Table 1). CIWA itself sits well with national and regional priorities in SSA, as well as with World Bank core agendas (and related UK support) and other development-partner interventions. There is good alignment with DFID’s overarching action in the water sector, especially regarding growth, gender, climate change and sustainability agendas. CIWA also has synergies with, and utilises knowledge generated from, certain Centrally Management Programme action areas, such as around Infrastructure and Climate Change, and International Climate Finance.

The case for intervening and for DFID to continue to play a leadership role on this agenda (DFID is already a proactive member of the CIWA Advisory Committee) is strong. The economic, climate, social and political appraisal clearly demonstrates the opportunity to support economic development and poverty reduction, to build resilience both at an economy-wide and community level, to contribute to gender and social equality, and to contribute to regional stability. Using the CIWA multi-donor Trust Fund mechanism enables enhanced coherence and synergy with key international partners. CIWA’s interventions are demand led from country requests, increasing prospects of sustainability. Sustainability and exit type issues considered in design process of interventions for the prioritized international Basins.

Support to CIWA aligns well with the Gender Equality Act, and DFID will continue to emphasise this aspect in its engagement with the programme. CIWA has a gender mainstreaming strategy and considers gender issues in planning and design of its interventions, such as is happening in the Nile Basin and Niger Basin and SADC Groundwater support.

What are the main programme activities?

The objective of the programme is to strengthen cooperative management and development of international waters in Sub-Saharan Africa to facilitate sustainable climate resilient growth. This is achieved through demand driven, tailored support to the various SSA priority international basin contexts, primarily in various combinations of Technical Assistance, dialogue platforms, investment project design and facilitation, institutional development, and related asset provision; and also through continent-wide evidence and knowledge products. Key programme activity streams include:

Sustained engagements – The programme responds to demand for balanced support in long-term engagement in a finite number of priority basins to strengthen information, institutions, and investments. In the priority Nile, Zambezi, Niger, and Volta river basins, the programme balances support for institutional development and information systems with assistance that helps Member Countries to advance higher quality regional investment projects.

Targeted support for high impact opportunities – The programme responds to demand for highly targeted projects and interventions. It provides turnkey support for analysis of water resources management and development opportunities and support for innovative approaches to water resources management with relevant regional entities in SSA. If merited, these can include shorter-term engagement on a more opportunistic basis that explores collaborative, potential high impact investment opportunities in basins other than core CIWA priority basins.

Knowledge management and technical assistance – The programme responds to demand for knowledge management and technical assistance in SSA through discrete activities to generate, share and manage knowledge that can facilitate cooperative development and management of international waters as well as and helping underpin related CIWA targeted institutional and infrastructure engagement in specific basins. Examples include Political Economy Analysis (PEA) and Africa-Wide Hydro-meteorological Services as well as analysis deepening evidence on the importance of transboundary water cooperation for building climate resilience.

What are the key risks to the success of the programme?

Overall programme risk rating is assessed as Moderate .

The principal programme risks are:that the political will of Member States (in the targeted Basins) to cooperate over water resources diminishes and that the capacity of the public and private sector in the region severely slows delivery and replication of demonstrated good practice because they have insufficient financial resources or human resources. All work in international waters faces an inherent risk that domestic or international political issues may negatively impact the context in which such projects operate. Whilst these are ultimately outside the programme’s control they can be influenced by the programme’s activities and enhancing capacity is one of the programmes objectives. Furthermore the portfolio nature of CIWA means that a range of interventions with varying risk profiles can be selected such that overall risk across the whole portfolio is attenuated to an acceptable level. CIWA offers a programmatic delivery mechanism with flexibility to adjust relative geographic and technical areas of focus and associated resource allocations, as new issues emerge or risk profiles change over time.

Strategic Case / The British Government, through DFID, has successfully supported transboundary water management in the SSA via CIWA since 2012 and is considered a proactive member of the CIWA Advisory Committee. Through DFID’s engagement and finance, along with other donors, significant strides have been made in establishing and strengthening River Basin Organisations (RBOs) and other regional institutions with a mandate on water management, in improving collection and dissemination of hydrological data (e.g. on flood risk) and in planning, designing and building water infrastructure. This has contributed to: / Improving regional cooperation between member states and stability in the region; / Facilitating improved design, construction and operation of strategic water infrastructure that stimulates economic growth and enables poverty reduction; / Building resilience to climate variability and change through strengthening flood warning systems, reducing exposure to drought, and ensuring infrastructure planning and investment are robust under different climate change scenarios; and / Economic growth at macro level through providing access to water for multi-purpose productive uses (e.g. irrigation or hydropower); and through demonstrating that the economic benefits of regional development outweigh the economic benefits of unilateral development. / This business case sets out the strong rationale for continued engagement by DFID in this area, and the proposed extent of such engagement over the period 2016 – 2020. / The CIWA programme accords well with the international aid priorities of the UK Government in terms of helping to end extreme poverty by building inclusive economies of developing countries. In doing so, it recognises that addressing climate change is a critical element in the fight against poverty, and that sustainable and equitable economic development cannot take place without women and girls playing an active role[1]. The new phase of the programme is aligned with and contributes to the ODA strategy and the NSC strategy and contributes towards achieving the manifesto commitments. See Table 1. / DFID also recognises, due to the fragmented nature of the Africa geopolitical landscape, and the large number of transboundary basins on the continent, that action at the regional level is an essential ingredient. CIWA is considered by DFID as one of the preferred vehicles for attaining transboundary water cooperation, climate resilience, economic growth and poverty reduction, including by virtue of its proactive approach on gender and political economy dimensions.
[1] https://www.gov.uk/government/uploads/system/uploads/attachment_data/file/209168/Africa-Regional_.pdf

Table 1: Examples of CIWA Alignment and contribution of the programme to the ODA Strategy, NSC Strategy and manifesto commitments
ODA Strategy	Programme alignment (examples)
Strengthening global peace, security and governance	Promoting regional cooperation over managing and developing transboundary water resources and creating and strengthening flows of information between countries / Strengthening the delivery capability role of relevant regional water related entities to member states / For example, CIWA is exploring how it can best engage on Lake Chad and advance management and development of that critical resource, in a context where the region is beset with instability and governance issues.
Strengthening resilience and response to crises	Increasing the resilience of communities to climate variability and change / Reducing the adverse impacts of poor management and information upstream on downstream countries (e.g. flood risk)
Promoting global prosperity	Supporting economic development through providing water for multipurpose productive uses (e.g. irrigation and power generation) / macro level economic development through demonstrating that the economic benefits of regional development outweigh the economic benefits of unilateral development (e.g. economically efficient planning of energy infrastructure taking into account climate change) / supporting energy projects conducive to trade agreement between countries (with benefits also to regional stability)
Tackling extreme poverty and helping the world’s most vulnerable	Although CIWA is not directly tackling extreme poverty, by its nature, a key focus of CIWA interventions across Information, Infrastructure and Institutions are on reducing chronic and extreme event water related vulnerability (e.g. floods and droughts), that disproportionately affects the poorest.
National Security Strategies	Programme alignment
	Southern Africa NSC strategy: Clear alignment with the sub-objective ‘Risks reduced from climate and water insecurity’ / Similar alignment with other sub-regional strategies objectives on reducing vulnerability and instability
Manifesto commitments	Programme contribution
Peace, stability and effective institutions for reducing poverty	As above for ODA pillar 1
Help at least 60 million people get access to clean water and sanitation, to stop terrible diseases.	The project supports the design, implementation of multi-purpose water infrastructure and more optimal use of often limited water resources - with benefits for water supply and sanitation along with other sectors depending on the basin context.
Work to prevent climate change and assist the poorest in adapting to it.	The programme will be funded through the International Climate Fund (ICF) and will make an important contribution to the adaptation target. It will build resilience to climate change at a number of levels: / At the regional level, the programme will engage in policy and strategy development to ensure climate change is factored into forward planning. For example Niger Basin Climate Resilience Investment Plan and the Lake Chad Climate Resilience Development Action – both of these were developed by the countries and RBOs with CIWA support and promote adaptation planning through a basin-wide approach, looking for conflicting priorities or investments that may introduce maladaptation. / At the regional level, the programme will support better information systems to ensure that countries receive improved information and warning about climate extremes (e.g. in the Nile Basin)
Africa Regional Department (ARD) Business Plan	Programme alignment
	CIWA’s aim is to improve water resources management and development in the Sub Sahara African region, at the transboundary level, allowing water resources to be more effectively harnessed for climate resilient social and economic development. This is clearly aligned to the climate change objectives under the resilience pillar of the ARD Business Plan and corresponds directly to priority intervention action identified under ARDs Regional Inclusive Growth Diagnostic
Climate finance commitment	Programme contribution
UK commitment to spend £5.8bn on climate finance between 2016 and 2021	The additional finance for CIWA will be funded through the International Climate Fund and will build resilience to climate change in SSA. The programme is well aligned to all three ICF objectives – supporting sustainable and inclusive economic growth, building resilience to manage risks, and improving stewardship of natural resources

Current Status in Sub-Saharan Africa

Sub-Saharan Africa is characterised by generally low levels of economic development and high levels of poverty. 27 of the 48 Sub-Saharan countries are low-income countries with an average income per person of less than USD 1025 per annum, and in 13 of them the average income per person is less than USD 500[2]. Despite rich natural resources, the need for sustainable water management and development in Africa is critical: 345 million people in Africa live without access to safe drinking water, only 10% of the continent’s potential hydropower is exploited[3], only 5% of the land cultivated and irrigated, water storage capacity per capita is generally very low, and a range of 75-250 million people being exposed to increased water stress by 2020 as a result of climate change.
[2] Losch B., Magrin G., Imbernon J. (eds.), 2013, A new emerging rural world. An overview of rural change in Africa. Atlas for the NEPAD Rural Futures programme, Montpellier: CIRAD, 46 p
[3] Related to this - Electricity consumption per capita is less than 20% of world overall average and access rates, particularly in Sub-Saharan Africa, are amongst the lowest in the world with only 20% of the population having access to electricity

In many basins, the development of water resources is therefore high on the political agenda[4],[5], and the development opportunities are therefore significant despite financial and capacity resource constraints.
[4] Proposal for Development Partners. World Bank Group. CIWA, 2014
[5] GIZ, 2014 Transboundary Water Management: Support to cooperation on shared waters. GIZ: Eschborn, p5.
Although Sub-Saharan Africa is generally endowed with a generous supply of water resources, most of its rivers, lakes and aquifers cross country borders, highlighting the importance of effective institutions that help to ensure shared benefits from cooperation[6],[7]. Africa has estimated annual runoff of 63,736 cubic kilometers, more than 90 percent of which is in eight large transboundary river basins: Congo, Nile, Zambezi, Niger, Ogooue, Lake Chad and the Volta3. Moreover, a total of 63 transboundary river basins account for 90 percent of Africa’s surface water resources, 63 percent of its surface area, 83 percent of its precipitation, and 92 percent of its annual discharge[8]. In addition to rivers, international basins contain more than 330 lakes, twelve of which are characterized as major perennial surface water bodies. Two or more countries share all of the major water sources in Africa and the key sectors that contribute to growth depend on development and management of water (CIWA, 2015[9]).
[9] CIWA, 2015 Political Economy Analysis and Transboundary Waters Guidance Note. January, 2015. World Bank.

Figure 1: Transboundary River basins of Africa (Oregon State University[10])
[10] http://www.transboundarywaters.orst.edu/images/Images%20for%20image%20and%20map%20gallery/Basin%20by%20continent/Africa%20Basins.jpg
Given the foregoing, the lack of water storage infrastructure causes heavy economic losses from flooding and drought. Countries in sub-Saharan Africa store only about 4% of their annual renewable flows, compared with 70%-90% in many developed countries, yet water storage is essential to ensure reliable sources of water for irrigation, water supply and hydropower and to provide a buffer for flood management (FAO[11]; FAO, 2009:3).
[11] http://www.fao.org/nr/water/topics_wwf6-t5.html (accessed 15-01-2016).

Trends & Challenges

In most countries in the region, the sectors that are driving economic growth are still primary sectors, such as agriculture, energy and mining, which are both dependent on reliable water availability and often a source of pollution. Population growth, market and governance failures, and climate change coupled with increasing water demand from the agriculture, industry and energy sectors are putting those economic development gains at risk. Water resource challenges have long existed in sub-Saharan Africa, but their impact has been amplified by such recent trends..

Given the above, climate resilient growth and poverty reduction in Africa depend on the sustainable management and development of its transboundary waters. The transboundary nature of Africa’s rivers, lakes and aquifers adds considerable political, technical, environmental, and financial complexity to their sustainable development. Consequently, unilateral, uncoordinated development by riparian countries in a transboundary basin may foreclose opportunities for optimized development from a regional perspective and may even have detrimental consequences for the hydrology of the basin. The additional complexity of working on transboundary waters has often resulted in stalled investments or the adoption of sub-optimal development choices that have a real and significant cost (ibid). Cooperative action is necessary to optimize benefits regionally and mitigate the shared risks including those of climate variability and change.

Part of the challenge is the increased number of ‘players’ and the increased complexity of relationships between institutional and individual players. This is primarily so owing to the multi-dimensional, multi-country nature of transboundary waters where trying to ‘capture it all’ runs the risk of generating overly general or unfocused interventions (CIWA, 2015). For example, the political and institutional considerations relevant to an irrigation project will be different to those relevant for developing a regional investment plan or building consensus around a regional water charter. This makes it is especially important to match the interventions to the specific needs of a given context and to use the results to shape the scope of further engagement.

Population growth, rapid urbanisation and lack of delivery of water services

The population of sub-Sahara Africa has grown from 186 million to 856 million people from 1950-2010. By 2060, the population of sub-Sahara Africa is estimate to be as large as 2.7 billion people (compared for example to projected declining population in Europe over the same period)[12]. Nigeria, Ethiopia, Tanzania, DRC, Niger, Zambia, and Uganda will contribute significant to this increase – countries where much of their water resources are shared... Despite rapid rural-urban migration and the growth in urban population, the absolute number of rural people is also likely to continue to grow (ibid). Most of the countries with the lowest levels of sanitation are located in sub-Saharan Africa, where 45% of the population resorts to using shared or dangerously inadequate facilities (Freitas, 2013:2[13]). According to FAO, about 340 million Africans lack access to safe drinking water, and almost 500 million lack access to improved sanitation facilities (FAO[14]). The water stress caused by inadequate sanitation tends to reach critical levels in regions with higher population densities. Moreover, the rapid urbanisation process currently underway in sub-Saharan Africa is therefore expected to worsen the situation. Currently one billion people live in urban areas in sub-Saharan Africa and, according to the United Nations Human Settlements Programme (UN-Habitat), that figure is expected to rise by 50% by 2030 (Freitas, 2013:2). With cities expanding fast and water consumption growing twice as fast as the levels of population growth, tensions may also emerge among city dwellers as they compete for the vital and increasingly scarce resource.
[12] World Bank 2015 http://blogs.worldbank.org/africacan/7-facts-about-population-in-sub-saharan-africa
[13] Freitas, A. 2013 Water as a Stress Factor in Sub-Saharan Africa. Brief 12, European Union Institute for Security Studies. http://www.iss.europa.eu/uploads/media/Brief_12.pdf (accessed 15 January, 2016).
[14] http://www.fao.org/nr/water/topics_wwf6-t5.html (accessed 15-01-2016).

As figure 2 below illustrates, Sub-Saharan Africa risks being the only region where there is a projected increase in the absolute numbers of people without access to an improved drinking water source if the trends seen continue and if service provision is not accelerated. This clearly remains a huge challenge for the region.

Figure 2: Projected change in the absolute numbers of people without access to an improved drinking water source 2005–2015. Source: World Health Organisation (2012; in Freitas, 2013:2).

Climate Change

Africa has been identified by the IPCC as the continent most vulnerable to the impacts of climate change, due to the significant bio-physical impacts of climate change, high levels of poverty, and the low institutional capacity for adaptation[15]. Managing the freshwater impacts of climate change in Africa is as much a development challenge as a climate change challenge. Even without climate change, many of Africa’s water resources are facing overuse, pollution, and degradation. Poor land-use practices are contributed to this process. Large numbers of people living in poverty in rural and informal urban areas are already vulnerable to water-related risks, whether floods, droughts, poor water quality, or increasing water scarcity.
[15] IPCC report, 2007, Chapter 11 – Regional Climate Projections

The status of water resources in Africa has been changing for many decades, whether through decreasing water quality, lowered groundwater, more or less rainfall, and changed timing of rainfall. Change is not new. Climate change, however, will profoundly accelerate the rate of change, affecting the ability of people and societies to respond adequately. The rate of change is compounded by uncertainty of the impacts of climate change. While there are a number of models that attempt to predict the impacts of climate change, many of these are at a very coarse scale and do not predict localised impacts, which may differ from the generalised picture. At the same time, different models predict different climate change trends in the same areas. Managing for high rates of change in a context of uncertainty is therefore required. While predicted decreases in precipitation are readily understood as a risk, predicted increases are not necessarily of benefit depending on the actual rainfall patterns. As such, increasing inter-annual and intra-annual variability in precipitation is one of the largest risks facing Africa as irregular and uncertain rainfall makes the need for infrastructure and governance more pronounced.

The impacts of changes in climate will vary depending on both the emission trajectory and the socio-economic response. However, it is likely that it will have severe implications for the poorest communities who rely mostly on rain-fed farming as their source of food and income, particularly in arid and semi-arid areas. Flooding and drought will destroy arable land and crops, kill people and livestock, and destroy valuable infrastructure. Climate change is likely to enhance the water-related challenges in the region, across a range of sectors

Trade-offs between sectors

According to the Food and Agriculture Organization of the United Nations (FAO, 2009), nearly 85% of fresh water resources in sub-Saharan Africa are utilised for agricultural purposes. It is estimated that erratic and extreme weather conditions as well as insufficient irrigation could lead agricultural productivity in several countries to fall by up to 50% over the next 10 years, severely affecting their prospects of greater social and economic development (FAO, 2009; Freitas, 2013). Despite abundant natural water supplies at the continental level, this abundance is not evenly distributed and it is apparent that Africa has not been able to intensify its agricultural production through irrigation and improved water management (water harvesting and storage) (FAO, 2009). Equally, the energy sector is also directly and negatively affected by water shortages. This is not only the case of hydropower, an important source of energy in Sub-Saharan Africa, but also of thermal-based power with nuclear, coal- and gas-fired power stations all being extremely water-intensive structures (Freitas, 2013). Given the competing needs between water for energy and agriculture (among other uses) in Sub-Saharan Africa, it becomes apparent that the chances of developing a durable industrial and manufacturing sector are slim without proper access to water resources and sufficient energy production. Therefore, water (or rather lack thereof) can significantly constrain the much needed diversification of African economies, especially in instances where there is lack of integrated planning and coordination to facilitate trade-offs between sectors competing for water resources.

As with single-country policy issues, strategic assessments of trade-off between and among sectors should focus on key drivers of decision making which can be used to inform regional strategies, engagement and dialogue (CIWA, 2015). These would be unlikely to provide sufficient depth to inform the design of a project, but might already begin to consider in which water related sectors reforms may be more or less likely to gain traction. Moving right across the political economy continuum of transboundary water management, assessments would become more focused and detailed, unpacking dynamics around a particular sub-sector of water management (i.e. irrigation, hydro, tourism, food security, fisheries, agriculture, etc.) or around a specific project in the pipeline (ibid). Figure 3 shows a typical political economy continuum in transboundary water management.

Figure 3: Typical political economy continuum in transboundary water management. Source: CIWA (2015).

Trade-offs between and among countries

It is widely acknowledged that growing pressure on water resources can lead to domestic unrest, exacerbate existing inter-state tensions and even constitute a source of armed conflict (Freitas, 2013; Grey and Sadoff, 2007[16]). As water becomes rarer in Sub-Saharan Africa, competition among those who depend on it may rise, potentially re-igniting longstanding tensions and disputes. Given that water is largely a shared resource in sub-Saharan Africa, where some 17 major river basins span as many as 35 countries, establishing effective cooperation over the management of cross-border natural resources is seldom an easy task (ibid). It is even less so when such resources are also markers of countries’ sovereign borders as is often the case for rivers and lakes in Africa. There are several examples of rising (local and regional) tensions linked to water access and management (Freitas, 2013:3[17]).
[16] Grey, D and Sadoff, C, W. 2007 Sink or Swim? Water security for growth and development. Water Policy 9 (2007) 545–571. doi: 10.2166/wp.2007.021
[17] Freitas, A. 2013 Water as a Stress Factor in Sub-Saharan Africa. Brief 12, European Union Institute for Security Studies. http://www.iss.europa.eu/uploads/media/Brief_12.pdf (accessed 15 January, 2016).

With no clear and agreed cooperation framework, disputes that have long remained dormant can resurface overnight and unravel previous, sometimes tacit, arrangements. In the Great Lakes region of East Africa, Tanzania has been seeking international mediation to help resolve its longstanding border dispute with Malawi over rights to Lake Malawi. Lake Chad’s waters, used for farming purposes by Niger, Chad, Cameroon and Nigeria, are shrinking rapidly. Regardless of the existence of a Lake Chad Basin Commission (created in 1964 and the oldest of its kind in Africa), the affected states have been unable to reach an agreement over the use of the lake’s water (Freitas, 2013). Recent disputes over the waters of the Nile Basin, currently shared by 11 countries, represent another good example of where and how tensions can arise (World Bank, 2015[18]), with major developments by individual riparians causing concern to other riparians, and occurring in a context of the existing agreements not being seen as balanced or equitable. These few examples only serve to amplify the fact that without clear and agreed cooperation frameworks where trade-offs can be mutually agreed between and among countries, managing Sub-Saharan Africa’s water resources remains a huge challenge. Conversely, with willing parties, shared water resources can be a significant catalyst for cooperation and associated agreements for and mutually beneficial development such has happened in the Senegal River Basin generating substantial hydropower and in the Orange-Senqu Basin with hydropower for Lesotho and and water supply for South Africa.
[18] World Bank, 2015 Annual Report. Cooperation in International Waters in Africa (CIWA) Program.
Governance and market failures and the politics of transboundary cooperation
Related to the above trade-offs challenge, governance and market failures prevent the efficient and optimum regional management of water resources. General governance and market failures are outlined below – all of which play out to varying degrees in SSA.
Sovereignty and security: Cooperation inherently requires giving up some degree of sovereignty in relation to water (and thereby energy and food security) and may be perceived as a direct threat to national security. National interest and security may trump a regional approach if a) the economic/ social benefits are not clearly stated and b) the institutions developed to oversee the shared resources are not considered to be robust or are not sufficiently trusted. This links directly to issues of power and technical capacity – riparian neighbours have very different economic and military power and technical capacity to develop and exploit water resources which will critically influence how they engage in trans-boundary negotiations. In SSA, Shared Water Institutions (SWIs) are at varying levels of development and Member State trust in them to manage transboundary waters is uncertain.
Regional versus national policy incompatibilities are also likely to be a major barrier to trans-boundary water resources management. Colonial boundaries rarely match natural boundaries of watersheds and variance between legal and administrative systems, development of infrastructure, history of resource exploitation, technical capacity and the strength of post-colonial ties also leaves an historical legacy which has contemporary political and economic implications. Within the various international river basins in SSA there are differences between legal and administrative systems that while not necessarily incompatible, can make collaboration more difficult. This includes different requirements for project level Environmental Impact Assessment, different land ownership models and different legal systems for Public Private Partnerships.
Data and information sharing is also an issue, with data asymmetry between riparian neighbours used in negotiations, for example with upstream riparian states controlling data critical for downstream country planning. A key driver for international cooperation is disaster risk management, where mitigating the effects or floods, droughts and climatic disasters can depend on investing in a neighbouring country. Improved data and analysis is important not just for planning but also in terms of generating robust evidence to challenge preconceived but entrenched perceptions of negative consequences of plans and actions of neighbour countries.
Water resources management has also tended to develop and work as a distinct sector, with water ministries focussed on their own budgets and programmes with less attention on the economic value of water as it refers to other parts of the economy. For agriculture, energy, fisheries, manufacturing, etc. water is a key input and commodity. Whilst international water law defines the space at stake in terms of cooperation, perspectives on ownership and utilization of water are entrenched and can lead to countries preferring to maintain the status quo rather than enter into agreements on the use of shared watercourses.
Market failures also prevent adequate investment in the water sector. One reason is that in many countries water is priced artificially low to help to ensure its availability but typically this leads to inefficient allocation and usage limiting its potential to driver human and economic development and sometimes reducing access for the poor and vulnerable. The value of water is typically greater than its present cost. Inefficient water usage almost always leads to inadequate allocations for ecosystems causing degradation and decline.
Political Economy
The political economy of transboundary water is highly complex. Compounding the factors discussed above, given the potential impact that upstream projects can have on riparian neighbours and the trade-offs involved, decisions that affect water resources are highly politically contested. Local interests and rivalries, commercial and business interests, the power base of national elites and politicians, competition between government departments and many other factors will drive the politics and incentives of decisions on water resources. The influence of regional historical tensions and political rivalries on domestic politics may also overshadow even the most clearly understood mutual benefits of transboundary cooperation. Because water is required for so many critical parts of the economy, from subsistence farmers to heavy industry, political contestation over its usage will remain a fundamental element of the sector – and this will increase in periods of stress and drought. Two examples of the political economy in action are provided below and further examples of the delivery mechanisms set up to navigate the political economy are provided in the appraisal case.
- In one Member State, the department for irrigation and department for energy have developed incompatible plans to use the same water for both large scale irrigation and for a hydropower project.
- Experience has shown that some Member States can play a proactive and supportive role in one River Basin Organisation where they stand to benefit from better joint management of the resource and a negative and destabilising role in another RBO where they perceive a risk to their water supply if the water is managed more fairly across the basin
The politics of transboundary water are not static, so the programme will need to ensure that it is constantly informed by strong political economy analysis informing project selection and decision making process, as well as maintaining the flexibility to reprioritise funds away from areas of political stalemate to work with the grain of regional and national politics on water resources.
Fostering cooperation and driving change in complex African river basins requires a nuanced understanding of context, especially the political and economic incentives facing local actors. Undeniably, and as widely acknowledged, decisions related to water resource management are shaped by a range of considerations (CIWA, 2015). These include traditional economic factors and physical constraints, as well as political considerations such as the need to manage political support within a single state or to navigate complex international relationships with riparian countries (ibid). Accordingly, the effectiveness of development programing in transboundary waters is influenced by the incentives facing local actors to pursue, appear to pursue, or limit reform. Unpacking the diverse drivers of reform can improve effectiveness of operational engagements; risk identification and mitigation strategies; and responsiveness to client demand for context-specific and context-sensitive approaches to advancing effective transboundary water resource management.
The impacts of poor water management on poverty
As noted above poverty is entrenched in much of SSA. At the regional level, demonstrating the direct link to poverty reduction is difficult, and efforts can best be described as ‘poverty enabling’. Strengthening the capacity of regional institutions to manage shared water resources and to mediate between different Member States falls into this category. Better capacitated River Basin Organisations can challenge the hegemony of certain countries and advocate for a more equitable distribution of water resources. More equitable and efficient use of water resources between countries will in turn mean that those living in water insecurity (with insufficient access to water for drinking and productive uses) receive more water. They will also benefit from macro-level economic development and reduction in national vulnerability to shocks and stresses, allowing more scope for national level poverty reduction and intervention (see later sections). However, with the complex factors and long term nature involved, empirical evidence on these aspects is lacking.
Arguably, the structure of economies plays an important role with more vulnerable economies requiring more investment to achieve water security. Historical investments in water management institutions and infrastructure, the economy’s reliance on water resources for income generation and employment and its vulnerability to water shocks will all be relevant (Grey and Sadoff, 2007:550[19]). Water vulnerable economies, for example those with highly variable rainfall that rely heavily on rain-fed agriculture, or those whose most productive assets or areas lie in flood plains, will require more extensive investments in order to achieve basic water security (ibid). Without investment, not only will these economies regularly suffer greater setbacks from water shocks, but this vulnerability will be likely to prove a strong disincentive for domestic or foreign entrepreneurial investments that could shift the structure of the economy toward a more diversified, water-resilient structure.
[19] Grey, D and Sadoff, C, W. 2007 Sink or Swim? Water security for growth and development. Water Policy 9 (2007) 545–571. doi: 10.2166/wp.2007.021.
Economic studies conducted at country level by the World Bank over the past 15 years have shown that impacts resulting from poor management of the water sector typically cost African countries 4.3% of annual Gross Domestic Product[20]. These effects are most pronounced in low-income countries with a high reliance on agriculture (defined as situations in which agricultural production contributes over 20% of total GDP) and water stress. The dependence on agricultural production, low incomes and water stress are likely to combine with climate change to impact national growth prospects. These losses make the economic case for action on transboundary water management compelling.
[20] World Bank 2015, ­Post 2015 Water ­Thematic Consultation - Water, Sanitation and Hygiene, The economic case for increasing access to improved sanitation and water supply: Quantifying the Costs and Benefits of Water Supply and Sanitation.
In the water sector, Grey and Sadoff (2007:551) highlight that in the poorest countries, of which Sub-Saharan Africa has many, where survival is a real concern for large parts of the population and there are few functional social safety nets, economic actors tend to be extremely risk averse, investing only after there is significant demonstration of returns. In these circumstances, levels of risk aversion may therefore influence the threshold at which water security can trigger private investment and downstream market chains. Moreover, in water insecure countries, the unpredictability of rainfall and runoff, amplified by occasional droughts and floods, is likely to constrain growth and diversification by encouraging risk-averse behaviour at all levels of the economy in all years, as economic actors, particularly the poor, focus on minimizing their downside risks rather than maximizing their potential gains (ibid).
There is much clearer evidence that improved cross-border water management can reduce the costs imposed by water-related hazards and in particular floods. It is often the poorest segments of the population that are most vulnerable to flood risk. Mozambique is particularly vulnerable to flood risk and it is the 1.4million poor people living in the flood plains of the lower Limpopo that have borne the brunt of previous floods. The loss of harvest or income caused by drought or floods can easily push households below the poverty line.[21] Assessing drought, extreme temperature and flood hazards alone, reveals that between 176 and 319 million extremely poor people will be living in the 45 countries most exposed to these hazards by 2030. [22] As such, activities to strengthen early flood warning systems and provide a warning further in advance (by having better inter-country communication) has a direct benefit on the poor and climate vulnerable.
[21] Schmuck - The Economics of Early Response and Resilience: Mozambique Country Study
[22] ODI (2013) The geography of poverty, disasters and climate extremes in 2030
The link to poverty reduction in relation to building water infrastructure is much more direct. Infrastructure can have a significant impact in reducing poverty through improving water supply and reducing drudgery for women, through providing reliable irrigation and a source of income to farmers and through reducing the economic, household and health costs of floods and drought. Inadequate investments in water management, infrastructure and services can have a severely detrimental impact on the food security of the majority of the poor and hungry, who live in rural and peri-urban areas and depend directly or indirectly on agriculture for their livelihoods (FAO[23]; FAO, 2009). This is further compounded by insufficient investment in agricultural production value chain development and support services. Therefore the need for substantial investment in public goods that support agriculture, irrigation and power supply, rural roads, and storage facilities such as dams is urgently required in Sub-Saharan Africa, where the majority of rivers are transboundary in nature.
[23] http://www.fao.org/nr/water/topics_wwf6-t5.html (accessed 15-01-2016).
Summary of the impacts of water insecurity on the SADC region
The evidence presented above clearly demonstrates a number of water risks and their potential to depress or even reverse development gains:
- Population growth and urbanisation in SSA will increase the demand on water resources – on the one hand, the growth of informal settlements in urban areas are outpacing water supply and sanitation, on the other an ageing rural population is becoming more vulnerable to floods and droughts;
- The impacts of climate change are uncertain, but the at a general level the likely increased variability and projected impacts (increasing temperature, increasing intense precipitation, and increasing drought) coupled with the existing adaptation deficit poses a real risk to development. Climate change will be felt across the region and coordination action is required to respond to the consequences;
- While progress is being made to improve the governance and market failures there is still a long way to go;
- Water demand from industry, agriculture and energy is typically set to increase in most regions. However, water will often be increasingly scarce. As such, there will be trade-offs between sectors and countries. A regional approach to planning and management is required to optimise water use across the sectors.

Investment in information, institutions and infrastructure to support sustainable economic growth in Sub-Saharan Africa
The evidence demonstrates that there is a clear need for intervention to support improved management and development of SSA’s transboundary water resources. To do this, there is a need to invest in information, institutions and infrastructure. Example evidence for investing in each of these areas is presented below:
Improved Information to Support Decision Making
The availability of up-to-date data (hydrological, geohydrological, meteorological, water use, demographic, etc.) at an appropriate level of granularity and spatial coverage is a pre-requisite for effective water resource planning and allocation decisions. While historical data is necessary to obtain reasonable flow statistics, track climatic variability and identify emergent hydrological dynamics with socio-economic impacts, climate change also means that new ways of analysing data are needed to prepare for an uncertain future.

Across SSA there is in general a lack of capacity to monitor, plan and manage water resources[24],[25]. Often government and water resource managers have a limited ability to collect the data needed for long-term water resources management, particularly good quality hydro meteorological time series, such as rainfall and river flow and critical geohydrological data. In addition, the gender-disaggregation of data in the region in order to support effective gender mainstreaming in the sector is in its infancy.
[24] Houghton-Carr, 2007 in Climate Variability and Change—Hydrological Impact. The decline of hydrological data collection for development of integrated water resource management tools in Southern Africa
[25] Giles 2005, Nature, Solving Africa’s climate data problem
Currently, data asymmetry between riparian neighbours in shared river basins complicates engagement and negotiations over water sharing although a great deal has been done to improve this situation in some basins in recent years, including through support provided by DFID. Currently, poor water monitoring networks and communication in the region result in uncoordinated responses to flooding in particular. For example, the economies of Zambia, Malawi, Mozambique and Zimbabwe are vulnerable to floods and droughts where a single event could (and has) reduced GDP by as much as 7%[26]. These risks are often driven by developments and rainfall events in the upstream countries impacting on downstream country(ies). The co-ordination of early warning systems across the basin is critical in reducing the impacts from floods and in improving disaster risk reduction in the region. The World Metrological Organisation suggests that for every dollar invested in early warnings issued by National Metrological and Hydrological Services’, at least seven dollars of losses are offset[27]. The World Bank Group suggests investments in such data and services can deliver benefit cost rations ranging from 4:1 to 36:1[28].
[26] World Bank 2005 Review of the role of water in SADC economies
[27] WMO, 2015, The role and operation of national meteorological and hydrological services,
[28] World Bank Group, USAID and WMO, 2015, Valuing Weather and Climate: Economic Assessment of Meteorological and Hydrological Services, https://www.gfdrr.org/sites/default/files/publication/SEB%20HYDROMET.pdf
The value of geo/hydrological data is also likely to increase over time. For example, stream gauges with a long period of record are particularly valuable as they form a baseline for information about future changes when matched with climate change scenario assessments.

In order to translate access to reliable data into material benefits it needs to be turned into information and then insight that can be used by practitioners and policy makers.[29] In addition it is important for water users to be able to hold government accountable and for information to be available to water users and stakeholders.
[29] Steward, 2015 Measuring what we manage – the importance of hydrological data to water resources management http://www.proc-iahs.net/366/80/2015/piahs-366-80-2015.pdf
Effective and well-resourced institutions
Strong institutions, designed to manage the competing demands of water users including across national boundaries and to develop and operate appropriate water resources infrastructure, are critical.[30] Studies have consistently demonstrated that there is a direct correlation between the countries most lacking in water services and those with the weakest governance[31]. In this context the benefits of building the capacity of national departments and agencies and shared watercourse institutions is clear. The evidence supporting its economic effectiveness in the water sector and beyond is also robust[32].
[30] Ostrom, 1993, Design principles in long-enduring irrigation institutions
[31] Plummer and Slaymaker, (2007), “Rethinking Governance in Water Services,” Overseas Development Institute, London, UK)
[32] World Bank meta-analysis of 1864 water sector interventions between 1997 – 2007, Parker, Ronald, 2010, An evaluation of World Bank support, 1997-2007: Water and development, World Bank Group. See also DFID’s Literature and Evidence Review
The institutional landscape regarding management of transboundary waters across SSA is highly variable. There are some examples of good practice such as the Senegal River Basin Organisation and of conducive policy instruments such as the SADC Protocol on Shared Watercourses. However, even in those cases with a conducive policy environment, the institutions typically themselves still face constraints (including limited finances, human resources, equipment, data, and issues of co-ordination and process); and tacit constraints (including issues of power, authority and legitimacy, such as unresolved mandate overlap, low political will and confused sovereignty; issues of integrity, motivation; and low institutional incentives and accountability).[33] This suggests that, while ‘effective’ institutions play a major role in enabling water management, capacity building programs are complex and delivering support is subject to a series of substantial challenges. Evidence suggests that capacity building approaches are most successful when they are based on detailed analysis of the factors determining institutional performance, in advance of initiating capacity building interventions and institutional reforms.[34]
[33] Hepworth, 2009,CMS Information and Capacity Building, Multilateral Environmental Agreements and the Biodiversity Liaison Group.
[34] Hepworth 2009
Strong institutions will enable delivery on a number of key themes:

- Implementation instruments for cooperation: Policy and intent for cooperation requires entities capable of developing and administering appropriate governance instruments[35], and challenges exist in adequacy of instruments, including the need for guidelines and standards that will assist Member States in using these instruments[36] effectively
  [35] GIZ TWM Evaluation Report 2015
  [36] RSAP III MTR 2014
- Stakeholder Engagement: Stakeholder engagement is crucial in supporting the performance in water institutions. They boost levels of accountability and enable citizen, media and political performance monitoring and oversight. Stakeholder engagement can help ensure that decisions made by elites do not override the interests of less privileged social groups, leading to potentially negative repercussions.
- Gender mainstreaming and youth involvement: Women, more than any other group in society, carry the biggest burden of water insecurity. It is therefore critical that decisions relating are sensitive to these vulnerable groups and, where possible, seek to positively redress the balance.
Infrastructure Development, Operation and Maintenance
SSA has significantly less water infrastructure, measured in terms of storage capacity per capita, than other parts of the world[37]. This is considered to be a significant constraint on economic development[38] and a major factor increasing the regions’ vulnerability to climate change[39]. Countries in sub-Saharan Africa in average store only about 4% of their annual renewable flows, compared to 70% - 90% in the developing world. For example, Zimbabwe is estimated to use only 3.6 km3/year of its 13.1 km3/year internal surface water resources, Zambia has high theoretical resource availability but in practice has the lowest per capita storage (excluding Lake Kariba) compared to a range of other countries in Africa and elsewhere.[40] Providing additional storage capacity is critical due to the significant spatial and temporal variability in flow across the region.
[37] White, W. R. 2005. World water storage in man-made reservoirs: A review of current knowledge. Marlow, UK: Foundation for Water Research. 40 pp
[38] Grey, D.; Sadoff, C. 2006. Water for growth and development. Thematic documents of the IV World Water Forum. Mexico City: Comision Nacional del Agua.
[39] M McCartey and V Smakhtin, 2010. Water Storage in an Era of Climage Change: addressing the Challenge of Increasing Rainfall Variability. International Water Management Institute
[40] SADC Economic Accounting for Water Use Project

Different types of water infrastructure have different benefits and risks. Large-scale Infrastructure: Despite numerous reports and case studies of the negative impacts of large scale infrastructure, such infrastructure remains an essential element for water security in an area of significant seasonal and inter-annual climate variability, and in the face of climate change. Small- and medium-scale infrastructure investments offer the rural and peri-urban poor, amongst others, options to boost access to water through relatively inexpensive measures including systems of small off-stream reservoirs. Small scale water infrastructure projects include small reservoirs, small weirs and coffer dams, boreholes, sand dams, small-scale irrigation schemes, and rain water harvesting infrastructure. The main benefit is that it has limited environmental impacts, benefits the poor directly (and potentially women especially) and the benefits can be realised within a relatively short period of time. Ecological Infrastructure: Supporting the protection and rehabilitation of ecological infrastructure[41] such as wetlands and natural aquifer recharge zones, which provides a range of ecological services including groundwater recharge, dissipation of flood waters, water purification, and food sources is also important. Lack of investment in ecological infrastructure threatens the sustainability and cost of physical infrastructure through, for example, sedimentation. Degraded land and destruction of wetlands also increases run-off resulting in increased flooding in extreme rainfall events.
[41] TEEB (2010) The Economics of Ecosystems and Biodiversity Mainstreaming the Economics of Nature: A synthesis of the approach, conclusions and recommendations of TEEB. Available at: www.teebweb.org.
Investing in improved water infrastructure is critical in addressing current and future climate change risks and vulnerabilities in the region[42] as well as harnessing any potential benefits. A recent study in South Africa showed the benefits of a highly integrated water supply infrastructure in terms of reducing the potential for economic risks from climate change[43]. One of the challenges of investing in climate resilient infrastructure is that it often involves an upfront cost that will only be recovered over time and which is dependent on the uncertainty of future climate scenarios. A recent study of the potential impacts of climate change on the water infrastructure across Africa[44] showed that not taking climate change into account could lead to a significant cost in terms of lost opportunities or in terms of a poorly functioning asset. For the Zambezi basin, this shows that if hydropower infrastructure in the Zambezi was designed now based on the driest climate change scenario it would avoid losses of USD 42.1billion if that scenario was accurate. Conversely if hydropower was built now based on the wettest climate change scenario it would contribute an additional USD 15.4billion to the member state economies if that scenario was accurate. The study illustrates that adopting a risk based approach to incorporating climate change risks into the design and optimisation of critical water infrastructure (irrigation and hydropower) can significantly reduce costs of maladaptation or no-adaptation and improve performance.
[42] UN Water (2010) Climate Change Adaptation: The Pivotal Role of Water. Policy Brief.
[43] Cullis J, Alton T, Arndt C, Cartwright A, Chang A, Gabriel S, Gebretsadik Y, Hartley F, de Jager G, Makrelov K, Roberson G, Scholosser A, Strzepek K, Thurlow J (2015) An uncertainty approach to modelling climatic risk in South Africa. WIDER Working paper 2015/045. UNU-WIDER, Helsinki, Finland.
[44] Cervigni R, Liden R, Neumann J.E. and Strsepek M (ed) (2015) Enhancing the Climate Resilience of Africa’s Infrastructure A copublication of the Agence Francaise de Developpement and the World Bank.
The currently weak capacity in the region to develop and promote bankable projects to funders must be enhanced to enable governments to take advantage of a range of available sources of financing. This is an area where external support can drive significant change through facilitating the development of bankable projects and associate financing arrangements. It is also expected that the opportunities around climate finance for the region will increase over the programme duration. The private sector is also a potentially significant source of both finance and expertise. Across the region the private sector has identified water risks as amongst the greatest risks they face.[45] There is therefore appetite from the private sector to support improved water management both for commercial reasons and to demonstrate corporate social responsibility, but again external support can often be decisive in leading to action through lowering initial transaction costs and sharing risk.
[45] World Economic Forum (2016) The Global Risks Report 2016.

A regional approach to transboundary water management - opportunities
There is a clear need and opportunity to invest in enhancing water security throughout the region. There is a critical need for national level investment in information, institutions, and infrastructure but there is also a complementary need to invest in regional cooperation around managing shared water resources.
The transboundary nature of water resources in SSA poses both challenges and opportunities. The challenges associated with the political economy, the increasing pressure and demand on water resources from productive sectors and the risk of climate variability and change have been considered above. The opportunities are summarised briefly below:
Economic efficiency: There is evidence that joint planning of water resources and optimising the siting of water infrastructure is significantly more economically efficient that unilateral development of water resources. Sadoff et al (2002)[46] and Grey and Sadoff (2007)[47] use analytical economics to explore the costs and benefits of cooperation, and the case for cooperation is compelling. For example, the Multi-sectoral Investment Opportunity Analysis for the Zambezi[48] suggests that coordinated development of hydropower resources can provide an additional 23% generation over uncoordinated operation.[49]
[46] Sadoff, C.W.; Whittington, D. and Grey, D. 2002. Africa’s international rivers: An economic perspective. Washington, DC: The World Bank
[47] Grey, D & Sadoff, CW, 2007. Sink or swim: Water security for growth and development. World Bank, Washington DC
[48] World Bank (2010): Zambezi River basin: a multi-sectoral investment opportunity analysis: Summary Report
[49] Economic Commission for Africa (ECA), Southern Africa Office (SRO-SA), 2010: Cost-Benefit Analysis for Regional Infrastructure in Water and Power Sectors in Southern Africa
Regional stability and peace: Transboundary water management has the potential to improve regional peace and security. As is well known many countries across SSA suffer from considerable instability and fragility. Peace and political stability is critical for the development of the region, and while there are many dimensions affecting peace and security it has been suggested that increased co-operation over water resources can increase the potential for peace[50]. While major national scale conflicts over water resources are rare, it is recognised that this ‘may happen in the future if cooperation on transboundary resources is not nurtured and possibly further enhanced’[51] [52]. Turton et al report empirical evidence which indicates a propensity for states to choose cooperation over conflict where a critical shared resource could limit future development potential. [53] However, the ‘propensity’ for cooperation needs to be facilitated by capable institutions and financial investments.
[50] Quibell G and Entholzner A (2015) Sovereign Security with a Cherry on Top. Building Climate Resilience through Virtual Water and Nexus thinking in SADC – A think “peace”.
[51] Trondalen JM, 2011 Conflict Prevention and Peace Dividends through Cooperation on Transboundary Water Management in SADC Achieving Peace Dividends through the Prevention of Water Conflicts, Geneva, August, 2011
[52] See also extensive research conducted by Peter Ashton, such as: ‘Are Southern Africa Water Conflicts inevitable or preventable?’ in Solomon, H. & Turton, A.R., eds, 2000: Water Waters: An Enduring Myth or an Impending Reality? ACCORD Publisher, Durban.
[53] Turton, A. R., M. J. Patrick, et al. 2006. "Transboundary water resources in Southern Africa: Conflict or cooperation?" Development 49(3): 22-31
Learning and best practice: Regional solutions enable individual countries to learn from each other and to share experiences relating to common challenges and promote best practice.
If regional cooperation can be fostered, national and local benefits will follow. These will include:
1. Agricultural productivity: improved access to reliable water supply can increase agricultural yields and boost the economic prospects for both commercial and small-holder agriculture[54].
  [54] AfDB, 2015, Transforming Africa’s Agriculture to Improve Competitiveness
2. Poverty reduction: Women and older people play a disproportionate role in small-scale agricultural[55]. Boosting water supply to rural areas and improving water productivity can help reduce poverty.
  [55] Parekh S & Wilcox S (2014) Feminist Perspectives on Globalisation. The Stanford Encyclopaedia of Philosophy (Summer 2014 Edition). Zalta E (ed.). From:http://plato.stanford.edu/archives/sum2014/entries/feminism-globalisation.
3. Energy sector performance: Hydropower is the main source of base-load power generation in many SADC countries.[56] [57] However, production is predicated on availability of sufficient water. Successful transboundary water management can therefore reduce the risk of hydropower outages[58].
  [56] World Bank & Ministry of Energy and Minerals, 2014, Tanzania’s Hydropower Development Assessment (unpublished) p.7
  [57] 23 countries in Africa rely on Hydropower for more than 50% of total electricity generation. Hamududu et al, 2012, Assessing Climate Change Impacts on Global Hydropower
  [58] In Tanzania the 2008 hydropower shortage accounted for an estimates 4.2% reduction in GDP (IRENA, 2014 Southern and East African Energy Corridors)
4. Health: Studies suggest that the benefit cost ratio for water and sanitation projects in Sub-Saharan Africa is typically 1:15[59] and has a disproportionately greater benefit for women and girls.
  [59] Hutton et al, 2007 Economic and health effects of increasing coverage of low cost household drinking-water supply and sanitation intervention to countries off-track to meet MDG target 10. Geneva: WHO
5. Education and employment: increasing access to clean water reduces the time spent collecting water, particularly for women and children. In Tanzania, 75% of water collection is performed by women and girls. By improving water access, time can be released to engage in economically productive activities and for girls to attend school.[60]
  [60] According to the WHO, 2014 total national GDP in SSA increases 0.3% for each 10% increase in female literacy, reinforcing the case for reducing the time associated with collecting water.
6. Cost savings: New and rehabilitated infrastructure can reduce leakages and water wastage, and increase the availability of water for consumption and reduce treatment costs in potable water systems. Evidence from South Africa suggests interventions to address non-revenue water have a payback period of between 2-5 years[61]. Additionally, investment in improved transboundary water management can avoid a range of future costs. These could include the costs of new bulk water transfer schemes or expensive desalination plants.
  [61] WRC, 2008, The status and use of drinking water conservation and savings devices in the domestic and commercial environments in South Africa
Existing programmatic building blocks
DFID is already engaged in the field of transboundary water resources management in Africa. It supports:
- the Cooperation in International Waters in Africa (CIWA) programme. The World Bank and a group of development partners established CIWA in 2011. The financing mechanism is a multi-donor trust fund (MDTF), currently running until 2020, administered by the World Bank with an initial contribution from the UK and subsequent contributions from Denmark, the Netherlands, Norway and Sweden. The CIWA programme aims to support riparian governments to unlock the potential for sustainable and climate resilient growth by addressing constraints to cooperative management and development of international waters. CIWA’s focus on water-related growth reflects the desire of riparian governments engaged in cooperative management of water resources to accelerate water resources development in support of economic growth and poverty reduction. It also leverages the comparative advantage of the programme’s host institution, the World Bank, to bring knowledge and experience of investment in infrastructure, institutions and information systems across the water-related sectors in Africa. The programme is implemented across several priority basins in Sub-Saharan Africa.
- The Transboundary Water Management in SADC (SADC TWM) programme. This has three components: a capacity building component through GIZ; the Climate Resilient Infrastructure Development Facility (CRIDF) programme; and LIDAR mapping and application in the Limpopo and Zambezi basins. The TWM programme focusses on Southern Africa specifically - because of the conducive institutional and political operating environment and established relationships their – and as such provides both a deeper and broader level of support in this sub-region compared to CIWA. The current phase of SADC TWM is until March 2017 and DFID will be supporting one more phase until 2020.
- linkages and synergies exist between CIWA and SADC TWM programmes, primarily through CRIDF and LIDAR components and in relation to the Zambezi and Okavango river basins.
The potential for CIWA to continue delivering is reviewed in the appraisal case; and further information is also given on the relationship between CIWA and SADC TWM.

Gender and Equality Act - Gender and Social Inclusion
Gender inequality results from cultural and religious practices, and in some cases through laws and statutes, and intersects with other forms of inequality, such as class, ethnicity and race. Despite gains over recent years, women and girls typically remain more disadvantaged than men and boys in Africa, and face specific challenges that deny them access to and control over productive resources, including water, exacerbating their already disadvantaged position in the economy.  In the face of climate change and variability, women are especially vulnerable, and typically have less resources and capacity to respond or adapt to these changes. Women bear a disproportionate burden of the negative impacts of increased competition for water and climate change, further entrenching their disadvantaged position in society.
In many countries in Africa, women own or manage less than a quarter of the total agricultural land[62]. They are also disadvantaged in terms of access to extension services, which provide agronomic advice, and are able to access less than 10 percent of the agricultural credit offered to small-scale farmers in Africa overall[63]. Globally, women disproportionately shoulder the risks and physical burden of agricultural production. In Southern Africa, 60% of small farmers are female, and women make up 70% of the workforce for cash-crop farmers. They also provide between 80% and 90% of the labour for subsistence farming[64].Estimates suggest that women could increase their farm yields by 20–30 percent if they had equal access to land and other productive resources – which would lead to concrete benefits for food security and nutrition[65].
[62] FAO, „Gender and Land Statistics‟. http://www.fao.org/gender-landrights-database/data-map/statistics/en/
[63] ActionAid International et al. (2012) „What Works for Women: Proven approaches for empowering women smallholders and achieving food security‟, London. http://www.actionaid.org/sites/files/actionaid/what_works_for_women_-_final.pdf
[64] Harnessing the SADC Regional Agricultural Policy through smallholder agriculture, July 2014 http://www.esaff.org/images/stakeholder_policy_brief_20_8_14.pdf
[65] FAO (2011) „The State of Food and Agriculture 2010–11. Women in Agriculture: Closing the gender gap for development‟. Rome: FAO, p.5. http://www.fao.org/docrep/013/i2050e/i2050e.pdf
In the water and development sector, the issue of gender is particularly important. Research in sub-Saharan Africa suggests that women and girls in low-income countries spend in the region of 40 billion hours a year collecting water[66]. Providing access to clean water close to the home can dramatically reduce women’s workloads, and free up time for other economic activities as well as increase protection for women and girls brought about by reducing the distances to collect water. For their daughters, this time can be used to attend school.
[66] UNIFEM (now UN Women). 2009. Progress of World's Women. Who Answers to Women? Gender and Accountability. p. 36.
There is significant evidence that the beneficial impact of development and water projects is enhanced by the involvement of both women and men[67], while lack of attention to gender issues and initiatives can reinforce inequalities and increase gender disparities between women and men. In addition, involving both women and men in the design and implementation of interventions can result in innovative and sustainable solutions to water problems; improve the effectiveness of investments; make projects more sustainable; enable optimal social and economic returns from infrastructure investments; and ensure improved attainment of development goals, such as reducing hunger, child mortality and improving gender equality. [68]
[67] See, for example: Mainstreaming Gender in Water Management http://www.undp.org/content/dam/aplaws/publication/en/publications/environment-energy/www-ee-library/water-governance/resource-guide-mainstreaming-gender-in-water-management/IWRMGenderResourceGuide-English-200610.pdf;
[68] World Water Development Report 2012
Addressing gender mainstreaming is considered further in the appraisal of thematic options and in the appraisal of the preferred delivery mechanism.

Impact, Outcome and Results
Impact, outcomes and indicative results are set out at the end of the appraisal case.

Appraisal Case

The appraisal case is structured as follows:

Section A -	Assessing the feasible options around thematic focus

Having identified in the strategic case the considerable need for intervention and support in transboundary water management across Sub Saharan Africa, this section examines the appropriateness of a response involving a combination of intervention across the 3 key themes (noted in the strategic case) – institutions, infrastructure and information.

Section B -	Assessing the potential delivery mechanisms

Based on the preferred thematic focus of the next phase of the programme, this section appraises the feasible delivery mechanisms and identifies the preferred delivery mechanism.

Section C -	Presenting the Theory of Change for the preferred option

This section illustrates how the preferred delivery mechanism engage on transboundary water management process and effect changes at the outcome and impact level.

Section A - Assessing the feasible options around thematic focus
The strategic case identifies three primary focus areas for intervention to help improve transboundary water management in SSA: institutions, information and infrastructure.

Information: the collection, storage and dissemination of up-to-date data in such a way that it can practically be analysed and used to produce information that supports effective decision making over the allocation, treatment and use of water resources .

Institutions & capacity building/institutional strengthening: the existence of organisations with the mandate, legitimacy and capabilities (technical, legal, financial and managerial) to take and implement effective, gender-sensitive and socially equitable decisions about water resource management and development.

Infrastructure: the existence of adequately designed, appropriately located, climate resilient and well maintained water infrastructure as an important pre-requisite for climate resilient growth.

The ‘three I’s’ framing is instructive when thinking about how DFID support to the water sector can best be targeted. Appraisal of the most appropriate combination of these thematic elements in Africa was considered in detail in the DFID Business Case for the Transboundary Water Management Programme in Southern Africa. This considered the following options[1]:
[1] A sole focus on information was excluded – experience has demonstrated how well intentioned investments in sophisticated data collection and analysis become redundant when capacity, training and internal change management approaches are not pursued in parallel.
- Option 1: Information and Institutional Strengthening
- Option 2: Infrastructure only
- Option 3: Information, Infrastructure and Institutional Strengthening
- Option 4: The counter-factual (do-nothing)
This analysis included appraisal of quality of evidence, climate and environment aspects, gender and inclusion aspects, and political economy dimensions, and economic evaluation. Based on this the preferred thematic option was Option 3 – that is to say DFID support should comprise a combination of all three elements of Information, Infrastructure and Institutional Strengthening.

Section B - Assessing the potential delivery mechanism(s)
What is the preferred delivery mechanism?
This section considers delivery mechanism options for delivering the three I’s framework for TWM support in SSA. There are at least four delivery mechanisms that could be considered[2]:
[2] To note that the Do Nothing counterfactual was considered within the appraisal of Thematic Options
1. Continued support for the World Bank managed Cooperation in International Waters in Africa (CIWA) program
2. Provide support to the African Water Facility
3. Expansion of the existing CRIDF mechanism to address TWM issues outside of SADC
4. Establishment of a new funding mechanism
Costs and benefits of each option
This business case assumes that DFID will invest a total of £4.5 million under each option for delivery. Quantifying and monetising the benefit of DFID investment in any of the proposed delivery mechanisms is challenging, as attempting to quantify and compare benefits across such a diverse range of delivery mechanisms with different mandates would be inaccurate. Rather, the focus is to assess which mechanism would be the best in delivering the three I’s approach to TWM in SSA as identified in the strategic case.
In the section below we look at each of these delivery mechanisms in turn and evaluate their suitability, including facets such as: alignment with DFID Theory of Change for TWM support in SSA, specifically the three Is approach (information, institutions and infrastructure); where possible ,the potential financial and economic benefits/costs relative to other delivery mechanisms; ability of the mechanisms to absorb additional DFID support
Option 1: DFID to continue providing support to CIWA
DFID to provide CIWA with £4.5 million as a means to support delivery of effective transboundary water management in sub-Saharan Africa. CIWA is a multi-donor trust fund established in 2011 and represents a partnership between the World Bank and the governments of Denmark, Norway, Sweden, the Netherlands, and the United Kingdom. CIWA supports riparian governments in SSA to unlock the potential for sustainable and inclusive growth, climate resilience, and poverty reduction by addressing constraints to cooperative management and development of international waters.
CIWA’s programmatic focus fits well with DFID’s Theory of Change (TOC) for support to (TWM) in SSA. Specifically, CIWA recognises the benefits from supporting the three I’s, Information, Institutions and Infrastructure as reflected in its current funding portfolio split. CIWA has the capability to engage on a spectrum of scales of infrastructure, and has particular strength in relation to development of larger scale water infrastructure, which often manifest more direct financial and economic benefits. Within CIWA’s current portfolio of $73 million, 43% of this is spent on large-scale infrastructure (8% on small-scale infrastructure) and 50% is spent on institutions, information and capacity building. With the set up of the Trust Fund and the underlying support architecture of the World Bank, absorption of additional finance would not be a problem, in fact is actively sought by CIWA in order in increase its scale of impact.
DFID has consistently assessed CIWA more recent performance as being strong[69]. Currently the number of people directly benefiting from improved water resources management and development in target basins through projects supported by CIWA is estimated by CIWA at 43 million through potential investment projects influenced and further 5.6 million through mobilised investments influenced by CIWA[70]. More detail on CIWA engagement and achievements to date can be found via the following link CIWA's Annual Report and Results Framework
[69] CIWA received an ‘A’ rates programme score from DFID in 2012,2013 and 2014
[70] NB: these are inevitably indicative figures due to the stage of analysis associated with the stage in the project cycle of many of the investment projects; and will be refined as the more detailed feasibility and other analysis is conducted through CIWA support and the projects advance in the cycle
CIWA aligns well with DFID’s evolving policy, strategy and engagement regarding regional integration and climate change. In particular it has a strong fit with the UK International Climate Finance Implementation Plan -primarily regarding adaptation objectives[71]. CIWA’s objectives not only align very well with UK objectives but are also well aligned with WB core mainstream business, including concerning infrastructure, poverty reduction and climate change, meaning that important synergies with wider Bank major lending operations can be (in fact there are examples already) achieved for greater impact.
[71] DFID, 2014, Annual Programme Review
Since inception CIWA has delivered a multitude of multi-faceted benefits related to long-term strengthening of information, institutions and investments in priority basins and short-term catalytic work. CIWA has not calculated a portfolio benefit cost ratio for the projects that it has supported in SSA but does provide evidence in terms of the number of beneficiaries and the net benefit per individual as well as the benefits in terms of additional financing secured for these investments. In this respect CIWA showed value for money with a potential beneficiaries ratio of 1.34 beneficiaries/US$ contributed and an investment financing influence ratio of 263, i.e. on average for every dollar that CIWA contributed, the investment financing that it influenced (potential and mobilized investments) was US$ 263[72].
[72] CIWA Annual Report 2015
At a project level the Kariba Dam Rehabilitation project provides just one illustrative example of the type of benefits that CIWA brings. CIWA played a key role in the initiation of the US$294 million Kariba Dam Rehabilitation Project, which secured financing from the World Bank, The European Commission, The African Development Bank, Sweden and the Zambezi River Authority (ZRA). CIWA’s strategic and flexible support was able to provide a platform to influence and forge key partnerships and leverage significant external financing using partnerships where they have a comparative advantage. The investment will assist ZRA in reinforcing the reliability of the dam, which provides more than 50% of Zambia and Zimbabwe’s electricity and securing the long-term safety of an estimated 4.5 million people through securing their lives and livelihoods.
Through its current engagement on CIWA, DFID is very familiar with the technical, management and financial arrangements, which is advantageous.
Option 2: DFID to provide £4.5 million in support to the African Water Facility
The African Water Facility (AWF) is an initiative led by the African Ministers’ Council on Water (AMCOW) to provide grants and expert technical assistance to implement innovative water projects and raise investment for water projects throughout Africa. Hosted by the African Development Bank (AfDB), AWF has developed 84 projects in 51 countries, mobilising 151.2 million euros from 15 bilateral, multilateral financial institutions, foundations and African governments. AWF provides grants of 50,000 euros to 5,000,000 euros to water projects that need financial and technical help for implementation around:
- Project Preparation: The AWF provides financial and technical assistance for the preparation of high quality pre-feasibility and feasibility studies, investment plans, and structured public, private and public-private partnership operations;
- Water Governance: Grants provided in this sector go to strengthening water governance on a national, regional and transboundary level that creates an environment conducive for effective and sustainable public and private investments;
- Water Knowledge: Support in this sector typically includes information management, knowledge generation and dissemination and data collection; and
- Small-scale Pilot Projects: These projects tend to be small, strategic, innovative and catalytic investment projects that are community-driven or located in fragile states with promising ideas with scalable intention.
AWF works with member countries of the AfDB, political subdivisions or agencies working within these countries, or regional agencies or institutions concerned with water resource development in Africa. AWF funding has supported transboundary and basin projects like the Support for the creation of the Volta River Basin Authority. On average, each one euro contributed by the AWF has attracted a further 35 euros in additional investment. AWF projects have impacted 29 million people across Africa.
AWF therefore does engage across the thematic areas of interest. However, its focus is not exclusively regional (as is the case with CIWA), with individual country level support making up a significant part of its action. So while AWF could absorb additional finance, this attenuates the level of impact likely at transboundary level, both in terms of financial resource allocation and in terms of dedicated human resource support and direct transboundary implementation experience. Past engagement with AWF revealed that there were issues of long delays in moving from concepts to implementation, with associate uncertainty in disbursements and results. Historically, AWF has tended to focus on smaller size projects (as still evidence by its grant thresholds).
Option 3: Expansion of the existing CRIDF mechanism to address TWM issues outside of SADC
CRIDF, also funded by DFID under its SADC TWM programme, was set up to design and implement small scale water infrastructure in the SADC region. The expansion of CRIDF beyond SADC would necessitate a major shift in its geographic and technical mandate. This would be disruptive and would require renegotiating and repositioning it with existing SADC partners. It is still important for CRIDF to mature its relationships and delivery specifically with stakeholders and member states in the SADC region; an expansion of mandate would pose risks in this regard. In addition while CRIDF has demonstrated flexibility and proficiency in executing infrastructure projects it has typically worked on smaller scale infrastructure with transformational development impacts – which are a feature of its value for money proposition for DFID.
Option 4: Establishment of a new funding mechanism
Commissioning and establishing an entirely new delivery mechanism with a similar objective to CIWA would be costly and time consuming disproportionately so for the level of resources currently available to be committed – and there would inevitably be a delayed start up and generation of results. It would create a competitor to CIWA and would be unlikely to foster a comparable level of development partner collaboration, as CIWA’s other contributors would be unlikely to withdraw their funding. DFID would incur significant transaction costs procurement costs and would be unlikely to be able to secure an effective managing/implementing partner with overhead costs as low as those offered by the World Bank Trust fund. Furthermore, without the Bank’s direct involvement the implicit benefits of World Bank engagement and the security of its balance sheet/credit rating would be lost.
Similarly, it is not seen as feasible or appropriate for DFID to set up direct bilateral support to a sub-set of prioritised transboundary river basins in SSA, in terms of transaction and implementation costs to DFID, the ability of DFID to provide timely and detailed technical oversight regarding each basin, and the undermining of the existing partnership developed with CIWA.

The preferred delivery mechanism
The multi-criteria analysis below makes it apparent that additional financing via CIWA would be the most suitable delivery mechanism. Each of the existing Transboundary Water Management funding mechanisms as presented below have a distinct focus and plays an important role in supporting the collective achievement of DFID’s goals for transboundary water management. However, this table demonstrates that CIWA offers very relevant and targeted services to address the preferred thematic focus.
To summarise, none of the other mechanisms offer the technical, managerial or financial capabilities of CIWA which benefits from operating as a World Bank Trust fund. The Bank can offer access to the capabilities and relationships established by its numerous country offices, and the longevity of Bank’s involvement in transboundary issues has been recognised in the Mid-Term Review of CIWA as a major contributor to its success to-date. As well as access to the Bank’s personnel the level of financial control and risk management associated with the World Bank offers advantages as does the high level of transparency and strong governance controls, which lead to the Bank being rated in the top 7 donor institutions, classified as ‘very good’ by the Aid Transparency Index, 2014. Because CIWA channels funds from multiple development partners it also provides an in-built co-ordination function. The alternative, channelling funds into an alternative mechanisms, would potentially undermine (or raise the costs of) coordination and create a competitor to CIWA.
Criteria	Climate Resilient Infrastructure Development Facility (CRIDF)	Africa Water Facility (AWF)	Cooperation in International Waters (CIWA)
Geographical scope	1	3	3
Engagement across Information, Infrastructure and Institutions	3	2	3
Focus on regional interventions	2	2	3
Project preparation	3	3	3
Focus on small to medium scale infrastructure	3	3	1
Focus on medium to large scale infrastructure	2	2	3
Ability to mobilise large scale finance	2	3	3
Convening capability and Formal relationships with Member States	1	2	3
Adsorptive capacity for SSA transboundary intervention	1	2	3
Familiarity, recent direct experience of successful implementation and client interface	3	1	3
TOTAL	21	23	28

Key 1 - Low relevance, alignment and/or ability to deliver
2 - Medium relevance, alignment and/or ability to deliver
3 - High relevance, alignment and/or ability to deliver

The direct experience and familiarity DFID already has with CIWA affords opportunities to further influence and help strengthen its strategy and implementation arrangements, and building on the evidence of the Mid-Term Review conducted on CIWA in 2015. This is discussed in more detail in subsequent sections of this Business Case.
Respective focus of CIWA and SADC TWM programmes
It is also relevant at this point to further examine the relationship and coherence of CIWA and the SADC TWM programmes, given that DFID already is a financier of both. They operate at different geographic scales (CIWA works across Sub-Saharan Africa in priority river basins, TWM in Southern Africa works in mainland SADC countries and basins). They focus on different interventions – for example CIWA supports larger scale critical water infrastructure planning and delivery, which will take a longer time to come on line, while TWM in Southern Africa more focused on smaller scale water infrastructure. The specific circumstances in SADC region (e.g. the SADC Protocol on Shared Water Courses) and the established stakeholder relationships allow for opportunities for a higher level of direct DFID programme support which can be realised by the proposed TWM programme. CIWA and TWM utilise different implementation modalities – CIWA works through World Bank architecture, capitalising on the advantages available from World Bank Group (e.g. convening power and technical rigour and due diligence suitable for larger scale, critical water infrastructure) which are important to CIWA’s interventions areas, whereas TWM in Southern Africa contains a flexible, private-sector facility model (CRIDF) that is responsive and is delivering smaller water infrastructure projects at relative pace. As such, CIWA is distinct but complementary to TWM in Southern Africa, and they are not substitutable programmes. This complementarity also manifests in direct collaboration at operational level where beneficial – for example, CRIDF is currently working jointly with CIWA with the Okavango River Basin Commission on a Member State led planning and prioritisation process for sustainable development and poverty reduction related investments.
Section C Theory of Change for the preferred option

The Theory of Change for CIWA, the preferred delivery mechanism, is summarised below. A more detailed results chain unpacking elements of the Theory of Change is presented in Annex A
Results
CIWA’s high level results envisaged by 2020 (current end date of Trust Fund) are as follows. The fuller CIWA results framework, to which all current financiers have subscribed is presented in Annex B.
- 10 year target to leverage $10billion; 50million people benefiting indirectly; at least 5 basins supported to Strengthen regional cooperation and integration to foster cooperative transboundary institutions for greater regional stability and creation of an enabling environment for shared sustainable growth.
- Strengthened water resources management to support evidence based knowledge for planning and decision-making to maximize development opportunities and minimize climate risks.
- Strengthened water resources development to support investments that improve resilience to climate variability and change, enhance food and energy security, and enable countries to follow a lower carbon growth path.
To achieve these results, the programme currently works in the Nile River, Niger Delta, Lake Chad, Okavango, Volta and the Zambezi River Basins.[3] It also is working with SADC Groundwater Institute and the ECOWAS secretariat. Information on progress made to date is discussed further in the Value for Money section and Section B Option 1: CIWA and can also be seen via CIWA's Annual Report and Results Framework
[3] All of which cover the following 30 countries: Angola, Burundi, Botswana, Benin, Burkina Faso, Cote d’Ivoire, Chad, Cameroon, DRC, Ethiopia, Egypt, Guinea, Ghana, Kenya, Lesotho, Malawi, Mozambique, Mali, Namibia, Niger, Nigeria, Rwanda, Sudan, South Sudan, South Africa, Tanzania, Togo, Uganda, Zambia, Zimbabwe.

CIWA Summary Theory of Change

Sustainability
Ensuring the sustainability of the interventions under the CIWA programme is central to the way the projects are set up and their scope of activities, and builds on active demand from stakeholders. CIWAs coverage and integrated approach across information infrastructure and institutional aspects directly reflects its focus on maximising prospects of sustainability. Recognising the complex challenges and substantial timelines involved to address issues, part of CIWA’s sustainability strategy is also to prioritise certain basins for sustained and more intensive engagement rather than spreading its intervention too thinly.
 For institutional capacity building, the programme will set out ‘pathways of change’ that demonstrate what aspects of institutional capacity will be strengthened through the programme (e.g. financial, technical, strategic etc.) and how that will enable the institution to deliver on its mandate into the future. A key focus will be on promoting financial sustainability so that CIWA can progressively reduce support. For activities focussing on information, emphasis on capacity to use that information and support on actual application is provided. In terms of infrastructure, The World Bank’s comprehensive assessment processes consider various technical, financial and management aspects key to understanding and ensuring the sustainability of the investment projects concerned. At a broader level, CIWA also shares and disseminates its knowledge and experience - facilitating replication and uptake elsewhere in the region and hence larger scale impact.
Other CIWA aspects pertinent to sustainability, risk management and longevity of impact include its approaches on gender, political economy and safeguards.
Gender mainstreaming
CIWA has progressively strengthened its approach on gender. Gender Mainstreaming in the CIWA Program occurs at both programme and project levels. While one must recognise the inherent challenges of mainstreaming gender in a program that focuses on upstream technical and policy support for multi-country cooperation on transboundary water resources (as opposed to providing direct financing for implementing development projects), CIWA has identified four key strategic areas for gender mainstreaming at the program and project levels where it is focusing its efforts: 1) gender-informed stakeholder engagement; 2) gender-informed climate resilience; 3) gender-informed allocation of water for multiple uses; and 4) gender-inclusive mitigation of conflict over water resources. These actions are and will be taken in relevant basins depending on the context, client demand and resource availability. At the programme level, CIWA has appointed a Senior Gender and Social Development Specialist who oversees the incorporation of gender perspectives into intervention design and implementation. Gender Mainstreaming Tools and Resources have been developed for application by CIWA Basin Teams.
A gender sensitive results framework plays a key role in influencing strategic considerations of gender issues in planning and designing CIWA-supported interventions. Similarly, gender-informed monitoring and evaluation guides assessment of differential outcomes of these interventions. Progress toward the program’s overall development objective is measured by assessing the dollar amount of the investments influenced by the program and the number of people who will benefit from those investments and other interventions of the program. Where data are available, the program gathers sex-disaggregated data for beneficiaries of the projects it influences.
Political Economy
As the strategic case makes clear, political economy issues are a major and challenging factor in regional engagement and action on transboundary water resources. CIWA has undertaken a number of political economy case studies for certain transboundary river basins. Based on this it developed CIWA specific tools and internal resourcing to proactively consider political economy issues in the design and implementation of CIWA interventions. CIWA recognises that the issues are not static so need to be built into review and monitoring and evaluation processes as appropriate. There has been interaction between DFID and World Bank Governance advises in order to ensure a suitable ex ante approach, even though it should be noted that learning and refinement through actual application and implementation is likely to remain key given the complexity and diversity of issues in play.
Safeguards
The central thrust of CIWA is highly aligned to strengthening management of water as a critical natural resource and dealing with associated climate and environmental dimensions, and it is making a significant contribution in this regard. CIWA is also helping Member States of river basins to access international climate finance, such as via its support regarding the Niger Basin Climate Resilience Investment Plan and the Lake Chad Climate Resilience Development Action Plan. Nevertheless, it is understood that infrastructure delivery elements can also pose risks, especially where larger scale infrastructure is involved. CIWA is well placed to identify and address such potential risks, through its mandatory use of the comprehensive and stringent World Bank’s safeguards.

Commercial Case

DFID will invest in CIWA as a means to pursue transboundary water management and cooperation in Sub-Saharan Africa. CIWA operates as a World Bank administered Multi Donor Trust Fund (MDTF), with both Bank Executed and Recipient Executed grant elements. Using this mechanism DFID is able to invest in a process alongside other development partners (DPs) without needing to take a lead role in its operational management.

The advantages of Bank managed trust funds includes their ability to mobilise strong technical experts with the skills required to undertake the enhanced supervision and enabling support to TWM activities that the DPs require. This pool of expertise is available both remotely and in-country through the Bank’s country offices, and has established relationships with regional transboundary institutions. These teams are typically able to respond promptly to particular needs and have a detailed knowledge of the local operating environment. The Bank also has considerable informal and formal convening power compared to many other actors, an important factor when promoting and facilitating dialogue across countries and sectors. Following some initial challenges with the operating model for CIWA, the mid-term review of its performance and last DFID Annual Review demonstrated improved management, with CIWA team making more of the strengths and synergy opportunities of the Bank architecture.

Management fees charged by the World Bank for administering a Trust Fund include a flat fee of 2% plus other charges depending on the level of services required. While CIWA has agreed a management cost ceiling for other charges of 6% with its funders for services provided, the 2015 Annual Report clarified that to date only 2% of the total program budget has been spent on management. While care must be taken in comparing management costs given subtle structuring differences that may apply, costs seen so far would appear to be less than that charged at commercial rates by a consultancy firm which would typically be between 10% and 15% of the programme budget. Since this agreement, WB has now formalised a policy seeking full cost recovery for managing Trust Funds (which UK, as a shareholder, has approved). This will see adjustment in the cost profile when applied to the case of CIWA in due course but based on expenditure rates noted above there is still substantial headroom to accommodate increase and still remain competitive in terms of charges. In any case, DFID will scrutinise and challenge as appropriate proposed adjustments (precise implications will be made clear at the forthcoming CIWA Advisory Committee meeting in October) to ensure VFM prior to confirming the amended Administrative Agreement.

By working through multi-donor Trust Funds, DFID is able to contribute to a process that facilitates the achievement of increased harmonisation amongst participating Development Partners who might otherwise run their own independent programs which could conflict or, at the least, require significant time to be invested in co-ordination. CIWA has also been able to demonstrate its ability to leverage funds from other organisations such as GEF. The CIWA 2014 Annual Review shows that for every dollar CIWA spends on a co-financed project it is able to leverage 1.75 US dollars[4]
[4] CIWA Annual Report, 2014 p. 80

The World Bank provides a well-established, and technically proven, set of procurement guidelines and procedures[73] for its own procurement and for recipient Government compliance. In addition, it is able to support Government through the provision of its procurement expertise located in its country office. The Bank also has a clear set of procedures for sanctioning corrupt and fraudulent practices in connection with Bank-funded or executed projects. It takes the issue of fraud and corruption very seriously and its anticorruption policies are recognised as being of a high standard by the Aid Transparency Initiative, which ranked the Bank in the top 7 donor institutions for transparency in 2014. The Bank requires from both the borrower and from the bidders “the highest standard of ethics” during the procurement and execution of contracts. The Guidelines define what is meant by fraud and corruption (in section 1.16 of the Procurement Guidelines and section 1.23 of the Consultant Guidelines). These definitions go well beyond the definitions used by other development banks and so evidence the commitment that the Bank has to reducing corruption.
[73] These include (i) "Guidelines: Procurement of Goods, Works, and non-Consulting Services Under IBRD Loans and IDA Credits & Grants by WB Borrowers" dated January 2011; (ii) "Guidelines: Selection and Employment of Consultants Under IBRD Loans and IDA Credits & Grants by WB Borrowers" dated January 2011; and (iii) “Guidelines on Preventing and Combating Fraud and Corruption in Projects Financed by IBRD Loans and IDA Credits and Grants” dated October 15, 2006; and (iv) introduction of Exceptions to National Competitive Bidding Procedures.

Although there are many positive features of channelling DFID’s investment through these Trust Funds, this mechanism does present some risks, mostly around potential delays in project procurement processes. However, these risks are also present in other delivery modalities. There is also a trade-off regarding the risk of delay – which is commensurately higher assurance of transparency, rigour, probity and minimising opportunities for fraud and corruption in the WB procurement process The semi-annual review process will provide a regular opportunity for these and any other risks to be monitored and for immediate remedial action to be taken, if required. All key decisions and key documents will be stored so that reliable audit trails are available for the funding processes that are followed. A more detailed risk matrix is set out in the Management Case and outlines mitigation actions for some of the risks identified.

Value for Money (VfM)
Overall value proposition:

Based on the economic evaluation undertaken on the technical thematic options (see Appraisal Section) it is recommended that DFID continue to support all three themes critical to the development of climate resilient water management and development (i.e. a combination of all of information, institutions and infrastructure support – the 3 Is). The appraisal estimated that support for all three aspects would have a positive Benefit to Cost Ratio (BCR) of around 1.40 (at a 10% discount rate). It is worth noting that the estimation used more conservative infrastructure estimates applicable to small to medium scale projects. Additional economic benefits are likely to be realised when emphasising - as CIWA does - more investment in larger infrastructure projects, such as hydropower and large scale irrigation which also have greater potential for the leveraging of additional funds and greater financial returns (although, at such scale, particular care needs to be taken to confirm social and local level returns not just macro level returns). Specific value for money (VfM) benefits associated with supporting across the 3 ‘I’s include:

- Enhancing the availability, and institutional capacity to process, hydrological and climatological data, to inform the appropriate planning, design and management of climate resilient infrastructure. Strengthening information and institutions will build a sustainable foundation on which the benefits of improved climate resilient infrastructure can be realised.
- Building strong relationships with national and regional water institutions in the prioritised international basins will assist in the identification of potential projects and support sustainable implementation by encouraging leadership and ownership and realising in-kind and other resources to enable effective management.
- Benefits from maintaining institutional support that help avoid the loss of trust, political will and momentum gained to date
- The likelihood that a lack of support from DFID for the timely implementation of climate resilient infrastructure would hinder development of critical infrastructure and constrain the potential for economic growth in the respective basins. Further, delay in the incorporation of climate resilience into infrastructure planning is also likely to contribute significant additional costs for later implementation given higher remedial costs (‘prevention better than cure’).
- Benefits in terms of continuation of support and the avoidance of additional transaction and commissioning costs for the establishment of new delivery mechanisms, and the associated delays in achieving results on the ground.

CIWA specific VfM attributes:

CIWA tracks VfM related metrics such as[74]:
[74] CIWA Annual Report 2015
- Investment financing influence ratio (at 263 as of 2015, i.e. on average for every dollar that CIWA contributed, the investment financing that it influenced (potential and mobilized investments) was US$ 263).
- Co-finance leverage ratio ( eg 1.75 as of 2014, ie that for every dollar CIWA spends on a co-financed project it is able to leverage 1.75 US dollars )

As noted above, large infrastructure projects of the nature that CIWA engages on have robust and attractive project level BCRs otherwise they will not be taken forward; this is another metric through which CIWA’s VfM can be tracked and assured.

While such ratios, as proxies, should only be taken as indicative rather than precise, they do demonstrate how CIWA is on the right trajectory and harnessing resources and/or influencing projects of substantial value on the way to subsequent impact at scale for sustainable growth, resilience and poverty reduction. And they are relevant evidence that CIWA represents sound Value for Money.

Recognising that considering VfM is not a static matter, CIWA continues to strengthen its overall VfM approach. In the first phase of the CIWA programme, DFID, via the Advisory Committee, introduced the Value for Money concept for more explicit tracking and reporting to the CIWA PMU and other donor stakeholders. This resulted in the World Bank developing a VfM matrix for the programme which outlines how the programme will achieve the following:

- Economy – fees, daily rates, overheads etc. and unit costs of specific inputs (including via WB procurements processes);
- Efficiency – number of days and/or staff required to deliver outputs, inclusion of recommendations that would improve the delivery of outputs or reduce fiduciary risks etc.;
- Effectiveness – elements of the proposals that would improve the overall impact of local technical capacity or introducing better management practices into the sector as a whole.

CIWA now reports annually with a dedicated Annex in its annual report on its progress in implementing and monitoring VfM . With an additional financial contribution, DFID will continue to engage to further entrench VfM principles in implementation and reporting of the CIWA programme.

Financial Case

DFID proposes an additional financial contribution to CIWA of £4.5m over 5 years (2016 – 2020 – the remainder current CIWA Trust Fund lifespan). DFID initially committed £10m to the World Bank’s multi donor trust fund (MDTF) which helped catalyse subsequent contributions from Denmark, the Netherlands, Norway, Sweden and recently, the EU. This £10m has already been fully disbursed to WB. At the time of writing, 91% of the total budget of US$74 million pledged from donors has been allocated. The below table provides a breakdown of the balance of funds .
Source: WB August 2016

As can be seen from the table above, there is currently a negative balance of circa. $4million when taking account of current income/deposits vs endorsed immediate commitments for FY17, and a much larger negative balance of about $26 million against the intended planned pipeline commitments. This only in part can be addressed by other donors fulfilling further deposits against their pledges, and demonstrates CIWA being constrained financially and not operating with funds in advance of need.

With the current pledges fully allocated, CIWA also has pipeline of concepts and plans for further use finance but cannot advance these further, including signing agreements, without new funds being pledged. It should be emphasised that developing appropriate and inclusive interventions at the regional level with strong ownership can take considerable time from concept to initiating implementation so proactive and early pipeline development is critical. While existing and new donors such as Sweden and Canada are intending to contribute finance (additional finance in the case of Sweden and a first contribution in the case of Canada) and are currently undertaking there internal appraisal processes they are at an earlier stage of decision making and approval than DFID.

In short CIWA is in urgent need of additional funds. In this context, DFID’s contribution of £4.5 million is a timely and needed contribution, which would facilitate further pipeline development and secure additional development results in line with CIWA and DFID’s TWM related objectives. This will help drive things forward but the amount is such as to preserve a suitable burden share for DFID compared to other current financiers. With the additional financing DFID would remain as the third largest contributor with a slightly increased burden share from 22 to 27% (and this burden share will decrease again once the anticipated funds from other like Sweden come on stream). Similarly in light of the urgency of need, the contribution is proposed as a single payment in 2016 (see below); meeting immediate needs in the interim while other donor funds will come on stream later (for example Sweden is appraising a further contribution in 2017),.

Payment profile for the Financial Contribution

Programme costs / (£ million)	2016/ 2017	2017/ 2018	2018/ 2019	2019 /2020	2020/ 2021	Cost over five years
CIWA	£4.5m	0	0	0	0	£4,5m
Total	£4.5m	0	0	0	0	£4.5m

Distribution of Budget

The CIWA budget is typically spread across three main areas:
- The basin sub-programmes (c. 75% of allocation)
- Catalytic sub programme (c.16% of allocation)
- Programme Management Unit (c.6% of allocation)
It is highly likely the portfolio will comprise C-DEL relevant projects, although at this stage it is not easy to allocate, given the demand-nature of the projects, where it is difficult to predict beforehand if projects will go ahead to full development.
Financial management and expenditure reporting
The funding of the MDTF will be administered through an Administration Arrangement between DFID and the World Bank. The agreement describes key contractual dimensions such as:
•	Administration of the contribution;
•	Exchange and investment of the contribution;
•	Administrative cost recovery;
•	Grants to recipients and downstream partners
•	Procurement;
•	Accounting and financial reporting;
•	Progress reporting; and
•	Disbursement and break clauses on cancellation and refunds.

The funding process is consistent with standard World Bank procedures for Trust Funds as outlined in the table below. Funds pledged into the Trust Fund will be allocated to specific projects. The CIWA Advisory Committee endorses the allocation of funds, where after CIWA develops a Grant Agreements for each intervention or project and funds are committed through standard World Bank fiduciary processes to allow for fund disbursement. The process is outlined in the figure below:

CIWA has up in the past experienced low levels of fund disbursement, largely due to the lengthy time frames in getting new basin projects approved and ready for implementation. The difficult and politically sensitive nature of transboundary water resource management has played a significant role in the time-frames taken to date. However, the programme now has a full suite of projects and has learned valuable lessons which have been instrumental in improving fund allocation and disbursement timelines. DFID has continued to influence the World Bank and the CIWA PMU to improve disbursement timelines through the Advisory Committee.

The World Bank provides the CIWA annual report which details programme, financial expenditure and disbursement progress, set against a results framework. The annual Advisory Committee meeting also provides a platform for the CIWA PMU to make a detailed presentation on financial expenditure to donor representatives. In addition, the World Bank’s Client Connect online platform provides real time financial updates on allocation and expenditure of received funds throughout the year, and DFID can access these figures through this platform.

A single payment of £4.75m will be paid into the CIWA Trust Fund according to standard procedures, upon finalising an amended version of the current DFID-World Bank Administration Agreement for CIWA. DFID will monitor expenditure through scrutiny of CIWA financial reporting and through the Advisory Committee mechanism. Capital assets procured will be subject to standard Bank procedures for Multi-donor trust funds and substituent Grant Agreements.

Assessment of Financial Risk
Overall the financial risks are moderate because of the World Bank’s rigorous financial and procurement systems, as well as excellent internal and external audit mechanisms to mitigate against this risk. In addition, DFID keeps track of audit plans, applies rigour in scrutinising all financial and audit reports, and liaises as relevant with the CIWA finance and management staff. A more detailed analysis of fiduciary risk is included in the programme’s risk matrix in the Management Case.

Audit requirements
The World Bank will provide an annual single audit report from the Bank’s external auditors which reviews the adequacy of their internal controls, as well as financial statements for all of the Bank’s cash-based trust funds. DFID has access to high level audit information via the World Bank’s Client Connect system. For Recipient executed Grants implemented under CIWA, independent annual audits are required as part of Grant conditions. Any return of funds will be handled in accordance with agreed DFID procedures.

Management Case

There is a range of management bodies that support and guide the management of the CIWA programme at different levels of engagement. DFID interfaces with all of these structures via the key role we play on the CIWA Advisory Committee (AC), which enables us to provide strategic advice, oversight and guidance across the entire programme, whilst allowing more detailed engagement at the basin/project level where relevant. The diagram below outlines the levels of engagement at strategic, oversight and coordination levels through the AC, the Consultative Group (CG), and the Basin Advisory Committee (BAC).

DfID’s engagement through CIWA’s project governance structures

Governance and Management Arrangements

The management and governance of the programme takes place at two levels namely:
1. at program level, focused on strategy and implementation of activities across the program,
2. at basin level with the focus upon the detailed activities within a basin support plan

The three structures outlined in the diagram above (the Consultative Group; Advisory Committee and the Basin Advisory Committee) provide a useful balance between strategic support and guidance. The CG provides input on the positioning and overarching strategy of CIWA, the AC provides advice on the strategic content of the CIWA portfolio and the programmatic level management, and the CIWA Programme Manangement Unit (PMU) provides technical coordination, supervision, quality assurance and day-to-day management and administration of the programme (PMU). The diagram below outlines the composition of the 3-tier management structure:

CIWA program strategic advisory and management structure

The Programme Management Unit (PMU)

The World Bank as manager of the CIWA MDTF undertakes day-to-day operational activities and retains the overall decision making authority linked to its fiduciary responsibility through the Programme Management Unit (PMU). The PMU, led by the Program Manager, is comprised of both management and technical staff responsible for managing all CIWA operations. The PMU provides high-level multi-sectoral technical input, oversight and quality assurance to the CIWA program, and day-to-day management and administration of the CIWA program and its projects. DFID will continue to interact formally with the PMU at AC meetings, and more informally during the year, and therefore can make recommendations to the PMU as to how it provides support across the program. World Bank Technical Team Leaders (TTLs) support and guide the basin projects. These TTLs are not purely dedicated to CIWA projects and as such provide the opportunity to link initiatives and leverage possible synergistic opportunities. DFID will continue to interact with the TTLs at the Basin Advisory Committee (BAC) meetings where appropriate and so at that platform can influence project level matters.

The Consultative Group (CG)

The CG comprises of CIWA donors, fund recipients, RECs, RBOs and other national and regional stakeholders. DFID can participate in the CG and can therefore input in discussions about strategic intent, alignment with other continental and regional programmes, as well as broader programmatic trends. The recently completed mid-term review of the CIWA programme does highlight the need to revisit the functionality of the CG to ensure wider stakeholder input to inform the strategic direction of the programme. In this next phase of funding, DFID will monitor the implementation of the MTR Action Plan to ensure that the CG is revitalised, or that CIWA explore other platforms that can provide this level of discussion.

The Advisory Committee (AC)

DFID, as with other development partners, is represented at the Advisory Committee level. The function of the AC is to provide strategic advice and guidance to the World Bank regarding CIWA’s programmes and plans. The AC meets at least annually, but can meet more frequently where the need arises. The Committee has both a consultative and an advisory role and provides a forum for contributing development partners to meet, exchange information, and consult on a regular basis. This provides DFID with a suitable platform to discuss programmatic matters of project level intent and to have oversight on progress and performance. The committee formally meets annually, and has ongoing communication and meetings throughout the year.

As such DFID, as a member of the AC, can:
- Review CIWA program strategy in order to provide guidance on the overall content and direction of the program and ensure the use of Trust Fund resources to meet the objectives of the program;
- Review “Justification Notes” to assist with the decision for CIWA to begin sustained engagement in a prospective basin;
- Review “Project Concept Notes” to assist with the decision for CIWA to allocate funding for specific projects in basins where CIWA has sustained engagement;
- Review of CIWA Support Plans as part of relevant Basin Advisory Committees in order to provide guidance on the content and direction of the program in basins where CIWA has sustained engagement (this applies to basins where AC members have a particular interest, experience, or expertise; AC members are not expected to review all CSPs in detail);
- Provide feedback on planned and on-going projects to help ensure alignment with basin strategies and target results as well as with overall program strategy and target results;
- Review overall program implementation progress, financial and risk management, and administration;
- Review CIWA funding needs and promotion of participation of new donors to close funding gaps and support new program components;
- Encourage donor harmonization, either through the CIWA Trust Fund or bilaterally, for potential investments;

The Basin Advisory Committee (BAC)

CIWA has currently prioritised certain international basins for sustained engagement and support. At the basin level, the BAC structure is aimed at providing the guidance and oversight to ensure that the projects within the basin or across the region achieve their objectives. A key role of the BAC is to ensure coordination with other on-going activities across the basin. Thus the BAC also provides an opportunity for interested partners to consult and contribute to discussions on basin plans and priorities (at a greater level of detail than happens via the AC which is more focused on CIWA programmatic and portfolio level. The membership of the BAC depends on the basin context. It can include representatives from the riparian states, regional bodies such as the RBOs and the RECs, international agencies such as GWP or the IUCN, CIWA donors, other non-CIWA donors (such as GIZ who typically have bilateral support agreements), other interested stakeholders, and the CIWA/ World Bank staff.

DFID Internal Management

The CIWA programme will be managed within the Resilience Pillar of DFID’s Africa Regional Department. The DFIDSA Climate Change Team leader will assume the role of Senior Responsible Owner, one Climate and Environment Adviser will act as lead adviser, and one Programme Manager will oversee programmatic, financial and contract management; due diligence and compliance with other DFID corporate processes.

Risk Management
Working in transboundary water basins is inherently risky, and requires a clear, robust and more regular monitoring & reporting framework that enables a more adaptive management approach. DFID’s engagement in the in the CIWA AC has already helped clarify and strengthen risk management (and alignment with DFID needs). DFID will continue to engage with the WB on risk management. Risks are identified and managed both at program and basin levels as outlined in the risk assessment below:

Risks	Probability	Impact:No mitigation	Mitigation	Residual Risk
Programme Level Risks
Political: Political context makes working on transboundary water management difficult	Possible	Major	Strategically place program amongst array of international programs / Longer term diplomacy to unlock issues / Diversity of projects / Robust political economy analysis applied to CIWA intervention design and implementation	Moderate
Operational: Technical complexity of / international water projects / can lead to long-term delays	Possible	Major	Draw on technical expertise available through the World Bank’s Water Global Practice / Engage regional experts working on transboundary water management / .	Minor
Operational: Unforeseen delays due to unexpected events such as economic, climate shocks, or transfer of key decision-makers	Possible	Moderate	Programme management structures to meet regularly. / Allow for some flexibility to accommodate some degree of slippage or reprioritisation of different activities.	Minor
Financial: insufficient resources mobilised to meet CIWA project demand	Likely	Severe	Develop longer term funding strategy / Management of project pipelines / Program management structures functional	Moderate
Fiduciary: Financial mismanagement or fraud	Unlikely	Major	WB has strong financial management procedures / Monitoring of budget forecasts, financial reports and activity plans by WB will reduce the probability of the risk from occurring. WB conduct assessments on Grant recipients to verify financial management capability; audits will also be conducted annually. DFID will liaise with CIWA financial staff as necessary on status and any issues arising.	Minor
Sustainability: Support for investments in institutions, information systems, and infrastructure is not sustained or advanced by riparians.	Likely	Major	Program response to basin needs should make interventions appropriate for the longer term / Robust political economy analysis applied to CIWA intervention design and implementation / Inclusive stakeholder design process / Ensure adequate attention to longer term financial sustainability issues	Moderate
Delivery: Failure to secure / leverage financing for projects	Likely	Major	Given the type of projects that will be developed under this programme there is a risk that the World Bank will fail to mobilise additional finance for the projects. Early engagement with financiers is key. They will also explore the potential of climate finance and private sector finance to make a contribution. (nb This risk is present with all delivery options, not something specific to World Bank)	Moderate
Delivery: Infrastructure projects poorly designed	Unlikely	Severe	The World Bank has a strong track record relating to the design of water infrastructure projects and strong engineering and related technical skills. The residual risk is therefore deemed minor.	Minor
Operational: Management or design problems result in failure to deliver anticipated results	Unlikely	Major	The programme will be entering its second phase of implementation and has thus far showed marked improvement in the successful delivery of activities, and we anticipate that the second phase will build on that success. However, should challenges be experienced, the various monitoring mechanisms including the AC, BAC and CG, progress reports and the annual review, will identify bottlenecks early and provide opportunities to address identified issues.	Minor
Basin level Risks
Capacity: Insufficient institutional and human capacity in the Region affecting CIWA results	Likely	Major	Institutional and human resource capacity in many relevant institutions is typically weak. This can constrain pace of progress and results achieved. The programme seeks to directly support capacity building and will factor in capacity bottlenecks to mitigate. However, there are limits to scale of CIWA support and in certain basin contexts the breadth and depth of stakeholders and the required processes and needs may mean there is a level of residual risk This does not mean not engaging, rather adjustment to the level of ambition and expected pace of progress. Longer term engagement by Bank staff identifies capacity constraints / Additional technical resources provided to bolster capacity	Moderate
Stakeholder engagement: Inadequate prioritization of stakeholder engagement and coordination (Intermediate Results Area 4) and engagement with organizations that represent the interest of women and vulnerable people	Possible	Moderate	Design processes must consider stakeholder engagement from outset; Ensure engagement at various stages of the project cycle / Identify specific engagement requirements for marginalised groups / Ensure WB is sourcing Social Development advice from its Practices of experts to provide guidance on programming for vulnerable groups including women and girls	Minor
Tracking and analysis of Programmatic level delivery is hindered due to reliance only on individual project level M&E.	Unlikely	Moderate	MTR flagged this issue and action is underway by PMU to improve the situation, principally around: Strengthening M&E frameworks and reporting from basin/project level to programmatic level; and / Improving knowledge management to support sharing of lessons learned	Minor

Partnership principles
It is not feasible to conduct a full partnership principle assessment (PPA) where a programme is operating in a regional rather than national context. PPAs will not normally apply to regional programmes.  However DFIDSA will, if considered necessary, ask for either a partial or full PPA on aspects of a regional programme where significant actions will take place at a country level, if there are risks related to the PPs and there is no PPA in place for that country. If a DFID prepared PPA exists it will be used to inform spending decisions. In the case of the transboundary water management programme, the Head of DFIDSA has considered its operating environment and concluded that no PPA needs to be carried out.
Results Framework
The CIWA programme is governed by a multi donor trust fund with five other donor partners contributing in addition to DFID. As a result, the World Bank has developed a results framework for the programme that meets the results and reporting needs of various stakeholders. DFID, as an active member of the Advisory Committee has provided guidance and significant input into the development and endorsement of the CIWA results framework, against which results are measured. The framework is reviewed annually at the AC meetings to ensure the framework remains relevant to the needs and targets of the programme.
Monitoring and Evaluation

The adequate monitoring and evaluation of a programme of this scale will be crucial to ensuring that outcomes and impacts are delivered to beneficiaries. Monitoring and evaluation of programme performance is central to determining whether outputs are being delivered in accordance with scheduled work plans and in determining efficiency of expenditure against outputs.
A Mid-Term Review (MTR) of the CIWA Programme was conducted in 2015 and concluded in January 2016. While favourable overall, a number of issues were identified (see Annex C). The WB and CIWA team responded constructively to the MTR and developed an action plan based on the recommendations which has been under proactive implementation during 2016. Progress in implementation will be discussed at the forthcoming AC meeting in October 2016, allowing DFID to confirm satisfactory action prior to finalising the amended Administration Agreement and actual funds transfer.
One of the major monitoring tools that the programme will use is the CIWA Results framework (see Annex B). CIWA takes a programmatic framework approach, and as such the results framework captures a diverse basket of interventions, the detail of which will vary according to the political economy, the stakeholders, the technological solution and other facts. It is therefore a broad-framework under which a range of diverse activities can be undertaken appropriate to the diverse needs across SSA. The broad framework allows and essential level of flexibility in order i) to not be excessively prescriptive i) to navigate the political economy, ii) to promote innovation, iii) to allow a level of opportunism and, iv) to facilitate adjustment during implementation.
Other elements of the CIWA M&E include:
Annual Reports: CIWA issues Annual Reports covering technical and financial and progress, risk management and other relevant aspects.

Advisory Committee annual meetings and other meetings: the AC will formally meet annually to review progress against results framework outcomes and outputs and ensure that the programme is on track, and provide technical and advisory inputs. DFID also has ongoing ad hoc discussions with members of the CIWA Advisory Committee and the WB CIWA team, to provide timely additional guidance and steer on technical and management aspects of the programme, as well as receive progress updates. In addition, the DFID programme manager will interact on a as needed basis with the Bank’s financial and programme managers to ensure adherence to DFID financial, budgeting and forecasting requirements, and monitor programme expenditure. Where relevant, DFID will also participate in Basin Advisory Committee processes.

Annual Reviews: DFID-SA will undertake mandatory annual reviews which will measure progress against annual milestones and VfM metrics. It will also look at budget execution and all aspects of implementation arrangements, as well as governance structures. The annual review process will provide recommendations to enhance delivery on activities and milestones that are facing challenges or slower to deliver.

Evaluation: As noted above a mid-term review was completed in January 2016) and made recommendations for remaining implementation. The World Bank, through the CIWA PMU, has developed an action plan to implement recommendations and track progress against these commitments. An end of programme independent evaluation will be commissioned in 2019/20 by the WB to examine results and establish the relevance, efficiency and effectiveness of the CIWA model, as well as to determine the extent to which programme outcomes and impacts have been realised, the extent to which these can be attributed to the intervention and the existence of any positive or negative unintended outcomes.. The evaluation will also provide best practice and lessons for DFID, the World Bank and other stakeholders on the continent, and will be useful for any future Water programming in Africa.

LIST OF ABBREVIATIONS AND ACRONYMS

AC	Advisory Committee
AfDB	African Development Bank
AMCOW	African Ministers Conference on Water
ANBO	African Network of Basin Organisations
AU	African Union
AWF	African Water Facility
BAC	Basin Advisory Committee
BCR	Benefit Cost Ratio
BMZ	German Federal Ministry for Economic Cooperation and Development
CBA	Cost Benefit Assessment
CG	Consultative Group
CICOS	International Commission for the Congo-Oubangui-Sanga Basin
CIF	Climate Investment Fund
CIWA	Cooperation in International Waters in Africa
CSP	CIWA Support Plan
CRIDF	Climate Resilience Infrastructure Development Fund
DFID	Department for International Development
DP	Development Partners
DRC	Democratic Republic of Congo
EAC	East African Community
ECOWAS	Economic Community of West African States
ENSAP	Eastern Nile Subsidiary Action Program
FTS	Full Time Staff
GBP	British Pound
GDP	Gross Domestic Product
GIZ	Deutsche Gesellschaft fur Zusammenarbeit
GWP	Global Water Partnership
ICA	Infrastructure Consortium for Africa
IBRD	International Bank for Reconstruction and Development
IPCC	Intergovernmental Panel on Climate Change
IUCN	International Union for Conservation of Nature
JWC	Joint Water Commission
KOBWA	Komati Basin Water Authority
KfW	German Development Bank (Kreditanstalt für Wiederaufbau)
LCBC	Lake Chad Basin Commission
LIMCOM	Limpopo Watercourse Commission
LTA	Lake Tanganyika Authority
LVBC	Lake Victoria Basin Commission
M&E	Monitoring and Evaluation
MDTF	Multi Donor Trust Fund
MDG	Millennium Development Goal
MoW	Ministry of Water
MRU	Mano River Union
MTR	Mid-Term Review
NBA	Niger Basin Authority
NBI	Nile Basin Initiative
NELSAP	Nile Equatorial Lakes Subsidiary Action Program
NEPAD	New Partnership for African Development
NGO	Non-governmental Organisation
NPV	Net Present Value
OECD	Organisation for Economic Cooperation and Development
OKACOM	Okavango Commission
OMVG	Organisation pour la Mise en Valeur du Fleuve Gambie
OMVS	Senegal River Basin Development Organization
ORASECOM	Orange-Senqu Watercourse Commission
PIDA	Programme for Infrastructure Development in Africa
PJTC	Permanent Joint Technical Commission
PMU	Programme Management Unit
PPP	Public-Private Partnership
RBO	River Basin Organisation
REC	Regional Economic Community
SA	South Africa
SADC	Southern Africa Development Community
SITWA	Strengthening the Institutions for Transboundary Water Management in Africa.
SSA	Sub Saharan Africa
TAC	Technical Advisory Committee
TEEB	The Economics of Ecosystems and Biodiversity
TOC	Theory of Change
TTL	Technical Team Leader
TWM	Transboundary Water Management
UK	United Kingdom
UN	United Nations
UNDP	United Nations Development Programme
UNEP	United Nations Environment Programme
UNICEF	United Nations Children’s Fund
USD	United States Dollar
USAID	United States Aid
VBA	Volta Basin Authority
VfM	Value for Money
WACDEP	Water and Climate Development Programme
WASH	Water Sanitation and Hygiene
WB	World Bank
WHO	World Health Organisation
WMO	World Meteorological Organisation
WRC	Water Research Commission
WSDP	Water Services Development Plan
WWF	World Water Forum
ZAMCOM	Zambezi Watercourse Commission
ZRA	Zambezi River Authority
REFERENCES