## Venezuela Crisis logframe
Please refer to the Smart Guide for advice on completing the various fields in the logframe.
Note: we do not publicly dislclose the names of our partners inside Venezuela
PROJECT TITLE | Humanitarian Response to the Venezuela Crisis (300828)
IMPACT | Impact Indicator 1 |  | Baseline | Milestone 1 (September 2019) | Target (April 2020)
Lives saved, suffering prevented or alleviated, dignity preserved. | Total number of people reached with humanitarian assistance | Planned | 0 | N/A | 1399849
|  | Achieved |  |  | 1685835
Source
Partner reporting
OUTCOME | Outcome Indicator 1 |  | Baseline | Milestone 1 (September 2019) | Target (April 2020) | Assumptions
The most immediate assistance and protection needs of Venezuelans, including those on the move, are met and those who have migrated to Colombia are integrated into society. | Number of hospitals or healthcare facilities receiving support and improving care for Venezuelans as a result of UK support | Planned | 0 | 6 | 51 | The humanitarian impact of the crisis does not dramatically deteriorate.
|  | Achieved |  | Not available | 51
Source
Partner reporting
| Outcome Indicator 2 |  | Baseline | Milestone 1 (September 2019) | Target (April 2020) | Humanitarian actors have sufficient capacity, resources and access to mount an appropriate response.
| Number of vulnerable Venezuelans receiving WASH, nutrition and protection support as a result of UK bilateral support | Planned | 0 | 18400 | 1159150
|  | Achieved |  | 77200 | 1300000
Source
Partner reporting
| Outcome Indicator 3 |  | Baseline | Milestone 1 (September 2019) | Target (April 2020) | Humanitarian actors have sufficient capacity, resources and access to mount an appropriate response.
| Number of Venezuelan migrants receiving critical health, nutrition and protection services as a result of UK support | Planned | 0 | N/A | 240699
|  | Achieved |  |  | 385835.23
Source
IFRC Colombia and Regional appeals and reports
| Outcome Indicator 4 |  | Baseline | Milestone 1 (September 2019) | Target (April 2020) | The Government of Colombia maintains a progressive integration policy and has sufficient capacity and resources to implement its migration plan.
| Number of additional Venezuelan migrants with access to residency status, jobs, health and education services thanks to the policies of the Government of Colombia | Planned | 0 | N/A | 280000
|  | Achieved |  |  | 281557
Source
World Bank reports
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | Milestone 1 (September 2019) | Target (April 2020) | Assumptions
Life-saving assistance and protection to the most vulnerable amongst the Venezuelan population | Number of health facilities given essential and special emergency obstetric care commodities to strengthen the quality of MNCH services and contribute for the equitable reduction of preventable maternal and newborn deaths | Planned | Not applicable | 6 hospitals | 6 hospitals + 36 primary healthcare centres | The de facto Venezuela authorities allow unfettered access and security conditions are sufficient.
|  | Achieved |  | Not available | 18 hospitals and 20 outpatient clinics supported
Source
Partner reporting
| Output Indicator 1.2 |  | Baseline | Milestone 1 (September 2019) | Target (April 2020) | UK burden share applied
| (i) Hosptials given tools or spare parts for maintaining electricity, water and sanitation systems (ii) hospitals provided with medical supplies, equipment and/or training on advanced emergency-room trauma case (iii) healthcare facilities that are strengthened to enable provision of basic medical services (including the provision of outreach services to vulnerable communities) | Planned | Not applicable | N/A | (i) 1 hospital repaired (ii) 3 hospitals given training (iii) 4 health facilities strengthened
|  | Achieved |  |  | (i) 2 hospitals repaired (ii) staff in 3 hospitals given training (iii) 4 health facilities
Source
Partner reporting
| Output Indicator 1.3 |  | Baseline | Milestone 1 (September 2019) | Target (April 2020) | Partners are able to scale-up their operations.
| Number of people (children under 5, pregnant & lactating women) being nutritionally screened and receiving nutritional supplements | Planned | Not available | 15,000 children nutritionally screened; 5,000 children receiving supplements. | 27,000 children nutritionally screened; 5,000 children receiving supplements.
|  | Achieved |  | 0 | 26,872 children/PLW screened; 19,833 children/PLW received micronutritent supplements
Source
Partner reporting
| Output Indicator 1.4 |  | Baseline | Milestone 1 (September 2019) | Target (April 2020) | Downstream partners have the capacity and resources to implement activities.
| Number of primary school children accessing school feeding programme | Planned | Not available | N/A | 17000
|  | Achieved |  |  | 29390
Source
Partner reporting
| Output Indicator 1.5 |  | Baseline | Milestone 1 (September 2019) | Target (April 2020) | Partners are able to import adequate supplies, inlcuding medical.
| Number of people provided access to safe drinking water through the repair of water-supply systems and renovation of facilities, such as schools and bus terminals | Planned | Not available | 3000 | 1089650
|  | Achieved |  | 77200 | Over 1,300,000
Source
Partner reporting
| Output Indicator 1.6 |  | Baseline | Milestone 1 (September 2019) | Target (April 2020)
| Numbers of children accessing protection services (including GBV and PSS) | Planned | Not available | 10000 | 16000
|  | Achieved |  | 23391 | 9 CSOs/66 Child Protection Councils supported to reach 48,100 children/caregivers with protection services, case management and referral; 6,217 children accessing child-friendly spaces; 5,093 children and families receiving psychosocial services
Source
Partner reporting
IMPACT WEIGHTING (%) | Output Indicator 1.7 |  | Baseline | Milestone 1 (September 2019) | Target (December 2019)
40% | 4,500 nets and 2 treatment centres | Planned |  | N/A | 4,500 nets and 2 treatment centres
|  | Achieved |  |  | 4,500 nets and 2 treatment centres
|  | Source |  |  |  | RISK RATING
|  | Partner reporting |  |  |  | Medium-high
INPUTS (£) | DFID (£) |  | Govt (£) | Total (£) | DFID SHARE (%)
8050000
INPUTS (HR) | DFID (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | Milestone 1 (September 2019) | Target (April 2020) | Assumptions
Essential assistance and protection to Venezuelan migrants and refugees | Number of people receiving assistance to cover their shelter and settlement needs | Planned | 0 | N/A | 3688 | Host countries maintain open-door policies towards Venezuelan migrants and refugees.
|  | Achieved |  |  | 817.02
Source
IFRC Colombia and Regional appeals and reports
| Output Indicator 2.2 |  | Baseline | Milestone 1 (September 2019) | Target (April 2020) | IFRC and national Red Cross Societies capacity to maintain or scale-up activities in accordance with the number of migrants arriving in each country. Timely procurement and delivery of supplies and cash transfers.
| Number of people accessing livelihood interventions (multi-purpose cash, vocational training and/or productive assets) and services supporting basic needs | Planned | 0 | N/A | 6678.2
|  | Achieved |  |  | 6231.91
Source
IFRC Colombia and Regional appeals and reports
| Output Indicator 2.3 |  | Baseline | Milestone 1 (September 2019) | Target (April 2020) | Migrants population and host communities support and make use of services
| Number of services provided giving timely medical care, first aid and psychosocial support | Planned | 0 | N/A | 79531
|  | Achieved |  |  | 135608.48
Source
IFRC Colombia and Regional appeals and reports
| Output Indicator 2.4 |  | Baseline | Milestone 1 (September 2019) | Target (April 2020)
| Number of people accessing appropriate and sustainable water, sanitation and hygiene services | Planned | 0 | N/A | 138499
|  | Achieved |  |  | 217746.3
Source
IFRC Colombia and Regional appeals and reports
IMPACT WEIGHTING (%) | Output Indicator 2.5 |  | Baseline | Milestone 1 (September 2019) | Target (April 2020)
17% | Number of protection assistance services provided (Friendly spaces and Restoring Family Links etc) | Planned | 0 | N/A | 12131
|  | Achieved |  |  | 25431.52
|  | Source |  |  |  | RISK RATING
|  | IFRC Colombia and Regional appeals and reports |  |  |  | Medium
INPUTS (£) | DFID (£) |  | Govt (£) | Total (£) | DFID SHARE (%)
3270000
INPUTS (HR) | DFID (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | Milestone 1 (September 2019) | Target (April 2020) | Assumptions
Government of Colombia efforts to regularise the status and facilitate access to employment and basic social services for Venezuelan migrants and refugees, as well as the communities that are hosting them are supported. | Number of Venezuelan migrants on the RAMV (Administrative Registry of Venezuelan Migrants) as at June 8, 2018 that have been issued with a PEP and had their status regularised (Pillar 3 of the DPL: Support regularisation and integration of migrants) | Planned | 0 | N/A | 280,000, of which 125,000 are women | Baseline is from 2015 - we do not currently have up to date figures. GoC do not change commitment
|  | Achieved |  |  | 281,557, of which 139,586 are women
Source
WB appraisal document and GCFF progress report
| Output Indicator 3.2 |  | Baseline | Milestone 1 (September 2019) | Target (April 2020) | Baseline is from 2015 - we do not currently have up to date figures
| Number of migrants from Venezuela receiving services from either the National Employment Agency or the national health/social services system (Pillar 3 of the DPL: Support regularisation and integration of migrants) | Planned | 0 | N/A | 50,000 (cumulative figures between 2016-2019)
|  | Achieved |  |  | 115,012 (cumulative figures between 2016-2019)
Source
WB appraisal document and GCFF progress report
| Output Indicator 3.3 |  | Baseline | Milestone 1 (September 2019) | Target (April 2020) | Funds disbursed in a timely manner
| All prior actions and targets are met under Pillar 2 of the DPL (Foster productivity and growth in non-extractive sectors by strengthening the policy framework for trade facilitation, business regulation, innovation and green growth) | Planned | N/A | N/A | All met
|  | Achieved |  |  | All met apart from one which was almost met
Source
WB appraisal document and GCFF progress report
IMPACT WEIGHTING (%) | Output Indicator 3.4 |  | Baseline | Milestone 1 (September 2019) | Target (April 2020) | Funds disbursed in a timely manner
40% | All prior actions and targets are met under Pillar 1 of the DPL (Support fiscal sustainability measures and improved contingent liabilities management) | Planned | N/A | N/A | All met
|  | Achieved |  |  | All met apart from one due to lack of data
|  | Source |  |  |  | RISK RATING
|  | WB appraisal document and GCFF progress report |  |  |  | Medium
INPUTS (£) | DFID (£) |  | Govt (£) | Total (£) | DFID SHARE (%)
8000000
INPUTS (HR) | DFID (FTEs)
OUTPUT 4 | Output Indicator 4.1 |  | Baseline | Milestone 1 (September 2019) | Target (April 2020) | Assumptions
The response to the crisis is strengthened through DFID technical capacity/engagement, provision of key technical assistance to partners and financial support for vital short term surge positions within the UN | Number of UN standby partnership surge posts filled | Planned | 7 | 9 | 12 | High quality candidates are available for immediate deployment. UN stands up and SBP requests reduce.
|  | Achieved |  | 9 | 13
Source
SBP final reports
| Output Indicator 4.2 |  | Baseline | Milestone 1 (September 2019) | Target (April 2020) | Contracted six month advisory support in place from April 2019 with decision to be taken in August 2019 as to continuation of the post. Operating enviroment allows staff to work in Caracas.
| Number of HSOT Humanitarian Advisers in the region | Planned | 1 HCS, 1 HSOT Constractor | 1 HSOT Contractor managing the programme in region | 1 HSOT Contractor managing the programme in region
|  | Achieved |  | 1 HSOT Contractor managing the programme in region | 1 HSOT Contractor managing the programme in region
Source
HSOT HDT reports
IMPACT WEIGHTING (%) | Output Indicator 4.3 |  | Baseline | Milestone 1 (September 2019) | Target (April 2020)
3% | Enhanced coordination of the response in Venezuela through greater predictability, accountability and partnership | Planned | N/A | N/A | i) MSNA designed; ii) 3W reporting system reviewed; iii) UN Volunteers hired; iv) trainings with partners conducted
|  | Achieved |  |  | i) No MSNA conducted but four field-based needs assessment workshops undertaken; and one nationwide telephone survey on community perceptions of need and aid (reaching over 7,900 people); ii) 3W tools developed and implemented through clusters with monthly updates; iii) 18 UNV community monitors hired; and iv) 120 partners (1,190 people) trained in the Humanitarian Programme Cycle, including AAP, PSEA, protection and inclusion.
RISK RATING
|  | Partner reporting |  |  |  | Medium-low
INPUTS (£) | DFID (£) |  | Govt (£) | Total (£) | DFID SHARE (%)
680000
INPUTS (HR) | DFID (FTEs)