Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Policy Development Facility 2 (PDF 2)
Programme Value: £18.5m		Review Date: 03/10/2016
Programme Code: 203922	Start Date: 01/04/2015	End Date: 31/03/2020

Summary of Programme Performance
Year	2014/15	2015/16	2016/17
Programme Score	A / (Pre-contracting)	A / (Inception phase)	A / (First full year of implementation)
Risk Rating	Moderate	Moderate	Moderate

Summary of progress and lessons learnt since last review

The UK’s Policy Development Facility (PDF 2) has mobilised technical assistance to support President Buhari and his economic team’s emerging policy agenda. It has been a year of ‘responsiveness’ and has laid the foundation of support and policy influence for the next three years of the political cycle. It is now critical to leverage this base of support and influence for better policy outcomes for Nigeria. The programmatic choices of the next year will be instrumental to the programme’s overall success.

PDF has been responsive to opportunities with Nigeria’s Federal government, but importantly, is also helping to facilitate consultation on policy areas that may be having unintended harm on economic growth and the livelihoods of the poor. With Nigeria’s economy going into recession in the second quarter of 2016, helping to produce credible evidence and consultation processes can help influence some of the more damaging economic policies (such as the Central Bank’s delay in allowing the naira to adjust to lower oil prices and the accompanying foreign exchange restrictions it introduced). This type of influencing role has been valuable over the last year.

The UK’s programmatic response to Trade Policy in Nigeria has now been established within PDF. This approach focuses on the ‘building blocks’ for trade policy, aiming to increase the voices of under-represented groups in trade policy discussions (such as consumer voices) and widen the trade policy debate away from narrow vested-interests. Partly this is about making policy discussions more evidence based and inclusive, but critically this recognises and tries to address the underlying political incentives that have constrained Nigeria to damaging restrictive trade practices in the past and undermined the use of trade to drive Nigeria’s long-term economic competitiveness.

Delays from Nigeria’s Government to appoint a Cabinet meant a slow start to Nigeria’s policy agenda. Following appointments of the cabinet, and the second phase of the Political Economy Analysis (PEA) in November 2015, work supporting Nigeria’s champions of change quickly ramped up. PDF has contracted a total of 37 embedded advisors (of which three have completed their assignments, one moved on to work for the presidency, three were dropped, and one sadly passed away). There are currently three embedded adviser projects in the pipeline. PDF is also on course to complete 15 projects under output two (i.e. studies/events/activies) that support policy formulation in Nigeria by the end of September. These include the high-profile study on ‘Unrecorded Trade and Financial flows’, initiating broader support to the Office of the Auditor General’s office, ‘Enabling Consumer Voices’ study, the ‘Youth Employment’ summit, and work with the Overseas Development Institute (ODI) to launch its report on ‘Supporting Economic Transformation in Nigeria’. There are currently six ongoing projects, and six pipeline projects under output two.

Whilst this is the third official review of the programme, PDF has only been operating for 18 months. This delayed start date was caused by lower than anticipated finances available for the 2014/15 financial year and the opportunity to better align the programme commencement with Nigeria’s political cycle. The programme was ultimately contracted to the start at the begining of the 2015/16 financial year a few months before President Buhari assumed office. The 2015 annual review coincided with the end of the inception period (from April 2015 to September 2015), a period which also aligned nearly perfectly with Nigeria’s own post-election period. The period was focused on extensive thought and planning of how PDF 2 would operate, closing out of inherited projects from PDF 1, and a Political Economy Analysis (PEA) of the post-election political landscape (in July and November), considering potential opportunities and implications for the programme over the next few years.

Table 1: Action on recommendations from 2015 Annual review of PDF
	Recommendations from 2015 Annual review	Action(s) Taken
1	Quickly complete the second phase of political economy analysis on the new cabinet Ministers to help inform programming decisions.	Achieved – PDF completed the second phase of the PEA in November 2015. This was shared with relevant stakeholders within DFIDN and has fed into programming plans and decisions for PDF. A one-year-on assessment of the administration is now planned for October 2016.
2	Develop a five year plan to strengthen Consumer Groups within Nigeria, including their base of representation and how they feed into policy processes.	Achieved: PDF commissioned a study to analyse the state of exisiting consumer groups and identify key players and areas for support. This fed into further work and agreement that a new work stream be developed under PDF that would by 2020 strengthen consumer groups so that gains in their participation and influence in the policy space would be sustainable beyond the close of PDF in 2020. Design for the workstream is completed. Recruitment to the workstream is underway.
3	Identify high-impact non-government groups that may help demand more inclusive policies from government and consider appropriate approaches to help strengthen them.	On-going: This has been progressed for trade policy issues and potential partners have been identified. The PEA of non-government groups for broader economic issues is now planned for October 2016.
4	Develop and grow the use of social media and the proposed website platform for the dissemination of policy research, learning and policy influence. Identify a target audience and explore different ways of recording and disseminating key messages from PDF facilitated events.	Partially Achieved: The PDF website is now fully operational. The set process involved identification of target audience, and development of social media platforms (facebook, twitter etc.) through which PDF disseminates information, and are linked to the website. Important for PDF to grow the reach of those accessing these platforms over the next year.
5	Establish a policy within PDF and agreed with DFID on the types of content that will be made public, and a risk mitigation policy to avoid reputational risk and ensure no damage to the UK government’s partnership with the Nigerian Government.	Completed: An information release procedure has been developed by PDF and agreed with DFID Nigeria (DFIDN). The process applies a list of criteria to determine suitability of products for dissemination. All material posted on the website are subjected to this rigourous clearance process.

Summary of recommendations for the next year

The following recommendations have been identified as part of this annual review.

Economic Policy Dialogue

Stengthen mechanisms for regular economic policy dialogue with State House and Nigeria’s Economic Management Team.

Quickly step-up engagement with DFID embedded adviser network on the substance of economic policy issues.

Supporting Champions of Change

Sense-check the balance of its support through the next round of political economy analysis.

Collaborate with DFID advisers and other DFID programmes to improve the efficiency and effectiveness of the UK’s package of technical support to the office of the Vice President.

Supporting Institutions

PDF should explore ways to strengthen the Efficieny Unit within the Ministry of Finance.

Consider anchoring an embedded adviser within the Office of the Auditor General to coordinate UK support such as NAO missions and other PDF support.

Building Blocks for Trade Policy

Set a target for increasing Nigeria’s non-oil exports into regional and non-regional markets and work with partners such as Nigeria’s Export Promotion Council, Ministry of Industry, Trade and Investment and Ministry of Foreign Affairs as well as potential exporters to help make this achievable.

Develop a vision, strategy and workplan for building consumer voices in Nigeria that covers the remaining period of the PDF programme and commence a range of interventions.

Build the knowledge developed from the Chatham House study into the new workstream on trade policy influencing.

Strengthen the collaboration between PDF and the Nigeria Economic Summit Group, Lagos Chamber of Commerce, and develop a new relationship with the British Nigeria Chamber of Commerce in Lagos.

Disseminating Information

Grow the active user-base of PDF research and evidence products.

Gender and inclusion
Strengthen gender and inclusion appraisals within newly developed interventions.
A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/5178112.odt
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/4030907.xls

Outline of the programme

PDF 2’s objective is to provide targeted assistance over a 5 year period to help Nigeria’s ‘champions of change’ implement economic and social policies that lead to poverty reduction, enabling HMG to back reform through:

- Backing key economic and public sector reformers in Nigeria with technical support
- Conducting research and studies that can be used to influence and shape Nigeria’s economic reform agenda.
- Initiating explorative studies for potential complimentary DFID programming.

The Impact of PDF 2 is that the Nigerian Government implements policies that lead to poverty reduction. The Outcome is that Nigeria’s ‘champions of change’ make increased use of capacity and evidence to enable them to pursue vital economic and social reform.

Context

Nigeria, with the largest population and second largest economy on the continent, a delicate security situation with a history of internal conflict, and a large diaspora with strong links to Britain, matters greatly to West Africa, Africa as a whole, and the UK.

Yet after over 50 years of independence, and 50 years since oil revenues came on stream, and more than a decade of high economic growth, a third of Nigerians still live in extreme poverty, while a small elite is extremely wealthy. Why is this? “The system [in Nigeria] is deeply rooted in vested interests, a history of intrinsic tension between traditional values and electoral government, systemic violence and conflict often fuelled by ethnic rivalry”[1]. This review and those of its predecessor programme finds that these fundamental features of Nigeria, identified in a DFID paper of 2005, remain valid, and help explain persisting mismanagement of public resources, weak accountability, and a personalised public policy process which in general gives little weight to evidence of what would most effectively achieve wider national objectives. These contribute to weak institutions and government agencies, pervasive corruption, and to poor governance and policy outcomes.
[1] C Heymans, C Pycroft, DFID 2005.

For 17 years, Nigeria has been embedding democratic politics after decades in which military government predominated, with a harmful effect on public ethics and the quality of governance; until 2014, economic growth had accelerated (though the benefits were poorly distributed); and some (but by no means all) social indicators had improved (though far below potential)[2].The 2015 elections created increased reform momentum, and with the dominant incumbent political party losing the election and allowing a peaceful transition to the opposition, there was hope that this democratic landmark for Nigeria may increase public accountability and help shift policy making to be more reflective of a broader constituency rather than just the will of a small dominant elite. To some extent, this has been seen over the last year with President Buhari’s anticorruption agenda and determined desire to hold government appointees and officials to account.
[2] http://unstats.un.org/unsd/mdg/Data.aspx

The external economic environment for President Buhari’s government has been harsh. With the global fall in oil prices since 2014, Nigeria has faced substantial economic challenges due to its overdependence on oil exports. In 2016 the economic situation went from bad to worse with oil prices falling below $40 per barrel from January through to March. Since then prices have only risen to less than $50 per barrel as at October 2016. This compares with oil prices that were in excess of $100 per barrel for much of the period from 2012 to 2014. Combined with oil production disruptions in the Niger Delta from systematic targeting of oil and gas infrastructure by militant groups, Nigeria has struggled to keep its economy on track, sliding into recession in the second quarter of 2016. The IMF have forecasted -1.8% growth for 2016 and the pressure is on the government to enable a rapid economic recovery.

The economic policy agenda of the new government, whilst well intentioned, has been varied in terms of impact. Unprecedented progressive reform began on the Nigerian National Petroleum Corporation (NNPC), pushing for the agency to clean up its act and move towards operating as a commercial entity that is a net contributor of value to the Nigerian economy, and the removal of fuel subsidy has been a decisive step in this direction. There has also been early demonstrative commitment to the private power market development through decisive action by the Vice President. Public financial management was given a ‘shot-in-the-arm’ with the announcement of forensic audits on key revenue generating agencies and manadatory requirement that all MDA funds be held in the Treasury Single Account (TSA) in an effort to increase resources available for national development. Though frought with many concerns, the 2016 Budget process which began with a move towards zero-based budgeting- presented an opportunity to challenge old assumptions that have sat within countless previous budgets.

Yet monetary and trade policy remain concerning and have sent damaging signals to the private sector. Capital controls that had been in place since the previous year to maintain a strong currency, and the restriction of access to foreign exchange on key imports had a negative impact on domestic business activity and foreign investment. Although the exchange rate determination was notionally floated in June 2016 with a significant devaluation in the currency, the Central Bank remained highly interventionist, some banks complain of having to queue for up to two months in order to convert their naira investments into foreign currency. Most foreign businesses also have to queue to remit their profit to their home countries. Restrictions on 41 imported goods remain in place despite the apparent liberalisation of the foreign exchange market, and the parallel market for foreign currency still offers a substantial premium. Rhetoric on trade policy remains highly protectionist, with the attiude of a critical mass of Nigeria’s policymakers and governing elite largely following in the footsteps of former administrations by pushing import substitution policies despite their poor track record in Nigeria[3]. The delay in action by the Central Bank and persistence of a number of restrictions has meant some of the post-election good will from international markets to invest in Nigeria has been lost. If Nigeria is going to sufficiently mobilise private investment to kick-start its economic growth, much needs to be done to send positive signals to the private sector and re-awaken the interest of investors.
[3] See studies on textile, rice and cement industries on the PDF 2 website http://www.pdfnigeria.org/

Given the importance of Nigeria to achieving the SDGs, and the broadly positive governance agenda of the administration, there is a strong case for DFID continuing to be engaged in influencing Nigeria’s policy process for better development outcomes. Progress is possible, and the potential gains in security, and development are large. However, realism is necessary on the risks and uncertainties involved. There remains an unsettled economic approach which the UK could help positively influence and on the DFID technical support through PDF could play an important role in doing so. Despite the democratic progress and positive demonstration of accountability in the 2015 election, vested interests continue positioning themselves to attempt to influence government’s public policy agenda. In some instances the influence of this group may well outweigh both evidence and the wider national interest. In certain cases even the best efforts of PDF will not be able to overcome this influence.
B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

The intended outcome of PDF 2 is that Nigeria’s ‘champions of change’ use increased capacity and evidence to enable them to pursue vital economic and social reform. There is no formal milestone on this until 2017 when the programme will be expected to demonstrate at least seven substantial case studies as part of its mid-term review. These case studies should show how the programme’s support has influenced the policy process in a way that could plausibly feed-through to poverty reduction (the programme’s overall intended impact). Until 2017 this will be assessed in a qualitative way.

Even from this early stage in the programme cycle, there is little doubt that the support provided by PDF to beneficiaries is appreciated and provides them with capability to deliver impact during their four years in office. The UK Government’s ability to be responsive and provide this type of support helps the UK to stand-out as a donor partner of choice and provides important political capital to the UK’s work in Nigeria. Yet, the current recession Nigeria is going through and the inital policy responses of government demonstrate the limits of providing technical assistance to influence policy outcomes. Critically, the work that PDF has done in building an evidence base on policy has been complemented by UK Government influencing through DFID Advisers along with support from the British High Commission. PDF should continue to operate in ways which leverages the full-suite of UK government influencing to ensure it has the most possible effect. This follows the theory of change set-out in the PDF 2 business case (see below), which this review assesses to still be valid.

PDF 2 has established and shaped itself with the appropriate competencies and approach to be on the right trajectory to achieve its intended outcome. Whilst it is still early days, an impact level baseline considering policies within the APC manifesto and early policy announcements was carried out in November 2015 as part of the second PEA. Since then, Nigeria’s recession and the economic policies that have been associated with it have presented substantial challenges and the risk towards achieving the second part of the programme’s outcome has arguably increased. It is too early to say whether this is off-track, but it is clear that the programme and the UK Government will need to increase their influencing work to mitigate the risk surrounding this.

Overall output score and description

The programme output score for 2016 is an ‘A’, reflecting the good progress made in the last year in responsively shaping technical assistance to targeted parts of President Buhari’s government. The programme has achieved its key output indicators and is ontrack to achieve its programme outputs by the end of the programme.

Key lessons

Responsiveness of technical assistance to beneficiaries is critical to help shape policy direction and improve the likelihood of good policy implementation.

Agreeing fee-rate caps on technical support can be effective when carried out in conjunction with other DFID programmes.

Bringing in sector specific programmes to lead on or help shape the terms of reference for embedded advisers in their area creates ownership and provides technical networks that the embedded adviser can later draw on.

Key Actions

Take action on recommendations set-out in page 3 of this review.

Complete the current round of political economy analysis to sense-check current areas of technical support.

Strengthen gender and inclusion appraisals within newly developed interventions.

Review contract provisions to identify ways of mitigating risks of potentially damaging public positions or actions taken by DFID funded embedded advisers.

Has the logframe been updated since the last review?

No, the logframe was last revised as part of the inception period discussions. This was to reflect annual milestone targets commencing a year from inception and also to include a third indicator to the two outputs. Indicators were also adjusted at impact and outcome level to better represent measurable progress of the programme. This was before the last annual review, and no further amendments have been made since then.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Relevant and high quality PDF II organisational support delivered to beneficiaries
Output number per LF		1.	Output Score	A
Risk:		Moderate	Impact weighting (%):	60%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones (2016)	Progress
Number of projects assessed as executed satisfactorily (as planned) or better during implementation	19[4]	Target Achieved
Beneficiary, user perceptions of relevance and quality of PDF II funded organisational support	Average ratings[5]: / Relevance…………………92% / Quality……………………..85%	Target Achieved
Number of instances where beneficiaries/EAs say that PDF II-supported data and analysis has directly influenced any of the 5 stages of policy formulation	MDAs, NASS, CSOs………..4	Target Achieved: From 18 technical assistance interventions there were 21 examples of where these projects had contributed towards stages of the policy cycle.
[4] Completed/Closed projects and those for which the initial contracted period have been completed were assessed. Projects assessed by the APMU as less than satisfactory at implementation stage are not included in this number, only successful projects are counted. Where PDF II was not involved in the design of a project (e.g. the APC dialogue), they are not included (even though they could be considered a success).
[5] Based on Beneficiary Assessment of project performance at implementation stage.

There are three key citations by Embedded Advisers (EAs) for Output 1, that have been validated from independent sources like media reports, government publications etc.:

1. Sector Road Map for Federal Ministry of Agriculture and Rural Development (FMARD): The EA contributed to the development of draft FMARD overarching policy which incorporated stakeholder inputs. It contributes to securing procedural change at domestic and international level
2. Sector Road Map for Solid Minerals: The EA supported the Minister in the realisation of a road map for the solid mineral sector. Stakeholders were engaged and States validated the roadmap in a meeting held in Kaduna. The president made reference to this roadmap in his anniversary speech. This contributes to framing debates and getting issues on to the political agenda and securing procedural change at domestic and international level
3. Nigeria Sovereign Investment Authority (NSIA) Communications: The NSIA's response/handling of negative press. The EA contributed to framing debates and getting issues on to the political agenda. This was evidenced in his contribution to changing the mind-sets of governors including a southern Governor who made critical remarks in the media. The EA contributed extensively to media management through stories which highlighted NSIA's achievements. The success was evidenced by the federal government's allocation of an additional $250 million to the NSIA following NSIA's engagement with various arms of government to rebut the negative allegations

Key Points

DFID and PDF moved quickly to shape its offer of support to those identified as potential ‘Champions of Change’ within President Buhari’s cabinet (appointed in November 2015). The second Political Economy Analysis of the new cabinet (PEA) was carried out and focused on individuals within the cabinet and potential policy opportunities. The findings of the PEA fed into internal DFID efforts to identify areas of promise on the development agenda, and priorities for PDF. A one-year-on refresh of the PEA is now ongoing for October 2016

Technical Assistance has been provided to the following Federal Ministries, Departments and Agencies (MDAs) as set-out in table 1 below.

Table 1: Overview of areas of technical assistance.

Federal Ministry, Department & Agency	Areas of Technical Assistance
State House	Economic Advisory Council
	Job Creation & Youth Employment
	Policy and Delivery Unit
	Internally Displaced Persons (IDPs)
Ministry of Industry, Trade and Investment	Special Advisers on Investment & Strategic Communications
Ministry of Foreign Affairs	Senior Adviser on trade & investment issues
Ministry of Finance	Chief of Staff, Support to Efficiency Unit, Economic Reforms
Ministry of Planning and Budget	Monitoring and Evaluation, Media adviser, Policy and Planning.
Ministry of Health	Universal Health Coverage Agenda: One PHC Per Ward and Rapid Results Initiative
Ministry of Environment	Special Adviser
Ministry of Agriculture and Rural Development	Project Management
Ministry of Solid Minerals	Delivery Unit /Technical Adviser
Nigeria Extractive Industries Transparency Initiative (NEITI)	Policy, Planning & Strategy
Nigeria Sovereign Investment Authority (NSIA)	Communications
Office of the Auditor General of the Federation	National Audit Office Partnership

PDF had 22 ongoing projects under output one, six completed projects, five pipeline projects, and three dropped projects at the time of this annual review. Eight of the 22 ongoing projects, EA at the Office of the Vice President, have officially been extended. One project, EA at the Nigerian Sovereign Investment Authority, is awaiting extension as the Revised Terms of Reference (ToR) has not been finalized by the consultant and beneficiary. Another project, ‘Support to Presidential Policy and Delivery Unit’ (four embedded advisers), was stopped at the request of the beneficiary in March and then later restarted.Ten projects were inherited from PDF which were completed and archived during the Inception Phase of the programme.

Office of the Auditor General: The role of office of the Auditor General fits neatly into President Buhari’s prominent anti-corruption agenda and complements the UK’s broader anti-corruption approach. DFID/PDF 2 responded to this by agreeing to fund an embedded adviser to this function, initially for six months. During this time to complement this support PDF 2 helped coordinate a retreat and two missions from the UK’s National Audit Office (through DFID’s iFuse programme) to form links between the UK and Nigerian Public Accounts Committee. These partnerships together aim to help Nigeria think through its high-level audit strategy for the next five years and consider how they can strengthen accountability through parliament and adopt more transparent approaches to increase public engagement in this work. This partnership was later formally announced as part of the deliverables from the Prime Minister’s Anit-Corruption Summit with Nigeria’s President Buhari in May 2016. On completion of the second NAO mission, the acting Auditor General and her team set out an indication of future requested support which PDF 2 is now working with the iFuse programme to design and fund. In addition, PDF 2 is facilitating coordination of DFID Nigeria’s support through other programmes such as the new public service reform programme to ensure that DFID’s support is optimally structured and delivers value for money.

Trade Policy Support: The political economy of trade policy remains challenging with certain groups dominating the policy discourse and many other local voices unrepresented. Rather than traditional institutional support the balance of PDF 2’s efforts is focused on the building blocks of long-term trade policy by strengthening alternative (or under-represented) voices that can feed into the policy processes. PDF 2 explored how it might strengthen the role of relatively weak consumer groups to feed into policy formulation as well as consider how it could work to reflect a broader group of manufacturers and businesses into policy discussions (including Small and Medium Enterprises (SMEs) and the informal sector). Based on findings from the study PDF 2, has designed a new work stream that would by 2020 strengthen consumer groups so that gains in their participation and influence in the policy space would be sustainable beyond the close of PDF 2 in 2020. Design for the workstream is completed and recruitment is underway.

Summary of responses to issues raised in previous annual reviews (where relevant)

Table 2: Summary of responses

	Recommendations from 2015 Annual review	Action(s) Taken
1	Quickly complete the second phase of political economy analysis on the new cabinet Ministers to help inform programming decisions.	Achieved – PDF completed the second phase of the PEA in November 2015. This was shared with relevant stakeholders within DFIDN and has fed into programming plans and decisions for PDF II. A one-year-on assessment of the administration is now planned for October 2016.
2	Develop a five year plan to strengthen Consumer Groups within Nigeria, including their base of representation and how they feed into policy processes.	Achieved: PDF commissioned a study to analyse the state of exisiting consumer groups and identify key players and areas for support. This fed into further work and agreement that a new work stream be developed under PDF that would by 2020 strengthen consumer groups so that gains in their participation and influence in the policy space would be sustainable beyond the close of PDF 2 in 2020. Design for the workstream is completed. Recruitment to the workstream is underway.
3	Identify high-impact non-government groups that may help demand more inclusive policies from government and consider appropriate approaches to help strengthen them.	On-going: This has been progressed for trade policy issues and potential partners have been identified. The PEA of non-government groups for broader economic issues is now planned for October 2016.

Recommendations

Macro- Economic Policy

PDF should step-up its engagement with its embedded adviser network on the substance of economic policy issues. Given the current economic challenges Nigeria is facing, and the strong network of technical assistance being deployed, PDF should explore options such as informal policy groups to explore concrete and credible economic policy ideas that could feed into a future economic strategy of Nigeria’s government.

PDF should sense check the balance of its support with the next round of political economy analysis. The mix of beneficiaries appears broadly balanced around potential champions of change and a range of policy issues but there may be important opportunities not currently identified that could be explored.

PDF should work with DFID advisers and other programmes to improve the efficiency and effectiveness of the UK’s package of technical support to the office of the Vice President. This can build on the findings of the recent National School of Government review of DFID support to the office as well as Nigeria’s Infrastructure Advisory Facility’s (NIAF) technical review panel report which considered the UK’s infrastructure technical assistance that had been provided to the office.

Supporting Institutions

PDF should explore ways to strengthen the Efficieny Unit within the Ministry of Finance. PDF should explore potential to expand the current partnership with the National Audit Office (NAO) to include a mission of support to Nigeria’s Efficiency Unit in the Ministry of Finance. This will build on the existing embedded adviser support and will help share experience from the UK on driving value for money across government.

Consider anchoring an embedded adviser within the Office of the Auditor General to coordinate UK support such as NAO missions and other PDF support and prepare the ground for the organisations strategy next year.

Building Blocks for Trade Policy

Set a target for increasing Nigeria’s non-oil exports into regional and non-regional markets and work with partners such as Nigeria’s Export Promotion Council, Ministry of Industry, Trade and Investment and Ministry of Foreign Affairs as well as potential exporters to help make this achievable. Nigeria’s non-oil exports have become more competitive with the weakening of the Naira- a significant part of Nigeria’s “Dutch Disease” from oil has been reversed- PDF should seize this opportunity. This builds on recommendations from the Overseas Development Institute ‘Supporting Economic Transformation’ report that using non-oil exports in a few selected sectors, the UK can help demonstrate how economic diversification and competitiveness can be enabled through more open trade policy approaches. It could also be important symbolically if Nigeria can increase its export of non-oil goods into the UK market.

Develop a vision, strategy and workplan for building consumer voices in Nigeria that covers the remaining period of the PDF programme and commence a range of interventions. Now that the underlying analysis has been done and the recruitment for the lead position has almost been completed, it will be important for the programme to quickly get going with this work. A suite of interventions should be developed that can come on stream in April 2017.

Gender and Inclusion

Strengthen gender and inclusion within newly developed interventions. PDF have put in places the systems to monitor the opportunities and risks for gender and inclusion, but the subject matter of many interventions often makes the opportunities and risks less obvious. PDF should work with DFID advisers to strengthen their approach and make sure stronger inputs are included within future interventions.

Output Title	Relevant and high quality PDF II policy research, explorative studies and consultation products delivered to beneficiaries
Output number per LF		2.	Output Score	A
Risk:		Low	Impact weighting (%):	40%
Risk revised since last AR?		No.	Impact weighting % revised since last AR?	No

*Notes under Output 1 apply for all asterisks
Indicator(s)	Milestones (2016)	Comment
Number of projects assessed as executed satisfactorily (as planned) or better during implementation	15*	Target Achieved
Beneficiary, user perceptions of relevance and quality of PDF II-supported policy studies and events	Average ratings:** / Relevance…………………95% / Quality……………………..85%	Target Achieved
Number of instances*** where beneficiaries/EAs say that PDF II-supported data and analysis has directly influenced any of the 5 stages of policy formulation	MDAs, NASS, CSOs………..3	Target Achieved

There are three key citations by consultants for Output 2 that have been validated from independent sources like media reports, government publications etc.:

1. Youth Employment Summit - The YouWiN evaluation report and lessons learned from other government initiatives on employment were disseminated at this event. The event contributed towards getting issues on to the political agenda, encouraging commitments from public sector and other policy stakeholders and securing procedural change at domestic or international level
2. Job Creation Framework for Nigeria: PDF 2 provided support to the Job Creation Unit in the VP's office, to develop a strategic framework and implementation plan for Job Creation and Youth Employment in Nigeria. This contributes to Framing debates and getting issues on to the political agenda, encouraging commitments from public sector and other policy stakeholder and affecting policy content. The framework is now being implemented in partnership with the private sector, and PDF 2 continues to support the JCU in implementation (e.g. proposed Innovation Hubs have significant potential for youth employment).
3. PDF 2 supported the public launch of a paper on Supporting Economic transformation. This works contributes to framing debates and getting issues on to the political agenda and encouraging commitments from the public sector

Key Points

PDF 2 currently has six onging projects under output two, 15 completed projects, and six pipeline projects. All ongoing projects are progressing as planned. Work under this output has not only continued where PDF 1 left-off with dissemination of two major studies funded under the previous programme (YouWin, and Unrecorded trade and Financial flows), and one study funded by the ODI, it has also gone on to enhance how PDF 2 generally goes about disseminating key studies.

Following recommendations from the programme completion review (PCR) of PDF 1 a website has been created which serves as a learning platform. PDF 2 now makes greater use of social media to highlight policy implications of PDF 2’s work. Building on lessons from using this approach during the policy dialogue that PDF 2 organised in collaboration with the Nigerian Economic Summit Group (NESG), PDF 2 now makes better use of a wider range of social media and conventional media approaches to try and have policy impact as demonstrated in the Youth Employment Summit in December 2015, and the launch of an ODI funded research paper in May 2016. Developing through experience, PDF 2 is well positioned in this area, although more needs to be done to build a stronger base of followers and users of PDF’s content. PDF was approached by the British High Commission to help organise a follow-on CBN Forex Policy event, which should hold in the last quarter of 2016.

Unrecorded Trade and Financial Flows Study- Chatham House

Informal trade activities in the Nigerian economy may reflect as much as 70% to 80% of trade between Nigeria and its neighbours. The purpose of this report was to highlight the activities which do not show up in formal economic statistics and look at the implications of this large informal sector for government policies. The report was completed and disseminated in three locations in Nigeria (Lagos, Abuja and Kano) and London in early December 2015. Chatham House engaged with a range of policy makers at different levels of government (including the Minister of Industry, Trade and Investment and the Chief of Staff to the President) to ensure understanding of the implications that their policies have on the informal sector, and how they can support and eventually formalise this vibrant part of the economy. This has become a flagship study on the informal sector in Nigeria.

Youth Employment / Job Creation Summit

The World Bank published the evaluation of the ‘YouWiN’ programme using the three rounds of extensive surveys funded under PDF 1. This innovative study made use of a randomised component of the selection process under the first round of YouWiN in 2011 to enable a control group and treatment group to be established and followed up on over a period of three years. The findings have been powerful, showing that three years after applying for the competition the 1,200 winners of round one of ‘YouWiN’ created 7,000 more jobs than the control group and were more likely to be innovating, with higher sales and profits[6]. Internationally there have also been a number of positive blog posts around this evaluation and the ‘YouWiN’ initiative[7].
[6] For access to the full evaluation see http://documents.worldbank.org/curated/en/2015/08/24899889/identifying-spurring-high-growth-entrepreneurship-experimental-evidence-business-plan-competition
[7] http://priceonomics.com/what-happened-when-nigeria-created-the-worlds/

A key objective for PDF 2 was to ensure an appropriate dissemination of this work with the new Nigerian Government so that they understood the implications of this work for job creation initiatives within Nigeria. The YouWiN! report was disseminated in Nigeria in December 2015 during an event facilitated by PDF 2 in collaboration with FEPAR (another DFID programme). Importantly, PDF 2 seized the opportunity to showcase lessons learned from past Nigerian initiatives and innovative approaches to creating jobs and raising incomes in Nigeria. The event featured a dymamic ‘market place of ideas’ in which innovative job creation initiatives from DFID programmes, the wider donor community, state governments, and the private sector were ‘on sale’. The Osun State government bought an idea on the day and has subsequently began to replicate the model in the State.

A fourth round of the survey has now been commissioned by PDF 2 to look at the longer term impacts of YouWiN! while also introducing additional areas to capture wider economic issues for which data is not currently captured elsewhere. The round four survey is expected to be completed in November 2016.

Other key pieces of work under Output 2 include:
- Strategic Framework and Implementation Plan for Job Creation and Youth Employment in Nigeria.
- Support to the Office of the Auditor General of the Federation.
- Launch of the ODI report on Supporting Economic Tranformation in Nigeria
- Poverty and Social Impact Assessment of Current Economic Challenges
- Franchising in Nigeria Study
- Improving livelihoods of Fishermen in Ogun State Study

Where already completed, these have been well received with excellent feedback from beneficiaries which has been included in the calculation of milestone metrics for this output.

Recommendations

Economic Policy Dialogue

Stengthen mechanisms for regular economic policy dialogue with State House and Nigeria’s Economic Management Team. Given the economic recession it is important to strengthen credible economic voices and ensure these views are feeding into the policy making processes. PDF should explore opportunities to support both credible local voices and international voices.

Trade Policy Workstream

Build the knowledge developed from the Chatham House study into the new workstream on trade policy influencing. The unintended consequence of Nigeria’s economic policies on incentivising informal sector activity and preventing the rise of formal businesses is an important constraint to Nigeria’s economic development and a key issue to bring into the new trade policy workstream.

Strengthen the collaboration between PDF and the Nigeria Economic Summit Group, Lagos Chamber of Commerce, and develop a new relationship with the British Nigeria Chamber of Commerce in Lagos. Initial collaboration with the Nigeria Economic Summit Group (NESG) and Lagos Chamber of Commerce (LCC) has been promising and they continue to be influential voices on the economy. PDF should also build a relationship with the British Nigeria Chamber of Commerce which will be critical for understanding Nigeria’s export potential to the UK market.

Dissemination of Evidence

Grow the active user-base of PDF research and evidence products. PDF have made a good start in using different channels to disemminate information including through social media, but PDF continues to have a low number of followers and active users. For example, at the time of this annual review PDF had only 138 followers on twitter[8] and no link from the twitter account to the website), this will limit the use of PDF products and the team should explore low risk ways that they can engage more regularly on social media and build a targeted following from those who would benefit from PDF’s research and evidence products.
[8] For contrast DFID’s GEMS 4 programme have 1,361 followers,

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

The key cost drivers for PDF is the technical expertise it deploys through its two outputs. Building on the recommendations in the 2014 ITAD review of Value for Money (VfM) in Nigeria’s Economic Growth Portfolio, PDF 2 set-up an approach to monitoring value for money during its inception period which covers the following:

1. Recording cost data and, where meaningful, calculating moving six monthly averages of unit costs (e.g. fee rates and knowledge products/deliverables) and ratios of programmable to overhead costs (Economy);
2. Relating these to the changing values of the Outputs’ indicators (Efficiencies); and
3. Learning about how and to what extent the services and products made available through the programme’s outputs are being used, or rejected, by the Champions of Change and others, including DFID, and supporting changes that promote inclusive growth and other pro-poor policy impacts (Effectiveness and Equity).

The key questions regarding VfM (including the four Es) will also be tracked through individual project terms of reference and reports and assessed against the Programme’s Output and, later on, the Outcome’s indicators[9].
[9] The requirements for comparing their values would be with the previous six monthly report and among those at output level for the current reporting period

A strict cap remains in place on overall salaries for embedded advisers to control costs of this sensitive expenditure and has been applied on all embedded advisers recruited during the period under-review. This cap has now been applied across all DFID Nigeria programmes.

Per the Business case under PDF 2 below is a summary of the:
-	Average monthly cost of expertise for Output 1 (primarily embedded advisers fees)
-	Average daily cost of expertise brought in for Output 2 (policy studies and research)

Description	Monthly Fee Rate (£)	Daily Fee Rate (£)
Minimum	2,759	34
Mean	5,360	428
Maximum	6,250	870

Project budgets are individually designed with the objective of achieveing best value for money for agreed activities required to achieve the outputs and outcomes of the terms of reference (ToR). For Output 2 projects, activities are also planned to achieve the best VfM. Consultants are involved in the process of finalizing activity based budgets to ensure that the quality of their deliverable is considered. To further ensure VfM, PDF 2 has put in place a structured procedure for negotiating fees with consultants and has standard unit costs for certain expenditures.

Highlights of VFM under PDF 2:

1. During the negotiation process for the ‘Development of a Strategic Framework for Job Creation & Youth Employment’, PDF 2 was able to achieve a savings of 56% from the initial budget proposal of £225,600.
2. PDF 2 was able to negotiate with another professional services company to waive their professional fees for providing secretariat support to the National Economic Council Retreat on Tackling economic downturn – Options for Nigerian States; this amounted to a savings of £72,414.

VfM performance compared to the original VfM proposition in the business case

There has been strong progress on the economy of interventions and keeping costs low. It is too soon in the programme life-cycle to assess the efficiency and effectiveness of the programme, however, for some interventions it should be possible to start doing so during the next annual review.

Assessment of whether the programme continues to represent value for money

The overall Value for Money of the programme will depend on the ability of PDF to help shape, influence and support Nigeria to achieve two or three big policy wins over the life of the programme that starts having impact on beneficiaries. For example the backing of the Efficiency Unit within the Ministry of Finance could plausibly lead to large impact across the Nigerian Government in driving savings in the recurrent budget. The Innovation Hubs proposed by the Office of the Vice President may present an opportunity to create jobs and raise incomes within different regions of the country.

With the relatively slow start to policy making within President Buhari’s government, there remains a risk that PDF 2 may struggle to find the big policy wins that helps Nigeria make significant steps forward on its economic and social development. The next year will be critical in scaling up support in the areas that show the most promise, and identifying a few more potential big wins to support.

Quality of financial management

Financial Management from PDF has overall been good, and whilst a significant proportion of its expenditure is fixed through-out the year, it has done well to adjust the more flexible elements of its expenditure profile to fit with DFID requirements. The main challenge to financial management has stemed from the challenging economic environment in which Nigeria has been operating since 2014. In particular, since the exchange rate regime was moved from a fixed official rate to a floating exchange rate system, forecasting and the ability to achieve forecasts have come under pressure. PDF 2 has responded by developing a responsive tool for monitoring cost sensitivities, and impact of the new floating exchange rates on forecast.

Of the £13.2m funds set aside for PDF 2 projects, DFID has committed £4.4m; £1.2 of which will be set aside for the PDF 2 Trade Workstream which is currently in pipeline; leaving a balance of £8.8m for new projects over the next 3.5 years left of the programme.

To ensure accuracy in monthly financial forecasts to DFID, PDF 2 has put the following steps in place:
- During the budget negotiation process, PDF 2 agrees an invoicing schedule with contractors
- During the Induction to PDF 2, consultants are briefed on expectations for invoicing and encouraged to invoice in a timely manner as stated on their contract
- PDF 2 has put in place a process to adjust naira expenditures for fluctuation in exchange rate. Going forward PDF 2 will average the monthly exchange rate and apply it to forecasted spend, this should minimise the discrepancy between forecasted and actual spend
- Monthly reminder are sent to contractors and follow up action taken to ensure all expected invoices are received in a timely manner

Date of last narrative financial report	September 2016
Date of last audited annual statement	First audit scheduled for April 2017.

E: RISK (½ page)

Overall risk rating: Moderate: The overall risk rating remains unchanged at moderate. The substantial uncertainty about the political environment for reforms that PDF 2 was entering post elections has largely been cleared, although the pace of reform is likely to be slower than hoped, and the range of policies where progress is possible will be partial.

Overview of programme risk

Context: The operating context remains broadly positive. Initial promising opportunities for significant economic reform from the new government were in the oil and gas sector and the government’s continued commitment to the power market development. DFID’s engagement on these issues have been mostly through its Facility for Oil Sector Transformation (FOSTER) and Nigeria Infrastructure Advisory Facility (NIAF). There remains pockets of potential reform from various ‘champions of change’ within the administration who have carved out policy space. The opportunities on this side have been tempered by the slow pace of government appointments and general policy formulation along with restrictive positions on trade and foreign exchange policy that have damaged private sector confidence.
Gross risk: Major risk
Mitigation: Strengthen voices (such as private sector) feeding into policy debates & link up with UK Government influencing. Identify areas – such as Office of the Auditor General and the Ministry of Finance Efficiency Unit where political will may exist for quiet reform through-out the programme lifespan.
Net risk: Moderate risk

Delivery: The service provider has been contracted in a flexible responsive way which minimises delivery risk due to its ability to be adaptive to the reform environment. The main delivery risk to the programme is that short-term embedded adviser support can undermine long-term institutional strengthening.
Gross risk: Moderate risk.
Mitigation: This risk is mitigated to an extent by PDF coordinating support with other DFID programmes and where possible, putting together a cohesive long-term package of support to build the capabilities of the agencies. For other risks within each terms of reference there is a screening for gender and climate change issues (both opportunities and risks within the intervention) and the programme is at low risk of doing harm towards conflict and fragility – however this low risk would be reconsidered should PDF supply technical assistance to higher risk agencies such as the National Security Adviser.
Net Risk: Minor risk.

Operational: PDF 2 has a small in-country team (mostly focused on programme administration and management) and it relies on DFID Nigeria’s strategic and tactical direction disproportionately compared to other programmes.
Gross risk: Minor risk.
Mitigation: DFID has recently strengthened its capacity to provide strategic oversight by hiring a new Country Economist to support the Economic Growth Team Leader. It has also approved the hiring of two new advisers within the PDF team to lead on trade policy and strengthening consumer groups, providing more operational capacity to the programme.
Net risk: Minor risk

Fiduciary:  Risk that funds are misused or misappropriated.
Gross risk: Minor risk.
Mitigation: No funds are put through Nigerian Government systems and currently no grants are provided from the programme. Procedures are in place to properly monitor the use of expenditure through the programme. If the programme does start providing grants in the future it will need to have appropriate procedures in place and this risk rating will be re-evaluated. There is an associated reputational risk due to use of embedded advisers that in some cases may have a degree of influence over the use Nigerian Government funds.
Net risk: Minor risk.

Reputational:     As PDF starts to host more policy dialogues and make more of its studies public there is an increased risk that critical comments may be attributed to DFID harming the UK’s Government relationship with Nigerian counterparts. There is also a risk on the public position taken by DFID funded embedded advisers and their actions.
Gross risk: Major
Mitigation: PDF has put in place a rigourous approach to making reports public and staff avoid providing comments to the media. There is also reputational risk from the use of embedded advisers who are not directly managed by the programme. This risk is mitigated to an extent by regular performance reviews with the beneficiaries, and taking prompt action if problems are identified. PDF should review contract provisions to identify ways of mitigating risks of potentially damaging public positions or actions taken by embedded advisers.
Net risk: Moderate

Outstanding actions from risk assessment
PDF should review contract provisions to identify ways of mitigating risks of potentially damaging public positions or actions taken by DFID funded embedded advisers.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
Contracting commenced in April 2015, after an open tender process, and the inception period was successfully completed by the programme within six months. A year into full implementation and the programme remains on track.

Performance of partnership (s)
PDF 2 service provider has performed well and been responsive to DFID and beneficiaries during this period. Formal feedback was recently provided as part of DFID’s key supplier management process.

Asset monitoring and control
Appropriate systems and processes have been put together for asset monitoring and control and are updated regularly and shared with DFID.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)
The programme does not use the Partnership Principles as formal conditionality in programming as no UK aid money goes directly to the Government of Nigeria. But we will use the relevant Partnership Principles at two levels to guide our decisions; first as criteria in the selecting the partner institutions and ‘champions of change’ that PDF provides technical assistance to and with the choices of modes/depth of engagement (and as part of the decision on when to exit support from these institutions), and secondly as ‘live’ principles for active monitoring during annual reviews. In particular, institutions committed to pursuing pro-poor economic and social policy, strengthening transparency and minimizing corruption, and enabling domestic accountability may be considered when determining the level of technical assistance that the programme provides. Greater resources will be directed to those institutions that demonstrate greater commitment to the partnership principles and this will be used alongside political economy analysis of where pro-poor economic transformation is likely to come from.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

There is no formal evaluation planned for PDF 2. A review of key case studies from the programme is scheduled for the mid-term review in 2017 which will provide an important opportunity for lesson learning and path-correction.

Monitoring progress throughout the review period

A logical frame work has been agreed with DFID and is in place to guide PDF 2’s outputs and activities. Monitoring and Project Management tools and processes have been put in place and continue to be tested and improved upon. Through a light touch monthly project monitoring approach and more formal interim reporting, PDF 2 collects knowledge on opportunities, threats, and lessons learned which are regularly fed back to DFID for better coordination and planning of DFID interventions.

PDF 2 Abuja office team developed templates and procedures for project administration and monitoring that incorporated new features for monitoring VfM, environmental/climate impacts, gender impacts, progress of projects towards achieving outputs and outcomes

Beneficiary Feedback

Relationship with Beneficiaries have continued to develop. Given the late start for Ministers, most projects are still in their early stages. Nevertheless, PDF 2 has sought beneficiary feedback through an interim project scoring matrix which shows that beneficiaries are satisfied with projects, and PDF 2’s management of projects, and on average rate PDF 2’s project as scoring 94% on relevance and 85% on quality, well above the log frame requirement of 90% and 80% respectively.

Furthermore new relationships that were being developed last year, have begun to bear fruit. The relationship with the directors of the Office of the Auditor General’s office, one of which is now Acting Auditor General, has provided a good foundation on which wider support from other DFID programmes (e.g. PERL) are now building. Good working relationship between PDF 2 and the Nigerian Economic Summit Group (NESG) which began during the foreign exchange policy dialogue in September 2015, has proved to be a useful partnership with the CEO featuring at the ODI event and is lined up for the follow-on dialogue organised by PDF II in collaboration with the British High Commission (BHC) and the NESG.

Review Process

This review was a desk review carried out by the DFID Senior Responsible Owner (SRO) with input from the PDF project team and selected beneficiaries.