Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: International Finance Facility for Immunisation (IFFIm)
Programme Value: £1.63bn		Review Date: October 2016
Programme Code: 111073 & 201185	Start Date: 2007	End Date: 2029

Summary of Programme Performance
Year	2012	2013	2014	2015	2016
Programme Score	A	A	A	A	A+
Risk Rating	Medium	Medium	Medium	Medium	Moderate

Summary of progress and lessons learnt since last review:

The International Finance Facility for Immunisation is an innovative financing mechanism which, as of September 2016, has frontloaded US$2.5 billion of disbursements to Gavi from US$6.3 billion of secured donor commitments made up until 2030. IFFIm has provided approximately 18% of Gavi’s total resources since 2000, and 21% since its inception in 2006. IFFIm is expected to provide a further $1.3 billion to Gavi between 2016 and 2020, representing approximately 15% of Gavi’s overall resources in the period.

As of the end of September 2016, no bond issuances or disbursements were made since the previous annual review. Consequently, the realisation of donor commitments has decreased IFFIm’s gearing ratio (the proportion of its outstanding debt to the NPV of donor commitments) from 35% as noted in last year’s annual review to 28% in September 2016. This is well below the effective gearing ratio limit (including a 12% risk management buffer) of 57.7%, giving IFFIm the flexibility to disburse to Gavi should it be called upon to do so.

A bond issuance and the first tranche of the US$1.3 billion disbursement to Gavi for the 2016 – 2020 period is planned to happen before the end of 2016. IFFIm has continued to be affected by the downgrading of market ratings of its major donors, and is currently rated Aa1 (stable) AA (negative) and AA (negative) by Moody’s, S&P and Fitch, respectively; the latter represents a downgrade in the outlook from Stable in June of 2016. The bond issuance will need to be monitored in this regard to assess how the spread between IFFIm’s cost of financing and that of its donors compares; recent issuances have been at a higher cost than that of the weighted average for donors, while cumulative outstanding issuances are still at a lower cost of finance than the weighted average of donors.

Over the past 12 months, DFID and other donors have actively engaged with IFFIm to explore how it can best support Gavi as a financing mechanism. A donor workshop was held during the Gavi Board in June 2016 at which a number of potential options for future roles of IFFIm were discussed: namely, medium to long-term purchase guarantees (financial guarantees to support Gavi’s supply and procurement strategy); funding the cold chain equipment optimisation platform (CCEOP; to support Gavi’s health system and immunisation strengthening framework), and acting as a financing instrument to respond to infectious disease outbreaks.

Ultimately, the discussion highlighted that IFFIm has performed very well to date and given its projected funding requirements to Gavi for 2016 – 2020, would require additional donor pledges to significantly expand its remit in supporting Gavi. In a constructive dialogue, potential options were considered within the current extent of donor pledges, and further information on these will be provided to donors ahead of the IFFIm Board in March 2017 to assess whether it is possible to further improve the value for money proposition of the investment.
This is the first Annual Review which combines IFFIm, with DFID’s Gavi and AMC investments with the aim of improving coherence and efficiency. This means that IFFIm is scored against a reduced number of indicators but much more within the context of contributing towards the effectiveness and results delivery of Gavi, the Vaccine Alliance.

Summary of key recommendations for the next year:

R1. The Gavi secretariat should present updated and detailed analysis to IFFIm donors regarding the potential future roles and the resultant recommendations discussed at the workshop in June 2016, before March 2017 (see recommendation 2).

R2. The Gavi secretariat to manage another constructive donor meeting ahead of or alongside the IFFIm Board in March 2017. This should enable a discussion for donors on the next steps.

R3.	The Gavi secretariat, IFFIm Board and the Treasury Manager to effectively manage the end-2016 bond issuance and to report to donors on the comparative weighted average cost of financing for donors.

R4. The Gavi secretariat, together with the IFFIm Board and Treasury Manager, to continue to support donors to ensure the successful signing of the 2015 pledge agreements.

R5. The Gavi Secretariat to manage openly and transparently with IFFIm donors the potential pressure from other donors to use IFFIm for activities outside its own or Gavi’s mandate, building on the consensus reached at the donor workshop.

Responses to issues raised in the previous annual review:

R1. [internal] As per the 2014 Annual Review recommendation, consider the relevant indicators within Output 1 as part of the Gavi/IFFIm/AMC log frame consolidation.

COMPLETE – The investments in Gavi, IFFIm and AMC have been consolidated into a single logframe. The IFFIm investment comprises one output in the new logframe, taking two indicators from the previous IFFIm-specific logframe, and adding a new indicator. The new logframe better reflects IFFIm as a financing instrument of Gavi.

R2. IFFIm should ensure that the Board-led strategic review is consultative and considers IFFIm’s future role in supporting Gavi’s immunisation programme, while respecting the UK’s conditions for disbursing its core contributions to Gavi. The output of the review should be a strategy paper to inform a stakeholder workshop to be held by Q1 2016. The review is tracked quarterly by the DFID delivery plan.

COMPLETE – The IFFIm Board produced a Future Roles of IFFIm paper for comment ahead of the stakeholder and donor workshop that was held on 20th June 2016. The paper presented four potential future roles for IFFIm, all of which considered how IFFIm could best be leveraged by Gavi to achieve its strategic goals in the current cycle and beyond. Gavi and the IFFIm Board are currently undertaking further analysis to report back to donors ahead of the IFFIm Board in March 2017.

R3. [internal] DFID to communicate to the IFFIm Board and Gavi Secretariat outlining its expectations regarding the output of the review. The expectations will include: detailed options for the future role of IFFIm; an assessment of IFFIm’s investment and financing performance to date against comparable financing options; a future financing strategy that seeks to ensure continued value for money against NPV and average donor cost of fund benchmarks; and a review of IFFIm’s structure to accommodate the different economic and financing environment including currency risk on new pledges.

COMPLETE – DFID engaged with IFFIm ahead of the circulation of both the Future Roles paper and the Resource Guide to communicate its expectations for both of the documents. The Resource Guide presents the key details of how IFFIm works in a manner that is understandable to non-financiers. DFID provided detailed comments on drafts of both documents.

R4. IFFIm should manage and run meaningful donor meetings at the Board which report on IFFIm’s financial performance to date and discuss issues arising from the strategic review on its future role and operational efficiency, so as to engender a greater collective sense of ownership of its donors to IFFIm as an investment tool.

ONGOING – IFFIm enabled a very constructive meeting at the Gavi Board, including a donor-only session which was facilitated very effectively by the Netherlands. The donor only session allowed for a very open discussion of views on the different potential roles, and operational issues that donors wanted to discuss. We would like to see a similar meaningful meeting ahead of or alongside the IFFIm Board in March 2017.

R5. [internal] As per the 2014 Annual Review recommendation, consider the relevant indicators within Output 2 as part of the Gavi/IFFIm/AMC log frame consolidation.

COMPLETE – see R1.

R6. IFFIm and the Treasury Manager should provide support to current and potential donors on matters relating to currency risk for pledges made in 2015.

ONGOING – Three existing donors pledged additional amounts in 2015: Australia, France and the Netherlands. Australia’s pledge has been signed, while a satisfactory agreement has been reached with France regarding currency risk on their new pledge. France are expected to sign their pledge by the end of the year, while work continues with the Netherlands on their pledge.

R7. IFFIm should provide an information pack outlining the fundamental of its operating model for stakeholders without financial expertise prior to the stakeholder workshop to be held in Q1 2016.

COMPLETE – As noted in the response to R3, IFFIm developed a Resource Guide to explain how IFFIm works and answer commonly held questions about IFFIm by non-financiers. The Resource Guide was circulated ahead of the stakeholder workshop, and it was well received. DFID provided comments on the Resource Guide.

R8. Recommendations still ongoing from the previous annual review should be resolved following the conclusion of the strategic review and decisions arising from the stakeholder’s workshop in Q1 2016.

COMPLETE – The outstanding recommendations have been successfully addressed through: the development of the Future Roles and the subsequent stakeholder workshop (1); DFID’s comments on the Future Roles paper and its strong engagement in the stakeholder workshop in June (2); the consolidation of the Gavi, IFFIm and AMC logframes (4); and a thorough assessment of IFFIm’s efficiency and value for money in this annual review, as well as logframe indicators that are focused on IFFIm’s efficiency in raising financing for Gavi (5).

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	N/A
DevTracker Link to Log frame:	To be finalised Q4 2016

Outline of the programme

IFFIm is a financing mechanism that frontloads donor pledges to fund immunisation programmes managed through Gavi. IFFIm uses long-term pledges from donor governments as backing to sell 'vaccine bonds' in capital markets, making large volumes of funds immediately available for Gavi programmes.

Developing countries assessing whether to adopt a new vaccine look for assurance that programme support will continue until they can take over full financing. Likewise, vaccine manufacturers investing in new or expanded production that can take several years of lead time need confidence that there is guaranteed demand. The International Finance Facility for Immunisation (IFFIm) is therefore an important component of the long-term, predictable funding required to support Gavi programmes.

The diagram below illustrates how IFFIm works, showing how legally-binding donor pledges are turned into funds which are immediately available for vaccination programmes.

IFFIm was originally designed to enable Gavi to scale up rapidly in order to meet immediate and urgent needs, and to accelerate progress towards MDG 4 (reducing child mortality). The intention was to disburse US$4 billion of frontloaded and predictable financing to Gavi in order to avert 10 million future deaths; this would have required US$7 billion of funding from donors[1]. In total, IFFIm has received legally binding pledges from donors of approximately US$6.3 billion spanning 23 years. The UK is providing a total of £1.63 billion to IFFIm. UK support is made up of two legally binding pledges, one made in 2006 for £1.38 billion and payable over 20 years from 2007 – 2026, and the second for £250 million, made in 2009 and payable over 20 years from 2010 – 2029. The UK is the largest donor to IFFIm. This review applies to both tranches of UK commitments to IFFIm.
[1] This is because the pledges are over 20 years and due to the time value of money in order to achieve frontloading of $4 billion for programme financing, a higher nominal value of pledge is required.

A key feature of IFFIm is its favourable treatment of pledges on donor governments’ balance sheets. While commitments are attributed to donors at the time of pledging, pledges are only reflected as government expenditure when payments are made to IFFIm. This means that governments can make long-term pledges to IFFIm without the full value immediately appearing on government balance sheets.

With the World Bank as Treasury Manager, IFFIm has kept the average costs of capital below that of the average donor to date. A 2011 independent evaluation found that IFFIm had operated efficiently in respect of IFFIm’s funding costs relative to the weighted average funding costs of its donors. The effects of frontloading increased Gavi’s overall impact, both in terms of delivering results in the short-term and cementing Gavi’s place in the global health architecture, which has subsequently enabled successful replenishments for both the 2011-2015 and 2016 – 2020 strategic periods. IFFIm has also supported Gavi in giving clear signals to the pharmaceutical industry around the size and sustainability of vaccine markets in low income countries. Gavi’s market shaping work has encouraged investment and competition in vaccine production (including from manufacturers in developing countries).

The rate at which programmatic results are achieved depends on both the level of financing available from IFFIm and how rapidly Gavi calls down IFFIm funds; Gavi may call down support more slowly if it has high levels of direct funding from donors in the short term. Estimates of deaths averted depend on a number of factors, many of which are outside IFFIm’s control and depend on Gavi programming and policy decisions – including the mix of vaccines supported by Gavi and the countries funded, since vaccines have widely differing results in terms of deaths averted, chronic health conditions prevented, and efficacy in different regions and countries. It is logical to relate expectations of lives saved through IFFIm funding to our overall expectations of lives saved through total Gavi financing.

This review is based on a new logframe which has taken into account recommendations from the previous annual review to consolidate the Gavi, IFFIm and AMC investments under the same logframe. The focus in the IFFIm review is now on the efficiency of IFFIm as a funding mechanism, better recognising the IFFIm investment as a financing instrument of Gavi. The Gavi results are presented in the Gavi Annual Review.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

As of the end of September 2016, IFFIm had disbursed US$2.48 billion to Gavi and is set to disburse a further US$1.3 billion during the 2016 – 2020 Strategic Period. Gavi has helped to prevent more than 8 million future deaths in developing countries since its inception in 2000 by immunising almost 580 million children. In the 2011 – 2015 period, Gavi immunised 277 million children, preventing in excess of 4 million future deaths; this exceeds targets of immunising 243 million children and averting 3.9 million future deaths.

IFFIm has played a critical role in Gavi’s achievements. As of the end of 2015, IFFIm had provided approximately 20% of Gavi’s total funding, however in its first 5 years of operation from 2006 to 2010, this was in excess of 50%. This investment enabled the rapid scale up of vaccine introductions, and in particular pentavalent; since 2006, IFFIm has provided almost US$1.3 billion to purchase pentavalent vaccines, which in turn resulted in the number of Gavi-eligible countries introducing pentavalent into routine immunisation increasing from 18 at end-2007 to 36 by end-2008, 59 at end-2010 and as of 2014 in all 73 Gavi countries.

Overall output score and description – A+:

Output	Weight	Score	Risk	Comment
1. Demonstration that IFFIm is a feasible, efficient and acceptable mechanism, and is an effective tool for development financing.	100%	A+	Moderate	Good progress & especially strong engagement on how best to leverage IFFIm to support Gavi. Potential options identified which could further improve the VfM proposition of IFFIm.

Key lessons
Over the previous 12 months, DFID and other donors have actively engaged with IFFIm to explore how it can best support Gavi as a financing mechanism. This resulted in a donor workshop at the Gavi Board in June 2016 which enabled a detailed discussion of potential options for future roles of IFFIm; ultimately the discussion highlighted that IFFIm has performed well to date and given its projected funding requirements to Gavi for 2016 – 2020, would require additional donor pledges to significantly expand its remit in supporting Gavi.

Some options that could be considered within the current extent of donor pledges, and which could further improve IFFIm’s value for money proposition, were identified. In particular the use of medium to long-term purchase guarantees to support Gavi’s market shaping activities (e.g. driving down the cost of vaccines or securing supply) was highlighted; this could utilise IFFIm’s strong balance sheet, especially when the gearing ratio is low relative to the defined limit. IFFIm agreed to provide additional information around this option to donors ahead of the IFFIm Board in March 2017.

Fitch changed their outlook for IFFIm from AA (stable) to AA (negative) following the UK referendum vote in favour of exiting the EU in June. This reflects downgrades in the UK’s credit rating, as IFFIm’s rating is primarily based on the rating of its two largest donors, the UK and France. Exchange rate volatility has also continued to place pressure on the World Bank’s swap exposure through IFFIm pledges, and continues to request that any new long-term pledges are made in US$. IFFIm has continued to function effectively in spite of these wider global economic changes.

No additional bond issuances were made by IFFIm in the year to end of September 2016, nor were any disbursements made to Gavi during this time. However a bond issuance and subsequent disbursement to Gavi is planned before the end of the year. This will need to be closely monitored to assess how spreads between IFFIm’s cost of financing and those of donors have changed since the last issuance in 2014.

Has the logframe been updated since the last review? YES

The Gavi, IFFIm and AMC investments have been consolidated into a single logframe. The IFFIm indicators now comprise a single output within this logframe. Two indicators have been taken from the previous IFFIm-specific logframe, with a new third indicator added to ensure the focus of the IFFIm Board remains on financially supporting the successful delivery of Gavi activities. The indicators consequently focus on the efficiency and effectiveness of IFFIm as a financing mechanism.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Demonstration that IFFIm is a feasible, efficient and acceptable mechanism, and is an effective tool for development financing.
Output number per LF		6	Output Score	A+
Risk:		Moderate	Impact weighting (%):	100%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	No

Indicator(s)	Progress 2015
6.1 Net Present Value (NPV) of disbursement to Gavi: NPV of disbursements for other uses (such as interest cost, etc.)	2014: 92.9 : 7.1 / 2015: 93.1 : 6.9
6.2 The spread between IFFIm’s cost of financing and that of the weighted average cost for donors for cumulative outstanding issuances	Current average IFFIm funding costs for outstanding issuances: 3M US$ Libor + 10.0 bps (2014: +9.5 bps) / Current donor average weighted funding costs: 3M US$ Libor + 20.3 bps / (2014: +23.2 bps)
6.3 Proportion of IFFIm disbursements allocated to programmes within Gavi Board mandated policies and the Gavi 2016 – 2020 Strategy	2015: N/A – no disbursements / Historical: 100%

Key Points

6.1: This indicator is a measure of IFFIm’s efficiency as a funding mechanism. It compares how, over the lifetime of IFFIm, funds raised by IFFIm on capital markets have been used, in terms of the ratio of the NPV of the disbursements to Gavi to the NPV of disbursements for other uses (i.e. the cost of raising capital). NPV is used to compare the value of disbursements made at different points in time. As of the end of 2015, 93.1% of the NPV of funds raised have been disbursed to Gavi to fund its activities. This has improved slightly from 2014 when it was just below 93%; this represents the impact of wider economic factors and primarily the continued low interest-rate environment. The 2015 result is significantly better than the 90:10 target ratio.

6.2: Indicator 6.2 is another measure of IFFIm’s efficiency, assessing the cost of IFFIm raising funds against a weighted average of donors’ costs. The indicator specifically assesses outstanding issuances; that is, all bonds which have been issued by IFFIm and are still being repaid, against the weighted average cost for donors for raising funds at the same time as those issuances. In 2015, the weighted average cost of IFFIm’s outstanding bonds was 3M US$ Libor +10.0 bps, 0.103 percentage points lower than the weighted average cost of funding of IFFIm’s donors, which was 3M US$ Libor +20.3. There has been a narrowing in the spread since 2014, when this value was 0.137 percentage points, due primarily to a fall in donors’ cost of funding.

However as noted in the 2015 Annual Review, recent issuances by IFFIm have come at a higher cost of financing than the weighted average cost for donors. The planned issuance this year will provide a further guide to how this spread is developing. However due to past performance, IFFIm costs for outstanding issuances currently remain lower than the weighted average costs for donors.

6.3: Indicator 6.3 was introduced into the consolidated Gavi, IFFIm and AMC 2016-2020 logframe. The intent of the indicator is to ensure that the IFFIm Board are focused on maintain IFFIm’s role as a key funding instrument for Gavi, and that 100% of the disbursed funds are used for Gavi Board mandated policies and the 2016 – 2020 Strategy. No disbursements were made in 2015, but historically this target has been achieved.
Gavi and the IFFIm Board have engaged with donors to consider how to best leverage IFFIm to support Gavi. This resulted in very constructive discussions regarding the viability of these roles, and some potential opportunities to further improve the VfM proposition of IFFIm. Further analysis on these roles will be provided ahead of the IFFIm Board in March 2017. The willingness of IFFIm to initiate these discussions and the openness and helpfulness in taking them forward is particularly noted.

The overall output score also takes into account progress documented against economy, efficiency, effectiveness and equity in the Value for Money section of the Annual Review.
## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

As IFFIm is an innovative financing arm of Gavi, its value for money is assessed based on its Governance costs and the fees of the Treasury Manager, as well as the cost of the funds it raises relative to the UK and other IFFIm donors.

As mandated in IFFIm’s Finance Framework Agreement, IFFIm has no employees. IFFIm outsources all administrative support to Gavi, and outsources its treasury function, together with certain accounting and financial reporting, to the World Bank. Governance costs therefore include those directly associated with the IFFIm Board (e.g. consultancy fees, legal fees, indemnity insurance premiums, meeting and travel costs, and administrative support) as well as the IFFIm Auditor’s remuneration, while the Treasury Manager’s fees cover bond issuance (market research, design, and execution); investment management; financial risk management (hedging of pledges and bonds); management of donor pledges and payments; fund management (commitments, disbursements, programme tracking); ratings maintenance including the gearing ratio model; liquidity monitoring; accounting and financial reporting; and reporting to donors and for IFFIm Board Meetings.

The Treasury Manager’s fees and governance costs give an indication of the economy of IFFIm. Following an uptick in Treasury Manager’s fees in 2011, these have subsequently been reduced and stabilised at around US$2.3 million per year. Governance costs fell substantially (by 32%) in 2015, primarily due to reductions in consultancy fees, legal fees and trustees’ indemnity insurance premiums; however it is not clear that this will represent a new normal going forward. 59% of governance costs in 2015 were attributable to administrative support from Gavi.

Table 1 presents the actual IFFIm governance costs, Treasury Manager fees, and the investment income generated on IFFIm’s assets from IFFIm’s inception in 2006 until the end of 2015. In 7 out of the 10 years presented, investment income has exceeded the Treasury Manager’s fee and governance costs combined. However, the global macroeconomic environment has changed significantly since IFFIm’s inception, and this has had an impact on IFFIm’s funding cost and potential Value for Money. Where market movements are more volatile, for example around interest rates and exchange rate movements as in recent years, it may increase the level of management required (and cost incurred).

Table 1: Overview of governance costs, Treasury Manager fees and investment income, 2006 – 2015 (US$ millions)
	2006	2007	2008	2009	2010	2011	2012	2013	2014	2015
Governance Costs	1.6	2.2	2.8	3.0	2.9	2.7	3.0	2.7	2.8	1.9
Treasury Manager Fees	1.9	1.3	1.8	2.0	2.2	2.6	2.4	2.3	2.3	2.3
Investment Income	3.5	14.4	4.5	10.8	5.7	8.0	6.3	3.8	3.0	4.8

As evidenced in the Output assessment, IFFIm continues to deliver efficiency in terms of using its inputs (donor pledges) to deliver value-for-money financing to Gavi. As of 2015, more than 93% of the NPV of total disbursements that IFFIm makes go directly to Gavi; this is comfortably above the 90% target. The cost of financing the outstanding issues overall remains lower than the IFFIm donor average by 0.103 percentage points, although this has narrowed since 2014. This means that IFFIm has been able to mobilise long term resources from donors in a more efficient way collectively than if they had done so individually. Recent bond issues have had a higher cost of funding than the average donor, and the planned bond issue later in 2016 will need to be monitored to see how the spread compares to previous issues.

The effectiveness and equity of IFFIm’s investments are based on Gavi’s overall performance as it has provided 18.6% of its total financing to date (including AMC proceeds, 2000 to end June 2016), and these are measured separately in the Gavi Annual Review. IFFIm has strongly contributed to Gavi’s overall results performance in 2015 in which an additional 65 million children were immunised and in excess of 0.9 million lives saved.

VfM performance compared to the original VfM proposition in the business case

The 2005 IFFIm Project Memorandum based its analysis on IFFIm being only 3.5% more expensive in NPV terms than financing the programme through a normal grant. However, it set the target maximum difference to be 10%. In line with the performance of previous years, IFFIm reaffirmed in their 2015 Annual Financial Statement that they expect to stay within this 10% over the lifetime of the programme. Factors such as the significant change in the economic environment (principally the historically low interest rate environment) and the effect of the downgrade in IFFIm’s risk rating on its cost of borrowing have led to this difference in performance.

IFFIm has so far been able to mobilise resources in a more efficient collective way than if donors had done so individually, which is further evidence of delivering on the VfM proposition.

Assessment of whether the programme continues to represent value for money

IFFIm has played a key role in supporting Gavi’s evolution as a global health organisation. This will continue as IFFIm is expected to provide US$1.3 billion over the 2016 – 2020 period, representing approximately 15% of Gavi’s overall resources in the period. As outlined above, it is expected that IFFIm will continue to be less than 10% more expensive in NPV terms than traditional donor grants, while also enabling greater frontloading of resources.

An IFFIm donor workshop was held in June 2016. The workshop reviewed three additional potential roles for IFFIm to support Gavi’s activities, alongside IFFIm’s traditional role of supporting vaccine scale up: medium to long-term purchase guarantees; funding the cold chain equipment optimisation platform; and acting as a financing instrument to respond to infectious disease outbreaks.

The latter role would require additional donor pledges, and so cannot be considered within this investment. The most promising of the potential roles was thought to be medium to long-term purchase guarantees to support Gavi’s supply and procurement strategy; this would not necessarily require additional pledges and could utilise IFFIm’s particularly strong balance sheet. IFFIm agreed to provide further analysis around how this could be implemented, along with potential benefits, costs and risks of doing so. IFFIm donors also agreed to revisit the topic of supporting the CCEOP following Gavi Board discussions on this topic in December 2016.

Assuming that operational costs continue at the same level, and wider market conditions do not deteriorate further, then it is expected that IFFIm will continue to represent good value for money. The potential roles for IFFIm could also represent an opportunity to further improve the value for money proposition.

However, IFFIm could be operating more efficiently; it currently has a significant negative swap exposure[2], the size of which means that it must set aside more money to mitigate risk[3]. Despite these constraints, IFFIm will still be able to meet all its currently agreed future funding commitments to Gavi, but reducing the swap exposure would provide IFFIm greater flexibility; the IFFIm Board and the World Bank are discussing ways to lower the swap exposure.
[2] IFFIm enters into swaps with the World Bank to protect both IFFIm’s assets and its outstanding debt from movements in foreign exchange and interest rates. The value of these swaps is minus US$826 million as of August 31st 21016, which means that in the hypothetical case that IFFIm went into default, the World Bank would incur a cost of US$826 million. The value of the swaps will naturally unwind (decrease to zero) as pledges are paid and bonds mature.
[3] IFFIm is required to maintain 12% additional capital over and above the 70.1% set by the gearing ratio limit (end June 2016); in theory this means that IFFIm can only transfer 58.1% of the net present value calculated in US dollars of all the donors pledges to Gavi.

Quality of financial management

IFFIm’s financial reporting is in line with international best practice. Financial forecasts for IFFIm disbursement are aligned with Gavi’s needs and are reported to the IFFIm Board on a quarterly basis. The IFFIm financial statements are audited by KPMG, an external independent auditor, who also issues unqualified audit opinions.

Is the spend profile detailed in the Business Case being followed?

Yes. The UK spend profile to IFFIm is agreed in advance, legally binding and the UK cannot vary from this agreement.

Date of last narrative financial report	31 December 2015
Date of last audited annual statement	31 December 2015

E: RISK (½ page)

Overall risk rating: Moderate

Overview of programme risk

IFFIm is a well-functioning instrument which has operated efficiently and achieved credibility in the international bond markets. IFFIm has been able to continue to operate and to fund Gavi programmes at low cost despite losing its original AAA rating. S&P and Fitch both rate IFFIm as AA (negative), with Fitch having downgraded its outlook from AA (stable) in June 2016. Moody’s rates IFFIm as Aa1 (stable). IFFIm’s rating is primarily based on the rating of its two largest donors, the UK and France; if their ratings deteriorate then further downgrades to IFFIm are possible. The strength of donor support and commitment, and the credibility of the World Bank as Treasury Manager, are both cited as positive aspects supporting IFFIm’s credit rating.

A key risk for IFFIm continues to be around managing currency swap exposure and its impact on attracting new pledges. Exchange rate volatility and risk rating downgrades have led to high levels of exposure imposed on the Treasury Manager. New long term pledges have been requested in dollars with donors being asked to subsume the currency risk or hedge future movements themselves. This additional requirement can cause issues both on the ability of donors to take it on due to institutional constraints as well as their propensity to take on risk. Resolution of this issue has proven challenging and affects the ongoing transferability of the model. This risk does not affect existing pledges.

Risk of funds not being used as intended

IFFIm financial management is governed by the IFFIm legal agreements, including the Finance Framework Agreement. These set out how donor payments are made and how funds are managed by the World Bank as Treasury Manager, and transferred to Gavi. There is a very low risk of funds not being used as intended i.e. not transferred to Gavi to fund vaccination and health systems strengthening programmes. The success of IFFIm may lead to increased pressure from other donors to use it for activities outside its own or Gavi’s mandate; however the commitment to use IFFIm solely to support Gavi’s vaccination and health systems strengthening programmes was reaffirmed during the IFFIm donor workshop in June 2016. The Gavi Annual Review covers the safeguards in place to protect funds from misuse at programme level – i.e. following their transfer from IFFIm to Gavi.

Outstanding actions from risk assessment: None

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

IFFIm has provided US$2.5 billion to Gavi as of September 2016; this represents approximately 18% of Gavi’s total resources since 2000 (US$13.7 billion), and 21% since its inception in 2006. This is below its original target of providing US$3.3bn by the end of 2015, due to Gavi exceeding its replenishment targets for the 2011 to 2015 period and not requiring additional frontloading of IFFIm funds at the scale originally envisaged. In its first 5 years of operation, IFFIm provided more than half of Gavi’s total funding (53%); this is evidence of its ability to frontload resources.

The IFFIm logframe had previously concentrated on the public health benefits attributed to IFFIm funding; the new logframe explicitly recognises that IFFIm is a financing tool for Gavi to use as it needs to do so. This new logframe therefore concentrates on the efficiency of IFFIm’s operating model. Over the 2016 – 2020 strategic period, IFFIm is expected to disburse a further US$1.3 billion between 2016 and 2020, representing approximately 15% of Gavi’s overall resources in the period. The first tranche of this disbursement will occur before the end of 2016.

Performance of partnership(s)

Partnerships continue to perform well, with the World Bank acting as a highly engaged, efficient and credible Treasury Manager. The World Bank and the IFFIm review continue to engage to discuss options that could alleviate the pressures presented by the negative swap exposure.

Asset monitoring and control

The IFFIm Board and the World Bank continue to monitor market issues that affect IFFIm’s performance, and have put in place a limit on the gearing ratio (69.7% as of September 2016); with a further 12% additional capital to be held as a result of the risk management buffer (making the effective gearing ratio limit 57.7%). The actual gearing ratio was 28.0% as of the end of September 2016, down from 28.3% at the end of June.

G: CONDITIONALITY (½ page)

DFID does not currently apply a conditionality policy to Gavi or IFFIm.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

IFFIm was independently evaluated in 2011[4]. This evaluation assessed “whether the IFF concept is proven and whether the IFFIm pilot has worked”. A number of key strengths and weaknesses were identified, including that it had successfully demonstrated a proof of concept but that it had not fully utilised the potential the model offers in terms of frontloading and predictability.
[4] http://www.gavi.org/results/evaluations/IFFIm-evaluation/

The IFFIm donor workshop in June 2016 presented an opportunity to review how IFFIm has operated to date, and how it could be best leveraged going forwards. The opportunity to use IFFIm’s balance sheet for medium to long-term purchase guarantees was explored, with further information to be provided by the IFFIm Board by March 2017. In addition, the World Bank and the IFFIm Board are engaged in assessing whether there are other potential options to alleviate the pressures presented by the negative swap exposure.

Monitoring process throughout the review period

DFID monitors IFFIm’s progress via quarterly reports issued by the World Bank, bi-annual IFFIm donor meetings, and regular dialogue with the Gavi Secretariat. DFID also has a good overview of the progress Gavi made against its 2011-2015 strategic plan, as outlined in the Project Completion Report for the 2011 – 2015 Gavi investment, along with initial progress against the 2016 – 2020 Strategy in the 2016 Gavi Annual Review.

The IFFIm Annual Review 2016 involved discussions with Gavi staff in Geneva, the IFFIm team in Washington DC by videoconference and further desk based analysis carried out in consultation with the Gavi Secretariat. Sources of information included: previous IFFIm annual reviews, Gavi Annual Review 2016, and data from the Gavi Secretariat, World Bank and IFFIm website. Scoring was conducted internally by the DFID Global Funds Department team based on the evidence provided, including a senior staff member not directly involved in the Gavi programme.
Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessment
Key points
Summary of response to programme issues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Output Risk Rating: L/M/H / Enter Low, Medium or High, taken from the overall Output risk score calculated in ARIES
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Review the key risks that affect the successful delivery of the expected results. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process