Annual Review - Summary Sheet

Title: / Africa-Brazil Partnership on Climate-Smart Agriculture and Food Security – ClimAA
Programme Value: / £ 13.4 m		Review Date: / September-October 2016 (review covers implementation period from October 2015 to September 2016)
Programme Code: / 203707	Start Date: / October 2012 (approved March 2012); no-cost extension approved October 2014	End Date: / March 2017

Summary of Programme Performance
Year	2012	2013	2014	2015	2016
Programme Score	-	B	A	A	A
Risk Rating	-	Med	Med	Med	Moderate

Summary of progress and lessons learnt since last review

The programme has made excellent progress towards delivery of outputs during the review period and has consolidated the many partnerships amongst Brazilian, African and international development institutions established over the past three years. An important and exciting development has been the emergence of evidence on the applicability of Brazilian agriculture development approaches to African countries, with important lessons for scale up and great potential for further UK-Brazil collaboration. Most components of the ClimAA programme are near completion and those which had experienced delays are now on track to be completed by the end of the programme’s lifetime.

In line with DFID`s Emerging Powers` objectives, DFID works with Brazil to enhance development impact in Low Income Countries (LICs) by taking some of its learning and testing it in other contexts. Brazil has demonstrated that change is possible by transforming its agriculture sector and tackling hunger faster than most countries and this has prompted a clear demand from LICs to learn from its experience. The programme is enabling the transfer of Brazilian tools and innovative approaches to increase agricultural productivity and food security for the benefit of small farmers in Africa. Through the programme outputs - strengthened partnerships between credible Brazilian and African institutions, testing and adapting Brazilian models focused on improving access to local markets for smallholder farmers, increasing capacity of researchers and government institutions, and the generation of evidence - the programme is showing positive results in targeted LICs. The success of the outputs shows the potential to scale up the use of these technologies and models to enhance impact on the ground. The new UK Aid Strategy emphasis on promoting trade with LICs opens opportunities to build on ClimAA by strengthening the business component of successful agriculture pilots and partnerships which has already started with the M-BOSS project. In addition, the programme serves as a vehicle to facilitate policy dialogue on global development issues between the UK and Brazil, especially in the areas of food and nutrition security and sustainable agriculture, as for example through our partnership with Brazil on Nutrition for Growth, which in turn can help deliver UK’s policy priorities.

All recommendations made in the 2015 annual review have been followed up:

- Additional support to the MKTPlace and WFP CoE components was considered and discussed with the centre but declined due to the need to reduce overall programme spend (as a result of increasing humanitarian crisis). Nonetheless, the WFP CoE was still able to allocate some funding in support of the N4G event preparations.
- IFPRI`s preliminary results from the trials in Malawi and Senegal were disseminated in Brasilia amongst key stakeholders in a seminar hosted by the International Policy Centre for Inclusive Growth (IPC-IG) in December 2015.
- The M&E component of PAA Africa has been prioritised, with significant progress made against targets. DFID has also supported dissemination and resource mobilisation efforts through participation in the international seminar held in Rome in May 2016.
- The DFID Brazil Team have regularly kept DFID country offices up to date with programme implementation and engaged country advisers at the early stage of M-BOSs.

Key highlights

1. The Brazilian Agricultural Research Corporation´s (Embrapa) MKTPlace programme has already met and in some instances, surpassed targets set. It has continued to see an increase in the number of proposals for joint collaboration between Africa and Brazil in agriculture research and it has been selected as a best-practice example at the UN conference on South-South Cooperation to be held in Dubai in November 2016. The past year has also seen a strengthening of its M&E component and huge efforts to share information on the platform, with the publication of a book in October 2016 and a website control panel which provides an interactive overview of all the projects.
2. The new programme called M-BoSs (Building on Successes of the Africa-Brazil Agricultural Innovation MKTPlace) experienced delays caused by contractual issues among Embrapa and Funarbe (the financial management agency), but a first call to scale up the best MKTPlace projects was completed in August 2016. Six projects in Africa which were tested under MKTPlace will be scaled up, with implementation scheduled to start in the last quarter of 2016.
3. The International Food Policy Research Institute (IFPRI) programme has completed the implementation of the randomised control studies in Senegal and Malawi. Preliminary end-line data shows impressive results on the impact of the adaptation of Brazil`s Fomento programme towards increasing agricultural productivity among small farmers. This provides concrete evidence that this model can work in Low-Income Country (LIC) contexts.
4. CALBEE, the programme managed by the World Food Programme Centre of Excellence against Hunger (WFP CoE) component has continued to experience high demand for capacity development support between Low-Income Country (LIC) governments and Brazil[1] and focused on consolidating institutional school-feeding partnerships in Africa. The WFP CoE has been pivotal in accomplishing one of our main policy gains (see below) and it has been identified as a best-practice in South-South cooperation by the United Nations Office for South-South Cooperation.[2]
  [1] The WFP CoE received more than 40 country requests for assistance since 2014 and from 2015 to 2016 it has provided assistance to 28 countries in Africa and Asia
  [2] http://ssc.undp.org/content/dam/ssc/documents/e-library%20docs/Good%20Practices%20in%20South-South%20and%20Triangular%20Cooperation%20for%20Sustainable%20Development(1).pdf, pg. 11-12.
5. Despite delays in the evaluations, in all five pilot countries there are draft plans to scale up the PAA Africa model or some of its components. Two more countries (Gambia and Kenya) are also integrating the PAA model into their national school feeding strategies. A resource mobilisation strategy is underway to secure additional funding for a 3rd phase.
6. DFID Brazil has made attempts to increase engagement of DFID country offices but beyond information sharing, selected project feedback at early stages of the project management cycle and participation in annual reviews, this is difficult. Country advisers allude to time constraints and the small value of DFID Brazil supported projects in terms of spend as the reason why their engagement can only be limited.

Programme management has continued to be rigorous, including follow up on agreed due diligence actions, update of the delivery plan and completion of new audits and studies. Despite having had to reduce overall programme spend, strong relationships with programme partners have prevailed.

Policy accomplishments

A major accomplishment regarding policy collaboration between the UK and Brazil has been the hosting of the Nutrition for Growth event on the eve of the Rio Olympics, despite the unprecedented political and economic crisis in Brazil in the last two decades. The event brought together more than 120 participants, including a number of LICs (Ethiopia, Guatemala) and was opened by the Brazilian Minister of Health and by the General Directors of WHO and FAO. The UK Ambassador in Brazil dubbed it our main policy prize of the Olympics. The event helped to maintain momentum on nutrition through a joint communique by the governments of Brazil, UK and Japan which calls for accelerated action on nutrition and a financial commitment-making event in 2017. N4G Rio followed on from Brazil`s participation at the WHO side-event on nutrition held in Geneva in May 2016 and the UN endorsement of the Decade for Action on Nutrition tabled by Brazil in June 2016. This is testimony that our work on food and nutrition security through ClimAA has contributed to Brazil’s increased global leadership and advocacy on these issues.

Another major policy gain has been the Africa Union designation of 1st March as the Africa School Feeding Day which recognises the contribution of home-grown school feeding to education and income generation at community level and calls for African countries to scale up home-grown school-feeding strategies based on the Brazilian model. This is a direct result of our partnership with the WFP CoE and PAA Africa. In September 2016 a joint communique by more than 40 participating low and middle-income countries in the Global Child Nutrition Forum (Armenia) called for prioritising the scale up of nationally-owned and financed home-grown school feeding policies and programmes.

We also worked with Brazil to host a joint Gender-Based-Violence side-event during the 2016 Humanitarian Summit but the political crisis and resulting senior official staff changes rendered the event impossible. However, working in collaboration with the FCO, we succeeded in encouraging Brazil to make a significant financial contribution to the Syria summit hosted by the UK Prime Minister in February and to the endorsement of our main policy goals. Brazil committed up to US$1 million of support to address food shortages in Syria. Ongoing dialogue with CGFome, the Hunger and Humanitarian Division within the Ministry of Foreign Affairs, one of our main ClimAA partners, was instrumental in ensuring Brazil`s agreement publically to make this commitment.

Finally, we have maintained a strong relationship with the Brazilian Cooperation Agency (ABC) and strengthened collaboration, with much closer engagement from ABC in the monitoring of current projects and the development of a new programme.

Main recommendations for the remaining of the programme

Given the relevance of the IFPRI trials, ensure wider dissemination of results and lessons on the applicability of Brazilian models to African contexts. This can be done by DFID Brazil engaging with country offices and policy teams as well as other funders, to explore potential further support and integration of the Fomento model or elements of the model (e.g. strengthening extension systems and warehousing) into other programmes. The same recommendation applies to PAA Africa.

Ensure ClimAA results are part of the larger seminar on lessons learnt and results from DFID`s Brazil programmes which is planned in 2017, and produce a summary brief to disseminate among DFID country offices and relevant policy teams.

M-BOSs provides an initial scale up of successful MKTPlace projects but beyond this, it needs to start considering how to leverage additional support in order to achieve greater scale, influence national agricultural planning and potentially change national policy.

Consider further support to the World Food Programme Centre of Excellence against Hunger as a GoB’s mechanism to respond to demand from LICs, particularly given the difficult political context in Brazil and uncertainties over government funding in the short-term. Any additional support should be based on prioritisation of countries, stronger follow up on the ground and include nutrition-specific interventions.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/4446020.doc
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/4446027.xls

Outline of the programme

DFID is supporting a set of integrated interventions with a total budget of £13.4 m up to March 2017, to boost agricultural productivity, food security and poverty reduction in Africa through stronger Africa-Brazil cooperation. ClimAA is in line with the new UK Aid Strategy and GPD`s Operational Plan, focusing on encouraging a constructive role from Brazil on global public good challenges as well as expanding and improving the effectiveness of its development assistance to LICs. The Business Case was approved in March 2012 for 3 years at £10.8 m. An additional sum of £2.6 m was agreed in July 2013 for two additional projects giving a total of £13.4 m. Subsequent programme adjustments and an overall budget reduction of 6% for financial year 2016/17 bring the total committed funds to £8,785,543. The programme consists of a number of projects with different Brazilian organisations working in cooperation with Brazilian government institutions and international research institutes.

Our work with Brazil falls under our Emerging Powers` Programme, which has the following objectives: i) to make development assistance more effective; ii) to enhance the development impact of investment in poorer countries and regions; iii) to respond better to global challenges and iv) to work towards an international system that reflects the needs of poor countries. Our development collaboration with Brazil focuses primarily on objectives i, ii and iv. Through ClimAA, we are working with Brazil to address the Zero Hunger, Climate Action, Life on Land and Partnerships Global Goals and expect an increased contribution of Brazil’s development cooperation to poverty reduction in LICs. Although ClimAA pre-cedes its publication, it is aligned with the new UK Aid Strategy objectives 3 and 4 as follows:

- Strengthening resilience and response to crises: Through work with Brazil to strengthen the resilience of small holder farmers in selected African countries, by transferring climate smart agricultural expertise and technology, thus supporting efforts to mitigate and adapt to climate change.
- Tackling extreme poverty and helping the world’s most vulnerable: Our partnership with Brazil on food security and nutrition supports the transfer of the Brazilian experience in eradicating chronic hunger, and provides a platform for global advocacy to promote evidenced based approaches to tackle undernutrition.

The main projects are:

The Africa-Brazil Agricultural Innovation MarketPlace (MKTPlace)
Through a competitive application process MKTPlace supports small innovative research for development projects between Embrapa, African and Latin American and Caribbean (LAC) institutions (mostly academia and research) focused on benefiting smallholder agriculture. Since its inception in 2010, the MKTPlace has supported 82 projects in 13 countries in Africa and 10 countries in LAC. Most DFID funds support projects in Africa, in addition to policy dialogue and knowledge sharing.

Enabling Food Security Policy and Capacity in Africa: Leveraging Brazil’s Experience and Expertise - CALBEE (WFP Centre of Excellence against Hunger)
The WFP Centre of Excellence is an innovative partnership between the Government of Brazil and WFP. It serves as a global platform for South-South cooperation on school feeding, nutrition and food security by sharing best practices and lessons learned from the Brazilian experience. DFID funds support six additional countries: Benin, Cameroon, Ethiopia, Kenya, Mozambique and Togo. The Centre is co-funded by the Brazilian Government and more recently other donors such as the Bill and Melinda Gates Foundation (BMGF).

IFPRI – International Food Policy Research Institute
Through an initial scoping study IFPRI identified two potential Brazilian programmes which might be suitable for application in Africa. One, PAA (a local food purchasing programme), was already being tested through PAA Africa. The other programme, Fomento (a business support package for small farmers), has been adapted and tested by IFPRI in Senegal and Malawi through local implementing partners and has provided evidence on the potential impact of adapting Brazilian models to resource-constrained African settings.

Purchase from Africans for Africa project – PAA Africa
PAA Africa builds on two key components of Brazil’s Zero Hunger Strategy to increase food security through a local food purchasing programme (PAA) and a school feeding programme (PNAE). PAA Africa combines the approaches and learnings from PAA and PNAE in five African countries (Senegal, Niger, Ethiopia, Malawi and Mozambique) and builds on the expertise of the World Food Programme, the Food and Agriculture Organization (FAO), the now dismantled Humanitarian Office (CGFome) of the Brazilian Ministry of Foreign Affairs (MRE), the now merged Ministries of Social Development and Fight Against Hunger (MDS) and Ministry of Agrarian Development (MDA). Phase 2 (consolidation) of the project is now almost complete. DFID funds the knowledge management component, which includes monitoring and evaluation of results as well as dissemination of the evidence and lessons generated.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment
Through ClimAA, DFID works with Brazil to facilitate the application of Brazil’s successful development experience in agriculture and food security to Africa, given agro-ecological similarities and strong demand from African countries. An important objective of the programme is to build the evidence base on the impact and applicability of Brazilian development models to low-income countries. This year has seen exciting results on the potential impact of these models when they are adapted to local contexts in Africa. Moreover, the programme has shown increased demand from LICs to learn from Brazil in the areas of agriculture and food security and has helped Brazil meet this demand effectively. Several proofs of concepts tested and adapted will be scaled up and/or integrated within national strategies and beyond the programme`s life-time. This demonstrates the overall success of the programme.

Key observations from the annual review discussions are:

MKTPlace

- The MKTPlace has won recognition from donors and partners and it has been selected by the United Nations Office for South-South Cooperation as a best-practice example. Since its start in 2010, MKTPlace has launched seven calls for proposals, it has received 793 pre-proposals and approved a total of 82 projects. Out of these, a total of 33 projects in Africa and 9 in LAC have been financed, totally or in part, by DFID resources and 46 have been concluded. Total cash and in-kind contribution to the initiative reached £26 m in 2016, with a DFID contribution of £3.2 m.
- Over 2016, the monitoring and evaluation components have been considerably strengthened, including tighter fiduciary controls and the commissioning of a second external independent evaluation[3]. Field monitoring visits to Africa and to Brazilian collaborating centres were also undertaken by Embrapa’s M&E team.
  [3] Being currently conducted by the European Centre for Development and Policy Management (ECDPM)
- Six successful MKTPlace projects have been selected for scale up under M-BOSs.

Examples of outcomes achieved from MKTPlace Africa projects supported by DFID funds which will be scaled up under M-BOSs include:

- On-farm trials of biological Rhizobium inoculants in Ghana increased mean cowpea grain yields by between 27 to 57%. The potential of this technology is very significant given that cowpea is one of the most important crops in Africa. Through non-DFID funding, a large facility for the production of inoculants will be built in Northern Ghana to facilitate their distribution and provision at low cost for agricultural input suppliers and build awareness of their benefits amongst farmers.
- New technologies for improved honey production in Ethiopia were developed and 80 peer-to-peer farmers were trained on queen bee rearing techniques to improve honey production and quality. Under M-BOSs selected best performing honeybee colonies in the intervention area will be multiplied and distributed to beekeepers based on a joint evaluation and implementation plan by the community and the project team.
- Generation of comprehensive data on economically relevant goat traits, including reproduction and growth performance, parasite resistance, parasite control strategies and marketing in Ethiopia. This knowledge was used to test a community-based goat breeding programme which showed potential for wider adaptation among small farmers. The plan now is to consolidate, refine and scale up this model in Ethiopia and Tanzania, expecting to reach 1,300 households.

CALBEE
- The partnership signed between the WFP CoE with the AU in 2015 has led to a major policy achievement by the Africa Union nominating 1st March as the Africa School Feeding Day.
- In 2016 the African regional school feeding network has been consolidated with support from the centre and a South Asian network is currently under development. The networks bring countries together to share information about home-grown school feeding (HGSF) policies and programmes.
- The centre has been promoting the integration of HGSF into broader social protection strategies and actively sought greater complementarity with broader national and global nutrition efforts.
- The WFP CoE has responded to our request on the need to increase the evidence base of their work by contracting an external impact evaluation of its interventions and the development of a stronger monitoring and evaluation strategy. The evaluation will consider the impact of the Centre against the overall goal and specific objectives of the Implementation Programme agreed by the WFP and the Brazilian government since its establishment in 2011, and its adherence to South-South Cooperation principles[4].
  [4] Brazil does not consider itself a “donor” and all its development activities with LICs is framed within the term “South-South” cooperation. Key principles of Brazilian South-South cooperation include: demand-driven, mutual benefit and country ownership.
- Following recommendations by an independent audit of WFP’s school feeding programme, CALBEE has commissioned a study for the African Union to be led by EPRI (Economic Policy Research Institute, University of Cape Town). The study objectives are:1) to consider how best to assess the impact of school feeding as a vector for development; 2) to define an institutional framework for the implementation of sustainable school feeding programmes and 3) to develop guidelines to support AU states in their adaptation of school feeding programmes.

IFPRI
- IFPRI has completed the endline survey collection in both Senegal and Malawi and preliminary data is very encouraging – the trials have led to a significant increase in small farmers` productivity and income.
- Survey results from Senegal show positive impacts after one year on agricultural outcomes among farmers who received the business plan plus a cash transfer. On average, their millet production was 475 kg higher than among the extension only group, and their gross value of agricultural output was 217,000 FCFA (Franc of the French Community of Africa) or £241 (in May 2015) higher than the extension only group, indicating a more than 100 percent average return on the cash transfer.
- In Malawi, survey results found that both the cash transfer and input packages led to large increases in outputs and yields of the project target crops. There was 22% increase in the overall production of groundnuts and soy; with gains higher in groundnut production, which increases of 36 to 55 %.[5]
  [5] Increases in groundnut production are partly related to the doubled-rid planting technique, which is not possible with all types of crops. Increases might not be as large in other crops.
- The IFPRI trials provide a significant contribution to ClimAA results and have generated evidence on the potential impacts of the adapted Brazilian agriculture model Fomento to African settings. Field-visits showed that the trial results have great potential to influence policy discussions on how to strengthen agriculture extension and improve warehouse systems in Malawi. This is a major contribution to the limited evidence available on the applicability and potential impact of Brazilian models in Africa.

PAA Africa
- In 2015/16, mid-term monitoring reports have been produced for all five countries and a standard monitoring system has been set up with support from the Brazilian International Policy Centre for Inclusive Growth (IPC-IG). The final monitoring report is being drafted. Some delays occurred in the evaluation process but the evaluation is currently underway in Senegal. In Malawi an evaluation team has been selected but the start has been delayed largely as the result of the drought emergency situation and is scheduled to start in November. Final evaluation and monitoring results should be finalised by February 2017.
- Funds for a 3rd phase of PAA Africa have not yet been secured. Implementation and government ownership is at different stages and is influenced by external factors which are beyond the scope of the project, but in all countries there is a strong engagement from government counterparts and interest to scale up, with most progress made in Senegal and Ethiopia where state resources have been committed to home-grown school feeding in the national plans.
- In Ethiopia, the HGSF model was used to implement an emergency feeding programme during the food crisis, showing the potential of the model to build resilience among small holder farmers.

Despite the current political crisis and financial constraints, Brazil continues to actively share its development experience and is committed to expanding its development cooperation with LICs, and ClimAA provides a good platform for the UK to work with Brazil in achieving this. The country has an impressive track record of growth and development and has significantly increased its investment in development cooperation (with estimates of expenditure in the five years to 2009 varying between approximately US$1.6 bn and US$4.17 bn). In the last 20 years average life expectancy increased from 64.7 years to 73.9 years and average income per head per week increased from 447 reais to 793 reais R$554 in 2015). Brazil has almost eradicated chronic hunger and malnutrition. Its development model has been strong on sustainability (reducing levels of deforestation by 80%) and inclusion in terms of both gender and minorities, and Brazil is the only one of the BRICS to have reduced poverty and inequality whilst continuing to grow economically. This is why many Low-Income Countries, particularly in Africa, look to Brazil as a source of learning in their own efforts to reduce poverty and why we are responding to this demand.

Overall output score and description
The annual output score is A (Meets Expectation). This is a complex programme which encompasses many partnerships and the testing of a number of approaches. Overall, very good progress has been made over the past year with the completion of several projects, the emergence of exciting evidence and a clear focus on strengthening monitoring and evaluation. The programme offers important lessons and successes to build on, integrate and leverage on other donor and country food security and agriculture programmes in African countries.

Key lessons for Brazilian Development Cooperation, recipient countries and DFID

South-South cooperation, and particularly the adaptation of successful Brazilian models to African contexts, is a relatively new area of work with increasing demand from LICs but limited evidence of actual impact on the ground. Therefore monitoring and evaluation play an important role in generating lessons on what works and ClimAA has made a significant contribution to strengthening the evidence base.

Most lessons from 2015 AR continue to be relevant:

1. Open and transparent partnerships, information sharing and communication as well as the credibility of Brazilian researchers and the relevance of Brazil`s experience in tackling hunger, are all key factors leading to the success of the MKTPlace and CALBEE to date.
2. Successful research for development projects are stimulating the creation of new projects as they facilitate the establishment of research partnerships between Brazil and LIC institutions.
3. Understanding the local context is key for adapting agricultural development models which have been successful in Brazil and understanding the political economy is also key for scale up and sustainability of results.
4. Political instability and weak leadership in many African countries, some of which are receiving support from Brazil (e.g. Mozambique, Ghana) mean that learning exchanges do not always come to fruition and in some instances, new government officials need to be engaged.
5. Limited capacity in many African settings, particularly at local level, means that long-term technical support is needed to effect change, and that change is often slower than it was in the Brazilian context.
6. Beyond proofs of concept and testing approaches, there is a real need to think of value-addition and understanding the many barriers smallholder farmers face to access markets, financial services and agricultural knowledge and inputs.
7. The importance of irrigation solutions for smallholder farmers and the development of simple technologies which can work and be sustained in resource-poor settings is crucial.
8. As the revised ToC shows, there is a more complex process to go from outputs to outcomes, with the need to understand and address key constraints smallholders face to access local markets, as well the political economy and the necessary actions to influence policy and programmes.
9. Given that this is a relatively new area of work, relationships and partnerships took some time to develop. In future programmes we should ensure some versatility and adaptability, both to respond to emerging demands from LICs as well as to a changing political context with likely new opportunities, challenges and risks.

Key actions

Key follow up actions are captured in the Summary Sheet and through detailed recommendations after each output.

Has the logframe been updated since the last review?

Yes, some of the logframe targets for this review have been increased as the result of including targets from one or two project components (mostly CALBEE) which had not been taken into account in the revised logframe. All targets changed have been increased except for output indicator 3.4 which has been revised down to avoid duplication with other output targets.

Most targets for the remainder of the programme (to March 2017) are cumulative but there are a few which are not. Overall targets should therefore be confirmed by December 2016 to ensure expected cumulative and additional targets are clear to all partners.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Increased capacity of LIC researchers, government institutions and extension staff through participation in LIC-Brazilian pilots, training and policy dialogue
Output number per LF		1	Output Score	A
Risk:		Moderate	Impact weighting (%):	25%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Note: Number in brackets indicates women out of the total number
Indicator(s)	Milestones	Progress
Number of researchers participating in joint research/pilot programmes and exchange visits disaggregated by gender/institutional affiliation and seniority	116 / IFPRI - 4 (2) / PAA - 50 (10) / CALBEE - 60 (20)	Overachieved (291) / IFPRI - 6 (1) / PAA – 38 (8) / CALBEE - 247(110)
Number of people trained in adaptive research, sustainable agriculture technologies, local food purchase systems and extension approaches to disaggregate by gender	350 / PAA - 150 (40) / IFPRI - 200 (60)	Overachieved (360) / PAA –159 (32) / IFPRI – 201(72)
Number of training materials and capacity building events addressing gender issues	9 / IFPRI - 3 / PAA -1 / CALBEE – 5	Overachieved (12) / IFPRI- 5 (training manuals) / PAA - 2 seminars (Ethiopia, Rome) / CALBEE - 5 (all 5 focus countries)

Key Points
The programme has continued to support the capacity building of researchers participating in joint programmes and of a broader range of people including public officials, farmers, farmer associations and school teachers, through their participation in agriculture extension training and data collection, action planning and lesson sharing meetings. The numbers of participants in lesson sharing events has far exceeded expectations. Anecdotal evidence from interaction with farmers and community members linked to both the IFPRI trials and PAA Africa show that the training had been effective – people mentioned what they had learnt and how they applied it. However, because numbers are a poor indication of quality and impact and it is difficult to systematically assess the quality of gender inputs and whether participants were researchers, the overall score should be conservatively an A.

PAA Africa has delivered training on local food purchases to more than 150 government officials and farmers in Malawi, Mozambique and Ethiopia. In May 2016 it held an international seminar in Rome for officials of 7 countries involved in school feeding programmes (PAA Africa countries, Gambia and Kenya) and it also delivered a training workshop in Ethiopia in January 2016.
CALBEE has organised 2 learning exchange visits in Brazil for officials from Burkina Faso and Kenya. In addition, it has supported the Global Child Nutrition Forum in Armenia, bringing together more than 40 countries and 247 participants (including 110 and 13 ministers) to share lessons about school feeding - proving to be a vehicle for sharing Brazil`s experience in a more cost-effective manner (and replacing some of the planned exchange visits).
IFPRI reported that up until September 2016, six researchers (5 males and 1 female) participated in the trials. The IFPRI project is also responsible for a large contribution to Output 1.2 with 201 people (72 women) having been trained in agriculture extension services and data collection. Finally on output 1.3 IFPRI produced five training manuals for data collection that specifically address gender issues.

Summary of responses to issues raised in previous annual reviews (where relevant)

DFID Brazil has continued to share programme information with relevant country offices and sought alternative ways to increase their engagement. Asking for feedback at early stage of new project development (M-BOSs) and inviting participation in field visits are good ways of securing engagement. This is a chance for country advisers to provide inputs and promote coherence with their broader country strategy. However, time constraints and the fact that DFID Brazil`s supported projects are very small in budgetary terms compared to DFID bilateral programmes, are cited as reasons why country advisers can only provide limited support.

The review has seen evidence that the PAA Africa and CALBEE teams have made efforts to ensure greater synergy between their programmes – e.g. participation in key meetings (Ethiopia workshop on home-grown school feeding, international PAA Africa seminar) and thinking about integration of HGSF programmes into broader national social protection platforms.

Recommendations

For future programmes, consider how to assess the quality of capacity building provided by Brazilian institutions to African stakeholders as well as the quality of “gender mainstreaming” beyond counting numbers of people and women who attended seminars or received training.

Output Title	Proof of concepts tested and validated for LIC- specific context for potential outscaling
Output number per LF		2	Output Score	A+
Risk:		Moderate	Impact weighting (%):	25%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones	Progress
Number of proof of concepts/pilots (PoC) initiated	11 / MKP	Overachieved (17) / MKP – 11 (additional round selected in 2015; 6 more in 2016)
Number of PoC tested and validated, with at least 40% showing potential positive impact on women and girls	9 / MKP -7 / IFPRI – 2	Overachieved (11) / MKP – 9 concluded (26% co-led by women) / IFPRI- 2 (Senegal, Malawi)
Number of PoC identified with the potential for upscaling (and number of projects with upscaling initiated and completed)	10 / M-BoSs – 3 / IFPRI – 2 / PAA) – 5	Overachieved (15) / M-BOSs – 6 / IFPRI – 2 (potential for components to be scaled up) / PAA – 7 (Senegal, Niger, Ethiopia, Malawi and Mozambique, Gambia and Kenya)

Key Points

With the programme nearing completion, there has been excellent progress against all output milestones, with targets exceeded in terms of the proofs of concepts identified with potential to be scaled up (2.3). Six successful projects from the MKTPlace will be scaled up under M-BOSs, and the PAA Africa model or elements of the model are being integrated into national school feeding plans in seven countries. Thus, the overall scoring for this output is an A+.

In addition, the two Randomised Control Trials (RCTs) implemented by IFPRI which have tested the potential of an adaptation of the Fomento programme in two different African contexts have been completed in Senegal and Malawi, leading to a significant increase in the income of small farmers, with potential for some components to be scaled up (e.g. the seed replicability programme). In terms of gender, in Malawi more than 40% of participants are women.

PAA Africa has completed the implementation of five country pilots and there is strong indication of commitment from all five governments to expand, strengthen and integrate the local purchase model and institutional market linkages. In addition, two non-PAA Africa countries participated in the international seminar held in Rome in May 2016 and shared plans to integrate elements of the Brazilian model into their national strategies.

The additional 11 MKTPlace proposals approved in 2015 are now well underway. A total of 13 DFID-funded projects (from the 2010, 2012 and 2013 calls) have been finalised (9 during the review period) and evaluation reports were submitted by co-leaders through the online system. See examples of key results in the overall performance section. In addition, MKTPlace supported 6 additional projects through programme re-investment funds.

Summary of responses to issues raised in previous annual reviews (where relevant)
There has been excellent progress towards following up recommendations from the 2015 annual review:

- Monitoring and evaluation will be a key focus of the selected M-BOsS projects (this has been reflected in the accountable grant agreements)
- The methodology and preliminary results from the IFPRI trials were shared with Brazilian partners at a seminar in December 2015 and also in London in September 2016
Recommendations (for end of project)
1. DFID and partners to continue to share results and lessons learnt from the completed pilots and studies, both through seminars in Brazil and dialogue with country offices and relevant policy teams. This will help to build on results and the potential integration of Brazilian models into wider DFID and country programmes.
2. DFID and partners to engage also with other potential funders and through efforts led by Brazilian Embassies in the relevant LICs.

Output Title	Lessons learnt and robust evidence generated on adoption of Brazilian technologies and interventions relevant for policy and programme development in LIC
Output number per LF		3	Output Score	A
Risk:		Moderate	Impact weighting (%):	25%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones	Progress
Number of best practices, lessons learnt documents, internet discussions and policy briefs widely disseminated with at least 30% of papers/briefs addressing gender dimensions	30 / MKT – 2 / PAA – 6 / IFPRI - 2 / CALBEE - 20	Overachieved (43) / MKT – 3 (book, Rev Pol Agric, ECDPM) / PAA – 10 (country fact sheets, FAO briefs, int seminar reports and others)IFPRI – 4 (IPC-IG; 3 draft publications) / CALBEE 26 (twice monthly through WFP CoE website)
Number of evaluation studies/action plans initiated and completed	10 (completed) / 2 complete- IFPRI / 2 complete– PAA / 3 CALBEE action plans completed / 3 MKTPlace evaluations completed	Met (10 completed; 4 underway) / IFPRI- 2 complete / PAA – 2 initiated / CALBEE 5 - 3 action plans completed; 2 studies ongoing / MKTPlace (3 completed;2 initiated)
Number of learning and policy events organised by ClimAA partners	8 / IFPRI 2 / MKP 1 / PAA 1 / CALBEE - 4	Overachieved (12) / IFPRI – 3 (IPC-IG seminar; Brasilia seminar, Senegal learning event) / MKP 4 / PAA – 2 WFP Rome seminar; WFP workshop in Ethiopia / CALBEE (3) 1 GCNF; Ethiopia regional workshop; N4G Rio; Rome)
Number of presentations of lessons learnt from ClimAA at international and national events	8 / IFPRI 4 / PAA 4	Overachieved (9) / IFPRI – 5 (FAO conf; What Works summit, Economic Assoc. Malawi conf, S-S with FONGS and NASFAM) / PAA 4 –Africa Day of School Feeding, Global meeting of the Farmers’ Forum (IFAD), National workshop in (Gambia) WFP 50th Anniversary, GCNF workshop)

Key Points
This past year has seen a major effort from project partners to disseminate information and results, both at national and international level. Efforts to strengthen the evidence on the potential impact and relevance of Brazilian models to low-income countries have also been considerable, with a number of important evaluations and studies underway and on track to be completed by March 2017. Most programme components have contributed to output 3 this year showing significant evidence of impact at both policy and programmatic level. Only output indicator 4.2 has been partially met as the PAA evaluations were expected to be completed or well underway by now. However, there will be additional, non-planned evaluation studies completed by the end of the programme by the WFP CoE. Given that all other indicators have been met or exceeded and that the PAA Africa evaluations are now on-track, the overall outcome for Output 3 is A.
The endline data collection from the IFPRI trials has shown ground-breaking results given that at the start of ClimAA, evidence about the effectiveness of Brazilian interventions for reducing poverty and/or improving food security was largely non-existent. Data from Senegal shows that farmers in the pilot doubled their inputs or return to their investments (for every 200 inputs they received 400 or more in return). The was also a 39% increase in livestock ownership (cows, pigs and chickens). In Malawi, farmers in the programme saw a 25-30% increase in their groundnut yields. In both Senegal and Malawi, the impact of the business plans (extension support to farmers) was not significant. In both cases, the trials show a high return from the cash transfers and also benefits from the synergies between cash transfers and extension services (either cash or a combination were effective). These results are new for agriculture and cash transfer interventions and replicate results from cash transfers used in health and education interventions, where the evidence for training alone is weak whereas the evidence of both cash transfers with education is strong[6].
[6] E.Owuso-Addo and R.Cross, “The impact of conditional cash transfers on child health in low and middle-income countries. A systematic review, International Journal of Public Health 59 (2014); P.Gerler, The Impact of Progresa on Health

IFPRI is planning to publish at least 5 peer-reviewed publications - one on the Malawi trial, one on the Senegal one, one on gender, one comparing the two trial sites and results and one focused on measurement and data collection. Also, with support from the IPC-IG, IFPRI hosted a seminar in Brasilia with a broad range of Brazilian stakeholders in December 2015 to disseminate the preliminary results of the midline surveys, which were already promising at the time. And a presentation at DFID headquarters was hosted in September 2016.
PAA Africa’s main contribution to this output was the international seminar hosted in Rome in May 2016, which brought together more than 120 participants, including government officials, representatives from international organisations, farmer organisations and researchers from seven African countries. The seminar had a session dedicated to M&E where monitoring results from the five pilot countries and plans for the evaluations were presented. The event secured attendance from senior FAO and WFP officials and the programme has got stronger buy-in as a result. The national plans (7 countries) to scale up PAA were also presented. A new programme brochure has been published the publication “Good Practices in South-South and Triangular Cooperation for Sustainable Development”, includes a chapter on PAA Africa [7].
[7] Publication by the United Nations Office for South-South Cooperation (UNOSSC) in 2016 which showcases best practices in South-South cooperation within the UN system, grouped according to the 17 Sustainable Development Goals. It was shared with Heads of States and ministerial representatives of G77 countries during the session.

The publication of a book about the MKTPlace platform and the considerable attention it has received by other international organisations, including IFAD, as well as the high number of in situ evaluations conducted in Africa and Brazil are worth highlighting. In addition, MKTPlace has participated in the following four lesson learning and dissemination meetings: 1) “Towards a Research Agenda for the International Fund for Agricultural Development” at IFAD headquarters in Rome, Italy, December 2015; 2) Two M&E and Procurement Workshops hosted by IFAD in Brazil (one in Bahia and one in Terezina) and 3) the official launch of the M-BoSs programme in Rwanda, June 2016.
CALBEE has held a regional school feeding workshop in Ethiopia and supported the Global Child Nutrition Conference in Armenia, September 2016, with over 240 participants from 45 countries. The 18th GCNC focused on how to design and implement sustainable national school feeding programmes and how to track governments` financial commitments, culminating with the issuing of a joint communique calling for countries to promote national home-grown school feeding policies. As the largest global forum on school feeding, the GCNF plays a key role in enabling high policy dialogue, sharing experience and lessons learnt as well as supporting existing and new regional home-grown feeding networks (indicator 3.4). In addition, the work of the centre was featured at the Rio N4G event.

Summary of responses to issues raised in previous annual reviews (where relevant)

Recommendations from the previous annual review were thoroughly followed up. DFID Brazil worked with WFP to prioritise the evaluations of PAA Africa (the DFID Adviser had several meetings with GoB, WFP and the IPC-G on this issue, and attended the Rome international seminar). DFID Brazil also supported the organisation of the seminar hosted in Brasilia in December 2016 to share the IFPRI trials` methodology and preliminary results, ensured follow-up meetings with ABC and facilitated a London seminar in September 2016.

Recommendations
- Continue to follow up on the PAA Africa evaluations to ensure they are finalised and robust by February 2017.
- Share the evaluation and study findings on home-grown school feeding and organise an internal discussion within DFID on school feeding to address some of the prevailing concerns (e.g. lack of evidence, costs and prioritisation over other interventions in resource-constrained contexts).

Output Title	South-South collaboration strengthened between Brazil and LIC government, research and development institutions working on agriculture and food security
Output number per LF		4	Output Score	A
Risk:		Minor	Impact weighting (%):	25%
Risk revised since last AR?		N/a	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones	Progress
Number of Brazilian and LIC institutions collaborating as part of ClimAA	0	N/A
Number of joint partnerships with signed MoU between LIC and Brazilian institutions working under ClimAA programme	0	N/A
Number of presentations to Brazilian institutes to demonstrate relevance of Brazilian expertise to South-South cooperation and technology transfer	2 / IFPRI – 1 / PAA Africa – 1	Met / IFPRI –1 / PAA – 1

Key Points
Targets for this year were small because given the project cycle, the expectation was for established partnerships to be maintained and strengthened. ClimAA has undoubtedly helped to establish many new partnerships between Brazilian and African institutions and international organisations. Through the MKTPlace alone there are 53 low income country organisations and 32 EMBRAPA centres collaborating in the 82 approved projects. These partnerships are already showing positive impacts both at programmatic (IFPRI collaboration with national farmer organisations) and at policy level (African Union nomination of the Africa School Feeding Day). In terms of expected targets, these were met both by IFPRI (the December seminar hosted with support from the IPC-IG) and PAA Africa (the international seminar held in Rome had representation from the Brazilian Ambassador and other Brazilian government officials) and a workshop in Ethiopia with the participation of the CG-FOME and the Brazilian ambassador. As the targets are somehow reflected in other outputs, the overall score should conservatively be an A.

Summary of responses to issues raised in previous annual reviews (where relevant)
N/A

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance

During twelve months of project activities DFID disbursed £1,872,988 covering the period of October 2015 to September 2016.

At the start of financial year 2016/17 there was an overall programme budget reduction of £564,596.31 (about 6% of original committed funds) due to senior management decision to reallocate departmental spend to meet increasing humanitarian funding needs. Based on the reallocated budget, spending pace is currently at 85% of total funds committed. There has been a shortfall in planned disbursements to PAA Africa due to delays in starting the two country evaluations. It is expected that the last two payments will be made by December 2016.

An outstanding balance of £750,000 remains to be disbursed by end March 2017, which is the closing date for all components. Total approved funds for ClimAA were £13.4 m but given the overall budget programme reduction for financial year 2016/17 and that the EMBRAPA TRU and capacity building components were cancelled, it is expected that by the end of the programme, total funds disbursed will amount to 61.2% of the original approved funds and 95% of the revised total (£8,785,543)..8,785,543.

ClimAA Programme / Components	Total original commitment	12 months Financial Execution / (Oct 15-Sep 16)	Total amount disbursed to date	Balance after reduction
1. PAA Phase I (CG Fome, WFP, FAO)	(closed)	£0	(closed)	£0
2. PAA Phase II (CG Fome, WFP, FAO)	£1,300,000	£0	£673,065	£400,000
3. CALBEE (WFP)	£1,300,000	£447,129.72	£1,299,290.36	£0
4. IFPRI	£1,870,139.50	£545,858.20	£1,633,694.76	£150,000
5. MKTPlace (EMBRAPA)	£3,100,000	£130,000	£3,100,000	0
6. M-BoSs / (EMBRAPA)	£1,200,000	£750,000	£750,000	£200,000
7.Training (EMBRAPA)	£580,000 / (cancelled)	£0	£0	N/A
8.TRU (EMBRAPA)	£580,000 / (cancelled)	£0	£0	N/A
Total original	£9,930,140	£1,872,988	£7,456,050.12	£750,000
Total after reduction	£8,785,543

Following a request from the WFP CoE a no-cost extension to March 2017 for CALBEE was approved in August 2016 to allow this component to be finalised at the same time as all other programme components.

The largest share of expenditure under ClimAA is on fees for personnel and logistics. For some projects, such as with EMBRAPA, staff costs are part of their in-kind contribution. The costs for both are within reasonable limits for the nature and scope of interventions.

Spending is well underway except for the PAA Africa component and has been largely in line with forecasted amounts.

VfM performance compared to the original VfM proposition in the business case
No formal VfM assessment was carried out during this review, but the team was able to consider whether systems currently in place are adequate to ensure VfM and additional examples of how partners ensure VfM are provided below.

Although the project does not have an agreed, routinely reported against set of VfM metrics at output level, partners confirmed their commitment during the annual review to drive project costs down, and many good examples were provided. See below:

- In the IFPRI trials, VFM was an issue in choosing countries for the pilot interventions.  One of the issues that came up in considering some countries (e.g. Kenya instead of Malawi) was that costs of intervention and data collection would be higher.
- IFPRI selection of data collection partners was based on a comprehensive search in both countries, and used the best quality based on average costs.
- The MKTPlace was able to fund 6 additional projects from project re-investment funds.
- CALBEE replaced some individual country missions by the GCNF which proved to be a more cost-effective way of sharing the Brazilian experience with LICs.
- PAA Africa and CALBEE made savings from joined participation at international seminars and meetings instead of separate ones.

Assessment of whether the programme continues to represent value for money

Quality of financial management

Funds for projects are channelled to project partners from DFID’s Global Partnerships Department in Brazil in the following way:

ClimAA Annual Programme	Recipient Institution
1. PAA Phase II (CGFome, WFP, FAO)	WFP P4P Unit in Rome
2. CALBEE (WFP)	WFP Centre of Excellence
3. EMBRAPA (MKTPlace)	FUNARBE[8]
4. EMBRAPA (M-BoSs)	FUNARBE
5. IFPRI	IFPRI (Washington)
[8] Due to the Brazilian Constitution, Embrapa cannot spend funds outside of Brazil without congressional approval for each spend. FUNARBE, a foundation associated with the Federal University of Viçosa, works as financial management agent with Embrapa in selected projects to support and facilitate financial activities .

Recipient institutions have been working in Brazil and with DFID for a long time, with clean audits and no issues of concern. Review of due diligence follow up actions have been conducted twice throughout the reporting period. In addition, there has been an audit of the WFP CoE with some recommendations made to strengthen programme performance but no significant financial issues raised[9].
[9] Independent audit of WFP’s school feeding programme and the WFP CoE’s partnership with Brazil. By the Government of India Control Auditor, June 2016

Date of last narrative financial report	Varies across partners
Date of last audited annual statement	NA

E: RISK (½ page)

Overall risk rating: MEDIUM

Individual risks have not been modified. The programme encompasses some components that are low risk (e.g. delays in approval and transfer of funds by DFID) and some that are medium risk (e.g. where Brazilian models may not be sufficiently adapted to context). The commitment to the programme by Brazilian partners has clearly matured, reducing the risk identified at the outset of the Business Case in 2012 (with some risks moving from high to medium). In addition, the main risks identified at the outset were related to the TRU and training components which have now been removed. The main new risk is the sustainability of some of the programme components in view of the protracted political and economic crisis in Brazil and the absence of secured resources for the scale up of some programme components (PAA Africa, IFPRI trials) However, this risk is unlikely to have a significant impact during the remaining of the programme.

Overview of programme risk

Risks	Level		Mitigating factors
	Probability	Impact
1.Lack of commitment from partners by virtue of shifting political priorities	Low	Medium	Continue to work with focal points in Government and forge partnerships with civil society
2.Resistance of partner Governments and international agencies in reviewing national policies, procedures and programmes to apply lessons and take up new approaches	Low	Medium	Continue to engage local authorities (formal and/or traditional) in all project planning and evaluation stages. Work with focal points in Government and forge partnerships with civil society. / Improve the Brazilian institutions knowledge and understanding of the political economy of the recipient African countries.
3.Brazilian models not sufficiently adapted to context	Medium / (it was high)	Medium	Processes of lesson learning, testing and multi-stakeholder dialogue built into or the primary focus of recommended components. / Better consultation with DFID African countries where and when suitable.
4.Insufficient ownership by African participants and DFID country offices	Low	Medium	DFID Brazil to agree for appropriate engagement opportunities with African country offices / Lead partners build an effective multi-stakeholder network to build buy-in and capacity to engage in recipient countries / Seek country specific road maps for the dissemination & adoption of technology or evidence from research.
5.Capacity of developing country partners insufficient to engage effectively with Brazilian actors	Medium	High	Capacity strengthening built into all main components of ClimAA.
6.Insufficient evidence base to measure results	Medium (it was high)	High	M&E must be part of the engagement with project partners, built into each component, supported by analysis and decision support.
7.Financial mismanagement or fraud within project partners	Low	Medium	No DFID funds are channelled through government systems: / EMBRAPA manages annual funds of US$1bn and Funarbe’s fiduciary systems channel significant international funds, and meet DFID requirements / WFP has a good track record, DFID delivers more humanitarian assistance through WFP than any other agency. WFP meets all of DFID’s fiduciary risk requirements. / IFPRI has a track record of managing DFID funds, and meets CGIAR standards

Outstanding actions from risk assessment

Overall risks to the project are outlined in the updated risk matrix with the following highlighted as key risks:

Engagement with DFID country offices remains a challenge but efforts have been made to engage country offices early at the design stage and in participation of annual reviews.

M-BOSS: Projects are capped at US$700,000 (higher value than under the MarketPlace as it is seeking to scale up successful projects). Funarbe will be responsible for overall management of DFID funds and has agreed to conducting in-country audits of grantees. Grantees will be informed of a zero tolerance policy towards fraud. Financial capacity and track record will be part of the assessment process. Funds will be released against clear expected outputs and financial reporting requirements. Funding will be terminated if any evidence of financial mismanagement or fraudulent activities is identified or if performance targets are not met. In addition, more rigorous evaluation and monitoring arrangements have been agreed with EMBRAPA and budgeted for.

The current political and economic crisis in Brazil poses some challenges to Brazil expanding its development cooperation with LICs at least in the short-term. In addition, Ministerial budget cuts may hamper the expansion of Brazil’s cooperation activities. There might also be potential detrimental impacts on existing activities – e.g. PAA Africa and MKTPlace are unlikely to receive more Brazilian government funding for the time being. Some of these projects are potentially good candidates for future DFID Brazil programme funds.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
On Track?	Y

The programme is on track to deliver against agreed targets by end March 2017.

Performance of partnership (s)
ClimAA is an umbrella programme with decentralised management and a diversified set of partnerships. DFID has established good clear relationships with the key implementing partners and has avoided a centralised programme management service provider, which would be costly and defeat the purpose of having ClimAA as an influential tool to strengthen the UK-Brazil relationship. Instead, the programme does not have a single Brazilian institutional lead, but uses a variety of institutions. This reduces risk and increases the flexibility of DFID support.

Overall, implementing partners are adhering to reporting agreements and have improved their financial management and forecast. Although the beginning of the financial year was difficult in view of the need to revise down budget allocations across the programme, regular communication with partners and explaining the rationale behind has helped to keep relationships on a solid footing.

PAA Africa has felt the impact of the political crisis in Brazil more than other projects as the lead Brazilian official moved on and the division responsible for overall coordination of the programme is being dismantled – although it seems that this might shift to ABC.

Asset monitoring and control

N/A

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)	N/A

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation
The project is based on outputs related to formative research between research institutes in Brazil and Africa and on pilot programming. A significant number of programme results are associated with the publication of scientific research that provides strong evidence of the potential of Brazil’s agricultural development and food security programmes in African countries. Most of the implementation is conducted by project partners - Brazilian institutions with Brazilian expertise - subject to continuous evaluations and peer-reviews. A list of all published briefs and publications in 2015/16 is enclosed in Annex 1.

Methodology

This was an in-depth annual review which combined a desk-review of programme documents, meetings with implementing partners in Brasilia, teleconferences with partners in Rome and Washington and field-visits to two countries in Africa – Ethiopia and Malawi. In Malawi, visits were made to PAA Africa and IFPRI trial sites, including discussions with all relevant stakeholders – female farmers, school principals, teachers, cooperatives, etc. In Ethiopia visits were made to PAA Africa sites and Embrapa partners.
Views from community beneficiaries and evidence from the ground
Discussions held with programme beneficiaries and African partners during the field visits highlight the interest generated about Brazilian models and experiences and the appreciation of some of its unique characteristics – most notably the linking of small farmers with school feeding programmes and the use of cash combined with strengthened extension support services. In Malawi, women engaged in PAA Africa and the IFPRI trial mentioned how they had benefited from raised incomes and explained how they were using this on childcare and household expenditures. Community members also noted improvements in school attendance by girls in PAA Africa schools. Although the reasons behind merit more analysis, a possible reason is the fact that girls do not need to spend so much of their time fetching wood and preparing cooked meals at home and/or that as incomes are growing at the household level, there is less need for girls to work. An examination of drop out and retention records in the schools visited revealed potential positive education impacts[10]. In addition, an examination of the food stores and the school meals provided to children showed evidence of diverse diets and in turn, the links to diversification of agricultural production in programme areas, as the HGSF programme offers farmers a guaranteed market.
[10] Enrolment at Thema 1 has gone from 1059 students in 2011 to 1,468 students now (706 boys and 762 girls). This compares favourably with a national average gender balance which with 1468 pupils would be 866 boys to 602 girls. The principal at Thema 1 also noted that improved nutrition significantly improved attention levels in the classroom. The school had no feeding programme prior. At Kankhande enrolment has gone from 112 in 2011 to some 212 students in 2016 (115 boys and 97 girls). Again this compares favourably to the national average gender balance, which for 212 students would be 125 boys to 87 girls. Also the school principal reported higher rates of graduation from Grade 5, the final grade at the school to Grade 6 for the cohort that received the home-grown school feeding compared to prior cohorts that received traditional school feeding providing some anecdotal evidence of a link between improved enrolment, nutrition and education outcomes. .
These field observations, if corroborated by the evaluations, merit an internal discussion on DFID`s current position on school feeding.

List of documents reviewed and supportive documentation:
1. ClimAA Business Case
2. ClimAA Annual Review 2015
3. MKTPlace interim annual report
4. MKTPlace website
5. IFPRI mid-line reports for Malawi and Senegal
6. IFPRI publically available policy briefs
7. CALBEE annual report
8. CALBEE online policy briefs
9. M-BoSs project proposal
10. PAA Africa`s report from the international seminar
11. PAA Africa country monitoring reports
12. PAA Africa brochure
13. Global Child Nutrition Forum report (2016) and joint communique when available
14. Programme financial reports
15. WFP school feeding programme audit report (include key highlights from audit)