Annual Review - Summary Sheet

Title: South African Partnerships for Effective Development Cooperation (SAPEDC)
Programme Value: £5,042,850		Review Date: 26 October 2016
Programme Code: 203622	Start Date: 1 November 2012	End Date: 31 March 2017

Summary of Programme Performance
Year	2013	2014	2015	2016
Programme Score	A	A	A	A
Risk Rating	Medium	Medium	Medium	Moderate

Summary of progress and lessons learnt since last review
South Africa continued to play an active role in regional and international development cooperation over the past year. The period under review included the culmination of South Africa’s chair of the G77, its chair of the Open Government Partnership (OGP), and taking on co-chair of the Green Climate Fund (GCF). The South African Partnerships for Effective Development Cooperation (SAPEDC) programme was granted a one year no cost extension to maximise some of these opportunities, taking its completion date to 31 March 2017. Addressing feedback from Internal Audit Department (IAD) and the previous annual review, the non-governmental organisation (NGO) Southern Africa Trust (SAT) took on the management function for three new grants during its final year.

Over the past year seven SAPEDC components were completed and three new development cooperation projects were started, with a focus on climate change and inclusion of minorities in Southern Africa. Highlights include a successful pilot for the Twende Mbele (‘Moving Forward Together’) monitoring and evaluation (M&E) programme in partnership with the South African Department for Planning, Monitoring and Evaluation (DPME), which has since become a standalone programme implemented by the Wits School of Governance (WSG). The NGO Open Democracy Advice Centre (ODAC) delivered a well-received project to support the role of African civil society in the OGP, including in Nigeria which has subsequently become a member. Gender reporting and inclusion of gender approaches saw an improvement over the year, particularly by partners such as the Institute for Justice and Reconciliation (IJR), the Southern Africa Liaison Office (SALO) and Gender Links. Challenges were presented by limited progress in the establishment of the South African Development Partnerships Agency (SADPA), as well as by over-optimistic planning and forecasting by some partners.

Lessons learned include:
- South African civil society organisations (CSOs) continue to play a leading role in Africa on a range of UK development priorities, including governance, transitional justice and ‘Leave no-one behind’.
- UK support can play a catalytic role in facilitating South African development assistance, in joint priority areas such as tax capacity building and monitoring the impact of government service delivery.
- Research and policy work on South Africa’s development approaches has had limited traction with the South African government given the lack of progress on SADPA.
- The use of SAT as a managing agent has reduced the administration burden on DFID staff and improved SAPEDC’s financial management overall. However, it has also reduced the level of direct engagement of DFID staff with the implementing partners.

Key recommendations include:
- Using a managing agent is an effective approach for a programme of this nature and should be considered for any similar programmes in future, whilst ensuring that DFID staff retain meaningful engagement with the implementing partners themselves.
- Any future programme should allow DFID to have a qualitative review function of events and research papers, to ensure the quality and relevance of outputs.
- Any future programming in the area of ‘Leave no-one behind’ in Southern Africa should select implementing partners using a call for proposals, to ensure the most effective projects are selected.
- SAPEDC’s flexible funding mechanism should be incorporated into any follow on programme.
- Support to research on South Africa’s development approaches should be pursued only when there is a request for support and clear ‘customer’ in the South African government.
- A successor programme to SAPEDC should explore a work stream to support South Africa’s contribution to SDG Goal 16.
A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-203622/documents
DevTracker Link to Log frame:	http://devtracker.dfid.gov.uk/projects/GB-1-203622/documents

South African Partnerships for Effective Development Cooperation (SAPEDC) is a £5,042,850 programme running from August 2012 to March 2017, funded under DFID Southern Africa (DFIDSA)’s Emerging Powers allocation for South Africa. The programme is designed to increase the transformational impact of South Africa’s development co-operation on poverty, under-development and marginalisation in Africa, as well as its contribution to national and global debates on development.

South Africa is increasingly recognised as an important development actor, both in Africa and globally. In the region, South Africa’s economy drives growth and jobs, accounting for 85% of inter-SADC trade and higher rates of FDI into Africa than China. South Africa’s public institutions, including National Treasury, judiciary and democratic institutions, are widely seen as models across Africa. A number of its government departments are active in addressing development challenges in Africa, including tax capacity strengthening, addressing regional health challenges, and support to peacekeeping and mediation efforts. South Africa’s civil society organisations (CSOs) are active across the region on UK development priorities including transparency, the ‘leave no-one behind agenda’ and transitional justice.

As the only African member of the G20 and BRICS, South Africa is one of the leading representatives of African perspectives in global institutions. As G77 Chair in 2015, it played a key role in the successful outcome of the Sustainable Development Goals (SDGs). During the period of this review, it was lead chair of the Open Government Partnership (OGP) and co-chair of the Green Climate Fund (GCF). South Africa is a prominent economic and political player in the AU, and a key driver of its Africa 2063 development vision.

This programme contributes to South Africa’s development role by partnering with its institutions to help maximise their impact at regional and international levels. It does so partly on the basis of the high level partnership between the UK and South Africa, reviewed every two years at the Ministerial Forum. The meeting held in October 2015 committed the UK and South Africa to ‘enhance partnerships to accelerate the implementation of the Global Goals in Africa, particularly through the UN and also including through the G20, the Commonwealth and UK support to South Africa’s co-chairmanship of the OGP.’

SAPEDC initially focused partly on supporting the establishment of the South African Development Partnerships Agency (SADPA). However, the delays in establishing the Agency have meant that activities to support SADPA have not been possible. Instead, the programme has sought to facilitate development partnerships with a range of South African institutions. It has also provided support to the Parliamentary Committee on International Relations and Co-operation in its development oversight function, via a project with the Institute for Global Dialogue (IGD).

The overall impact of SAPEDC is that SA regional development assistance and global policy influence have a transformational impact on poverty in Africa.

The programme outcome is that South African regional development interventions are selected, designed and managed for maximum results for poor men and women, in line with international best practice.

The programme outputs are:
UK expertise and funding make a significant contribution to the South African Parliament's oversight of Government development and peacebuilding approaches, and the establishment of the South African Development and Co-operation Agency (SADPA)

South African civil society, academia and think tanks increasingly able to contribute to and constructively shape national and international debate on development issues.

South Africa - UK programmatic partnerships in Africa result in sharing and improving expertise on approaches to development cooperation on both sides
## PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

Outcome	South African regional development interventions are selected, designed and managed for maximum results for poor men and women, in line with international best practice.

Indicators	Milestone – September 2016	Progress
Status of progress towards establishment of the South African Development Cooperation Agency as a functional organisation.	Timetable for SADPA bill to Parliament announced	DIRCO’s report to parliament on SADPA in February 2016 noted that a draft bill would be submitted to Cabinet for approval to gazette for public comment. However, this has not yet been done and the timetable remains unclear.
Number of South African development cooperation initiatives achieving results in other countries with UK support through this programme	6 (Oct 2015-Sep 2016)	SAPEDC facilitated 7 initiatives achieving results in other countries, via projects with DPME, IJR, WCO/SARS, ODAC, African Monitor, South South North and Gender Links.
Extent to which SAPEDC partners include gender disaggregation within their quarterly reporting	SAPEDC partners reporting from October to March 2015 include gender disaggregation in their quarterly reports.	Some good progress was made by a number of partners, with some more work to do by others. Projects including Twende Mbele, IJR and Gender Links integrated gender objectives into their programming. Projects including UCT and SALO provided gender disaggregation in their reporting. Others did not fully disaggregate their reporting, which should be improved in the final 6 months.

Overall output score and description
SAPEDC scored 2 As and 1 A+ across its three objectives, thereby scoring an A overall. Under output 1, the Institute for Global Dialogue (IGD) continued its constructive partnership with the Parliamentary Committee for International Relations and Co-operation, providing at least four well received events and publications. Given the committee’s busy schedule and challenges in bringing its members together at the same time for training, the project performed well to deliver the planned outputs within the timeframe.

Under output 2, the WCO/SARS project delivered capacity building activities in 5 countries, exceeding the target, but in the absence of the final report it is not possible to assess whether these corresponded with an improvement in national customs capacities. The project delivered by South South North faced delays caused by political uncertainties in Zambia, which meant that the target was only partially met. Finally, governance and peacebuilding projects delivered by the Institute for Justice and Reconciliation (IJR), the Open Democracy Advice Centre (ODAC) and Wits School of Governance (WSG) for Twende Mbele) exceeded the number of countries targeted. Overall the output is assessed to score an A.

Output 3 also met or exceeded its targets, scoring an A overall. IGD delivered 5 publications on trilateral development co-operation and development diplomacy. African Monitor, Southern Africa Liaison Office (SALO) and the University of Cape Town (UCT) delivered more papers and events on the sustainable development goals (SDGs) and regional integration than planned. African Monitor continued to make a positive contribution to the post-2015 development agenda by securing a collaboration with NEPAD to be the main civil society network to support SDG implementation in Africa. Gender Links exceeded the target for number of local councils with revised gender and gender based violence action plans.

These outputs translated into some achievements at outcome level, notably the support to 7 initiatives achieving development results in other African countries under this programme. However, there was limited observable progress in the formation of the South African Development Partnerships Agency (SADPA). A progress report by the Department for International Relations and Co-operation (DIRCO) to the parliamentary committee on 17 February 2016 stated that DIRCO has completed all the steps necessary for the establishment of SADPA (business case and draft bill developed). It was noted that the executive authorities of DIRCO and National Treasury were still to agree on the institutional arrangements, and that the draft bill would be submitted to Cabinet for approval to gazette for public comment. This has not yet been done at the time of writing.

SAPEDC made some good progress on improving its gender reporting. Some partners effectively integrated gender into their programme activities, whilst others provided gender disaggregated data in their reporting. However, some still need to improve in this area and it is recommended that the Southern Africa Trust (SAT) ensure that all their implementing partners provide gender disaggregated reporting, and consider how gender perspectives can be integrated into their programming.

Key lessons
- South African civil society organisations (CSOs) continue to play a leading role in Africa on a range of UK development priorities, including good governance, transitional justice and inclusion.
- UK support can play a catalytic role in facilitating South African development assistance, in areas of joint priority such as customs reform and monitoring the impact of government service delivery.
- Research and policy work on South Africa’s development approaches has had limited traction with the South African government given the lack progress on SADPA.
- The use of SAT as a managing agent has reduced the administration burden on DFID staff and improved SAPEDC’s financial management. However, it has also reduced the level of direct engagement of DFID staff with the implementing partners.
- Several partners did not spend their full grants and had a balance remaining which will need to be returned to DFID. There appears to be an ‘optimism bias’ amongst some partners in their budgeting and forecasting.
- The new projects developed over the past year have demonstrated SAPEDC’s strengths in responding flexibly to emerging priorities with programmatic interventions.

Key actions
- DFID’s branding requirements should be adhered to by implementing partners. These should be reiterated to SAT and the remaining implementing partners.
- Logframe targets should be reviewed to ensure that they are realistic, particularly for Gender Links and South South North.
- SAT should ensure that all their implementing partners provide gender disaggregated reporting, and consider how gender perspectives can be integrated into their programming.
- Partners’ budgets and forecasts should be scrutinised more robustly for accuracy and realism before disbursements are made.
- DFIDSA should urgently address the current projected overspend (caused by the weakening of the British pound) with SAT to ensure that budgets for the final period do not exceed the approved budget ceiling.
- DFIDSA should ensure that interim auditing measures are put in place by SAT if required, to ensure that the project closure can take place in good time after the end of the programme in March 2017.

Broader recommendations relating to future programming in this area are made in the summary sheet above as well as throughout the output scoring below.

Has the logframe been updated since the last review?
Yes, in order to reflect the new projects supported following the no cost extension, as well as to address the recommendations from the last annual review.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	UK expertise and funding make a significant contribution to the South African Parliament's oversight of Government development and peacebuilding approaches, and the establishment of the South African Development and Co-operation Agency (SADPA)
Output number per LF		1	Output Score	A
Risk:		Moderate	Impact weighting (%):	10%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
1.1 Number of briefings, training events and publications provided for the Parliamentary Committee for International Relations and Co-operation	4 (October 2015-Nov 2016)	Target met. At least four events/publications were delivered, including: / Development diplomacy meeting for Committee Chair and members, 11 Nov 2015. / Strategic planning workshop for the Parliamentary Committee on 9 Feb 2016. / Workshop on development diplomacy on 22-23 Feb 2016, attended by the Committee Chair, content advisor and several members. / Briefing paper on parliamentary oversight of UK development co-operation.

Key Points
The Institute for Global Dialogue (IGD) continued its constructive partnership with the Parliamentary Committee for International Relations and Co-operation over the project period, providing several well received events and publications. This included a workshop on development diplomacy in Cape Town in February 2016, attended and reviewed by the DFIDSA Governance Advisor. The workshop was well attended by Committee members, government and development partners, and received a very positive response from its Chair. IGD has also developed major publications on development diplomacy and trilateral co-operation to capture the research undertaken over the entire project since 2012, reflecting these events and inputs from the committee (captured under output 3 below). These can usefully be drawn on by Committee members in future to support their oversight of South Africa’s development spending, particularly if SADPA makes progress towards becoming operational. Unfortunately, a planned exchange visit under this project to the Parliamentary Committee on International Development in the UK was cancelled due to scheduling challenges. Given the slow progress on SADPA, engagement from the South African government in IGD’s work under this output, including from the Department for International Relations and Cooperation (DIRCO), was limited.

Summary of responses to issues raised in previous annual reviews (where relevant)
DFIDSA staff attended several IGD events over the year to gauge the quality and relevance of their activities. These were largely assessed to be of good quality and well received by the target audiences. However, the 2012 agreement with IGD did not include any formal mechanisms for assessing quality or impact, or to link these to payments. Consequently formal qualitative assessments of outputs did not take place prior to the project’s end in August 2016.

The target indicator was updated as part of the logframe revision to ensure that it was realistic.

Recommendations
For future research projects on South Africa’s development approach, it is recommended a) that DFIDSA take on a formal role in assessing the quality of outputs and b) that monitoring mechanisms are developed to gauge their impact.

Whilst DFID is acknowledged in IGD publications, they are not fully consistent with the current UKAid branding guidelines. This should be addressed in any future programmes.

Output Title	South Africa - UK programmatic partnerships in Africa result in sharing and improving expertise on approaches to development cooperation on both sides
Output number per LF		2	Output Score	A
Risk:		Moderate	Impact weighting (%):	50%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
2.1 Contribution of UK-South African partnerships to enhanced regional trade and investment in the extractives industry	Case study evidence demonstrates increased national capacities in customs procedures in at least 3 countries.	Target met. Capacity building activities conducted in Kenya, Zambia, Zimbabwe, Malawi and Botswana. Final report from WCO documenting outcomes has not yet been received.
2.2 Contribution of UK-South African partnerships to addressing global challenges in other African countries, including health and climate change. between other African countries	Development of draft climate change portfolios for 2 countries as a result of South African assistance.	Target partially met. Preparatory consultations held in Zambia and Namibia. These have secured mandates for the development of investment portfolios, but these remain work in progress.
2.3 Contribution of UK - South African partnerships to building more open and effective governance institutions and more peaceful societies in and between other African countries	Case study evidence of enhanced capacities to promote governance, open institutions and peacebuilding in or between at least 5 African countries as a result of UK-SA partnership	Target exceeded. IJR conducted workshops for Burundi; Rwanda-Burundi-DRC; and Uganda-South Sudan-Kenya. ODAC delivered support for partners in Malawi, Kenya, Tanzania, Ghana and Nigeria. Twende delivered peer learning support involving Uganda and Benin.

Key Points
Projects under this component were broadly successful against the output targets, showcasing South Africa’s development expertise in a range of areas. The project with the World Customs Organisation (WCO) and the South African Revenue Service (SARS), intended to support customs reforms in East and Southern Africa, completed in September 2016. Activities delivered, both bilateral training events and regional training workshops, appear to have been high quality and impactful from the reports received and activities observed by DFIDSA. SARS officials were involved in all missions and hosted several training events, meaning that the project succeeded in its goal of supporting SARS in its regional capacity building role. However, the project struggled to deliver its planned work plan, requiring a six month extension. The interim report indicates that a third of the activities planned were incomplete by the end of the project period.

A new project with the NGO South South North, developed at the request of the Department for Environment Affairs (DEA), has only completed one quarter at the time of this report. It has had a slow start in part due to political uncertainties in Zambia, and targets may need to be revised to ensure that they are realistic for the remaining 6 months.

The Institute for Justice and Reconciliation (IJR) delivered regional reconciliation workshops for university students in the Great Lakes and women activists in Uganda, South Sudan and Kenya. The project also provided transitional justice support to the Burundi Truth and Reconciliation Commission, African Union (AU) and Southern African Development Community (SADC). Reports received provide evidence of impact beyond the activities delivered, and those events attended by DFIDSA were reported to have been well attended and high quality. However, the South Sudan work stream had to be cancelled due to the instability in country.

The project delivered by the Open Democracy Advice Centre (ODAC) conducted a range of activities to support African CSOs to engage with the OGP, coinciding with South Africa’s chair and an African regional conference in May 2016. These included peer learning exchanges with civil society representatives in Malawi, Kenya, Tanzania and Ghana; a civil society day at the Africa regional conference attended by 220, and support to the OGP process in Malawi, Ghana, Kenya and Nigeria. An independent evaluation found that the project strengthened the implementation of the OGP in these countries and civil society involvement, made a meaningful contribution to Nigeria’s successful bid for membership, as well as strengthening CSO networks across Africa and awareness of the OGP. ODAC also co-ordinated a well-received meeting between CSO representatives and the Minister for the Cabinet Office in May 2016, during his visit to South Africa to attend the OGP steering committee.

Finally, the Twende Mbele (‘Moving forward together’) pilot project delivered by the Wits School of Governance (WSG) in partnership with the Department for Planning, Monitoring and Evaluation (DPME) delivered a range of outputs with partners in Uganda and Benin which successfully laid the foundation for the full programme now underway. These included a diagnostic tool to measure the strength of government M&E systems, gender diagnostic to measure their gender responsiveness, country engagement strategy, workshop on engaging CSOs, communications strategy, and concept notes to roll out South Africa’s management performance assessment tool (MPAT) in Uganda and Benin.

Summary of responses to issues raised in previous annual reviews (where relevant)
SAPEDC continued to respond to emerging priorities, as demonstrated by the Twende Mbele pilot. This provided short term, rapid funding to respond to the opportunity presented by this new flagship programme led by DPME, whilst building up the evidence base required for the full programme. The recommendation to reduce the management burden of the programme was addressed by outsourcing this responsibility to the Southern Africa Trust (SAT), at their proposal following a similar arrangement with the Southern Africa Liaison Office (SALO) during previous years of SAPEDC.

Recommendations
The end of the WCO/SARS project marks the completion of two successful customs reform collaborations between WCO, DFID and SARS. There are no plans to pursue a third phase of the project under the Emerging Powers portfolio, but SARS’ expertise and convening role are clearly relevant to regional customs reform efforts. It is recommended that DFIDSA’s future regional trade programme consider whether a component involving SARS could usefully be incorporated, in consultation with WCO and SARS.

Partners including IJR, WCO and ODAC did not spend their full grants and had a balance remaining which will need to be returned to DFID. It is recommended that partners’ budgets and forecasts are scrutinised more robustly for accuracy before disbursements are made.

Governance and peacebuilding are important aspects of South Africa’s development ‘offer’ to the region, via both government and NGOs/CSOs. A successor programme to SAPEDC should explore a work stream to support South Africa’s contribution to SDG Goal 16.

Targets under the output delivered by South South North (2.2) should be reviewed for realism and the logframe updated accordingly.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	South African civil society, academia and think tanks increasingly able to contribute to and constructively shape national and international debate on development issues.
Output number per LF		3	Output Score	A+
Risk:		Minor	Impact weighting (%):	40%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
3.1 Number of UK-funded, SA civil society-produced research papers or events on South African bilateral and trilateral development policies.	5 (October 2015-Sep 2016)	Target met. IGD delivered 5 publications, including on trilateral development co-operation, development diplomacy and a briefing paper on South Africa’s White Paper on international peace initiatives.
3.2 Number of UK-funded, SA-produced research papers or events on global/regional development policy issues including the post-2015 development agenda and its implementation, financing for development and regional integration	10 (October 2015-Sep 2016)	Target exceeded. / - African Monitor conducted 4 dialogues in Kenya, Uganda, Burkina Faso and South Africa, as well as a training for 28 youth from 7 countries in August 2016. / - SALO delivered 5 multi-stakeholder dialogues, 2 CSO engagements and 4 research/policy briefs / - UCT delivered workshops in West and Southern Africa
3.3 Level of involvement and influence of South African civil society organisations in support of priority issues on the post-2015 development agenda	South African civil society actors making a positive contribution to the implementation of the post-2015 development goals in Africa.	Target met. The Africa CSO Working Group, chaired by African Monitor, has secured a collaboration with NEPAD to be the main civil society network to support SDG implementation in Africa.
3.4 Level of involvement of women in championing and advocating for issues affecting them in SADC gender protocol and post -2015 development agenda	At least 100 councils incorporate the SADC gender protocol targets and SDGs into their gender action plans and form a Community of Practice	Target exceeded. 256 local councils (of a targeted 339) have revised their gender and gender based violence action plans.

Key Points
The review period saw a number of work streams come to an end following the finalisation of the Sustainable Development Goals (SDGs). These included a project managed by the South African Liaison Office (SALO), which delivered a number of multistakeholder workshops examining the implementation of the SDGs and the inclusion of minorities, including migrants, people with disabilities, Lesbian, Gay, Bisexual and Transgender (LGBT) communities, and women in conflict situations. These were well attended by regional CSOs representatives and the South African government, particularly DIRCO, the Department for Justice and Department for Social Development.

African Monitor also concluded a successful project which had engaged with African government representatives at both national, regional and UN levels. Their attention also shifted towards domestication of the SDGs, and they undertook four dialogues in Kenya, Uganda, Burkina Faso and South Africa to shift the focus of CSOs and government to this priority. This paved the way for a new project supported under SAPEDC in its final year, with a focus on youth engagement in the implementation of the SDGs in 7 African countries (Ghana, Burkina Faso, Senegal, Kenya, Uganda, South Africa and Nigeria). In its first quarter, this project conducted training for youth champions from each of these countries to participate in national SDG platforms. It also secured agreement with NEPAD to be the main civil society network to support SDG implementation in Africa, conducted a mapping exercise for 5 countries to assess National Development Plan alignment with the SDGs, and translated the SDGs into 7 local languages in 2 countries.

Also under output 3.2, the University of Cape Town (UCT) delivered two regional workshops under their Building Bridges programme, designed to link academics, policy makers and civil society to help address the challenges underpinning the lack of regional integration in Africa. These were held in Dakar for West Africa (on culture, history and ideas) and in Lusaka for Southern Africa (measuring progress in regional integration), the latter attended by DFIDSA’s regional trade advisor. An external evaluation commissioned by the programme found that the workshops involved a broad range of stakeholders, received positive feedback from participants, and successfully broadened the conversation away from the ‘usual suspects’. It questioned the realism of the theory of change, which it found to be too ambitious in its timeframe, particularly given that it was seeking to address ‘wicked problems.’ It also highlighted that the efficacy of the project was limited to satisfaction surveys rather than measuring impact per se. However, the programme clearly attracted some high quality and influential participants from government, academia and international organisations, in part due to the involvement of the influential Policy and Research fellows Trevor Manuel and Thandika Mkandawire. The Lusaka event was reviewed by DFIDSA as good quality, with high calibre participants, but without clear implications for ‘what next.’

The Institute for Global Dialogue (IGD) completed their research project to inform South Africa’s development approaches. They delivered five publications over the programme period, including on trilateral development co-operation, development diplomacy and a briefing paper on South Africa’s White Paper on international peace initiatives. These remain relatively understudied research areas and these publications should provide a rich source of analysis and evidence to inform South Africa’s development approaches in Africa in future. Whilst IGD’s work has had good traction with the Parliamentary Committee on International Relations, the lack of progress on SADPA meant that there was no obvious interlocutor within the South African government, which has limited the extent of their impact compared with some of their products in previous years.

Finally, a new project with Gender Links, designed to increase the level of involvement of women in the implementation of the SDGs in Southern Africa, completed its first quarter. Activities included training of council staff in Botswana, Lesotho, Madagascar, Mozambique, Namibia, Swaziland, Zambia and Zimbabwe. A gender responsive budgeting tool was developed to provide a budgeting framework for councils to use.

Summary of responses to issues raised in previous annual reviews (where relevant)
The last annual review recommended that future programming should focus on the implementation of the Global Goals and Financing for Development agenda, to build on the momentum achieved to date. This was addressed through new projects involving African Monitor and Gender Links, designed to increase the involvement of youth and women respectively in implementation of the SDGs in Africa.

Recommendations
Future research projects to support South Africa’s development approaches should be based on a request for support and clear ‘customer’ in the South African government.

Future policy engagement projects should focus on addressing identified opportunities or ‘policy windows’, to ensure the achievement of tangible development outcomes.

A number of South African based organisations are well placed to promote the ‘leave no-one behind agenda’ in Southern Africa. Any future programming in this area should select implementing partners using a public call for proposals, in order to ensure that the most effective projects are selected.

The new projects developed over the past year have demonstrated SAPEDC’s strengths in responding flexibly to emerging priorities with programmatic interventions. This flexible funding mechanism should be incorporated into any future programme operating in this area.

The targets under output 3.4 have been significantly exceeded. These should be reviewed to ensure that they are sufficiently stretching for Gender Links during the final six months of the programme.
## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance
The key cost drivers remain those highlighted in the Business Case: staffing costs (including for research and policy work), travel costs, events and related expenses. Secondary drivers include the cost of producing publications and training.

VfM performance compared to the original VfM proposition in the business case
In the business case, VfM was defined by effectiveness, efficiency and economy. As recommended in the annual review in 2013 DFIDSA developed a range of metrics to measure VfM at each of these levels.

SAPEDC’s economy was based on the scrutiny of partners’ budgets and processes during the approval process, to ensure consistency with DFID guidelines. Specific metrics include scrutiny of procurement policies; savings achieved through multi-country working; and the delivery against agreed timeframes and budgets. Over the project period, due diligence assessments were conducted for WSG and SAT, which also conducted VfM analyses of African Monitor, SSN, and Gender Links. Procurement processes were found to be in line with DFID guidelines and costs analysed by DFID’s commercial advisors were reviewed as economically competitive. For example the consultant rates used by WSG represented good VfM compared with international consultants. SAT’s management fee was 7% of the overall grant cost, representing good value compared with commercial providers. Several projects (ODAC; IJR; UCT; Twende; WCO) conducted activities across multiple countries, achieving savings compared with equivalent bilateral approaches. The main limitation has been the delivery against agreed timeframes and budgets. No cost extensions were granted for WCO, IGD and ODAC, and a number of refunds have been required at the end of projects.

Efficiency was measured by the programme’s ability to “respond flexibly to changing needs and to evidence on which components are performing well”. Additional metrics developed considered whether events and publications under SAPEDC met the needs of the relevant audience or customer. In terms of its flexibility, SAPEDC’s flexible funding mechanism allowed three new projects to respond to emerging opportunities. The project with SSN in particular allowed DFID to respond to a request from the Department for Environmental Affairs (DEA) to maximise an opportunity presented by the Green Climate Fund (GCF). The no cost extension granted to ODAC allowed the programme to provide strategic support to the OGP Africa regional conference in May 2016. In terms of relevance, the picture is mostly positive. The SSN project was requested by DEA, support by IGD was at the request of the parliamentary committee, and WCO training events were well attended by regional customs officials. However, there was some overlap between the post-2015 projects delivered by African Monitor and SALO. In the absence of SADPA, some partners struggled to find a regular interlocutor within the South African government for their activities.

The effectiveness of the programme was defined by the extent to which activities funded achieved the intended outputs and outcomes. Supplementary indicators focused on the vibrancy, connectivity and effectiveness of networks created, and the contribution of the activities to the development of SAPDA. At output level, activities have met the intended outputs, and made a positive contribution of outcome indicators 2 and 3. However, as highlighted in the logframe’s assumptions, SAPEDC was not able to influence the timetable on SAPDA in the absence of clear political will from Government. Finally, evaluations produced, activities observed and discussions with key stakeholders suggest that some of SAPEDC’s projects made a positive contribution to establishing vibrant regional networks, including ODAC, WCO/SARS and Twende Mbele.

Assessment of whether the programme continues to represent value for money
As with the previous annual review, the picture on VfM looks broadly positive. SAPEDC’s economy indicators appear to be broadly cost effective; it demonstrated good efficiency by flexibly responding to urgent programming requirements and delivering relevant support to key partners; and it contributed to a number of vibrant networks. Key areas to strengthen in the final six months and for future programming include:
- Ensuring that the delivery plans of implementing partners are realistic in terms of their timeframes and budgets.
- A more competitive process to select project implementers for certain work streams.
- Ensuring that all research and policy projects have a ‘customer’ in the South African government.

Quality of financial management
Most SAPEDC partners demonstrated sound financial management over the past year, with partners including IJR and UCT particularly strong. Only one partner demonstrated obvious weaknesses in financial management, requiring significant staff support from DFIDSA and an external audit to be arranged in order to ensure that funds were spent in compliance with DFID systems.

The adoption of SAT as a managing agent from July 2016 and reduction in number of grants has improved the quality of financial management by consolidating reporting and financial requirements. This has allowed the project to proceed on the basis of one payment each quarter rather than multiple, which has improved the programme’s forecasting, payment and variance performance. There are three main concerns in this area for the remainder of the programme. One is a current underspend by each of the three partners under the SAT grant according to agreed workplans, which was in part caused by a late disbursement of funds. The second, as identified below under commercial considerations below, is a projected programme overspend caused by the weakening of the British pound over the first quarter of the SAT grant. In addition, three projects have closed with a small balance remaining, which will need to be refunded prior to the final closure of the programme.

The auditing requirements of the projects under SAPEDC have been a mix of annual audited accounts (with DFID funds identified) and project audits. The former often involve a time lag of up to six months following the end of each organisation’s financial year. The agreement with SAT for the remaining three grants is for annual audited accounts to be provided for SAT and each of the implementing partners. DFIDSA should ensure that interim auditing measures are put in place by SAT if required, to ensure that the project closure can take place in good time after the end of the programme in March 2017.

Date of last narrative financial report	Various. Last was October 2016
Date of last audited annual statement	Various. Last was September 2016

E: RISK (½ page)

Overall risk rating: Moderate

Overview of programme risk
The overall risk rating remains unchanged since the last programme review. Key risks include some of those highlighted in the Business Case, including the risk of a ‘lack of commitment by the Government of South Africa’. This continued to manifest itself with delays to the development of SADPA, which made the IGD project in particular more difficult to deliver.

Additional risks identified over the last year include instability in focus countries, such as in South Sudan which prevented a planned project there by IJR. Another is a potential lack of coherence between those programmes operating regionally and the priorities of DFID country offices. This has been managed through consultation with and regular updates to DFID country offices, for example for the projects delivered by IJR, WCO, ODAC and WSG. Whilst this has been largely effective, the regular turnover of staff in country offices requires this risk to be actively managed. The weakening of the British pound over recent months also raises a risk that partners will overspend according to their agreed budgets (see commercial considerations below).

Outstanding actions from risk assessment
Recommendations from the due diligence assessment of SAT are in the process of being implemented. Programme level risks have been updated in the DFIDSA programme risk matrix and escalated to the DFIDSA leadership group as required. In addition, SAT is developing a risk matrix with its three implementing partners which will be kept under review at quarterly programme meetings.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
SAPEDC’s total spend to date is £4,431,233 of a total approved budget of £5,042,850, which includes £1,649,463 spent during the annual review period. The current forecast on Aries (DFID’s financial management system) for the remainder of the programme is £731,934, meaning that the projected final spend is £5,163,167. This projected overspend is due to the decrease in the value of the British pound since the finalisation of project budgets, which are in Rand (whilst the grant agreements are made in Sterling). DFIDSA should urgently address this with SAT to ensure that budgets for the final period do not exceed the approved budget ceiling.

Performance of partnership (s)
The major change over the past year has been the adoption of SAT as a managing agent for the programme, meaning that for its final six months SAPEDC is based on only one accountable grant. This has responded to the recommendation of the last annual review and significantly reduced the DFID staff management burden of the programme. However, it has also distanced DFIDSA staff from the project implementers themselves, in terms of routine engagement and oversight. It is recommended that the strengths and weaknesses of this approach are reviewed over the next six months and addressed in the business case for any follow on programme.

More broadly, SAPEDC has continued to facilitate relationships between DFID and a range of influential South African institutions, including in civil society, academia, government and parliament. These have been instrumental in facilitating DFID’s development partnerships agenda in South Africa, as well as complimenting broader HMG objectives.

Asset monitoring and control
Only UCT bought assets with project funds (mostly IT equipment and furniture). These were reviewed by a DFIDSA staff member during a spot check in May 2016. UCT provided an asset list and requested a transfer of these assets to support their follow on project, which was approved by the DFIDSA senior responsible owner (SRO).

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)
The Partnership Principles (PPs) are not being used as part of the management or monitoring of this programme. South Africa’s adherence to the PPs was last assessed by DFID in 2014 as follows:

A commitment to reducing poverty and achieving the Millennium Development Goals (MDGs)
Summary: South Africa’s progress on the Human Development Index is static. Progress against MDG targets in health and education is positive and progress against HIV related indicators impressive given the scale of the problem. Inequality, slower than expected economic growth, equitable access to public services are major challenges, but remain central to government planning and development strategies.

A commitment to respecting human rights and other international obligations
Summary: Domestic respect for international human rights instruments is delivered through South Africa’s constitution - widely recognised as one of the most progressive in the world, with robust independent accountability mechanisms and the inclusion of both civil and political rights and economic and social rights. The Constitutional Court and independent bodies like the office of the Public Protector have been able to enforce the provisions of the Constitution. The positive framework provides a strong enabling environment although there are still areas of concern in relation to human rights as reflected in responses to South Africa’s Universal Periodic Report to the Human Rights Council.[1]
[1] http://www.ohchr.org/EN/HRBodies/UPR/Pages/Highlights31May2012pm.aspx

A commitment to strengthening financial management and accountability, and reducing the risk of funds being misused through weak administration or corruption
Summary: There have been many reported and prosecuted incidents of official corruption. South Africa was ranked at 72 of 177 countries in Transparency International’s 2013 Corruption Perceptions Index. Official corruption remains high on the political agenda; South Africa is a global leader on budget transparency with South Africa ranked second globally on the Open Budget Index. The EU and South Africa carried out a PEFA assessment in 2014 and South Africa was again given an ‘A’ rating for its overall public financial management capability.

A commitment to strengthening domestic accountability
Summary: South Africa is a founding member of the ‘Open Government Partnership’ and its successful bid to become co-chair and then lead chair for the OGP demonstrates a commitment to increasing government accountability and transparency both in South Africa, in the region and globally. This partnership aims to bring together government and civil society to find innovative means to improve accountability despite some tensions between the two in recent years.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation
New evidence on South Africa’s regional development role identified over the past year include a research paper by the OECD Development Co-operation Directorate on ‘Development Cooperation by Countries Beyond the DAC’ (May 2015) which estimates South Africa’s development cooperation flows to be $183 million in 2013. An EU funded, National Treasury commissioned research paper (September 2015) into South Africa’s trilateral co-operation activities in Africa found that development partners committed R512m for 72 projects from 2004 to 2014. Of these, the Department of Science and Technology (DST) managed 13 projects, the South African Police Service (SAPS) led on 7 projects and the Department of Defence (DoD) oversaw 6 projects. DRC hosted the highest number of trilateral cooperation activities (9 projects), followed by Burundi (6 projects) and South Sudan (5 projects).

Monitoring progress throughout the review period
This annual review was conducted via a desk review by the South Africa Team Leader in DFIDSA. Information reviewed included partners’ interim and final reports, external evaluations conducted for the UCT and ODAC projects, and reports of events observed throughout the year by the DFIDSA South Africa Team Leader, Governance Advisor and Regional Trade Advisor.
Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. The Aid Management Platform (AMP) and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
A: Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Output Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on AMP as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Minor/Moderate/Major/Severe / Enter: Minor, Moderate, Major or Severe / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on AMP as part of loading the Annual Review for approval). / Where the Risk for this Output has been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section E Risk
Key points
Summary of response to programme issues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D: Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of financial management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E: Risk
Overall Risk Rating: Minor/Moderate/Major/Severe / Enter Minor, Moderate, Major or Severe, taken from the overall Output risk score entered in AMP
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Detail the key risks that affect the successful delivery of the expected results and mitigating actions. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix etc. / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process