Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Sixth General Capital Increase (GCI) of the African Development Bank
Programme Value: £46,741,576		Review Date: September 2016
Programme Code: 202280	Start Date: 2011	End Date: October 2018

Summary of Programme Performance
Year	2012	2013	2014	2015
Programme Score	B	A	A
Risk Rating	L	L	L

Summary of progress and lessons learnt since last review

The AfDB has been able to continue delivering at a time of significant upheaval in the Bank, including the return of the Bank’s Headquarters from Tunis to Abidjan and the introduction of a number of policy and institutional reform priorities intended to improve delivery and impact by President Adesina who took up office in September 2015. During this time the Bank has been able to deliver on its operational commitments without interruption and according to the 2015 evaluation undertaken by Independent Development Evaluation (IDEV) on the AfDB’s GCI VI, ADF12 and ADF13 for the period 2010 – 2014 the Bank is “on the move, and is on the road to positive reform, in the direction that both it and its stakeholders want to see. Put simply, the evaluation finds that the Bank delivers on its commitments; produces important documents, tools and structures; and launches exciting initiatives”. But the evaluation is less able to conclude positively on the Bank’s ability to resource these initiatives, implement them effectively, and bring them to their full conclusion, thus realizing the intended final benefits.” The report reaffirms the considerable progress made and the base created for ongoing improvements in effectiveness and efficiency to be made.However, this period of change has seen a slowdown in several of the institutional improvements such as cost efficiency, staffing and disbursement rates we expected to see have not progressed at the anticipated pace, which means outputs related to these have not scored as well as previously.

In 2015 Bank Group approvals totalled UA 6.33 bn, a 24% increase over 2014. In line with the Bank’s Ten Year Strategy (TYS) infrastructure operations, mostly transport (UA 871.6 mn) and energy (1.72 bn) received the bulk of financial resources. The Bank was also successful in mobilising partnership support launching the New Deal on Energy for Africa and the African Reneable Energy Initiaitive (AREI). Energy and other insfrastructure investments benefitted mostly from the Bank’s private-sector financing window. On the softer side of Bank programming, the sum of UA 595 mn was approved to support vaious human development and relief operatons including the Post Ebola Recovery social Investment Fund (PERSIF) for the three worst affected countries; Guinea, Liberia and Sierra Leone.

In late 2015 the Bank’s new President set out his vision to re-energise the Bank’s Ten Year Strategy. The High Five Agenda is set around five pillars: Feed, Power, Integrate, Industrialise and Improve the quality of life across the continent. The Bank has also embarked on a new cycle of institutional reform through a new Development and Business Delivery Model (DBDM), which aims to further empower regional and field offices and streamline processes to improve efficiency. These are positive steps but as they are yet to be fully rolled there will be limited progress before the end of the GCI VI. We assess these changes will keep the Bank on a positive change trajectory that should support improved delivery and impact once embedded over the coming year.

Summary of recommendations for the next year

Outcome
Through direct DFID contact with the Bank and through our constituency office we will seek to ensure that the Bank delivers its reform agenda associated to the High Five and DBDM quickly to end the hiatus in the reform process, enabling the Bank to become more agile, responsive and reliable for improved delivery and impact.

Output 1
As part of the DBDM scrutiny, DFID and the UK Representative should engage in the design and implementation of the new decentralisation plan under the DBDM banner and monitor its progress and the outcomes.

Output 2
DFID and the Constituency Office will closely monitor the institutional reforms pushing for effective and speedy implementation to ensure a positive impact on delivery and costs.

Output 3
The Constituency Office should report back to the UK on the progress of the next managerial Effectiveness index as an indicator in staff confidence and in the introduction and adoption of the High Five and DBDM.

The Constituency Office should monitor and report on the impact the reform processes have on staff morale and engagement.

Output 4
The UK should work directly with constituency partners, other shareholders and the Bank to ensure that the new High Five strategies and the DBDM are consistent with yet sharpen the focus and delivery of the Ten Year Strategy in areas of comparative advantage, are well prioritised and are within its capacity limits.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	Pre-business case
DevTracker Link to Log frame:	http://eks-web-03/AMP/Project/Documents/202280

Outline of the programme

The AfDB has 78 members, of whom 53 are African regional member countries. The Bank is 60% owned by its regional members The UK at approximately 1.75% is a relatively small shareholder.

The General Capital Increase (GCI) increased its authorised capital by 200% from £22bn to £65bn, and it’s paid in capital by 200% from £1.23bn to £3.484bn The UK subscribed to 73,434 new shares at a total value of £734m. Of the allocated shares, 6% are paid for at a cost of £43,986,199.50, in eight equal annual instalments of £5.5 million per year. The remaining 94% or 69,028 callable shares, valued at £689,123,781, have been recorded in DFID’s Annual Resource Accounts as a contingent liability. In 2010 the UK subscribed to additional shares in the African Development Bank (AfDB) to enable the AfDB to increase the amount it loans to governments in Middle Income Countries (MICs) and to private sector organisations to reduce poverty and promote economic growth and development. These investments have increased the UK’s shareholding at the Bank of 1.75%.

The GCI proposal was supported by a series of reforms to improve the Bank’s operational effectiveness, including strengthening risk management, human resources, the moving HQ staff to field offices, and a stronger focus on results. It also committed the AfDB to developing new energy and private sector policies, and to transfer at least £35m of its operating profits (known as ‘net income’) each year to the African Development Fund – benefiting the poorest countries on the continent.

The AfDB uses its shareholders’ capital to lend to middle-income countries (MICs) at near-market rates, and to lend to and invest in the African private sector. Before the global financial crisis, the Bank loaned and invested around £1.8bn a year. In 2009, this rose to £5.4bn to enable the provision of counter-cyclical finance to help countries through the crisis. The AfDB’s response depleted its reserves, and regulations on its levels of capital adequacy meant that without a General Capital Increase (GCI) it would have been unable to do any new lending in 2011 or 2012. The GCI has enabled the Bank to maintain and increase the amount it lends and invests in Africa.

The GCI also enabled the Bank to increase its investments in the private sector across Africa. The AfDB has typically lent and/or invested around £1bn a year in the private sector in Africa – 40% of which is in low-income countries (by number of loans). This has risen to £1.5bn in 2015.

The GCI primarily benefits Africa’s MICs eligible to borrow from the Bank on near-market terms: Algeria, Botswana, Egypt, Equatorial Guinea, Gabon, Libya, Mauritius, Morocco, Namibia, Seychelles, South Africa, Swaziland and Tunisia. Many of these face a number of development challenges similar to those of low-income countries, such as fostering sustainable growth, and addressing high unemployment rates and poverty. About 128m of Africa’s 320m poor (below USD1.25/day) live in MICs. Basic health services and basic infrastructure remain inaccessible to a high proportion of the population in a number of MICs, such as Botswana, Namibia, and Swaziland where HIV-AIDS affect more than 15% of the population.

The AfDB focuses on accelerating growth to reduce poverty, working in a small number of core sectors: a) infrastructure, b) private sector development, c) governance, d) higher education, science and technology, and e) regional integration. The AfDB has the potential to scale up and be a major player in developing a Pan-African free trade area – both politically and through its infrastructure investments.

Some of the intended outcomes for the GCI VI period are:
•	Population living below $1.25 a day. From 39% in 2009 to 22% in 2015.
•	Under 5 child mortality (per 1000 live births). Reduced from 109 in 2009 to 70 in 2015.
•	Percentage of population with access to an improved water source. From 64.9% in 2009 to 70% in 2015

Additional share issue

In early 2015 the UK confirmed its intention to purchase additional Bank shares. These shares have become available to non-regional member countries and comprise unsubscribed or forfeited shares previously allocated to non-regional member states, and shares that have become available for subscription by non-regional countries following the ratification of South Sudan as a member of the Bank in order that the Bank maintains the approximate shareholding balance between non-regional and regional member countries 60%:40% respectively. This share acquisition was debated and passed through Parliament in September 2015. The share issues comprised:
10,117 unsubscribed and forfeited shares previously allocated to non-regional member countries under the Sixth General Capital Increase (GCI-VI) in 2010; and
22,597 Special Capital Increase (SCI) shares that became available for subscription by non-regional countries following the ratification of South Sudan as a member of the Bank.

The UK has purchased the maximum amount of shares made available. This meant the UK was allocated:
•	1453 shares from GCI-VI (87 paid-up and 1366 callable); and
•	3157 shares from the SCI (189 paid-up and 2968 callable).

Therefore, a further £2,755,377 of paid-in non-fiscal capital expenditure will be paid to the AfDB. It also means the UK is liable to pay an additional £43,267,406 in the unlikely scenario there is a major crisis affecting the bank’s assets or loans (this is known as the contingent liability).

The Breakdown of the share offer is as follows:

Share issue	Shares available to all non-African shareholders	Total shares allocated to the UK	Paid-in shares	Paid-in Capital	Callable capital shares	Contingent liability
GCI VI (share transfer)	10,117	1453	87	£868,542.75	1,366	£13,637,120
SCI (South Sudan balance)	22,597	3157	189	£1,886,834.25	2968	£29,630,286
Total	32,714	4610	276	£2,755,377	4334	£43,267,406
UK SCI share allocation + Total GCI share issue	13,274	13,274	796	£7,946,866.67	12,478	£124,570,794

As of September 2015, the UK is in possession of 113,020 total shares £1.06 billion contingent liability.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

In 2015 Bank Group approvals totalled UA 6.33 bn, a 24% increase over 2014. In line with the Bank’s Ten Year Strategy (TYS) infrastructure operations, mostly transport (UA 871.6 mn) and energy (1.72 bn) received the bulk of financial resources. The Bank was also successful in mobilising partnership support launching the New Deal on Energy for Africa and the African Reneable Energy Initiaitive (AREI). Energy and other insfrastructure investments benfitted mostly from the Bank’s private-sector financing window. On the softer side of Bank programming, the sum of UA 595 mn was approved to support vaious human development and relief operatons including the Post Ebola Recovery social Investment Fund (PERSIF) for the three worst affected countries; Guinea, Liberia and Sierra Leone. The Bank continued with its instutional reforms and effectiveness programmes, implementing the new Bank President’s vision for vision to re-energise the Bank’s Ten Year Strategy. The High Five Agenda is set around five pillars: Feed, Power, Integrate, Industrialise and Improve the quality of life across the continent. The Bank has embarked on a new cycle of institutional reform through a new Development and Business Delivery Model (DBDM).

AfDB enhances its portfolio performance by making key reforms

As part of the GCI VI, the Bank committed to a number of measures to improve the speed and cost effectiveness of programme design and implementation and to give greater emphasis to a number of cross cutting policies. As of 2015 33 of the 35 commitments had been completed,- (commitment 35 being an evalution of commitment 34). A number of follow-up initiatives stemming from these reform commitments are closely monitored to ensure they yield tangible results. These initiatives include: a committee chaired by the Bank President to monitor private sector development implementation; a staff survey which focuses on the four pillars of the Bank’s people strategy and a framework of a policy on guidelines on integrity, due-diligence and non-sovereign operations.

Outcome indicator	Planned	Achieved
Country strategy papers rated satisfactory (1 – 6)	2015 - 5	2015 – 4.3
Percentage of Project completion reports rated satisfactory or higher.	2015 - 78%	2015 – 83%

In 2015, the number of CSPs rated satisfactorily using the CSP readiness methodology were short of the set target. The Bank is currently reviewing the way CSPs are prepared and drafted. The new CSPs will make use of results tools that will improve the Bank’s strategic alignment and track results in a comprehensive manner at country level. The new CSP is currently being piloted.

The 2015 target for the PCRs rated satisfactory or higher was 78%, and achieved 83%. Although this year’s target has been exceeded it is less than was achieved in 2014 when 93% of PCRs met the satisfactory or higher standard.

Overall output score and description

Overall the Bank was able to meet most of its output indicators in 2015. The targets not met in areas of organisational reform reflect a number of changes and uncertainties the Bank has faced since 2014. Firstly the Bank shifted its operations from Tunis to Abidjan, but were able to maintain operations although some reforms were delayed. Secondly the prospect of a new president arriving at the Bank in September 2015 meant a number of policy changes and subsequent reforms were put on hold for most of 2015 until his arrival. Once in post President Adesina began to introduce a number of positive changes that will take time to complete and embed before benefits are seen. Results show that the Bank has been able to increase the number of projects tasked from field offices, even though they are still short on operational staff. The staff engagement index showed positive results indicating that staff remain engaged despite the move to Abidjan and the prospect of change as an outcome of the new president’s reforms. Although Bank experienced delays in pushing new policies forward, some important ones such as the procurement policy and the sovereign operations policy were completed by the end of 2015 while others were put on hold while the new DBDM and High Five strategies including its supporting policies were being drafted for presentation and approval in 2016.

Key lessons

The arrival of the new President in September 2015 has brought considerable organisational and policy change to the AfDB. He has committed to decentralise further, improve portfolio performance and grow the Bank’s business.

In late 2015 the Bank’s new President set out his vision to re-energise the Bank’s Ten Year Strategy. The High Five Agenda is set around five pillars: Feed, Power, Integrate, Industrialise and Improve the quality of life across the continent. The Bank has embarked on a new cycle of institutional reform through a new Development and Business Delivery Model (DBDM), which aims to streamline processes to improve efficiency. This is a positive way forward for both programming and staffing, if managed well and successfully implemented.However, most of these changes will take place during 2016 and early 2017 and so we are cautious about our expectations for the GCI period.

The new changes, whilst welcome, have meant it has been harder for both DFID and the constituency to monitor the progress of some indicators as they have been superceded by the new reforms and processes being put in place. A number of the recommendations going forward for 2016 will be a repeat of those made for 2015 or revised to take account of more to date processes.

Key actions

Through direct contact with the Bank and our Constituency Office we will seek to ensure that the President’s ambitions to raise the profile of the Bank does not undermine, and is in fact supported by, the critical requirement of improving the Bank’s agility, responsiveness and reliability to deliver.

Has the logframe been updated since the last review?

Yes. Output 4 is a rolling indicator, changing every year to highlight pieces of work being undertaken by the Bank, which hold a keen DFID interest. These are mostly policies and strategies so as one completes, new work for the next year is inserted. See the recommendations at Output 4 to see what we shall monitor for 2016.

C: DETAILED OUTPUT SCORING
Output Title	Output 1: AfDB decentralises to improve operational effectiveness
Output number per LF		1	Output Score	B
Risk:		Minor	Impact weighting (%):	30
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
Indicator 1.1 - Operations professional staff based in field offices. %	2015 target 45% achieved 40.6% / 2014 target 40% achieved 50% / 2013 target 35% achieved 39% / 2012 target 35% achieved 36% / 2011 target 30% - achieved 29%	Target not met
Indicator 1.2 - Projects tasked from field offices %	2015 target 53% achieved 60% / 2014 target 50% achieved 51% / 2013 target 45% achieved 50% / 2012 target 35% achieved 42% / 2011 target 22% achieved 25%	target exceeded

Key Points

There has been a decrease in operational staff based in field offices. According to the Bank’s Decentralisation Action Plan, staffing in a number of country offices was intended to rise to relatively large numbers of internationally recruited staff as well as a significant number of locally recruited professional and support staff in2015. However the recruitment freeze and focus on the return to Abidjan in 2014 and 2015 meant there has been an increase in the use of consultants.

A number of actions to update or develop staff guidelines are proposed to ensure that all five regional hubs and country offices are optimally staffed to ensure delivery of the Ten Year Strategy and the High 5s. As at May 2016, the Bank had about 600 budgeted staff positions in its regional and country level offices,but anticipate the continued use of consultants during 2016 and 17, while posts are being filled. Once the posts are filled the Bank expects to greater responsiveness and flexibility in the Bank’s operations.

The target for tasking projects has been exceeded. This shows that other reforms and initiatives such as further delegation of decision making authority to decentralised staff are having a positive effect.

Summary of responses to issues raised in 2014 annual review (where relevant)

DFID and the UK ED should continue to monitor the decentralisation process and press the Bank to submit the decentralisation MTR and revised roadmap by the end of 2015. The Bank, as part of the DBDM has developed a new decentralisation plan which was approved in mid-2016.

Review the MTR and roadmap to decide on key UK priorities and push these with others to ensure full implementation of the plans and improved portfolio performance and assess whether decentralisation has promoted better Bank-Client relationships. See above.

Recommendations
As part of the DBDM scrutiny DFID and the UK Representative should engage in the design and implementation of the new decentralisation plan under the DBDM banner and monitor its progress and the outcomes.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	AfDB improves its business processes and practices streamlining its operations
Output number per LF		2	Output Score	C
Risk:		moderate	Impact weighting (%):	20
Risk revised since last AR?		Yes	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
Indicator 2.1 Lapse of time between project approval and first disbursement of funds decreases.	2015 target 11 achieved 12.6 / 2014 target 11 achieved 10 / 2013 target 12 achieved 11 / 2012 target 10 achieved 13 / 2011 target 11 achieved 13	Target not met
Indicator 2.2 Decrease in admin costs spent per UA 1million disbursed	2015 target 87k achieved 98.9k / 2014 target 87k achieved 98k / 2013 target 89k achieved 92k / 2012 target 93k achieved 86k / 2011 target 105K – achieved 79K	Target not met

Key Points

Targets have not been met in some areas of organisational reform and reflect the significant changes and uncertainties the AfDB has faced since 2014 when the Bank has shifted its operations from Tunis to Abidjan, but impressively were still able to maintain operations. Secondly, the prospect of a new President arriving at the Bank in September 2015 meant that a number of policy changes and strategy decisions were put on hold for most of 2015 until his arrival. Once in post, President Adesina has begun to introduce a set of positive changes but that will take time to complete and embed before the benefits are seen.

The IDEV GCI VI Evaluation rated the efficiency of the process for agreeing commitments as satisfactory. It noted “Efficiency of the GCI VI process is reflected in the number and management of meetings, the small number of papers, and the Bank’s internal management of the overall process. Given the resulting 2005 increase in capital, the time and effort invested in this process was cost effective. In addition the process was inclusive – involving all shareholders through the extended Governors Consultative Committee and regional and civil society consultations.”

There has been a regression in time to first disbursement of funds. Some of the delays can be attributed to weak institutional and management capacity in some member countries, leading to slow project implementation and slow procurement and the inability to meet disbursement conditions. AfDB management has begun implementing the following recommendations from recent internal reviews:

Strengthening the technical review process;
Enhancing accountability in portfolio performance matters;
Shifting focus and resources towards upstream project preparation activities to enhance readiness for implementation before board approval and;
Establishing training programmes for task managers in designing, approving and supervising operations.

President Adesina has also set up a Development, accountability and process efficient committee and a Transformation Management Team, which will both look at issues in programme delivery and costs to improve efficiency and effectiveness of eth Bank to increase speed and quality of delivery.

The actual admin costs per UA 1million disbursed for 2015 was over 10% above the figure forecast. The Bank’s Annual Development Effectiveness Review (ADER) attributes this to a decrease in project approvals in 2015. The same number of skills and staff will have to be deployed and paid for whether 80 or 100 projects are being prepared.

However total Bank Group administrative expenses decreased to UA 323.3 million in 2015 from UA 372.1 million in 2014, primarily due to lower expenses related to the Bank’s return to its Headquarters. Total manpower expenses decreased by UA 33.07 million (12.58 percent) to UA 229.87 million in 2015. The Bank’s share of the total Bank Group’s administrative expenses amounted to UA 122 million for 2015 compared to UA 123.16 million in the previous year. Bank Group administrative expenses are shared between the Bank, the AfDF, and the NTF, based on a cost-sharing formula.

The Bank has indicated that further efficiencies are planned, for example decentralisation will lead to reduced travel costs, an improved balance of local and international staff and a smaller foot print in Abidjan (a high cost base). They also plan to modernise IT systems that should introduce efficiencies.

Summary of responses to issues raised in previous (2014) annual reviews (where relevant)

We should revise indicator 2.2 as this no longer reflects the current reality of the Bank’s HQ being located in Abidjan. We should agree a revised figure by April 2016 in the light of further discussion of the Total Compensation Framework and reflect the outcome of the 2016 Budget discussions. After consultation, we have continued to report on this indicator, but will consider whether to use it as an indicator for future funding.

Recommendation
DFID and the Constituency Office will closely monitor the instutional reforms to ensure effective and speedy implementation that has a positive impact on delivery and costs.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Output 3: AfDB improves efficiency by improving HR management
Output number per LF		3	Output Score	A+
Risk:		Moderate	Impact weighting (%):	30
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
Indicator 3.2– Staff engagement index %	2015 target 67% achieved 73% / 2014 target 64% achieved 64% / 2013 target 62% achieved 61% / Baseline 53% in the year 2012.	Target exceeded

Key Points

Overall, the survey results have been exceeded and show an improvement on last year’s figures. These results are notable given the level of change within the Bank has not seen a drop in staff engagement and also at a time when the managerial effectiveness survey shows that staff are less happy with the quality of management. The ADER highlights some reccurring themes that need addressing; a culture of openness, trust and respect, the persistent gender gap, career development and the toleration of poor performance. However a number of areas reveal some of the Bank’s strengths; pride in working for the AfDB, a sense of accomplishment, clarity of expectations and improvements in work/life balance.

Summary of responses to issues raised in previous (2014) annual reviews (where relevant)

The UK’s Executive Director should use his role as Vice Chair of the Human Resources and Admin Board Committee to continue to encourage the Bank to address the HR challenges by;
•	Push for early resolution to the new business model, decentralisation plan and reorganisation. The new DBDM,organisational structure and decentralisation plan have been presented to and approved by the Board of Directors.
•	Ensuring the HR Director and Corporate Services VP are recruited in good time and to a high standard. Once appointed to work closely with them to define the appropriate HR strategies within the Bank. Both posts were filled in mid-2016 and are helping to operationalise the DBDM.
•	Pushing for greater emphasis on dealing effectively with poor performance. The new DBDM introduced a new perfoamnce management system that includes performance based contracts for all staff (already in place for new VPs, DGs and Directors that have recently been recruited).

The UK should continue to encourage the Bank to consider restraint and cost effectiveness when finalising the new compensation framework, whilst ensuring it reflects the realities of being based in Abidjan and competitive with its market comparators. The compensation framework was agreed with some compromise in May 2016, after a long negotiation between all stakeholders.

Recommendations

The Constituency Office should report back to the UK on the progress of the next managerial Effectiveness index as an indicator in staff confidence in the management and introduction of the High Five and DBDM.

Th Constituency Office should monitor and report on the impact of the reform processes in tow on staff morale and engagement.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Output 4: The AfDB strengthens its strategies and policies to guide long-term activities and improve efficiency and effectiveness.
Output number per LF		4	Output Score	A
Risk:		Minor	Impact weighting (%):	20
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
Indicators 4.1 – 4.3 were completed by end 2014.
Indicator 4.4 procurement policy finalised by end of 2015 meets UK priorities		Target met.
Indicator 4.5 the non-sovereign operations policy finalised by end of 2015 and meets UK priorities		Target met.

Key Points

In 2015 IDEV undertook an evaluation of the Bank’s policy and strategy making and implementation, which supported the findings of the Independent Development Evaluation (IDEV) on the AfDB’s GCI VI, ADF12 and ADF13 for the period 2010 – 2014. The Bank was commended for the wide range of topics covered which were relevant to both the Bank’s and regional member countries’ (RMCs) needs. Implementation was found to be the Bank’s most fundamental challenge. The evaluation found that the production of these policies and strategies “did not guarantee their correct and full implementation”, noting that the bank had not consistently focused on implementation in terms of resourcing, training and guidance, and also in terms of monitoring progress.

Some of the recommendations made by the evalution were:
- Strengthen management of the suites of policies and strategies.
- Streamline and improve the process for formulation of policies and strategies.
- Identify the skills, resources, and support needed for compliance with policies and effective implementation of strategies and ensure their availability as part of the formulation and approval process.
- Hold managers and staff accountable for effective
The overall Bank reform programme already makes reference to the need for the recommendations listed above to be addressed.

More specifically, the Bank’s procurement policy document was approved in October 2015. The UK are satisfied that this new policy model is more flexible allowing for a fit for purpose (FfP) procurement solution including use of Government systems or alternative procurement systems based on risk identification. However we will have to wait and see whether these changes will change the culture within the Bank especially enabling staff so that they feel empowered to make better use of their new delegated authority.

Summary of responses to issues raised in previous (2014) annual reviews (where relevant)

Recommendation: We should continue to monitor the progress of new strategies, policies and initiatives; contributing to Board discussions through the UK Executive Director at the Bank.

This is an ongoing and regular part of DFID’s direct interaction/cooperation with the AfDB, and will continue to be a priority.

We should ensure the procurement policy and non-sovereign operations policy are concluded in a timely manner. These are opportunities where we can influence the Bank’s thinking and ways of working and support so DFID’s interest in economic development. Following substantial input from DFID the final procurement policy was approved in October 2015 largely achieving our objectives.

IFID will update the logframe with two new output indicators for 2015 to reflect that the current indicators have been fully delayed: Indicator 4.4 will be “new procurement policy finalised by end of 2015 and meets UK priorities” and 4.5 that “the non-sovereign operations policy finalised by end of 2015 and meets UK priorities. Indicator updated with progress set out in table above

The UK should continue to monitor progress of new strategies and initiatives, encouraging the Bank to focus its efforts more strategically in line with the IDEV Evaluation recommendations. The UK have continued to be involved in the production of new strategies and initiatives, commenting on draft documents this year, in particular the DBDM, the jobs and energy stragies.

Through the UK ED continue to contribute to Board discussions on corporate, policy, and programme issues and support the Bank’s reform programme. The UK ED consults with the UK seeking advice on both programme and policy issues making the use of briefing and information provided, for use at board meetings.

Recommendations
The UK should work directly with the constituency, other shareholders and in direct contact with the Bank to ensure that the new High Five strategies and the DBDM are consistent with the Ten Year Strategy and maintain the Bank’s focus on areas of comparative advantage, with its capacity limits and effectively prioritised.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

A key cost measure is the annual administrative budget. One of the measures used by the Bank is to assess cost efficiency as administration costs per UA1m disbursed. The Bank has gone through a number of changes during the GCI VI period. The most significant has been the return of the Bank’s HQ from its temporary base in Tunis back to Abidjan. The 2014 admin budget increased, but also made allowances for the return to Abidjan. In 2015 the bank failed to meet its target of UA 87k for every UA1m disbursed spending 98.9k. According to the Bank’s 2015 ADER this is due to a decrease in overall disbursements. The cost of supporting project implementation has also decreased but the cost of preparation increased also due to less projects being approved.

The main cost driver is personnel. The AfDB admin budget totalled UA 123.1 million. The AfDB’s share of the value in respect of officers, staff, organisation, services and facilities and is based on a formula approved by the board.

As part of the return to Abidjan the AfDB paid staff an addition 26% temporary allowance on top of salaries to compensate for the higher cost of living from Tunis, whilst a new salary package was agreed. Following months of consultation, in May 2016, the Board of Directors approved a consolidate pay package, which included an increase of 23% on salaries, based on an MDB comparator model. This took effect from July 2016. Settling this issue should bring certainty following the move to Abidjan and improve the Bank’s recruitment and retention of good quality staff.

The package was agreed within the 19% admin cost increase agreed last December. At that time the Board made clear no additional resources would be made available to support a deal on the salary package. The Bank is currently seeking a fairly modest admin cost increase of 2.72% for 2017 and not based on salaries but to implement the High Five and restructuring costs related to the DBDM (decentralisation, etc.). The UK is proactively engaging in the considerations.

VfM performance compared to the original VfM proposition in the business case

The AfDB GCI VI was approved before the use of Business Cases became standard procedure within DFID.

Overall the 2016 MAR assessed the AfDB as providing good VFM in the delivery of a range of results in Africa’s lowest income countries.

DFID will continue to measure the Bank’s organisational and operational efficiency through the Bank’s Results Framework, which is analysed in the Bank’s Annual Development Effectiveness Reviews. Based on the above, the UK will proactively push for, and monitor, improvements in the Bank’s management and accountability systems with a strong focus on delivering of results and achieving value for money in programme and administrative spend. This includes the Bank giving greater emphasis in its procedures for programme design to require Bank staff to provide different options when designing programmes and challenging and supporting implementing partners justify the value for money in their policy and programme options.

Assessment of whether the programme continues to represent value for money

The 2016 MAR found that the AfDB represented good value for money for the UK having a critical role in meeting UK and international objectives and being integral to the UK’s support to poor African countries. The MAR also found that the AfDB has provided leadership across the MDBs on vfm by leading a working group responding to DFID’s call for a greater focus on vfm. This has resulted in a paper which will form the basis of further consideration by the MDBs, individually and possibly collectively, on how to measure VFM and how to improve it further.

Some of the factors that support the conclusion that the AfDB is good value for money for the UK’s investment are:

- The Bank has a significant focus on economic development, and following the Ten Year Strategy, increased focus on growth, infrastructure, regional integration and a strong focus on wealth creation.
- On the management side the joint AfDB Results Management Framework and the Annual Development Effectiveness Review (ADER) is clear coherent and transparent.
- The AfDB has an independent evaluation department, whose findings are often acted upon and a strong governing body that holds management to account.
- The AfDB offers strong client support particularly in the areas of project design, country strategy consultations and public financial management.
- Finally the Bank continues with its reform agenda which continues to build on its strong reform record. An evaluation undertaken by Independent Development Evaluation (IDEV) on the AfDB’s GCI VI, ADF12 and ADF13 for the period 2010 – 2014 stated that of the 35 commitments to policy and strategy, operations and resources and financial management reform; 33 had been completed.

Quality of financial management

The main financial oversight functions, apart from the Board of Directors, are the responsibility of the following three Bank units: the Office of the Auditor General (independent financial assurance), the Ethics Office (ethical behaviour), and, the Integrity and Anti-Corruption Department (mainstreaming integrity programmes in Bank operations and investigating suspected fraud). The three offices work at arms-length from the rest of the Bank (operations and management).

The Bank is rated by all of the four major rating agencies (Standard & Poor, Moody’s, Fitch Ratings and the Japan Credit Rating Agency – all four have regular update reports on the Bank on their websites) to have sound financial management processes in place. The rating agencies’ positive rating reflects the Bank’s strong financial position (based on sound capital adequacy) and prudent financial and risk management policies. This, together with a positive assessment on its financial systems by the MOPAN 2012, provides external evidence of the Bank’s financial structures, systems and processes.

Audit processes

The Bank is considered by external reviewers to have good audit procedures. The 2012 Multilateral Organisation Performance Network (MOPAN) reported the AfDB as strong in the areas of internal auditing, organisation-wide external audit and its anti-corruption policy. However, MOPAN were less confident about audits at country and project level due to the AfDB using local country auditors. Using country systems means that the responsibility to engage the auditor lies with the borrower as does the decision of whether to release audit reports to the public which could protect the borrower from further scrutiny. However, given the documentary evidence that such audits are taking place, the MOPAN review scored the country and project level auditing as “adequate”.

In 2013 DFID’s Internal Audit Department (IAD) undertook an audit of the AfDB. The IAD focused its audit activities on what it judged to be the most significant risks which could hinder the DFID’s ability to deliver its core objectives. These risks were reported to both IFID and AfDB. IFID regularly reports back to Internal Audit Department on what action is being taken by the Bank to mitigate these risks.

The Board of Directors of the Bank have established an Audit and Finance Committee (AUFI) to assist the Board, among other things, in their oversight responsibility for the soundness of the Bank’s accounting policies and practices and the effectiveness of internal controls. AUFI, which is comprised entirely of selected members of the Board of Directors, oversee the process for the selection of external auditors and makes a recommendation for such selection to the Board of Directors, which in turn makes a recommendation for the approval of the Board of Governors. AUFI meets periodically with management to review and monitor matters of financial, accounting or auditing significance. The external auditors and the internal auditors regularly meet with AUFI to discuss the adequacy of internal controls over financial reporting and any other matter that may require AUFI’s attention.

Date of last narrative financial report	May 2015
Date of last audited annual statement	May 2015

E: RISK (½ page)

Overall risk rating: Minor

The overall risk rating continues to be Minor.

Overview of programme risk

The Bank faces four primary types of risk: fiduciary risk, credit risk, market risk and operational risk. These are closely monitored by the newly created Group Risk Office (GCRO).

Fiduciary risks are assessed by the procurement team during project design and prior to disbursement. The UK has been working with the Bank to strengthen their oversight of fiduciary risk management as a result of the audit by DFID’s Internal Audit Department this is a work in progress and is being led by IAD.

The GCRO aims to strengthen credit risk management and ensuring full risk governance by reviewing all credit risk related issues and making recommendations to the Operations Committee.

In order to manage operational risks such as an Ebola outbreak or a security incident the Bank has a well tested business continuity plan which is implemented when incidents occur. The Bank’s regional resource centres have extra capacity in Pretoria and Nairobi to house extra business critical staff. Parts of the current temporary HQ in Tunis have also been retained following relocation of the HQ to Abidjan to provide further business continuity capacity.
.
Outstanding actions from risk assessment

Reform processes within the Bank do not proceed and (and the return to Abidjan HQ) fail to maintain quality of staff. The Bank now has a clear plan for taking forward institutional changes including Human Resource (HR) reforms which includes a commitment to open, transparent and merit-based recruitment systems. DFID will continue to place the highest priority on this through meetings of donors and through its Executive Director at the Board as the success of both the GCI and AfDF are contingent on the reform processes being implemented and embedding quickly. If not, it poses a significant risk to delivery.

The weak institutional capacity of AfDB countries, especially fragile states, reduces the likelihood of sustainable outcomes from programmes The AfDB has committed to undertake more thorough institutional and political economy analysis before committing investments. The MAR 2016 acknowledges progress and cites the Mali CSP as good example. This should further improve through the Bank’s increased field presence and decentralisation.

Low political will and capacity in partner countries undermines achievement of the Bank’s climate change commitments. The Bank’s Climate Change Action Plan should open the way for greater dialogue in partner countries and increased technical support and institutional strengthening projects. This continues to be a challenge with the Bank. The Bank would like there to be more projects with a climate informed focus within their designs and investors are still not taking up the climate change funding incentives being offered.

External economic risks and the long term viability of the AfDB

Risk	Probability	Impact	Residual risk	Mitigation

Deterioration of global economic environment undermines ability of governments to provide matching finance and put in place complementary conditions for projects to achieve outputs.	Medium	Major	Moderate	When preparing Country Strategy Papers and during project preparation the Bank considers in detail the ability of the recipient Government to repay a loan or to provide the counterpart funding. The final proposal will explicitly state what the recipient Governments contribution will be and ensure that the project will not exceed the country’s debt sustainability based on IMF figures...
Reform processes within the Bank do not proceed and there is a failure to maintain quality of staff.	Moderate	Major	Minor	The Business Delivery Model (DBDM), aims to streamline processes to improve efficiency. In both programming and staffing, and was approved after wide consultation in mid-2016
The weak institutional capacity of AfDB countries, especially fragile states, reduces the likelihood of sustainable outcomes from programmes.	Moderate	Major	Moderate	The Bank undertakes Country Portfolio Performance Reviews to assess the Bank’s in-country performance and a country’s institutional, political and economic capacity before committing investments. The Bank’s increased field presence also supports constant monitoring. .
AfDB projects involved in corruption cases, misused or misappropriated.	Minor	Moderate	Minor	AfDB has the systems and procedures in place to identify fraud and take the necessary anti-corruption measures. We assess that these systems provide reasonable reassurance that funds are used for the right purpose.
Inadequate monitoring leads to failure to take action on poorly performing programmes and projects.	Moderate	Major	Minor	The Bank is introducing a new online system for tracking performance. We will work closely with the Bank to ensure that this system if rolled out effectively and does not damage the implementation of the current portfolio.
Low political will and capacity in partner countries undermines achievement of the Bank’s climate change commitments.	Moderate	Minor	Moderate	The Bank’s Climate Change Action Plan will be renewed in 2016. The Bank has identified a number of issues and are planning training to support staff in the importance of factoring climate change into project design.
Not sufficient Bank attention to gender issues.	Moderate	Moderate	Minor	The Bank finalised the revised Gender Framework and Action Plan in 2014, and since then the Bank’s results have shown an increase in projects with gender informed design and an increase in completed projects showing satisfactory gender outcomes. Where relevant the Bank publishes results that disaggregate between sex and gender. MTR papers note continued challenges given resource limitations.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
The spending profile agreed between DFID and the AfDB and approved by the UK government is being followed.

Performance of partnership (s)
The UK has a small share (1.72%) of the Bank. The UK’s close relationship with the Bank means there is opportunity to influence at policy level corporate issues, less so at project level due to the non-regional voting share being only 40%. The UK also collaborates closely with its constituency countries (Italy and the Netherlands) holding twice yearly constituency meetings and working with other like-minded non-regional and regional members where appropriate.

Asset monitoring and control
N/A

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)
Not applicable

H: MONITORING & EVALUATION (½ page)
The Bank assesses its own portfolio performance and reports on this to the Board. This is an internal, self-assessment process and is closely monitored by senior management.

The Bank’s Independent Development Evaluation (IDEV), though independent is guided by the Bank’s Independent Evaluation Strategy 2013-2017, which focuses on the complimentary objectives for learning, accountability and the promotion of an evaluation culture, in support of the overarching goal of improving evaluation effectiveness.

IDEV has also agreed a new rolling work programme for 2016-2018 that includes the following planned evaluations which match UK interests:

•	Private Sector Development policy and strategy(2016)
•	Bank lines of credit (2017)
•	Programme based operation (2018)
•	Bank’s support to RMC’s response to climate change (2018)
•	People Strategy (2016)
•	Bank Gender Strategy (2017)
•	Integrated Safeguards System (2017)
•	Addressing Fragility and Building Resilience in Africa (2018)
•	Mainstreaming green growth into strategies and operations (2018).
•	Ten Year strategy (2018)
•	Decentralisation(2016)

Monitoring progress throughout the review period

In 2015 a number of evaluations were completed such as:
•	Evaluation of the Quality and Process of Supervision of Bank Project and Program Implementation
•	Independent Evaluation Policy and Functional Responsibilities of the Operations Evaluation Department (OPEV)
•	Administrative Budget management of the AfDB
•	General Capital Increase VI and AfDF 12 and 13 Commitments
•	Water supply and Sanitation in Africa

The aim of these is to provide credible evidence based information that can help inform the Bank’s strategic direction on inclusive growth and transition to green growth; in addition these evaluations inform the production of annual publications such as the African Development Effectiveness Review (ADER), and the AFDB Annual Report.

The 2015 evaluations also provide DFID with evidence on performance in key area such as transport and private sector and core functions such as procurement. No modifications are required in the programme design at this point in time. The evaluations were also used by DFID for the Multilateral Aid Review (MAR) in 2015 as the reports contributed to the wider evidence base. The Bank needs to work further with its partners to improve capacity at country level on statistics and data collection, which remains a challenge in Africa in regards to timely and correct data, including disaggregation by sex and age and other variables of interest for both the Bank and DFID as a subscriber to the AfDB. .

Other sources of information that support monitoring will be the new RMF and the policies and strategies that result from the introduction and implementation of the High Five and DBDM agendas

In September 2015 IDEV published their independent evaluation of the sixth General Capital Increase and AfDF 12 and 13 Commitments.

Overall the evaluation found that the Bank that delivered on its commitments (albeit often late): and produced important documents and tools; established agreed structures; and launched exciting initiatives. However the evaluation could not conclude that the Bank had the ability to resource these initiatives, implement them effectively bringing them to their full conclusion, thus realising the intended final benefits. The evaluation added a note of caution to both the Bank and its stakeholders suggesting that any new major initiatives and reforms should be launched only after thorough planning and clear resourcing of their implementation and recommended the following for future AfDFs and GCIs

•	Focus on fewer and more strategic commitments, with realistic timelines and estimated costs for delivery.
•	Enhance monitoring and managerial accountability for effective performance and results in terms of continued implementation, not only one-off deliveries.
•	Simplify the replenishment processes
•	Seek early Board ownership of commitments

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessment
Key points
Summary of response to iprogrammessues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Output Risk Rating: L/M/H / Enter Low, Medium or High, taken from the overall Output risk score calculated in ARIES
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Review the key risks that affect the successful delivery of the expected results. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process