## HIEP logframe master
PROGRAMME NAME: | Humanitarian Innovation and Evidence Programme (HIEP)
IMPACT | Impact Indicator 1 |  | Baseline | Dec-2013 (programme commenced Dec 2012) | 2014-12-01 | 2015-12-01 | 2016-12-01 | 2017-12-01 | Dec-2018 (target date)
Humanitarian actors use evidence and innovation in the design, financing, planning and delivery of humanitarian policies, programmes and practiciesto deliver effective responses in humanitarian crises. | Number of case studies of HIEP projects that demonstrate HIEP funded research is used and applied by humanitarian policy-maker, practitioners and other relevant stakeholders in decision-making. | Planned |  | Independent evaluation of the HIEP commissioned and completed its inception phase. This includes the section of 8 research impact case studies purposively sampled from the HIEP portfolio. | Independent evaluation completes its formative evaluation stage, which includes positive early observations on set-up the 8 research impact case studies. Independent evaluation enters its summative data collection stage. | Project teams in the 8 research impact case studies continue to influence policy and practitioner communities, and record influencing activities. | Independent evaluation completes the first stage of its summative evaluation. At least 6 of the research impact case studies continue to perform well at engaging and influencing relevant humanitarian policy and practitioner communities. | Within the 8 case studies as projects start to concluded, DFID project teams work with partners to ensure research studies and innovation projects influence the discussions and decision-making of humanitarian policy-makers, practitioners and other stakeholders. | Independent evaluation completes the final summative evaluation. At least 2 of the 8 research impact case studies demonstrate significant influence of the design, financing, planning and delivery of humanitarian policies, programmes and practicies, with at least a further 4 impact case studies demonstrate a positive influence.
|  | Achieved |  | Independent evaluation commissioned, inception phase complete and eight case studies agreed between HIEP/evaluation team | Independent evaluation completes its formative evaluation stage, which includes positive early observations on set-up of the 8 research impact case studies. | Independent evaluation case studies underway. Some early examples of HIEP projects influencing policy and practice, for instance R2HC Ebola response research, and policy engagement around capacity building research.
HIEP Pillar and Business case
All Pillars and Business Cases.
Source (i.e. HIEP project contributing to the indicator)
Each of the Case Study projects from the Independent Evaluation by Itad: 1. Improving the Application of Risk Modelling for Disaster Management; 2. Improving understanding of the institutional framework for delivering cash in emergencies at scale/ Preventing acute under nutrition using food and cash-based approaches; 3. Improving the evidence base on public health in emergencies (R2H2); 4. Improving access to humanitarian evidence (HESC); 5. Innovation : testing to proof of concept (Humanitarian Innovation Fund (HIF)); 6. Improving the Evidence Base of how to Deliver Aid in Highly Insecure Environments; 7. Improving the Evidence Base on How to Work with National and Local Authorities to Improve Disaster Risk Management; 8. Strengthening the Quality and use of Humanitarian Evaluation.
Who is responsible?
Independent Evaluation Team; HIEP project team meeting and contact records.
OUTCOME 1 | Outcome 1 Indicator 1 |  | Baseline | Dec-2013 (programme commenced Dec 2012) | 2014-12-01 | 2015-12-01 | 2016-12-01 | 2017-12-01 | Dec-2018 (target date) | Assumptions
International donors develop funding instruments and frameworks for investment into humanitarian evidence and innovation, and it applications. | Influenced in some way by the HIEP, other international donors establish new or expanded humanitarian research and innovation funding instruments (with description of type of funds/investments). | Planned | 0 (2012) | Not assessed as too early in the programme's development. | Not assessed as too early in the programme's development. | One example of another donor scoping or establishing new research and innovation funding instruments. | Two examples of other donors scoping or establishing new research and innovation funding instruments (cumulative). | Three examples of other donors scoping or establishing new research and innovation funding instruments (cumulative). | At least three examples of other donors scoping or establishing new research and innovation funding instruments (cumulative). | DFID needs to stimulate new operational relationships and markets with donor counter-parts and agencies through joint analysis, programming and funding to influence changes behaviours, systems and cultures around evidence-use
|  | Achieved |  |  | 1 achieved: SIDA are investing in gender violence challenge fund, replicating the HIF WASH stream. | Links developed with other donors to share knowledge and learning. DFID working with others on the Global Alliance for Humanitarian Innovation, and links formed with USAID/SIDA/Rockerfeller (GRP)
HIEP Pillar and Business case
n/a
Source (i.e. HIEP project contributing to the indicator)
Intellegence gathered from the HIEP Secretariat's knowledge of the humanitarian research sector.
Who is responsible?
HIEP Secretariat
OUTCOME 2 | Outcome 2 Indicator 1 |  | Baseline | Dec-2013 (programme commenced Dec 2012) | 2014-12-01 | 2015-12-01 | 2016-12-01 | 2017-12-01 | Dec-2018 (target date) | Assumptions
Local, national and international humanitarian actors show changes in skills, behaviours, relationships, cultures and systems to promote the regular integration of evidence in the design, financing, planning and implementation of humanitarian response. | Number of DFID humanitarian business cases where the process of development and intervention strategy is informed by HIEP evidence products (with description). | Planned | 0 (2012) | Not assessed as too early in the programme's development. | Two examples of the design of DFID business cases influenced by HIEP evidence. | Three examples of the design of DFID business cases influenced by HIEP evidence (cumulative). | Five examples of the design of DFID programmes or business cases influenced by HIEP evidence (cumulative). | Seven examples of the design of DFID programmes or business cases influenced by HIEP evidence (cumulative). | At least eight examples of the design of DFID business cases influenced by HIEP evidence (cumulative). | The scale of adoption is inhibited or accelerated by contextual, local institutional, environmental, political and financial factors, most of which are beyond DFID's capacity to influence.
|  | Achieved |  |  | 2 achieved: 1. Business case extension for the Developing Operational Research Capacity in the Health Sectors (DORCHS), 2. DFID Afghanistan remote/third party monitoring business case has SAVE links | 3 cumulative achieved: at least 1 example in 2015, in Ethiopia humanitarian business case. Full review of all business cases was not possible in 2015 however.
HIEP Pillar and Business case
all
Source (i.e. HIEP project contributing to the indicator)
DFID Quality Assurance Unit feedback on design stage humanitarian business cases
Who is responsible?
HIEP Secretariat
| Outcome 2 Indicator 2 |  | Baseline | Dec-2013 (programme commenced Dec 2012) | 2014-12-01 | 2015-12-01 | 2016-12-01 | 2017-12-01 | Dec-2018 (target date) | Assumptions
| Number of DFID external humanitarian approach papers, policy papers, briefing papers and strategies informed by HIEP evidence (determined to some extent by citations). | Planned | 0 (2012) | Not assessed as too early in the programme's development. | One example of HIEP evidence informing external DFID policy and practice pieces. | Two examples of HIEP evidence informing external DFID policy and practice pieces (cumulative). | Three examples of HIEP evidence informing external DFID policy and practice pieces (cumulative). | Four examples of HIEP evidence informing external DFID policy and practice pieces (cumulative). | At least five examples of HIEP evidence informing external DFID policy and practice pieces (cumulative). | This is based on the assumption that DFID external papers, policies and strategies will have a ripple effect on other donors.
|  | Achieved |  |  | Approach paper to World Humanitarian Summit as part of WHS Innovation team | This was not formally assessed as part of the annual review in 2015. A number of projects fed into WHS submissions: protracted displacement, disaster risk financing and sovereign insurance, localisation, innovation and evidence.
HIEP Pillar and Business case
All
Source (i.e. HIEP project contributing to the indicator)
CHASE Humanitarian Policy Group -& Gov.uk online
Who is responsible?
HIEP Secretariat
| Outcome 2 Indicator 3 |  | Baseline | Dec-2013 (programme commenced Dec 2012) | 2014-12-01 | 2015-12-01 | 2016-12-01 | 2017-12-01 | Dec-2018 (target date)
| Number of examples where HIEP evidence products have contributed to the deliberation and decision-making of external humanitarian actors (e.g other donors, UN, multi-laterals, and operational agencies. | Planned | 0 (2012) | Not assessed as too early in the programme's development. | One example of HIEP evidence informing the policy and practice of other humanitarian actors. | Three examples of HIEP evidence informing the policy and practice of other humanitarian actors (cumulative). | Five examples of HIEP evidence informing the policy and practice of other humanitarian actors (cumulative). | Eight examples of HIEP evidence informing the policy and practice of other humanitarian actors (cumulative). | At least 10 examples of HIEP evidence informing the policy and practice of other humanitarian actors (cumulative).
|  | Achieved |  |  | Not assessed - too early | HIEP research is informing humanitarian response. Research used by R2HC used during the Ebola crisis, and HDX plaform hosting El Nino datasets. Several references to HIEP outputs during prep for WHS, including Strengthening the Humanitarian Ecosystem (PRF funded but resourced through HIEP).
HIEP Pillar and Business case
n/a
Source (i.e. HIEP project contributing to the indicator)
All projects, as appropriate
Who is responsible?
i) HIEP Secretariat; ii) HIEP Independent Evaluation Team
| Outcome 2 Indicator 4 |  | Baseline | Dec-2013 (programme commenced Dec 2012) | 2014-12-01 | 2015-12-01 | 2016-12-01 | 2017-12-01 | Dec-2018 (target date)
| Key individuals in humanitarian organisations reporting shifts within their organisations (with description). | Planned | 0 (2012) | Not assessed as too early in the programme's development. | Not assessed as too early in the programme's development. | Two individuals reporting shifts in their organisations | Four individuals reporting shifts in their organisations | Six individuals reporting shifts in their organisations | At least eight individuals reporting shifts in their organisations
|  | Achieved |  |  |  | not assessed in 2015
HIEP Pillar and Business case
all
Source (i.e. HIEP project contributing to the indicator)
i) Project-level Annual reports; ii) interviews with DFID MAR leads (UNICEF, UNHCR, WFP, OCHA, IFRC, GFDRR, ICRC, IOM, CERF UNISDR)
Who is responsible?
i) HIEP Secretariat; ii) HIEP Independent Evaluation Team
OUTCOME 3 | Outcome Indicator 1 |  | Baseline | Dec-2013 (programme commenced Dec 2012) | 2014-12-01 | 2015-12-01 | 2016-12-01 | 2017-12-01 | Dec-2018 (target date) | Assumptions
Local, national and international humanitarian actors invest in and support innovation that benefit people affected by humanitarian crises. | DFID contributes to the UN World Humanitarian Summit in 2015, resulting in a clearly articulated vision, priorities and objectives for humanitarian innovation, and ensures follow up action on recommendations. | Planned | 0 (2012) | DFID proactively engages in the agenda setting of the World Humanitarian Summit, supporting innovation as a key theme. | DFID engages deeply in the development of the innovation theme within the World Humanitarian Summit. | DFID is a key player in the World Humanitarian Summit and with others ensure appropriate and concrete recommendations to support innovation in the humanitarian sector. | DFID continues to play a key role in the follow-up actions from the World Humanitarian Summit, ensuring momentum is not lost. | DFID continues to play a key role in the follow-up actions from the World Humanitarian Summit, with tangible progress against recommendation made. | DFID continues to play a key role in the follow-up actions from the World Humanitarian Summit, with tangible progress against recommendation made. | Evidence is not enough. DFID needs to generate a broader context of interactions, spaces for debate, make visible initial responses from actors and broker relationships for humanitarian actors to choose to advocate for the use of HIEP-related evidence to be used in policy and practice. This will be different in different contexts.
|  | Achieved |  | DFID co-convened with OCHA policy group an innovation workshop in London which set the foundations for the World Humanitarian Summit. Also co-commission research with OCHA on "humanitarian innovation systems", to support the evidence base for the Summit. | DFID is closely engaged in the development of the innovation theme within the World Humanitarian Summit. | Several references to work completed by HIEP programmes and team during preparations for WHS. DFID part of innovation task team, developing the Global Alliance for Humanitarian Innovation. Several international meetings held and concrete recommendations in place for GAHI by end 2015.
HIEP Pillar and Business case
n/a
Source (i.e. HIEP project contributing to the indicator)
Subjective assessment of the World Humanitarian Summit's outcomes - records of meetings/action summaries, back to office reports.
Who is responsible?
HIEP Secretariat
| Outcome Indicator 2 |  | Baseline | Dec-2013 (programme commenced Dec 2012) | 2014-12-01 | 2015-12-01 | 2016-12-01 | 2017-12-01 | Dec-2018 (target date)
| Number of commitments, declarations of new initatives and changes in patterns of investments to pilot, test and scale humanitarian innovations. | Planned | 0 (2012) | Not assessed as too early in the programme's development. | One example of a new commitment to provide investment support to humanitarian innovations. | Two examples of new commitments to provide investment support to humanitarian innovations (cumulative). | Three examples of new commitments to provide investment support to humanitarian innovations (cumulative). | Four examples of new commitments to provide investment support to humanitarian innovations (cumulative). | At least examples of new commitments to provide investment support to humanitarian innovations (cumulative).
|  | Achieved |  |  | 1 | 1 additional (achieved) - HIF secured additional Dutch funding
n/a
Source (i.e. HIEP project contributing to the indicator)
Intelligence gathered by the HIEP Secretariat from their knowledge of the humanitarian community.
Who is responsible?
HIEP Secretariat
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | Dec-2013 (programme commenced Dec 2012) | 2014-12-01 | 2015-12-01 | 2016-12-01 | 2017-12-01 | Dec-2018 (target date) | Assumption
Research and evidence products are generated that are high quality and relevant to humanitarian policy-makers and practitioners. | Number and type of primary research papers available in open access format. | Planned | 0 (2012) | Designing, procurement and initiation of up to 15 HIEP research projects. | 5 | 8 additional | 10 additional | 11 additional | At least 40 evidence products in total. | A precondition to evidence being considered and used by policy-makers and practitioners is that it is high-quality, relevant and rigorous. The HIEP through it's design, through co-ownership between DFID policy, programming and research leads, selects highly relevant questions and commissions/manages rigorously designed and implemented research activities. Rigour and quality of published outputs is achieved through peer-review (by DFID or by suitably qualified external peer reviewers).
|  | Achieved |  | Achieved. | Number of reports: 16. Number of inception reports: 4 | Achieved. 26 in 2015. • IFRC final report • Protracted displacement final report • Pakistan final report - Scaling up Innovation in Disaster Risk Management in Pakistan, September 30 2015 • East Africa Mapping final report • R2HC – 4 papers (not including 4 x systematic reviews) • Sovereign Insurance – 13 papers to date • SAVE - 3 interim component reports • Urban ARK – Disaster Risk Reduction paper • Social Protection working paper (literature review due Jan 2016)
HIEP Pillar and Business case
Pillar 1 "analysing risk" (Business Case 1); Pillar 2 "what works & innovation"; Pillar 3 "institutional capacity" (Business Case 1);
Source (i.e. HIEP project contributing to the indicator)
All projects
Who is responsible for collecting data?
Project Lead Advisors and HIEP Secretariat
| Output Indicator 1.2 |  | Baseline | Dec-2013 (programme commenced Dec 2012) | 2014-12-01 | 2015-12-01 | 2016-12-01 | 2017-12-01 | Dec-2018 (target date)
| Number and topic of evaluations independently quality assured and available in open access format. | Planned | 0 (2012) | Designing, procurement and initiation of two HIEP evaluation projects. | Effective management of two HIEP evaluation projects, with both successfully completing inception phases. | One evaluation reports produced, independently quality assured and available in open access format. | Three additional evaluation reports produced, independently quality assured and available in open access format. | No additional results anticipated this year. | At least seven evaluation reports produced in total, independently quality assured and available in open access format.
|  | Achieved |  | Achieved. | Two HIEP evaluation projects have completed inception phases, plus an independent evaluation of the programme underway | Not achieved. • Thematic Resilience Evaluation underway, two draft reports produced but not published in 2015 • An independent evaluation of the HIEP programme is also underway (formative report counted in 2014) • Evaluation as part of Humanitarian Education Accelerator due to be contracted in 2016.
HIEP Pillar and Business case
Pillar 1 "analysing risk" (Business Case 1); Pillar 2 "what works & innovation"; Pillar 4 "research uptake" (Business Case 3)
Source (i.e. HIEP project contributing to the indicator)
Strengthening the Quality and use of Humanitarian Evaluation; Impact Appraisal for Sovereign Disaster Risk Finance and Insurance: towards better evaluation and evidence; Protection of civilians: building the evidence base on what works (ICRC - 'Roots of Behaviour' project)
Who is responsible for collecting data?
Project Lead Advisors and HIEP Secretariat
| Output Indicator 1.3 |  | Baseline | Dec-2013 (programme commenced Dec 2012) | 2014-12-01 | 2015-12-01 | 2016-12-01 | 2017-12-01 | Dec-2018 (target date)
| Number and topic of literature review research papers available in open access format (not including Systematic Review see indicator 4.2) | Planned | 0 (2012) | 5 | 2 | 2 | 7 | No additional results anticipated this year. | 16
|  | Achieved |  | 5 | 2014: 2 complete and open access, 3 more due to be complete by end of December 2014. 1 Completed from PRF funding (but resourced through HIEP) 2012/13: 2 completed, of which one funded by PRF but resourced through the HIEP. | 3 in 2015. • Refani Lit Review (Mar 2015) • Education in Emergencies Lit Review (Aug 2015) • SAVE updated literature review (component 2) Also: • HESC has 3 literature reviews underway (6 reviews total of which 3 systematic reviews and 3 less in depth evidence reviews).
HIEP Pillar and Business case
Pillar 1 "analysing risk" (Business Case 1); Pillar 2 "what works & innovation" (Business Case 2); Pillar 3 "institutional capacity" (Business Case 1); Pillar 4 "research uptake" (Business Case 3)
Source (i.e. HIEP project contributing to the indicator)
Responding to protracted displacement; Education in emergencies; Improving access to humanitarian evidence: research synthesis and communication for decision makers and practitioners; R2HC; Development of Technical Guides to Improve Humanitarian Practice; Protection of civilians; Improving the evidence base on how to work with national and local authorities for disaster risk management; Building the evidence base on risk to urban populations in developing countries; SAVE
Who is responsible for collecting data?
Project Lead Advisors and HIEP Secretariat
| Output Indicator 1.4 |  | Baseline | Dec-2013 (programme commenced Dec 2012) | 2014-12-01 | 2015-12-01 | 2016-12-01 | 2017-12-01 | Dec-2018 (target date)
| Number and topic of M&E toolkits available in open access format. | Planned | 0 (2012) | Designing, procurement and initiation of three HIEP project with objectives to develop M&E toolkits for practitioners. | Effective management of three HIEP projects with M&E components, with all successfully completing inception phases. | Effective ongoing management of three HIEP projects with M&E components. | One M&E toolkit complete for practitioners, published in an open access format. | Two additional M&E toolkits complete for practitioners, published in an open access format. | Three in M&E toolkit in total published in open access formate forhumanitarian practitioners.
|  | Achieved |  | Achieved. | Three HIEP projects being managed with M&E componenets, all completed inception phase and M&E frameworks being tested. | Achieved. IFRC, SAVE and Sovereign Insurance all underway - IFRC complete.
HIEP Pillar and Business case
Pillar 2 "what works & innovation" (Business Case 2); Pillar 3 "institutional capacity" (Business Case 1); Pillar 4 "research uptake" (Business Case 3)
Source (i.e. HIEP project contributing to the indicator)
SAVE; Improving the evidence base on how to work with national and local authorities for disaster risk management; Impact Appraisal for Sovereign Disaster Risk Finance and Insurance: towards better evaluation and evidence
Who is responsible for collecting data?
Project Lead Advisors and HIEP Secretariat
| Output Indicator 1.5 |  | Baseline | Dec-2013 (programme commenced Dec 2012) | 2014-12-01 | 2015-12-01 | 2016-12-01
| Number of catastrophic risk models produced in an open access format. | Planned | 0 (2012) | Design, approval and initiation of one HIEP project with objectives to develop risk models. Effective management of risk finance and insurance project, with successful completing of the inception phase. | Sovereign disaster risk finance and insurance project makes good progress in selecting countries for cat models and producing models. | Five country cat risk models available in open access format. | Five country risk models available in open access format
|  | Achieved |  | Achieved. | Good progress made on models. | Underway but Delayed. • Sovereign Disaster Risk Finance and Insurance project - on track to deliver, slight delay until spring 2016.
HIEP Pillar and Business case
Pillar 1 "analysing risk" (Business Case 1);
Source (i.e. HIEP project contributing to the indicator)
Impact Assessment of Sovereign Disaster Risk Finance and Insurance.
Who is responsible for collecting data?
Project Lead Advisors and HIEP Secretariat
| Output Indicator 1.6 |  | Baseline | Dec-2013 (programme commenced Dec 2012) | 2014-12-01 | 2015-12-01 | 2016-12-01 | 2017-12-01 | Dec-2018 (target date)
| Number of peer reviewed publications produced (i.e. journal articles and other types of externally peer reviewed publications), and percentage of peer reviewed publications which comply with our open access policy | Planned | 0 (2012) | Designing, procurement and initiation of up to 15 HIEP research projects. | 2 | 4 additional | 20 additional | 9 additional | At least 30 peer review journal articles in total.
|  | Achieved |  | Achieved. | 1 Peer reviewed publication, 2 guidance publications that have been through a moderated process. | 6 in 2015. • R2HC Humanitarian Health Evidence Review updated and 4 x systematic reviews • Disaster Risk and Its Reduction: an agenda for Urban Africa IDPR, 37(1) (Urban Risk: Feb 2015) • World Disasters Report (IFRC), 2 HIEP funded research based chapters, also helped IFRC develop the concept note.
HIEP Pillar and Business case
all
Source (i.e. HIEP project contributing to the indicator)
all
Who is responsible for collecting data?
Project Lead Advisors and HIEP Secretariat
| Output Indicator 1.7 |  | Baseline | Dec-2013 (programme commenced Dec 2012) | 2014-12-01 | 2015-12-01 | 2016-12-01 | 2017-12-01 | Dec-2018 (target date)
| Number of data sets made openly and freely available to external researchers | Planned | 0 (2012) | Design, procurement and initiation of three HIEP projects making datasets open access. | Effective management of the three HIEP projects producing datasets, with successful completing of the inception phases. | Effective management of the three HIEP projects producing datasets. | Increase in number of datasets available on HDX platform | Increase in number of datasets on HDX platform | Increase in number of datasets on HDX plaform
|  | Achieved |  | Achieved. | Two projects have completed inception phase, a further project has made good progress (no formal inception phase). One more project delayed due to protracted procurement period. The HDX Repository also launched. | • The HDX platform is now functional and operating with 172 datasets as of December. At the time of the PCR, it had received over 8,500 unique visitors.
HIEP Pillar and Business case
all
Source (i.e. HIEP project contributing to the indicator)
Improving the quality of data used in humanitarian decision-making; Scaling up innovation in Disaster Risk Management in Pakistan ; Building the evidence base on risk to urban populations in developing countries
Who is responsible for collecting data?
Project Lead Advisors and HIEP Secretariat
| Output Indicator 1.8 |  | Baseline | Dec-2013 (programme commenced Dec 2012) | 2014-12-01 | 2015-12-01 | 2016-12-01 | 2017-12-01 | Dec-2018 (target date)
| [New indicator October 2016] Number of projects conducting gender and social inclusion analysis | Planned | 0 (2012) | Baseline established | Not tracked | Not tracked | All projects undertake gender and social inclusion analysis at annual review stage. Where not conducted, recommend immediate action. List gender / social inclusion specific outputs. | All projects undertake gender and social inclusion analysis at annual review stage. List gender / social inclusion specific outputs | All projects continue to undertake gender and social inclusion analysis at annual review stage. List gender / social inclusion specific outputs
|  | Achieved |  | 30% of projects undertook some analysis - 20% scored 2; 10% scored 1 out of 3 point scale: 0 (no analysis) to 2 (analysis completed)
HIEP Pillar and Business case
All
Source (i.e. HIEP project contributing to the indicator)
All - inception reports, annual reports, quarterly meetings
Who is responsible for collecting data?
Project Lead Advisors and HIEP Secretariat
IMPACT WEIGHTING (%) | Output Indicator 1.9 |  | Baseline | Dec-2013 (programme commenced Dec 2012) | 2014-12-01 | 2015-12-01 | 2016-12-01 | 2017-12-01 | Dec-2018 (target date)
| Number and topic of DFID Technical Guidance documents for Humanitarian Advisors produced in open access format. | Planned | 0 (2012) | Commissioning and publishing of three evidence synthesis products to inform the development of guidance. | 2 | 2 additional | 1 additional | No additional results anticipated this year. | At least 5 guidance documents in total.
|  | Achieved |  | Achieved. | 3 technical guidance documents produced for Humanitarian Advisors and available internally | No further guides produced with HIEP involvement this year.
30 |  | HIEP Pillar and Business case
Pillar 2 "what works & innovation" (Business Case 2)
Source (i.e. HIEP project contributing to the indicator)
Shock-responsive social protection systems; Development of Technical Guides to Improve Humanitarian Practice; CaLP
|  | Who is responsible for collecting data? | [7 empty] | RISK RATING
|  | Project Lead Advisors and HIEP Secretariat | [7 empty] | Minor
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | Dec-2013 (programme commenced Dec 2012) | 2014-12-01 | 2015-12-01 | 2016-12-01 | 2017-12-01 | Dec-2018 (target date) | Assumptions
Cross-institutional relationships and partnerships are formed, so there is an active HIEP network influencing the uptake of research and evidence. | Number of HIEP projects with a proportionate and sufficiently resourced research uptake strategy linked to HIEP wide research uptake strategy | Planned | 0 (2012) |  |  |  | [New indicator in 2016] Conduct light touch review of project research uptake strategies by Dec 16 to establish baseline and suggest ways to strengthen project level strategies; Draft HIEP wide research uptake strategy and implementation plan | All HIEP projects implement proportionate and sufficiently resourced research uptake strategies linked to wider HIEP uptake and influencing strategy | All projects continue to implement research uptake strategies linked to HIEP strategy; Lessons learned in HIEP research uptake shared across the HIEP (and beyond). | (1) HIEP is attempting to influence sector-wide change by influencing DFID humanitarian policy and operational staff, multiple humanitarian stakeholders and potential users at international, national and local levels from the start of research process to enhance relevance and drive acceptance and uptake. (2) Influencing and uptake depends on actively engaged DFID HIEP individuals, guided by a prioritised HIEP influencing strategy, supported by incentives to use evidence, advocating for evidence-use with identified champions amongst DFID humanitarian advisors, counterparts within partner agencies and wider humanitarian networks
Achieved
HIEP Pillar and Business case
All Pillars and Business Cases
Source (i.e. HIEP project contributing to the indicator)
All live projects
Who is responsible for collecting data?
HIEP Secretariat
| Output Indicator 2.2 |  | Baseline | Dec-2013 (programme commenced Dec 2012) | 2014-12-01 | 2015-12-01 | 2016-12-01 | 2017-12-01 | Dec-2018 (target date)
| Number of HIEP projects with an established network of DFID advisors across departments [and external stakeholders] helping shape and inform humanitarian research and evidence (description and composition). | Planned | 0 (2012) | Design, commissioning and initiation of at least 15 HIEP projects. Intention to establish formal steering/advisory groups in at least 40% of HIEP projects. | At least 40% of HIEP projects establish steering/advisory groups with DFID advisors and external stakeholders. | Steering/advisory groups meet regularly at key project junctions, providing technical advice and guidance. 40% of HIEP projects with formal advisory/steering groups maintained. | Steering/advisory groups meet regularly at key project junctions, providing technical advice and guidance. 40% of HIEP projects with formal advisory/steering groups maintained. | Steering/advisory groups meet regularly at key project junctions, providing technical advice and guidance. 40% of HIEP projects with formal advisory/steering groups maintained. | Steering/advisory groups have a role in scrutinising the analysis of findings and research recommendations. 40% of HIEP projects with formal advisory/steering groups maintained.
|  | Achieved |  | Achieved. | Over 40% have advisory groups that include DfID advisors and external stakeholders. | Achieved. All live projects with steering/advisory groups, except MEI (but consortia with peer review element) and Digitization of Child Records (UNICEF) as this is a short six month project with close PM oversight.
HIEP Pillar and Business case
All Pillars and Business Cases
Source (i.e. HIEP project contributing to the indicator)
SAVE; Improving the evidence base on how to work with national and local authorities for disaster risk management; calp; Impact Appraisal for Sovereign Disaster Risk Finance and Insurance: towards better evaluation and evidence; 3ie; Strengthening the Quality and use of Humanitarian Evaluation; Moving Energy Initiative (MEI); EiE
Who is responsible for collecting data?
HIEP Secretariat
| Output Indicator 2.3 |  | Baseline | Dec-2013 (programme commenced Dec 2012) | 2014-12-01 | 2015-12-01 | 2016-12-01 | 2017-12-01 | Dec-2018 (target date)
| Number of new collaborations formed between DFID and institutional partners to co-design and commission humanitarian research and evidence. | Planned | 0 (2012) | 3 | 1 | no additional, relationships ongoing | no additional, relationships ongoing | no additional, relationships ongoing | At least 4 partnerships in total
|  | Achieved |  | Achieved. | Achieved 4: 1. Protracted displacement (WB and UNHCR), 2. Education in emergencies (INEE), 3. 3ie (USAID, WFP) 4. Humanitarian Innovation Ecosystems (Policy Development and Studies Branch, UN OCHA)& 3 in 2012/13: IFRC; Wellcome Trust; PRF | No new projects started in 2015.
HIEP Pillar and Business case
All Pillars and Business Cases
Source (i.e. HIEP project contributing to the indicator)
Responding to protracted displacement; Building the evidence base on risk to urban populations in developing countries; calp; Impact Appraisal for Sovereign Disaster Risk Finance and Insurance: towards better evaluation and evidence; Moving Energy Initiative (MEI); EiE
Who is responsible for collecting data?
HIEP Secretariat
IMPACT WEIGHTING (%) | Output Indicator 2.4 |  | Baseline | Dec-2013 (programme commenced Dec 2012) | 2014-12-01 | 2015-12-01 | 2016-12-01 | 2017-12-01 | Dec-2018 (target date)
| Amount of funds (or resource) leveraged for humanitarian innovation and evidence through DFID institutional partnerships. | Planned | 0 (2012) | Tangible commitments from a number of other humanitarian donors and research funders to co-fund HIEP projects. | At least £0.5m contributed from other donors/funders. | At least an additional £1m contributed from other donors/funders. | At least an additional £1.5m contributed from other donors/funders. | At least an additional £1.5m contributed from other donors/funders. | At least £5m in total contributed from other donors/funders.
|  | Achieved |  | Over £5m approved and committed from other donors/ funders (Wellcome, USAID, CIDA, SIDA, and ESRC). No funds actually contributed/spent to date. | Exceeded - Wellcome contribute over £0.5m to R2HC project in 14/15 | Achieved over £2m plus staffing/logistical resource. • HIF secured £1.8m from the Dutch government to provide additional accelerator services to grants • For Education in Emergencies, significant resources in kind from UN (UNHCR and UNICEF and country offices) on EiE Amplify, Accelerator, and the Platform. • 3ie - USAID, OCHA have provided funds leveraged by DFID. WFP provided $1.25m to fund evaluations of their nutrition interventions.
HIEP Pillar and Business case
20 |  | All Pillars and Business Cases
Source (i.e. HIEP project contributing to the indicator)
Building the evidence base on risk to urban populations in developing countries; 3ie; Improving the evidence base on how to work with national and local authorities for disaster risk management; R2HC; EiE
|  | Who is responsible for collecting data? | [7 empty] | RISK RATING
|  | HIEP Secretariat | [7 empty] | Moderate
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | Dec-2013 (programme commenced Dec 2012) | 2014-12-01 | 2015-12-01 | 2016-12-01 | 2017-12-01 | Dec-2018 (target date) | Assumptions
Capability to design, commission, manage, and apply humanitarian research strengthened through learning by doing amongst DFID staff, partner agencies and country based research communities. | Number and types of 'rigorous'/empirical research commissioned by DFID in CHASE, ARD and Policy Division. | Planned | 0 (2012) | CHASE, ARD and Policy Division leading on the design and commissioning of at least a third of the projects in the HIEP. | At least 30% of the HIEP portfoilo of projects are managed by advisors in CHASE, ARD and PD. | At least 30% of the HIEP portfoilo of projects continue to be managed by advisors in CHASE, ARD and PD. | At least 30% of the HIEP portfoilo of projects continue to be managed by advisors in CHASE, ARD and PD. | At least 30% of the HIEP portfoilo of projects continue to be managed by advisors in CHASE, ARD and PD. | At least 30% of the HIEP portfoilo of projects continue to be managed by advisors in CHASE, ARD and PD. | (1) HIEP is attempting to influence sector-wide change by influencing DFID humanitarian policy and operational staff, multiple humanitarian stakeholders and potential users at international, national and local levels from the start of research process to enhance relevance and drive acceptance and uptake. (2) Influencing and uptake depends on actively engaged DFID HIEP individuals, guided by a prioritised HIEP influencing strategy, supported by incentives to use evidence, advocating for evidence-use with identified champions amongst DFID humanitarian advisors, counterparts within partner agencies and wider humanitarian networks
|  | Achieved |  | Achieved. | 73% HIEP projects managed by advisors in CHASE, ARD and PD | Out of 18 live projects, 6 managed by other divisions except RED (c.40%). Some issues caused by turnover of staff and reprioritisation within CHASE.
HIEP Pillar and Business case
All Pillars and Business Cases
Source (i.e. HIEP project contributing to the indicator)
All HIEP Projects
Who is responsible for collecting data?
HIEP Secretariat
| Output Indicator 3.2 |  | Baseline | Dec-2013 (programme commenced Dec 2012) | 2014-12-01 | 2015-12-01 | 2016-12-01 | 2017-12-01 | Dec-2018 (target date)
| Number of partner institutions designing, commissioning or managing rigorous research for the first time. | Planned | 0 (2012) | At least four HIEP projects are designed and initiated with partners who have not commissioned rigorous research before. | At least four HIEP projects complete their inception phases with partners who have not commissioned rigorous research before. | At least four HIEP projects are ongoing with partners who have not commissioned rigorous research before. | At least four HIEP projects are ongoing with partners who have not commissioned rigorous research before. | At least four HIEP projects are ongoing with partners who have not commissioned rigorous research before. | At least four HIEP projects are concluded with partners who have not commissioned rigorous research before.
|  | Achieved |  | Achieved. | Four HIEP projects complete their inception phases with partners who have not commissioned rigorous research before. | Oxfam, IFRC, ELHRA, Hikam, Kenya • HESC partner Oxfam commissioned/managed Systematic Reviews for first time. • For IFRC capacity building project, first time they have managed research in this way. • SAVE – working with, amongst others, Hikam (Kenya), which is new to research. • R2HC - ELRHA have commissioned grants before (i.e. the HIF) but they have not managed research awards of the type they are managing currently.
HIEP Pillar and Business case
All Pillars and Business Cases
Source (i.e. HIEP project contributing to the indicator)
Improving access to humanitarian evidence: research synthesis and communication for decision makers and practitioners; r2h2; Scaling up innovation in Disaster Risk Management in Pakistan; Improving the evidence base on how to work with national and local authorities for disaster risk management
Who is responsible for collecting data?
HIEP Secretariat
| Output Indicator 3.3 |  | Baseline | Dec-2013 (programme commenced Dec 2012) | 2014-12-01 | 2015-12-01 | 2016-12-01 | 2017-12-01 | Dec-2018 (target date)
| Number of Southern academic institutions conducting HIEP research and innovation projects | Planned | 0 (2012) | Designing, procurement and initiation of up to 15 HIEP research projects, with the majority holding competitions open to Southern academic institutions. | 4 | 10 in addition | no additional expected (track for monitoring purposes) | no additional expected (track for monitoring purposes) | Target removed (Oct 2016), as not within remit of HIEP to dedicate sufficient resource to capacity building. Monitor on annual basis
|  | Achieved |  | Achieved. | 5, plus one ministry and one private company | Achieved – over 21 in 2015.
HIEP Pillar and Business case
IMPACT WEIGHTING (%) |  | All Pillars and Business Cases
10 |  | Source (i.e. HIEP project contributing to the indicator)
R2HC; HIF; Improving the evidence base on how to work with national and local authorities for disaster risk management; East Aftrica Mapping
|  | Who is responsible for collecting data? | [7 empty] | RISK RATING
|  | HIEP Secretariat | [7 empty] | Moderate
OUTPUT 4 | Output Indicator 4.1 |  | Baseline | Dec-2013 (programme commenced Dec 2012) | 2014-12-01 | 2015-12-01 | 2016-12-01 | 2017-12-01 | Dec-2018 (target date) | Assumptions
New and innovative research methods applied to humanitarian evidence generation, which demonstrates that rigorous research is both feasible and ethical in humanitarian contexts | Number and topic of impact evaluations conducted in humanitarian contexts. | Planned | 0 (2012) | Design, approval and initation of a project to develop a humanitarian impact evaluation window. | Scoping and consultation of the best approach and focus of a humanitarian impact evaluation window, and launch of the impact evaluation window. Up to 10 impact evaluations identified and initiated with partners. | Up to 8 impact evaluations ongoing. | Up to 10 impact evaluations underway. Lessons on applying impact evaluation methodologies in humanitarian settings captured. | Up to 10 impact evaluations underway. Learning on applying impact evaluation methodologies in humanitarian settings captured and shared | Up to 10 impact evaluations completed in total, with final reports. Learning on applying impact evaluation methodologies in humanitarian settings captured. | Concerns about feasibility and ethics of research in humanitarian contexts prevents investment in rigorous research
|  | Achieved |  | Achieved | Scoping and consultation of the best approach and focus of a humanitarian impact evaluation window is taking place, launch of the impact evaluation delayed. | Achieved - 8 to date. • 3ie - 8 impact evaluations so far contracted; DFID involved in the selection. 3ie is also disseminating lessons on conducting impact evaluations.
HIEP Pillar and Business case
Pillar 2 "What works & innovation"; Business Case 2.
Source (i.e. HIEP project contributing to the indicator)
3ie Humanitarian Impact Evaluation Window; REFANI; R2HC
Who is responsible for collecting data?
Project Lead Advisor and HIEP Secretariat
| Output Indicator 4.2 |  | Baseline | Dec-2013 (programme commenced Dec 2012) | 2014-12-01 | 2015-12-01 | 2016-12-01 | 2017-12-01 | Dec-2018 (target date)
| Number and type of humanitarian systematic reviews conducted on "what works" questions. | Planned | 0 (2012) | Design and commissioning of systematic review platform project. One systematic review completed. | Establishment of a systematic review platform project. Up to one additional systematic reviews completed. | Up to two additional systematic reviews completed. | Up to two additional systematic reviews completed. | Up to two additional systematic reviews completed. | Up to 8 systematic reviews in total.
|  | Achieved |  | Achieved. | Systematic review platform project established (HESC). | Achieved. • R2HC - 4 systematic reviews complete. Also: • HESC has 6 reviews underway of which 3 are in depth systematic reviews.
HIEP Pillar and Business case
Pillar 2 "What works & innovation" (Business Case 2); and Pillar 4 "evidence uptake" (Business Case 3).
Source (i.e. HIEP project contributing to the indicator)
HESC; R2HC; 3ie
Who is responsible for collecting data?
Project Lead Advisors and HIEP Secretariat
| Output Indicator 4.3 |  | Baseline | Dec-2013 (programme commenced Dec 2012) | 2014-12-01 | 2015-12-01 | 2016-12-01 | 2017-12-01 | Dec-2018 (target date)
| Number and type of guidance products on the methodological and ethical challenges of conducting research and evaluation in humanitarian crises. | Planned | 0 (2012) | Design, commissioning and initiation of three HIEP projects, which will produce guidance/learning on research methods in humanitarian contexts. Publication of guidance on ethics in humanitarian contexts (R2HC). | additional 1 (3ie) | additional 1 (urban). Up to three project outputs on research methods. | additional 1. | Additional 1. Research Methods lessons compiled and shared | Additional 1. Research Methods lessons compiled and shared
|  | Achieved |  |  | Six projects designed, commissioned and initated which will produce guidance/ learning on research methods in humanitarian contexts. Guidance on Ethica in humanitarian contexts published. | Achieved. • 3ie - Lessons learned have been synthesised in annual reports to DFID and a video on impact evaluations in emergencies uploaded to the internet • R2HC have published their Ethics Review. • HESC – three initial documents to share learning on evidence appraisal: - Synthesizing practices of evidence appraisal in the humanitarian field report. - Briefing Paper summarising key insights from the full-length report. - Catalogue of evidence appraisal schemes for those seeking to identify a relevant appraisal approach to their project.
HIEP Pillar and Business case
IMPACT WEIGHTING (%) |  | Pillar 2 "What works & innovation" (Business Case 2)
10 |  | Source (i.e. HIEP project contributing to the indicator)
3ie Humanitarian Impact Evaluation Window; Wellcome Trust Research for Health in Humanitarian Crises (R2HC); Building the evidence base on risk to urban populations in developing countries
|  | Who is responsible for collecting data? | [7 empty] | RISK RATING
|  | Project Lead Advisors and HIEP Secretariat | [7 empty] | Moderate
OUTPUT 5 | Output Indicator 5.1 |  | Baseline | Dec-2013 (programme commenced Dec 2012) | 2014-12-01 | 2015-12-01 | 2016-12-01 | 2017-12-01 | Dec-18 (target date) | Assumptions
Humanitarian innovations (products, processes and programmes) tested, piloted and scaled-up. | Number and type of humanitarian innovations (products and processes) tested and piloted. | Planned | 0 (2012) | Design, approval and initiation of a core innovation and WASH challenge funds. | 14 small grants awarded through the small grant facility for testing (2014); and 16 grants awarded through the large grant facility for piloting (cululative); 3 WASH (cumulative) | Minimum of 16 large grant projects allocated funding by end 2015 of which at least one is led by a southern actor; minimum of 39 small grants allocated funding by end 2013 of which at least 4 are lead by southern actors; minimum of 3 WASH solutions ready for further scale-up | Year on year increase in number of grants (large and small). Increasing proportion led by southern actors | Year on year increase in number of grants (large and small). Increasing proportion led by southern actors. Increase in thematic windows | 50 innovations (products and processes) tested and piloted in humanitarian settings | Open sources of funding are a key barrier in the piloting, testing and scaling-up of innovation projects. Innovation projects by their nature are risky in terms of delivering planned for results. Therefore, only a small number of innovations will progress through the innovation cycle and be appropriate for scaling-up.
|  | Achieved |  | Achieved. | 11 small grants awarded (2014); 29 large grants awarded (cumulative); 5 WASH grants awarded | Partially achieved – large grants and WASH targets achieved, small grants target not quite met, but Southern actors target met (1 large, 4 small).
HIEP Pillar and Business case
Pillar 2 "What works & innovation"; Business Case 2
Source (i.e. HIEP project contributing to the indicator)
Humanitarian Innovation Fund (Core & WASH); Moving Energy Initiative phase 2 (when agreed); Education in emergenices, phases 1 and 2, Amplify and Accelerator; R2HC
Who is responsible for collecting data?
Project Lead Advisors and HIEP Secretariat
| Output Indicator 5.2 |  | Baseline | Dec-2013 (programme commenced Dec 2012) | 2014-12-01 | 2015-12-01
| Number and type of HIEP-supported humanitarian innovations (products and processes) scaled-up | Planned | 0 (2012) | Design, approval and initiation of a core innovation and WASH challenge funds. | At least one innovation taken to scale (adopted by more than five humanitarian organisations or reach more than 1,000,000 people) post HIF funding (cumulative) | At least 3 innovations scaled (cumulative) | 1 additional innovation scaled (4 cumulative). Wider scaling initiatives initiated | 1 additional innovation scaled (5 cumulative). Gap mapping/ future priorities feeds into innovation work | Target 10:1 innovations funded are scaled
|  | Achieved |  | Achieved | 2 - Ebola crisis in Sierra Leone | Achieved - 3 to date (1 in 2015). • R2HC - 3 innovations from ebola crisis taken to scale: the anthropology platform, the LSHTM epidemiology and the behaviour change messages. • HIF – 3 projects reached scaled to date: o WFP 'mobile Vulnerability Analysis and Mapping’ project scaled with help from Dutch and NGOs. o IFRC Beneficiary Communications in Haiti o OCHA Humanitarian Exchange Language (HXL). Also: • HIF has 3-4 further innovations which are close to achieving the HIF’s multiagency target, part of the definition of scale, in 2016. • In addition, new HIEP project on Digitization of Child Records aims to scale up HIF-generated UNICEF ‘FTR’ innovation
IMPACT WEIGHTING (%) |  | HIEP Pillar and Business case
Pillar 2 "What works & innovation"; Business Case 2
Source (i.e. HIEP project contributing to the indicator)
30 |  | Humanitarian Innovation Fund (Core & WASH); Education in Emergencies, phase 2 Accelerator; R2HC; Moving Energy Initiative (MEI)
|  | Who is responsible for collecting data? | [7 empty] | RISK RATING
|  | Project Lead Advisor and HIEP Secretariat | [7 empty] | Major