Business Case

Summary Sheet

Title: Transport Impact Evaluations with eight Multilateral Development Banks (ieConnect)
Project Purpose: / Generate a substantial new evidence base on transport policy and investments, including evidence about induced benefits, with a focus on urban mobility, transport corridors and road safety.
Programme Value: £7.5m		Country/ Region: Global
Project Code: / 204931	Start Date: 2016	End Date: 2021
Overall programme risk rating:	Moderate
Quest Number:

Intervention Summary

What support will the UK provide?
DFID will provide £7.5 million over five years from 2016 for Impact Evaluations of large transport projects across eight major Multilateral Development Banks[1]. The eight MDBs approve about $20billion in transport investments annually.
[1] These are the African Development Bank; Asian Development Bank; CAF-Development Bank of Latin America; European Bank for Reconstruction and Development; European Investment Bank; Inter-American Development Bank; Islamic Development Bank; and World Bank.

The Impact Evaluations to be funded under this project (ieConnect) will focus on three sub-themes of relevance to economic development:

1. Urban Mobility
2. Transport Corridors
3. Road Safety

The two cross cutting themes are fragile, conflict affected states and female economic empowerment.

DFID will support the new transport window within the Development Impact Evaluation initiative (DIME) which is housed within the World Bank[2]. DFID already supports DIME which aims to reduce poverty and scale up development results by improving the availability of impact evaluation evidence and its use. All transport programmes that are evaluated within ieConnect will be co-financed by at least two MDBs and / or other development partners. 100% of DFID funds will finance impact evaluations in low and lower middle income countries. At least 60% of funds will be spent in DFID focus countries.
[2] DIME is a cross-sectoral programme managed by the Development Impact Evaluation unit (DECIE) in the World Bank Research Department. Throughout this document, DIME is used to represent the institutional arrangement for impact evaluation within the bank as well as the administrative unit.

DIME is a very successful project and we chose to use it as the mechanism for this project (ieConnect) for value for money (VfM) reasons. DIME is one of DFID’s leading suppliers of impact evaluations. DIME has a portfolio of 135 ongoing or completed impact evaluations, covering most major development sectors, and scored A+ in recent Annual Reviews.[3] It would be slower and more costly to set up a duplicate of the DIME apparatus, and would not be likely to achieve the same level of access to either projects or policy makers.
[3] DFID Annual Review for “Impact Evaluation Support Facility”, March 2016 http://iati.dfid.gov.uk/iati_documents/5360680.odt

DFID funds DIME via a multi-donor trust fund called i2i. The current DFID overall share of i2i is 31%. A new contribution in transport (ieConnect) will increase the share to 40% for i2i overall. In the ieConnect transport window specifically the DFID share would be 60% initially. However, it is anticipated that DFID’s cost share will decline as the transport window becomes established, shows its worth and continues to attract contributions from other funders. The World Bank have committed to reduce this ieConnect burden share to 40% within the next two years.

What are the main programme activities?
ieConnect will undertake impact evaluations on large transport projects across eight multilateral development banks (MDBs) and facilitate learning from the findings of evaluations. More than 20% of the ieConnect DFID budget will fund impact evaluations for non-World Bank financed transport programmes which will develop impact evaluation expertise and knowledge in other MDBs and development partners. In a significant advance on existing studies, ieConnect will evaluate the broader impacts of the transport programmes including trade patterns, job creation, urban shape and female economic empowerment (FEE). This is ambitious and innovative.

ieConnect aims to achieve significant impact by improving the selection, design, and implementation of transport infrastructure projects in DFID focus countries and beyond. Potentially this could include re-prioritizing transport investments to connect remote areas to the global economy, create new trade corridors, ensure women and children are empowered and to permit the development of bigger, denser, more productive and cleaner cities.

DFID will provide funding and guidance to ieConnect to:

Technical knowledge. Provide expert technical support to programme teams (including DFID teams) to use impact evaluation in transport programmes;
- Build the capacity for evidence-based decision-making on transport investments within governments, MDBs and donors; and
- Knowledge management. Build on existing DIME knowledge platforms and institutional structures to share transport findings.

Why is UK support required?
Road and rail networks are one of the largest assets and liabilities for national governments in low and middle income countries. US$16.2 billion per annum is invested in transport infrastructure in sub-Saharan Africa alone. The transport sector is the largest sector lend in the World Bank, Asian Development Bank and African Development Bank. The profile of the sector is changing, an example of this is that the World Bank has committed to increase its urban transport portfolio from 15% to 30% by 2020. However, the evidence base in terms of impact evaluation is poor; only 0.4% of all Impact Evaluations since 2000 have been applied to transport projects.[4]
[4] Cameron, Drew B.; Mishra, Anjini; and Brown, Annette N. “The growth of impact evaluation for international development: how much have we learned?” Journal of Development Effectiveness Vol. 8, No. 1

More than 1 billion people globally do not have access to transport. Where populations are dense, the problems are different and there can be a reliance on cars that leads to congestion and pollution. Transport accounts for about 20% of world CO2 emissions, around 60% of global oil consumption, and around 27% of all energy use.[1] Road crashes now kill more people each year than HIV, tuberculosis, or malaria[5]. Road crashes are the biggest killer of youth (15-29year olds) globally.
[1] International Energy Agency, 2013 Key World Energy Statistics, page 33, http://www.iea.org/publications/freepublications/publication/KeyWorld2013_FINAL_WEB.pdf Annex 6: RISKS APPRAISAL Project-specific risks appropriate to ieConnect Risks for the main i2i project funded by DFID are set out in the detailed risks appraisal in the original Business Case produced by Evaluation Department. These are monitored at least annually and the risks appraisal updated in the Department’s delivery plan for i2i. Those risks apply generally to the ieConnect project. Specific risks relating to DFID funding of ieConnect will be monitored in addition to those applying generally to the ieConnect project. These are set out in the table below. The Growth Research Team will be responsible for monitoring these risks, and escalating any major issues to be resolved through the i2i governance mechanisms. The probability/impact scales used are: Probability	Impact Almost certain	Severe Likely	Major Possible	Moderate Unlikely	Minor Rare Overall risks for the ieConnect project, including risks that apply to the main i2i project, are judged to be Moderate. Table 1: ieConnect-specific risks (in addition to the i2i main project risks) RISKS CATEGORY AND RISKS	PROBABILITY	IMPACT (before mitigating)	MITIGATING MEASURES Delivery risks ieConnect is unable to secure additional funding from other donors.	Unlikely	Major	Currently, 69% of DIME funding is from other donors. A similar leverage is expected on DFID funding of ieConnect. ieConnect is not responsive to DFID’s geographical or topic focus.	Unlikely	Moderate	The Logframe includes numbers and / or % of IEs and spend in focus areas (LIC, FCAS, urban mobility, transport corridors, road safety, FEE). These will be reviewed annually. Research uptake risks: findings from impact evaluations do not feed through into decision making and design of transport projects.	Possible	Severe	This area will be closely monitored by DFID and DIME during implementation. While, ultimately, there is no guarantee with any research that it will lead to impact, measures in place to ensure a high degree of policy and operational relevance are: close working by the project with: (i) a cross-World Bank Council composed of Chief Economists and directors from operational vice presidencies that provide strategic guidance; (ii ) working groups in each global practice to set learning priorities and select cases; and (iii) with operational teams to shape project design and ensure experiments guide project implementation toward greater effectiveness. DIME engages clients from the beginning, to set research questions and agree on entry points to affect policy decisions using experimental results. Intellectual/Innovation risks The programme of works is too ambitious and therefore leads to inconclusive results.	Possible	Major	The programme is pushing new frontiers on transport with only 0.4% of modern IEs undertaken in the transport sector. Data is limited and RCTs are relatively new for transport. Conclusivity of results should be higher with planned use of clusters of IEs in up to 11 sites. This will require close monitoring by DFID and DIME during implementation Rigorous approaches to transport impact evaluation are not identified.	Unlikely	Major	It is original and challenging to assess the spatial and induced impacts of transport infrastructure in cities and corridors using impact assessment techniques. This would be a risk for all of the options considered. Impact evaluations not of sufficient quality.	Unlikely	Major	DIME has in place a blind quality assurance process to ensure all evaluations uphold the highest technical standards. Table 2: current DFID i2i risks appraisal (extract) Risk Description	Probability	Impact	Mitigation Delivery / Output Impact evaluations are not approved on time	Low	High	DIME and DFID are actively managing the pipeline of impact evaluations to ensure targets are met on time. To mitigate potential delays EVD will facilitate quarterly updates with those DFID offices engaged with DIME IEs. Differences between DFID and World Bank policies present a reputational risk for the funder when DIME engages with partners and clients, through workshops, events and impact evaluations, etc.	medium	Low	DIME has committed to ensuring it is acting within the boundaries of the administrative agreement and World Bank policies, and protecting DFID's reputation in the process of implementing the agreement. DFID will monitor feedback from staff and partners to ensure any reputational risks are dealt with appropriately. DIME does not uphold the UK Gender Act in a manner appropriate with DFID policies.	medium	medium	DFID will monitor the inclusion of gender focused evaluation activities across the DIME portfolio and ensure that where appropriate that gender be included as an explicit focus of any evaluation activity. DFID will also require that its own programme evaluations explicitly recognise gender dimensions where appropriate. Intellectual Impact evaluation are not sufficient quality	Low	High	DIME has put in place a rigorous vetting process to ensure that each concept note and approved impact evaluation meets technical quality. DFID will monitor the quality of concept notes, inception reports and final product for all DFID-funded evaluations. Financial Project unable to secure continued funding from other donors	Medium	High	DFID agreed to fund i2i as a multi-donor trust fund. DIME is actively seeking additional donors to join the initiative. DFID is supporting the recruitment of additional funders by participating in meetings and answering questions. DFID is looking at extending funding for transport and ICT. Funding is not effectively managed: some of the World Bank trust fund protocols are not aligned with IE project cycles and DIME is therefore managing a parallel accounting system.	Low	Medium	DIME has put in place financial management practices the conform to World Bank. DFID mitigates this risk by comparing DIME and World Bank central reporting on a regular basis. Funding is provided in advance of need	Low	Medium	DFID has agreed to fund DIME according to the forecast of 5 years of IE activities. Funding for maintaining the agreed impact evaluation programme needs to be provided to DIME on a regular basis in line with World Bank policies around approving work after funds are available. To ensure that DIME is receiving funding in advance when needed, and not in advance of need, DFID is requesting regular account updates and forecasts DFID funding from DFID spending units is not aligned with agreed EVD payments to DIME	Low	Medium	Individual DFID impact evaluations are funded by the spending units who manage the programmes subject to evaluation. EVD works with DFID spending units to ensure the quality of IE design and coordinates with DIME researchers to agree a work-plan and budget. For those IEs included under the originally umbrella fund the risk of making payments on time lies with EVD, and regular budget transfers will need to be made from DFID spending units. To mitigate this risk EVD has requested spending units to agree a budget with DIME and EVD before the approval of an IE, and then consolidates the total payments on an annual basis. Management DFID internal management is not coordinated and this causes confusion and delays in achieving DIME outputs	High	Medium	DIME is conducting impact evaluations of DFID programmes that are managed by spending units at country and HQ offices. EVD will mitigate the management risk this represents for DIME by establishing an internal working group with representatives from each DFID team with an impact evaluation. Political / Security Security issues in partner countries limit implementation	Medium	High	DIME works in many countries where impact evaluations can be delayed due to context. To mitigate this risk EVD will maintain regular communications with DFID and DIME impact evaluation teams. Ethics DIME impact evaluations are implemented without due consideration for ethics	Low	Low	DIME will monitor the impact evaluation selection, quality assurance and management processes to ensure they uphold ethics standards. EVD will review the extent to which ethics are upheldby the processes used on a annual basis.
[5] World Bank and University of Washington (2014). Transport for Health – The Global Burden of Disease from Motorized Road Transport. Available at: http://documents.worldbank.org/curated/en/2014/01/19308007/transport-health-global-burden-disease-motorized-road-transport

The three transport sub-themes of ieConnect are core to DFID’s Economic Development agenda. Two of the three (urban and transport corridors) are key to DFID’s Climate Change agenda. They are relatively new areas of transport work within the MDBs and impact evaluations would be timely. 75% DFID Inclusive Country Diagnostics cited transport in their top three constraints on growth.

DFID support through ieConnect would use large transport investment projects as an opportunity to study the wider economic and social effects of urban and corridor transport projects. This is not an established research field and receives little research funding. DFID has been a world leader in transport research for the past 30 years. Transport research funding with relevance to LICs is minimal outside DFID funding. Transport research is noted as a comparative advantage in both the DFID Economic Development Strategy and the Infrastructure Policy Paper.

The first round of applications in 2015 to the existing ieConnect $2m transport window generated interest from 31 projects with a total investment value US$18.5 billion. The research costs in relation to investment is less than 1%. With existing funds DIME could support 6 transport impact evaluations. With DFID funding of ieConnect a total of 22 to 32 transport impact evaluations will be supported. At the outset DFID’s burden share is 60% for ieConnect and 31% for DIME overall, the support to ieConnect increases DFID’s burden share to 40% overall for DIME.  In outer years the annual contributions from DFID reduce and it’s hoped that additional contributions will be mobilised – some of these are already fairly firm such as $0.5m from IADB to evaluate a metro project, to date DIME have commitments of $8m in co-financing for ieConnect (see page 23 in Financial Case for summary). The World Bank have committed to reduce DFID burden share on ieConnect to 40% within two years of project start date.

ieConnect directly responds to the approved DFID Research Review. RED is seeking to fund research which is relevant to DFID and our partners, is feasible, and is not being funded by others. DFID’s EcDev directorate is supportive of this research and we will explore the relevance to CDC as their portfolio becomes clearer. This research meets these criteria and complements other cutting edge DFID research funding on rural roads, road safety and engineering aspects of urban and transport corridors.

A detailed World Bank proposal for ieConnect is available on Quest at 5508276

Strategic Case

A. Context and Need for Support

Progress has been made towards reducing global poverty over the last 20 years. However, significant challenges remain with over 1 billion people still in extreme poverty[6] and wide variations in the rate of poverty reduction. Sub-Saharan Africa and Western Asia, key focus areas for DFID, are the regions that made the least progress against the Millennium Development Goals. The Sustainable Development Goals (SDGs) now challenge us to leave no-one behind.
[6] World Bank Poverty Reduction and Equity Website.

Economic development is key to eradicating poverty, and accelerating progress is essential if the goal of zero extreme poverty by 2030 is to be achieved.[7]
[7] Department for International Development, “Economic Development for Shared Prosperity and Poverty Reduction: A Strategic Framework” https://www.gov.uk/government/uploads/system/uploads/attachment_data/file/276859/Econ-development-strategic-framework_.pdf

Cities are central to the process of economic development, accounting for 80% of global economic activity[8], and with higher levels of development consistently correlated with greater concentration of production and population in cities.[9] Sustained economic development requires creating cities that work, supporting increases in productivity, allowing trade-competitive production and stimulating investment and job creation. Long distance transport networks can alter spatial development on an even larger scale, and can be crucial enablers of international trade. Improved transport systems should be instrumental in meeting these challenges, urban transport may be the single greatest factor in creating cities that are unified, highly productive hubs rather than choked by congestion.
[8] World Bank Group “Harnessing urbanisation to end poverty and boost prosperity in Africa: an action for transformation” Africa region sustainable development series. September 2013.
[9] Glaeser, Edward; and Joshi-Ghani, Abha “The Urban Imperative: Toward Shared Prosperity” World Bank Policy Research Working Paper 6875, May 2014.

Between 2010 and 2040, Africa’s urban population is expected to grow by 450 million[10], and business-as-usual is likely to mean that urban growth is crowded, congested, and with costs that undermine international competitiveness. Strategic transport investments now, whilst much of the infrastructure that will influence how African cities develop is yet to be built, can change this trajectory and support the development of productive, competitive cities. There is, therefore, a crucial opportunity to act now to better inform decisions on investments that will determine the shape of cities for decades.
[10] Moretti, Enrico “Cities and Growth: IGC Evidence Paper”, April 2014.

All the net increase in global population up to 2050 being in urban areas should be an opportunity for massive gains in labor productivity, productive efficiency, environmental efficiency and human welfare. The greatest gains will be achieved where cities can reach a greater size and density so as to maximize agglomeration benefits (clusters, labor pooling, and knowledge spillovers). Urban transport is potentially a major constraint on size and density. Making an assessment of urban transport’s contribution to the growth of integrated, high density, highly productive, greener safer cities is a major driver for undertaking this programme of evaluations.

Global urbanization will require massive investments in improved public transport, urban planning, and car ownership and use. Getting urban transport systems right will be critical to address growing mobility needs, but also avoid the lock-in into unsustainable development patterns in the future. Public transit, for example, could reduce congestion, pollution and CO2 emissions. However, public transport continues to be generally far too expensive for the poorest 20 percent of people in developing country cities. Affordability is key to access, and in cities like Nairobi, and Dar es Salaam, urban transport is beyond the reach of the 20% at the bottom of the income pyramid.

High-density corridors, such as highways and national roads, freight and passenger railway links, inland waterways and even airport infrastructure constitute the backbone of a country’s transport network. Optimizing the transport network by looking at spatial planning and multimodality can support more efficient supply chains, reduce on-road freight transport costs, and facilitate trade, specialization and the migration of people and productive capital for new levels of productivity and regional and global integration.

Across both the urban space and transport corridors, road safety is key area that has been largely unexplored by impact evaluation research work in LICs / LMICs. Worldwide, road traffic crashes kill more than 1.3 million people every year and severely injure another 50 million or more. 92 percent of the annual deaths are in developing countries and half are among motorcyclists, pedestrians and cyclists. In Africa, sidewalks are missing from around 65 percent of the road network, resulting in pedestrians and motorized vehicles sharing the same space and creating unsafe urban transport. Road Safety evaluations are crucial to better understand how we can reduce the deaths and injuries associated with improved transport networks and increased motorisation. Globally road fatalities are the biggest killer of youth (15-29 year olds). The SDG target 3.6 on Road Safety is an indication of the global importance of the issue.

Yet, in practical terms, little is understood about how to make transport investments meet economic development goals. Specifically, the evidence base informing transport infrastructure investment decisions is out of date, generally focussing on changes in traffic volumes and travel times, stopping well short of consideration of the impacts that matter the most, such as improvements in labour market functioning, or access to markets.

Improving outcomes is not necessarily a matter of allocating more resources to transport construction projects- transport is consistently one of the largest sectors in aid, one of the top three investment sectors in almost every low income country budget, and the top sector lend for all multilateral development banks (MDBs).[11] Rather, it requires investment in improving understanding of how to prioritise, design, and implement projects so that they can meet the more important, but harder-to-measure broader objectives of economic and social development.
[11] The eight MDBs invest approximately US$20 billion per year in transport projects’ MDB Working Group on Sustainable Transport

Specifically, it would require addressing four challenges:

Lack of standard approaches for estimating the spatial development impacts of transport investment decisions. There is low stock of knowledge globally and limited capacity to apply it in actual planning processes.

Lack of clear evidence on how transport policy and investment choices impact on the spatial development of cities, and can facilitate uncongested expansion. There is a shortage of evidence on the broader economic development impacts of competing investments in urban transport programme areas. Transport infrastructure is durable and likely to determine the spatial development of cities for decades, this will have important consequences for productivity and competitiveness.

Lack of clear evidence on how long distance transport connections stimulate trade, spatial organisation, and the migration of people and production. Long distance transport will influence spatial development on an even larger scale, and as such will be a key factor in determining low-income countries’ potential to become competitive in the production of tradable goods.

Lack of clear evidence on how road fatalities and injuries can be reduced, the socio-political barriers and opportunities and the real GDP costs of road safety.

B. Why DFID should Provide Support

At the strategic level, improving the effectiveness of resources invested in transport infrastructure to support economic development in low income countries is clearly in line with the objective of promoting global prosperity set out in the UK ODA Strategy.[12] Moreover, the investment would help to implement DFID’s economic development strategic framework, specifically commitments to scale up efforts to monitor and evaluate the impact of our work on economic development, strengthen our knowledge base by commissioning new research on the tools we use to bring about economic development, and deepening knowledge through research and evaluation on what works and how to operate in fragile states.[13],[14]
[12] HM Treasury, Department for International Development “UK aid: Tackling global challenges in the national interest”, November 2015
[13] Department for International Development “Economic development for shared prosperity and poverty reduction: a strategic framework”
[14] It is expected that 50% of programme resources would be targeted at fragile and conflict-affected states.

Improving our understanding of the impact of large-scale transport investments will help DFID meet its commitment to make “British aid more effective by improving transparency and value for money”, and to discontinue “support [for] projects that are failing to perform” so that this money can “be redirected to programmes that are better placed to combat poverty”[15].
[15] DFID Business Plan 2011-2015

Compared to the MDBs, DFID’s direct bilateral investment in transport infrastructure is relatively small. However, of the 22 DFID Country Inclusive Growth Diagnostics undertaken in 2015, 17 identified transport as a binding constraint to faster, more inclusive growth. Multi-laterally DFID invests substantial resources in transport through core funding of MDBs and the EC. Tranport is the largest sector lend in all MDBs. Investing in research to address the challenges listed above would inform decisions on urbanisation and economic strategy, with implications far beyond a narrow focus on transport itself.

Investing in addressing the identified research gaps is likely to be highly additional. Transport represents about a third of MDBs lending, but accounts for only 0.4% of all impact evaluations since 2000[16] . In transport evaluation, the baseline is close to zero: the empirical literature has only a handful of cases of methodologically sound, full-fledged impact evaluations, which mainly address rural roads. However, an increasing portion of the operational portfolio of MDBs supports multi-faceted development challenges, such as high-density, multi-modal trade corridors, and urban mobility. In these operational areas, it is urgent to better understand the economics of project interventions, and their linkages with markets, trade, emissions and safety, and shape the investments, to ensure that they realize their full potential in terms of poverty reduction and sustainable growth.
[16] All impact evaluations since 2000; Cameron, Drew B.; Mishra, Anjini; and Brown, Annette N. “The growth of impact evaluation for international development: how much have we learned?” Journal of Development Effectiveness Vol. 8, No. 1

There is strong reason to believe that DFID can successfully commission and manage this ambitous research programme. DFID is a world leader on transport research. This was identified in the recent DFID Infrastructure Position Paper as a comparative advantage. We already support a rural roads research project, a road safety research project, and are procuring an engineering-oriented high volume transport research programme. Additional research on the specific impact and results of transport sector investments would complement Research and Evidence Division’s transport sector research portfolio.

There are no other significant funders of transport research that has direct relevance to LICs, fragile states and LMICs. The Growth Research Team in the Research and Evidence Division are involved with the MDB Working Group for Sustainable Transport and have hosted them twice in the last 18 months. The group consists of the transport directors for the eight major MDBs, who approve approximately $20 billion transport investments annually. The MDBs all prioritise impact evaluation and the ieConnect would work across the MDBs with more than 20% budget to non-World Bank impact evaluations.

By providing funding for transport impact evaluations, demonstrating that rigorous evaluation of the broader economic development impacts of investments is possible, DFID is likely to be able to crowd in additional investment by others. It is possible for DFID to take the lead because of the capacity and successful track record that it has built up in leading research on development in general, and on impact evaluation in particular. DFID has considerable influence on the evaluation market not only through its funding of the evaluation services it commissions, but also as a global leader in evaluation partnerships and as a promoter of evaluation capacity development.[17]
[17] UK Evaluation Society “Improving DFID’s contribution to evaluation market development: UKES response to DFID consultation” September 2015

C. How the Programme would address the Development Need

The proposed programme would fund a series of ambitious, rigorous impact evaluations on transport projects to better understand results achieved and inform future decisions, and then disseminate findings to key decision makers in governments and development agencies. Through this, the programme would generate evidence about how transport can alter spatial development in and between cities, this could ultimately lead to more informed use of resources and faster progress on economic development and poverty reduction.

There have been very few rigorous evaluations of transport projects that consider broader benefits related to economic development outcomes. This reflects specific challenges in using controlled experiments to assess this type of impact; the impacts of most interest take many years if not decades to unfold – the mass migration of people and production enabled by the development of a city or trade route. Furthermore, impact evaluations take longer than typical research experiments but capture far more real world information. The proposed programme would therefore push research into a new area, and so comes with attendant risks. The ability of competing programme options to manage this research risk is explicitly addressed in the Appraisal Case.

ieConnect is an ambitious programme with transformational potential if the global transport sector shifts to increased use of impact evaluations that focus on broader economic development impacts such as job creation, female economic empowerment and urban form.

Undertaking broader impact evaluation in transport is difficult and innovative. It requires the combination of innovation in the data strategy and innovation in methods. Innovation in data means developing empirically validated measurement frameworks across a great variety of outcome spaces (e.g. job creation, FEE, urban form), with cost-efficient data collection strategies that combine advancements in technology-led data collection (such as satellite imagery and mobile phone data) with the use of more traditional administrative and survey data to construct the data systems needed. Innovation in methods includes developing substantially more robust non-experimental methods than those currently used in the transport literature, and overlaying experimental approaches to understand: (i) complementarities with other policies and interventions, and (ii) specific parameter and causal mechanisms by which the project is theorised to produce benefits. Together, innovations in data and methods will enable ieConnect to estimate impacts across multiple outcome spaces such as land use and migration, jobs, economic output and trade, emissions and female economic empowerment.

A unique contribution of this programme is the cross-sector research agenda to capture the welfare gains at individual, household and market levels. The investment in data and analytical framing will be substantial. Overall, it is innovative to employ impact evaluation techniques to measure all these effects, and thus there will be a need for flexibility and innovation in methods.

Impact evaluation provides a rigorous way of attributing impact to a programme by comparing what happened to what would have happened had the programme not taken place. This counterfactual based evaluation approach has been significantly developed over the last ten years in other sectors, however transport has been slow to embrace impact evaluations in part due to the difficulties detailed above on data and methodology. Impact evaluation is able to credibly establish causal links between programmes and impact with more certainty than other evaluation approaches[18]. Impact evaluation therefore enables policy makers to make better-informed programme and policy changes, including:
[18] Independent Evaluation Group (2012), “World Bank Group Impact Evaluations: Relevance and Effectiveness.

- Scaling up an intervention to deliver further results across a larger population;
- Making adjustments to an existing programme to improve its delivery of results; and
- Discontinuing a programme proven to be ineffective.

There is growing demand for impact evaluation evidence in other sectors, showing that this type of evidence resonates with decision makers, in particular amongst governments and donors[19]. Mexico made impact evaluations mandatory for a variety of social programmes in 2001[20]. In 2009, the Government of Ghana established a Policy Evaluation and Oversight Unit (PEOU) to monitor and evaluate policy implementation across Ministries[21]. In Rwanda, their Economic Development and Poverty Reduction Strategy 2 (EDPRS 2: 2013-2018) includes ambitious sector policy evaluation plans[22]. Through ieConnect DFID will encourage the global transport sector to build on the gains in methodology and potential audience. We are aiming to push the transport sector to its efficient frontier. Specifically related to transport, the March 2015 DFID/MDB Transport Directors meeting identified road safety and impact evaluations as the two top priority research areas for all eight MDBs.
[19] The Journal of African Economics (November 2012) observes how the demand for evidence-based policy-making continues to grow in Africa in many policy areas. “Fafchamps M and Zeitlin Z (2012) “Impact Evaluation in Africa: Introduction to the Special Issue”. November 2012 21 (5) J Afr Econ (2012) 21 (5): 687-690. doi: 10.1093/jae/ejs024”
[20] Center for Global Development (2006), “When Will We Ever Learn?—Improving Lives Through Impact Evaluation” http://www.cgdev.org/content/publications/detail/7973
[21] Regional Centre for Learning on Evaluation and Results for Anglophone Africa (CLEAR-AA) (2013). “Study On The Demand And Supply Of Evaluation In Ghana”.
[22] Regional Centre for Learning on Evaluation and Results for Anglophone Africa (CLEAR-AA) (2013), “Study On The Demand And Supply Of Evaluation In Rwanda”.

HM Treasury’s Magenta Book makes it clear that “the knowledge we gain from good evaluation can be used to increase policy effectiveness and is essential for informing the development of new policies to achieve the best results”[23].
[23] HM Treasury (2011), “Magenta Book – Guidance for Evaluation”.

Projects that are subject to rigorous evaluations can directly benefit from feedback that can lead to mid-course corrections that improve results. However, much of the benefit from evaluations occurs through future projects, which can be better designed as a result of the learning that has taken place through evaluation of earlier programmes. Therefore, under the MDBs’ project-centred business models, individual projects receive only some of the benefits from the additional costs of including a rigorous evaluation in the project design, but would face all of the substantial costs for doing so. Therefore there is a clear need for additional external resources.

D. Expected Programme Results

The programme aims to generate impact evaluation evidence on transport policy and investments, including indirect benefits, at sufficient scale to secure a reasonable level of conclusiveness in the results. The programme intends to improve the theory and evidence-base of project design and structure experimentation during project implementation to inform mid-course decisions and improve delivery and effectiveness. Countries’ and multilateral development banks’ capacity for evidence-based decision making will be strengthened through direct participation and learning-by-doing.

DFID’s support to ieConnect will substantially expand the number of impact evaluations in the three priority areas of urban mobility, road corridors and road safety and strengthen the focus on low-income, fragile and conflict-affected countries. It will also introduce several experiments to generate gender-specific knowledge on the causal link between transport investments and female economic empowerment. The DFID resources will help the programme consolidate gains in the early phase, invest in the quality and harmonisation of measurement and data that will help strengthen the external validity of results. Substantially it will increase the number of impact evaluations from 6 to at least 22 and up to 32. All DFID funds will be spent in LIC and LMICs.

Specifically, ieConnect will prioritise improving understanding of “what” works and “how”. Within the transport sector, the focus will be in priority sub-sectors for DFID where evidence to date is scarce: urban mobility, transport corridors and road safety, and their impacts on economic growth, poverty reduction, female economic empowerment and sustainability.

Impact evaluation case selection will prioritise transport investments that are co-financed by multiple MDBs and bilateral donors, including World Bank, African Development Bank, Asian Development Bank, Development Bank of Latin America (CAF), DFID, European Investment Bank (EIB), European Union (EU), Inter-American Development Bank (IDB), China ExIm Bank, Korea ExIm Bank and Japanese Investment Cooperation (JICA). Collaboration in learning will be critical for the use and adoption of evidence generated by the programme and will contribute to improving transport policy in the medium to long term. ieConnect will be intensely focused on ensuring the highest levels of engagement from partner governments to ensure that the focus of each impact evaluation reflects national learning priorities, so that answers can directly feed into policy decisions.

The impact of the programme will be to reduce poverty and increase equity. At the outcome level, this will be achieved by increasing the extent to which transport interventions are based on evidence of what works and why to support economic development and meet the needs of different groups, including women, young people, vulnerable groups and the poorest.

In order to achieve this outcome, evaluations would be required to investigate impacts across multiple issues: (i) land use and migration; (ii) jobs; (iii) economic output and trade; (iv) emissions; and (v) physical and health costs. A unique contribution of this programme is the articulation of a cross-sector research agenda to capture the welfare gains at individual, household, and market levels, on measures ranging from connectedness and traffic, population density and land use, to migration and market access, integration and efficiency, and across commodity, goods, labour and land markets; as well as female economic empowerment.

To ensure relevance, the research agenda is forward looking and prioritises topics that reflect the evolving portfolio of the MDBs, in addition to using methods that provide credible and actionable answers to upcoming policy decisions. In the topic selection process, therefore, it is recognized that while roads and inter-city roads remain the core business for MDBs, the demand from partner countries to engage into more complex areas has grown, including urban mobility transport corridors and road safety. Relative to rural roads, these areas of the transport portfolio have been largely under-researched, even though their effects on the development pattern of LICs and LMICs are expected to be transformational.
### Urban Mobility: Investment in urban mobility cannot be designed and assessed without considering the broader urban planning perspective. Availability of new data on urban centres (for example high resolution satellite data) should allow better capture of the ex-ante the impact of these investments. For example, the impact of urban transport investments would depend on the locations of clusters of jobs within a city (many cities, especially in Africa, have very few clusters of jobs) and on the land use/zoning regulations (in many settings land use regulations are not flexible enough to swiftly accommodate a changing urban mobility situation). From a policy perspective, it is crucially important to take into account such interactions in the design of policies that could help influence the form of rapidly urbanising cities before they lock in to undesirable spatial patterns, especially in the context of the current urban expansion in Africa and Asia.[24]
[24] See Suzuki, H., Cervero, R. and K. Iuchi (2013) Transforming Cities with Transit: Transit and Land Use Integration for Sustainable Urban Development. The World Bank.

Transport investments in cities can have important impacts in reducing search costs in labor markets. Little is known about how choices to migrate or occupational choices are influenced by transport and technology. Migrants may be deterred from such opportunities because of concerns about the skills needed in unfamiliar trades, the risks involved, specific employers they may approach in different urban areas, whether such employers are credible and have opportunities, and logistical concerns regarding temporary relocation. Impact evaluations can test the importance of such spatial mismatches by, for example, testing the value of short-term subsidies to transport to facilitate mobility and employment. This programme would contribute to understanding whether transport platforms operating at scale may narrow the enormous spatial wage differentials across sectors, the rural-urban divide suggested by the macro literature, and urban economic integration.[25]
[25] Gollin D, Lagakos, D. and Waugh, M. E. (2014): “The agricultural productivity gap”. Quarterly Journal of Economics.

The programme will also focus on how to mitigate the emissions of transport projects (pollution, congestion, GHGs). In particular, it will try to generate evidence on how to improve land use planning and logistics for reducing climate impact. In addition, policy innovations to support a shift to lower-carbon transportation modes and more efficient technologies will be tested. This area will include a large behavioral component to understand how to nudge users on adoption of public transport and transport providers on adoption of energy efficient technology. Important advances will be sought also on the measurement side, as the ieConnect will contribute to properly considering the wider social costs of transport (e.g. those related to accidents, congestion and air pollution).
### Transport Corridors : Through a combination of both physical investments and policy advice, transport investments (in particular those related to road and railroad corridors, and regional integration schemes) can create an environment for better business linkages, reduction of regulatory and institutional barriers and impediments at border-crossing, increased private sector investments, and reduction in transportation costs. It is estimated that the intra-national road transport costs in Ethiopia and Nigeria are approximately 7 to 15 times larger than the freight costs between Canada and the US. Transport investments hold tremendous promise in improving the efficiency with which markets operate and promoting equality of opportunity in LICs.

This is especially but not solely true for land-locked developing countries (LLDC), which are indeed particularly dependent on connectivity infrastructure. On average, LLDCs’ trade costs are about 50 percent higher than the coastal economy average, and thus markedly reduce their trade volumes. Being landlocked adds four days to export transportation times relative to times for LLDCs’ coastal neighbors. All three transport corridors in the current ieConnect programme connect landlocked countries (Ethiopia, South Sudan, Uganda, Burundi, DRC) to ports.

ieConnect will focus on testing which interventions can make transport investments more effective in achieving impact on trade-related outcomes, such as export growth, reduction in import costs, the generation of additional import volumes, and the cost reduction in and generation of exports and domestic commerce, as well as on the degree of agglomeration (which has been shown to be correlated to increase in productivity) and the access to basic services in less developed, remote, and sparsely populated regions. Examples of these complementary policy actions include mobile technologies to crowd-source road quality information for operation and maintenance and for taking advantage of trade opportunities; incentives for business reconversion (e.g. in the trucking industry); and nudges for passengers and firms to switch to more efficient transportation modes.

Transport investments can then affect migration patterns of production and people. This includes movement from farm to non-farm employment in rural areas, or increased industrial specialisation in urban areas. Impact evaluations can be used to understand how transport investments can be used in guiding or accompanying the structural transformation process whereby economies gradually shift towards non-agricultural sectors. For instance, ieConnect could test incentives for firms to relocate to production hubs made accessible by the new or improved transport infrastructure.

Road Safety: Road traffic injuries are estimated to cost developing countries 5 % of GDP, or more than $1 trillion a year. Road traffic accidents are a key obstacle to economic development and a burden on public health. The World Health Organization (WHO) forecasts that in 2015, road accidents will be the main cause of premature death and physical disability for those aged five or more.

Although road traffic accidents are a leading cause of death and disability among young adults, there are still few rigorous impact evaluations looking at the effectiveness of road safety interventions. In addition, and despite the fact that most of the casualties are in low and middle-income countries, studies available are highly concentrated in developed or high-income countries. Research will focus on four subareas: infrastructure, institutional and normative aspects, human factors, and vehicles. While the impact evaluation literature has focused on safety education, little evidence is available on regulatory safety standards for vehicles, institutional and normative frameworks, and incorporating road safety elements in infrastructure projects. In addition, very little is known about how interventions work for different people, either based on income or place of residence or gender of the target population. For this work, key outcome indicators include fatal and non-fatal accidents, injury accidents, speed tickets, changes in behavior and cognition (crossing roads, perceptions, intentions to speed, selecting safe routes, knowledge about safe behaviors), speed of vehicles, and costs of accidents.

The types of data required include data on fatal and non-fatal accidents that comes from a specific reporting system, such as the Fatality Analysis Reporting System (FARS), which contains detailed information on all fatal motor vehicle crashes occurring on public roads in the United States; or it could come from insurance companies; geographic conditions and roads conditions; municipality or local-level panels of the number of cars investigated by police patrols and the number alcohol-related driving offenders separated by driving under alcohol influence (DUI), drunk driving, and driving in deficient conditions, provided by a Criminal Analysis Office, Police, or others; and economic and public health variables.

ieConnect methodology and approach
The size of multilateral investments in transport, and the multi-sector nature of the research agenda, together with the methodological and data challenges of doing impact evaluation in the transport sector are why ieConnect adopts a geographically focused, multi-experiment approach. The idea is to use a set of thematically-connected impact evaluations in a region to investigate the impact of transport investments, and conduct multiple conceptually linked experiments in similar settings, to narrow down the causal links between multi-sector complementary interventions and their effects on:
1. Densification of land use, and migration
2. Maximizing linkages to labor, input/output and trade markets to generate economic activity and create jobs for men and women;
3. Shifting norms and behavior, changing regulation and introducing technology to reduce emissions; and
4. Improving road safety behavior and road regulation and infrastructure to reduce physical and health costs of accidents.
The ieConnect East Africa work will encompass Kenya, Tanzania, Uganda, Rwanda and Ethiopia with strategic corridor linkages to Djibouti, Sudan, DRC and Burundi. The regional focus will enable conclusions to be drawn about the nature and impacts of transport investments on the above. The investment in a common measurement and data framework will also strengthen the external validity of results from this setting.

In addition, a series of single experiments in middle-income country (MIC) urban settings will be used to understand emerging issues in urbanisation and mobility. These experiments focus on pricing policy for poverty reduction, interventions to mitigate violence against women in urban transport, effects on economic conglomerations and emission-reducing modal-shift interventions. These will be financed by other (i.e. non-DFID) donors.

Currently, in East Africa, impact evaluations are under way in two urban settings (Nairobi and Dar es Salaam), one transport corridor (Ethiopia Expressway), and in one rural setting (Rwanda). The road safety work in Nairobi aims at understanding the accountability relationships between regulators, insurers, operators, drivers and riders in the informal transport system to develop an accountability system for road safety that will substantially curb accidents and mortality on the roads. The information developed under this programme about the structure, organisation, and utilisation patterns of the informal public transport system will set the stage for the evaluation of the Bus-Rapid-Transit (BRT) in Nairobi. The evaluation of the BRT in Tanzania adopts innovative methods to evaluate the introduction of the BRT and overlays experiments to understand the costs of migration of populations due to raising land and housing costs, and the value of the BRT in linking poorer populations to markets when their constraints to using transport are released. The Ethiopia work aims at understanding the potential of road corridors and incentives to private industry on the development of agglomeration economies, output and trade.

An example of new programmes that the DFID funding to ieConnect could support are the potential impact evaluations of the Kenya-Uganda-Sudan and Dar-Lake Tanganyika-Burundi/Dar-DRC corridors which will investigate the impact of increasing access to ports for countries like DRC and Sudan, heavily affected by conflict, as well as testing more sustainable performance-based road maintenance strategies, and exploring the efficiency potential of improved institutional frameworks for intermodal freight transport.

Compliance with Gender Equality Act

The project has specifically prioritised female economic empowerment as a cross cutting theme. We know that safe, reliable and affordable transport services are key to improving women’s mobility, and with that, their access to labour markets and economic opportunities. We expect DIME will contribute to the very weak existing evidence base one of the core enabling factors for female economic empowerment.

On top of this, ieConnect has specified an equity focus at impact level, which will examine what works for different groups, including women and young people. This will involve examining differential impacts of transport corridors and improved urban networks, including benefits for women in terms of meeting their reproductive / domestic responsibilities, and related outcomes (maternal mortality, access to health and education services).

DIME has already proved to be very active at promoting a gender lens throughout its impact evaluation portfolio. DIME also actively monitors and makes a distinction between evaluations where gender is analysed and those where interventions are specifically targeting gender. Going forwards, DIME also intends to produce gender-specific evidence products to reflect its significant gender activities.

Summary assessment on terrorism and financing

The project will be implemented by the World Bank, using World Bank procedures and systems which specifically include safeguards on terrorism financing and other areas, e.g. fraud. No additional measures are proposed for this project beyond those already being implemented by the Bank.

Appraisal Case

A summary Appraisal Case is set out below. The detailed Appraisal is contained in Annex 2.

The Strategic Case set out the need for high quality impact assessments of infrastructure investments to inform decision makers on the economic development impact that could be achieved through a range of transport investment options. This Appraisal Case considers alternate management options through which DFID could deliver these evaluations against their ability to address the three strategic challenges identified:

Lack of standard approaches for estimating the spatial development impacts of transport investment.

Lack of clear evidence on how transport policy and investment choices impact on the spatial development of cities, and can facilitate uncongested expansion.

Lack of clear evidence on how long distance transport connections stimulate trade, spatial organisation, and the migration of people and production.

And the following three implementation criteria:

Capacity to administer funds quickly;

Ability to minimise DFID’s transaction costs; and

Fit with DFID strategic objectives.

This Appraisal Case does not include a cost-benefit analysis of options. This reflects the high informational requirements for credible counterfactual analysis, which in this case are unlikely to be met, and sensitivity of estimates of rate of return on research investments to changes in assumptions. See ‘Costs and Benefits of the Preferred Option’ below for further details.

Feasible options that address the need set out in the Strategic Case

Four potential management options were identified:

1. Open tender for bids to deliver impact evaluations.
2. Scaling up DFID support to the International Initiative for Impact Evaluation (3ie).
3. Scaling up DFID support to the World Bank’s Development Impact Evaluation (DIME) unit to expand the existing window for transport impact evaluation (ieConnect).
4. Creating a dedicated window for transport impact evaluation in the existing DFID-World Bank Strategic Research Programme (SRP).

These are considered against the criteria set out above. Conclusions reflect the views of a panel of DFID technical staff. A ‘business as usual’ baseline scenario is retained as the counterfactual against which other options are compared.

Business-as-Usual Baseline

As noted in the Strategic Case, transport impact evaluations have made up only 0.4% of all modern impact evaluations. We are not aware of any significant new initiatives that would alter this balance without DFID committing additional resources.

DFID currently sponsors a limited portfolio of transport impact evaluations through the World Bank’s Development Impact Evaluation (DIME) unit under the existing Impact Evaluation to Impact Development Policy (i2i)[26] programme. i2i includes a theme on shared prosperity (which covers factors of production, firm behaviour, regulatory reform, transport corridors, urban mobility, ICT and rural roads) as one of 5 thematic pillars. A total of six impact evaluations of transport projects will be completed under existing funding arrangements. This makes up 7% of the evaluations being undertaken by the programme.
[26] Details and programme documents available on Development Tracker- https://devtracker.dfid.gov.uk/projects/GB-1-203872

DIME launched its transport evaluation window (ieConnect) in June 2015, making use of existing core funding from DFID and other donors. Of the 20 projects identified at launch, funding was only available for six, with a further 5 prioritised for evaluations contingent on identifying additional funding. To date, no further funding for these has been secured or, to our knowledge, is being considered. Therefore, it is considered unlikely that either the World Bank or other donors would invest significantly more in transport impact evaluation under business-as-usual.

Option 1: Open tender for bids to deliver impact evaluations.
Under this option, DFID would issue a call for organisations specialising in impact evaluations to bid to deliver an agreed programme of impact evaluations, either independently or as part of a consortium.

Summary: There are a number of organisations that may be interested in bidding and have experience of producing high-quality evaluations of development interventions generally (though generally little on transport projects specifically). However, the range of interventions that could be evaluated and policy stakeholders that could be engaged would likely be limited. Furthermore, the novel nature of activities envisaged in the programme would mean DFID entering into a contract with limited understanding of the underlying costs, which reduces the probability of achieving good value for money.

Option 2: Scaling up DFID support to the International Initiative for Impact Evaluation (3ie).
3ie is an international grant-making NGO promoting evidence-informed development policies and programmes. Since its establishment in 2008, 3ie has awarded over 200 grants (including 146 impact evaluations). DFID is one of three main funders of 3ie, along with the Bill and Melinda Gates Foundation, and the William and Flora Hewlett Foundation.[27] 3ie does not conduct impact evaluations in-house, rather they are contracted out to reseachers.
[27] International Initiative for Impact Evaluation website (http://www.3ieimpact.org/en/), accessed 19 May 2016.

Summary: There is a case that 3ie would be able to deliver high-quality impact evaluations on transport projects. 3ie’s experience with commissioning evaluations is likely to mean that they are well placed to manage procurement processes for individual evaluations, but they would be drawing from the similar pool of researchers as if DFID issued a tender directly, and therefore are likely to be subject many to the same limitations. The open call process involved in 3ie commissions risks commissioning an uncoordinated set of evaluations which, whilst individually of high quality, do not provide a sufficient depth of understanding to draw generalizable conclusions. Furthermore, DFID’s objectives for 3ie include reducing its reliance on DFID for funding, which is inconsistent with funding a substantial new window on transport.

Option 3: Scaling up DFID support to the World Bank’s Development Impact Evaluation (DIME) unit.

DIME is a unit housed in the World Bank’s Development Economics Research Group with a mandate to generate high-quality and operationally-relevant impact evaluations for development policy. DIME’s objectives are to increase the use of impact evaluation in the design and implementation of public policy, improve the quality of the World Bank’s operations, strengthen country institutions for evidence-based policy making, and generate knowledge in strategic development areas. DIME works with eight multilateral development banks (not just the World Bank), and in contrast to 3ie conducts impact evaluations in-house.

Summary: DIME performs well across the majority criteria assessed. It has a strong track record of delivering high quality impact evaluations, including increasingly on challenging transport projects. Furthermore, being housed in the World Bank, it has excellent access to decision makers in client governments and has a proven ability to translate improved evidence into concrete actions to improve results. As an existing recipient of DFID funding, with strong management and fiduciary systems and an oversubscribed pipeline of potential evaluations, DIME is likely to be able to administer additional funds relatively quickly. However, being housed within the World Bank, these considerations must be balanced against maintaining focus on DFID’s core objectives for the World Bank.

Option 4: Creating a dedicated window for transport impact evaluation in the existing DFID-World Bank Strategic Research Programme (SRP).

The SRP is a strategic level partnership between DFID and the World Bank, funding economic growth-related research against an agreed set of joint objectives. The high level aim is for the project to support management reform efforts within the Bank, through making the Bank’s research in this field much more responsive to the needs of operational and policy units and through making the process of commissioning and funding Bank research more transparent, efficient and effective. The partnership provides resources for the World Bank to procure research on seven interrelated themes, including one transport theme. Currently, DFID has committed £13.3 million in funding to the SRP.[28]
[28] Additional information on the SRP is available on Development Tracker- https://devtracker.dfid.gov.uk/projects/GB-1-204151

Summary: The SRP has demonstrated capability to deliver high-quality research, including on very relevant subjects. The key differences between funding a programme of transport impact evaluations through the SRP as opposed to DIME, are that DIME has developed specialised expertise in impact evaluation that would be especially valuable in pushing the research methods into new areas and would be able to provide strategic coordination between evaluations and longer-term research commitments to fill critical gaps. Conversely, the SRP would draw from a wider pool of potential researchers (which would include DIME), but is not specialised in impact evaluation and given the relatively open call process could not guarantee the same level of coordination across evaluations. Internal World Bank staff movements associated with SRP also mean that the SRP would take substantially longer to begin research than DIME.

Management Options Conclusions

Table 1 below summarises conclusions by assigning red, amber, and green ratings for each of the shortlisted management options against the strategic objectives and implementation criteria identified. On this basis, the preferred management option is to fund a new transport programme through DIME.

However, the programme should be reassessed at the end of the second year of operation with explicit consideration of the benefits of merging funding with the SRP. Taking a strategic approach to DFID’s research funding through the World Bank is important to ensure that only the best research proposals are funded, but currently it is assessed that DIME’s existing systems and processes offer the highest likelihood of addressing the identified research need.

Detailed management arrangements are elaborated in the Management Case.

Table 1: Management Options
Strategic Challenges		Business as Usual	Open Tender	Scale-up 3ie	Scale-up DIME	SRP Window
1	Lack of standard approaches for estimating the spatial development impacts of transport investment.
2 & 3	Lack of clear evidence on how transport policy and investment choices impact on the spatial development of cities, and can facilitate uncongested expansion and lack of clear evidence on how long distance transport connections stimulate trade, spatial organisation, and the migration of people and production.
Implementation Criteria
4	Capacity to administer funds quickly
5	Minimise transaction costs to DFID
6	Fit with DFID strategic objectives
	Little/no potential to address challenge.
	Moderate potential to address challenge.
	Strong potential to address challenge.

Programme Scale

The appropriate scale of DFID funding is contingent on the minimum efficient scale to deliver a portfolio of evaluations that would address the strategic need identified, and expectations about what support could be mobilised from other sources.

This business case seeks approval for up to £7.5 million to fund the programme. This would be sufficient seed financing for DIME to commit to expanding the existing portfolio of transport impact evaluations from six to at least 22 and up to 32. Evaluations would be thematically-connected, conducting multiple conceptually-linked experiments in similar settings, to narrow down the causal links between multiple complementary interventions and the outcomes of interest. If quality expectations are met, this would be sufficient to draw a reasonably generalizable, although not comprehensive, conclusions.

Actual disbursement of funds would be based on DFID assessment of performance and value-for money on an ongoing basis.

Costs and Benefits of the Preferred Option

A DFID-funded literature review on rates of return for research[29], concluded that while the returns to research such as that proposed under this intervention are likely to be high, there are substantial informational requirements for the counterfactual analysis to quantify the returns. Moreover, the calculations of the returns to research are likely to be very sensitive to minor changes in assumptions regarding links from research to policy.
[29] Kunal Sen Literature Review on Rates of Return to Research, 2010.

In the specific case of the research anticipated under this programme, the evidence base quantifying the likely impact of an improved understanding of how to design and implement transport projects is very thin, precisely because it has not been invested in historically. Detailed cost-benefit analysis would therefore need to be based on relatively uninformed assumptions about the nature of evaluations, their findings, and the speed with which their findings would be taken up. These would be subject to substantial uncertainty and would result in an unconvincing cost-benefit analysis.[30]
[30] The evidence supporting the expected impact of the intervention is set out in the ‘Theory of Change’ section below.

However, to the extent that it is possible to make assessments, it is likely that sufficient benefits would be realised to make the programme worthwhile (see below). The logic and evidence underpinning this view would be revisited during implementation on an ongoing basis as part of DFID’s standard Annual Review process.

Expected Costs of the Intervention

Under the preferred management and scale options, DFID would provide £7.5 million over 5 years through DIME. DFID staff time involved in monitoring the programme and providing strategic direction is expected to be 10% of one senior infrastructure adviser and 10% of one programme manager.

DFID resources would not meet the full cost of completing the evaluations. Additional resources would be provided by other donors to make up at least 60% of the cost of the evaluations by the end of the programme.

Expected Benefits of the Intervention

The expected impact of this investment is poverty reduction and increased equity through faster economic development as a result of improvements in the selection, design, and implementation of transport infrastructure projects. This will be achieved through information on the likely returns to investing in projects, and how they should be structured and implemented, resulting in more informed decision makers making more effective use of available resources. Specifically, investing in the programme is expected to result in changes in the prioritisation of projects, decisions on which projects to scale up/down, and changes in how projects are designed.

The programme would conduct impact evaluations in a relatively new field. It is not credible to make strong claims regarding what research findings will be, and what value could be attributed to these. However, given DIME’s track record for high quality evaluations and the relevance of the research questions being asked to spending decisions, the chance of not finding useful conclusions through the research is considered low. Moreover, historic underinvestment in transport-related research, in particular for rigorous impact evaluation, means that there is likely to be substantial room for improvement in understanding of how to prioritise, design and implement these projects. At a minimum, given the current paucity of evidence, rigorous estimation of the rate of return to a range of projects would help to prioritise future investment options even if specific actions to improve results within projects are not identified.

Furthermore, DIME’s track record suggests that when evaluations supported do identify useful findings, these are likely to be translated into changes by decision makers. As part of monitoring arrangements for DFID funding to i2i, DIME explicitly tracks the number of evaluations conducted that influence project design or implementation, and that generate evidence used to support project adoption, scale-up, scale-down, continuation, or cancellation decisions. On both of these indicators, DIME was exceeding expectations at the most recent Annual Review, with 36 and 9 cases recorded respectively.[31]
[31] DFID Annual Review for “Impact Evaluation Support Facility”, March 2016 http://iati.dfid.gov.uk/iati_documents/5360680.odt

Independent evidence from the World Bank’s Independent Evaluation Group indicates that World Bank impact evaluations influenced policy dialogue in 55% of cases; influenced the design of new projects in 23-40% of cases; informed scale up/down directly in 22-33% of cases; and increased capacity for impact evaluation with counterparts, such as partner governments in 33% of cases.[32]
[32] Independent Evaluation Group (2012) “World Bank Group Impact Evaluations: Relevance and Effectiveness”

The risk of additional DFID financing to DIME at the preferred scale displacing the World Bank’s own resources for impact evaluation is considered small. Substantial oversubscription for the infrastructure evaluation window of the existing DIME programme is indicative of substantial unmet demand for further investment in this area. Therefore, it is likely that improvements in knowledge that result from the programme would not have happened without DFID support.

All DFID resources would be focused on evaluations in LICs and LMIC, mainly in sub-Saharan Africa. We are exploring the potential for a limited number of IEs in South Asia. However, the overall DIME/ieConnect portfolio is likely to also include evaluations in Latin America and China, with findings that may be relevant in lower income settings. The focus of DFID resources would be focused on East Africa with experiments allowing for the establishment of a common measurement framework, administrative and data systems across Kenya, Tanzania, Uganda, Rwanda and Ethiopia, with strategic corridor linkages to Djibouti, Sudan, DRC, and Burundi. The geographical focus would allow for a deeper dive than would be possible with a more geographically dispersed portfolio, in turn enabling more comprehensive conclusions to be drawn.

Potential environmental and climate impacts are considered below. These are not monetised due to similar reservations regarding precise quantification of research results.

What are the likely major impacts on social development?

Particular constraints faced by women and girls: People have very different transport needs, which vary across contexts, yet most transport policy and infrastructure is developed without understanding differential access and use. In many contexts women and girls, the poorest and disabled, rely much more heavily on public transport because of their limited access to private vehicles.[33] Reliable and affordable public transport services are fundamental to improving their mobility, but are rarely designed with their needs in mind. Limited reliability, low and inappropriate network coverage, prohibitively high fares routes and timings do not reflect their particular needs, and impact on their usage.
[33] John Hawkins, Jill Wells and Bernadine Fernz.Maximising the Benefits to the Poor from Infrastructure Programmes aimed at Increasing Growth. Topic Guide. November 2014. http://www.evidenceondemand.info/topic-guides

Women and girls very often face real safety and security concerns travelling on public transport, where they risk verbal abuse, sexual harassment and violence[34]. In some contexts, social and cultural norms restrict women from travelling on transport alongside men.
[34] Babinard, J., Hine, J., Ellis, S. & Ishihara, S. (2010) Mainstreaming Gender in Road Transport: Operational Guidance for World Bank Staff. Washington, DC: World Bank Transport Sector Board.

Some of the DIME research will specifically focus on understanding and addressing the distributional impacts of transport infrastructure, unpacking and testing what works for women and girls, and for the poorest, within larger projects which may have wider aims and objectives. Improved evidence on what works to address distributional impacts between income groups will work towards informing inclusive and pro-poor transport policies. The DIME model offers particularly good opportunities to work alongside policy makers and embedding programming in real development environments.

The economic rationale for improved and more inclusive access: Reliable, safe and affordable transport services are key to improving women’s mobility, and with that, their access to labour markets and economic empowerment. One of the major barriers to female labour force participation is their mobility – their capacity to access jobs and, for the self-employed, markets to sell produce. In both urban and rural areas, safe and reliable transport networks can enhance women’s access to formal employment opportunities; as well as childcare facilities and other services to free up women’s time. DIME will focus specifically on two transport areas that the evidence suggests represent significant barriers: urban and rural/urban transport corridors[35]. Informed policy on gender-sensitive transport should lead to better outcomes for women and girls that enable them to engage in the economic sphere and contribute towards their economic empowerment.
[35] Pozarny, P. (2016). Gender roles and opportunities for women in urban environments (GSDRC Helpdesk Research Report 1337). Birmingham, UK: GSDRC, University of Birmingham.

See Annex 2 for full Social Appraisal.

Careful and sensitive design of the results and evaluation frameworks and their data requirements will be essential to mitigate risks.

What is the likely impact on climate change and the environment?

Climate change and environment risks and impacts category[36]	B
[36] (A) potential high risk/opportunity; (B) medium/manageable potential risk/opportunity; (C) low/no risk/opportunity; (D) core contribution to a multilateral organisation.

None of the options presented are likely to result in unmanageable impacts on the environment or climate. There will be impacts associated with the operation of the programme, for example travel, reports and conference materials, and use of office space. However, the World Bank has an effective environmental strategy in place to manage these. Specifically, consistent with existing DFID funding to DIME, the World Bank would be expected to:

- Reduce the need to travel through the use of teleconference/videoconference facilities and locally-based staff where appropriate;
- Choose the location for events to minimise excessive travel (e.g. regional events);
- When flights are required, ensure individuals travel in economy class and, where appropriate, flights are offset through a verified carbon offset project;
- Reduce the carbon footprint of the programmes outputs though, for example, use of online communications and web-based tools, recycled paper, and minimising printing and waste; and
- Opt for a ‘green office’ environment, with insulation and other energy efficient measures, and an energy, waste, and water reduction strategy in place.

In addition, the strategy should cover the work carried out as part of the individual evaluations themselves, to ensure evaluators/researchers mitigate and monitor environmental impacts of their actions associated with the research.

There are medium opportunities to improve outcomes regarding climate change and the environment through the programme.

A DIME transport window would bring opportunities to generate evidence for effective programming and policy development necessary to improve a transport sector that is carbon intensive. Transportation creates significant negative environmental externalities (accounting for 23 % of total energy-related CO2 emissions (6.7 GtCO2))[37] and, owing to the paucity of rigorous evaluation of the effectiveness of projects, ieConnect could better inform how these could be mitigated. Policies to reduce environmental damage have tended to focus on investments in public transport infrastructure, price disincentives to deter the use of polluting transport modes, and regulation and restriction of vehicle use. Yet the efficacy of these policies remains unverified through rigorous evaluation of their impact.
[37] Sims R., R. Schaeffer, F. Creutzig, X. Cruz-Núñez, M. D’Agosto, D. Dimitriu, M. J. Figueroa Meza, L. Fulton, S. Kobayashi, O. Lah, A. McKinnon, P. Newman, M. Ouyang, J. J. Schauer, D. Sperling, and G. Tiwari, 2014: Transport. In: Climate Change 2014: Mitigation of Climate Change. Contribution of Working Group III to the Fifth Assessment Report of the Intergovernmental Panel on Climate Change [Edenhofer, O., R. Pichs-Madruga, Y. Sokona, E. Farahani, S. Kadner, K. Seyboth, A. Adler, I. Baum, S. Brunner, P. Eickemeier, B. Kriemann, J. Savolainen, S. Schlömer, C. von Stechow, T. Zwickel and J.C. Minx (eds.)]. Cambridge University Press, Cambridge, United Kingdom and New York, NY, USA.. Available at: https://www.ipcc.ch/pdf/assessment-report/ar5/wg3/ipcc_wg3_ar5_chapter8.pdf

The programme would include efforts to better understand, through evidence generation, how to mitigate the emissions of transport projects (pollution, congestion, greenhouse gases); and prove the effectiveness of resilience strategies incorporated in the planning, design, provision and operation of transport. Policy innovations to support a shift to lower-carbon transportation modes and more efficient technologies would also be tested as part of the programme. The outcome of the Transport window for DIME will likely emphasise the sustainability implications of transport and is aligned to other DFID transport projects including the applied engineering research project on High Volume Transport (HVT).

What are the likely major impacts on conflict and fragility?

Transport presents one of the most pressing infrastructure needs in Fragile and Conflict Affected States (FCAS). Improved road transport and mobility is vital during stabilization, post-conflict-disaster recovery and reconstruction and for cost effective delivery of humanitarian relief. The economic vulnerabilities of these countries also mean that investment in resilient, climate proof transport infrastructure is a significant challenge. The lack of effective institutions and skilled human capital can also exacerbate the shortage of well-informed capacity to plan and provide transport solutions that can foster peaceful growth.

The improvement of the evidence base, achieved through ieConnect, on transport impact in FCAS is likely to direct investment towards a more efficient frontier. Direct involvement in research, particularly application of evidence that has proven itself elsewhere, provides an opportunity for FCAS to select appropriate solutions, accelerate learning and improve very constrained capacity.

Careful and sensitive design of ieConnect impact evaluations in FCAS will be essential to mitigate potential direct and consequential risks.

Theory of Change for the Preferred Option

As ieConnect would represent a scaling up of a specific component of an existing programme, the theory of change for additional DFID funding for infrastructure impact evaluation through DIME is consistent with the theory of change for DFID’s existing investment through DIME. A diagram outlining causal pathways is presented in figure 1.

Under the preferred option, DFID would provide £7.5 million in additional funding to DIME. This support would allow DIME to:

- Develop validated measurement frameworks for priority outcome spaces (economic growth, poverty reduction, emissions and air quality, and road safety).
- Build administrative and data systems for transport impact evaluations in East Africa.
- Expand DIME’s existing portfolio of impact evaluations from 6 to a minimum of 22. Participation in these evaluations would be extended to include other MDBs.

Which would deliver the following outputs:

- Increased quantity and quality of evidence from impact evaluations on transport available to improve policy and programme design and implementation.
- Increased capacity and knowledge to catalyze country-to-country learning. In particular, at the scale proposed support would contribute to building a knowledge platform of ‘what’, ‘why’ and ‘how’ interventions work in different contexts and sectors.
- Communities of practice for evaluations, relevant policymakers, researchers, development agencies, and other stakeholders increasingly engaged in impact evaluation.

Additional detail on the ToC is contained in Annex 3.

Impact
Figure 1: Theory of Change for ieConnect*
DFID $13m (61%)**
World Bank $825k (4%)

Clients $5m (23%)
Activities
Conduct innovative impact evaluations of transport infrastructure projects.

Build capacity in project teams and developing country governments on impact evaluation methods and on techniques for evidence-based decision making.

Disseminate knowledge on impact evaluation approaches, findings, and results.

Outputs
Increased quantity and quality of evidence from impact evaluations available to improve policy and programme design and implementation.

Increased capacity and knowledge to catalyse learning. In particular, at the scale proposed support would contribute to building a knowledge platform of ‘what’, ‘why’ and ‘how’ interventions work in different contexts and sectors.

Communities of practice for evaluations, policymakers, researchers, development agencies, and other stakeholders increasingly engaged in impact evaluation.

Outcomes
Improved awareness, demand for, and use of evidence in decision-making in transport, as evidenced by scaling up, scaling down, and mid-course correction of policies and programmes. Leads to improved effectiveness and impact of new and existing transport projects by DFID and the wider development community.

Reduced Poverty and Increased Equity

*As funding arrangements would be at programme launch. DIME has committed to attracting additional investment into the programme, which would reduce DFID’s burden share in ieConnect to a maximum of 40%. DFID’s burden share for support to DIME overall would be lower than this.

**This includes both up to £7.5m that would be committed under this programme and existing commitments under i2i that could be re-classified to ieConnect.

Other Donors $2.6m (12%)

Measures to Assess Value for Money

Maximising value for money in the programme depends on controlling the costs of producing impact evaluation, and maximising the probability that findings influence investment decisions.

Monitoring arrangements for additional resources provided to DIME would be consistent with existing arrangements, but tailored to reflect the specific nature of the anticipated ieConnect portfolio. Specifically, in addition to existing value for money reporting, the following indicators would be included in annual reporting requirements:

Economy and Efficiency	Completed impact evaluation papers/reports	Average cost of final impact evaluation papers/reports <=$275,000.[38]
Cost-Efficiency	Crowding-in of external funds	Amount and sources of financing for ieConnect impact evaluations coming from alternative sources. DIME have committed to achieve at least 60% by programme-end.
Benefits Quantification Effort	Innovations in design	Number of ieConnect impact evaluation designs that include multiple treatment arms.
	Mid-course correction	Number of ieConnect impact evaluations that inform mid-course policy/intervention correction.
	Informing scale-up.	Number of ieConnect impact evaluations that inform policy scale up/down.
[38] Note that this is substantially higher than the $275,000 target per paper target cost for funding provided to DIME under i2i. However, this because with i2i funding, DFID only supports researcher costs, not the cost of data collection. With ieConnect, we would support the cost of data collection as substantial additional data would need to be collected that would not routinely be part of programme activities.

Summary Value for Money Statement

Lack of information precludes credible cost-benefit analysis for the proposed intervention, but the evidence that is available suggests that there is likely to be sufficient benefits from a coordinated programme of transport impact evaluations through DIME to justify the costs. This is based on strong evidence that we would be able to identify the correct decisions, reach clear conclusions, and that the findings would have traction with decision makers, combined with a high level of transparency in costs on the part of DIME, which would allow DFID to play an active role in managing the costs involved in a relatively new area of research. However, these assumptions would be actively monitored during programme implementation. The approval level sought in this business case is an upper ceiling, subject to additional information continuing to support the validity of the theory of change and assumptions about DIME’s ability to simultaneously control costs and meet quality expectations.

Commercial Case

A. Why is the proposed funding mechanism/form of arrangement the right one for this intervention, with this development partner?

The project will be implemented through adding DFID funds to the existing DIME Trust Fund mechanism already funded by DFID through Evaluation Department. The World Bank receives funds from external partners such as DFID only through such Trust Funds, or through Externally Financed Outputs (EFOs). EFOs are suitable for small one-off pieces of work, which is not applicable in this instance. Additing to the existing Trust Fund is therefore the only viable funding mechanism available. This mechanism has worked well to date for DFID and the Bank.

B. Value for money through procurement

The World Bank’s approach to procurement is to ensure open and fair competition in all its tenders, so that it procures high quality goods and services at the lowest cost. It requires procurement of goods and services through International Competitive Bidding with limited exceptions similar to those used by other multilateral development banks.

Individual activities that are funded by the project will be managed by DIME, alongside the existing programme of DIME operations. Performance will be assessed against pre-determined criteria, and any staff recruitment under ieConnect will be in accordance with standard World Bank guidelines. All external contracting of goods and services will be done under standard World Bank procurement guidelines.

Using the World Bank for this intervention will save on DFID’s management costs given the Bank’s existing expertise and networks. Cost drivers for each of the studies contracted will be determined by commercial tenders.

Successive DFID Annual Reviews of DIME have not highlighted any particular concerns on value for money issues. However, DFID will continue to monitor this area closely in collaboration with the Bank.

Financial Case

A. What are the costs, how are they profiled and how will you ensure accurate forecasting?

DFID will contribute up to £7,537,147 between 2016/17 and 2020/21 for the ieConnect project. Costs are profiled as follows:

A detailed cost estimate is contained in the Bank’s proposal for the project.

DFID’s £7.5 million is approximately 33% of the total estimated final cost of ieConnect. The remaining funds will be provided through other donor/project sources, leveraged by the Bank. The Bank has already been successful in leveraging other sources of funding:

B. How will it be funded: capital/programme/admin?

Funding will be from the programme resources made available to the Growth Research Team in DFID Research and Evidence Division. The project is affordable within the existing budget for the Growth Team through to 2019/20. Approval for the use of funds beyond 2019 will be sought from HM Treasury. As with all DFID projects, funding availability is subject to wider management decision making and prioritisation.

C. How will funds be paid out?

Funds will be provided to the Bank on a six monthly advance basis, as per the existing DFID-World Bank funding arrangement and in line with standard practices for DFID contributions to World Bank Trust Funds. For each funding claim the Bank has been providing a financial statement showing spending to date and forecasted financing needs. There have been no issues with this mechanism so far.

DFID will follow the SMART rules guidance on payments to multilateral trust funds. Disbursements to ieConnect will be aligned with disbursements to the main DIME project by Evaluation Department.

D. What is the assessment of financial risk and fraud?

Financial risk and fraud is judged to be low.

DFID’s Multilateral Aid Review found that the World Bank’s financial accountability processes and policies are robust. The World Bank has established procedures to deal with financial mismanagement and other forms of malpractice if these are suspected. The Bank’s Institutional Integrity team investigates allegations of fraud and corruption in Bank-financed projects and Bank Group operations. Recent Due Diligence assessments by DFID staff have comfirmed the financial capability of the World Bank to be strong.

DFID monitoring of DIME to date has not thrown up any particular issues with financial risks or fraud.

E. How will expenditure be monitored, reported, and accounted for?

The funds will be monitored as part of DFID’s Annual Reviews, which will be co-ordinated between the two teams funding the ieConnect and main DIME projects.

Expenditure reporting and accounting will take place through the existing DIME system. The Bank has been producing six monthly financial statements to accompany each funding claim.

Annual World Bank auditing of the DIME Trust Fund will also cover audit of the ieConnect project.

Management Case

A. What are the Management Arrangements for implementing the intervention?

ieConnect will use the same governance mechanism as the overall DIME/i2i project.

The overall i2i governance structure includes several layers of coordination and oversight, comprising: a Council, Steering Group, Regional Focal Points and Global Practice Thematic Working Groups, Technical Committee, Technical Reviewers, and Managing Unit. The Steering Committee currently includes DFID representation, and will be expanded to include representation from the Growth Research Team that would be responsible for additional funding.

DIME already has a dedicated thematic working group on transport and ICT, with representation from the World Bank’s Transport and ICT Global Practice and DIME. This has responsibility to provide broad guidance on the strategic directions and allocation principles. As the appropriate level for transport-specific deiscussions on content, this group would be expanded to include DFID representation and representation from other multilateral development banks.

DIME will monitor gender   through the Technical Committee. Some external Technical Reviewers will have gender expertise; and the DIME research teams will include technical experts to provide gender analysis across DIME IEs. Gender issues will be monitored by DFID through the annual review processes.

The governance structure is summarized as follows:

For ieConnect, the DFID Senior Responsible Owner (SRO) will be within the Growth Research Team. The DFID Evaluation Department SRO for DIME and the Growth Research Team SRO for ieConnect will liaise closely to ensure a co-ordinated approach to Annual Reviews and harmonised reporting requirements for the Bank, to reduce transaction costs for both DFID and DIME. The overall relationship between DFID and DIME will continue to be managed through Evaluation Department, given the long-standing partnership and larger scale funding.

For day-to-day management of ieConnect activities, the Bank will use DFID funding to hire additional technical and management staff to work specifically on ieConnect impact evaluations. Details are in the Bank’s proposal.

ieConnect will operate under ethical principles agreed for the main DIME project.

B. What are the risks and how these will be managed?

The overall risk is assessed to be Moderate.

Risks for the main i2i project funded by DFID are set out in the detailed risks appraisal in the original Business Case produced by Evaluation Department. These are monitored at least annually and the risks appraisal updated in the Department’s delivery plan for i2i. Those risks apply generally to the ieConnect project.

Specific risks relating to DFID funding of ieConnect will be monitored in addition to those applying generally to the ieConnect project. These are set out in the table below. The Growth Research Team will be responsible for monitoring these risks, and escalating any major issues to be resolved through the i2i governance mechanisms. See the annex for the full risks appraisal.

ieConnect-specific risks (in addition to the i2i main project risks)

RISKS CATEGORY AND RISKS	PROBABILITY	IMPACT (before mitigating)	MITIGATING MEASURES
Delivery risks
ieConnect is unable to secure additional funding from other donors.	Unlikely	Major	Currently, 69% of DIME funding is from other donors. A similar leverage is expected on DFID funding of ieConnect.
ieConnect is not responsive to DFID’s geographical or topic focus.	Unlikely	Moderate	The Logframe includes numbers and / or % of IEs and spend in focus areas (LIC, FCAS, urban mobility, transport corridors, road safety, FEE). These will be reviewed annually.
Research uptake risks: findings from impact evaluations do not feed through into decision making and design of transport projects.	Possible	Severe	This area will be closely monitored by DFID and DIME during implementation. While, ultimately, there is no guarantee with any research that it will lead to impact, measures in place to ensure a high degree of policy and operational relevance are: close working by the project with: (i) a cross-World Bank Council composed of Chief Economists and directors from operational vice presidencies that provide strategic guidance; (ii ) working groups in each global practice to set learning priorities and select cases; and (iii) with operational teams to shape project design and ensure experiments guide project implementation toward greater effectiveness. DIME engages clients from the beginning, to set research questions and agree on entry points to affect policy decisions using experimental results.
Intellectual/Innovation risks
The programme of works is too ambitious and therefore leads to inconclusive results.	Possible	Major	The programme is pushing new frontiers on transport with only 0.4% of modern IEs undertaken in the transport sector. Data is limited and RCTs are relatively new for transport. Conclusivity of results should be higher with planned use of clusters of IEs in up to 11 sites. This will require close monitoring by DFID and DIME during implementation
Rigorous approaches to transport impact evaluation are not identified.	Unlikely	Major	It is original and challenging to assess the spatial and induced impacts of transport infrastructure in cities and corridors using impact assessment techniques. This would be a risk for all of the options considered.
Impact evaluations not of sufficient quality.	Unlikely	Major	DIME has in place a blind quality assurance process to ensure all evaluations uphold the highest technical standards.

C. What conditions apply (for financial aid only)?

Not applicable – not financial aid

D. How will progress and results be monitored, measured and evaluated?

There will be annual reviews of ieConnect that will be harmonized between the Growth research team and Evaluation Department, to ensure a co-ordinated DFID approach to i2i overall while allowing both teams to focus on their specific funding components.

The Logical Framework attached at Annex 1 will be the main means for measuring progress on ieConnect.

ANNEX1: Draft Final ieConnect Logframe

Draft Final ieConnect DFID Logframe
FY16-FY21

Notes: ** FY refers to DFID Fiscal Year (e.g., FY17 refers to April 2016-March 2017
** All targets are stocks or percentages of stocks (cumulative since the inception of i2i)

ieConnect DFID Logframe
Outcomes	Indicators	Targets					Definition of indicator (relevant base)	Source
		FY17	FY18	FY19	FY20	Total
1. Improved awareness, demand for and use of transport evidence in decision making	Proportion of transport project teams participating in ieConnect workshops that improve their knowledge of impact evaluation techniques	75%	75%	75%	75%	75%	% of IE transport teams participating in workshops with a teaching component that show improvement on pre-post knowledge test (% of teams participating to i2i workshops with a pre-post test)	Pre-post test during workshops
	Proportion of transport impact evaluations with multi-arm evaluation designs to test project innovations.	65%	65%	65%	65%	65%	% IEs that have more than one treatment arm	Monitoring system
	Proportion of impact evaluations that influence transport project during design or implementation	55%	55%	65%	65%	60%	% of IEs that improved design based on clear understanding of the underlying theory of change or whose baseline results were used to stimulate policy dialogue / help identify problems and solutions	Monitoring system
	Proportion of completed transport impact evaluations that generate evidence used to support project adoption, scale-up, scale-down, continuation or cancelation decisions	45%	45%	55%	55%	50%	% of IEs that contributed to change the "how many receive the policy or programme"	Monitoring system
2. Improved effectiveness and impact of new and existing transport interventions from DFID, MDBs and wider community	Proportion of transport impact evaluations that have influenced the design or implementation of other transport projects outside of the IE itself	15%	15%	25%	25%	20%	Proportion of transport impact evaluations that have influenced the design or implementation of other transport projects outside of the IE itself	Monitoring system
	Proportion of completed and published transport impact evaluations that are cited in the academic literature	25%	25%	25%	25%	25%		Google Scholar
Outputs	Indicators	FY17	FY18	FY19		Total	Definition of indicator	Source

1. Increased quantity, quality and relevance of transport evidence available to improve policy design and implementation	Increase the number of Impact Evaluations (IEs) across key sub-sectors (total):	9	25	25		25
	urban mobility	4	10	10		10
	transport corridors	4	10	10		10
	road safety	2	5	5		5
	Thematic knowledge reviews for policymaking	1	3	3		3	Stock of thematic knowledge reviews, e.g., mechanism, sector, country, pillar reviews
	Increased number of cross cutting reviews: FEE: FCAS:	1 1	2 2	2 2		2 2
	Developed data infrastructure (with ability for scale up)	1	1	1		1		Admin data
	Developed and validated measurement framework that is able to disaggregate impact (male / female ; rural/urban).	1	1	1		1	Cost effective ways to collect the efficient set of indicators in each outcome space of interest to better understand how transport investments contribute to poverty reduction and econommic development	Admin data
	Thematic distribution:		%				% of ieConnect-supported IEs	Admin data
	Gender (cross-cutting)		30%					Monitoring system
	FCAS		50%
	Regional distribution:		%				% of ieConnect-supported IEs	Admin data
	Sub-Saharan Africa		75%
	South Asia		Upto 25%
	Income level distribution:		%				% of ieConnect-supported IEs	Admin data
	Low income and lower-middle income / DFID focus countries		100%	>60%
	Female Economic Empowerment (FEE):					% of ieConnect-supported IEs	Monitoring system
	Proportion of IEs with FEE specific intervention		30%
	Proportion of IEs disaggregated by sex and age		40%
2. Increased capacity of transport policymakers, implementers, researchers, and partners to incorporate rigorous evidence/tools into policy making	Number of MDBs involved at the operational level	8	8	8	8	8		Admin data
	Proportion of co-financed transport programmes	100%	100%	100%	100%	100%
	Spend on non-WB funded or co-funded transport IEs	20%	20%	30%	30%	25%
	Proportion of people participating in workshops that come from low or lower-middle income countries	75%	75%	75%		75%		Admin data
	Proportion of people participating in workshops that come from FCASs	50%	50%	50%		50%		Admin data
	Number of people trained in workshops and / or by ieConnect supported teams/ researchers	2	4	4	4	1000	Stock of people (MDBs, governments, universities, other partners, etc) trained in ieConnect workshops and IE specific capacity building events	Admin data
	Number of workshops	2	4	4	4	4	IE design workshops, research clinics (thematic and cross-cutting), regional and country-specific strategy development workshops, dissemination events.	Admin data
3. Increased Communities of Practice and knowledge platforms for sharing of transport evidence and its application for policy making	Number of organisations participating in ieConnect workshops	50	75	100	100	100	Stock of organizations (donors, Multilateral Development Banks, government agencies, academic institutions, NGOs, etc) that have participated to at least one i2i workshop	Admin data
	Number of organisations, universities, research centers, and government agencies participating in ieConnect networks	50	70	100		100	Stock of organizations engaged in ieConnect-supported IEs (researcher and counterpart affiliation)	Monitoring system
	Number of non-WB hosted dissemination events	8	12	17	18	18		Admin data
	Number of active participants in Transport Practitioners Network	250	500	750	1000	1000
	Active MDB participation on DIME Steering Committee	1	1	1	1	1

ANNEX 2: DETAILED OPTIONS APPRAISAL

The Strategic Case set out the need for high quality impact assessments of infrastructure investments to inform decision makers on the economic development impact that could be achieved through a range of transport investment options. The Appraisal Case considers alternate management options through which DFID could deliver these evaluations against their ability to address the three strategic challenges identified:

Lack of standard approaches for estimating the spatial development impacts of transport investment.

Lack of clear evidence on how transport policy and investment choices impact on the spatial development of cities, and can facilitate uncongested expansion.

Lack of clear evidence on how long distance transport connections stimulate trade, spatial organisation, and the migration of people and production.

And the following three implementation criteria:

Capacity to administer funds quickly;

Ability to minimise DFID’s transaction costs; and

Fit with DFID strategic objectives.

This Busniess Case does not include a cost-benefit analysis of options. This reflects the high informational requirements for credible counterfactual analysis and sensitivity of estimates of rate of return on research investments to changes in assumptions. See ‘Costs and Benefits of the Preferred Option’ below for further details.

Feasible options that address the need set out in the Strategic Case

Four potential management options were identified:

1. Open tender for bids to deliver impact evaluations.
2. Scaling up DFID support to the International Initiative for Impact Evaluation (3ie).
3. Scaling up DFID support to the World Bank’s Development Impact Evaluation (DIME) unit to expand the existing window for transport impact evaluation (ieConnect).
4. Creating a dedicated window for transport impact evaluation in the existing DFID-World Bank Strategic Research Programme (SRP).

These are considered against the criteria set out above. Conclusions reflect the views of a panel of DFID technical staff. A ‘business as usual’ baseline scenario is retained as the counterfactual against which other options are compared.

Box 1: Challenges of Impact Evaluation of Infrastructure Projects / As outlined in the Strategic Case, there has been very little investment in impact evaluations of transport projects. In part this reflects specific challenges inherent in conducting these types of evaluation that may undermine the effectiveness of standard approaches. / Randomised controlled trials, often held up as the gold standard of evidence, randomly assign some agents to a treatment group and others to a control, and therefore are able to conclusively say that any difference observed between the two groups is due to the intervention. However, major transport investments are the result of purposive decision-making processes. Regardless of the basis for decisions, it cannot be credibly assumed that there is no difference between places that are targeted for investment and those that are not. Therefore, we cannot easily disentangle whether differences observed between the two areas after the investment are due to the investment itself, or due to other factors that were present beforehand. / Evaluating the impact of an infrastructure project therefore requires specifying a credible counterfactual (what would have happened were it not for the project) against which observed outcomes can be compared. Furthermore, traditional transport evaluations have not been based on solid economic theory that would allow analysis to look beyond proximate results like transport time and costs to more important socio-economic outcomes. Rigorously establishing this is very difficult. Developing and implementing approaches that allow for definitive conclusions to be drawn on the impact of these major projects is at the frontier of impact evaluation techniques.[39],[40] / Furthermore, the impacts of most interest take many years if not decades to unfold – the mass migration of people and production embodied by the development of a city or trade route. Impact evaluations take longer than typical research experiments, but capture far more real world information.
[39] Analysis of the challenges experienced in evaluations of Millennium Challenge Corporation transport investments is provided by BenYishay, A and Tunstall, R “Impact evaluation of infrastructure investments: the experience of the Millennium Challenge Corporation” Journal of Development Effectiveness, 2011 (3:1)
[40] Complexities involved in appraisal and evaluation of rural roads are discussed in Van de Walle, D “Chosing Rural Road Investment to Help Reduce Poverty” World Development, 2002 (Vol. 30, No, 4) and Mu, R and Van de Walle, D “Rural Roads and Local market Development in Vietnam”, 2011 (Vol. 47, No. 5)

Business-as-Usual Baseline

As noted in the Strategic Case, transport impact evaluations have made up only 0.4% of all modern impact evaluations. We are not aware of any significant new initiatives that would alter this balance without DFID committing additional resources.

DFID currently sponsors a limited portfolio of transport impact evaluations through the World Bank’s Development Impact Evaluation (DIME) unit under the existing Impact Evaluation to Impact Development Policy (i2i)[41] programme. i2i includes a theme on shared prosperity (which covers factors of production, firm behaviour, regulatory reform, transport corridors, urban mobility, ICT and rural roads) as one of 5 thematic pillars. A total of six impact evaluations of transport projects will be completed under existing funding arrangements. This makes up 7% of the evaluations being undertaken by the programme.
[41] Details and programme documents available on Development Tracker- https://devtracker.dfid.gov.uk/projects/GB-1-203872

DIME launched its transport evaluation window (ieConnect) in June 2015, making use of existing core funding from DFID and other donors. Of the 20 projects identified at launch, funding was only available for six, with a further 5 prioritised for evaluations contingent on identifying additional funding. To date, no further funding for these has been secured or, to our knowledge, is being considered. Therefore, it is considered unlikely that either the World Bank or other donors would invest significantly more in transport impact evaluation under business-as-usual.

Option 1: Open tender for bids to deliver impact evaluations.

Under this option, DFID could issue a call for organisations specialising in impact evaluations to bid to deliver an agreed programme of impact evaluations, either independently or as part of a consortium. In terms of expected ability to address the criteria established:

Lack of standard approaches for estimating the spatial development impacts of transport investment. There are a several organizations that have developed strong track records for delivering high quality impact evaluations and may be interested in bidding to conduct evaluations either individually or as part of a consortium with other organizations. These include university-affiliated research organizations with a strong academic track record, and consultancies with experience of conducting impact evaluations with a consistent focus on policy relevance. It is likely that a combination of both academics and development organizations with a broad footprint would be required to achieve both the dissemination and quality objectives of the programme.

Depending on bids attracted, academics commissioned through this process could be close to the global frontier of impact evaluation research, and may therefore be able to rapidly integrate lessons from other ongoing research. However, rigorous evaluations of urban transport programmes present a specific set of challenges that, as identified in the Strategic Case and Box 1, few evaluators have successfully tackled. Very detailed tenders would likely be required to provide DFID with sufficient assurance that bidders had identified approaches to the evaluations that could overcome these limitations.

Lack of clear evidence on how transport policy and investment choices impact on the spatial development of cities, and can facilitate uncongested expansion and lack of clear evidence on how long distance transport connections stimulate trade, spatial organisation, and the migration of people and production. Evaluation of both urban and transport corridor projects by the programme would be contingent on having access to projects to evaluate. If DFID were to be the sole commissioner of the evaluation programme, it is likely that evaluators would only be guaranteed access to DFID programmes. Compared to the scale of global investment in infrastructure, DFID only has a limited (existing and planned) portfolio of transport urban and transport corridor investments that would be suitable for evaluation under this programme. Therefore, unless bidders already had a very strong network of low-income country government relationships that would be sufficient to provide access to projects to evaluate independently, then the scope of possible evaluations could be quite limited. As a result of this, the body of evidence that could be generated may not be sufficient to draw broadly generalizable conclusions.

Capacity to administer funds quickly. A number of potential bidders have established networks and systems for impact evaluation, which would reduce the amount of time taken to administer funds. However, setting up a consortium of organizations to draw together a range of relevant capabilities and specializations would likely delay the process. Furthermore, this option would require a carefully-managed tendering and contracting phase.

Ability to minimise DFID’s transaction costs. Tendering competitively generally has the potential to provide value for money if the pool of potential suppliers is large enough to generate competition and reduce costs, and of sufficient quality to have intended impact. However, because of the novel nature of evaluations envisaged under this programme, clear benchmarks for expected costs are not available. A competitive tendering process therefore risks DFID entering a contractual relationship with a supplier without a clear understanding of the costs involved in conducting the evaluations and therefore placing DFID in a weak negotiating position to achieve value for money.

Fit with DFID strategic objectives. Issuing a competitive tender fits with wider DFID commercial objectives of developing key markets that grow the pool of potential suppliers, with the goal of driving value for money.[42] However, as noted above, where clear cost benchmarks for this type of work have not been established, value for money is more likely to be achieved by working closely with established, transparent, and like-minded partners than through commercial negotiations where we have limited information.
[42] Department for International Development “Commercial Vision” https://www.gov.uk/government/uploads/system/uploads/attachment_data/file/516048/DFID_s-Commercial-Vision.pdf

Summary: There are a number of organisations that may be interested in bidding and have experience of producing high-quality evaluations of development interventions generally (though generally little on transport projects specifically). However, the range of interventions that could be evaluated and policy stakeholders that could be engaged would likely be limited. Furthermore, the novel nature of activities envisaged in the programme would mean DFID entering into a contract with limited understanding of the underlying costs, which reduces the probability of achieving good value for money.

Option 2: Scaling up DFID support to the International Initiative for Impact Evaluation (3ie).

3ie is an international grant-making NGO promoting evidence-informed development policies and programmes. Since its establishment in 2008, 3ie has awarded over 200 grants (including 146 impact evaluations). DFID is one of three main funders of 3ie, along with the Bill and Melinda Gates Foundation, and the William and Flora Hewlett Foundation.[43] 3ie does not conduct impact evaluations in-house, rather they are contracted out to reseachers.
[43] International Initiative for Impact Evaluation website (http://www.3ieimpact.org/en/), accessed 19 May 2016.

Lack of standard approaches for estimating the spatial development impacts of transport investment. 3ie would draw bidders for the work from a similar pool as if DFID went directly to the market. However, as 3ie is specialised in commissioning high quality evaluations and has an extensive established network through which to communicate, there may be reason to believe that 3ie would be more successful at commissioning and managing high quality evaluations. Furthermore, 3ie have previously commissioned a limited number of evaluations covering both transportation and urban development, adding further credibility to this option.

Lack of clear evidence on how transport policy and investment choices impact on the spatial development of cities, and can facilitate uncongested expansion and lack of clear evidence on how long distance transport connections stimulate trade, spatial organisation, and the migration of people and production. 3ie’s relatively open call process risks identifying an uncoordinated set of evaluations such that even if all the individual studies are of high quality, we do not gain a sufficiently broad understanding of any individual context to draw definitive conclusions on the broader economic development impact of projects. Depending on the range of evaluators that could be reached by 3ie, this approach may also be limited by access to projects to evaluate in a similar way to issuing an open tender.

Capacity to administer funds quickly. Capacity to administer funds quickly. As an existing organization, 3ie already has management and financial systems in place that could potentially disburse new resources relatively quickly. However, the speed of implementation would be limited by 3ie’s operating model where prospective evaluators are invited to bid through resource windows, which is then followed by a procurement process. As a core funder of 3ie, DFID has a strong existing relationship and has already conducted due diligence assessments, which would be expected to accelerate the procurement process.

Ability to minimise DFID’s transaction costs. As 3ie would sub-contract researchers to conduct evaluations, this would essentially add an additional layer of administration as compared with DFID commissioning the evaluations directly. As of April 2015, 3ie retains 15% from all grant windows to cover expenses associated with running the organisation.[44] However, with 3ie’s strong track record on managing high quality evaluations, DFID staff time required would be substantially lower; as would the risk of evaluations being commissioned that do not meet quality expectations.
[44] DFID Annual Review for “3IE- To promote more rigorous and systematic assessment of the imact of development policies and programmes”, September 2015 http://iati.dfid.gov.uk/iati_documents/5159536.odt

Fit with DFID strategic objectives. DFID has currently committed to provide up to £49.7 million in funding to 3ie (including funding for a core social protection thematic window, an agriculture impact thematic window, and a humanitarian impact evaluation thematic window). Existing DFID support is performing well, scoring an ‘A’ (outputs met expectations) in the most recent DFID Annual Review.[45] However, DFID’s objectives for 3ie include reducing its dependence on the top two donors (DFID and the Bill and Melinda Gates Foundation) to make the institution more independently viable. Funding an additional infrastructure window would run counter to this.
[45] DFID Annual Review for “3IE- To promote more rigorous and systematic assessment of the imact of development policies and programmes”, September 2015 http://iati.dfid.gov.uk/iati_documents/5159536.odt

Summary: There is a case that 3ie would be able to deliver high-quality impact evaluations on transport projects. 3ie’s experience with commissioning evaluations is likely to mean that they are well placed to manage procurement processes for individual evaluations, but they would be drawing from the similar pool of researchers as if DFID issued a tender directly, and therefore are likely to be subject many to the same limitations. The open call process involved in 3ie commissions risks commissioning an uncoordinated set of evaluations which, whilst individually of high quality, do not provide a sufficient depth of understanding to draw generalizable conclusions. Furthermore, DFID’s objectives for 3ie include reducing its reliance on DFID for funding, which would is inconsistent with funding a substantial new window on transport.

Option 3: Scaling up DFID support to the World Bank’s Development Impact Evaluation (DIME) unit.

DIME is a unit housed in the World Bank’s Development Economics Research Group with a mandate to generate high-quality and operationally-relevant impact evaluations for development policy. DIME’s objectives are to increase the use of impact evaluation in the design and implementation of public policy, improve the quality of the World Bank’s operations, strengthen country institutions for evidence-based policy making, and generate knowledge in strategic development areas. DIME works with eight multilateral development banks (not just the World Bank), and in contrast to 3ie conducts impact evaluations in-house.

Lack of standard approaches for estimating the spatial development impacts of transport investment. DIME has built a strong track record for delivering high quality impact evaluations, and has been acknowledged by the World Bank’s respected Independent Evaluation Group (IEG) for its significant contribution to raising the standard of impact evaluation in the World Bank, resulting in over 90% of impact evaluations being classified as high quality.[46] DIME’s model involves employing academic researchers to work on specific evaluations and help to ensure high quality standards, but also working with core World Bank staff to maintain clear consideration of policy relevance.
[46] Independent Evaluation Group (2012) “World Bank Group Impact Evaluations: Relevance and Effectiveness”

Lack of clear evidence on how transport policy and investment choices impact on the spatial development of cities, and can facilitate uncongested expansion and lack of clear evidence on how long distance transport connections stimulate trade, spatial organisation, and the migration of people and production. With buy-in from across the major multilateral development banks, DIME would have access to a very broad portfolio of transport projects to evaluate. Furthermore, with evaluations being conducted in-house, strategic decisions can be made to coordinate evaluations such that they address the most important evidence gaps and provide results with a higher degree of generalizability. As part of the World Bank, DIME also has more direct access to policymakers, and by providing a more direct link between researchers and policymakers, DIME may be able to more effectively foster systematic use of evidence.

Capacity to administer funds quickly. Of the options considered, DIME is likely to be able to begin work on transport impact evaluations with the shortest lead time. The over-subscription to the existing window provides a readily available list of potential projects to be included in a first round of evaluations.[47] Furthermore, DIME’s demand-driven operating model (whereby individual projects signal their interest in being the subject to an evaluation) provides some assurance that evaluations are operationally relevant, and so means they can achieve policy impact faster.
[47] 30 transport projects submitted formal Expressions of Interest to the existing i2i window, of which 13 were rated of sufficient quality to be funded, but existing funding would only cover eight.

Ability to minimise DFID’s transaction costs. As DFID already provides funding through DIME, additional transactions costs involved in scaling up the transport window would be relatively small and predictable. These would include agreeing an amendment to the existing Memorandum of Understanding, and additional adviser staff time to monitor the additional work programme. With existing funding to i2i, DIME has demonstrated a very high level of transparency with regards to costs and spending. This is especially valuable given the novel nature of evaluations envisaged under this programme, as DFID would be able to maintain clear oversight of both direct and indirect costs involved, for which we do not have clear benchmarks at this stage. Under new World Bank trust fund rules, a standard cost recovery charge of 17% is applied on top of all staff and consultant costs, but does not apply to non-human resource costs. This replaces the previous system in which there was a 5% set up fee (on the whole contribution), another 5% for program administration (for the governance and operations), and in addition, 14% was charged on staff time charged to the Trust Fund.

Fit with DFID strategic objectives. DFID makes substantial core contributions to the World Bank through the IDA replenishment rounds, during which considerations of the UK’s appropriate burden share form an important part of decisions. Channeling substantial additional funding through World Bank trust funds risks diluting the results of these decisions, as well as reducing the World Bank’s focus on its core agenda. Whilst funding provided to any individual trust fund is small relative to core contributions, in aggregate they can have the effect of diluting focus. However, in this case there is considered to be a clear alignment between activities that would be funded under this programme and the World Bank’s core business. Furthermore, funding to DIME would be used to evaluation funding to all MDB transport projects, not only those funded by the World Bank.[48]
[48] At least 50% ieConnect funds would undertake impact evaluations in non-World Bank transport programmes to ensure that progress is made in other MDBs.

Summary: DIME performs well across the majority criteria assessed. It has a strong track record of delivering high quality impact evaluations, including increasingly on challenging transport projects. Furthermore, being housed in the World Bank, it has excellent access to decision makers in client governments and has a proven ability to translate improved evidence into concrete actions to improve results. As an existing recipient of DFID funding, with strong management and fiduciary systems and an oversubscribed pipeline of potential evaluations, DIME is likely to be able to administer additional funds relatively quickly. However, being housed within the World Bank, these considerations must be balanced against maintaining focus on DFID’s core objectives for the World Bank.

Option 4: Creating a dedicated window for transport impact evaluation in the existing DFID-World Bank Strategic Research Programme (SRP).

The SRP is a strategic level partnership between DFID and the World Bank, funding economic growth-related research against an agreed set of joint objectives. The high level aim is for the project to support management reform efforts within the Bank, through making the Bank’s research in this field much more responsive to the needs of operational and policy units and through making the process of commissioning and funding Bank research more transparent, efficient and effective. The partnership provides resources for the World Bank to procure research on seven interrelated themes, including one infrastructure and transport. Currently, DFID has committed £13.3 million in funding to the SRP.[49]
[49] Additional information on the SRP is available on Development Tracker- https://devtracker.dfid.gov.uk/projects/GB-1-204151

Lack of standard approaches for estimating the spatial development impacts of transport investment. Although the programme has only been operational for 2 years, it is built on strong capabilities within the World Bank Development Economics Vice Presidency[50], and has already demonstrated an ability to provide high quality research. Of particular relevance to this proposed programme, as part of the existing SRP research theme on infrastructure and transport, a grant has been approved for research to better understand the wider economic benefits of railway rehabilitation in East Africa, including through trading opportunities and industrial clustering.[51] However, whilst this shows capacity to commission very relevant research more broadly, it does not necessarily demonstrate ability to develop new approaches to impact evaluation specifically.
[50] A 2006 independent evaluation of World Bank research found that “Bank researchers have produced innovative and important new research that has maintained the Bank’s position as the intellectual leader among development agencies” Banerjee et al “An Evaluation of World Bank Research, 1998-2005”
[51] A full list of approved grants is provided in the Annual Review for “DFID/World Bank Strategic Research Partnership”, January 2016 http://iati.dfid.gov.uk/iati_documents/5333798.odt

Lack of clear evidence on how transport policy and investment choices impact on the spatial development of cities, and can facilitate uncongested expansion and lack of clear evidence on how long distance transport connections stimulate trade, spatial organisation, and the migration of people and production. The SRP’s operating model involves inviting bids for proposed research programmes under designated themes from researchers in the World Bank and, more recently, also externally. A higher priority is given to proposals that include both research staff and a partnership with World Bank operations. Therefore, considering impact evaluations specifically, the SRP would, therefore, be able to access a very wide pool of potential researchers, and potential projects to evaluate. However, a necessary trade-off for the competitive call process that is a core part of how the SRP operates would be significantly limiting capacity to ensure coordination across evaluations and reach more generalizable conclusions, which is a central objective of the programme. Moreover, many of the outcomes of interest would likely take longer to materialise than the relatively short timeframe of SRP research grants.

Capacity to administer funds quickly. The SRP is an existing DFID-World Bank research programme with governance arrangements that could be amended to reflect the new funding. However, expected World Bank staff movements over the coming months mean that decisions on future directions for the programme are on hold until new staff are in place (likely November 2016 at the earliest). If agreement were to be reached with the World Bank to open a new window, this would then be followed by a call process that would further delay the start of research.

Ability to minimise DFID’s transaction costs. The SRP has only been operational for two years, but the most recent DFID Annual Review found that to the extent progress can be assessed at this stage, the research is performing well on value for money grounds.[52] As an existing programme, amendments to administrative arrangements would involve relatively little staff time, as compared to establishing a new programme. As with DIME, under new World Bank trust fund rules, a standard cost recovery charge of 17% is applied on top of all staff and consultant costs, but does not apply to non-human resource costs
[52] DFID Annual Review for “DFID/World Bank Strategic Research Partnership”, January 2016 http://iati.dfid.gov.uk/iati_documents/5333798.odt

Fit with DFID strategic objectives. As with DIME, providing research resources to the World Bank would need to be considered in light of DFID’s central objectives for the organization set through the core contribution process. In addition to the points made regarding funding transport impact evaluations through DIME, providing funding through the SRP would have the additional benefit of using competition to ensure that the strongest research proposals would be funded, and that funding would be available to researchers outside of the World Bank and other MDBs.

Summary: The SRP has demonstrated capability to deliver high-quality research, including on very relevant subjects. The key differences between funding a programme of transport impact evaluations through the SRP as opposed to DIME, are that DIME has developed specialised expertise in impact evaluation that would be especially valuable in pushing the research methods into new areas and would be able to provide strategic coordination between evaluations and longer-term research commitments to fill critical gaps. Conversely, the SRP would draw from a wider pool of potential researchers (which would include DIME), but is not specialised in impact evaluation and given the relatively open call process could not guarantee the same level of coordination across evaluations. World Bank staff movements also mean that the SRP would take substantially longer to begin research than DIME.

Management Options Conclusions

Table 1 below summarises conclusions by assigning red, amber, and green ratings for each of the shortlisted management options against the strategic objectives and implementation criteria identified. On this basis, the preferred management option is to provide additional resource through DIME.

However, the programme should be reassessed at the end of the second year of operation with explicit consideration of the benefits of merging funding with the SRP. Taking a strategic approach to DFID’s research funding through the World Bank is important to ensure that only the best research proposals are funded, but currently it is assessed that DIME’s existing systems and processes offer the highest likelihood of addressing the identified research need.

Detailed management arrangements are elaborated in the Management Case.

Table 1: Management Options
Strategic Challenges		Business as Usual	Open Tender	Scale-up 3ie	Scale-up DIME	SRP Window
1	Lack of standard approaches for estimating the spatial development impacts of transport investment.
2 & 3	Lack of clear evidence on how transport policy and investment choices impact on the spatial development of cities, and can facilitate uncongested expansion and lack of clear evidence on how long distance transport connections stimulate trade, spatial organisation, and the migration of people and production.
Implementation Criteria
4	Capacity to administer funds quickly
5	Minimise transaction costs to DFID
6	Fit with DFID strategic objectives
	Little/no potential to address challenge.
	Moderate potential to address challenge.
	Strong potential to address challenge.

Programme Scale

There is global underinvestment in transport impact evaluation resulting in very high-value and durable decisions being made on the basis of thin evidence, and DFID is in a strong position to take a lead in addressing this. The appropriate scale of DFID funding is contingent on the minimum efficient scale to deliver a portfolio of evaluations that would address the strategic need identified, and expectations about what support could be mobilised from other sources.

This business case seeks approval for up to £7.5 million to fund the programme. This would be sufficient seed financing for DIME to commit to expanding the existing portfolio of transport impact evaluations from 6 to at least 22. Evaluations would be thematically-connected, conducting multiple conceptually-linked experiments in similar settings, to narrow down the causal links between multiple complementary interventions and the outcomes of interest. If quality expectations are met, this would be sufficient to draw a reasonably generalizable, although not comprehensive, conclusions.

This would not mean that the programme would necessarily spend £7.5 million. DFID would closely monitor the performance of the programme, the realised cost of evaluations, and contributions by others to the impact evaluation effort and adjust funding accordingly.

Compared to the cost of transport investments made, the cost of rigorous evaluation is low. As an illustration, the first round of applications to the $2 million transport window in the existing DIME i2i programme included 31 projects with a total value of US$18 billion; total research costs associated with evaluations were equivalent to less than 0.2% of this amount, with DFID’s contribution representing less than 0.1%.

As identified, little has been invested in transport impact evaluation globally. Therefore, by taking the lead in pushing rigorous impact evaluation into this area, DFID would at least initially be taking on a relatively high burden share.

Costs and Benefits of the Preferred Option

A DFID-funded literature review on rates of return for research[53], concluded that while the returns to research such as that proposed under this intervention are likely to be high, there are substantial informational requirements for the counterfactual analysis to quantify the returns. Moreover, the calculations of the returns to research are likely to be very sensitive to minor changes in assumptions regarding links from research to policy.
[53] Kunal Sen Literature Review on Rates of Return to Research, 2010.

In the specific case of the research anticipated under this programme, the evidence base quantifying the likely impact of an improved understanding of how to design and implement transport project is very thin, precisely because it has not been invested in historically. Detailed cost-benefit analysis would therefore need to be based on relatively uninformed assumptions about the nature of evaluations, their findings, and the speed with which their findings would be taken up. These would be subject to substantial uncertainty and would result in an unconvincing cost-benefit analysis.[54]
[54] The evidence supporting the expected impact of the intervention is set out in the ‘Theory of Change’ section below.

However, to the extent that it is possible to make assessments, it is likely that sufficient benefits would be realised to make the programme worthwhile (see below). The logic and evidence underpinning this view would be revisited during implementation on an ongoing basis as part of DFID’s standard Annual Review process.

Expected Costs of the Intervention

Under the preferred management and scale options, DFID would provide £7.5 million over 5 years through DIME. DFID staff time involved in monitoring the programme and providing strategic direction is expected to be 10% of one senior infrastructure adviser and 10% of one programme manager.

DFID resources would not meet the full cost of completing the evaluations. Additional resources would be provided by other donors to make up at least 60% of the cost of the evaluations by the end of the programme.

Expected Benefits of the Intervention

The expected impact of this investment is poverty reduction and increased equity through faster economic development as a result of improvements in the selection, design, and implementation of transport infrastructure projects. This will be achieved through information on the likely returns to investing in projects, and how they should be structured and implemented, resulting in more informed decision makers making more effective use of available resources. Specifically, investing in the programme is expected to result in changes in the prioritisation of projects, decisions on which projects to scale up/down, and changes in how projects are designed.

The programme would conduct impact evaluations in a relatively new field. It is not credible to make strong claims regarding what research findings will be, and what value could be attributed to these. However, given DIME’s track record for high quality evaluations and the relevance of the research questions being asked to spending decisions, the chance of not finding useful conclusions through the research is considered low. Moreover, historic underinvestment in transport-related research, in particular for rigorous impact evaluation, means that there is likely to be substantial room for improvement in understanding of how to prioritise, design and implement these projects. At a minimum, given the current paucity of evidence, rigorous estimation of the rate of return to a range of projects would help to prioritise future investment options even if specific actions to improve results within projects are not identified.

Furthermore, DIME’s track record suggests that when evaluations supported do identify useful findings, these are likely to be translated into changes by decision makers. As part of monitoring arrangements for DFID funding to i2i, DIME explicitly tracks the number of evaluations conducted that influence project design or implementation, and that generate evidence used to support project adoption, scale-up, scale-down, continuation, or cancellation decisions. On both of these indicators, DIME was exceeding expectations at the most recent Annual Review, with 36 and 9 cases recorded respectively.[55]
[55] DFID Annual Review for “Impact Evaluation Support Facility”, March 2016 http://iati.dfid.gov.uk/iati_documents/5360680.odt

Independent evidence from the World Bank’s Independent Evaluation Group indicates that World Bank impact evaluations influenced policy dialogue in 55% of cases; influenced the design of new projects in 23-40% of cases; informed scale up/down directly in 22-33% of cases; and increased capacity for impact evaluation with counterparts, such as partner governments in 33% of cases.[56]
[56] Independent Evaluation Group (2012) “World Bank Group Impact Evaluations: Relevance and Effectiveness”

The risk of additional DFID financing to DIME at the preferred scale displacing the World Bank’s own resources for impact evaluation is considered small. Substantial oversubscription for the infrastructure evaluation window of the existing DIME programme is indicative of substantial unmet demand for further investment in this area. Therefore, it is likely that improvements in knowledge that result from the programme would not have happened without DFID support.

All DFID resources would be focused on evaluations in sub-Saharan Africa. We will explore the possibility of expansion into South Asia. However, the overall DIME/ieConnect portfolio is likely to also include evaluations in Latin America and China, with findings that may be relevant in lower income settings. The focus of DFID resources would be in East Africa, with the concentration of experiments allowing for the establishment of a common measurement framework, administrative and data systems across Kenya, Tanzania, Uganda, Rwanda and Ethiopia, with strategic corridor linkages to Djibouti, Sudan, DRC, and Burundi. The geographical focus would allow for a deeper dive than would be possible with a more geographically dispersed portfolio, in turn enabling more comprehensive conclusions to be drawn.

ANNEX 3: Social Appraisal Annex

Social appraisal

Particular constraints faced by women, girls and more vulnerable groups: Everyone has different transport needs, which vary across contexts, gender, economic quintile and location, yet most transport policy and infrastructure is developed without understanding differential access and use. In many contexts, for example, women, girls, the poorest and disabled people rely much more heavily on public transport because of their limited access to private vehicles[57]. Social norms often define clearcut roles and responsibilities for women and men, which is turn affects their transport requirements, as well as dictating their mobility and access. Social norms also dictate that men often benefit from transport options that carry a higher status because of the stigma of travelling on certain forms of transport[58].
[57] John Hawkins, Jill Wells and Bernadine Fernz.Maximising the Benefits to the Poor from Infrastructure Programmes aimed at Increasing Growth. Topic Guide. November 2014. http://www.evidenceondemand.info/topic-guides
[58] UN-Habitat. 2013. Planning and Design for Sustainable Urban Mobility. Available at: http://mirror.unhabitat.org/pmss/listItemDetails.aspx?publicationID=3503 Page viii

Reliable and affordable public transport services are fundamental to improving women’s mobility, but are rarely designed with women or girls in mind. Limited reliability, low network coverage, prohibitively high fares routes and inappropriate timetabling all impact on usage. Even if public transport vehicles are designed to be accessible, this is only of limited utility if network coverage is patchy, for example. Urban transport systems tend to suit men, who have routine travel patterns between home and work during peak hours. Travel patterns for women involve more frequent short journeys during off-peak hours and longer travel times, for example to access a health centre, are often not on direct routes into a city centre.

Women and girls very often face real safety and security concerns travelling on public transport, where they risk verbal abuse, sexual harassment and violence[59]. This can impact significantly on public transport usage. In some contexts, social and cultural norms restrict women from travelling on transport alongside men. In places like Bangladesh, where “eve teasing” is prevalent on streets, taxis, bus and rail systems[60], it can lead to girls being ostracised or even suicide. Research examining how women’s fears and the real risk of violence (including sexual harassment) on public transportation networks has already highlighted the impact on their labour force participation[61]. Operator policies and poor siting of bus stops and termini can increase real and perceived dangers for women and children and for other groups, such as the aged or disabled, as well as preventing access.
[59] Babinard, J., Hine, J., Ellis, S. & Ishihara, S. (2010) Mainstreaming Gender in Road Transport: Operational Guidance for World Bank Staff. Washington, DC: World Bank Transport Sector Board.
[60] Faruk, F. Eve-teasing: A social disaster for women in Bangladesh. Eastern University Journal. Vol.3, Issue 3, December 2011. http://gsdl.easternuni.edu.bd/greenstone/collect/2eujournal/index/assoc/HASHb471.dir/doc.pdf
[61] http://www.urban.org/urban-wire/why-womens-access-safe-public-transportation-key-sustainable-development-0

Some of the DIME research will specifically focus on understanding and addressing the distributional impacts of transport infrastructure, unpacking and testing what works to improve opportunities for women and girls to access and then use transport safely and in ways that widen their economic opportunities. DIME will offer specific opportunities to examine options for improving the safety of public transport.

The economic rationale for improved and more inclusive access: Reliable, safe and affordable transport services are key to improving women’s mobility, and with that, their access to labour markets and economic empowerment. One of the major barriers to female labour force participation is their mobility – their capacity to access jobs and, for the self-employed, markets to sell produce. In both urban and rural corridor areas, safe and reliable transport networks can enhance women’s access to formal employment opportunities; as well as childcare facilities and other services to free up women’s time. DIME will focus specifically on two transport areas that the evidence suggests represent significant barriers : urban and rural/urban transport corridors[62].
[62] Pozarny, P. (2016). Gender roles and opportunities for women in urban environments (GSDRC Helpdesk Research Report 1337). Birmingham, UK: GSDRC, University of Birmingham.

Poor transport networks also prevent women from being able fulfil their reproductive responsibilities efficiently and on time, which in turn impacts on their ability to earn an income. Women and girls typically spend more time travelling than men, because of social norms that dictate their domestic responsibilities. Time spent accessing services such as food markets or health services constrains women’s access to economic activity – especially in urban areas. In Ghana, for example, the typical woman devotes almost three times as many hours per annum as men (on average 20 hours weekly) to transport. This represents 50 percent of the time a worker would expect to devote to a typical full-time job, severely limiting the hours women can devote to productive work[63].
[63] European Commission (2004) Toolkit on mainstreaming gender equality in EC development cooperation

Transport corridors: Well planned and improved transport corridors can promote economic activity that benefits women and the poorest. Underdeveloped road and rail networks lead to higher transport costs for agricultural products to the markets as well as of farm inputs, reducing farmers’ competitiveness[64]. Prices can exceed the income capacity of the poorest, in particular for regular or frequent trips[65]. People with better road or transport access are more likely to source income from other sectors, most notably service-based enterprises[66] [67] [68]. Transport that is safe, and culturally appropriate for women to use, can create opportunities for economic engagement that simply haven’t existed before. It is much easier for a woman to migrate for work if her access back to her family is easy, affordable and guaranteed.
[64] Brixiova, Z., A. Kamara and A. Salami (2010) Smallholder Agriculture in East Africa: Trends, Constraints and Opportunities. Asian Development Bank Working Paper No. 105
[65] Booth, D., L. Hanmer and E. Lovell (2000) Poverty and Transport
[66] Mu, R and D. van de Walle (2007) Rural Roads and Poor Area Development in Vietnam. World Bank Policy Research Working Paper 4340
[67] Escobal, J and C. Ponce (2002) The Benefits of Rural Roads: Enhancing Income Opportunities for the Rural Poor. Grade Working Paper 40
[68] Lanjouw, P., J. Quizon, R. Sparrow (2001) “Non-agricultural earnings in peri-urban areas of Tanzania: evidence from household survey data”. Food Policy. Vol 26

Poverty tends to correlate with isolation, the poorest people having least access to transport networks[69]. Evidence shows strong correlation between poverty and connectivity[70]. Studies show that road access can improve social welfare by increasing the proximity and quality of basic services, and broadening livelihood opportunities.
[69] World Bank (2006) Rural Access Index
[70] Porter, G. 2013. Transport services and their impact on poverty and growth in rural sub-Saharan Africa. AFCAP

Urban planning: The evidence on urban transportation, particularly from Asian cities, indicates that transport systems that are poorly planned can lead to a loss of productivity if the employment options of inhabitants are limited by their transport choices due to affordability or access, or there is excessive congestion. Transport systems that do not cater for users of all modes, including non-motorised ones, run the risk of exacerbating slum formation, urban poverty and employment in the informal sector.

The social cost of community severance in urban areas is a significant factor that particularly affects female access, for example when urban expressways and arterial roads are built. In Delhi when 700,000 squatters were resettled on the periphery of the city, female employment fell by 27 percent because travel time increased three-fold[71]. There is clearly scope for research into the specific application of transport solutions in African and Asian LICs, where modal splits are quite different.
[71] DFID. (2013) Social Dimensions of Transport: A resource for social impact appraisals. London: Department for International Development.

How DIME will address these issues: Improved evidence on what works to address distributional impacts between income groups will work towards informing inclusive, socially relevant and pro-poor transport policies. Informed policy on gender-sensitive transport should lead to more inclusive infrastructure benefits and better outcomes, particularly economic outcomes for women and girls. This is particularly so given the DIME model which involves working alongside policy makers and embedding programming in real development environments.

ieCi specifically aims to reduce poverty and increase equity by increasing evidence of what works and why to meet the needs of different groups. This will involve understanding and addressing the diverse needs of different transport users. DIME will enable the piloting and testing of safer transport initiatives. While a significant body of research already exists on gender and transport, particularly as this relates to rural transport[72], a greater research focus on the difficulties women and girls face on urban public transport will be a real contribution of the DIME work. Examples might include piloting women friendly public services or testing how to improve the safety of stations or pick up points.
[72] See Gender and Transport Resource Guide at: http://www.ssatp.org/sites/ssatp/files/publications/HTML/Gender-RG/module6/index-p2.html

The DIME work will complement very clearly RED and other research on female economic empowerment. For example, the IDRC GrOW (Growth and Economic Opportunities for women) programmes has already recognised transport and mobility as a major barrier to FEE, and includes a small component testing safe transport initiatives in Pakistan[73]. Investment in DIME will enable further replication and testing of initiatives already being trialled, such as the reservation of vehicles for “women only” that has been introduced to combat the sexual harassment in a number of cities[74].
[73] http://www.urban.org/urban-wire/why-womens-access-safe-public-transportation-key-sustainable-development-0
[74] Chantal Duchene. Gender and Transport. Discussion Paper 11. 2011. International Transport Forum.

While there may be appreciation at policy level that gender has to be better taken into account in transport design and planning, there is often little awareness of how to implement such principles in certain LIC settings. DIME’s operating model, working closely with the planners and officials who actually develop and implement transport policy, will enable a very strong focus on building planning and operational capacity to understand and accommodate the diverse needs of users.

ANNEX 4: Detail on Theory of Change

Conducting rigorous impact evaluations on how large-scale transport projects contribute to economic development and poverty reduction is novel and challenging (see Box 1 in Annex 2). Therefore a key assumption in delivering the expected outputs is DIME successfully developing new and better methods for transport impact evaluation. DIME has demonstrated some ability to do this. Specifically, DIME’s proposed approach involves undertaking evaluations based on a structured framework and will need to involve observing intermediate processes that might be assessed over a relatively short time period. This is expected to allow analysis to move beyond traditional transport project outcomes along a range of indicators that have preliminarily been clustered around 5 categories: land, job opportunities, output and trade markets, emission/low-carbon transport, and road safety. However, DIME’s ability to further develop and implement this approach is crucial for the programme to meet objectives, and therefore represents a major risk for the programme.

Broadly, the quality of impact evaluation practice is improving but remains uneven. The World Bank is the leading development organisation in this area and the technical quality of its impact evaluations has improved significantly: the number of evaluations assessed as being of medium to high quality has increased from 51% of impact evaluations initiated during 2000-2004 to 98% for those initiated after 2005[75]. The improvements in quality have been achieved in part through interventions such as the DIME and the Strategic Impact Evaluation Fund, which introduced uniform quality review procedures for impact evaluations[76].
[75] Independent Evaluation Group (2012), “World Bank Group Impact Evaluations: Relevance and Effectiveness”.
[76] Independent Evaluation Group (2012), “World Bank Group Impact Evaluations: Relevance and Effectiveness”.

Translation of the additional resources provided by DFID into the expected set of outputs is also conditional on other development agencies also putting resources into the impact evaluation effort. The total estimated cost of the envisaged minimum 22 impact evaluations is over $31 million, the total value of DFID contributions would be approximately $10 million (subject to exchange rate movements, as DFID commitments would be demoninated in Sterling). As such, another key assumption is that other donors also see value in the programme and have sufficient confidence in DIME systems. DIME has a strong track record of using an initial programme supported by DFID funding to attract co-financing from others.[77]
[77] DIME’s most recent financial statement shows 31 percent of funding coming from DFID, with 32 percent from other donors, 25 percent from client governments, and 5 percent from the World Bank’s own budget.

Successful delivery of programme outputs is expected to result in following outcomes:

Improved awareness, demand for, and use of evidence in decision-making in the transport sector, as evidenced by scaling up, scaling down, and mid-course correction of policies and programmes.

Improved effectiveness and impact of new and existing transport projects by DFID and the wider development community.

A key assumption necessary for the conversion of outputs into outcomes is DIME targeting the right policy and decision makers in knowledge and dissemination activities. DIME’s operational model -whereby clients are engaged from the beginning to set research questions, adapt policy implementation and agree on entry points to affect policy decisions using experimental results- makes this more likely.

There is some evidence of implementation efficiencies generated by applying impact evaluation to programmes. DIME has conducted analysis of World Bank-funded projects and the effect of impact evaluations on programme timeliness and disbursement delays.[78] Analysis found that impact evaluations have a large and significant effect on the rate of disbursement of operations, reducing the gap between planned and actual disbursements and increasing disbursements relative to average disbursements in the typical project in the same sector. This should not be interpreted as evidence of a causal relationship, but the analysis did identify credible channels through which an impact evaluation could potentially result in faster disbursement.
[78] Legovini, Arianna et al “Impact Evaluation Helps Deliver Development Projects” World Bank Policy Research Working Paper 7157, January 2015

To achieve the expected benefits of informing the design of a wide range of projects, a further assumption is that impact evaluation generated is transferable between contexts and interventions. This is only likely to be the case if the programme is successful in conducting a sufficient number and –importantly- range of evaluations to build a body of evidence of how results vary across projects. Achieving a high degree of external validity is dependent on running similar interventions in multiple contexts; the scale of support is unlikely to be sufficient to achieve this, but strategic coordination of evaluations that are conducted is expected to go some way to addressing this.

Whilst the programme would- through capacity building activities- include effort to increase demand for evidence in decision making, much of the theory of change rests on the key assumption that decision makers want improved evidence and operate in a context that allows for evidence-based decision making, but are frustrated by a lack of relevant evidence. Reviews have identified huge differences in partner country demand for impact evaluations and the use made of them from one partner country to the next.[79] This is a challenge for all research programmes, but to some extent is mitigated through DIME’s access to decision makers and early engagement with governments to gauge interest and willingness to compete for selection. This assumption would continue to be monitored through programme implementation.
[79] Pamies-Sumner, Stephanie “Development Impact Evaluations: State of Play and New Challenges”, Research Department, Agence Francaise de Developpment, February 2015.

However, despite the increasing demand for impact evaluation there remains little evidence of its actual use in practice and the wider use of evidence in policy making. The willingness of governments to use evidence for policy decisions varies greatly depending on their level of openness for objective and critical input[80]. The politically sensitive nature of impact evaluation means that successful support in this area has relied on the ability of initiatives to address constraints on both the supply and demand of evaluation evidence[81].
[80] Keijzer, N., Spierings, E., and Heirman, J, (2011), “Research for development? The role of Southern research organisations in promoting democratic ownership”. Discussion paper 106. ECDPM.
[81] McDonald, B., Rogers, P., and B. Keffurd (2003), “Teaching People to Fish? Building the Evaluation Capability of Public Sector Organizations.” Evaluation, vol. 19, no. 3, 9-29.

There is some evidence that the World Bank’s impact evaluations specifically do affect policy dialogue and development intervention decisions; a 2012 IEG study of all World Bank impact evaluations[82] concluded that they had: influenced policy dialogue in 55% of cases; influenced the design of new projects in 23-40% of cases; informed scale up/down directly in 22-33% of cases; and increased capacity for impact evaluation with counterparts, such as partner governments in 33% of cases. DIME continuously measures policy influence across the cycle of implementation of its programs and products.
[82] Independent Evaluation Group (2012) “World Bank Group Impact Evaluations: Relevance and Effectiveness”

IEG also found that limited active engagement of client government counterparts in the initiation, design, analysis and review of impact evaluations can undermine the influence of evidence in decision making and dialogue. For example, 83% of completed impact evaluations initiated by the client influenced policy dialogue with the government, compared to 46% of completed impact evaluations not initiated by private or government clients.

The resulting impact is expected to be improved development effectiveness of investments in transport infrastructure, contributing to faster, fairer and more inclusive economic development, and poverty reduction. Under the most ambitious scenarios for the programme, this could be through connecting remote areas to the global economy, creating new trade corridors, or permitting the development of bigger, denser, more productive, safer and cleaner cities.

ANNEX 5: Detail on the Themes and cross cutting areas of interest in ieConnect

DFID funds will support at least 22 and up to 32 Transport Impact Evaluations.

Theme 1: Urban Mobility
The theme will investigate emerging issues in urban transport, including transport pricing policies, modal shift and climate change approaches, congestion and road safety, and gender-based violence.

All the net increase in global population up to 2050 will be in urban areas, leading to around 70 percent of the global population living in cities by then, with more than 90 percent of the increase in developing countries. This huge shift should be an opportunity for massive gains in labor productivity, productive efficiency, environmental efficiency and human welfare. The greatest gains will be achieved where cities can reach a greater size and density so as to maximize agglomeration benefits (clusters, labor pooling etc.) Urban transport is potentially a major constraint on size and density – others include land use and regulation and the wider business environment/investment climate. Making an assessment of urban transport’s contribution to the growth of integrated, high density, highly productive, greener safer cities is a major driver for undertaking this program of evaluations even though it is clear that direct assessment of these impacts is a challenging prospect.
Global urbanization will require massive investments in improved public transport, urban planning, and car ownership and use—and in technology to reduce the need to travel. Getting urban transport systems right will be critical to address growing mobility needs, but also avoid the lock-in into unsustainable development patterns in the future. Public transit, for example, could reduce congestion, pollution and CO2 emissions. However, public transport continues to be generally far too expensive for the poorest 20 percent of people in developing country cities. Affordability is key to access, and in cities such as Sao Paulo and Rio, urban transport is beyond the reach of the 20% at the bottom of the income pyramid.

Likewise, investment in urban mobility cannot be designed and assessed without considering the broader urban planning perspective. Availability of new data on urban centers (for ex. high resolution satellite data) should allow to better capture the ex-ante the impact of these investments. For example, the impact of urban transport investments would depend on the locations of cluster of jobs within a city (many cities, especially in Africa, have only very few clusters of jobs) and on the land use/zoning regulations (in many settings land use regulations are not flexible enough to swiftly accommodate a changing urban mobility situation). From a policy perspective, it is crucially important to take into account such interactions in the design of policies that could help influence the form of rapidly urbanizing cities before they lock in into undesirable spatial patterns, especially in the context of the current urban expansion in Africa and Asia.[83]
[83] See Suzuki, H., Cervero, R. and K. Iuchi (2013) Transforming Cities with Transit: Transit and Land Use Integration for Sustainable Urban Development. The World Bank.

The program will assess the role transport plays in affecting housing and land prices, which are particularly sensitive to transport investments, and may entail gains or losses for the poor (especially for renters). There has been no experimentation on incentives for home-owners or changes in housing rental contracts to mitigate the potential negative effects of transport investments. IE work can be used to fill this gap. As discussed above, land use regulations can be a limiting factor to the impact of transport policies with the results that even well designed transport investments might not have the expected impact because of inflexible (and ill designed) land use regulations. While theory and simulations can provide some answers ex-ante to the expected response to transport investments, IEs can help to nail down the impact from an empirical point of view. For example, pilot studies (say restricted to few neighborhoods within a city) of how changes in land use regulation can facilitate the impact of changes in transport policies could provide very valuable results in terms of urban transport design.

Transport investments in cities can have important impacts in reducing search costs in labor markets. Little is known about how choices to migrate or occupational choices are influenced by transport and technology. In spite of enormous estimated gains to seasonal migration in urban areas, migrants may be deterred by such opportunities because of concerns about the skills needed in unfamiliar trades, the risks involved, specific employers they may approach in different urban areas, whether such employers are credible and have opportunities, and logistical concerns regarding temporary relocation.

The ability to target information to traditionally excluded groups such as the ultra-poor and women may have importance implications for intra-household decision-making and women’s labor force participation.
ICT-based interventions will also generate enormous amounts of information on employment choice, which may be aggregated to provide systematic information on the reputations of employers and recruiters. Such information may be used to inform potential migrants about employer quality and recruitment practices, which has been a noted hazard in the case of low-skilled migrant labor.

Finally, transport investments can generate significant environmental externalities (e.g. transport accounts for around 23 percent of GHG emissions worldwide). Policies to reduce environmental externalities have traditionally focused on investments in public transit infrastructure, prices incentives (to deter use of polluting transport modes), and regulations and restriction on vehicle use. The evidence on the impact of these policies is still far from established. For instance, it has been shown that imposing restriction on vehicle use in cities can even lead to an increase in the level of emissions (as people switch to higher emission cars). Likewise, policies that are effective in reducing emissions in city centers have to take into account the effects on suburbanization and increase of emissions in the peripheries. Amongst others, the Global Commission on the Economy and Climate, in its report “The New Climate Economy” (2014) puts great emphasis on more people living in denser, cleaner cities as a mitigation against severe climate change. Transport infrastructure facilitates larger, denser, cleaner cities – even if that infrastructure involves some emissions, the savings compared to a low density sprawl could have great environmental significance.

The program will focus on how to mitigate the emissions of transport projects (pollution, congestion, GHG). In particular, it will try to generate evidence on how to improve land use planning, logistics and ICT for reducing climate impact. In addition, policy innovations to support a shift to lower-carbon transportation modes and more efficient technologies will be tested as part of the program. This area will include a large behavioral component to understand how to nudge users on adoption of public transport and providers on adoption of energy efficient technology. Important advances will be sought also on the measurement side, as the program will contribute to properly consider the wider social costs of transport (e.g. those related to accidents, congestion and air pollution).

Theme 2: Transport Corridors
Exploiting the potential for technological leapfrogging in understanding transport-related development issues and establishing an ambitious experimental agenda to identify solutions to transport costs, safety, emissions, poverty and economic production and trade.

High-density corridors, such as highways and national roads, freight and passenger railway links, inland waterways and even airport infrastructure constitute the backbone of a country’s transport network. Optimizing the transport network by looking at spatial planning and multimodality can support more efficient supply chains, reduce on-road freight transport costs, and facilitate trade, specialization and the migration of people and productive capital for new levels of productivity and regional and global integration. Through a combination of both physical investments and policy advice, transport investments (in particular those related to road and railroad corridors, and regional integration schemes) can create an environment for better business linkages, reduction of regulatory and institutional barriers and impediments at border-crossing, increased private sector investments, and reduction in transportation costs. It is estimated that the intra-national road transport costs in Ethiopia and Nigeria are approximately 7 to 15 times larger than the freight costs between Canada and the US. Transport investments hold tremendous promise in improving the efficiency with which markets operate and promoting equality of opportunity in the developing world. Establishing how transport and communications infrastructure or technological platforms that leverage such infrastructure influence misallocation in markets and improve welfare can guide future investments and inform anti-poverty strategies.
This is especially but not solely true for land-locked developing countries (LLDC), which are indeed particularly dependent on connectivity infrastructure. On average, LLDCs’ trade costs are about 50 percent higher than the coastal economy average, and thus markedly reduce their trade volumes. Being landlocked adds four days to export transportation times relative to times for LLDCs’ coastal neighbors and lowers internet and telecommunication penetration. On average, LLDCs’ level for development is 20 percent lower than it would be were they not landlocked. Given dependence of LLDCs on neighboring transit countries, a breakthrough in LLDC trade and development demands improved regional connectivity and integration.
The program will focus on testing which interventions can make transport investments more effective in achieving impact on trade-related outcomes, such as export growth, reduction in import costs, the generation of additional import volumes, and the cost reduction in and generation of exports and domestic commerce, as well as on the degree of agglomeration (which has been shown to be correlated to increase in productivity) and the access to basic services in less developed, remote, and sparsely populated regions. Examples of these complementary policy actions include mobile technologies to crowd-source road quality information for operation and maintenance and for taking advantage of trade opportunities; incentives for business reconversion (e.g. in the trucking industry); and nudges for passengers and firms to switch to more efficient transportation modes.

Transport investments can then affect migration patterns of production and people. This includes movement from farm to non-farm employment in rural areas, or increased industrial specialization in urban areas. IE can be used to understand how transport investments can be used in guiding or accompanying the structural transformation process whereby economies gradually shift towards non-agricultural sectors. For instance, IEs could test incentives for firms to relocate to production hubs made accessible by the new or improved transport infrastructure.

Theme 3: Road Safety
Across both the urban space and transport corridors, road safety is another key area that has been largely unexplored by IE research work in developing countries. Worldwide, road traffic crashes kill more than 1.3 million people every year and severely injure another 50 million or more. 92 percent of the annual deaths are in developing countries and half are among motorcyclists, pedestrians and cyclists. In Africa, sidewalks are missing from around 65 percent of the road network, resulting in pedestrians and motorized vehicles sharing the same space and creating unsafe urban transport. Road traffic injuries are estimated to cost developing countries 5 percent of GDP, or more than $1 trillion a year. Road traffic accidents are a key obstacle to economic development and a burden on public health. The World Health Organization (WHO) forecasts that in 2015, road accidents will be the main cause of premature death and physical disability for those aged five or more.

Although road traffic accidents are a leading cause of death and disability among young adults, there are still few rigorous impact evaluations looking at the effectiveness of road safety interventions. In addition, and despite the fact that most of the causalities are in low and middle-income countries, studies available are highly concentrated in developed or high-income countries. Research will focus on four subareas: infrastructure, institutional and normative aspects, human factors, and vehicles. While the impact evaluation literature has focused on safety education, little evidence is available on regulatory safety standards for vehicles, institutional and normative frameworks, and incorporating road safety elements in infrastructure projects. In addition, very little is known about how interventions work for different people, either based on income or place of residence or gender of the target population. For this work, key outcome indicators include fatal and non-fatal accidents, injury accidents, speed tickets, changes in behavior and cognition (crossing roads, perceptions, intentions to speed, selecting safe routes, knowledge about safe behaviors), speed of vehicles, and costs of accidents.

The types of data required include data on fatal and non-fatal accidents that comes from a specific reporting system, such as the Fatality Analysis Reporting System (FARS), which contains detailed information on all fatal motor vehicle crashes occurring on public roads in the United States; or it could come from insurance companies; geographic conditions and roads conditions; municipality or local-level panels of the number of cars investigated by police patrols and the number alcohol-related driving offenders separated by driving under alcohol influence (DUI), drunk driving, and driving in deficient conditions, provided by a Criminal Analysis Office, Police, or others; and economic and public health variables.