## Logframe detail - Table 1
Building Core Systems in Sierra Leone
IMPACT | Impact Indicator 1 |  | Baseline 2015 | Milestone Dec 2016 | Target Dec 2017
Broad-based economic growth and prosperity | Annual rate of real non-iron ore GDP growth | Planned | 1% | 3.3% (2016) | 4% (2017)
Achieved
Source
IMF ECF reviews and Government of Sierra Leone / IMF projections
| Impact Indicator 2 |  | Baseline 2011 | Milestone Dec 2016 | Target Dec 2017
| Poverty headcount (national poverty line) | Planned | 52.9% | 44.7% | 43%
Achieved
Source
Integrated National Household Survey
OUTCOME | Outcome Indicator 1 |  | Baseline | Milestone Dec 2016 | Target Dec 2017 | Assumptions
Strengthened core budget systems and improved performance | Improved budget credibility (DLI1 2016 and 2017) | Planned | Variance in expenditure composition between actual and originally budgeted primary expenditure (PI-2) was 26.1% for 2015 performance (against a PAF target of 15%). The previous legal limit on contingencies was 10% of revenue. | Provisional variance in expenditure composition between actual 2016 and originally budgeted primary expenditure (PI-2) is <26.1% | Variance in expenditure composition between actual and originally budgeted primary expenditure does not exceed 20% and spending on contingency (pro rata at end of August) is within the amount approved by Parliament (i.e. 2% of non-extractive revenue) | Government of Sierra Leone (GoSL) retains commitment to improved economic and public financial management. DLIs for 2016 and 2017 are mutually agreed by DFID and GoSL. DFID performance payments provide incentive. Sufficient buy-in from Government stakeholders to undertake actions necessary for the achievement of the DLIs. Economic revenue growth remain in line with IMF forecasts and there no major external shocks. GoSL contingent liabilities are adequately understood and don’t disrupt budget execution. Processes and systems can be developed to effectively control budget execution and public sector wage bill. Tax administration reforms typical of the PFMICP and R4P have started have some impact on revenues. PFMICP and BCS programme technical assistance contributes to accelerated improvements in budget planning, credibility and execution.
|  | Achieved |  | 39% provisional
Source
PAF Review / UK DLI technical note
| Outcome Indicator 2 |  | Baseline 2015 | Milestone Dec 2016 | Target Dec 2017
| Domestic revenue collection (DLI2 2016 and 2017) | Planned | 120,122 million Leones of domestic GST was collected between Jan and June 2015. 2,359 bn Leones in total revenue (excluding extractives revenue) projected for the period July 2015 to June 2016. | Domestic GST increases by 15.6 bn Leone in first half of 2016 compared to same period of 2015. | Total revenue (excluding from extractives) increases by 454.886* billion Leones compared to same period (Jan - June) in 2017 *The exact value of the target is subject to change following IMF ECF program negotiations in Feb 2017
|  | Achieved |  | 15.1bn
Source
PAF Review / UK DLI technical note
| Outcome Indicator 3 |  | Baseline | Milestone Dec 2016 | Target Dec 2017
| The public sector wage bill for 2017 is reduced to X% of the forecast revenues and spending by end Q2 2017 is on track against budget (DLI4 2017) | Planned | X=65% for 2016 budget | X=60% for 2017 budget | No more than 50% of budgeted amount for wages and salaries has been spent in Q1 and Q2.
|  | Achieved |  | 50.28%
Source
PAF Review / UK DLI technical note
| Outcome Indicator 4 |  | Baseline | Milestone Dec 2016 | Target July 2017
| Sierra Leone on track with IMF programme (DLI4 2016) | Planned | 3rd and 4th Review completed.5th review ongoing at time of writing. | 6th review of Sierra Leone’s extended credit facility approved by IMF Board. | Successor IMF programme negotiated and agreed.
|  | Achieved |  | Met
Source
IMF Staff assessment
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£)
| FA (£20m) + TA (up to £5m) |  | NA | NA | 25 million | RISK RATING: High
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | Milestone Dec 2016 | Target Dec 2017 | Assumptions
Well-developed and well-executed national budget | Budget data and monitoring | Planned | Lack of consolidation and monitoring of budget data, resulting in ill-informed budget preparation process and eroding budget credibility | Prototype dashboard established using consolidated information from Access data, FMIS and Budget Book | MoFED conducting quarterly in-year analysis on budget execution An automated budget execution process (commitments and purchase orders without manual PET 1 and PET 2 forms) is designed and approved, ready for roll-out with current IFMIS | GoSL retains commitment to a well-developed and well-executed national budget. MDAs cooperate with MoFED on sharing of budget data. MoFED and BB have sufficient human resources available to carry out regular analysis. PFMICP project coordinate IFMIS upgrades with BCS project team
|  | Achieved |  | Met
Source
PAF Review, MoFED
| Output Indicator 1.2 |  | Baseline | Milestone Dec 2016 | Target Dec 2017
| Orderly budget process | Planned | No formal budget calendar, resulting in late budget formulation and key decisions taking place in new financial year and contradicting the PFM Act | Indicative budget calendar for formulation of 2018 budget approved by MoFED | 2018 Budget formulated in line with budget calendar 2018 MTEF and MTFF planning incorporates revenue, fiscal and wage-bill forecasts and scenarios
|  | Achieved |  | Met
IMPACT WEIGHTING (%) |  | Source |  |  |  | RISK RATING: Medium
25% |  | PAF Review, MoFED
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | Milestone Dec 2016 | Target Dec 2017 | Assumptions
Better processes and increased capacity for management of the public sector wage bill | Wage bill data and capacity for analysis increased | Planned | Inconsistent wage bill data between HR systems and general ledger. No comprehensive, detailed analysis of payroll. | Automated payroll system established and piloted for for 75% of sub-vented agencies who have provided data Total 2017 wage-bill budget compiled and analysed in relation to achieving 2017 DLI | 2018 budget developed using newly developed wage-bill templates and model Budget analysts trained to routinely track wage-bill expenditure and analyse the underlying causes for variations using Tableau Software, and they are applying this to track 2017 FY wage-bill spending. | Government of Sierra Leone committed to increase sustainability of wage bill/salaries - avoiding wage increases in the absence of commensurate increases in revenue BCS project continues to get access to different data sources and can procure Tableau Software MoFED and BB have sufficient human resources available to carry out regular analysis Adoption of paper on medium term-wage policy by Cabinet
Achieved
IMPACT WEIGHTING (%) |  | Source
20% |  | PAF Review, MoFED |  |  |  | RISK RATING: Medium
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | Milestone Dec 2016 | Target Dec 2017 | Assumptions
Improved transparency and more competition in national procurement | NPPA website functioning and contracts are uploaded (DLI3 2016 and 2017) | Planned | No contracts are uploaded and website doesn't function to allow this | Full details of 24 contracts above the national competitive bidding threshold are uploaded to website | 60% of the total value of public sector contracts are uploaded 2 months after received by NPPA and method of competition declared. And details published as part of 2016 DLI are still on the website. | GoSL retains commitment to increasing transparency and competition in national public procurement Procurement data is collected in a timely manner (funding is made available for data collection exercises) PFMICP and BCS programme technical assistance contributes to accelerated improvements in procurement DLIs remain constant; any changes to be reflected in logframe outputs Political push for an effective ECMC and MoFED oversight of public procurement remains
|  | Achieved |  | Exceeded
Source
NPPA website, UK DLI technical note
| Output Indicator 3.2 |  | Baseline - 2014 | Milestone Dec 2016 | Target Dec 2017
| Processes and capacity for national procurement enhanced, including empowering MoFED to detect and prevent contracts representing poor VFM being signed | Planned | Procurement law passed, but not yet reflected in processes. ECMC does not function, which limits MoFED's power to prevent poor contracts being signed. | Selected procurement regulations ammended and harmonised with new Procurement Act, internally approved by NPPA | Procedures developed and implemented for how requests for award certificates are received, reviewed and reported on by the Expenditure and Contract Management Committee (ECMC)
|  | Achieved |  | Met
IMPACT WEIGHTING (%) |  | Source |  |  |  | RISK RATING: Medium
25% |  | PAF Review, MoFED and NPPA
OUTPUT 4 | Output Indicator 4.1 |  | Baseline | Milestone Dec 2016 | Target December 2017 | Assumptions
Better processes and increased capacity for macroeconomic management | Improved processes and capacity for fiscal strategy and risk management | Planned | No Fiscal Strategy Statement, limiting Cabinet and government's ability to credibly plan within and influence available fiscal space Key fiscal performance indicators (including DLIs, IMF Performance Criteria etc) are inadequately monitored resulting in targets being missed | Pilot Fiscal Strategy Statement produced by MOFED MoFED are conducting in-year and ongoing monitoring of key fiscal performance indicators (inc DLIs, IMF PCs) | Development of a medium term fiscal framework for the EPRU MoFED adopt Fiscal risk framework and update it in 2017 to improve policy making | GoSL retains commitment to current IMF programme Government of Sierra Leone and IMF negotiate new programme EPRU has sufficient human resources available to carry out regular analysis Commitment to future fiscal planning remains despite short-term pressures
Source
PAF Review, MoFED
| Output Indicator 4.2 |  | Baseline | Milestone Dec 2016 | Target December 2017
| Improved processes and capacity for fiscal forecasting | Planned | Basic macroeconomic forecasting model in place though outputs are limited. Significant alteration is required to update estimates, such as inflation. Its limited use can undermine credibility when outputs are challenged externally (i.e. the IMF). | Macro model updated to accommodate deflator (by sector), inflation and terms of trade | Fiscal Strategy Paper incorporates analysis from updated macro model to improve budget planning and prioritisation within available or expected resources
|  | Achieved |  | Met
IMPACT WEIGHTING (%) |  | Source
20% |  | PAF Review, MoFED |  |  |  | RISK RATING: Medium
OUTPUT 5 | Output Indicator 5.1 |  | Baseline | Milestone Dec 2016 | Target Dec 2017 | Assumptions
Better processes and increased capacity for revenue policy, coordination and collection | Revenue data and monitoring | Planned | Lack of consolidation and monitoring of revenue data at ministerial, department and agency (MDA) level meaning there is incomplete information on total revenue and links to budgeting are missed | NRA's MDA revenue data shared with and analysed by MoFED Total revenue data tracked at NRA and MoFED for progress towards DLI | Initial forecasts of MDA revenue established and input into the overall macro revenue forecast. Reporting tool for MDA revenue monitoring adopted by MoFED and circulated to MDA budget officers | GoSL retains commitment to better processes and increased capacity for revenue policy, coordination and collection MDAs and NRA cooperate with MoFED on sharing of revenue data. MoFED has sufficient human resources available to carry out regular analysis Tax administration reforms as part of R4P support improved revenue reporting from NRA.
|  | Achieved |  | Met
IMPACT WEIGHTING (%) |  | Source
10% |  | NRA and ASI consultants working on DFID-funded R4P in NRA / UK DLI technical note |  |  |  | RISK RATING: Medium