Project Completion Review

Title: Food and Agriculture Organization (FAO): Core Assessed Contribution 2018-19
Final Programme Value £ (full life): £33,889,015.60		Review Date: June 2020
Programme Code: 204148-101	Start Date: January 2018	Final End Date: December 2019

Summary of Programme Performance

Year	2019	2018
Programme Score	A	A
Risk Rating	Major	Major

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/40280111.odt
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-204148

A. Summary and Overview

Description of programme and what it has achieved
This Project Completion Review covers the UK’s core assessed biennial (2018-19) contribution to FAO of $12,078,303.24 and €8,372,487.63, which is equivalent to approximately £17 million each year, subject to exchange rates at the time of payment. The total contribution for the biennium which has now been fully disbursed is £33,889,015.60. This represents 4.64% of the total assessed budget funded by all Member States. This does not include the additional voluntary contributions from DFID country offices for specific projects, including for FAO’s emergency response work.
FAO is a specialised UN agency that leads on food and agriculture in the UN system. An intergovernmental organization, FAO has 194 Member Nations, two associate members and one member organisation, the European Union. In June 2019, FAO’s supreme governing body, the FAO Conference, elected a new Director-General, replacing José Graziano da Silva (Brazil) after his second and final term. The (now former) Chinese vice minister of Agriculture, Dr Qu Dongyu, was the clear winner (108 votes against 71 for the French candidate) and took up office on 1 August 2019, starting his first term of four years (renewable once) .
FAO’s goals are: the eradication of hunger, food insecurity and malnutrition (Sustainable Development Goal - SDG2); the elimination of poverty and the driving forward of economic and social progress for all (SDG1); and, the sustainable management and utilisation of natural resources. Its work covers global normative standard-setting, including on food safety and plant health, and facilitation of international treaties; policy and technical support; and emergency response.
After a decade of progress, reporting over the last two years show that the world is off-track to meet SDG 2 and eradicate global hunger. More than 820 million people or 11% of the world population are hungry or undernourished (facing severe and chronic food insecurity), and 2 billion people, or 26.4 % of the world population are facing moderate or severe levels of food insecurity (SOFI Report 2019). This underscores the challenge of achieving the SDG 2 target by 2030 with much of this deterioration attributed to the rising number of conflicts worldwide, drought and disasters linked to climate change and poor economic performance. In addition, the impact of COVID-19 risks increasing the number of food insecure people.
This review examines progress against FAO’s output targets for 2018 and 2019 and finds that FAO met expectations for its output targets for the 2018-2019 biennium and thus the PCR scores FAO’s performance at ‘A - outputs met expectations’. FAO has clearly not yet achieved its overarching goals, linked to the SDGs. On the contrary, SDG2, in particular, is off-track with progress in reverse. Through the development of FAO’s new strategic framework, FAO will have the opportunity with its membership to review priorities as it aims to step up delivery of results for greater impact towards achieving its goals. In contributing to the overarching Sustainable Development Goals, this will also require more effective coordination and partnership across the international architecture for food and agriculture. This review was compiled and completed in June 2020.
The UK core assessed contribution (together with those of other member states) supports FAO’s Regular (core assessed) Budget, which provides a minimum guaranteed amount of resources that can be committed for priority activities agreed upon by member countries in the governing bodies. It is complemented by significant voluntary (earmarked) contributions to support the achievement of FAO’s Strategic Objectives. Of the total FAO Budget of USD 2.6 billion, 39 percent – or USD 1,005,635,000 - comes from core assessed contributions that member states are required to pay, and 61 percent is mobilised through voluntary contributions from Members and other partners. While the regular budget has maintained a zero-nominal growth in the past two biennia, the amount of voluntary contributions is moderately increasing.
FAO’s assessed or Regular Budget supports core functions of the organisation. Approximately 75% is spent on the technical and support staff who develop and oversee the range of tools, expert advice and global normative, standard-setting work that underpin FAO’s work on food, agriculture and rural poverty in developing countries. The assessed budget also covers central administrative functions, such as Human Resources, Information Technology and Security.
The FAO Programme Implementation Report (PIR, document C2021/8) finds that in 2018 and 2019 FAO fully met 95% (41) of its 43 output indicators targets, while 5% (2) were not achieved. The PIR also assesses the outcomes achieved and describes a generally positive trend. However, as mentioned above, the 2019 State of Food Insecurity report (SOFI) suggests that FAO’s goals may not be met. This raises aquestion around the theory of change that is set out in FAO's Strategic Results Framework (SRF) and underlines the importance of strengthening FAO’s Strategic Results Framework as the Organisation develops a new Strategic Framework for 2022 and beyond under new Director General Qu, as recommended in the 2018 Annual Review.

Recommendations

PCR Recommendation 1: UKREP Rome to update the proportion of the UK core contribution to FAO in 2020 and 2021 that is attributed to UK climate funding is lowered to 10%; and that ICF KPI 11 is incorporated into the logical framework for the UK core contribution to FAO in 2020 and 2021.

PCR Recommendation 2: UKREP Rome to press FAO to follow up its recent staff survey findings on Sexual Exploitation, Abuse and Harassment and to explore in more detail why staff have concerns around the handling of sexual harassment and revise policies and processes appropriately.

PCR Recommendation 3 UKREP Rome to scrutinise FAO’s HR Strategic Action Plan to be submitted to Finance Committee in November 2020, and include indicators to monitor progress in the logical framework for the UK contribution in 2020 and 2021
#### PCR Recommendation 4: UKREP Rome should continue to press management to implement outstanding recommendations made in the 2018 Annual Review (see Section G) and in particular, UKREP Rome should continue to encourage FAO to strengthen its Strategic Results Framework (SRF), its theory of change and improve the design and methodological transparency of results indicators so that they can be used to monitor the organisation’s progress, learn from experience and hold FAO to account.

## B: DETAILED OUTPUT SCORING

Output Title	Leadership and Collaboration - Greater collaboration, particularly with WFP and IFAD (the Rome-based agencies - RBAs) and strengthened coordination mechanisms for risk reduction and crisis management
Output number per LF		1	Output Score	A
Impact weighting (%)?		25	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
1.a Rome-based Agency (RBA) Collaboration	FAO undertakes joint needs assessments and country-level mapping with a target of developing at least three joint country strategies with IFAD and WFP	Milestone moderately did not meet expectation / FAO conducts joint needs assessments in emergency situations with WFP. FAO has also taken forward the use of the Food Insecurity Experience Scale (FIES), supporting the broader use of this tool globally in monitoring and measuring, which is positive. However, systematic collaboration between the three RBAs at country level is still very much work in progress. The November 2019 Joint RBA Progress report identifies three countries (Niger, Colombia, and Indonesia) where FAO, IFAD and WFP are working together to develop joint country strategies. FAO reports that the work is well advanced in all three countries and the aim is to have a final draft of the three RBA joint country plans in the second semester of 2020, providing the COVID-19 situation permits. / Reporting also notes that the three joint country strategies will be framed within the UNSG’s reforms to the UN Development System and, in particular, within the relevant UN Sustainable Development Cooperation Frameworks. The strategies will advocate for placing food security, nutrition and sustainable agriculture high on the UN Country Teams’ Agenda. (source: http://www.fao.org/3/na938en/na938en.pdf) / This is progress, but it required Member States pushing for joint strategies in governing bodies of the three agencies, even to deliver the minimal number of three. They are not yet complete, which accounts for the milestone moderately not meeting expectations. It is hoped that agencies will build on this for the future in developing truly joint strategies, going beyond bringing together existing individual strategies to ensure maximum synergies and complementarities between the different agencies’ work.
1.b Humanitarian Collaboration / Crisis management – / Number of countries or regions that improved resource mobilisation and coordination mechanisms for risk reduction and crisis management as a result of FAO support (FAO Output 5.1.2) / Emergency preparedness / Number of countries benefiting from FAO support to uptake standards, guidelines and practices for hazard and sector specific emergency preparedness (FAO Output 5.4.1).	Target 2018-2019 – 35 / Target 2018-2019 – 27	Met expectations – and surpassed targets / Actual 2018-2019: 43 (source: FAO PIR 2018-2019) / Actual 2018-2019: 41 (source: FAO PIR 2018-2019)
1.c Climate Change Leadership - Number of strategy documents on sustainable agriculture, forestry and fisheries developed through cross-sectoral policy dialogue, related to 2030 Agenda and NDC implementation plans / (FAO Output 2.2.2).	Target 2018-2019 – 40	Met expectations and slightly surpassed target / Target 2018-2019 – 43 (source: FAO PIR 2018-2019)

Provide supporting narrative for the score
Overall, progress with the indicators for this outcome has met expectations, with two targets achieved out of three. Despite not meeting the target for output 1.a, collaboration with IFAD and WFP has improved overall, and the targets for outputs 1b and 1c were exceeded.

Under output 1a, three joint (FAO, IFAD and WFP) country strategies are being developed in Colombia; Indonesia; and Niger. However, these strategies have not been completed and thus progress moderately did not meet expectations. Joint RBA steering committees have been established at country level and FAO expects the joint strategies to be completed in 2020.

FAO, IFAD and WFP are also developing a joint plan of action for the Sahel. It aims to scale up their collaboration in addressing food security and livelihood issues of vulnerable populations. The plan is framed within the United Nations Integrated Strategy for the Sahel (UNISS) – the principal UN vehicle for contributing to the 2030 Agenda for Sustainable Development in the Sahel. The RBA teams are currently working on supplementing the high-level plan with a set of concrete complementary, measurable actions in the region.

On collaboration more generally, FAO has engaged, with IFAD and WFP, in the repositioning of the UN Development System which will support collaboration with other UN entities as part of the new UN Sustainable Development Cooperation Framework (UNSDCF) mechanism. FAO also paid its increased contribution to funding the reinvigorated Resident Coordinator system ($4.7m) which became effective on 1 January 2019. The leadership of new Director-General Dr Qu Dongyu (China) will determine FAO’s future approach to RBA collaboration and the wider reforms of the UN Development system. While DG Qu has been in office for less than a year, there are early signs that FAO will embrace reforms to the UNDS such as FAO’s staff guidance for its country partnership frameworks (CPFs) which FAO has recently updated to ensure CPFs are aligned with UNSDCFs. UKREP Rome will continue to press FAO to implement its commitments to collaboration with IFAD and WFP as well as to the UNSG’s reforms to the UN Development system as recommended in the 2018 Annual Review.

FAO has moderately exceeded the planned targets for the other two indicators 1.b and 1.c as reported in FAO’s Mid-Term review (MTR) which was published in March 2019. FAO’s work to improve humanitarian collaboration (output 1.b) has benefitted from FAO capacity building around emergency preparedness as a priority, and feedback from DFID Country Offices in 2019 suggests they value FAO’s mechanisms for risk reduction and crisis management.

As well as exceeding the target for output 1.c, Climate Change Leadership, FAO has achieved or exceeded 36 of the 43 output targets set for 2018-2019 in FAO’s Climate Change Strategy. FAO’s Programme Implementation Report 2018-2019 (PIR) reports that FAO has mobilised USD1.22 billion in climate finance for its member countries.

Lessons identified this year linked to this output and recommendations for future programmes

For the first time in 2018 and 2019, 15% of the UK’s core contribution to FAO was attributed to the International Climate Fund (ICF). 15% was the proportion of FAO’s regular (i.e. core) budget which we estimated ex-ante would be spent on activities significantly associated with climate change. The FAO PIR reports (ex-post) that this proportion was 9.34%.

Also for the first time in 2019, UKREP worked with FAO to calculate which and what proportion of FAO’s climate change results could be attributed to the UK ICF. Using the ICF methodology we were able to attribute £30 million of the USD1.2 billion that FAO mobilised to ICF Key Performance Indicator 11, “quantity of public finance mobilised”.

PCR Recommendation 1: UKREP Rome to ensure the proportion of the UK core contribution to FAO in 2020 and 2021 that is attributed to climate funding adjusted from 15 to to 10% to reflect FAO reporting; and that ICF KPI 11 is incorporated into the logical framework for the UK core contribution to FAO in 2020 and 2021.

Output Title	Effectiveness - FAO follows best practice in seeking value for money; its accountability and fiduciary frameworks are strengthened. FAO enforces a zero-tolerance approach towards fraud and SEA.
Output number per LF		2	Output Score	A
Impact weighting (%)?		25	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
2.a - Following best practice / Implementation of audit and evaluation recommendations within agreed timeframes measured by: / Evaluation / Percentage of recommendations of strategic evaluations where the agreed management response has been completed by the due date (FAO kpi 10.3.b) / Audit / Percentage of high-risk audit recommendations which have been completed by due date (FAO kpi 10.3.c) / Percentage of long outstanding audit recommendations (i.e. above 24 months) (FAO kpi 10.3.d)	Target 2018-19 - 90% / Target 2018-19 - 80% / Target 2018-19 – below 10%	Met expectations overall / 2 of the sub-indicators under 2.a have fully achieved the target, 1 has not been achieved. / The percentage of evaluation recommendations where the agreed management response has been completed by the due date was 100%, exceeding the target of 90%. / The percentage of high-risk audit recommendations which have been completed by due date was 87%, exceeding the target of 80%. / The percentage of long outstanding audit recommendations stands at 12%, thus did not achieve the 10% target. / (source: FAO PIR 2018-2019)
2.b Anti-fraud action plan / Development of FAO comprehensive fraud risk assessment and anti-fraud action plan in accordance with Joint Inspection Report (JIU) report JIU/REP/2016/4 Recommendations 5 and 6.	FAO management reports to FAO Finance Committee on JIU/REP/2016/4 recommendations 5 and 6 in November 2018.	Met expectations / FAO launched a corporate Anti-fraud Strategy and related Action Plan in October 2018, as recommended by the JIU. / FAO is currently in its second year of implementing the action plan, building on the efforts initiated in 2018 and reports that it is: / strengthening fraud risk awareness and management capacity in fraud sensitive areas. / introducing new, risk- based Fraud Prevention Plans across all locations. / strengthening the related tools, corporate policies and procedures.
2.c SEA action Plan / Submission to Council and implementation of strengthened FAO action plan to prevent and respond to sexual exploitation and abuse (SEA).	FAO Management to provide annual reports under a stand-alone item to the Council, through the Joint Meeting of the Programme and Finance Committees, on the progressive implementation of the Action Plan and updates as required on FAO policies, starting with the November 2018 session of the Joint Meeting.	Met expectations / Following requests from the UK (and other members), FAO presented an action plan and progress report to Council in December 2018. FAO issued a further “Annual Report on Corporate Policy, Processes and Measures on the Prevention of Harassment, Sexual Harassment and Authority Abuse including results of staff satisfaction survey” to Council in December 2019.

Provide supporting narrative for the score

Progress with the indicators for this outcome has met expectations overall. Under Output 2a, FAO reports that it has exceeded the targets for its KPIs related to the implementation of audit and evaluation recommendations overall in 2018 and 2019. However, FAO just missed the target for addressing long outstanding audit recommendations. FAO reports that this is because of changes to the timelines for implementation agreed with the Office of the Inspector General. It is worth noting that a significant internal audit recommendation to improve FAO’s implementation of its HR recruitment roster is still outstanding but should be addressed with the development of a new HR policy under the leadership of a newly appointed HR Director by Director General Qu, who took up post in August 2019.

FAO also reports that total audit coverage achieved was 75% compared to a target of 90%, mainly due to resource constraints and staff vacancies in the Office of the Inspector-General (OIG). The UK continues to work with other FAO members to press FAO management to increase the resources available to the OIG.

Under Outputs 2b and 2c, FAO has issued action plans to tackle 2b] fraud and 2c] sexual exploitation, harassment and authority abuse (SEAH) and met expectations for both indicators.

The FAO has introduced new anti-fraud plans across its network. The new fraud plans were rolled out for decentralised offices in 2019. In September 2019, 13 of 139 plans had been validated by regional offices, with five under approval, and 22 under preparation. For HQ offices, 23 of 44 plans have been approved by the relevant oversight unit, with 10 under approval, and 11 under preparation. FAO’s Audit Committee noted (in its 2019 Annual Report) the progress with the implementation of FAO’s Policy against fraud and other corrupt practices. It particularly welcomed FAO’s “tone-at-the-top” reconfirmed by the Director-General’s message to staff on the occasion of the Anti-Corruption Day on 9 December, 2019.

In 2019, FAO separated its SEAH action plan into two plans on: Sexual Harassment; and Sexual Exploitation and Abuse respectively. Following requests from FAO Council and advice from FAO’s external auditors, FAO management strengthened action in both plans to clarify accountability for the actions. A number of the planned actions have been implemented, including strengthened reporting capabilities, improved awareness raising and learning both through compulsory training, face to face sessions for managers and reinforced communications. FAO Council members, including the UK, have requested FAO to conduct staff surveys on a regular basis and to monitor progress with a Key Performance Indicator in FAO's results framework. FAO is following up on these requests under the leadership of new DG Qu. Indeed, for the first time, FAO conduced a staff survey in December 2019 which is scheduled to be repeated biennially. It asked staff about their experience of harassment, sexual harassment and authority abuse and the overall results of the ‘2019 FAO Employee Satisfaction Survey’ were shared with Members transparently in May 2020. Responses to the question: “Were you subjected to harassment, sexual harassment, discrimination, abuse of authority or any biased treatment at FAO, within the past two years?” showed that: among men and women the most common forms of misconduct experienced were abuse of authority and non-specific misconduct. Other frequent forms for women were: discrimination/bias on gender identity/sex/sexual orientation, sexual harassment, and age. Other frequent forms for men: harassment based on ethnicity/nationality/language and age.” Less than 30% said they reported the incidents, with those who did not report noting that it was because ‘they thought nothing would be done anyway, they were afraid of retaliation, and investigations are not anonymous (potentially jeopardising their jobs)’. As with many Organisations, the recent survey shows that underreporting of SEAH remains a challenge and suggests that the prevalence of SEAH is much higher than the low levels of allegations reported by FAO’s Office of the Inspector General.

FAO is taking steps to address. FAO’s Audit Committee annual report submitted to the Finance Committee in May 2020 notes “improvements to FAO’s corporate policies, processes and measures on the prevention of harassment, sexual harassment and authority abuse; and issuance of a revised Whistleblower Protection Policy”. A new, stronger Key Performance Indicator (KPI) 10.3.F (Percentage of FAO staff who agree that FAO has effective policies, processes and procedures to address harassment and other unacceptable behaviour) is presented in the document Further Adjustments to the Programme of Work and Budget 2020-21 (CL 164/3) to be submitted to Council for agreement in July 2020. Following FAO’s Employee Satisfaction Survey, FAO is establishing a Task Force to prepare a corporate action plan, with actions cascaded and each Head of Office/Director to champion regional/divisional working groups and action plans in an effort also to tackle the issues within the Organisation that do not foster the creation of an environment where people feel able to speak up – creating a new culture of reporting in FAO will clearly be key.

Lessons identified this year, and recommendations for the year ahead linked to this output

Safeguarding staff and beneficiaries from sexual harassment, exploitation, or abuse is a high priority, complex area that the entire development community is working to address. FAO has introduced positive changes (including training, a staff survey that includes questions on sexual harassment and abuse, new policies, and roll-out of risk assessments of programme activities). These are in the very early stages and need additional work before becoming fully effective.

As recommended in earlier reviews, UKREP Rome has continued, and will continue, to work with other member states to encourage FAO to strengthen its work to prevent and respond to sexual harassment, exploitation and abuse of staff and beneficiaries, including work to encourage staff and others to report their concerns. This has resulted in much greater focus on the issue in governing body meetings in 2018 and 2019. Nonetheless underreporting remains a challenge.

PCR Recommendation 2: UKREP Rome to press FAO to follow up its recent staff survey findings on SEAH and to explore in more detail why staff have concerns around the handling of sexual harassments and revise policies and processes appropriately

Output Title	Accountability, Efficiency and Transparency - FAO to make a step change in accountability and transparency to Member States, funders, beneficiaries and the public, with better value for money for taxpayers.
Output number per LF		3	Output Score	A
Impact weighting (%)?		25	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones	Progress
3.a Accountability / Implementation of governing body decisions within prescribed deadlines (FAO Output 10.1.b). / Completion of a SIC report which is reported on annually and appended to FAO’s annual accounts (FAO kpi 11.2.a).	Target 2018-2019 - 90% / Target 2018-2019 – 1 / Unmodified external audit opinion (annual)	Exceeded expectations, with full implementation reported. In some areas, actions will need ongoing support to be fully embedded. / Actual 2018-19 – 100% / Implementation by Management of Council decisions was facilitated by means of an effective tracking system, and through regular reporting to Council on progress, resulting in full (100%) implementation of its 56 decisions during the biennium / Actual 2018-19 – 1 / (source: FAO PIR 2018-2019)
3.b Transparency / Project-level expenditure data published to IATI standards to continue on a quarterly basis (FAO Output 10.2.b).	Quarterly reporting to IATI throughout the biennium and annual report of expenditure to OECD.	Milestone met expectations - The latest data uploaded on IATI website in March 2020 / https://iatiregistry.org/dataset/fao-activity

Provide supporting narrative for the score

This output has met expectations and is scored A in this review, following the action taken by new FAO Director General Qu on his arrival in August 2019 to strengthen the independence of FAO’s Office of the Inspector General.

Despite FAO being on track to meet its accountability and transparency targets under Output 3a, serious concerns were raised about accountability and transparency by the FAO Audit Committee Chair’s letter of 28 July 2019, shared (alongside the outgoing DG’s response) with FAO Council members on 2 August. During an investigation of allegations raised against a senior official of the organization, the Audit Committee was not able to provide assurance that the FAO’s investigation function was operating in an independent manner. The letter also noted that an interim OIG was appointed by the DG, without consultation with the Finance or Audit Committees. The appointee was not independent (as an existing FAO employee) and was not a trained and qualified audit or fraud professional. On his arrival in August 2019, the DG appointed a second interim Inspector General and selected a highly qualified candidate but did not follow a competitive process. Since then, a qualified Inspector General has been appointed following a competitive process and approval by the FAO Finance Committee. The FC has also approved revisions to the charter of the Office of the Inspector General to further strengthen its independence.

Lessons identified this year, and recommendations for the year ahead linked to this output

As the process of appointing an interim Inspector General illustrates, HR management remains an area that needs further improvement at FAO. As noted above, internal audit recommendations on FAO’s recruitment process remain outstanding. In its 2018 assessment of FAO, the Multilateral Organisation Performance Assessment Network (MOPAN) also raised concerns about FAO human resource management and found that FAO’s change management lacked sufficient consultation and transparency, resulting in reduced staff morale and a lack of continuity in programme management. The new FAO Director General has recently appointed a new Director of HR who is preparing a detailed HR Strategic Action Plan to improve human resources management. The Finance Committee discussed this at its meeting in June 2020 and, as the Report notes: “the Committee welcomed the information provided on preparation of a detailed HR Strategic Action Plan with specific timelines and results to be achieved to improve human resources management and looked forward to reviewing the HR Strategic Action Plan at its next session in November 2020; encouraged Management to continue improving the information presented in future reports, including through an annual update on benchmarks and progress made on the HR Strategic Plan in line with other strategic documents and annual reports;
encouraged Management in its continued efforts to enhance the Organization’s human resources functions, including as regards: i) streamlined and merit-based selection and recruitment processes and procedures, taking into consideration equitable geographical representation both for staff and consultants; ii) further measures for the promotion of gender parity in the Organization, in particular in senior level positions; iii) staff development and learning initiatives; and iv) measures to enable strengthened employee engagement;

PCR Recommendation 3 UKREP Rome to scrutinise FAO’s HR Strategic Action Plan to be submitted to FAO’s Finance Committee in November 2020 and include output indicators to monitor progress over the 2020 - 2021 biennium.

Output Title	Performance, results and impact / FAO incorporates gender and nutrition objectives into its country programming frameworks; produces and disseminates high quality and internationally comparable food and agriculture statistics including for the 21 SDG indicators for which FAO is custodian; reports the results achieved from its work to improve national responses to cross border threats to food security and global health security, such as the threats posed by Fall Armyworm and Antimicrobial Resistance.
Output number per LF		4	Output Score	A
Impact weighting (%)?		25	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
4.a -Gender Number of performance standards of revised UN SWAP on gender equality and the empowerment of women met or exceeded by FAO (FAO kpi 6.3.b).	Target – 2018-19 – 10	Met Expectations and surpassed target / The indicator was revised in 2018 (UN-SWAP 2.0) to introduce new performance standards increasing their total number to 17 and upgraded the existing ones. At the end of 2018, FAO met or exceeded 13 out the 17 (one indicator does not apply to FAO) performance indicators, already exceeding the biennial target of 10 for 2019. / By the end of 2019, FAO had met or exceeded 15 out of 16 UN-SWAP indicators, thus exceeding the biennial target of 10 originally set / (source: FAO PIR 2018-2019)
4.b -Nutrition Progress made in incorporating nutrition concerns, considerations and objectives into Country Programming Frameworks and in developing capacities of FAO staff to assist governments in mainstreaming nutrition (FAO kpi 6.5.b).	Target 2018-19 - 25%	Met Expectations, significantly exceeding target / Actual – 2018-19 – 74% / (source: FAO PIR 2018-2019)
4.c -SDGS / Support provided to strengthen the capacity of national statistical systems to collect, analyse and disseminate food and agriculture statistics, including the 21 SDG indicators for which FAO is custodian. Measured by: Proportion of SDG indicators under FAO custodianship reported at national level in accordance with the Fundamental Principles of Official Statistics (ref. SDG 17.18.1 (FAO kpi 6.2.a).	Target 2018-19 - 40%	Met Expectations / Actual 2018-19 – 43% / (source: FAO PIR 2018-2019)

4.d -Cross-border threats to food security including FAW number of regions and countries that have improved threat monitoring mechanism/systems to enhance delivery of early warnings as a result of FAO support (2018-19) (FAO Output 5.2.1).	(Target 2018-2019 – 56)	Met Expectations / 57 countries or regions have improved threat monitoring mechanisms/ systems to enhance delivery of early warnings because of FAO support

4.e – AMR, Global health Implementation of FAO AMR action plan.	Progress report against FAO Action Plan submitted to the Programme Committee in 2018; evaluations of national plans for surveillance implemented.	Met expectations / A progress report on FAO’s AMR action plan was prepared for the Programme Committee in 2018 and the PIR reports that FAO has assisted 22 countries to assess their national surveillance systems. / (source: FAO PIR 2018-2019)

Provide supporting narrative for the score

Overall, the organisation has met the expectations for this output. FAO reports it has exceeded the performance targets related to mainstreaming gender equality and nutrition objectives in its Country Partnership Frameworks. As reported to the Finance Committee in June 2020. the updated Gender Equality Policy is currently under review by senior Management, and the Gender Action Plan will be developed in alignment with the corporate process around developing FAO’s new Strategic Plan, ensuring linkages to the objectives of the updated Gender Equality Policy. By November 2020, FAO will also compile an overview of key gender-related areas of work and results prioritised for the 2020-21 biennium to illustrate the linkages between the updated Gender Equality Policy and the Strategic Framework. FAO also reports that it has exceeded its targets to support national statistical capacity to measure the SDGs. However, recent evaluations of FAO work on these topics have highlighted multiple areas for further improvements.

Under Output 4e, FAO reports that the implementation of its Action Plan on AMR and its four focus areas (awareness, surveillance, governance and good practices), has delivered positive changes at country level. The PIR reports that FAO has developed and deployed an Assessment Tool for Laboratories and AMR Surveillance Systems (FAO-ATLASS), with the aim of assisting countries in assessing their national surveillance system and laboratory diagnostic capacity for AMR detection. During 2018-19, the FAO-ATLASS was implemented in 22 countries across Africa, Asia and Central Asia, and the roll out continues. Nonetheless, reporting on these results to FAO Governing bodies has been limited and the UK, together with other Member States, secured the agreement of FAO Council that FAO should track progress with its work to combat AMR in its Strategic Results Framework during 2020 and 2021.

Lessons identified this year, and recommendations for the year ahead linked to this output
Although FAO management reports that it is on track with its performance and results, this is not always consistent with recent evaluation findings nor reporting on progress with SDG 2 (see Theory of Change section below). As well as the issues raised in the recent evaluations of FAO’s work on Gender, Nutrition and statistics, MOPAN (the Multilateral Organisation Performance Assessment Network) assessed FAO in 2017 and 2018 and found that “…although reporting against the organisation’s [results framework] presents FAO as a highly effective organisation, limitations in both targets and indicators for outcomes and the degree of uncertainty around FAO’s role in reported changes make interpreting these results difficult”. UKREP Rome has continued to press FAO to improve the meaningfulness of FAO’s performance reporting, and in particular has requested the rapid implementation of recommendations from the evaluation of FAO’s strategic results framework (SRF), issued in October 2019 (as recommended in previous reviews).
#### PCR Recommendation 4: UKREP Rome should continue to press management to implement outstanding recommendations made in the 2018 Annual Review (see Section G) and in particular, UKREP Rome should continue to encourage FAO to strengthen its Strategic Results Framework (SRF), its theory of change and improve the design and methodological transparency of results indicators so that they can be used to monitor the organisation’s progress, learn from experience and hold FAO to account.

## C: THEORY OF CHANGE AND PROGRESS AGAINST OUTCOMES

Overall assessment of whether the expected outcomes and contribution to target impact(s) were achieved
FAO’s theory of change to achieve its objectives is set out in its Strategic Results Framework (SRF, document CL 158/3 WA1). The Strategic Results Framework (SRF) for the 2018 and 2019 period was agreed by FAO Member States in 2017 and has not changed during 2018 or 2019. The SRF includes indicators for measuring progress at output, outcome and strategic objectives level. Overall, FAO is expected to contribute to 36 SDG targets measured through 45 SDG indicators. DFID’s Logical Framework for UK Core Assessed Contribution to FAO is derived from this framework and focuses on leadership, effectiveness, accountability and performance with DFID priorities such as monitoring the 21 SDG indicators (for which FAO is the custodian) and improving national responses to cross border threats to food security and global health security, such as Fall Armyworm and Antimicrobial Resistance (AMR), while promoting gender equality and combatting climate change.

The FAO Programme Implementation Report (PIR, document C2021/8) finds that in 2018 and 2019 FAO fully met 95% (41) of its 43 output indicators targets, while 5% (2) were not achieved. The PIR also assesses the outcomes achieved and describes a generally positive trend, with 16 out of 22 indicators showing improved performance status for the majority of countries between the years 2015 and 2019. FAO also reports that its contribution to change is recognised as significant or moderate for all but two of the assessed outcome indicators.

As highlighted by the recent MOPAN report (ibid), FAO’s strategic results framework (SRF) has various weaknesses. As previously noted, FAO’s theory of change also needs to be strengthened to better demonstrate the contribution of FAO’s work at output and outcome level to its overarching goals, linked also to the Sustainable Development Goals. shows an upward trend while the overall trend of global hunger has deteriorated. While FAO is met its output targets in 2018 and 2019, the 2019 State of Food Insecurity report (SOFI) found that the number of hungry people in 2018 has risen for the third consecutive year - in part due to the increasing effects of climate change and growing number of conflict situations. The SOFI 2019 Report suggests that progress towards FAO’s overarching goals is off track. The UK, as a member of FAO’s Programme Committee, requested an evaluation of FAO’s SRF and the evaluation (document PC127/2) recommended “...updating the theory of change underpinning the Results Framework to identify more tangible, issue-based programmatic objectives and to articulate the result chains of its normative work on global public goods and development objective.” UKREP Rome will continue to press FAO to implement the recommendations of that evaluation as FAO develops a new strategic results framework under Director General Qu. More broadly, the UK will also promote more effective collaboration between partners in delivering results across the international system for food and agriculture, using the SDG framework and indicators to demonstrate progress towards getting SDG2 back on track. This will be even more critical in the context of COVID-19, where FAO will need to work closely together with others – including UN agencies, IFIs, civil society and the private sector - to support Governments in protecting livelihoods, ensuring food and nutrition security, and support economic recovery.

Explain major changes to the logframe in the past year

This logframe covers the 2018-19 biennium. This PCR is the final review against it and there have not been major changes to it. We will produce a new one for the 2020-2021 biennium.

## D: VALUE FOR MONEY

Assess VfM compared to the proposition in the Business Case, based on the past year and during the lifetime of the programme

The assessed contribution to FAO is exempt from the requirement for a business case because the contribution is a requirement for the UK membership of FAO. The percentage of the UK contribution of FAO’s core budget for the 2018/19 biennium is 4.64%. The percentage that each country is required to pay is determined by the UN centrally and reflected in the scale of contributions setting out the amount due from all Member States.

The FAO, like other UN agencies, has challenges in maintaining the level of funding needed to deliver its ambition and FAO Members voted a zero nominal growth budget over the last fifteen years. The FAO manages this through proactive management of assessed contributions, regular budget review, a full cost recovery model for programme activities, and a new fundraising strategy. In 2019, voluntary contributions rose to 67% of the budget.

More significantly, the FAO does not have a fully conceptualised and embedded approach to VFM and there has been a significant update of procurement practices, which are being rolled out. These reforms are positive, but will need to be monitored as they become operational.

FAO’s key cost driver and main asset is its staff, which accounts for 75% of the FAO 2018-19 net appropriation budget (as reported in the Programme of Work and Budget (PWB) 2020-21). FAO staff costs are linked to those agreed in the UN common system and FAO management has limited options for controlling them. The most significant components are salaries, medical costs and benefits, such as education grants and home leave. FAO management has used a number of strategies to contain these costs which include the use of consultants who are cheaper to employ because they are not entitled to staff benefits; and maintaining a relatively high vacancy rate. Only limited data on FAO’s human resources (both staff and consultants) was made available in 2018 and 2019. As a member of FAO’s Council, the UK has called, together with other Member States, for greater transparency in HR data. This resulted in improvements to FAO’s HR Management Report in 2020 which FAO’s Finance Committee welcomed in their June 2020 meeting. As reported above, FAO management is preparing a HR Strategic Action plan which UKREP Rome will scrutinise closely (see PCR recommendation 3).

Exchange rates are another key cost driver. FAO requires that its member states make their assessed contributions in both US Dollars (USD) and Euros (EUR) to minimise financial risks to FAO from exchange rate fluctuations. Nevertheless, FAO still faces some risk of unfavourable exchange rates. Furthermore, the requirement to pay the UK assessed contribution in USD and EUR means that the cost of this in GBP varies and is subject to fluctuations in the GBP: USD and GPB: EUR exchange rates. Thus the USD and EUR exchange rates are a key cost driver for the UK.

Despite FAO's limited control of these cost drivers, management has made savings over the past two biennia enabling the organization to allocate a greater portion of the budget to programmatic rather than administrative functions. FAO has implemented its Programme of Work and Budget for 2018 and 2019 (PWB) within the zero nominal growth budget level agreed by member states. FAO management consolidated the savings generated in the prior biennium and made further administrative savings of USD 11.7 million which have been reallocated to FAO’s programmatic work. In particular, additional savings of USD 3.6 million were expected under personnel costs, mostly due to the reduction in the headquarters professional staff net remuneration, the freeze on the salary scales for the general service staff, and the reductions in other allowances and entitlements reflecting the gradual implementation of the revised compensation package since 2016. Furthermore, USD 8.1 million in inflation costs for goods and services was absorbed through reduced costs of consultants, travel, and procurement.

Assessment of whether the programme represented value for money
Yes, the UK’s core contribution to FAO represents value for money. This is because of recent improvements in the economy and efficiency of FAO and progress in improving gender equality (as reported under Output 4a). However, there is still scope for improvement in effectiveness including through greater collaboration with other partners across the international system

E: RISK

Overview of programme risk (noting the rating from page 1) during the past year and over the life of the programme

FAO is at an early stage of its journey in developing risk management and, while it has been strengthened, it is not yet systematic. Positive steps have been undertaken to improve risk management but internal and external audit findings highlight areas for further improvement.

Efforts to strengthen risk management and internal control at FAO have progressed during the biennium with significant further steps taken towards full implementation of Enterprise Risk Management. In particular, guidance on risk assessment, risk log development and risk mitigation has been developed for FAO staff. A requirement for risk logs at all levels of the organisation was introduced in 2019 and has been accompanied by training and capacity building. FAO country offices with large emergency operations received dedicated support to their risk management practices.

FAO does not yet have a formally established risk appetite but is considering introducing in 2020/21. Without setting organisational risk appetite, FAO partners may also be operating at a higher level of risk than FAO deems acceptable and there a risk that partners may not be able to readily judge what is and what is not within FAO’s appetite, impacting escalation.

The partner specific Risk Mitigation and Assurance Plan (RMAP) is utilised to monitor partner specific risks identified through the due diligence process and should be updated in line with FAO monitoring activities. Project specific risks are monitored through a separate project specific risk register. The risk register template records: a description of risk, worse case consequence of the risk for the project, mitigation, risk owner and risk score (impact & likelihood). It is not explicitly clear whether the risk rating represents a gross (i.e. before mitigating action is put in place) or net risk rating (i.e. once mitigation is embedded). Frequency of risk reporting should be determined per each project.

FAO continues to strengthen its internal controls. This is based on a comprehensive global reporting process which culminates in the Statement on Internal Control which, since 2017, has accompanied FAO’s financial statements. Weaknesses identified in decentralised offices as part of this process are followed up in order to achieve gradual improvement.

FAO has frameworks and corporate processes in place to manage risks in human resources management, safeguarding, procurement and management of downstream partners, however how the frameworks are functioning in practice is not yet clear. UKREP Rome will continue to scrutinise these processes (see PCR Recommendations 2 and 3).

The concerns flagged in the July 2019 letter of FAO’s Audit Committee Chair to outgoing Director General Graziano da Silva (reported under Output 3 above) prompted an increase to the risk that the independence of FAO’s Office of the Inspector General is undermined. As reported above, FAO has now taken action to mitigate this risk.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Performance of partners and DFID, notably on commercial, and financial issues

FAO’s Programme of Work is funded by the net appropriation (assessed contributions) voted for by Conference and extrabudgetary resources provided through voluntary contributions. The assessed contributions budget for FAO for the 2018-19 biennium of USD 1,005,635,000 was approved by FAO’s 194 Member Nations (including the UK), one member Organization, the European Union, and two Associate Members at the FAO Conference in July 2017 as part of FAO’s Programme of Work and Budget (PWB) for 2018-2019. In December 2017, FAO Council took note of the updated estimates for extra-budgetary resources (Table 3 CL 158/3) of USD 1,564,368,000. Of the total USD 2.6 billion budget, 39 percent – or US$ 1,005,635,000 is FAO’s regular core budget and comes from assessed contributions paid by member states, and 61 percent is mobilised through voluntary contributions from Members and other partners.

As reported in Section D (Value for Money), the UK was required to contribute 4.64% of FAO’s regular core budget as our assessed contribution. For the 2018 and 2019 biennium the total cost of the UK assessed contribution was £33.9 million. This contribution was paid in two tranches in 2018 and 2019: in 2018, the UK contribution was £16,587,497.18, and in 2019 the amount was £17,301,518.42.

As reported in FAO’s PIR 2018-19, FAO spent 99.6% of its regular core budget of USD 1 005.6 million, resulting in an overall underspend of USD 3.6 million. As authorised by the Conference at its 41st Session in July 2019, the unspent balance of USD 3.6 million will be made available for one-time uses in 2020-21, based on the proposal to be submitted to and agreed by FAO Council in July 2020,

As mentioned above, the PIR also reports that FAO fully met 95% (41) of its output indicators targets.

Audit reporting
Auditing requirements have been met. The external audit of FAO’s financial statements is in compliance with the Financial Regulations and in conformity with the International Standards on Auditing (ISA). The audit report resulted in the issuance of an unmodified audit opinion on the Organisation’s financial statements for the financial year ended 31 December 2018. FAO concluded that the financial statements present fairly, in all material respects: (a) the financial position of FAO for the year ended 31 December 2018; (b) its financial performance; (c) the changes in net assets/equity; (d) its cash flows; and (e) the comparison of budget and actual amounts of its expenditures for the said year in accordance with IPSAS. Audited financial statements for 2019 will be presented to the Finance Committee in November 2020.

Date of last narrative financial report	Financial Position of the Organisation FC 180/2 / May 2020
Date of last audited annual statement	FAO Audited Accounts 2018 2021/5A / C FAO Audited Accounts 2018 – Report of the External Auditor C2021/5B / November 2019

G: MONITORING, EVIDENCE & LEARNING

Monitoring
UKRep Rome monitors FAO’s performance through scrutiny of FAO management reporting. UKREP Rome uses UK, and occasionally joint member, interventions in FAO governing bodies to discuss and press for further progress. UK Rep Rome also meets regularly with FAO’s senior staff overseeing policy, administration, finance and human resources and uses these meetings to monitor and discuss progress.

An Annual Review of progress in 2019 was completed by UK Rep Rome following the publication of FAO’s Mid Term Review (MTR) for 2018. The Annual Review and this Project Completion Review are based on FAO progress reports in the MTR, PIR and other documents presented to FAO's governing bodies; the deliberations of those bodies; on FAO and external evaluations and assessments; and on informal exchanges with FAO management.

UKRep also engages with DFID country offices and policy staff at headquarters, raising policy and administrative issues with FAO management on their behalf. These exchanges contribute to UKREP’s overview of FAO’s performance at country level and were supplemented with systematic feedback from all DFID owners of voluntarily funded projects with FAO in January 2019. This information has been incorporated in the AR and was also discussed with FAO senior management at the Strategic Dialogue meeting in February 2019.

Evidence
FAO’s Office of Evaluation reports to the membership through FAO’s Programme Committee as well as to FAO management. The UK served as one of the 12 members of FAO’s Programme Committee (PC) during 2018 and 2019 and plays an active role (and was re-elected by the FAO Council in July 2019 for the 2020-2021 biennium). The PC is responsible for scrutinising FAO’s programmatic work and reviewing evaluations of it.

These evaluations assess FAO activities, projects, programmes, strategies and policies and are published on the Office of Evaluation website. Thematic and strategic evaluations are submitted to the Programme Committee and FAO Council. Evaluations are often conducted in response to requests by the Programme Committee. Management responses to evaluation recommendations are also submitted to the Programme Committee, together with follow up reports on progress with recommendations. The most relevant evaluations and follow-up reports that have been examined by the Programme Committee in the biennium were:
- Evaluation of the strategy and vision for FAO’s work on nutrition (incl. Management Response)
- Evaluation of FAO’s work on gender (incl. Management Response)
- Synthesis of findings and lessons learnt from the Strategic Objective Evaluations (incl. Management Observations)
Evaluation of FAO’s strategic results framework (SRF) – and Management Response.

In parallel to these evaluations, in February 2019 the Multilateral Organisation Performance Assessment Network (MOPAN) released its assessment of FAO’s performance. The main findings are:

- FAO has strengthened its performance since the last MOPAN assessment in 2014. It has enhanced its strategic focus; strengthened operational management, including of fiduciary risk; and reinforced its commitment to partnerships, both with other UN agencies as well as civil society and the private sector.
- Looking ahead, the organisation will need to strengthen its systems and enhance its ability to manage risk, while remaining agile to take advantage of opportunities to advance its mandate.
- FAO has yet to find sustainable forms of funding for some of its core activities, such as normative work, where core funding is limited.
- FAO’s approach to measuring results, particularly in normative work, remains work in progress.

Learning
Although FAO management reports that it is on track with its performance and results, this is not always consistent with recent evaluation findings. As noted, MOPAN also found that “…although reporting against the organisation’s [results framework] for 2016-2017 presents FAO as a highly effective organisation, limitations in both targets and indicators for outcomes and the degree of uncertainty around FAO’s role in reported changes make interpreting these results difficult”. It is striking that reporting against FAO’s outputs and outcomes shows an upward trend while the overall trend of global hunger has deteriorated. This underlines the importance of strengthening FAO’s strategic results framework as discussed in Section C, as well as more effective collaboration with partners across the international system for food and agriculture. This will be even more critical in the context of COVID-19, where FAO will need to work closely together with others to support Members in protecting livelihoods, ensuring food and nutrition security, and support economic recovery.

Progress on recommendations from annual reviews for this programme (1/2 page)
This a summary of progress with recommendations made in the 2018 Annual Review (completed in 2019):

AR Recommendation 1: DFID should continue to press FAO to implement its commitments to collaboration with IFAD and WFP as well as to the UNSG’s reforms to the UN Development System (UNDS). DFID should also press FAO management to work with IFAD and WFP to produce a quantitative measure of the savings achieved through RBA collaboration initiatives.

Ongoing. UKREP continues to press for improved collaboration and progress with the UNDS reforms in our interventions at FAO governing body meetings and other informal and bilateral meetings.

AR Recommendation 2: DFID to press FAO leadership for action to address underreporting of Sexual Exploitation, Abuse and Harassment (SEAH) and work with other member states to foster the culture change that will support this.

Ongoing. UKREP continues to press for action, including from new FAO Director General Qu. Following the insistence of FAO’s Programme and Finance Committees (UK is a member of the Programme Committee) the DG commissioned an updated staff survey at the end of 2019; and FAO has committed to updating their action plan to reflect its findings.

AR Recommendation 3: DFID should review and update our risk assessment of FAO and identify priority actions to strengthen FAO’s transparency, internal controls, HR management, accountability, safeguarding and results reporting (through governing bodies). DFID should use FAO’s governing bodies to press new Director General Qu to implement these actions.

Completed. DFID reviewed our risk assessment in August 2019 and UKREP has continued to press FAO e.g. on action to strengthen the independence of FAO’s Inspector General.

AR Recommendation 4: DFID should press for the rapid implementation of recommendations from the evaluation of FAO’s strategic results framework (SRF), issued in October 2019. DFID should encourage FAO to revise its SRF, strengthen its theory of change and focus on recommendations to improve the design and methodological transparency of results indicators so that they can be used to monitor the organisation’s progress against objectives, learn from experience and hold FAO to account.

Partially completed. UKREP has pressed for these improvements to FAO’s SRF and this is reflected in the conclusions of FAO’s Programme Committee meetings in November 2019 and June 2020. UKREP should continue to encourage FAO to revise its Strategic Results Framework (SRF), strengthen its theory of change and improve the design and methodological transparency of results indicators so that they can be used to monitor the organisation’s progress against objectives, learn from experience and hold FAO to account.

Sources
- Medium Term Plan 2018-21
- Programme Implementation Report 2019
- Progress Report on RBA Collaboration May 2020
- Programme of Work and Budget 2018-19
- Human Resources Management May 2020
- Report on Financial Position of Organisation May 2020
- Reports of Finance Committee, November 2019
- Report of the Programme Committee, November 2019
- FAO Council Report, December 2019
- Annual Report on Budgetary Performance and Programme and Budgetary Transfers in the 2018-2019 Biennium FC180/6
- DFID Annual Review of FAO progress in 2018
- Programme Evaluation Report 2019
- Office of Inspector General Annual Reports 2019
- DFID Central Assurance Assessment November 2019
- Highlights 2019 FAO Employee Satisfaction Survey, May 2020

Smart Guide
The Project Completion Review is the opportunity to reflect on the entire programme, its performance, achievements, lessons and how learning will be shared to inform future programming.

The Project Completion Review assesses and rates outputs using the following rating scale. The Aid Management Platform (AMP) and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below when completing this template. Suggested section lengths are indicative. Some reviews may need to be longer and others can be shorter (eg first year of a programme which has largely focused on mobilisation activities) – it is for the SRO and Head of Department to decide. All text needs to be suitable for publication. Bullets rather than full narrative may make sense for some sections.

A: Summary and Overview
Programme Code is the AMP I.D. number (same on Devtracker) / Enter risk rating (Minor, Moderate, Major or Severe) at the time of the review, taken from AMP / Describe the programme in 1-2 paras including what it aimed to achieve. You might want to include headline points on changes in the operating context, partner performance, DFID management of the programme or other points relevant to the 10 Delivery Questions in the Smart Rules. You should assume that readers may not go beyond this summary. / Describe –without repeating detail from Section B- progress in the past year and why the programme has scored as it has against the output indicators. There needs to be a record of any follow up actions that may be required after completion of this review (eg related to final payments, audited statements etc – see the extension and closure section in the Smart Rules). These may sit best in the Delivery Plan – but you should agree them with the person signing off the PCR and include them in this (publicly available) report or the Delivery Plan.
B: Detailed Output Scoring
Output Title, Number, Weighting, Indicators and milestones / Use the wording exactly as is from the current logframe. This will need to be entered on AMP as part of loading the PCR for approval. Indicate (Yes or No) if the impact weighting has been revised since last Annual Review (Business Case approval if the programme is under 15 months and hasn’t had an AR) and if Yes in which direction (up or down). Input progress against the milestone for this review
Output Score / Enter the rating (using the scale A++ to C) exactly as generated on the programme scoring calculation sheet
Provide a brief description of the output (unless obvious from the information in the box above) and supporting narrative for the score
Lessons and recommendations linked to this output. Some of these may inform or need to be included in Section A. For anything that can’t be published please use the Delivery Plan
Repeat above for each Output in the logframe and add new sub-sections for additional outputs.
C: Theory of change and progress against outcomes
Overall assessment of whether the expected outcomes and contribution to target impact(s) were achieved? Review this in view of the overall programme score; but it is possible that outputs were delivered but the envisaged outcomes or impact were not – or vice versa – and consider reasons for this. It is not unusual for programmes to be off track against at least some of the expected outcomes or impact. You should refer to the indicators in the logframe. Did any unexpected outcomes emerge? Were there any significant changes in the planned timetable for delivery of the programme? Were there any changes to expected outcomes or impact on gender equality compared to what was described in the approved Business Case?
Theory of Change (ToC). You might want to use a diagram to summarise it. You should flag any major changes in the past year. You should consider if the steps to achieving outcome and impact were valid e.g. did the ToC logic, supporting evidence and assumptions hold up against implementation experience? Is there any new evidence which challenges the programme design or rationale? If relevant you might also want to flag any major changes since the programme started rather than just over the year in question.
Logframe. Describe major changes in the past year –including when they were made and why- and what their implications were for the programme. Ideally changes should not have be made to any targets or indicators less than six months before they are being reviewed unless agreed with the Head of Department. All changes should be recorded as part of the programme’s documentation (there is a ‘change frame’ tab on the logframe template). If relevant you might also want to flag any major changes since the programme started.
D: Value for Money
Assess VfM compared to the proposition in the Business Case, based on the past year and during the lifetime of the programme You should refer to VfM measures and metrics from the Business Case and/or ARs. Changes in cost drivers (e.g costs of major inputs) and the theory of change may be relevant. The assessment should encompass the 4 E’s of DFID’s value for money framework – economy, efficiency, effectiveness and equity, including gender equality (referring back to the relevant text in the approved Business Case’s Strategic Case may be relevant), disability and leaving no one behind. You should note any formal extensions or amendments to the programme giving brief details about cost, duration and the reasons why. Signifcant changes to logframe indicators or targets may also be relevant.

E: Risk

Provide an overview of the programme’s risk (noting the rating from page 1) during the past year and over the life of the programme / Note the overall risk rating now as captured in AMP and on p1. Flag any changes to the overall risk environment/ context in the past year and how they impacted on the programme and were mitigated. Use DFID’s standard risk terminology where possible eg categories of risk and risk appetite. Remember to take account of any relevant recommendations from Due Diligence Assessments on implementing partners. Some relevant information may not be suitable for publication but ensure the risk register on AMP and Delivery Plan are updated as necessary following this review (remember that projects remain open until they are archived, even after the PCR is complete). / Update on Partnership Principles. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four PPs over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences?
F: Delivery, Commercial and Financial Performance
Issues to consider for both the implementing partner(s) and DFID include: quality and timeliness of narrative reporting and audited financial statements; proactive dialogue on risks and updating of delivery chain maps; quality of financial management eg accuracy of forecasting; monitoring of assets. Consider also how DFID could have been a more effective partner to help deliver the programme (key points could be included in Section G too). / If there is a contract involved, set out: / Delivery against contract KPIs (and Terms and Conditions) / Compliance with the Supply Partner Code, where applicable, drawing on advice from PCD. / Compliance with the new cost and transparency requirements, where applicable (i.e. highlighting any profit variance and challenge and use of Open Book Accounting) / Performance of Partners. Where applicable, an annual summary of the new SRM scorecard assessment for each delivery partner involved in delivering this programme.
G: Monitoring, Evidence and Learning
Monitoring. / Summarise monitoring activities throughout the review period (field visits, reviews, engagement with stakeholders including beneficiary feedback) and how these have informed programming decisions. Where there is an external M&E supplier, how they engaged with the programme implementer(s) and DFID. Briefly describe the PCR process itself including any inputs from outside the programme team (within or beyond DFID). / Evidence / Describe any changes in evidence and implications for the programme. Include any relevant comments on the quality/breadth of the evidence. / Monitoring data, evidence and learning should consider the ‘Leave no one Behind’ agenda and as far as possible disaggregate information by age, sex, disability, geography (update geocoding information on AMP as needed) and other relevant variables. / Where an evaluation is planned or has taken place set out what progress has been made. / Learning / What learning processes have been used over the past year to capture and share lessons, new evidence and know-how? / What are the key lessons identified over the past year for (i) this programme (ii) wider DFID and development work? / Any specific implications or follow-up actions of that learning for this programme may be best captured in Section A / Progress on recommendations from previous review(s) / It is important to keep track of this. Some may not be publishable and feature in the Delivery Plan. But a brief update on progress against any recommendations from ARs (especially the last one) should be provided.