Title: Sustaining and Accelerating Primary Health Care in Ethiopia (SAPHE) programme / Review period: November 2015 – October 2016
Programme Value: £250 million		Review Date: November 2016
Programme Code: 204964	Start Date: November 2015	End Date: December 2020

Annual Review Summary Sheet

Acronyms Used:

ANC	Antenatal Care
AR	Annual Review
ARM	Annual Review Mission
AWD	Acute Watery Diarrhoea
BEMOC	Basic Emergency Obstetric Care
BPR	Business Process Reengineering
CAR	Contraceptive Acceptance Rate
CBHI	Community Based Health Insurance
CEMOC	Comprehensive Emergency Obstetric Care
CPR	Contraceptive Prevalence Rate
CSA	Central Statics Agency
DACA	Drug Administration and Control Authority
DFID	Department for International Development
DP	Development Partners
EDHS	Ethiopian Demographic and Health Survey
EFY	Ethiopian Financial Year
EPHI	Ethiopian Public Health Institute
FMHACA	Food, Medicine and Health Care Administration and Control Authority
FMoH	Federal Ministry of Health
GGs	Global Goals
GMU	Grant Management Unit
GOE	Government of Ethiopia
HAPCO	HIV/AIDS Prevention and Control Office
HEW	Health Extension Workers
HMIS	Health Management and Information System
HSTP	Health Sector Transformation Plan
IFMIS	Integrated Financial Management System
IMNCI	Integrated Management of Neonatal and Childhood Illnesses
JCCC	Joint Core Coordinating Committee
JCF	Joint Consultative Forum
JFA	Joint Financing Agreement
KPI	Key Performance Indicator
MDG	Millennium Development Goals
MDG-PF	Millennium Development Goals Performance Fund
MiTU	Ministerial Transformation Unit
MOFEC	Ministry of Finance and Economic Cooperation
NHA	National Health Account
NHCFS	National Health Care Financing Strategy
ORS	Oral Rehydration Solution
PFSA	Pharmaceutical Fund and Supplies Agency
PNC	Postnatal Care
PPA	Public Procurement Agency
SAPHE	Sustaining and Accelerating Primary Health Care in Ethiopia
SARA/SPA	Service Provision Assessment
SBA	Skilled Birth Attendance
SDG	Sustainable Development Goals
SDG-PF	Sustainable Development Goals Performance Fund
SHI	Social Health Insurance
SNNP	Southern Nations, Nationalities and Peoples
TA	Technical Assistance
TSP	Technical Service Provider
USAID	United States Agency for International Development

The Annual Review assesses and rates outputs using the following rating scale:

Description	Scale
Outputs substantially exceeded expectation	A++
Outputs moderately exceeded expectation	A+
Outputs met expectation	A
Outputs moderately did not meet expectation	B
Outputs substantially did not meet expectation	C

Summary of Programme Performance

Year	November 2015 to October 2016
Programme Score	A
Risk Rating	Major

Summary
The Sustaining and Accelerating Primary Health Care in Ethiopia (SAPHE) programme is a five-year project, approved in October 2015 at a value of £250 million. It supports the delivery of Ethiopia’s current five-year Health Sector Transformational Plan (HSTP, 2015-2020) to accelerate progress towards the health Global Goals (GGs). The programme provides support to the Federal Ministry of Health (FMoH) through a range of methods, including: funding to the health sector through the Sustainable Development Goals Performance Fund (SDG-PF), a multi-donor pooled fund; providing technical assistance by seconding a DFID health advisor to the health minister’s office, and; engaging a high quality Technical Service Provider (TSP) to support key ministerial priorities within HSTP.

Key ministerial priorities, supported by SAPHE, include: establishment of a Ministerial Transformation Unit (MiTU) to oversee implementation of HSTP’s transformational agendas; strengthening of the Ethiopian Health Insurance Agency (EHIA) to scale up community-based and social health insurance schemes; strengthening of the Food, Medicine and Health Care Administration and Control Authority (FMHACA) to promote and protect public health by ensuring safety and quality of health products and services; and, accelerating the pace of implementation of the Ethiopian Health Care Financing Strategy to make financing of health services in Ethiopia fairer and sustainable. DFID’s support to the Ethiopian health sector is crucial to sustain past gains and accelerate progress – particularly towards sustainable financing – to enable DFID’s planned, responsible exit from the health sector at the end of this programme.

The programme contributes to the SDG-PF, which is managed by the FMOH. The SDG-PF, like its predecessor the Millennium Development Goals Performance Fund (MDG-PF, 2008-2015), provides harmonised and aligned support from 10 development partners to fill critical funding gaps to make primary health care facilities fully functional for providing quality health services. It has a particular focus on services to adolescents, pregnant women, new-borns and children. Expected results include the aversion of almost 35,000 maternal and child deaths and 2.7million unhealthy years of life.

This is the first annual review for the programme. This review looks at SDG-PF’s performance during Ethiopian financial year 2015/16, during which a total of £29.4 million was disbursed by DFID to SDG-PF. SDG-PF has supported: procurement and distribution of life-saving maternal and child health commodities; improvement of primary health care facilities; and, training of primary health care providers. These, in turn, have improved the functionality of the primary health care units and contributed to an increase in quality, availability and use of essential maternal, new-borns and child health care services. DFID’s investment through SDG-PF continues to provide good value for money, due largely to cost savings achieved through the bulk purchase of consumables and improvements in efficiency and productivity of the primary health care delivery system. SDG-PF has also contributed to the preparation of key reform strategies and roadmaps, such as an Equity Strategy, a methodology for ensuring the FMoH allocates resources in a fairer and more efficient way, a roadmap for MiTU and a road map FMHACA, and enhancing the capacity of the key agencies and directorates of the FMoH for implementing the HSTP.

During this review period, Ethiopia witnessed a severe drought as a knock on effect from El Niño. This led to a worsening of child undernutrition in drought-affected areas and outbreaks of diseases, including measles and Acute Watery Diarrhoea (AWD). The SDG-PF was able to flex and adapt to the emerging crises by re-programming some of its resources to allow FMoH to respond to child under-nutrition, measles and AWD. SDG-PF resources were used for procurement of drugs and supplies, including Oral Rehydrating Solutions (ORS), measles vaccines, chemicals to treat water and nutrients/products for supplementary feeding. In addition, SDG-PF has supported the Federal Ministry of Health’s command post and rapid response units to better respond to disease outbreaks. This was a significant success of the programme in the last year. However, we are currently unable to attach specific additional results as the Ministry of Health does not differentiate between the elements of the drought response funded by this programme and the broader health and humanitarian interventions. DFID is working closely with the FMoH on lessons learned to ensure the programme remains able to adapt to emerging crises and will be able to demonstrate quantifiable results, including the number of rapid response units supported and their effectiveness.

The Ministerial Transformation Unit has been established to focus on health financing, equity and quality. On financing, the programme has made good progress by completing a competitive process for technical assistance and identifying the provider. However, the next year will be instrumental in delivering the priorities of the financing strategy. Specific indicators to measure progress on this part of the programme will be included in the logframe update. Similarly, the design and early implementation of the Equity Strategy has been a key achievement – winning support at all levels of Government. However, the strong focus of the next year is ensuring policy and words translate into action with accelerated reduction in disparities of health outcomes (both in terms of gender and geography). Building relationships with the new Minister of Health will be central to this agenda.

 DFID also needs to work with FMoH, the Central Statistical Agency (CSA) and others for timely completion of planned surveys for better assessments of the readiness and functionality of primary health care facilities and customer satisfaction/patient expertise.

This review was completed as DFID Ethiopia designs a new programme to reach 1 million additional new users of family planning by 2020 – further improving the capacity of the health sector and supporting DFID’s responsible exit. The lessons from this annual review must be used to inform the design and implementation of that programme.

Summary of key recommendations
DFID should continue to work closely with the Ministry of Health on lessons learned from the drought response to ensure the programme remains able to adapt to emerging crises and demonstrate quantifiable results. While, by their nature, hard to predict, including an output indicator on responding to crises should be considered as part of the logframe update.

Specific, time-bound, metrics should be included in the logframe to measure the progress towards sustainable, self-financing and implementation of the Equity Strategy and more equal health outcomes across genders, geographies and social/economic groups.

DFID should work with FMoH, the Central Statistical Agency (CSA) to ensure timely completion of planned surveys for better assessments of the readiness and functionality of primary health care facilities and customer satisfaction/patient expertise.

Building on work already conducted by DFID Ethiopia, for example, the sector financing analysis, DFID should accelerate its engagement on domestic financing as part of its responsible exit from the health sector. The arrival of the new health minister provides an opportunity for enhancing our engagement on this area.

A. Introduction and Context (1 page)
DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-204964/documents
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-204964/documents

Outline of the programme
SAPHE is a health sector programme that provides support to FMoH through a range of methods. It provides earmarked financial support to the health sector through the SDG-PF, which is managed by the FMoH and governed by a Joint Financing Agreement (JFA). The JFA was signed by the GoE and 10 Development Partners in July 2015, including GAVI, the World Bank, Irish Aid and Spanish Aid. The Fund allows FMoH to implement the HSTP and deliver progress on the health GGs. The SDG-PF is making a significant contribution to increasing the functionality of Primary Health Care Units by: improving procurement and distribution of essential medicines, medical supplies and equipment; upgrading primary healthcare infrastructure; building skills of primary health care providers to tackle maternal, new born and child morbidity and mortality; and, creating demand for adolescent, maternal and child health care. In all of these, SDG-PF has prioritised the Developing Regional States/Peripheral Regions.

The programme also provides support to the health sector through secondment of a DFID senior health adviser at FMoH as well as through procuring technical assistance (TA) to provide support in three priority areas of the HSTPs (i.e. MiTU, equity, health care financing and FMHACA).

In 2015/16 (year 1 of the SDG-PF), 31% of the SDG-PF resources were used for procuring essential public health commodities including pharmaceuticals and medical supplies through the Pharmaceutical Funds and Supplies Agency (PFSA), the national health procurement agency. Other areas of the SDG-PF spending include: upgrading of primary health care infrastructure, strengthening of the health extension programme, including training of health extension workers and support for improving quality of health service delivery.

Gender Summary
This programme continues to have a strong positive impact on women and girls. At the impact level, it is primarily aimed at reducing maternal morbidity and mortality. Within the individual components there are a number of interventions which are improving health outcomes for women and girls. Specifically, it is improving care during pregnancy, delivery and post-delivery. It is also improving accessibility of essential drugs to manage maternal and new-born health conditions. A significant achievement in the last year is the design and implementation of the Equity Strategy, which has gender at its heart. This is intended to ensure equal access to compassionate care and has been cascaded to all regions and districts.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment:
The expected outcomes from SAPHE are increased utilisation of Adolescent, Maternal and Child Health Services, increased equity and responsiveness of the Primary Health Service delivery system, and increased sustainability, fairness and efficiency of the Ethiopian Health Service Delivery system.

The logframe for SAPHE is comprised of six outcome indicators, of which three milestones were expected to be set and assessed using the Ethiopian Demographic and Health Survey 2015/16 (EDHS). The initiation of EDHS 2015/16 was delayed and only the preliminary results of this survey have been shared by the Central Statistical Agency of Ethiopia. Therefore, this review has triangulated information from EDHS 2011 and 2016, and information from HSTP Annual Performance report to assess progress. On the basis of these information sources, this review infers that: two indicators pertaining to family planning and financial protection against health shocks have met expectation during this review period; two indicators pertaining to care during pregnancy and domestic financing have not met expectations; one indicator pertaining to citizen experience could not be assessed because of lack of information; and, another one pertaining to equity is supposed to be assessed in 2018 and 2020. While lack of data means there are limitations in our ability to measure all outputs fully, this is not unexpected and some indicators were never intended to be assessed in the first year of the programme. However, DFID is working with the CSA and other donors to ensure timely completion of planned surveys and assessments.

Outcome Indicator 1: Contraceptive prevalence rate (CPR), national and positive progress for worst performing regions
No milestone was set for this indicator for this year, as this indicator would be measured at three points of time during the life of this programme through EDHS 2015/16 (base-line), mini-EDHS 17/18 (mid-term) and EDHS 2020/21 (end-line). As EDHS 2015/16 was delayed, DFID Ethiopia used the mini-EDHS 2014 data to establish the baseline. However, now with the availability of EDHS 2015/16 estimates, which is a more reliable source than the mini-EDHS, DFID Ethiopia has adjusted the baseline and set the mid-term and end-line milestones. Comparison of EDHS 2011 and 2016 tells us that contraceptive use, among married women of reproductive age 15-49 years, in Ethiopia has increased from 29% to 36%, an increase of nearly 1.5 percentage points per year. This translates in to over 400,000 additional family planning users during the review period. Therefore, this review infers that overall progress on CPR has met our expectation.

Despite progress, CPR varies significantly by region, and these geographic disparities in contraceptive use have resulted in disparities in the number of births per woman during their lifetime (Total Fertility Rate) by location.

Regional variation of modern contraceptive prevalence: CPR is high, close to 47% in Amhara and as low as 12% in Afar and 2% in Somali region.

The new equity strategy of the FMoH, which is supported by the SDG-PF, is trying to address this issue.
2%
56%
12%
29%
40%
35%
29%
36%
4.5

Outcome Indicator 2: Antenatal care coverage (4+ visits), national and positive progress for worst performing regions
The milestone for this indicator was 45% - against a baseline of three in 10 women (32%) having had a 4+ ANC visits for their most recent live births based on an average from the last five years. Urban women are more likely than rural women to have had 4+ ANC visits (63% and 27% respectively). There still exists a regional disparity with Somali being at 11.8%, Afar at 20.6% and Oromia at 22.1%. Comparisons with previous EDHSs, show that antenatal care coverage is increasing by around 2.5 percentage points per year. With this trend, the antenatal care coverage during this review period could be estimated to be around 39% - an improvement but still less than the target. Therefore, this review concludes that this indicator has not met expectation.

Outcome Indicator 3: Concentration Index (for a selected 11 maternal and child health care indicators)

No milestone was set for this indicator for this review period as progress is expected to be evaluated in 2018 (mid-term) and 2020/21 (end-line).

Outcome Indicator 4: Percentage of citizens satisfied with public health services
Progress on this outcome indicator could not be assessed due to the fact that the district and city benchmarking survey has not been completed by the World Bank. DFID is in consultation with the World Bank, CSA and others to ensure this survey is conducted as soon as possible.

Outcome Indicator 5: Percentage of public expenditure allocated to the health sector

Against a milestone of 8.5%, public expenditure on health as percentage of total government expenditure was 7.8% in 2015/16 (EFY 2008), a slight decline from 8.1% in 2014/15. Despite the decline as a share of total government expenditure, the absolute allocation to health increased by 16% between 2014/15 and 2015/16. Also, between 2014/15 and 2015/16, the percentage of regional block grant allocated to the health sector has increased in eight out of the 11 regions in Ethiopia. It has remained the same in Amhara Region and declined in SNNP and Gambella Regions due to their prioritisation between sectors. While the share of government allocation to health has declined a bit during the review period, to respond to the drought (in particular to respond to food and water challenges), allocations to the water and agricultural sector have increased.

Outcome Indicator 6: Number and percentage of households enrolled into Community Based Insurance (CBHI) Schemes
In 2011, in an attempt to increase access to health care and provide financial protection against health shocks, the Community Based Health Insurance (CBHI) pilot was launched. This pilot covered all family health services and curative care (that are part of the Ethiopian Essential Health Package) in 13 districts across four main regions (Tigray, Amhara, Oromia, and SNNP). After three years of piloting, in 2014 the government decided to scale up CBHI after undertaking an evaluation to assess its impact. In the last two years, CBHI has been scaled to 320 districts, of which 191 have already started service provision. In these districts, cumulatively CBHI has enrolled 2.4 million people, of which 959,830 people (40% of the cumulative enrolment) have been enrolled this review period. No milestone was set for this indicator and an improvement beyond the pilot’s 13 districts is seen as improvement. Therefore, progress on this indicator during this review period has met expectation. During the inception phase of the technical assistance, a costed-roadmap will be developed including a rigorous approach to monitoring, including measurement of usage and access. This will be reflected in the logframe.

Overall output score and description:
The overall output score for the SAPHE is an A (met expectations) implying satisfactory progress has been made towards improving functionality of primary health care facilities, equity in access and use of health services and HSTP’s other transformational agendas (such as fair and sustainable financing). In addition, in the first year of the programme, many preparatory milestones, including preparation of evidence-based roadmaps for the Ministerial Transformation Unit (MiTU), a roadmap for implementing the health equity strategy, identification and agreement on options for reforming the national health procurement agency and the regulatory agency have been achieved to accelerate the transformation agendas of the HSTP (2015-2020).

Overall conclusions across all outputs
Output 1: Improved access to functional Primary Health Care Units
Overall, this output has scored an ‘A’ - met expectation. The output has five indicators of which only three indicators pertaining to skills of providers, safe delivery and child immunisation were scored. Two indicators pertaining readiness of health facilities and availability of essential medicines could not be scored due to lack of information. The Service Availability and Readiness Survey (SARA/SPA), that was planned to be carried out by mid-2016, has not yet been carried out, affecting the assessment of these indicators.

Output 2: Reduced disparities between regions, rural-urban areas and wealth quintiles in the use of essential adolescent, maternal and new-born health services
Over all, the output has scored an A (met expectations). The output has two indicators pertaining to addressing disparities in the access and use of health services. Despite progress and intent of the government to reduce disparities, there is still a wide disparity across regions and many other social and economic parameters.

Output 3: Increased resources and sustainability of the health sector
Over all, the output has scored an A (met expectations). The output has three indicators of which only two indicators pertaining to progress on transformational agendas, in particular on MiTU, Health Care Financing Strategy and regulatory reforms have been scored. The indicator pertaining to per-capita health expenditure could not be assessed because of lack of information. This information, from the proposed National Health Account survey, will be available in 2017.

Key lessons
To accelerate progress towards the HSTP’s transformational agendas, it is important to work with the senior management team of the FMoH, in particular with the Minister’s office, to: prioritise a few reform agendas; identify transformation priority owners for each of these agendas at all level of the heath service delivery system; agree on key performance indicators (KPI) with transformation priority owners and other important stakeholders, including an agreement on how to objectively assess these agreed KPIs; and, establish routines to discuss opportunities and challenges around them.

Has the logframe been updated since the last review?
No. This is the first review, and thus no updates have been made. However, the log frame was revised in June 2016 to include process indicators. We plan to update it by March 2017.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Improved access to functional Primary Health Care Units
Output number per logframe		1	Output Score	A
Risk:		Moderate	Impact weighting (%):	60%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress	Score
1.1 Number and % of health facilities have adequate provisions to fulfil the 7 signals of BEMONC and CEMONC functions	No milestone for the review period	No progress updates were available for this indicator.	N/A
1.2 Number of HEWs upgraded from level III to level IV	No milestone for the review period – anything beyond baseline is seen as improvement	4,970 level III HEWs were upgraded to level IV. While there is no milestone, the achievement during 2015/6 is more than double the baseline year of 2015 (2,123).	A
1.3 Availability of tracer drugs at primary health care units	No milestone for the review period	No new progress updates available for this indicator at this point of time. Likely to available by March 2017.	N/A
1.4 Skilled Birth Attendance (SBA)	44% (this only includes deliveries at health centres while our progress measure includes SBA in home deliveries).	As per the FMoH’s health management information system (HMIS), SBA has increased from 61% in 2014/15 (EFY 2007) to 72% in 2015/16 (EFY 2008). The progress for the milestone reaches well above the target.	A
1.5 % Children fully immunized	84.5%	As per the FMoH’s HMIS, the immunisation coverage for the period is 90.9%, which is above the milestone target	A

These output indicators capture readiness and functionality of the primary health care service delivery system. During this review period, SDG-PF has made significant contribution to improving the skills of Health Extension Workers (HEWs). HEWs are primary agents for proving community based care, including child immunisation, and for health promotion, including promoting of safe deliveries. Coverage of child immunisation as well as safe delivery services has improved significantly during the review period. Despite progress, wide disparity exists across regions. For example, coverage of safe delivery services ranges from 25.0% in Somali to 100% in Harari and Addis Ababa. However, all regions improved their performance from the previous year, with the exception of Oromia, on safe delivery services.

Key Points
Although SARA and SPA surveys have not been conducted/published to assess the progress towards the number and percentage of health facilities that have adequate provisions to fulfil the 7 signals of BEMONC (Basic Emergency Management of Obstetric and Neonatal Care) and CEMONC (Comprehensive Emergency Management of Obstetric and Neonatal Care) functions, around 500 health centres (nearly 16% of all health centres) and 55 hospitals (nearly half of all health centres) have been provided with basic obstetric and gynaecologic medical equipment to strengthen the BEMONC services in addition to 548 health professionals being trained on BEMONC in the same period.
Although there was no milestone set to assess the number of HEW upgraded from level 3 to level 4, in 2015/16 (EFY 2008) a total of 4,642 level 3 HEWs were upgraded to level 4 (as compared to the baseline at 2,123). In line with that, level 3 replacement training has been continuing in all regions.

While there was no progress update available on availability level of tracer drugs at primary health care units, the FMoH through the PFSA equipped all levels of health facilities and warehousing centres with capacity building and management tools to strengthen supply chain management. This included training on rational drug use, as well as increasing physical drug storage capacity down to the health centre level, and opening new regional branches of PFSA

According to the HSTP annual performance report, the percentages of deliveries assisted by skilled health providers (SBA), at national level, has increased at an impressive rate. Comparison of the EDHS 2011 and 2016 estimates also point to the fact that births attended by skilled providers is increasing at an impressive rate of around 3.5 percentage points per year, from 18% in 2011 to 28% in 2016.[1] From this trend it could be inferred that each year at least 100,000 more women are accessing safe delivery services. GoE/FMoH continues to show strong commitment to encouraging safe delivery. It has continued upgrading health facilities and expanding the human resources for health and health extension programme. The progress in SBA was made possible by strengthening the Health Extension programme for facilitating institutional delivery and creating a comfortable environment in health facilities for pregnant mothers and their babies by building appropriate accommodations in many health facilities.
[1] HMIS counts deliveries by Health Extension Workers at home as ‘skilled/safe delivery’, unlike the EDHS. Also, EDHS captures deliveries during the last five years, whereas as HMIS captures deliveries during the past one year. Therefore, estimates from these sources differ.

Despite progress, there are wide variations in SBA by age, residence, region, mother’s education and income. As per EDHS 2016, 80% percent of births to urban mothers were assisted by a skilled provider as compared with 21% to rural mothers. In addition to the urban-rural divide, mothers’ educational status is highly correlated with deliveries being assisted by a skilled provider and deliveries in a health facility. For instance, 17% of births to mothers with no education were assisted by a skilled provider, as compared with 93% of births to mothers with more than a secondary education. A similar relationship is observed with household wealth quintile, 13% of births to mothers with lowest wealth quintile being assisted by a skilled provider as compared with 67% of births to mothers with highest wealth quintile.

As per the HMIS, full child immunisation coverage was above the target for the period with 91% achievement. The FMoH has also succeeded to expand the Integrated Management of Neonatal and Childhood Illnesses (IMNCI) programme and strengthen health extension programme during this period. Notwithstanding the HMIS data, the EDHS 2016 depicts a mixed picture on child immunisation. Further analysis of the EDHS data is being undertaken to fully understand its implications for strengthening the child immunisation services.
Summary of responses to issues raised in previous annual reviews (where relevant)
Not relevant as this the first year of implementation and the first review for the programme.

Recommendations

- In analysing available information, gaps are noticeable but decreasing across all measurable health indicators. Further focus should be continued to align the methodology of HMIS and EDHS, and also to work with FMoH, CSA and others for timely completion of SPA, SARA and district Benchmarking surveys.
- Undertake a comprehensive analysis of the HMIS and EDHS data pertaining to adolescent, women and children to fully understand their implications to strengthen the primary health care service delivery system.

Output Title	Reduced disparities between regions, rural-urban areas and wealth quintiles in the use of essential adolescent, maternal and new-born health services
Output number per Logframe		2	Output Score	A
Risk:		Moderate	Impact weighting (%):	10%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress	Score
2.1 Effective use of policy and programme forums to address disparities in adolescent, maternal and child health (# of JCF sessions held where equity concerned were raised)	3	The issue of equity has been raised in a number of forums including the JCF, annual health sector performance review. A national health equity strategy has been developed and launched. Also, a workshop on the Equity Plan of Action was carried out to orient the regional and sub-regional political leadership to ensure health equity is taken as a political priority and activities to address equity concerns are included in the District Health Plans.	A+
2.2 Gap between national average and worst performing regions in Skilled Birth Attendance (SBA) service provision reduced	Reducing trend	The worst performing regions in SBA are Afar, Benishangul Gumuz, Gambela and Somali. Two of these regions have progressed at a faster pace than the national progress. The gap between the national average and Afar has declined by 12 percentage points, and the gap between the national average and Benishangul Gumuz has declined by 4 percentage points. Pace of progress in Somali and Gambela are similar to the national progress.	A

Key Points
During the review period, FMoH has exhibited continued commitment to reduce disparities, particularly between regions, through putting health equity transformation at the heart of its reform agenda. Various policy and programme forums were used as platforms to digest equity issues, designing robust strategies and a roadmap to achieve equity.

Equity was one of the high priority areas of discussion during the annual performance review of the HSTP that took place in October 2016. In addition, equity issues have been discussed in JCF meetings as well. A discussion paper on ‘Health equity in Ethiopia: Determinants of Health Inequalities and Strategies to Address Health Equity’, was presented at ARM 2016. This paper is used as an input for developing the National Health Equity Strategy. The strategy focuses on achieving equal access, utilisation and quality of health care for all Ethiopians by 2020. Another achievement during this review period was advocacy being conducted on the Equity Plan of Action to the regional and sub-regional political leadership at all level to ensure health equity is taken as political priority, and included in the district health plans. The equity strategy was launched in the presence of stakeholders from the four emerging regions and seven sub-optimal performance zones in the Agrarian Regions.

A further achievement was demonstrated through the newly established Health Systems Strengthening Special Support Directorate through building the capacity of the health workforce as well as the health infrastructure. Improving the leadership management and accountability - FMoH has trained 370 health managers at all level of the health system from Somali, Afar, Benishangul Gumuz and Gambella. Also, a process has been initiated for recruiting 59 high level experts/practice leaders for regional health bureaus and zones. One of the challenges is high turnover of health care professionals which affects equity in the health sector. To address that, a design was prepared for construction of staff residential accommodation in health centres found in the periphery and hard to reach areas to retain and motivate staff.

This work has been a major step forward. The Equity Strategy, alone, is the first of its kind in Ethiopia in any sector and it has won the backing of Government at all levels. However, the focus now must be on translating these policies and promises into action.

Summary of responses to issues raised in previous annual reviews (where relevant)
Not relevant as this the first year of implementation and the first review for the programme

Recommendation
- While progress has been made towards reducing disparities in the use of health services, further dialogue at higher level should continue to address and narrow the gap of equity particularly at regional level.
- Despite progress, gaps have continued to be wide among regions in comparison to the national average. Further focus should be continued on the four emerging regions and seven special zones to further reduce the health equity gap.
- Specific, time-bound, metrics should be included in the logframe to measure implementation of the Equity Strategy and more equal health outcomes across genders, geographies and social/economic groups.

Output Title	Increased resources and sustainability of the health sector
Output number per Logframe		3	Output Score	A
Risk:		Major	Impact weighting (%):	30
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress	Score
3.1 Reviews conducted on the progress of implementation of transformational agenda including MiTU, the NHCF Strategy, and FMHACA	1	Concept note for MiTU has been designed and approved by FMOH, Organisational assessment of EFMHACA was also conducted and reform options discussed with the Minister’s office and EFMHACA senior management.	A
3.2 Per capita health expenditure	No milestone set for 2015/16	National Health Accounts (NHA) data comes up every two years	N/A
3.3 Technical assistance provided to FMOH support MiTU, National Healthcare Financing Strategy (NHFS) implementation, and regulatory reform	- MiTU concept note drafted and discussed, / - NHCFS discussed and approved by the cabinet, / - Organisational assessment conducted for FMHACA, and / - A Technical Service Provider has been identified and contractual negotiation initiated.	The progress made in this period includes, / the concept note for MiTU has been discussed with FMOH and was approved. / The NHCFS was approved by the cabinet. / The organisational assessment for FMHACA was conducted & the draft was presented to FMOH & FMHACA. / The procurement for TSP provider has progressed well. Service provider has been identified and the winner has been informed.	A

Key Points
During the review period, DFID's support and SDG-PF have been instrumental in driving forward the key Ministerial Transformation Agendas. A concept note that outlines a road map for MiTU to support the HSTP (2015-2020) has been drafted and was approved by FMoH. The concept note outlines how the Office of the Minister will be re-organised, summarises the transformational priorities of the HSTP; describe the scope of the re-organised Office of the Minister’s office, in particular the scope for the Ministerial Transformation Unit (MiTU), to facilitate achievements of HSTP’s transformational priorities through the existing management and delivery structures (i.e. directorates and agencies of the Federal Ministry of Health, regional and district health offices).

One of the practical actions by the FMoH to ensure inclusion and affordability of health for the poor was through piloting Community-based Health Insurance (CBHI) and Social Health Insurance (SHI). CBHI provides financial protection in case of illness for informal sector employees and rural residents. In this review period, this sector has shown a remarkable success. Currently, the CBHI is covering 6.5 million people with a scale up plan to reach 20 million people by 2020 as part of the NHCF strategy. In 2015/16 (EFY 2008), several activities were planned and implemented accordingly, comprised of: mobilising resources from different partners; implementing innovative health financing strategies; strengthening the health care financing programmes; strengthening health partnership and coordination; establishing health economics and financial analysis case team; and, institutionalising and conducting the sixth round NHA study.

In the reporting period DFID had supported FMoH in conducting an assessment of FMHACA. The agency was set up in 2009 after business process reengineering (BPR) resulted in a recommendation to bring together all regulatory functions into one organisation. FMHACA succeeded the Drug Administration and Control Authority (DACA), whose mandate included human and veterinary medicines only. The main purposes of the review were to assess capacity, motivation, external environment and current performance of FMHACA; and identify change options to enable the organisation to achieve its desired level of performance and its organisational goals. The draft report has already been shared to all stakeholders and the first presentation was conducted in early September. The change options identified through this process has been discussed with the Minister’s office.

Provision of high quality Technical Service Provider (TSP) for up to four years to FMoH to support MiTU, NHCFS implementation, and regulatory reform were other areas of work to be conducted by SAPHE. The procurement for TSP has progressed well. A TSP has been identified and informed by following DFID’s procurement rules.

Separately, DFID Ethiopia conducted its own sector financing analysis – assessing trends in Government allocation and spending and identifying gaps. This work will inform a strategy for DFID’s engagement with Government on domestic financing as part of its responsible exit from the health sector.

Summary of responses to issues raised in previous annual reviews (where relevant)
Not relevant as this the first year of implementation and the first review for the programme.

Recommendations
- Keeping the senior management changes at the FMoH in mind, the scope of the TSP needs to be refined, and the TSP needs to be adequately supported by DFID to make them fully functional and effective.
- Increased effort needed to effectively implement the Health Care Financing Strategy (2015-2020), in particular for increasing domestic financing for health.

Specific, time-bound, metrics should be included in the logframe to measure the progress towards of sustainable, self-financing. DFID should consider moving the outcome indicator (% of public expenditure allocated to the health sector) to output level.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key Cost drivers of the SDG-PF

As set out below, the key cost driver of the SDG-PF in 2015/16 was Public Health Commodity Procurement (31.4%) under which medical equipment and pharmaceuticals were procured. This was followed by health system strengthening, which accounted for 25.7% of the total spend for the year and maternal & child health, which received close to 28.6% of the annual spend of SDG PF.
SDG PF Allocation by components (2015/16)

Expenditure Category	MDG-PF Allocation 2014/15 (million USD)	Share from total (%)	SDG-PF Allocation 2015/16 (million USD)	Share from total (%)
Public Health Commodity Procurement	61,798,719	61.5	64,600,000	31.4
Maternal Health	343,506	0.3	12,000,000	5.8
Child Health Services	3,542,972	3.5	46,809,570	22.8
Prevention & Control of Communicable & Non Communicable Diseases	4,027,635	4.0	18,000,000	8.8
Health Service Delivery	946,421	0.9	2,565,000	1.2
Health System Strengthening	26,614,278	26.5	52,916,350	25.7
Health Extension Program	2,453,590	2.4	7,750,000	3.8
Miscellaneous	778,229	0.8	900,000	0.4
Total SDG PF Expenditure	100,505,350	100	205,540,920	100.0

A recent study for the FMoH revealed that at health facility level, the main cost drivers are human resources and drugs and supplies. For health centres, drugs consist of half (50%) of the recurrent costs on average, while human resources account for an average of 37%. For primary hospitals, human resources and drugs are still the main cost drivers, however they are more evenly distributed (42% and 36%, respectively) and indirect costs are higher compared with health centres. For health posts, 69% of the costs are accounted for by drugs and supplies, and the balance (31%) is for the salaries for HEWs.

VfM Performance Compared to the Original VfM Propositions in the Business Case

Economy: SDGPF contribution to key health system cost drivers

As highlighted in the SAPHE BC, the main inputs (economy indicators) for the health service delivery are costs of commodities (tracer drugs) and skill development of the primary health care workers.

Unit cost of essential drugs

Because of bulk-purchasing by PFSA, essential drug prices are less than the unit prices in comparison with international standards. (See Table 2.) For instance, Magnesium Sulphate and Depo Provera were obtained at prices much lower than the international standard (with the price for the latter falling significantly from the price paid in 2012).

Table 2: Drug price comparisons, PFSA vs International prices, US$
Drug	PFSA Price 2012	PFSA Price 2014	International price (seller - buyer median prices)[2]
Amoxicillin, 125 mg/5 ml suspension, per ml		0.0067	0.0049 - 0.0066
Cotrimoxazole 250 mg/5ml suspension, per ml		0.005	0.0051 - 0.0048
Magnesium Sulphate, 40 mg/ml, per ml	0.44	0.070	0.1062 - 0.1002
Depo prover, vial	0.078	0.489	0.7694 - 1.3
[2] MSH (Management Sciences for Health). 2014. Edition. (Updated annually.) Medford, Mass.: MSH.

The PFSA was consolidating and enhancing efficiency gains by implementing strategic initiatives to strengthen pharmaceutical supply in Ethiopia. Key examples include the following:
- Strengthening forecasting and quantification of pharmaceuticals: A technical working group on forecasting, quantification, procurement, distribution, stock management, and rational drug use was established; vital and essential stock status monitoring templates were developed and put to use; the national vital and essential pharmaceuticals stock status reached, on average, 86% and the stock difference of essential drugs between the centre and branch warehouses has been lowered to 4.1%, below the planned target of 5%; and a list of vital and essential drugs and medical supplies (713 in total) was prepared and distributed to health facilities to facilitate pharmaceutical and medical supply forecasts for EFY 2009.
- Procurement and distribution of essential pharmaceuticals and health programme commodities: The Agency accomplished 72% of the planned procurement for the year; distributed pharmaceuticals and medical supplies worth £672m to health facilities (123% of the planned target of £545m); and effected direct deliveries of pharmaceuticals and medical supplies every two months to 292 hospitals, 1,473 health centres, 644 district health offices, and 49 zone health offices countrywide, following the predetermined delivery schedule in an integrated manner.
- Strengthening the production capacity of local pharmaceuticals and medical supplies manufacturers: With the objective of strengthening local manufacturers engaged in the sector, £27.8m worth of pharmaceuticals and medical supplies, which is 77% of the planned target, was procured from local pharmaceuticals and medical supplies manufacturers.
- Strengthening and Enhancing Systems for Advanced Pharmaceuticals and Medical Supplies and Warehouse Management System: Inventory of pharmaceuticals and medical supplies was conducted at the end of EFY 2007, to have an estimated cost on stock level at hand for 2008 and to further strengthen and enhance stock management; distribution of malaria pharmaceuticals and medical supplies was done in an integrated manner with other pharmaceuticals and medical supplies through an integrated pharmaceuticals logistics system; and efforts were made to minimize wastage rates and enhance proper utilisation of pharmaceuticals and medical supplies by redistributing pharmaceuticals and medical supplies with the highest stock level and slow moving items based on the reports received from branches.
- Promoting Rational Drug Use: To promote the rational use of drugs, various activities including advocacy, training, and public education on rational drug use (including drug storage, handling, use, prescribing, adverse effects) was conducted using print media; to strengthen drug and therapeutic committees at health facility level, a detail service implementation guideline/operating procedure was prepared and 3,000 copies were printed and distributed; supportive supervision was conducted jointly with development partners on 300 health facilities mainly focusing on supply of pharmaceuticals and medical supplies for maternal and child health and 922 health facilities (423 hospitals and health centres, 117 district Health Offices, 370 health posts, and 12 PFSA branches) focusing on supply of pharmaceuticals and medical supplies for child health services, specifically on diarrhoea and pneumonia. Similarly, an assessment was conducted focusing on handling and utilisation of vital pharmaceuticals and medical supplies for paediatrics.

Unit cost of Training for Health Extension Workers
In 2008, 4,642 level III HEWs were enrolled to be upgraded to level IV. Also level III replacement training has been given to 5005 HEWs in line with the upgrading program in all regions. Accordingly, a total of 9647 HEWs were enrolled in EFY 2008. Given the total spend of Birr 44.3 million (£1.6 million) for training of HEW in 2015/16, this translates to £164 per HEW trained which seems reasonable.

Efficiency: SDG-PF contribution to improvements in health system

Efficiency of the SAPHE programme is assessed by looking at the allocations to health system strengthening as well as the cost per output. Like its predecessor, the MDG-PF, the SAPHE programme continued to give priority to health system strengthening by allocating increased resources to trainings and essential health infrastructure. Of the total allocation for SDG-PF, system strengthening accounted for 26% in 2015/16. This supported continued and new trainings of HEWs in the period including level three and four paramedics, bio technicians, and anaesthesia level five. There was also expatriate recruitment from overseas to develop faculties in university hospitals for specialist nursing, including obstetrics and gynaecology.

The first year of the HSTP planned to maintain an increase in the construction of health posts. Accordingly, 33 new health posts were built throughout the country. The cumulative number of functional health posts increased to 16,480 in EFY 2008. Also, the number of new operating theatres also increased significantly. There were also a major construction of blood banks, biomedical workshops, and finalisation of health centres in emerging regions. The installation of solar power in the selected health centres and health posts was also finalised in the year. There were also major medical equipment procurements initiated in the year to strengthen the health system by distributing to primary hospitals.
The unit cost study for the FMoH revealed that the average cost of an outpatient visit for primary hospitals is 223 birr (£8), while for health centres it is 122 birr (£4.4). The cost for in-patient care across these two health facilities is substantially higher with an average cost for primary hospitals of 807 birr (£28.8) per patient and 579 birr (£20.7) per patient. The average cost for a maternal and child health visit within a primary hospital is 317 birr (£11.3), while in a health centre it is 146 birr (£5.2) per patient. The average cost for each delivery in a primary hospital is 576 birr (£20.6), while at a health centre it is slightly higher with an average cost of 705 birr (£25.2) per patient.

Table: Cost per output Estimates (£)
	Health Centre	Primary Hospital
Out-Patient Dept	4.4	8.0
In-Patient Dept	20.7	28.8
Maternal and Child Health	5.2	11.3
Delivery	25.2	20.6

The average ‘unit’ (per capita) cost is 137 birr (£4.9) per patient at the health post level. This is slightly lower than the average per capita cost per patient for primary hospital (147 birr or £5.3) and health centre (131 birr or £4.7).
These unit costs for primary health care are reasonable compared to other countries. For instance, the average unit costs at health centre level are higher in Ghana: US$18 (£12) for an ANC visit and US$63 (£42) for spontaneous delivery at health centres in Ghana[3].For Tanzania the estimated unit cost for ANC visit was US$16 (£10.7) and for delivery at health centre US$ 79.4 (£52.9)[4].
[3] Dabala et.al (2013), Cost of Maternal Health Services in Selected Primary Care Centres in Ghana: a Step Down Allocation approach, BMC Health Services Research 2013 13:287
[4] Saronga et al (2014), Efficiency of antenatal care and childbirth services in selected primary health care facilities in rural Tanzania: a cross-sectional study, BMC Health Services Research 2014 14:96

Effectiveness: SDG-PF contribution to Key Health results

SAPHE’s support to the first year of the Health Sector Transformation Plan helped to maintain the recent gains in health service coverage in the country. Expanding, equipping, furnishing, maintaining, and managing health facilities delivered impressive health results in the review year.
- Contraceptive Acceptance Rate increased from 69.9% in EFY 2007 to 70.8% in 2015/16 and Antenatal Care coverage (at least one and at least four visits) rose from 96.9% and 67.9% in EFY 2007 to 98.4% and 75.9% in EFY 2008, respectively.
- The percentage of deliveries attended by skilled health personnel increased from 60.7% to 72.4% in the same period.
- The proportion of pregnant women counselled and tested for the prevention of mother to child transmission (PMTCT) of HIV increased from 92.6% to 94.8% in EFY 2008.
- With regards to child health services, pentavalent 3, measles and fully immunized children coverage reached 97%, 93.7% and 90.9%, respectively.

The flexible nature of the fund allowed and facilitated DFIDs emergency response to the massive drought and the AWD outbreak in many parts of the country in 2015/16.
Table: Summary of Emergency response costs covered by SDG-PF in EFY 2008
Description	Amount in USD
Measles	6,091,818
Wuha Agar (water treatment chemical)	83,333
Media Messages	199,511
Operational Costs	1,295,196
Total	7,669,859

Cost Effectiveness measures
The SDG-PF continued to deliver VfM on cost effectiveness measures as well. It is still generating over £3 return for each £1 invested and the cost per Disability Adjusted Life Year (DALY) averted is below the GNI per capita indicating the cost effectiveness of the SDG PF.

Assessment of whether the programme represented VFM

The SDG-PF continued to be relevant for the overall health sector development programme of the Government of Ethiopia and that of the UK’s manifesto commitments. Also, the programme’s theory of change as well as the key evidence underlying the cost effectiveness analysis remained valid over the review period. The huge transaction cost savings associated with the pooled fund structure, the unit cost advantage of the bulk procurement by PFSA, the low overhead cost of the programme, the reasonable cost per output and the attractive cost per DALY/ benefit cost ratio suggest that the SDG-PF is delivering very good VfM.

Quality of financial management
SAPHE is a programme that has two main components, SDG-PF (separated as capital and resource) and Technical Assistance (TA, separated as secondment of a DFID staff and Technical Service Provider). The overall programme spending for 2015 is summarised below.
Year	Budget	Disbursement	Variance
2015	£29,984,221.62	£29,984,221.62	Nil

Summary of spend by component:

Component	Approved Budget	Spend
SDG-PF resource (204964-101)	£25,466,000.00	£25,466,000.00
SDG-PF capital (204964-105)	£4,494,000.00	£4,494,000.00
Secondment of Senior Health Advisors for Technical Assistance to FMoH (204964-102)	£24,061.22	£24,061.22
TSP (204964-103)	£160.40	£160.40

For SDG-PF

Date of last narrative financial report	October, 2016
Date of last audited annual statement	N/A. The SDG-PF audit report is to be received in April 2017

Audit
This disbursement made under SDG-PF will be audited in 2016/17 and the report is expected to be received in April 2017. The JFA had put several requirements including this year’s audit reports as pre-conditions for next year’s disbursement. The audit reports required and received during the review period were that of the MDG-PF, on which this pooled-fund has been build.

Financial
The financial audit report for 2014/15 (EFY 2007) of MDG-PF has been received with an unqualified external audit remark. The report showed that all external funds had been used in accordance with the funding agreement and complied with the national laws and regulations. However a few issues were highlighted in this report:
- Asset registers are not complete;
- Some coding errors at regional level;
- Poor financial management in a developing regional states;
- Presence of unutilised balance at the Ministry and some Regional Offices; and,
- A few internal control weaknesses.
Given the recurrent nature of the issues found in the audit, which are listed above, clear plans and actions to address those weaknesses are vital to prevent their ongoing recurrence. DFID, along with other SDG-PF contributing partners, raised these issues with the FMoH. Subsequently, the FMoH has shared status report on 2013/14 (EFY 2006) audit recommendations and a plan of action to address issues raised in the 2014/15 (EFY 2007) audit.
To discuss and strengthen these plans, a meeting was held with the state minister. In addition, a combined risk assurance plan, that address most of the issues raised in the audit report has been developed by the ministry along with DPs (Global Fund and SDG-PF donors), was endorsed and implementation has started. Report on status of the risk assurance plan will be received on a quarterly basis along with the financial and activity report of the SDG-PF.

On top of effective implementation of the combined risk assurance plan, an agreement with ministry had been reached to revise the quarterly financial and activity report in a manner that will reflect status on unutilised funds and balance at PFSA, the national health procurement agency. The last two quarterly reports, received in the new format, show major progress.

The SAPHE programme is also being included in DFID Ethiopia’s ‘Portfolio Assurance Programme’. Independent financial experts will review the programme, testing systems and controls, and will advise on where they can be strengthened.

Procurement

Previously, a backlog of procurement audit reports was a major issue. In this reporting period, the ministry had delivered procurement audit reports for EFY 2006 (2014/15) and 2007 (2015/16) audited by Ethiopia’s Public Procurement Agency (PPA). Findings of these audit reports include: compliance issues with the Government’s procurement procedures including use of uncertified tender documents, limited tender invitation processes, sole sourcing of procurements without sufficient justification and the use of the price negotiation committee, improper notification of bidding process outcomes to competitors, and failure to use standard bidding documents.

Similar to the financial audit issues, these were also followed up with the ministry along with SDG-PF donors. A meeting was held with the state minister to address some of the issues. In addition, strong commitments have been made by the FMoH to effectively implement the risk assurance plan that addresses most of the issues raised in the procurement audit report. Report on implementation status of the risk assurance will be received on a quarterly basis along with the financial and activity report of the SDG-PF. Development partners have established a follow up mechanism to monitor and follow up the implementation and progress of the risk assurance plan.

E: RISK (½ page)

Overall risk rating:
The overall risk rating for the programme during the business case approval was Major. There is no change in 2016.

Overview of programme risk
The programme’s risks are regularly assessed using its own risk matrix which was last updated in May 2016. This sets out operational, fiduciary and corruption, and, environmental and social risks. The Joint Financing Agreement which was signed in June 2015 also contains an Action Plan with actions for strengthening financial and procurement systems, as a result of which a combined risk assurance plan has been developed and implemented.

The combined risk assurance plan was developed and endorsed by FMOH and DPs in June 2016. The risk assurance plan sets out performance, financial management, procurement and supply chain and governance related risks and mitigation measures.

The SDG-PF does not support the Government of Ethiopia’s Commune Development Programme. However, as SDG-PF resources are deployed nationwide it is likely to provide medicines, medical equipment and possibly renovate health facilities in areas where the Commune Development Programme is being concurrently implemented. To mitigate this risk, SDG-PF only provides funding for the renovation of existing health facilities and does not provide any funding for building new health facilities.

Outstanding actions from risk assessment:
DFID, and other SDG-PF contributors, will receive the first quarterly update on the implementation of the combined risk assurance plan. This report needs to be critically examined and timely feedback needs to be provided to the FMoH.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
In general, all elements of SAPHE are delivering as expected. Overall progress is on track to meet next year’s milestones.
Performance of partnership (s)
In addition to 10 SDG-PF partners, during this review period, Global Fund has worked closely with SDG-PF partners in order to align its programme. USAID is also beginning to work closely with SDG-PF.

Management of Asset
In this review period, asset management is only relevant to the SDG-PF component of the programme. All SDG-PF assets are governed by Ethiopia’s public financial management systems. Following a strong desire to have an effective and efficient financial management system, the government of Ethiopia, through Ministry of Finance and Economic Cooperation (MoFEC), has already endorsed and started implementing an Integrated Financial Management System (IFMIS), which includes asset management. IFMIS is an oracle-based financial application currently deployed on 21 selected sites throughout the country for a powerful financial management system. The project is owned and managed by MoFEC, leapfrogging from pilot to roll out, with the help of a pool of staff with diversified skills housed within the project office. FMoH was one of the organisations chosen for pilot implementation of IFMIS. A team composed of seven individuals have been fully involved in supporting the day-to-day operations of the Ministry’s directorates in utilising the system for their regular activities. The Ministry has successfully implemented all nine modules, involving General Ledger, Account Payables, Account Receivables, Cash Management, Public Sector Budgeting, Procurement and Inventory (Supply chain Management), Fixed Assets, and Payroll (Human Resource Management). Currently, all the directorates of FMoH are using the system for their daily operations (especially inventory and fixed asset). Meanwhile, the best practices and lessons learned from the implementation of IFMIS at the FMoH is very helpful in putting the IFMIS system into action for organisations that have a relationship with FMoH. Activities have already started to bring these efforts together in order to implement the system in collaboration with MoFEC at the six organizations, namely: Blood Bank, Federal HIV/ AIDS Prevention and Control Office (HAPCO), Ethiopian Public Health Institute (EPHI), PFSA, FMHACA, and Health Insurance.

DFID carried out a health sector FRA in 2015. This FRA judged the risk of corruption is ‘moderate’ and the overall fiduciary risk is ‘substantial’. The fiduciary risk rating of substantial is largely assigned due to the delay in rolling-out of accounting systems[5] and in conducting external audits, particularly of the health.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant):
The programme-level Partnership Principle Assessment (PPA) is relevant for the SDG-PF component of the SAPHE programme. A PPA was completed for the health sector in October 2016 in alignment with the country level PPA conducted in June 2016. The PPA for the health sector concluded that “Overall the Government of Ethiopia has shown strong commitment to improving the health and wellbeing of their citizens and that there is sufficient evidence of the Government’s commitment to the partnership principles to allow the disbursement of non-budget support financial aid to the SDG-PF.”

Although the country has seen protests across Oromia and Amhara regions since the last update of the country level PPA, and the current State of Emergency, DFID Ethiopia’s assessment is that “it remains appropriate to use aligned financial aid in Ethiopia to deliver results for poor people”.

H: MONITORING & EVALUATION (½ page)

Log Frame
For the purposes of DFID internal AR process, DFID has selected a number of indicators from the HSTP for monitoring performance, which are set out in a DFID specific log frame. The log frame has three outputs with a total of 10 output level indicators. The challenge is that this is first Annual Review for this programme, and three output indicators could not be scored due to unavailability of information/data. An update of the log frame should be done to refine these milestones and their data sources.

Annual Review Process
This was primarily a collaborative desk based AR process, with a week’s inputs by Kourtney Rusow (DFID Ethiopia, Humanitarian and Livelihoods team), Lelise Duga (DPM, DFID Ethiopia), Berhanu Lakew (Economist, DFID Ethiopia) with substantial support from Atsednesh Getachew (DPM for Health and Family Planning, DFID Ethiopia). This review was managed by Atsednesh Getachew and quality assured by Jyoti Shankar Tewari (DFID Ethiopia, Senior Human Development Adviser) and Robert Stansfield (DFID Ethiopia HD Team Leader).

Evidence and evaluation
Data used in this review has mainly been taken from the Health Sector Transformational Plan – Annual Performance Report for 2015/16 (EFY 2008) and Ethiopian Demographic Health Survey (EDHS, 2011 and 2016). Other data sources used include the draft report of the Assessment of the Ethiopian, Food, Medicines and Health Care Administration and Control Authority (FMHACA), concept note on Roadmap for the Ministerial Transformation Unit (MiTU) to support the Health Sector Transformation Plan (2015-2020), Health Care Financing Strategy, and JCF meeting minutes and presentations.

Monitoring progress throughout the review period
In monitoring the progress of the SDG-PF, the pooled fund uses Government of Ethiopian systems and procedures for planning, budgeting, disbursement, financial management, procurements of goods and reporting. This is regulated by a Joint Financing Agreement which defines the responsibilities of partners and how the fund should be governed. There is a Grants Management Unit (GMU) at FMoH which was established in 2015 to assist the government in monitoring its planning, budgeting, and resource utilisation of SDG-PF and grants from other partners.
The SDG-PF is overseen by a Joint Core Coordinating Committee which meets quarterly and includes members of GoE and DPs. This process feeds into the annual review of the health sector, where outputs and outcome targets and progress are reviewed by the FMoH, Regional Health Bureaux and Development Partners. This includes a review of the contribution of the SDG PF to health sector targets.
Reports on SDG-PF financial and activity progress are sent to DPs on quarterly bases showing expenditure against activity. Draft reports are shared on time and these are reviewed by DPs and is then finalised. Progress has been observed in the reporting template in the last two quarters which provides an elaborative picture on the financial and programmatic progress.
Beneficiary feedback
There was no direct beneficiary feedback sought specific to the SDG-PF during this review process. Due to the current security situation in the country, travel out of the city has been difficult. DFID is working with FMoH, the Wold bank and others to carry out the next round of the district benchmarking survey (citizen experience survey) to scientifically obtain beneficiary feedback.