 Annual Review Template – from April 2020

Title: Africa Division funding to the African Agriculture Development Company (AgDevCo)
Programme Value £ (full life): £154.4m		Review date: May 2020 for calendar year 2019
Programme Code: 204270	AMP start date: 24th September 2013	AMP end date: 31st December 2023

Summary of Programme Performance
Year	2014	2015	2016	2017	2018	2019	2020
Overall Output Score	A+	A	A	A+	A	A	A
Risk Rating	Severe	Severe	Major	Major	Major	Major	Major

DevTracker Link to Business Case:	44827985
DevTracker Link to results framework:	47011038

A. SUMMARY AND OVERVIEW [1-1 ½ pages]

Description of programme [1-2 paragraphs]
Over three quarters of people living in extreme poverty in Africa are located in rural areas. Two-thirds of these, mostly women, earn a living from agriculture. Investing in agribusiness (food production, processing and related services) and working with private companies to improve agriculture productivity is one of the most efficient ways to foster inclusive growth. It was for this reason AgDevCo was created over ten years ago and is now active in ten countries. As a UK based agribusiness investor and project developer, AgDevCo’s investment objective is to build profitable businesses that contribute to food security, drive economic growth and create jobs.
[note] 11 if Senegal is counted. The SDU has a programme in Senegal
In addition to adverse weather and climate related events impacting certain countries and markets in 2019, the Covid-19 pandemic has increased the risk to business operations of AgDevCo’s investees since February 2020. The varying country responses on restriction of movement has also impaired AgDevCo staff ability to travel and undertake routine investment and monitoring activities. Whilst some risks are known, there is uncertainty around the extent of the impact and duration. AgDevCo has maintained strong communication with investees and has put in place a defensive response to protect existing investees by making available both financial and in-kind support where appropriate to do so. These challenges are additional to the barriers for agri-business development more broadly that heighten the risk of investing in the sector. AgDevCo was setup to operate in this niche, providing patient capital and ongoing management and technical support to agriculture companies, accepting high risks and moderate returns over time.
The UK had committed £99.5 million to the AgDevCo programme under the central Business Case funded by the Africa Regional Department (ARD), Private Sector Department and the following Country Offices: Ghana; Malawi; Sierra Leone; Tanzania; and Zambia. Additional funding of £55 million was approved in 2018 under a cost extension, bringing the total cost to £154.4 million and extending the programme until December 2023, with the objective of providing AgDevCo with the continuity of funding required to continue progress towards financial sustainability, and to transition towards attracting funding from Development Finance institutions (DFIs) and other capital providers. £1.7m has been earmarked for monitoring, evaluation, and gender focused activities.
This Annual Review covers progress for the DFID Africa Division funding to AgDevCo (i.e. all countries covered through the central Business Case) for the delivery of outputs and progress towards outcomes. Value for money has been assessed for the entire portfolio. Separate dedicated Annual Reviews for the DFID Rwanda and Uganda contributions can be found under projects 204940 and 204012 respectively. A summary table on AgDevCo’s progress in 2019 as a whole and disaggregated by DFID programme can be found in Annex C.

Summary supporting narrative for the overall score in this review [1-2 paragraphs]
The project has scored an [A] overall, and is currently meeting expectations, in terms of delivery and achievements. It continues to operate in varied and challenging environments, resulting in a range of commercial and development impact performance across the portfolio. Both aspects should improve as the portfolio, and AgDevCo’s learnings, continue to develop and mature.
Due to Covid-19 restrictions on DFID staff travel, the Annual Review process this year was limited in scope to desk-based and focussed virtual interviews with DFID country teams (Rwanda and Tanzania). This complemented the ongoing engagement during routine quarterly steering committee meetings and ad hoc engagement on specific investments and operational matters.

The majority of DFID country teams were positive about the role AgDevCo plays, especially as it often operates within a tough market environment. Concerns expressed were largely related to recent changes in AgDevCo’s operating model, where the transition to regional offices from individual country presence has meant changes in level of intensity of local engagement. As with any operating model transformation time is needed for adjustments to be effectively embedded. We will continue to monitor and ensure appropriate feedback loops between stakeholders to adapt the model where required.

Major lessons and recommendations for the year ahead [1/2 page]

Recommendation 1: The methodology for the Outcome 4 indicator should be revised and the targets reviewed to ensure that it more accurately reflects AgDevCo’s progress towards financial sustainability.
Recommendation 2: DFID and AgDevCo to jointly review log-frame indicators on commercial portfolio performance in the light of information already collected and monitored by AgDevCo management and board; and expected involvement of DFI capital in the short to medium term.
Recommendation 3: Given that the targets for both the annual and cumulative value of exports have been significantly exceeded in 2019, the targets for future years will need to be reviewed to ensure that they are sufficiently stretching and reflect the ambition of AgDevCo’s shift in strategy towards financial sustainability, whilst considering the potential impact of Covid-19.
Recommendation 4: With the changes in operational structure to regional hubs, in 2020 AgDevCo and DFID should regularly discuss staff location and ability to support existing investee businesses (including as part of response to COVID19), and identify and mobilise support for new agribusinesses.
Recommendation 5: DFID and AgDevCo should develop principles which act as guidance for both institutions on ways of working and engagement, which are set out in a short document. Both DFID and AgDevCo can benefit from more structured information sharing and collaboration.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [1-2 pages]

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case. [1/2 page]

AgDevCo’s updated Theory of Change is set out in the diagram above. The key change in 2019 was the refinement of the transformational change and additionality frameworks following the external review of AgDevCo’s portfolio for transformational change. The new frameworks clarify definitions alongside the mechanisms by which AgDevCo achieves transformational change using learning from two case studies. The revised frameworks formed the basis of the new tools now used in AgDevCo to score the potential for investments to achieve transformational change and additionality, as well as to track emerging signs of progress during implementation.
The 2019 external review of AgDevCo’s M&E system found that “overall AgDevCo has a strong impact monitoring system in place – particularly in terms of practicality – with many positive features”. AgDevCo has made good progress in addressing the recommendations from the review with seven being completed or in progress. Progress for the remaining five recommendations has been paused during the C-19 pandemic due to capacity constraints, primarily of downstream partners.
In 2019, AgDevCo commissioned a baseline study for the Africado outgrower scheme and a follow up study on the Uzima business model to assess progress for the sales agents and smallholder farmers. AgDevCo also trialled the use of the Lean Data approach for collecting and analysing beneficiary feedback. Findings were disaggregated by gender and age group, and the short set of Washington Group Questions were included to better understand the disability profile of the group of 466 smallholder farmers.
[note] Lean Data is an approached developed by Acumen to rapidly collect and analyse data on social impact performance using low-cost technology and lean experimentation principles.
It is too early to fully assess the extent to which assumptions will hold throughout the C-19 pandemic and within the recovery period. Lessons learned on C-19 implications will be considered as part of the focus for case studies in 2020 depending on the feasibility in undertaking fieldwork.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead? [1/2 page]

Indicators		Milestones for 2019	ARD Progress	Met
1	Value of capital leveraged/invested in agribusinesses annually in 2019 ($) / Total / Private / DFI	$29,580,000 / $7,395,000 / $22,185,000	$24,506,637 / $11,506,637 / $13,000,000	No
	Value of capital leveraged/invested in agribusinesses cumulatively ($) (total)	$222,932,876	$209,545,299	No
2	Total income created to date through exited and active investments ($) / Total / Smallholder farmers / Employees	$44,011,238 / $32,089,411 / $11,921,827	$49,498,134 / $28,780,041 / $20,718,092	Yes
3	Value of exports annually in 2019 ($)	$5,572,476	$125,873,581	Yes
	Value of exports cumulative ($)	$19,757,696	$139,678,545	Yes
4	Percentage of AgDevCo operating costs which are covered by income from investments	40%	30%	No

AgDevCo is on track against two out of the four outcomes, and should be credited for operating in a sector and set of geographies that are challenging. Outcome indicator 4 was substantially stretching, and so the current year outcome shows positive progress towards an appropriate level of cost cover. In the year ahead, as the new investment strategy continues to progress with a growing focus on growth and venture deals, there should be appropriate attention given to the type of capital being deployed between equity and debt including the level of tenor and type of debt. As well as on deepening the level of impact through increased and sustained income uplift of employees and Smallholder Farmers (SHFs).
Outcome 1 (not met): was below the 2019 milestone, and the milestone for cumulative capital leveraged was therefore also missed, despite being 10% higher than 2018. In 2019, 53% of the total capital leveraged was private funding and 47% was from DFIs, which shows a positive shift towards leveraging a greater proportion of capital from outside the conventional international development sources. Tanzania, Malawi and Kenya made up 80% of the capital leveraged in 2019. This is due to large investments in EFTA, Jacoma and Afrimac.

Outcome 2 (met): Overall the total income created this year has exceeded the 2019 milestone by 12%. This is also an increase from the prior year 27%. Despite the progress overall, the current year sub-milestone for SHF income uplift has been missed again, this year by 10% (missed by 16% in the prior year. It is noteworthy that income per SHF increased or stayed the same at every investment from 2018 to 2019 except for a change in uplift methodology impacting results of three investments.
The second sub-milestone, continues to have good results for the total income uplift for employees, exceeding the 2019 milestone substantially by 74%. The rise is driven by a combination of investees increasing their hiring as well as the amount paid per Full Time Equivalent (FTE). Over two thirds of employee income generated continues to be attributable to the Tanzanian portfolio and primarily the EFTA business, with some increased diversification across investments in other countries.
The challenge of delivering longer-term impact will be to grow the portfolio of smallholder engagement and improve income generation. This will also require focussing on lessons learnt and adapting models where appropriate or exiting where not.
Outcome 3 (met): In 2019, the value of export was the highest since 2013 at $125,873,580 and significantly exceeded the milestone. This massive increase in exports are mainly from Kuapa Koko, who exported $80m of cocoa in 2019, although AgDevCo would have exceeded the target without this investment. The cumulative figure will need to be revisited in light of this increase.
Outcome 4 (not met): This measure, in its second year, had a stretching milestone, which has not been achieved for 2019. Using cash income in the calculations, the results for 2019 is 30%. However, this does not given the most accurate representation of AgDevCo’s performance because it excludes a significant amount of income that is accrued at the end of the year. Using an accrued income in the calculations results in 46%. Moving forward, the methodology of the indicators needs to be reviewed to ensure that it more accurately reflects AgDevCo’s progress towards financial sustainability.
Case Study: Westfalia Fruto grows, sources, ripens, packs, processes and markets avocados to international markets. AgDevCo’s investment into Westfalia has helped connect local commercial companies and emerging farmers to export markets. By accessing Westfalia’s infrastructure and services two large commercial agribusinesses and 22 emerging farmers now sell up to 1,000 tons of avocados and litchis on export markets. This has allowed these farmers to considerably increase the price at which they sell their products, and in some cases doubling their revenues. Through demonstrated good performance Westfalia has now also received $1.2m from other funding sources.

Source: adapted from IPE Triple Line case study

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio [1 paragraph]
Based on the analysis of outcomes (above) and output achievement (in section C), theory of change and VfM analysis, there is sufficient evidence that the programme continues to represent good value for money. The programme also continues to be a key part of DFID and Africa Regional Department’s portfolio. The table below demonstrates positive progress on Effectiveness (VfM) indicators for investment committed per SHF and FTE, a decrease in impairment of investments and a negligible increase in write-offs. Progress continues with increasing gender equity, but more needs to be done on identifying the areas of the investee businesses and agri-value chains where equity can be enhanced.
VfM Dimension*	VfM indicator	2016	2017	2018	2019
Effectiveness	Investment committed per smallholder (SHF) engaged ($)	440	613	556	598
	Investment committed per Full Time Equivalent (FTE) jobs created ($)	9,042	12,737	8,471	8,566
	Write-offs (%)	4.00	4.30	10.28	10.32
	Impairments (%)	14.80	18.00	24.50	19.61
Equity	Proportion of smallholder farmers engaged who are women (%)	39.17	42.00	37.93	34.89
	Proportion of Full Time Equivalent jobs which are filled by women (%)	28.19	26.00	23.77	22.36

*Economy and efficiency are covered in Section E
**2018/19 figures exclude the Demeter investment

## C. DETAILED OUTPUT SCORING [aim for 1 page per output]

Output Title	Develop or expand agribusiness enterprises that are financed, owned, or operated on a commercial basis by AgDevCo
Output number:		1	Output Score:	A
Impact weighting (%):		20%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1 Value of investment committed to agribusinesses or agricultural development projects ($) (a) annual (b) cumulative	(a) $29,580,000 / (b) $180,808,752	(a) $26,566,182 / (b) $161,890,088
1.2 Percentage of businesses reporting an increase in EBITDA (%)	50%	68%

Briefly describe the output and provide supporting narrative for the score. [max 1/2 page]
This output provides a core measure of how AgDevCo is putting DFIDs funding to work and improving the profitability of its investees.
In 2019, AgDevCo committed $26,566,182 into the ARD portfolio, which is 10% lower than the milestone. However, the value committed is 43% higher than that in 2018.
Across the whole portfolio, AgDevCo committed an additional $46,594,898 into six new companies and six existing investees. This is the highest annual amount AgDevCo has ever committed. By value, 80% were into Growth deals and 95% of these were debt investments. This is in line with the new investment strategy of rebalancing the portfolio with Growth deals. Companies working in primary production and value addition attracted the majority of the new commitments, followed by processing.
In 2019, 68% of business reported an increase in EBITDA. This exceeds the ARD logframe milestone of 50%. The proportion of companies improving their EBITDA has increased since this measure was introduced in 2016, up from 44% in 2018. Although just one of several measures that can be used to measure a company’s operating performance, the improving EBITDA scores show the increasing profitability of AgDevCo’s investees.
Case Study: Africado Ltd. is a Tanzanian avocado producer and exporter. AgDevCo’s investment in Africado was designed to enable the business to develop in three main interlinked ways of (1) expanding the company’s avocado production capacity by financing a new 175ha plantation; (2) investing in expanded packing shed capacity; and (3) trialling blueberry and macadamia production. Overall the investment is projected to support the creation of 241 full-time jobs, whilst creating livelihoods benefits for Africado’s outgrowers through yield and quality improvements. The 2019 Baseline Study on the Africado outgrower scheme found that overall it is working well, however side-selling was cited as a challenge for longer-term commercial viability.

Source: adapted from LTS International Baseline Study

Describe any changes this output, and any planned changes as a result of this review. [1 paragraph]
No changes during the year or planned.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]
Progress on previous year’s recommendations: Recommendation 1 is in progress given it requires a shift in portfolio; Recommendation 2 is complete.
Lessons learned:
A key challenge for longer-term commercial viability found within the Africado baseline study was the high level of side-selling to informal traders coming across the border from Kenya, who pay farmers in full at the time of purchase. They may also trigger immature fruit and nut to be harvested. These types of issues are also faced by other tree crop outgrower schemes within AgDevCo’s portfolio, including Rungwe Avocado Company (RAC), Tradin and Jacoma. Although there may be benefits to employment, from a commercial viability perspective these schemes need to consider how to limit side-selling and pre-mature harvest as much as possible. The study highlights the importance of having clear information on how prices are calculated and when payments take place and clarity on contracts for outgrowers which may reduce their incentive to side sell.
Recommendations for year ahead:
Recommendation 2: As the portfolio composition evolves to Growth and Venture businesses,
DFID and AgDevCo to jointly review log-frame indicators on commercial portfolio performance in the light of information already collected and monitored by AgDevCo management and board; and expected involvement of DFI capital in the short to medium term.

Output Title	Increase integration of smallholders into commercial agribusinesses through access to irrigation, processing infrastructure, modern inputs, finance, markets and services
Output number:		2	Output Score:	A+
Impact weighting (%):		35%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1 Total number of smallholders engaged to date through exited and active investments / (a) Total / (b) Men / (c) Women	190,252 / 95,126 / 95,126	299,453 / 204,338 / 95,115

Briefly describe the output and provide supporting narrative for the score. [max 1/2 page]
This output demonstrates the extent of AgDevCo investments engaging smallholder farmers (SHF) into the commercial agri-business operations, which is key for achieving the intended development impact. Engaged in this context refers to either an informal or formal exchange (that can be monetised) between a small-scale entrepreneur, farmer, or customer and AgDevCo investees.
Progress against this indicator shows AgDevCo reached significantly more overall SHFs and female SHFs in 2019 than in 2018, although the proportion of women decreased. This is largely due to increased number of Growth working capital deals during 2019. The change in proportion of female SHFs is due to exiting investments which worked with a high proportion of women as well as decreased SHF engagement at Afrioils and Kapani, both of which worked with a high proportion of women.
The impact on SHFs is less concentrated (by country and investment) than in 2018. In 2018, one country made up 73% of the SHF engaged total, whereas in 2019 no one country engaged more than 32%, demonstrating positive progress for distribution of results. Consequently, AgDevCo’s significant improvement in both the overall numbers of SHFs engaged and geographic spread is an encouraging trend for enhancing the development impact of the programme.
With the increase in Growth investments and higher proportion of debt financing as opposed to equity, it will be important to track the sustained transformation that is achieved and any implications of different instrument types on long term impact. Furthermore, where AgDevCo support alongside investment is expected to increase productivity of SHF’s and increase income by extra volume to sell to the AgDevCo investee, lesson’s should continue to be shared of management challenges and market challenges which may have reduced expected SHF engagement or income uplift, e.g. in Malawi - Afri-Oils and Tanzania - RAC.
Case Study: AfriMac Consortium is a group of companies that purchase macadamia nuts from farmers in Kenya. Feedback from 466 farmers highlighted that whilst AfriMac companies are opening up a new market to farmers by bringing access to services that farmers did not have before, there is room to improve social and business performance. Farmers suggested operational fixes such as improved customer service accessibility, provision of inputs such as seedlings, and the provision of bonuses. The survey also highlighted that the greatest gender differences are in the average land size, number of trees owned and seasonal revenue.

Source: adapted from 60 Decibels Afrimac Lean Data Survey

Case Study: Uzima Chicken Ltd in Rwanda is the sole supplier of the Sasso breed – a dual purpose bird that is bred to excel in outdoor ‘backyard’ environments. Uzima promotes the breed through a network of sales agents who rear day old chicks for six to eight weeks and then sell them to smallholder farmers. Since the 2018 baseline study Uzima Chicken has adapted the business model and introduced Cell Poultry Development Ambassadors to reach a greater number of smallholder farmers. The 2019 study found that there are income benefits for both the agents and smallholder farmers and smallholder keeping Sasso chickens are consuming poultry meat and eggs in greater volumes than they did previously. However, smallholder demand is a key constraint to the growth of the business model given the majority of smallholders do not have the available cash nor commercial appetite to invest in large numbers of Sasso birds

Source: adapted from LTS International Follow-Up Study

Describe any changes this output, and any planned changes as a result of this review.
No changes during the year or planned.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]
Progress on previous AR recommendation: Recommendation 3a) complete. Annual Report and accompanying reports from AgDevCo provides analysis on rationale for output variance.
Lessons learned:
The highest development impact within AgDevCo’s portfolio is often achieved where a commercial agribusiness is both a pioneer of a new model and engages with a large network of smallholder outgrowers or customers (e.g. Jacoma and Uzima).
AgDevCo investments are able to reach a larger number of smallholder farmers through aggregation and processing businesses e.g. for cotton, coffee, and cocoa. The impact per farmer is higher where market premia (for quality, fair trade and/or organic) are shared with producers and further deepened through SDU type farmer support programmes.
Recommendations: N/A

Output Title	Increase employment through the development of agribusinesses
Output number:		3	Output Score:	A
Impact weighting (%):		15	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1 Number of jobs created and sustained (FTE) to date through exited and active investments / (a) Total / (b) Men / (c) Women	(a) 10,141 / (b) 5,071 / (c) 5,071	(a) 14,290 / (b) 11,085 / (c) 3,205

Briefly describe the output and provide supporting narrative for the score. [max 1/2 page]
This output demonstrates the development impact created within the economy through jobs created and sustained as a result of AgDevCo investment activity.
AgDevCo’s total active portfolio created and sustained more Full Time Equivalent (FTE) jobs in 2019 than in 2018. Whilst the total FTE jobs for women is under the milestone, this has increased since 2018 (2,652), but the proportion of women in these roles is still low. Given the decreasing trend of the proportion of women benefiting, AgDevCo have not exceeded expectations in 2019 despite the significant progress in creating and sustaining jobs. There should be a continued focus to ensure both men and women benefit from the impact of increasing job creation.
Similar to prior year, the increase in total FTE jobs is being driven mainly by increased employment in AgDevCo’s Tanzania and Malawi portfolio. In Tanzania, EFTA and Rungwe Avocado Company (RAC) experienced the highest increases. In the case of Malawi, Kasinthula (a new impact generating investment in 2019) contributed 565 FTE jobs, while growth at Jacoma meant they hired an extra 138 FTE jobs in 2019.
AgDevCo seeks to achieve gender-equal impact throughout its theory of change, and have continued to focus on this in 2019 despite this being challenging. An example of this is the proactive promotion and support for implementing decent employment policies to protect women and further empower them. In 2019, Goldenlay (in Zambia) began providing women employees special leave days in the event that they need to care for an ill child. They also increased their maternity leave from 90 days to 120 days. SFEL (in Zambia) built dedicated female accommodation, childcare services, and food shops for its employees reducing their time poverty and improving safeguarding.
Describe any changes this output, and any planned changes as a result of this review.
No changes during the year or planned
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]
Progress on previous AR recommendation: Recommendation 3b is in progress and engagement between stakeholders is ongoing. Recommendation 4 is complete through a combination of lean data and impact studies including benchmarking impact systems with a comparator group of investors.
Lessons learned:
For 2019, AgDevCo have been able to undertake an initial analysis on the Full Time Equivalent (FTE) jobs created by sector and by investment type to better understand what are the most effective investments, for maintaining and creating jobs. Initial findings suggest that venture deals created both a high number of jobs and are the most cost-efficient at creating jobs, presumably as they are starting from a low FTE base. The companies that are driving this trend in 2019 such as Kasinthula, Jacoma, Citrum, Uzima, and RAC, are on average more mature than the growth deals, which may account for the observed trend.
Initial observations also suggest that investments in primary production and value addition are more cost-efficient at creating and sustaining jobs than processing, storage, and distribution. This is likely due to these business models being more integrated and therefore require a wider variety of jobs and skill sets than other stages in the value chain.
Recommendations: N/A

Output Title	Investments meet AgDevCo’s criteria for additionality and transformational change
Output number:		4	Output Score:	B
Impact weighting (%):		30	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
4.1 Percentage of investments achieving a score of 3 or higher on level of Transformation Score (as measured by number of investments)	66%	73%
4.2 Percentage of investments achieving a score of 3 or higher on Level of Additionality Score (measured by number of investments)	66%	62%

Briefly describe the output and provide supporting narrative for the score. [max 1/2 page]
AgDevCo ranks all potential investments ex ante based on the extent of transformational change that is expected. In 2019 AgDevCo developed an improved transformational change scoring framework which is more detailed and gives a more nuanced assessment of what transformational change to expect from each investment. Investment teams have reported that the new framework is much clearer than the old one and is easy to use.
Signs of transformational change starting to emerge, primarily in investments over two years old. The primary routes to transformational change are multiplier effects within a community, crowding-in value chain actors, supportive infrastructure and services for a value chain, and establishing new agricultural industries. The most common transformational change taking place in 2019 was crowding investment into value chains by stimulating growth up and down stream for AgDevCo’s investees.
This year 73% of AgDevCo’s investments were considered transformational, which is slightly higher than in 2018 (71%). There are various examples of how AgDevCo’s investees are stimulating growth up and down the value chain, for example Transurban and Uzima are selling their manure biproducts to local organic companies who are now benefiting from a consistent supply of organic fertiliser. Other examples provided include how investee companies such as Westfalia, has helped emerging and commercial farmers to meet international certification standards required for export. This has enabled access to premium markets.
In terms of additionality, 62% of investments achieved a score of 3 or higher, which is slightly below the target of 66% and lower than last year’s score of 74%. This lower score reflects AgDevCo’s shift towards investing a higher proportion of its portfolio in Growth deals as part of its commitment to increasing its overall financial sustainability for attracting private investment. Growth deals make up 39% of total value, in general have low additionality (22% only scored highly) but have high transformational scores. Most of the impact for expansion Growth deals is indirect. Given the decrease in additionality below the annual threshold for maintaining performance the output has moderately not expectations.
Describe any changes this output, and any planned changes as a result of this review.
AgDevCo’s Transformational Change framework was revised in 2019 following an external review of transformational change within AgDevCo’s portfolio. The new framework clarifies definitions alongside the mechanisms by which AgDevCo investments could contribute to transformational change. A new scoring tool now accompanies the framework, with AgDevCo investment teams now needing to screen potential investments by the three transformational change drivers and the likelihood for each rather than providing an aggregate score.
AgDevCo’s Additionality Framework was also revised in 2019 to complement the changes to the Transformational Change framework. The new framework now includes both financial and non-financial additionality, and the scoring criteria for the other finance options available to investees instead of solely examining EBITDA and profitability.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]
Progress on last year’s recommendation: Recommendation 5 is complete. Recommendation 6 is in progress with internal DFID discussions and engagement with AgDevCo continuing on ways of working.
Lessons learned:
Key lessons from the transformational change case studies include:
- Community uplift is more likely to come from employees than smallholder farmers due to the geographic concentration of increased incomes, making spillovers more likely
- Expenditure priorities for additional incomes most often centre around schooling
- There are strong demonstration effects when working with emerging farmers, especially when producers are organised in an association. In the case of Westfalia, only 4 farmers initially sold litchi through Westfalia, while now over 200 are on track to start producing commercial grade litchi in the next few years. However, women are less likely to benefit as they tend to have access to less land and capital.
- In the case of Westfalia, to adapt to new production techniques and business practices to lead to more transformational change, behaviour change in a number of areas was required including business management skills and shifting attitudes towards traditional gender roles.
Formalisation of labour can have unintended positive benefits of increasing access to financial services. For example, previously unbanked employees for investee were being paid through bank accounts, which indirectly led to increased availability of ATM’s in the local area.
Recommendations: N/A

D: RISK [½ to 1 page]

Overview of risk management [1/2 page]
The overall risk continues to be major. This is due to AgDevCo currently shifting strategy towards financial sustainability, which is compounded by the emerging C-19 pandemic. The major risk rating is within DFID’s appetite and reflects AgDevCo’s pioneering business model of investing in agribusinesses in Africa that cannot access finance from other institutions.
Risks are monitored quarterly through a Steering Committee chaired by the DFID SRO and attended by AgDevCo HQ, DFID Africa Regional Department, and DFID country offices. Both DFID and AgDevCo have separate risk registers that are updated, shared, and discussed. A delivery chain risk map is also updated quarterly and submitted to DFID with following each disbursement, and the latest update also included C-19 risk analysis. DFID country offices also escalate risks on an ad-hoc basis to that Africa Regional Department as needed.
Health and safety, safeguarding, external operating environment, and business integrity risks were key risks that were monitored in 2019 by AgDevCo and discussed during the Steering Committee meetings. AgDevCo continues to implement risk action plans, which often include AgDevCo specialist teams providing technical assistance and training. AgDevCo also leverages its equity stakes within the portfolio to strengthen the risk management capabilities of the downstream partners for which AgDevCo has a controlling stake.
Emerging risks during the reporting period have primarily been contextual risks. For example, foot and mouth disease emerged as a risk for a Zambia investment, which was managed through establishing an onsite abattoir to allow meat to be produced and sold without animal movements. More recently, the evolving C-19 pandemic has a potential major impact on the programme delivering the results within the intended timeframe. AgDevCo have increased the level of engagement and support to existing investees who have identified potential workforce and supply chain challenges. The table below outlines the key risks and mitigation strategies.
AgDevCo has implemented all the recommendations related to the major risks identified in DFID’s 2018 Due Diligence Assessment and has made good progress for the moderate risks identified.
Key Risk Identified	Mitigation Strategies	Risk Assessment
AgDevCo not receiving funding from DFIs so DFID either loses its investment or must invest more in AgDevCo. Potential causes include perceived high risk of investing in AgDevCo or the limited profitability of agri-business investments.	AgDevCo continues to discuss with potential investors the feasibility of investing in AgDevCo and is diversifying the risk profile of the investment portfolio.	The net risk rating continues to be major. Escalation or de-escalation of the risk is anticipated in 2020 depending on whether DFI funding materialises within the year.
Ongoing trade-off between development impact and financial sustainability resulting in AgDevCo not simultaneously promoting poverty reduction and economic growth. Potential causes include limited staff capacity in leaner structure, and management choices to promote financial sustainability over poverty reduction.	DFID continues to monitor AgDevCo’s portfolio for additionality and impact, including feedback from country offices. AgDevCo commissions development impact studies, with oversight from DFID to ensure robust methodology.	The net risk rating continues to be major with an upward trajectory during the C-19 pandemic. In 2019, AgDevCo continues to be on track for promoting poverty impact, however the sustainability of these impacts is at risk due to potential deterioration of investee business performance during the C-19 pandemic.
At the country level, standards for environmental, social, and governance safeguards are lower than international best practice resulting in harm to individuals or the environment.	AgDevCo has implemented DFID’s due diligence recommendations and has undertaken an ESG and gender audit. AgDevCo continues to screen potential investees for ESG risks and oversees implementation of recommendations.	The net risk rating continues to be moderate. AgDevCo has strengthened ESG risk management capacity and capability however the ongoing C-19 pandemic limits the team’s ability to conduct site visits.
C-19 Risks Identified	Mitigation Strategies	Risk Assessment
Continuing C-19 pandemic worsens with Governments restricting the movement of people to stem the spread of the virus. Potential impacts include: deteriorating macroeconomic situation with lost income and job; blockages in the food supply chains; loss of appetite to invest in Africa.	The extent to which the risk is mitigated is primarily outside of the team’s control. AgDevCo and DFID are monitoring changes in the context at least weekly using information and analysis provided by AgDevCo downstream partners, WHO, World Bank, IMF, AGRA, and others.	The net risk rating is major. The C-19 pandemic continues to worsen and there is a potential major impact on programme objectives. It is too early to fully assess the extent to which the negative impacts are materialising.
Reduced capacity of DFID, AgDevCo, and downstream partner staff due to staff illness, restriction of movement, or increased caring responsibilities. Potential impacts include: reduced staff health and wellbeing; no site visits; food crops are not harvested or processed.	AgDevCo and DFID have business continuity plans in place, and teams are working from home. AgDevCo and DFID have had weekly catch ups on C-19 implications and strategic issues.	The net risk rating is major. AgDevCo and DFID continue to be able to operate with no staff C-19 illness to date, however it remains likely that the capacity of downstream partners will be impacted.
Continuing C-19 pandemic worsens and AgDevCo unable to deliver the desired results in 2020 and beyond due to the sustained disruption in activities.	AgDevCo assessed the risk exposure of each investment to C-19 related operational and delivery risks alongside the need for emergency finance or rescheduling of loans. AgDevCo is in regular communication with investees. AgDevCo has also written to all investees and hosted a webinar to provide guidance on managing operations through the crisis.	The net risk rating is major. The C-19 pandemic continues to worsen and there is a potential major impact on programme objectives. Despite this, food value chains have been prioritised in the majority of countries so the risks may not fully materialise. It remains too early to fully assess the extent to which the negative impacts are materialising.

E: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE [1 - 1 ½ pages]

Summarise the performance of partners and DFID, notably on commercial and financial issues, and including consideration of VfM measures of economy and efficiency. [max 1 page]
Delivery Performance
As part of progressing towards financial sustainability AgDevCo has shifted towards a regional operating model rather than having teams in each country. The restructuring is now in full effect with the targets, staff, and investment pipeline activity being managed by three regional hubs. The type of technical assistance support AgDevCo provides to downstream partners has also shifted. Increasingly AgDevCo is working with established businesses (typically in their growth phase) for which the focus is on improving existing systems of control rather than building the necessary systems to move from small to medium enterprises.
Improvements in 2019 included:
- The legal, agriculture, and ESG teams developed a tool for the investments teams to better manage risk and compliance for those companies that AgDevCo has an equity investment in.
- Refresh of the Gender Strategy and Action Plan in response to the 2018 Gender and ESG Audit
- Updating investment papers to more explicitly address climate risk and resilience measures.
In 2019, consultants undertook a survey across 25 companies (AgDevCo finances or has investment in) to solicit feedback on AgDevCo’s technical assistance support. Overall there was a high level of awareness of the type of support services AgDevCo offers and respondents often cited the helpfulness of AgDevCo’s teams and the quality of available resources. Respondents were less satisfied with the compliance services due to the resource intensive nature of the process.
AgDevCo rapidly developed a Business Continuity Plan in response to the emerging C-19 pandemic and proactively undertook a risk assessment of the investment portfolio and has developed an approach for supporting existing investees through the crisis. AgDevCo has also written to all investees and hosted a webinar to outline guidance for escalating and managing emerging operational, human resourcing, and community risks. It is too early to fully assess to what extent AgDevCo has been able to adapt to the ongoing C-19 pandemic and mitigate against negative impacts.
Commercial Performance
AgDevCo continues to fulfil the key provisions within the Accountable Grant Arrangement and teams proactively check whether new scoping activities are within scope. AgDevCo shares an updated asset register annually, however DFID is unable to spot check asset management for 2019 due to the C-19 travel restrictions. AgDevCo also continues to submit the six-monthly reports on time, which are well-structured.

Financial Performance
VfM Dimension*	VfM indicator	2016	2017	2018	2019
Economy	Fund management cost ratio	3.1%	3.3%	2.8%	2.5%
Efficiency	Administrative cost ratio	5.3%	6.1%	4.3%	3.8%
	Leverage ratio	$1.54	$1.37	$1.78	$1.40

*Effectiveness and equity are covered in Section B
**2018/19 figures exclude the Demeter investment
For 2019, AgDevCo had budgeted for a core loss of $4.6m however the actual loss was $3.7m so $0.9m (20%) better than anticipated. This was primarily driven by cost savings through the regional restructure with staff, office and travel costs being below budget. Due to the lower costs, both the fund management and administrative cost ratio continued to improve as outlined in the above table.
Concurrently, the actual income received from investments was $4.3m, which was $0.5m (9%) worse than budgeted. This was due to the delays in disbursing committed investments, which delays the timing of AgDevCo receiving income.
The leverage ratio is lower in 2019 than 2018 as the rate at which AgDevCo was able to commit additional investments significantly outpaced the rate at which funding was leveraged by the private sector and DFIs.

Date of last narrative financial report	15th April 2020
Date of last audited annual statement	Calendar Year 2019 (TBC – the auditors now have additional processes to finalise the opinion due to Covid-19, which has caused a delay in a final audit report)

Annex A: Annual Review Process

The core team comprised of a Senior Private Sector Development Advisor, an Economic Advisor, and two Programme Managers. Due to the travel restrictions during the ongoing COVID-19 pandemic at the time of the review the assessment is primarily based on a document review of AgDevCo Annual Reports and in-year monitoring information. Information has been triangulated to the extent feasible with interviews with DFID Country Offices and the independent case studies and longitudinal studies undertaken in 2019/20.

Annex B – Revised Transformational Change and Additionality Scoring Criteria
AgDevCo Transformational Change Scoring Criteria
1 = All three transformational change drivers are “not present”
2 = One “moderate” and two “not present” transformational change drivers
3 = Two “moderate” and one “not present” or all are “moderate”
4 = At least one transformational change driver is “strong”.

AgDevCo Financial Additionality Scoring Criteria
	Available Finance	Indication	Benchmark
4	No funding from concessionary or commercial financial sources is available. Or AgDevCo is responsible for the origination and concept development for the deal.	Commercial and concessionary finance has not been provided for a reasonable period of time.	Kasinthula, Babator, Satemwa
3	Funding is available from concessionary financial sources but not on terms that accept the same risks appetite as AgDevCo’s finance.	DFIs or impact investors have invested in the past/are still invested but offering terms that are more risk averse than AgDevCo.	Miro 1
2	Funding with similarly viable terms* is available from concessionary financial sources.	DFIs or impact investors have invested in the past/are still invested in making similar investments in the company as AgDevCo.	GADC, Kuapa Koko, Africado
1	Funding with similarly viable terms* is available from private/fully commercial financial sources.	The investment is competitive against commercial financial institutions, or commercial financial institutions were/are already invested.	Blueskies, Meridian, Goldenlay
[note] Concessionary finance excludes grants and includes all finance that is provided with the intention to generate positive, measurable social, economic and environmental impact alongside a financial return

AgDevCo Non- Financial Additionality Scoring Criteria
	Assistance Offered By AgDevCo	Indication	Benchmark
4	Offering non-financial assistance that will improve the development impact of the company and no other interested investors (commercial or concessionary) will/can offer. Or AgDevCo is responsible for the origination and concept development for the deal.	No other available funding is offering this assistance and there is a clear narrative on how this assistance will change outcomes for employees and SHFs.	Babator, Satemwa, Dekeloil
3	Offering non-financial assistance that will improve the development impact of the company and is not available to the company from commercial lenders but is available to this company from concessionary investors.	The assistance planned for the investee in the IA goes beyond complying with AgDevCo minimum requirements, and we have evidence other concessionary investors provide very similar assistance to this investee.	Jacoma, ECA, Westfalia
2	Offering non-financial assistance that is limited to assisting the investee to comply with AgDevCo standards and is not available to the company from commercial lenders but is available to this company from concessionary investors.	The ESG, EDT and agriculture assistance panned for the investee in the IA focuses on complying with AgDevCo minimum requirements, which we have observed other concessionary investors provide to their investees.	Minimex, Uzima
1	Either offering no non-financial assistance*, or only offering non-financial assistance which is also available from other interested/potential commercial investors.	The company already receives similar assistance from a commercial investor, or interested commercial investors provide this assistance to their other investees.	Blueskies, Afrimac

Annex C – AgDevCo output delivery and progress towards outcomes for 2019