Annual Review - Summary Sheet

Title: Effective Health Care (EHC) – Research Programme Consortium (RPC) 2010-17
Programme Value: £6,457,012		Review Date: October 2016
Programme Code: 201400	Start Date: Nov 2010	End Date: 31st January 2017

Summary of Programme Performance

Year	2011/12	2012/13	2013/14	2014/15	2015/16
Programme Score	A+	A+	A	A+	A+
Risk Rating	Medium	Medium	Medium	Medium	Moderate

Summary of progress and lessons learnt since last review

The Effective Health Care Consortium is an international research consortium led by the Liverpool School of Tropical Medicine. The RPC includes the Cochrane Infectious Disease Group which produce robust systematic reviews, summarising available evidence. The RPC’s aim is to improve health care for the poor by ensuring that decisions are based on best available evidence. Further objectives are to increase the use of the results of the reviews and to build capacity.

The programme is moderately exceeding expectations and has made good progress to deliver its objectives, confirmed by the positive Mott-Macdonald independent evaluation and the independent stakeholder analysis in 2015. Since 2011 the RPC has produced over 120 new and updated Cochrane Reviews, including 26 in the year under review, as well as other types of research and systematic reviews. In addition in the last year, there is good evidence of their results being used in global guidelines, for example, World Health Organistion (WHO) guidelines on daily iron supplementation in children; in national guidelines, for example, the Indian Government’s guidelines on extra-pulmonary tuberculosis; and on capacity development, for example, 39 authors from lower and middle income countries (56% women) have had articles published in peer reviewed journals.

The performance of partners is in line with their budgets and the RPC uses results-based financing. Programme management and administration remains strong and the programme continues to represent good value for money. There is strong leadership in place across the RPC and measures have been taken to support succession planning.

There were four recommendations in the last annual review which have all been successfully implemented.

Summary of recommendations for the next year

DFID and the RPC should clarify cumulative figure for the different types of research and reviews by end January 2017.

The RPC to work with the communications office of the Liverpool School of Tropical Medicine on a messaging section for the dissemination checklist and to evaluate its effectiveness by March 2017.

The RPC to continue to look for opportunities to influence the introduction of Codes of Conduct by October 2017.

A. Introduction and Context

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-201400/documents/
DevTracker Link to Log frame:	http://devtracker.dfid.gov.uk/projects/GB-1-201400/documents/

Outline of the programme
There is a need for reliable, evidence-based syntheses and summaries of research to improve the health care for the poor in low and middle income countries (LMIC). Better evidence for health care interventions can lead to informed decision making, promotion of more effective interventions and treatments, and reduced wastage on ineffective health care. Reliable systematic reviews are a prerequisite to translating research into policy and practice: they can help inform decisions in policy and clinical practice and identify research gaps.

The specialist methods and skills required for research synthesis have developed rapidly over the last 15 years and are now clearly established. This Effective Health Care RPC for Evidence Building and Synthesis Research is part of the Cochrane Collaboration, which is having a major impact on systematic review methods globally and is a major producer of reliable reviews. The investment made by this RPC in capacity building will help ensure that these methods are understood by LMIC researchers and that they develop the requisite skills to undertake scientifically defensible systematic reviews themselves.

The UK is providing £6 million over the period 2011 – 2016. In 2015 this was extended to £6.5 million to January 2017. The objectives are to generate high quality, reliable systematic reviews of the evidence for health relevant to LMICs with the ultimate aim of improving health care for the poor and accelerating achievement of the Millennium Development Goals (MDGs). The MDGs have now been replaced by the sustainable development goals (SDGs) and the consortium has assessed whether its reviews were still relevant. All of its Cochrane reviews and all but 8 other reviews are well aligned to the SDGs, particularly SDG 3 (good health and wellbeing) and SDG 10 (inequality).

The main results areas were:
- Rigorous systematic reviews relevant to the MDGs/SDGs. The RPC will build on its existing work in Cochrane reviews, broaden the scope, and include organisation and financing of care;
- Relevant, accessible messages in reviews and dissemination products. The RPC will improve access, build on existing products, diversify for specific target audiences, and use a variety of multimedia approaches and Web tools to maximise uptake and use of results;
- Stronger policy networks that demand and use evidence. The RPC will build links with policy networks through dialogue, products and facilitate the use of evidence in decision-making;
- Increased capacity in evidence building and research synthesis in partners and stakeholders.

The focus of reviews are communicable diseases (malaria, TB, diarrhoea and neglected tropical diseases), organisation and financing of health care, nutrition and aspects of food security, child health, maternal health, growth, aspects of HIV, poverty and gender.

## B: PERFORMANCE AND CONCLUSIONS

Annual outcome assessment - A+ – Outcome moderately exceeded expectations

The RPC is making good progress and has moderately exceeded expectations towards its outcome of an increased number of evidence-informed decisions by global and national organisations, networks and decision-makers that will benefit the poor.

The RPC has had another strong year and looks likely to exceed its targets on new or amended policies, guidelines and major financing decisions influenced by its evidence. Since 2011, the RPC has produced over 120 new and updated Cochrane Reviews, including 26 in the year under review, as well as other types of research and reviews. New examples include the uptake of their evidence by global guidelines in multilateral agencies e.g. WHO guidelines on daily iron supplementation in children and on national guidelines e.g. the Indian Government’s guidelines on extra-pulmonary tuberculosis.

More broadly, the RPC is continuing its institutional strengthening. For example, active participation on WHO technical working groups and guideline committees is supporting the development of more robust guidelines that are based on graded evidence. The RPC is supporting the Cochrane Collaboration to adopt a number of the RPC’s approaches, such as use of stakeholder dissemination strategies and review classification frameworks, standardisation of language for abstracts and Cochrane editor training.

Overall output score and description – A+ – Outputs moderately exceeded expectations

This RPC has had another good year, substantially exceeding expectations in the number of systematic reviews produced and have increased the number of platforms and outlets for disseminating the information. They have also exceeded targets for the number of new authors and editors from Southern institutions, a reflection of their capacity building strategy.

There were some challenges with the RPC having taken over the HIV/AIDS portfolio last year. The team reviewed the portfolio and rejected a number of reviews, either because of quality or relevance. The increased workload may be relieved by the Cochrane Steering Group agreeing to fund a post to help.

International Development Act (Gender Equality) 2014
The programme was commissioned before the introduction of the Act, but has had a focus on gender equity in its work and has a gender monitoring plan since the end of year 1. This focuses on 3 aspects: the impact of research on women (i.e. the number of reviews on topics that directly address women’s issues); participation of women as authors, editors and at events; and the progress and/or recognition of women. The programme synthesises existing research findings and is able to identify gender and equity outcomes in all areas of work. The finalised systematic reviews highlight where there are gaps in the existing evidence-base and make recommendations, including ensuring that gender equality and equity are included in future research. The consortium promotes the involvement of female reviewers and pays attention to the gender balance of the staff composition. Of the 26 Cochrane reviews completed in the last year, approximately 50% related to women and gender issues, with half of these having a direct focus. One out of three new editors this year was female as were 4 out of 9 first-time authors of reviews.

Key lessons
Previous lessons are still relevant. In addition, what is emerging is that the capacity building is resulting in partners moving on and upwards to new opportunities. Although a sign of success, it leaves institutions or groups understaffed with the need to start building capacity of new people.

An independent evaluation in 2015 was very positive and the RPC has addressed most of their commendations. There are plans to address all outstanding recomendations (see more under individual outputs).

Has the logframe been updated since the last review?

No. The logframe should be updated if the extension is approved.
## C: DETAILED OUTPUT SCORING

Output Title	High quality, up to date Cochrane or related systematic reviews relevant to improving health outcomes for the poor
Output number per LF		1	Output Score	A++
Risk:		Minor	Impact weighting (%):	40%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
1.1: Number of new Cochrane Reviews, relevant to the content and delivery of poverty-related health programmes	Target 10 each year	Target achieved – 10 new reviews
1.2: Number of updated Cochrane reviews, relevant to the content and delivery of poverty-related health programmes	Target 5 each year	Substantially exceeded expectations: 16 updated reviews
1.3: Number of qualitative reviews, scoping reviews, overviews, systematic reviews relevant to the content and delivery of poverty related programmes	Target 2 each year	Substantially exceeded expectations: 15 new other reviews

Key Points
The programme has substantially exceeded the target number of reviews to be carried out or updated in the last year. Topics continue to be those most relevant to poor people such as malaria, tuberculosis, diarrhoea and unintended pregnancy. A significant proportion of the reviews were led by teams based in Africa and Asia.

Summary of responses to issues raised in previous annual reviews (where relevant)
The RPC should strengthen efforts to explicitly include gender and equity issues in Cochrane reviews. The RPC should fully implement the ‘gender monitoring plan’ and report on this in the next annual report.
Done – the RPC does considerable monitoring of its gender plan and responds where necessary. In one case they noted a gender imbalance of participants at an event and worked with partners to address it.

The RPC should monitor and manage risks relating to the new HIV and AIDS portfolio especially those specified in its risk register and report on this to DFID by May 2016.
Done – As well as managing the portfolio described above, they have actively managed the risks and, for example, recruited a series of experienced authors as editors and extended the LIXA training to include HIV.

Recommendations
DFID and the RPC should clarify cumulative figure for the different types of research and reviews by end of January 2017.

Output Title	Accessible products for knowledge uptake
Output number per LF		2	Output Score	A+
Risk:		Moderate	Impact weighting (%):	30%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
2.1: Number of new dissemination platforms identified that we can then regularly contribute to. Such as regular column in a journal, a blog that the RPC regularly contribute to.	1 new series	Met expectations: 1 new series produced
2.2: Number of discrete demand projects (specific reviews, training courses, or synthetic technical products to support guidelines commissioned by national decision-makers or intermediary organisations and networks ("pull" products)	Target 2 each year	Substantially exceeded expectations: 6
2.3: Level of stakeholder engagement and satisfaction assessed via establishment and evaluation of stakeholder management plans	First survey by May 2013	Achieved in February 2015. No further targets

Key Points
The RPC has moderately exceeded expectations for this output. It has continued to explore and identify new outlets for disseminating the results of its reviews. Following the success of the ‘Cochrane Corner’ in the International Journal of Epidemiology, the South African Medical Journal has agreed to introduce the same and published summaries of three reviews on disparate topics of immunisation, smoking and HIV/AIDS.

All partners work on a wide variety of demand projects. For example, in South Africa, they have responded to requests from the National Department of Health to provide systematic review evidence on diet for preventing obesity and treating obesity; and to produce a three day evidence primer on essential medicines, based on the course developed by the RPC. The World Health Organisation commissioned the Nigeria consortium partners to conduct reviews to inform the global guideline development on the management of health complications from female genital mutilation.

Summary of responses to issues raised in previous annual reviews (where relevant)
Continue the good work on development of accessible products, aiming to address the recommendations of the independent evaluation of stakeholder engagement and satisfaction and report on these in the next annual report.
The RPC continues to develop new ways to make results more accessible as outlined above and has fulfilled most of the recommendations in the independent evaluation.

Recommendations
The RPC to work with the communications office of the Liverpool School of Tropical Medicine on a messaging section for the dissemination checklist and to evaluate its effectiveness by March 2017.

Output Title	Consortium partner institutions and researchers in the South have increased competence for research
Output number per LF		3	Output Score	A
Risk:		Moderate	Impact weighting (%):	30%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
3.1: Number of institutions with a developed strategy and code of conduct to promote research integrity	Target 1 per year	Target partially achieved: all collaborating institutions have adopted publication policy of the RPC although achieving codes of practice is more difficult.
3.2: Number of new Cochrane editors appointed or new authors completing reviews from Southern Institutions	Target 1 editor in total and 8 authors per year	Moderately exceeded expectations: 3 new editors (1 female:2 male) and 9 new first authors (4 female: 5 male)
3.3: Number of Partners with multiplier funding at least matching DFID investment	Target 1 partner each year	Substantially exceeded: 4 partners received new grants this period

Key Points
The RPC is meeting expectations for this outcome. It is continuing to see results of its capacity building with the number of new authors and editors exceeding targets, with a good gender balance. Its Learning Initiative for eXperienced Authors (LIXA) continues to contribute to these results. They are helping Cape Town move to a capacity for editorial management, which will be vital for future sustainability and a similar approach will be developed with malaria for the sharing, and ultimately transfer, of responsibilities. They continue to monitor gender representation in a variety of indicators such as meetings, panels, rewards etc. The proportion of women ranges from 42% (prizes, panel, external recognition) to 58% (events and visiting fellows).

The RPC continues to receive additional support, with Vellore, Fudan, Cape Town, Nigeria, Cameroon and Kenya all having at least matching funds and infrastructure report. New external grants were received this year for China, South Africa and UK teams.

Addressing research integrity is a challenging area. The Consortium has developed a Publishing Policy to help address the issue and this has been adopted by all partners. Achieving institutional codes of practice is more difficult because the researchers in the consortium do not necessarily have institutional responsibilities or authority. The exception is India, where the partner advises government and other institutions on these matters. Additional policies are being developed including a policy for dealing with potentially fabricated data with the Cochrane’s Editor in Chief.

Summary of responses to issues raised in previous annual reviews (where relevant)
Senior colleagues from the Cochrane Collaboration should join the RPC, to discuss their potential role in improving standards of research integrity globally, at the next review meeting with DFID staff.
Done – The Chief Executive of Cochrane is now a member of the Consortium Advisory Group. In addition, a joint meeting between DFID, the consortium and the Cochrane Central Executive was held in April 2016.

Recommendations
The RPC to continue to look for opportunities to influence the introduction of Codes of Conduct by October 2017.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance
Key cost drivers are direct/indirect staff, travel and supervision costs. Managing these includes policies such as terms of reference being used as a benchmark to assess whether travel is justified. Air travel is always in economy; the number of people travelling to conferences is kept to a minimum; and electronic communications are used when possible. The RPC makes efforts to obtain discounts on large, repeat purchases. The main cost driver, other than review production, is personnel costs which are reasonable when benchmarked against recommended sector rates.

Since 2014, communications has been contracted to an in-house media team; this costs only 60% of the original full time staff member; services provided are reported to be excellent. Use of results-based financing approach continues successfully. The budgets for two partners were reduced this year. Partners are now performing satisfactorily in line with revised budgets.

VfM performance compared to the original VfM proposition in the business case
The RPC is performing well against its targets and significantly over-performing on several output indicators while remaining under-budget. Financial forecasting is strong but they have been running with an underspend since the second year. However they keep DFID well informed. Forecasting by partners shows larger variations; the RPC has recognised this and corrective actions are taken when required.

The RPC has estimated that their systematic reviews cost on average less than £66K each, well below estimated norm for a systematic review (£100-200K). The RPC observes that it does many large, technically complex reviews that probably cost considerably more than smaller ones.

Assessment of whether the programme continues to represent value for money
Overall the RPC continues to represent good VfM. It continues to perform well with more results than anticipated, and the RPC is paying careful attention to cost containment. The RPC uses results-based contracting as a key management strategy and carefully monitors the quality of all outputs. The systematic reviews assist decision makers to identify, access and use the results of good quality research to inform policy, and highlight future areas of investigation for other researchers. This allows research funds to be targeted where they are most useful, reduces poor quality research by setting standards, and prevents unnecessary duplication or expensive clinical trials.

Quality of financial management
The lead partner has a strong financial monitoring and management system in place, which enables senior managers to monitor spend against budgets and workplans. All partners are required to report against standardised expenditure items covering personnel, travel, programme costs, equipment, systematic review production, research uptake, with over/under-spend against the budget clearly indicated. Partner narrative and annual budgets are reviewed six monthly against a template that includes an assessment of VfM – these reviews take place within a results-based financing framework and focus primarily on the efficient production of deliverables and effectiveness. The lead partner uses performance-based funding to its partners. It has a strong track record for careful management and financial oversight, and robust counter fraud and anticorruption policies in place. There have been no cases of fraud or corruption reported this year.

Date of last narrative financial report	June 2016
Date of last audited annual statement	Nov 2015. Report for year ending July 2016 expected November 2016

E: RISK

Overall risk rating: Moderate

Overview of programme risk
Overall the risk is unchanged but now ‘moderate’ under DFID’s new classification. The RPC management team and Consortium Advisory Group regularly review the risks and update their risk register.

The main risk for DFID is that there could be insufficient capacity to meet the growing demand for complex and specialist systematic reviews. The advance LIXA training for experienced authors is helping to address this. There are also capacity risks associated with the group’s new responsibilities for Cochrane HIV and AIDS reviews. This has been mitigated by reviewing the portfolio and rejecting some of the planned reviews. In addition, the Cochrane Steering Group has agreed to fund an additional post.

Another risk relates to insufficient uptake of the high quality review evidence when review findings are sometimes at odds with current guidelines and practices. The RPC understands the importance of strong engagement with the World Health Organisation and participating governments and is seeing positive results from this, as well as promoting open international dialogue with those who have different views.

As people build capacity and experience, new opportunities present themselves so that some partners and staff are moving on to new posts. If it is not possible to replace them or if replacments need substantial capacity building, there could be a risk to implementation. There would be a similar risk if senior RPC management were not to continue.

Outstanding actions from risk assessment
None.

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe
The RPC has made substantial progress with its reviews and the inclusion of evidence into national and international guidelines.

Performance of partnerships
The DFID-RPC partnership is strong and during the reporting period there has been dialogue around the communication of results of systematic reviews within Research and Evidence Division.

The Consortium Advisory Group advises the Consortium Director on strategic direction, risk management and problem solving. The Executive Committee helps to monitor progress, facilitates decisions about partnerships and new members, considers priorities and facilitates cross‐RPC working and coordination. The results-based financing approach is working well. The devolution to regional hubs in South Africa and India is going well, and effective measures are being taken for succession planning.

Affiliation to the Cochrane Collaboration allows the RPC to share cutting-edge methods, resources, software and capacity development approaches, while tapping into media support services and expanded networks. At the same time, the RPC is adding value through contributions to the Collaboration based on new tools, approaches and best practice. DFID officials met with the Cochrane Central Executive and the RPC in April this year. The meeting confirmed a very positive relationship between this RPC and the Collaboration and that the broader Collaboration is taking on board lessons learnt from the RPC.

Asset monitoring and control
Effective systems are in place, including asset registers in each country programme. These are monitored during routine supervision and country visits by the Director.

G: CONDITIONALITY

Update on partnership principles (if relevant)

Not applicable. DFID provides funding to the RPC through the lead institution and no funding flows directly through any Governments.

H: MONITORING & EVALUATION

Evidence and evaluation

An independent Mid-Term Evaluation of this RPC was completed in March 2015 which reviewed RPC performance against the criteria of relevance, coordination, effectiveness, efficiency and VfM, impact and sustainability. The RPC performed well against all these criteria and continues to exceed expectations against milestones. The recommendations focused on three main areas: to strengthen gender and equity components of reviews, strengthen ways of ensuring demand for reviews and consider how to better map pathways to impact. The first two have been addressed. On pathways to impact, the RPC has started developing case-studies of impact which will help provide a framework for analysis.

Monitoring progress throughout the review period
Progress is monitored through meetings with the RPC and other stakeholders and following up on the Mid-Term independent evaluation report. The annual review was a desk review carried out by members of the Health Research Team in DFID’s Research and Evidence Division, following a meeting with the RPC and Senior Managers from the Cochrane Collaboration, using data and evidence from the RPC annual report and responses to follow up questions.

2015 Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Effective Health Care (EHC) – Research Programme Consortium (RPC) 2010-16
Programme Value: £6,457,012		Review Date: October 2015
Programme Code: 201400	Start Date: Nov 2010	End Date: 31st January 2017

Summary of Programme Performance
Year	2011/12	2012/13	2013/14	2014/15
Programme Score	A+	A+	A	A+
Risk Rating	Medium	Medium	Medium	Medium

Summary of progress and lessons learnt since last review

This RPC has had another good year. The finding of the Mott-Macdonald independent evaluation and the independent stakeholder analysis were positive and the RPC has continued to be productive in delivering results. The RPC has substantially exceeded expectations in the number of systematic reviews produced and there has been good representation from women and Southern institutions among lead authors.

The South Africa Centre of Excellence has been especially productive; its review on low carbohydrate diets for weight loss received considerable media and academic attention in the country and raised the profile of evidence-based decision-making. There are some risks associated with the recent agreement to expand the Cochrane Infectious Disease Group (CIDG) portfolio to include HIV and AIDS, although strategies are currently being developed to mitigate these risks. Work continues on the dissemination of accessible products and the Communications Team is working well, offering support services to all partners across multiple dissemination platforms.

The performance of partners is in line with their budgets following action linked to results-based financing. Programme management and administration remains strong and the programme continues to represent good value for money against the criteria of economy, efficiency and effectiveness. There is strong leadership in place across the RPC and measures have been taken to support succession planning.

Summary of recommendations for the next year

The RPC should strengthen efforts to explicitly include gender and equity issues in Cochrane reviews wherever relevant. The RPC should ensure full implement the ‘gender monitoring plan’ and report on this in the next annual report.

The RPC should monitor and manage risks relating to the new HIV and AIDS portfolio especially those specified in its risk register and report on this to DFID by May 2016.

Continue the good work on development of accessible products, aiming to address the recommendations of the independent evaluation of stakeholder engagement and satisfaction and report on these in the next annual report.

Senior colleagues from the Cochrane Collaboration should join the RPC, to discuss their potential role in improving standards of research integrity globally, at the next review meeting with DFID staff.