## Sheet1
PROJECT NAME | Transparency for Development: From Transparency to Accountability, Delivery, & Impact
IMPACT | Impact Indicator 1 |  | Baseline | Milestone 1 (Project Year 1) | Milestone 2 (Project Year 2) | Milestone 3 (Project Year 3) | Milestone 4 (Project Year 4) | Target (Project Year 5)
Policymakers, donors, practitioners, and experts design programs and policies based on what does and doesn't work to improve health through T/A | Number of key stakeholders who report incorporating lessons from T4D research in to their own programs and policies | Planned
Achieved
Source
OUTCOME 1 | Outcome Indicator 1.1 |  | Baseline | Milestone 1 (Project Year 1) | Milestone 2 (Project Year 2) | Milestone 3 (Project Year 3) | Milestone 4 (Project Year 4) | Target (Project Year 5) | Assumptions
Policymakers, donors, practitioners, academics and other experts have access to new evidence and engage in evidence-informed discussions about whether and how T/A can improve health outcomes | Event Reach: Number of key stakeholders (as identified in the outreach and dissemination strategy development) attending presentations and/or consultations where study design, results, and the policy implications are discussed. | Planned | N/A |  |  | 25 | 300, at least 25% from the global South. | 400, at least 25% from the global South. | The timelag between the completion of fieldwork and availability of results is correct.
|  | Achieved |  |  |  | 200
Source
1. T4D team records
| Outcome Indicator 1.2 |  | Baseline | Milestone 1 (Project Year 1) | Milestone 2 (Project Year 2) | Milestone 3 (Project Year 3) | Milestone 4 (Project Year 4) | Target (Project Year 5) | Assumptions
| Academic Reach: Number of downloads and Google Scholar Citations of T4D papers and research products. | Planned |  |  |  | 2 | 1500 downloads, 30 citations. | 2000 downloads, 40 citations. | Assumes that there will be publications on the theoretical framework and other project outputs before final results are available. Assumes there will be findings to begin reporting in 2016 (before finalizing research papers).
|  | Achieved |  |  |  | 1058 downloads, 26 citations.
Source
Google Scholar search of T4D publications
| Outcom Indicator 1.3 |  | Baseline | Milestone 1 (Project Year 1) | Milestone 2 (Project Year 2) | Milestone 3 (Project Year 3) | Milestone 4 (Project Year 4) | Target (Project Year 5)
| Product Reach: Number of views of briefs, blog posts, and other practical guides related to the intervention design, evaluation, and approaches to improving transparency and accountability in health (particularly by women-empowerment groups). | Planned | N/A |  | 50 | 100 | 1000 | 2000
|  | Achieved |  |  |  | 663
Source
1. Measured through project website using Google Analytics.
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  |  | DFID SHARE (%)
| 1500000 |  | 1500000 | 3700000 | 5200000 |  |  | 28.85%
INPUTS (HR) | DFID (FTEs)
OUTCOME 2 | Outcome Indicator 2.1 |  | Baseline | Milestone 1 (Project Year 1) | Milestone 2 (Project Year 2) | Milestone 3 (Project Year 3) | Milestone 4 (Project Year 4) | Target (Project Year 5) | Assumptions
Improvements in citizen empowerment and participation in communities in which the intervention takes place | Percentage of treatment communities that have community activists still active in the final follow up meeting of the intervention | Planned | N/A |  |  |  | 90% of Phase 1 communities | 90% of Phase 2 communities
Achieved
Source
1. T4D social action plans and facilitator reports
| Outcome Indicator 2.2 |  | Baseline | Milestone 1 (Project Year 1) | Milestone 2 (Project Year 2) | Milestone 3 (Project Year 3) | Milestone 4 (Project Year 4) | Target (Project Year 5) | Assumptions
| Percentage of treatment communities that report completing at least one social action | Planned |  |  |  |  | 90% of Phase 1 communitieis | 90% of Phase 2 communities
Achieved
Source
1. T4D social action plans and facilitator reports
| Outcome Indicator 2.3 |  | Baseline | Milestone 1 (Project Year 1) | Milestone 2 (Project Year 2) | Milestone 3 (Project Year 3) | Milestone 4 (Project Year 4) | Target (Project Year 5) | Assumptions
| Number of people who attend meetings focused on transparency, accountability, and health | Planned |  |  |  |  | 3000 people | 3225 people
Achieved
Source
1. T4D social action plans and facilitator reports
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | Milestone 1 (Project Year 1) | Milestone 2 (Project Year 2) | Milestone 3 (Project Year 3) | Milestone 4 (Project Year 4) | Target (Project Year 5) | Assumptions
High quality, policy relevant research products on the impact, generalizability, and scalability of T/A interventions are completed. | Development of testable theoretical framework for which T/A approaches are appropriate under which conditions. | Planned | Draft rubric developed and included in proposal |  | Theoretical framework published | Brief written and disseminated including how theoretical framework included in intervention | Brief written and disseminated including how theoretical framework included in phase 2. | Final theoretical framework paper incorporating research findings. | Assumes that there will be publications on the theoretical framework and other project outputs before final results are available. Assumes that there will be findings to begin reporting in 2016 (before finalizing research papers). Note that the evaluation will be unable to test all possible contexts, and so even the final theoretical framework will require further testing.
|  | Achieved |  |  | Completed | Completed
Source
1. T4D deliverables and progress reports
| Output Indicator 1.2 |  | Baseline | Milestone 1 (Project Year 1) | Milestone 2 (Project Year 2) | Milestone 3 (Project Year 3) | Milestone 4 (Project Year 4) | Target (Project Year 5)
| Number of published, peer-reviewed research papers based on study results and research citations of study results. | Planned | N/A |  |  |  |  | 4 papers (1 per RCT plus one crosscutting), 50 research paper citations, 100 popular media citations.
Achieved
Source
1. T4D deliverables, 2. Review of popular media and publications using Google Alerts, etc.
IMPACT WEIGHTING (%) | [8 empty] | RISK RATING
30% | [8 empty] | LOW
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  |  | DFID SHARE (%)
TBD
DFID (FTEs)
INPUTS (HR) | TBD
TBD
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | Milestone 1 (Project Year 1) | Milestone 2 (Project Year 2) | Milestone 3 (Project Year 3) | Milestone 4 (Project Year 4) | Target (Project Year 5) | Assumptions
Learning from intervention and co-design process is accessible to practitioners (particularly CSOs) that implement T/A interventions. | Number of implementing partners that report having benefitted and learned from the co-design process. | Planned | N/A |  | 2 |  |  | 5 | Year 5 Target for Indicator 2.1 assumes that Phase II of the project involves working with an additional 4 CSOs.
|  | Achieved |  |  | 2
Source
1. Survey of CSO partners
| Output Indicator 2.2 |  | Baseline | Milestone 1 (Project Year 1) | Milestone 2 (Project Year 2) | Milestone 3 (Project Year 3) | Milestone 4 (Project Year 4) | Target (Project Year 5)
| Number of briefs, blog posts, and other practical guides produced related to the intervention design, co-design process, and approaches to improving transparency and accountability in health. | Planned |  |  |  |  | 15, at least 10 specifically targetting global South practitioners. | 30, at least 20 specifically targetting global South practitioners.
Achieved
Source
1. T4D deliverables
IMPACT WEIGHTING (%) | Output Indicator 2.3 |  | Baseline | Milestone 1 (Project Year 1) | Milestone 2 (Project Year 2) | Milestone 3 (Project Year 3) | Milestone 4 (Project Year 4) | Target (Project Year 5)
20% | Development of an intervention that can be rigorously evaluated | Planned | N/A |  | Completion of draft intervention design documents for use by CSOs | Intervention design report written and disseminated based on phase 1 intervention. Completion of 2 briefs presenting work from the pilot. | Completion of draft intervention design documents for phase 2. Completion of pre-analysis plan for Phase 1. | final drafts of intervention design guidelines, revised based on evaluation results.
|  | Achieved |  |  | Completed | Completed
|  | Source | [6 empty] | RISK RATING
|  | 1. T4D deliverables | [6 empty] | LOW
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  |  | DFID SHARE (%)
TBD
INPUTS (HR) | DFID (FTEs)
TBD
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | Milestone 1 (Project Year 1) | Milestone 2 (Project Year 2) | Milestone 3 (Project Year 3) | Milestone 4 (Project Year 4) | Target (Project Year 5) | Assumptions
Evidence from research product is widely disseminated to T/A practitioners and donors, policymakers, academics, and other experts. | Development of an outreach and dissemination strategy including the identification of key stakeholders. | Planned | N/A | Draft strategy developed |  | Strategy updated to include more detail on results dissemination activities. |  | Report on dissemination ouputs and results based on strategy | Assumes that there are research results to be shared and disseminated as of 2016.
|  | Achieved |  | Completed |  | Completed
Source
1. Research team's records
| Output Indicator 3.2 |  | Baseline | Milestone 1 (Project Year 1) | Milestone 2 (Project Year 2) | Milestone 3 (Project Year 3) | Milestone 4 (Project Year 4) | Target (Project Year 5)
| Number of research papers, policy briefs, and other materials on project results produced. | Planned |  |  |  |  | 5 | 10
Achieved
Source
1. Review of products on T4D website
IMPACT WEIGHTING (%) | Output Indicator 3.3 |  | Baseline | Milestone 1 (Project Year 1) | Milestone 2 (Project Year 2) | Milestone 3 (Project Year 3) | Milestone 4 (Project Year 4) | Target (Project Year 5)
30% | Number of blogs, thought pieces, podcasts, and other media products on lessons from the research and implementation process. | Planned |  |  |  |  | 10 | 20
Achieved
Source
1. Review of products on T4D website
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  |  | DFID SHARE (%)
TBD
INPUTS (HR) | DFID (FTEs)
TBD
OUTPUT 4 | Output Indicator 4.1 |  | Baseline | Milestone 1 (Project Year 1) | Milestone 2 (Project Year 2) | Milestone 3 (Project Year 3) | Milestone 4 (Project Year 4) | Target (Project Year 5) | Assumptions
Successful management and implementation of health-focused T/A intervention and evaluation in five countries. | Number of communities in which the T/A intervention has been successfully implemented | Planned | N/A |  |  | Launched in 200 | Completed in 200, launched in another 15. | Completed in 215 total. | Assumes that there are research results to be shared and disseminated as of 2016.
|  | Achieved |  |  |  | Completed
Source
1. Research team's records
| Output Indicator 4.2 |  | Baseline | Milestone 1 (Project Year 1) | Milestone 2 (Project Year 2) | Milestone 3 (Project Year 3) | Milestone 4 (Project Year 4) | Target (Project Year 5)
| Development of new evidence highlighting the role of community-level T/A in health outcomes | Planned | N/A |  | Completion of protocol design and testing for baseline survey, standard coding scheme, empowerment survey, network analysis protocol, and ethnographer questions | Baseline data compiled, cleaned, and analyzed. | Qualitative tool data compiled, cleaned, and analyzed. Reports from ethnographers completed. Completion of baseline report from RCT data. | Design of endline protocols completed.
|  | Achieved |  |  | Completed | Completed
Source
1. Research team's records
IMPACT WEIGHTING (%) | Output Indicator 4.3 |  | Baseline | Milestone 1 (Project Year 1) | Milestone 2 (Project Year 2) | Milestone 3 (Project Year 3) | Milestone 4 (Project Year 4) | Target (Project Year 5)
20% | Successful launch of T/A intervention over two phases of work | Planned | N/A |  | 2 partners selected, intervention co-design completed, and intervention launched in 2 countries | Intervention completed in all treatment sites in two countries. Successful submission of overall phase 2 design. | Selection of 3 phase 2 partners. Completion of P2 intervention design and materials. Launch of P2 intervention in 3 countries. Completion of evaluation design and final protocols for evaluation data collection. | Completion of P2 intervention in three countries. Data from evaluation compiled, cleaned, and analyzed.
|  | Achieved |  |  | Completed | Completed
Source
1. Research team's records
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  |  | DFID SHARE (%)
TBD
INPUTS (HR) | DFID (FTEs)
TBD

## Sheet1 (2)
| Baseline | Year 2 - 2014 | Year 3 - 2015 | Year 4 - 2016 | Year 5 - 2017
Development of evaluation design documents and guidelines | Outline of evaluation plan in proposal | Completed evaluation design documents for Phase 1 evaluations |  | Completed evaluation design documents for Phase 2 evaluations
Number of partners selected and T/A interventions designed and implemented | N/A | 2 |  |  | TBD (Depends on structure of second phase of research to be agreed by project steering committee).
Progress toward testable theoretical framework | Draft rubric developed and included in proposal | 1 draft theoretical framework for funder group review and comment |  |  | Final theoretical framework incorporating research findings
Progress toward intervention design | N/A | Completion of draft intervention design documents for use by CSOs |  |  | Final drafts of intervention design guidelines, revised based on evaluation results
Successful completion of data collection and analysis for evaluations | N/A | Completion of baseline data collection for Phase I | Completion of midline data collection for Phase I (2015) and baseline data collection for Phase II |  | Completion of endline data collection for Phase 1 and Phase 2 studies
Number of published, peer-reviewed research papers and research citations of study results | N/A |  |  | 30 citations in popular media/blogs | 3 papers (1 per RCT plus one crosscutting), 50 research paper citations, 100 popular media citations
Number of academics attending events at which research is presented | N/A |  |  | 50 | 100
Number of policymakers and sectoral experts who the team interacts with in presenting findings | N/A |  |  | 75 | 150
Number of distinct actionable products disseminated to practitioners to support T/A work | N/A |  | 10 |  | 20
Number of implementing partners that continue to use the successful intervention types identified by evaluation | N/A |  |  |  | Each partner has started 2 new proejcts with the successful intervention types
Number of downloads of resource guides | N/A | 100 |  |  | 300
Percentage of T/A interventions institutionalized by target stakeholders in target countries increases | TBD |  |  | Baseline + 10 percentage points | Baseline + 20 percentage points
Percentage of policymakers and sectoral experts surveyed who report incorporating new T/A interventions into work as a result of the project | 0 |  |  | 10% | 20%
Percentage of targeted stakeholders who report anticipated changes in actions because of research findings | N/A |  |  | 25% of those who report awareness of research | 50% of those report awareness of research
Percentage of target stakeholders who report awareness of research findings | N/A |  |  | 25% of those surveyed | 50% of those surveyed