## LF 1 BC logframe
PROJECT NAME Strengthening Action Against Corruption Ghana (STAAC)
IMPACT | Impact Indicator 1 |  | Baseline (2015) | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Target (2020)
Reduction in levels of corruption in Ghana | % of respondents perceiving that some, most or all of the following are corrupt: i) National level government officials; ii) police; iii) judges and magistrates; iv) the President and officials in his office | Planned | i) 86% ii) 89% iii) 85% iv) 83% | TBA |  |  |  | i) 81% ii) 84% iii) 81% iv) 78%
Achieved
Source
Afrobarometer Ghana perception surveys
| Impact Indicator 2 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Target (2020)
| Number of people reporting that they have never offered a bribe for: i) medical services; ii) public school services; iii) identity documentation; iv) water, sanitation and electrical services; v) to the police; vi) to the courts | Planned | i) 32% ii) 21% iii) 11% iv) 10% v) 4% vi) 2% | TBA |  |  |  | i) 36% ii) 25% iii) 16% iv) 14% v) 8% vi) 6%
Achieved
Source
Afrobarometer Ghana perception surveys
| Impact Indicator 2 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Target (2020)
| Government ability to control corruption | Planned | 56% percentile | TBA |  |  |  | Improvement in score
Achieved
Source
World Bank Worldwide Governance Indicators Control of Corruption composite indicator (higher percentile score = better rating)
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) |  |  | Total (£) | DFID SHARE (%)
| £9.6 million |  | 0 |  |  |  | £9.6m | 100%
INPUTS (HR) | DFID (FTEs)
OUTCOME | Outcome Indicator 1 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Target (2020) | Assumptions
Active implementation of anti-corruption measures | Case duration - average length of time from case report to case disposal covering each stage of the process (report handling, investigation, legal/administrative process, adjudication) | Planned | TBA | [5 empty] | That stronger, better coordinated and committed anti-corruption institutions will take strong action to deter, detect and sanction the corrupt and thereby increase risk to those engaged in corruption. That the Government of Ghana will continue to provide necessary funding and staffing to programme partners That anti-corruption institutions themselves are not subject to corruption or other influence that prevents them from taking action That communities, individuals, civil society, the private sector and all Ghanaians are increasingly willing and able to identify and report corruption to the authorities and not tolerate corrupt behaviour
Achieved
Source
To be designed by service provider
| Outcome Indicator 2 |  | Baseline- 2015 | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Target (2020)
| % of Ghanaians NOT rating government performance on fighting corruption as "fairly bad" or "very bad" | Planned | 29% |  |  |  |  | 45%
Achieved
Source
Afrobarometer Ghana perception surveys
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Target (2020) | Assumptions
Improved technical capacity and joint working among oversight agencies | Number of value for money and special audits conducted by PPA (total annual) | Planned | TBA
|  | Achieved | [6 empty] | That PPA will continue to provide high quality audits that allow for identification of those engaged in corruption or financial mismanagement That increasing the availability of usable audit information will provide better information for anti-corruption institutions and agencies to take action upon PPA and LEAs willing to work together operationally and share specialist expertise. Political exists to ensure the status of FIC within Egmont Group will be sustained and actions taken as needed to ensure an improved legal and regulatory environment That the government ensures relevant institutions have sufficient resources to operate effectively and staff are kept in their positions for long enough for institutions and agencies to maintain a core of skilled and experienced staff That JLOS programmes continue to boost core functions of criminal justice system
Source
Managing agent to agree methodology with partners and gather the data
| Output Indicator 1.2 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Target (2020)
| Duration of investigation / number of corruption cases where forfeiture orders are granted and carried out | Planned | TBA
Achieved
Source
Managing agent to agree methodology with partners and gather the data
| Output Indicator 1.3 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Target (2020)
| Number of cases brought to charge | Planned | TBA | TBA |  |  | TBA | TBA
Achieved
Source
Managing agent to agree methodology with partners and gather the data
| Output Indicator 1.4 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 2 | Target (2020)
| Length of time between laying a charge in court to conclusion of the case | Planned | TBA | Needs assessment conducted and core group of judges identified | Core body of judges trained in corruption cases and Court practices amended to ensure full case management | 50% of corruption trials conculded within 12 months of 1st mention in court | 70% of corruption trials conculded within 12 months of 1st mention in court | 90% corruption trials to be concluded within 12 months of 1st mention in court
Achieved
IMPACT WEIGHTING (%) |  | Source
15% |  | To be agreed with PPA - Programme reports
OUTPUT 2 |  |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 2 | Target (2020)
Strengthened structures, systems and procedures to support more effective intelligence gathering and dissemination |  | Planned | [5 empty] | Significant increase on baseline
40% |  | Managing Agent to design and agree data methodology with partners and Data Tracking Mechansim, who will gather data | [6 empty] | HIGH
OUTPUT 2 | Output Indicator 2.1 |  | Baseline 2013 | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Target (2020) | Assumptions
Fewer opportunities and incentives to be corrupt | Value and number of assets i) seized, ii) realised and iii) confisctaed (as a % of those lost TBC) from corrupt individuals and firms | Planned | data not available | effective systems for recording/monitoring established (baseline established) |  |  |  | Significant increase on baseline | That the legislative framework for asset declaration, tracking and recovery is improved to strengthen the ability of anti-corruption institutions to enforce asset declaration, forfeiture and compensation orders That increased threat of asset forfeiture helps strengthen anti-corruption institutions and increases risks for those engaged in corrupt activity Inception phase accurately identifies effective mechanisms for citizen reporting and feedback loops that will sustain engagement Willingness and ability of citizens to report corruption
Achieved
Source
Managing agent to design and agree data methodology with partners and Data Tracking Mechnansim, who will gather data
| Output Indicator 2.2 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Target (2020)
| Number of criminal corruption cases brought to court and number of convictions | Planned | TBA |  |  |  |  | Significant increase on baseline
Achieved
Source
Service provider to agree methodology with relevant partners
|  |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 2 | Target (2020)
|  | Planned | [5 empty] | Significant increase on baseline
Managing agent to design and agree data methodlogy with partners and Data Tracking Mechnansim, who will gather data
| Output Indicator 2.3 |  | Baseline 2013 | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Target (2020)
| Citizen reporting of corruption | Planned | TBA |  | Significant increase on baseline |  |  | Sustained number reporting
Achieved
IMPACT WEIGHTING (%) |  | Source | [6 empty] | RISK RATING
30% |  | Managing agent monitoring; partner reports | [6 empty] | HIGH
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Target (2020) | Assumptions
Increased domestic and international incentives for Government to tackle corruption | Increase in quality, evidenced and sustained coverage of corruption | Planned | TBA |  |  |  |  | Significant increase on baseline | Accurate assessment of political economy of institutions, politicians and MPs determining their likely response to corruption reporting International community share same priorities on corruption Relevant international standards that are of importance to Government International community has influence on Government
Achieved
Source
Managing agent will work with relevant programme partners to enable tracking and monitoring of this data
| Output Indicator 3.2 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Target (date)
| % that don't strongly disagree or disagree agree ordinary people can make a difference in the fight against corruption | Planned | 27% (2013) | 1% point reduction in ratings | additional 1% point reduction in rating | additional 2% points reduction in ratings | additional 2% points reduction in ratings | additional 2% points reduction in ratings
Achieved
Source
Global Corruption Barometer; Programme surveys
| Output Indicator 3.3 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Target (2020)
| Success rate of anti-corruption requests made/issues brought to the attention of government agencies by i) civil society and the media ii) the international community | Planned | i) TBA ii) Limited coordination | i) TBA ii) International partners identify top anti-corruption priorities, agree levers to use and core script, and present clear consistent messages to government | i) TBA ii) International partners monitor government response and make further requests | i) TBA ii) Government addresses at least 2 of international partners' requests | i) TBA ii) Government addresses at least 2 additonal international partners' requests | i) TBA ii) Government addresses at least 3 additonal international partners' requests
Achieved
Source
Programme reports. Managing agent to work with relevant programme partners to agree targets and definitions
| Output Indicator 3.4 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Target (2020)
| Compliance with FATF/GIABA recommendations to FIC and other international standards (TBD) | Planned | TBA |  |  |  |  | Significant increase on baseline
Achieved
IMPACT WEIGHTING (%) |  | Source
30% |  | Managing agent to work with relevant programme partners to agree targets and definitions

## LF 2 Dec 2015
PROJECT NAME Strengthening Action Against Corruption Ghana (SAAC)
IMPACT | Impact Indicator 1 |  | Baseline (2015) | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Target (2020)
Reduction in levels of corruption in Ghana | % of respondents perceiving that some, most or all of the following are corrupt: i) National level government officials; ii) police; iii) judges and magistrates; iv) the President and officials in his office | Planned | i) 86% ii) 89% iii) 85% iv) 83% | TBA | to be determined during inception phase | to be determined during inception phase | to be determined during inception phase | i) 81% ii) 84% iii) 81% iv) 78%
Achieved
Source
Afrobarometer Ghana perception surveys
| Impact Indicator 2 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Target (2020)
| Number of people reporting that they have never offered a bribe for: i) medical services; ii) public school services; iii) identity documentation; iv) water, sanitation and electrical services; v) to the police; vi) to the courts | Planned | i) 32% ii) 21% iii) 11% iv) 10% v) 4% vi) 2% | TBA | to be determined during inception phase | to be determined during inception phase | to be determined during inception phase | i) 36% ii) 25% iii) 16% iv) 14% v) 8% vi) 6%
Achieved
Source
Afrobarometer Ghana perception surveys
| Impact Indicator 2 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Target (2020)
| Government ability to control corruption | Planned | 56% percentile | TBA | to be determined during inception phase | to be determined during inception phase | to be determined during inception phase | Improvement in score
Achieved
Source
World Bank Worldwide Governance Indicators Control of Corruption composite indicator (higher percentile score = better rating)
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) |  |  | Total (£) | DFID SHARE (%)
| £9.6 million |  | 0 |  |  |  | £9.6m | 100%
INPUTS (HR) | DFID (FTEs)
OUTCOME | Outcome Indicator 1 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Target (2020) | Assumptions
Active implementation of anti-corruption measures | Case duration - average length of time from case report to case disposal covering each stage of the process (report handling, investigation, legal/administrative process, adjudication) | Planned | TBA | Service Provider procured and CPS Justice Adviser recruited | to be determined during inception phase | to be determined during inception phase | to be determined during inception phase | to be determined during inception phase | That stronger, better coordinated and committed anti-corruption institutions will take strong action to deter, detect and sanction the corrupt and thereby increase risk to those engaged in corruption. That the Government of Ghana will continue to provide necessary funding and staffing to programme partners That anti-corruption institutions themselves are not subject to corruption or other influence that prevents them from taking action That communities, individuals, civil society, the private sector and all Ghanaians are increasingly willing and able to identify and report corruption to the authorities and not tolerate corrupt behaviour
Achieved
Source
To be designed by service provider
| Outcome Indicator 2 |  | Baseline- 2015 | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Target (2020)
| % of Ghanaians NOT rating government performance on fighting corruption as "fairly bad" or "very bad" | Planned | 29% | N/A | to be determined during inception phase | to be determined during inception phase | to be determined during inception phase | 45%
Achieved
Source
Afrobarometer Ghana perception surveys
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Target (2020) | Assumptions
Improved technical capacity and joint working among oversight agencies | Number of value for money and special audits conducted by PPA (total annual) | Planned | TBA | Service Provider procured and entry engagements completed with PPA | to be determined during inception phase | to be determined during inception phase | to be determined during inception phase | to be determined during inception phase
|  | Achieved | [6 empty] | That PPA will continue to provide high quality audits that allow for identification of those engaged in corruption or financial mismanagement That increasing the availability of usable audit information will provide better information for anti-corruption institutions and agencies to take action upon PPA and LEAs willing to work together operationally and share specialist expertise. Political exists to ensure the status of FIC within Egmont Group will be sustained and actions taken as needed to ensure an improved legal and regulatory environment That the government ensures relevant institutions have sufficient resources to operate effectively and staff are kept in their positions for long enough for institutions and agencies to maintain a core of skilled and experienced staff That JLOS programmes continue to boost core functions of criminal justice system
Source
Managing agent to agree methodology with partners and gather the data
| Output Indicator 1.2 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Target (2020)
| Duration of investigation / number of corruption cases where forfeiture orders are granted and carried out | Planned | TBA | Service Provider procured, CPS Justice Adviser recruited and entry engagements completed with judicial services | to be determined during inception phase | to be determined during inception phase | to be determined during inception phase | to be determined during inception phase
Achieved
Source
Managing agent to agree methodology with partners and gather the data
| Output Indicator 1.3 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Target (2020)
| Number of cases brought to charge | Planned | TBA | Service Provider procured, CPS Justice Adviser recruited and entry engagements completed with judicial services | to be determined during inception phase | to be determined during inception phase | to be determined during inception phase | to be determined during inception phase
Achieved
Source
Managing agent to agree methodology with partners and gather the data
| Output Indicator 1.4 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 2 | Target (2020)
| Length of time between laying a charge in court to conclusion of the case | Planned | TBA | Service Provider procured, CPS Justice Adviser recruited and entry engagements completed with judicial services | Needs assessment conducted and core group of judges identified | Core body of judges trained in corruption cases and Court practices amended to ensure full case management | 50% of corruption trials conculded within 12 months of 1st mention in court | 70% of corruption trials conculded within 12 months of 1st mention in court
Achieved
IMPACT WEIGHTING (%) |  | Source
15% |  | To be agreed with PPA - Programme reports
OUTPUT 2 |  |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 2 | Target (2020)
Strengthened structures, systems and procedures to support more effective intelligence gathering and dissemination |  | Planned | [5 empty] | Significant increase on baseline
40% |  | Managing Agent to design and agree data methodology with partners and Data Tracking Mechansim, who will gather data | [6 empty] | HIGH
OUTPUT 2 | Output Indicator 2.1 |  | Baseline 2013 | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Target (2020) | Assumptions
Fewer opportunities and incentives to be corrupt | Value and number of assets i) seized, ii) realised and iii) confisctaed (as a % of those lost TBC) from corrupt individuals and firms | Planned | data not available | Service Provider procured | effective systems for recording/monitoring established (baseline established) | to be determined during inception phase | to be determined during inception phase | Significant increase on baseline | That the legislative framework for asset declaration, tracking and recovery is improved to strengthen the ability of anti-corruption institutions to enforce asset declaration, forfeiture and compensation orders That increased threat of asset forfeiture helps strengthen anti-corruption institutions and increases risks for those engaged in corrupt activity Inception phase accurately identifies effective mechanisms for citizen reporting and feedback loops that will sustain engagement Willingness and ability of citizens to report corruption
Achieved
Source
Managing agent to design and agree data methodology with partners and Data Tracking Mechnansim, who will gather data
| Output Indicator 2.2 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Target (2020)
| Number of criminal corruption cases brought to court and number of convictions | Planned | TBA | Service Provider procured, CPS Justice Adviser recruited and entry engagements completed with judicial services | to be determined during inception phase | to be determined during inception phase | to be determined during inception phase | Significant increase on baseline
Achieved
Source
Service provider to agree methodology with relevant partners
|  |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 2 | Target (2020)
|  | Planned | [5 empty] | Significant increase on baseline
Managing agent to design and agree data methodlogy with partners and Data Tracking Mechnansim, who will gather data
| Output Indicator 2.3 |  | Baseline 2013 | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Target (2020)
| Citizen reporting of corruption | Planned | TBA | entry engagements with core STAAC accountability partners | Significant increase on baseline | to be determined during inception phase | to be determined during inception phase | Sustained number reporting
Achieved
IMPACT WEIGHTING (%) |  | Source | [6 empty] | RISK RATING
30% |  | Managing agent monitoring; partner reports | [6 empty] | HIGH
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Target (2020) | Assumptions
Increased domestic and international incentives for Government to tackle corruption | Increase in quality, evidenced and sustained coverage of corruption | Planned | TBA | N/A | to be determined during inception phase | to be determined during inception phase | to be determined during inception phase | Significant increase on baseline | Accurate assessment of political economy of institutions, politicians and MPs determining their likely response to corruption reporting International community share same priorities on corruption Relevant international standards that are of importance to Government International community has influence on Government
Achieved
Source
Managing agent will work with relevant programme partners to enable tracking and monitoring of this data
| Output Indicator 3.2 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Target (date)
| % that don't strongly disagree or disagree agree ordinary people can make a difference in the fight against corruption | Planned | 27% (2013) | N/A | 1% point reduction in rating | additional 2% points reduction in ratings | additional 2% points reduction in ratings | additional 2% points reduction in ratings
Achieved
Source
Global Corruption Barometer; Programme surveys
| Output Indicator 3.3 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Target (2020)
| Success rate of anti-corruption requests made/issues brought to the attention of government agencies by i) civil society and the media ii) the international community | Planned | i) TBA ii) Limited coordination | Service Provider procured and entry engagements with donor partners and ToRs for mapping fo donor activities developed | i) TBA ii) International partners identify top anti-corruption priorities, agree levers to use and core script, and present clear consistent messages to government | i) TBA ii) International partners monitor government response and make further requests | i) TBA ii) Government addresses at least 2 of international partners' requests | i) TBA ii) Government addresses at least 2 additonal international partners' requests
Achieved
Source
Programme reports. Managing agent to work with relevant programme partners to agree targets and definitions
| Output Indicator 3.4 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Target (2020)
| Compliance with FATF/GIABA recommendations to FIC and other international standards (TBD) | Planned | TBA | Service Provider procured and entry engagements completed with FIC | to be determined during inception phase | to be determined during inception phase | to be determined during inception phase | Significant increase on baseline
Achieved
IMPACT WEIGHTING (%) |  | Source
30% |  | Managing agent to work with relevant programme partners to agree targets and definitions

## LF 3 Jan 2016
PROJECT NAME Strengthening Action Against Corruption Ghana (STAAC)
IMPACT | Impact Indicator 1 |  | Baseline (2015) | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Target (2020)
Reduction in levels of corruption in Ghana | % of respondents perceiving that some, most or all of the following are corrupt: i) National level government officials; ii) police; iii) judges and magistrates; iv) the President and officials in his office | Planned | i) 86% ii) 89% iii) 85% iv) 83% | TBA | to be determined during inception phase | to be determined during inception phase | to be determined during inception phase | i) 81% ii) 84% iii) 81% iv) 78%
Achieved
Source
Afrobarometer Ghana perception surveys
| Impact Indicator 2 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Target (2020)
| Number of people reporting that they have never offered a bribe for: i) medical services; ii) public school services; iii) identity documentation; iv) water, sanitation and electrical services; v) to the police; vi) to the courts | Planned | i) 32% ii) 21% iii) 11% iv) 10% v) 4% vi) 2% | TBA | to be determined during inception phase | to be determined during inception phase | to be determined during inception phase | i) 36% ii) 25% iii) 16% iv) 14% v) 8% vi) 6%
Achieved
Source
Afrobarometer Ghana perception surveys
| Impact Indicator 2 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Target (2020)
| Government ability to control corruption | Planned | 56% percentile | TBA | to be determined during inception phase | to be determined during inception phase | to be determined during inception phase | Improvement in score
Achieved
Source
World Bank Worldwide Governance Indicators Control of Corruption composite indicator (higher percentile score = better rating)
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) |  |  | Total (£) | DFID SHARE (%)
| £9.6 million |  | 0 |  |  |  | £9.6m | 100%
INPUTS (HR) | DFID (FTEs)
OUTCOME | Outcome Indicator 1 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Target (2020) | Assumptions
Active implementation of anti-corruption measures | Case duration - average length of time from case report to case disposal covering each stage of the process (report handling, investigation, legal/administrative process, adjudication) | Planned | TBA | Service Provider contracted and CPS Justice Adviser identified | to be determined during inception phase | to be determined during inception phase | to be determined during inception phase | to be determined during inception phase | That stronger, better coordinated and committed anti-corruption institutions will take strong action to deter, detect and sanction the corrupt and thereby increase risk to those engaged in corruption. That the Government of Ghana will continue to provide necessary funding and staffing to programme partners That anti-corruption institutions themselves are not subject to corruption or other influence that prevents them from taking action That communities, individuals, civil society, the private sector and all Ghanaians are increasingly willing and able to identify and report corruption to the authorities and not tolerate corrupt behaviour
Achieved
Source
To be designed by service provider
| Outcome Indicator 2 |  | Baseline- 2015 | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Target (2020)
| % of Ghanaians NOT rating government performance on fighting corruption as "fairly bad" or "very bad" | Planned | 29% | N/A | to be determined during inception phase | to be determined during inception phase | to be determined during inception phase | 45%
Achieved
Source
Afrobarometer Ghana perception surveys
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Target (2020) | Assumptions
Improved technical capacity and joint working among oversight agencies | Number of value for money and special audits conducted by Public Procurement Authority (PPA) (total annual) | Planned | TBA | Service Provider contracted and entry engagement meetings completed with PPA | to be determined during inception phase | to be determined during inception phase | to be determined during inception phase | to be determined during inception phase
|  | Achieved | [6 empty] | That PPA will continue to provide high quality audits that allow for identification of those engaged in corruption or financial mismanagement That increasing the availability of usable audit information will provide better information for anti-corruption institutions and agencies to take action upon PPA and LEAs willing to work together operationally and share specialist expertise. Political exists to ensure the status of FIC within Egmont Group will be sustained and actions taken as needed to ensure an improved legal and regulatory environment That the government ensures relevant institutions have sufficient resources to operate effectively and staff are kept in their positions for long enough for institutions and agencies to maintain a core of skilled and experienced staff That JLOS programmes continue to boost core functions of criminal justice system
Source
Managing agent to agree methodology with partners and gather the data
| Output Indicator 1.2 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Target (2020)
| Duration of investigation / number of corruption cases where forfeiture orders are granted and carried out | Planned | TBA | Service Provider contracted, Crown Prosecution Service (CPS) Justice Adviser identified | to be determined during inception phase | to be determined during inception phase | to be determined during inception phase | to be determined during inception phase
Achieved
Source
Managing agent to agree methodology with partners and gather the data
| Output Indicator 1.3 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Target (2020)
| Number of cases brought to charge | Planned | TBA | Service Provider contracted, CPS Justice Adviser identified | to be determined during inception phase | to be determined during inception phase | to be determined during inception phase | to be determined during inception phase
Achieved
Source
Managing agent to agree methodology with partners and gather the data
| Output Indicator 1.4 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 2 | Target (2020)
| Length of time between laying a charge in court to conclusion of the case | Planned | TBA | Service Provider contracted, CPS Justice Adviser identified | Needs assessment conducted and core group of judges identified | Core body of judges trained in corruption cases and Court practices amended to ensure full case management | 50% of corruption trials concluded within 12 months of 1st mention in court | 70% of corruption trials concluded within 12 months of 1st mention in court
Achieved
IMPACT WEIGHTING (%) |  | Source
15% |  | To be agreed with PPA - Programme reports
OUTPUT 2 |  |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 2 | Target (2020)
Strengthened structures, systems and procedures to support more effective intelligence gathering and dissemination |  | Planned | [5 empty] | Significant increase on baseline
40% |  | Managing Agent to design and agree data methodology with partners and Data Tracking Mechanism, who will gather data | [6 empty] | HIGH
OUTPUT 2 | Output Indicator 2.1 |  | Baseline 2013 | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Target (2020) | Assumptions
Fewer opportunities and incentives to be corrupt | Value and number of assets i) seized, ii) realised and iii) confiscated (as a % of those lost TBC) from corrupt individuals and firms | Planned | data not available | Service Provider contracted | effective systems for recording/monitoring established (baseline established) | to be determined during inception phase | to be determined during inception phase | Significant increase on baseline | That the legislative framework for asset declaration, tracking and recovery is improved to strengthen the ability of anti-corruption institutions to enforce asset declaration, forfeiture and compensation orders That increased threat of asset forfeiture helps strengthen anti-corruption institutions and increases risks for those engaged in corrupt activity Inception phase accurately identifies effective mechanisms for citizen reporting and feedback loops that will sustain engagement Willingness and ability of citizens to report corruption
Achieved
Source
Managing agent to design and agree data methodology with partners and Data Tracking Mechanism, who will gather data
| Output Indicator 2.2 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Target (2020)
| Number of criminal corruption cases brought to court and number of convictions | Planned | TBA | Service Provider contracted, CPS Justice Adviser identified | to be determined during inception phase | to be determined during inception phase | to be determined during inception phase | Significant increase on baseline
Achieved
Source
Service provider to agree methodology with relevant partners
|  |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 2 | Target (2020)
|  | Planned | [5 empty] | Significant increase on baseline
Managing agent to design and agree data methodology with partners and Data Tracking Mechanism, who will gather data
| Output Indicator 2.3 |  | Baseline 2013 | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Target (2020)
| Citizen reporting of corruption | Planned | TBA | entry engagement meetings held with core STAAC accountability partners | Significant increase on baseline | to be determined during inception phase | to be determined during inception phase | Sustained number reporting
Achieved
IMPACT WEIGHTING (%) |  | Source | [6 empty] | RISK RATING
30% |  | Managing agent monitoring; partner reports | [6 empty] | HIGH
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Target (2020) | Assumptions
Increased domestic and international incentives for Government to tackle corruption | Increase in quality, evidenced and sustained coverage of corruption | Planned | TBA | N/A | to be determined during inception phase | to be determined during inception phase | to be determined during inception phase | Significant increase on baseline | Accurate assessment of political economy of institutions, politicians and MPs determining their likely response to corruption reporting International community share same priorities on corruption Relevant international standards that are of importance to Government International community has influence on Government
Achieved
Source
Managing agent will work with relevant programme partners to enable tracking and monitoring of this data
| Output Indicator 3.2 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Target (date)
| % that don't strongly disagree or disagree agree ordinary people can make a difference in the fight against corruption | Planned | 27% (2013) | N/A | 1% point reduction in rating | additional 2% points reduction in ratings | additional 2% points reduction in ratings | additional 2% points reduction in ratings
Achieved
Source
Global Corruption Barometer; Programme surveys
| Output Indicator 3.3 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Target (2020)
| Success rate of anti-corruption requests made/issues brought to the attention of government agencies by i) civil society and the media ii) the international community | Planned | i) TBA ii) Limited coordination | Service Provider contracted and entry engagement meetings with donor partners held | i) TBA ii) International partners identify top anti-corruption priorities, agree levers to use and core script, and present clear consistent messages to government | i) TBA ii) International partners monitor government response and make further requests | i) TBA ii) Government addresses at least 2 of international partners' requests | i) TBA ii) Government addresses at least 2 additional international partners' requests
Achieved
Source
Programme reports. Managing agent to work with relevant programme partners to agree targets and definitions
| Output Indicator 3.4 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Target (2020)
| Compliance with Financial Action task Force (FATF)/Inter Governmental Action Group Against Money Laundering in West Africa (GIABA) recommendations to Financial Intelligence Center (FIC) and other international standards (TBD) | Planned | TBA | Service Provider contracted and entry engagement meetings completed with FIC | to be determined during inception phase | to be determined during inception phase | to be determined during inception phase | Significant increase on baseline
Achieved
IMPACT WEIGHTING (%) |  | Source
30% |  | Managing agent to work with relevant programme partners to agree targets and definitions

## LF 4 Aug 2016
PROJECT NAME Strengthening Action Against Corruption Ghana (STAAC)
IMPACT | Impact Indicator 1 |  | Baseline (2015/16) | Milestone 1 (2017) | Milestone 2 (2018) | Milestone 3 (2019) | Target (2020) | Assumptions
Increase in risks for those engaged in corrupt activities (including financial crimes and money laundering) resulting in a reduction in the incidence of corruption at all levels. | Percentage of people reporting that the 'level of corruption' has 'decreased' or better | Planned | 7.5%
Achieved
Source
Afrobarometer Ghana
| Impact Indicator 2 |  | Baseline (2015/16) | Milestone 1 (2017) | Milestone 2 (2018) | Milestone 3 (2019) | Target (2020)
| Ghana's score on the Corruption Perception Index | Planned | CPI 2015 Ghana score 47/100 Ghana rank 56/168 | TBA
Achieved
Source
Transparency International Corruption Perception Index
| Impact Indicator 3 |  | Baseline (2015/16) | Milestone 1 (2017) | Milestone 2 (2018) | Milestone 3 (2019) | Target (2020)
| % of respondents perceiving that some, most or all of the following are corrupt: i) National level government officials; ii) police; iii) judges and magistrates; iv) the President and officials in his office | Planned | i) 86% ii) 89% iii) 85% iv) 83% | TBA |  |  | i) 81% ii) 84% iii) 81% iv) 78%
Achieved
Source
Afrobarometer Ghana
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) |  | Total (£) | DFID SHARE (%)
| £9.6 million |  | 0 |  |  | £9.6m | 100%
INPUTS (HR) | DFID (FTEs)
OUTCOME | Outcome Indicator 1 |  | Baseline (2015/16) | Milestone 1 (2017) | Milestone 2 (2018) | Milestone 3 (2019) | Target (2020) | Assumptions
Strengthened anti-corruption and accountability institutions working together to tackle corruption more effectively | Percentage of people rating the government's ability to control corruption as 'good' or better | Planned | 56% |  |  |  |  | That stronger, better coordinated and committed anti-corruption institutions will take strong action to deter, detect and sanction the corrupt and thereby increase risk to those engaged in corruption. That anti-corruption institutions themselves are not subject to corruption or other influence that prevents them from taking action
Achieved
Source
World Bank Worldwide Governance Indicators Control of Corruption composite indicator (higher percentile score = better rating)
| Outcome Indicator 2 |  | Baseline (2015/16) | Milestone 1 (2017) | Milestone 2 (2018) | Milestone 3 (2019) | Target (2020)
| Percentage of Investigated cases convicted in court | Planned |  | N/A
Achieved
Source
| Outcome Indicator 3 |  | Baseline (2015/16) | Milestone 1 (2017) | Milestone 2 (2018) | Milestone 3 (2019) | Target (2020)
| Value and number of assets i) seized, ii) realised and iii) confiscated (as a % of those lost TBC) from corrupt individuals and firms | Planned
Achieved
Source
OUTPUTS
OUTPUT 1 | Output Indicator 1.1 |  | Baseline (2015/16) | Milestone 1 (2017) | Milestone 2 (2018) | Milestone 3 (2019) | Target (2020) | Assumptions
STAAC support results in improved mechanisms, processes, capability to detect, analyse and investigate STRs | Processes and mechanisms for improving effectiveness of Intelligence Gathering Agencies | Planned | * | STAAC prepares recommendations | Adoption of recommendations, early results | Significant improvement over 2018 | Significant improvement over 2019 | While many bodies in the anti-corruption chain receive donor support, it is the responsibility of the Government to ensure that key public agencies are funded in accordance to their need. While bureaucracies will always claim to be underfunded by politicians, there is a difference between rationalizing budgets in times of fiscal austerity and completely undermining public bodies by limiting their ability to implement their mandates. STAAC can contribute to a better understanding of the roles and needs of key anti-corruption agencies, but ultimately it will be up to the government arising from the 2016 elections to allocate them sufficient funds to operate effectively
Achieved
Source
ETA reports; STAAC annual assessment reports
| Output Indicator 1.2 |  | Baseline (2015/16) | Milestone 1 (2017) | Milestone 2 (2018) | Milestone 3 (2019) | Target (2020)
| Compliance rate with FATF and GIABA recommendation for FIC and other international standards | Planned
Achieved
Source
| Output Indicator 1.3 |  | Baseline (2015/16) | Milestone 1 (2017) | Milestone 2 (2018) | Milestone 3 (2019) | Target (2020)
| Percentage of Suspicious Transaction Reports (STRs) from Accountability Institutions submitted to FIC and processed for investigation | Planned
Achieved
IMPACT WEIGHTING (%) |  | Source
30% |  | ETA reports; STAAC annual assessment reports
OUTPUT 2 | Output Indicator 2.1 |  | Baseline (2015/16) | Milestone 1 (2017) | Milestone 2 (2018) | Milestone 3 (2019) | Target (2020)
STAAC support results in improved mechanisms and processes for overcoming the problems to investigation and prosecution of corruption | Processes and mechanisms for improving effectiveness of investigative and prosecution agencies | Planned |  | STAAC prepares recommendations | Adoption of recommendations, early results | Significant improvement over 2018 | Significant improvement over 2019
Achieved
Source
ETA reports; STAAC annual assessment reports
| Output Indicator 2.2 |  | Baseline (2015/16) | Milestone 1 (2017) | Milestone 2 (2018) | Milestone 3 (2019) | Target (2020)
| Percentage of Intelligence Reports from FIC and Government sources submitted to STAAC-supported investigative agencies taken up for investigation | Planned
Achieved
Source
ETA reports; STAAC annual assessment reports
| Output Indicator 2.3 |  | Baseline (2015/16) | Milestone 1 (2017) | Milestone 2 (2018) | Milestone 3 (2019) | Target (2020)
| Number of corruption cases where forfeiture orders are granted and carried out | Planned
Achieved
IMPACT WEIGHTING (%) |  | Source | [5 empty] | RISK RATING
30% |  | ETA reports; STAAC annual assessment reports | [5 empty] | HIGH
OUTPUT 3 | Output Indicator 3.1 |  | Baseline (2015/16) | Milestone 1 (2017) | Milestone 2 (2018) | Milestone 3 (2019) | Target (2020) | Assumptions
STAAC support results in improved capacity of CSOs in working together effectively in the fight against corruption | Quality, evidenced and sustained coverage of corruption | Planned | [5 empty] | Key STAAC partner CSOs will conduct themselves in a non-partisan manner: As observed in the STAAC PEA report, Ghana’s civil society landscape has become “increasingly politicised”. Some CSOs and media houses are openly partisan, or are viewed as such. While engaging with political parties is an important aspect of remedying this situation, it is equally important to work with CSOs in a genuinely non-partisan issues manner around issues of corruption.
Achieved
Source
Annual STAAC Accountability Review
| Output Indicator 3.2 |  | Baseline (2015/16) | Milestone 1 (2017) | Milestone 2 (2018) | Milestone 3 (2019) | Target (2020)
| Mechanisms and processes to work with a collective action approach to enhance effectiveness in tackling corruption. | Planned |  | Joint coordination forum operational | Two coordination meetings; actions taken forward
Achieved
Source
Annual STAAC Accountability Review
| Output Indicator 3.3 |  | Baseline (2015/16) | Milestone 1 (2017) | Milestone 2 (2018) | Milestone 3 (2019) | Target (2020)
| Success rate of anti-corruption requests made/issues brought to the attention of government agencies by i) civil society and the media ii) the international community | Planned
Achieved
IMPACT WEIGHTING (%) |  | Source
30% |  | Annual STAAC Accountability Review
OUTPUT 4 | Output Indicator 4.1 |  | Baseline (2015/16) | Milestone 1 (2017) | Milestone 2 (2018) | Milestone 3 (2019) | Target (2020) | Assumptions
Project Management indicators (STAAC management) | Percentage of STAAC key partners subject to due-diligence assessments, and implementation of recommendations | Planned |  | 100% DDAs; Timeframe agreed for implementation of recommendations | 100%; 100% | 100%; 100% | 100%; 100%
Achieved
Source
Managing agent reports
| Output Indicator 4.2 |  | Baseline (2015/16) | Milestone 1 (2017) | Milestone 2 (2018) | Milestone 3 (2019) | Target (2020)
| Percentage of STAAC grants which have been subject to expenditure verification audits | Planned |  | 100% | 100% | 100% | 100%
Achieved
Source
Managing agent reports
| Output Indicator 4.3 |  | Baseline (2015/16) | Milestone 1 (2017) | Milestone 2 (2018) | Milestone 3 (2019) | Target (2020)
| VfM indicator | Planned
Achieved
Source
Managing agent reports
| Output Indicator 4.4 |  | Baseline (2015/16) | Milestone 1 (2017) | Milestone 2 (2018) | Milestone 3 (2019) | Target (2020)
| Number of STAAC-funded learning documents disseminated | Planned |  | 1 | 2 | 2 | 2
Achieved
IMPACT WEIGHTING (%) |  | Source
10% |  | Managing agent reports

## LF 4 Proposed ToC
Accountability institutions
Learning
Detection & Intelligence
Investigation, Prosecution & Adjudcation
STAAC support will enhance mechanisms, processes, capability of official AC agencies to detect, analyse and investigate STRs
STAAC management will combine robust project management with implementation of an effective learning agenda
CSOs working together jointly, using collective action strategies
STAAC support will improve mechanisms and processes for investigation and prosecution of corruption
Support to government institutions
Robust project management systems
Research; work with media; establish resource hub (website)
Coalitions for change - across state and non-state actors
Ensuring Local Ownership from govt agencies & civil society
Innovative and Adaptive in its programming
Demonstrate Evidence-based programming and continuous learning,
Use STAAC's convening power to coordinate - 1. donors 2. CSOs
Sustainable institutional reforms
Politically aware & smart programming
Government creates space for CS to share information, act as watch-dogs
Reduction in the levels of corruption in Ghana
Increase in risk of corruption due to more active implementation of anti-corruption measures
IMPACT
PROGRAMME-LEVEL OUTCOMES
OUTPUTS
ACTIVITIES
STAAC PRINCIPLES
Work with political parties; Activities to influence political parties
CRITICAL ASSUMPTIONS
STAAC research/evidence will be of high quality
Assumtpion: Amended PPA law passed/Beneficial Ownership legislated, etc
Assumption: GoG will fund official AC agencies
CSOs are willing to partiicpate in a programme focused on coalition-building
CSOs are able to conduct themselves in a non-partisan manner
Demand side: Accountabilty institutions strengthened, genuine engagement
Supply side: Government ability to detect, investigate and prosecute corruption enhanced
Strengthened anti-corruption and accountability institutions working together to tackle corruption more effectively
Joint action
Corruption as a genuine national/development issue - beyond immediate electoral benefits
Information is used by citizens to initiate dialogue, critique and demand action from government

## LF 5 Nov 2016
Project Title | Strengthening Action Against Corruption - Ghana
IMPACT | Impact Indicator 1 |  | Baseline 2016 | Milestone 2 Feb 17 | Milestone 3 Feb 18 | Milestone 4 Feb 19 | Milestone 5 Feb 20 | Target Dec 20 | Key Measurement Risks at Impact Level
Increase in risks for those engaged in corrupt activities (including financial crimes and money laundering) resulting in a reduction in the incidence of corruption at all levels. | Corruption Perception Index (CPI) | Planned | CPI 2015 Ghana score 47/100 Ghana rank 56/168 | Ghana's score and rank remains the same or improves over baseline | Ghana's score and rank remains same or improves over previous year | Ghana's score and rank remains same or improves over previous year | Ghana's score and rank remains same or improves over previous year | CPI Score improves over baseline figure and is sustained over the course of the project. | The following measurement risks will be taken into consideration in the interpretation of monitoring data at the impact level; 1.Volatility – Trends in surveys such as CPI, Afrobarometer, and WGI can only be measured over the long-term due to significant inter-year volatility; 2.Error Margins – CPI, Afrobarometer, and WGI have significant error margins undermining our ability to measure the small changes expected over five years; 3. Regressions to the mean – countries with significant deviation from peers’ are likely to experience ‘regression to the mean’. Ghana is already better performing compared to peers, and there is a likelihood that ratings could slide downwards (towards the mean); 4. Paradoxical results – Higher perceptions of corruption could indicate that the project is, in fact, succeeding by increasing the citizen's awareness of corrupt activity. 5. The Afrobarometer has recently had a large funding cut, as such there is a risk that there will be a delay in the next survey or the survey will not happen again.
Achieved
Source
Transparency International Corruption Perception Index, Ghana, available at www.transparency.org
| Impact Indicator 2 |  | Baseline 2016 | Milestone 2 Feb 17 | Milestone 3 Feb 18 | Milestone 4 Feb 19 | Milestone 5 Feb 20 | Target Feb 20
| % of respondents perceiving that some, most or all of the following are corrupt: i) National level government officials; ii) police; iii) judges and magistrates; iv) the President and officials in his office | Planned | i) 86% ii) 89% iii) 85% iv) 83% Data captured in Afrobarometer survey of June 2014. |  | Baseline results stays the same or improves by 1.5% Data captured in Afrobarometer survey of June 2017. |  |  | Baseline results stays the same or improves by 1.5% Data captured in Afrobarometer survey of June 2020.
Achieved
Source
Afrobarometer Survey Data Ghana, available at http://www.afrobarometer.org
| Impact Indicator 3 |  | Baseline 2016 | Milestone 2 Feb 17 | Milestone 3 Feb 18 | Milestone 4 Feb 19 | Milestone 5 Feb 20 | Target Feb 20
| Convictions as a % of anti-corruption cases filed by the DPP at the Financial Courts. | Planned | To be determined. | Workplan agreed for developing baseline data. | % increase to be determined following baseline. | % increase to be determined following baseline. | % increase to be determined following baseline. | % increase to be determined following baseline.
Achieved
Source
Measurement framework to be determined/Project monitoring reports
INPUTS (£) | £9.7 million |  | 0 |  |  | £9.7m |  | 100%
INPUTS (HR) | DFID (FTEs)
OUTCOME | Outcome Indicator 1 |  | Baseline 2016 | Milestone 2 Feb 17 | Milestone 3 Feb 18 | Milestone 4 Feb 19 | Milestone 5 Feb 20 | Target Feb 20 | Assumptions
Strengthened anti-corruption and accountability institutions working together to tackle corruption more effectively. | Number of anti-corruption cases that are presented to the Financial Courts. | Planned | To be determined. | Develop relations with LEA and Judiciary to promote transparency and create a process to capture base line data. | % increase of the number of cases, to be determined following the baseline. | % increase of the number of cases, to be determined following the baseline. | % increase of the number of cases, to be determined following the baseline. | Strong evidence of an effective and sustainable joint operational approach to tackle corruption, which is independent of STAAC. | Stated milestones and targets for the outcome level are based on the assumption that 1. Stronger, better coordinated and committed anti-corruption institutions will take strong action to deter, detect and sanction the corrupt and thereby increase risk to those engaged in corruption. 2. Anti-corruption institutions themselves are not subject to corruption or other influence that prevents them from taking action 3.There will be a strong government commitment or a higher level champion of the initiatives. 4. DFID continues to maintain a positive and strong relationship with the Ghanaian Government on the Anti-corruption agenda and the GoG's commitment to the London Anti-Corruption Summit 2016. 5. Anti-corruption institutions provide the necessary data to measure outcome indicators. 6.Effective and collective action from civil society organisations and actors will lead to delivery of anti-corruption results. 7. Motivation and pace of change of institutions is aligned to STAAC delivery intention. 8. Ghana's political environment remains stable. 9. The full cooperation and will of the top political and technical leadership within Government to enforce sanctions (Criminal, Civil and Administrative) against individuals found culpable of having engaged in corruption.
Achieved
Source
Measurement framework to be determined/Project monitoring reports
| Outcome Indicator 2 |  | Baseline 2016 | Milestone 2 Feb 17 | Milestone 3 Feb 18 | Milestone 4 Feb 19 | Milestone 5 Feb 20 | Target Feb 20
| Number of cases of asset seizure and forfeiture. | Planned | To be determined. | Develop relations with LEA and Judiciary to promote transparency and create a process to capture base line data. | % increase of the number of cases, to be determined following the baseline. | % increase of the number of cases, to be determined following the baseline. | % increase of the number of cases, to be determined following the baseline. | Strong evidence of an effective and sustainable joint operational approach to tackle corruption, which is independent of STAAC.
Achieved
Source
Measurement framework to be determined/Project monitoring reports
| Outcome Indicator 3 |  | Baseline 2016 | Milestone 2 Feb 17 | Milestone 3 Feb 18 | Milestone 4 Feb 19 | Milestone 5 Feb 20 | Target Feb 20
| Number of anti-corruption issues that are brought to public attention by more than one CSO collectively. | Planned | 0 | 0 examples of CSOs working collectively to force a GoG response. | 2 issues (1 in incubation, 1 in the latter stages of engagement) | 5 issues (cumulative) (2 incubation, 2 moderate level of engagement, 1 high level of engagement.) | 6 issues (cumulative) (1 incubation, 3 moderate level of 2 high level of engagement) | 7 issues (cumulative) (1 incubation, 2 moderate, 4 high level of engagement)
Achieved
Source
Annual STAAC Accountability Review, STAAC Annual Assessment Results; STAAC Voice & Accountability Index: (Level of functionality of CSOs as agents of voice & accountability. 1 Not good; 2: good; 3: very good; 4: excellent).
OUTPUT 1 | Output Indicator 1.1 |  | Baseline 2016 | Milestone 2 Feb 17 | Milestone 3 Feb 18 | Milestone 4 Feb 19 | Milestone 5 Feb 20 | Target Feb 20 | Assumptions
STAAC support results in strengthened mechanisms, processes, and capability in the functions of the anti-corruption chain (detection, investigation, prosecution, adjudication) | Mechanisms, processes, and capability problems jointly identified in the detection function and addressed and progressed through STAAC support. | Planned | 0 | Functional reviews completed. M1: 2 M2: 0 M3: 0 | M1: 5 M2: 1 M3: 0 | Expected increase on milestone three with an increase in moderate and major problems, numbers to be determined as the programme progresses. | Expected increase on milestone three with an increase in moderate and major problems, numbers to be determined as the programme progresses. | The increase of minor problems successfully addressed with a moderate degree of independence from STAAC provides for trust in the PDIA process and enables institutions to address more moderate and major problems with confidence. This results in an increase in the number of moderate and major problems jointly identified and addressed and progressed with STAAC support. | 1. Government counterparts buy into the PDIA approach. 2. GoG will continue to provide necessary funding and staff to anti-corruption chain institutions. 3. Relevant institutions on the anti-corrupting chain remain open to engagement and to receiving technical support.
Achieved
Source
Adviser reports; STAAC annual assessment reports
| Output Indicator 1.2 |  | Baseline 2016 | Milestone 2 Feb 17 | Milestone 3 Feb 18 | Milestone 4 Feb 19 | Milestone 5 Feb 20 | Target Feb 20
| Mechanisms, processes, and capability problems jointly identified in the investigation function and addressed and progressed through STAAC support. | Planned | 0 | Functional reviews completed. M1: 2 M2: 0 M3: 0 | M1: 12 M2: 2 M3: 1 | Expected increase on milestone three with an increase in moderate and major problems, numbers to be determined as the programme progresses. |  | The increase of minor problems successfully addressed with a moderate degree of independence from STAAC provides for trust in the PDIA process and enables institutions to address more moderate and major problems with confidence. This results in an increase in the number of moderate and major problems jointly identified and addressed and progressed with STAAC support.
Achieved
Source
Adviser reports; STAAC annual assessment reports
| Output Indicator 1.3 |  | Baseline 2016 | Milestone 2 Feb 17 | Milestone 3 Feb 18 | Milestone 4 Feb 19 | Milestone 5 Feb 20 | Target Feb 20
| Mechanisms, processes, and capability problems jointly identified in the prosecutions and adjudications function and addressed and progressed through STAAC support. | Planned | 0 | Prosecutions Adviser put in place and stakeholder engagement commenced. | Indicators to be determined when adviser in place. | Indicators to be determined when adviser in place. | Indicators to be determined when adviser in place. | Indicators to be determined when adviser in place.
Achieved
Source
OUTPUT 1 IMPACT WEIGHTING: 30% |  | Adviser reports; STAAC annual assessment reports | [6 empty] | RISK RATING: MAJOR
OUTPUT 2 | Output Indicator 2.1 |  | Baseline 2016 | Milestone 2 Feb 17 | Milestone 3 Feb 18 | Milestone 4 Feb 19 | Milestone 5 Feb 20 | Target Feb 20 | Assumptions
Improved capability of STAAC CSOs working together effectively in the fight against corruption | Individual institutional capability (related to anti-corruption work and problem driven interative adaption (PDIA) approaches) | Planned | 0 | Level 2 out 4 for 2016 partners | Level 3 out 4 for 2016 partners Level 2 out of 4 for 2017 partners | To be determined as new partnerships and issues will emerge but expecting a point above previous assessment of 2016 - 2017 partnerships | To be determined as new partnerships and issues will emerge but expecting a point above previous assessment of 2017 - 2018 partnerships | Level 3 out 4 for 2016 partners Level 3 out of 4 for 2017 partners | Milestones and targets for Accountability Institutions are based on the assumptions that: 1.Key STAAC partner CSOs will conduct themselves in a non-partisan manner 2. STAAC partner CSOs will be willing to work in a cooperative, innovative way with greater commitment to the common goals. 3. There will be sustained commitment from CSOs to a new way of working. 4. Supply side actors which may come into partnerships will not derail the process and progress made.
Achieved
Source
Adviser reports; STAAC annual assessment reports STAAC Individual Assessment Index: Score 1: No skill or understanding technically; Score 2: Low skill, capability and understanding; Score 3: good understanding, has skills and confidence in the area but needs some strengthening to be even more impactful and effective; Score 4: excellent capability, understanding and is a leader in expertise and skill (weighted survey)
| Output Indicator 2.2 |  | Baseline 2016 | Milestone 2 Feb 17 | Milestone 3 Feb 18 | Milestone 4 Feb 19 | Milestone 5 Feb 20 | Target Feb 20
| Capability for collective action among STAAC CSOs | Planned | 0 | Level 1 out of 5 | Level 2 out of 5 | Level 3 out of 5 | Level 3 out of 5 | Level 4 out of 5
Achieved
Source
OUTPUT 2 IMPACT WEIGHTING: 30% |  | Annual STAAC Accountability Review; STAAC Partnership Assessment Index | [6 empty] | RISK RATING: MAJOR
OUTPUT 3 | Output Indicator 3.1 |  | Baseline 2016 | Milestone 2 Feb 17 | Milestone 3 Feb 18 | Milestone 4 Feb 19 | Milestone 5 Feb 20 | Target Feb 20 | Assumptions
STAAC provides support to anti-corruption and accountability institutions to tackle corruption more effectively through joint working focused at both the operational and strategic levels. | STAAC supports the anti-corruption chain to establish and strengthen joint working practices and mechanisms that facilitates enhanced strategy and planning. As measured by the number of moderate and major collaborative or joint working events that support this. | Planned | 0 | Develop relationships with institutions of the anti-corruption chain. | STAAC facilitated meetings M2: 4 M3: 4 Independently convened M2: 0 M3: 0 | To be determined. | To be determined. | There is a significant increase in the number of STAAC facilitated moderate and major events as the anti-corruption chain becomes more comfortable meeting together to discuss operational and strategic issues. There is an increase of independently convened events but it does not exceed those facilitated by STAAC. | 1. Stronger commitment by leaders of anti-corruption institutions to move away from 'business as usual ' practices towards more strategic and joined up working. 2. Independence of civil society within working group practice will occur within the timeframe of STAAC 3. Other civil society actors will be willing to engage and want to work with existing partners. 4. Civil society partners are able to be facilitative in their approaches with other CS actors, not top down. 5. Supply and demand side actors will appreciate the mutual benefits of coming together on AC 6. GoG will continue to provide necessary funding and staff to anti-corruption chain institutions
Achieved
Source
Adviser reports; STAAC annual assessment reports
| Output Indicator 3.2 |  | Baseline 2016 | Milestone 2 Feb 17 | Milestone 3 Feb 18 | Milestone 4 Feb 19 | Milestone 5 Feb 20 | Target Feb 20
| STAAC supports the anti-corruption chain to establish and strengthen joint working practices and mechanisms that improves the anti-corruption law enforcement process. As measured by the number of moderate and major collaborative or joint working events that support this. | Planned | STAAC facilitated meetings M2: 0 M3: 0 Independently convened M2: 0 M3: 0 | Conduct functional reviews. Build relationships with institutions of the anti-corruption. | STAAC facilitated meetings M2: 7 M3: 2 Independently convened M2: 1 M3: 0 | To be determined. | To be determined. | There is a significant increase in the number of STAAC facilitated moderate and major events as the anti-corruption chain becomes more comfortable meeting together to discuss operational and strategic issues. There is an increase of independently convened events but it does not exceed those facilitated by STAAC.
Achieved
Source
Adviser reports; STAAC annual assessment reports
| Output Indicator 3.3 |  | Baseline 2016 | Milestone 2 Feb 17 | Milestone 3 Feb 18 | Milestone 4 Feb 19 | Milestone 5 Feb 20 | Target Feb 20
| STAAC supports the anti-corruption chain to establish and strengthen joint working practices and mechanisms that improves the asset tracing, seizure and forfeiture process. As measured by the number of moderate and major collaborative or joint working events that support this. | Planned | STAAC facilitated meetings M2: 0 M3: 0 Independently convened M2: 0 M3: 0 | Conduct functional reviews. Build relationships with institutions of the anti-corruption. | STAAC facilitated meetings M2: 6 M3: 2 Independently convened M2: 1 M3: 0 | To be determined. | To be determined. | There is a significant increase in the number of STAAC facilitated moderate and major events as the anti-corruption chain becomes more comfortable meeting together to discuss operational and strategic issues. There is an increase of independently convened events but it does not exceed those facilitated by STAAC.
Achieved
Source
Adviser reports; STAAC annual assessment reports
| Output Indicator 3.4 |  | Baseline 2016 | Milestone 2 Feb 17 | Milestone 3 Feb 18 | Milestone 4 Feb 19 | Milestone 5 Feb 20 | Target Feb 20
| STAAC supports civil society to establish and strengthen collective action practices and mechanisms that enables high profile and sustained anti-corruption initiatives. As measured by the number of moderate and major collaborative or joint working events that support this. | Planned | 0 | Stakeholder mapping conducted of CSO actors. STAAC facilitated meetings M2: 3 M3: 4 Independently convened M2: 1 M3: 0 | STAAC facilitated meetings M2: 10 M3: 3 Independently convened M2: 12 M3: 1 | To be determined (expect here a possible shift or beginning of shift towards more major meetings and moderate becomes simplified. Also a change in initiated meetings by CS actors and less by STAAC) | To be determined (expect here a possible shift or beginning of shift towards more major meetings and moderate becomes simplified. Also a change in initiated meetings by CS actors and less by STAAC) | There is a significant increase in the number of independently convened moderate and major events with only small number of STAAC-facilitated events.
Achieved
Source
OUTPUT 2 IMPACT WEIGHTING: 30% |  | STAAC Activity Reports; STAAC Meeting Notes; STAAC Problem - Process Journals | [6 empty] | RISK RATING: MAJOR
OUTPUT 4 | Output Indicator 4.1 |  | Baseline 2016 | Milestone 2 Feb 17 | Milestone 3 Feb 18 | Milestone 4 Feb 19 | Milestone 5 Feb 20 | Target Feb 20 | Assumptions
STAAC adopts a problem driven iterative adaptive (PDIA) approach that is evidence-based and lesson-sharing. This is underpinned by effective programme management. | PDIA is embedded in technical delivery and lessons on what works are gathered and shared. | Planned | 0 | 1. PDIA guidance and tools for STAAC developed. 2. 1 engagement with donor academic and practitioner communities on sharing lessons and insights on PDIA in anti-corruption. | 1. Consistent use of the tools. 2. Decisions are based on the evidence generated from PDIA tools. 3. 1 learning document and 1 engagement with donors, academics and/or practitioners on sharing lessons and insights on PDIA in anti-corruption. | 1. Consistent use of the tools. 2. Decisions are based on the evidence generated from PDIA tools. 3. 1 learning document and 1 engagements with donors, academics and/or practitioners on sharing lessons and insights on PDIA in anti-corruption. | 1. Consistent use of the tools. 2. Decisions are based on the evidence generated from PDIA tools. 3. 1 learning document and 1 engagements with donors, academics and/or practitioners on sharing lessons and insights on PDIA in anti-corruption. | Strong body of evidence that demonstrates that PDIA works in anti-corruption programming and these lessons and guidance is shared with donors and practitioners. | 1. Donor programmes are willing to cooperate and make time for quarterly meetings and support to each others common impact areas on anti-corruption. 2. PDIA interventions in anti-corruption yield rigorous evidence of how to achieve tangible and measurable improvements. 3. Sufficient capacity and resources is committed to embed VFM in programme.
Achieved
Source
STAAC annual assessment reports
| Output Indicator 4.2 |  | Baseline 2016 | Milestone 2 Feb 17 | Milestone 3 Feb 18 | Milestone 4 Feb 19 | Milestone 5 Feb 20 | Target Feb 20
| Joint working and lessons sharing across donor programmes related to anti-corruption within Ghana. | Planned | 0 | 2 initial meetings taking place to define common impact areas and ways of supporting each other Programme Inception Reports Shared Programme Annual Reviews shared Draft MoU with EU-funded programme, ARAP. | 4 quarterly meetings Strategy / MoU updated and reviewed so that impact areas are gaining traction and potential areas for synergy, scale up and support are clear | 4 quarterly meetings Strategy / MoU updated and reviewed. | 4 quarterly meetings Strategy / MoU updated and reviewed. | Donor programmes have supported each others key nodes of synergy, and it has been identified in Annual Reviews on how this has scaled up and supported sustained action against anti-corruption.
Achieved
Source
| Output 4.3 |  | Baseline 2016 | Milestone 2 Feb 17 | Milestone 3 Feb 18 | Milestone 4 Feb 19 | Milestone 5 Feb 20 | Target Feb 20
| Original research and political analysis commissioned to support STAAC's overall programme of activities, including engagement with academic community on anti-corruption. | Planned | 0 | 1 PEA report; STAAC Approach to Research; 2 research projects commissioned; 1 anti-corruption research event in UK | 2 PEA reports; 2 STAAC issue papers; 4 research projects commissioned (cumulative); 2 anti-corruption events in UK and 1 in Ghana | 2 PEA reports; 4 STAAC issue papers (cumulative); 6 research projects commissioned (cumulative); 2 anti-corruption events in UK and 2 in Ghana | 2 PEA reports; 5 STAAC issue papers (cumulative); 6 research projects commissioned (cumulative); 2 anti-corruption events in UK and 2 in Ghana | Strong body of research and pea information. 2 PEA reports; 6 STAAC issue papers (cumulative); 2 anti-corruption events in UK and 3 in Ghana
Achieved
Source
STAAC annual assessment reports
| Output 4.4 |  | Baseline 2016 | Milestone 2 Feb 17 | Milestone 3 Feb 18 | Milestone 4 Feb 19 | Milestone 5 Feb 20 | Target Feb 20
| High quality programme management of STAAC that delivers VFM | Planned | 0 | VFM framework developed. Capacity of programme team built to deliver VFM; | VFM framework operationalized and achievements reported | VFM framework operationalized and achievements reported | VFM framework operationalized and achievements reported | Programme management assessment indicates positive results in the economy, efficiency and effective use of programme resources.
Achieved
Source
OUTPUT 4 IMPACT WEIGHTING: 10% |  | STAAC annual assessment reports; VfM framework and tracker | [6 empty] | RISK RATING: MODERATE

## LF 5 Definitions
Strengthening Action Against Corruption
| Indicator | Definition | Notes on changes to milestones/targets | Means of Verification
Impact: Increase in risks for those engaged in corrupt activities (including financial crimes and money laundering) resulting in a reduction in the incidence of corruption at all levels. |  |  |  | Data Source | Frequency | Data Collection Method | Responsible
Impact Indicator 1 | Corruption Perception Index | A measure of perceived levels of public sector corruption for countries from a scale of 0 (highly corrupt) to 100 (very clean).The indicator also ranks about 168 countries worldwide in terms of how corrupt they are.
Impact Indicator 2 | % of respondents perceiving that some, most or all of the following are corrupt: i) National level government officials; ii) police; iii) judges and magistrates; iv) the President and officials in his office | Perceived levels of corruption among endemic corruption sectors in Ghana according to the Afrobarometer Survey.
Impact Indicator 3 | Convictions as a % of anti-corruption cases filed by the DPP at the Financial Courts.
Outcome: Strengthened anti-corruption and accountability institutions working together to tackle corruption more effectively.
Outcome Indicator 1 | % increase in the number of anti-corruption cases that are presnted/committed to the Financial Courts.
Outcome Indicator 2 | % increase in the number of cases of asset seizure and forfeiture.
Outcome Indicator 3 | An increase in the number of anti-corruption issues that are brought to public attention by more than one CSO collectively. | Incubation stage: An issue has gone beyond identification stage, has a core group of actors and a clear strategy for engagement and deliver and is in the very early stages of testing and adapting. 1 out of 2 issues are in first stage of incubation and testing and the initial first issue of 2016 is beyond incubation into several engagements of action, strategy testing, adaption and delivery. 2- Incubation stage common intent, testing protypes, researching, reflecting on issues 2 - Medium level of strategy testing and delivery 1 - High level of engagement, process with variety of actors, scale up happening and delivery STAAC CS partnerships have achieved an accumulation of results from their anti-corruption work that demonstrates impact and is helping to institutionalise approaches and ways that increase the risk of those engaged in corruption activities. All issues have moved well in advance of incubation and are in scale up and a moderate degree of independence from STAAC.
Output 1: STAAC support results in strengthened mechanisms, processes, and capability in the functions of the anti-corruption chain (detection, investigation, prosecution, adjudication)
Output Indicator 1.1 | Mechanisms, processes, and capability problems jointly identified in the detection function and addressed and progressed through STAAC support. | Mechanism • An established system to facilitate joint working supported by an established MOU Processes • A series of actions that produce a positive response to capability problems. Capability Problems • Impacting on an institutions’ ability to tackle corruption either individually or in partnership with other institutions. M1 Minor Problem • Specific to a single institutions ability to tackle corruption M2 Moderate Problem • Directly relevant to two or more institutions ability to tackle corruption or of significant concern to one institution, which has the potential to significantly impact on another institution M3 Major Problem • Significant impact on the majority of institutions in the ‘anti corruption supply chain to tackle corruption Priority • Job or task most important to one or more institutions Coordination • Organisation of different institutions to enable them to work together efficiently and effectively.
Output Indicator 1.2 | Mechanisms, processes, and capability problems jointly identified in the investigation function and addressed and progressed through STAAC support
Output Indicator 1.3 | Mechanisms, processes, and capability problems jointly identified in the prosecution and adjudication functions and addressed and progressed through STAAC support.
Output 2: Improved capability of STAAC CSOs working together effectively in the fight against corruption
Output Indicator 2.1 | Increased individual capability (related to anti-corruption work and problem driven interative adaption (PDIA) approaches)
Output Indicator 2.2 | Increased capability for collective action among STAAC CSOs | Level 1 out of 5 There is an appreciation of each others skills within the partnership and the importance of pooling expertise, knowledge, networks and practice together but it has yet to take off. There is a tendency to stick to the tried and tested approaches to look for external resources to carry out activities, linear and non-adaptive...some of the partners are ready to lead and some are less inclined. There is an appreciation of AC and the importance and there is an understanding that a new way of working is necessary in partnerships Level 2 out of 5 Roles and responsibilities of the partnership is clear and well coordinated. Constructive meetings and less confusion, greater clarity and action happens. The partners have potential allies and is beginning to develop strategies, test and reflect on strategies carried out. Planning is becoming strategic. Reflection is regular, rather than periodic. Ideas are emerging about the process of change, rather then the content of individual activities. There is some action towards a move from appreciation of mobilising CS and the resourcefulness of CS is needed. The partnership reflects on a variety of approaches and see's what combination works and what does not. With the strategy in place, partners are engaging GoG, Media and PS as an initial step. Level 3 out of 5 Partners are successful engaging in CS networks and platforms within a variety of geographical areas. Other CS actors are keen and interested in the partnership approach. Working with the media is proactive and responsive. There is a solid relationship between media and CS. The partnership issue is grounded in the identified issues and experiences of citizens on AC. Public participation is playing a role and leading to new developments and reviews of policy / action against corruption. Citizens are becoming involved and the partnership is seeing the supply side engage around the issue. The partnership uses collective skills, have a bank of knowledge to draw from. The partnership capitalises on success, and drops failing plans fast, leveraging potential faster. Learning is now integral to the work of the partnership. Partners are inviting others who work on similar issues. The partnership is always prepared, ready, well documented, strong evidence so any argument is well backed up. Level 4 out of 5 The partnership understands the process well enough to guide others, scale up and continue to impact positive changes in AC. There is an understanding that the deep seated issues of AC cannot be done in isolation and partners share the approach with others, to address similar issues to begin to engage government to tackle some of the most fundemental challenges together. The partnership uses collective skills, sharing learning to build a sustainable community of practice. The partnership leverages resources and identifies where scale up can happen and begins to open opportunities. It adds value and teh bridge between the demand and supply side actors is being maintained and the their mutual understanding of the issue, content and process is clear.
Output 3: STAAC provides support to anti-corruption and accountability institutions to tackle corruption more effectively through joint working focused at both the operational and strategic levels.
Output Indicator 3.1 | STAAC supports the anti-corruption chain to establish and strengthen joint working practices and mechanisms that facilitates enhanced strategy and planning. As measured by the number of moderate and major collaborative or joint working events that support this. | MODERATE COLLABORATIVE EVENTS • Coordinated priority event linked to Operational/Organisational planning involving the middle management of 2 or more institutions MAJOR COLLABORATIVE EVENTS • Coordinated priority event linked to joint Policy or Strategic Planning involving the SMT of the majority of institutions engaged in the Anti-Corruption chain. JOINT WORKING • Two or more of the institutions of the Anti-Corruption chain actively engaged in addressing a common goal
Output Indicator 3.2 | STAAC supports the anti-corruption chain to establish and strengthen joint working practices and mechanisms that improves the anti-corruption law enforcement process. As measured by the number of moderate and major collaborative or joint working events that support this.
Output Indicator 3.3 | STAAC supports the anti-corruption chain to establish and strengthen joint working practices and mechanisms that improves the asset tracing, seizure and forfeiture process. As measured by the number of moderate and major collaborative or joint working events that support this.
Output Indicator 3.4 | STAAC supports civil society to establish and strengthen collective action practices and mechanisms that enables high profile and sustained anti-corruption intitiatives. As measured by the number of moderate and major collaborative or joint working events that support this. | Definition Major Event: Various organisations present Effective collaboration Approach + Results oriented Strategic in focus Supply and demand side connections Definition Moderate Event Focus on planning Focus on light touch follow up STAAC facilitated meetings M2: Substantial decrease to a select few M3: Substantial decrease to 0 Independently convened M2: 7 Decreased - less planning needed as strategy is aligned and tightly linked to plans consistently and results are being achieved M3: 19 increase in major meetings as strategy work deepens. Type of meeting moving from STAAC, DFID, CSO working group to strictly CS working group (10); partnerships are relied on by supply side so more engagement of major strategic monitoring and discussions (5); continuous sharing and learning meetings to scale up AC initiatives (4)
Output 4: Flexible and adaptive Programme Management approach which delivers results in VFM, lesson learning and Effective Working Relationships with partners.
Output Indicator 4.1 | PDIA is embedded in technical delivery and lessons on what works are gathered and shared. | Definition: As evidenced by; the extent to which the tools and process are integral to the way of working, the use of evidence and feedback loops in strategic and operational decision-making and the number of lessons-learning documents disseminated.
Output Indicator 4.2 | Joint working and lessons sharing across donor programmes related to anti-corruption.
Output Indicator 4.3 | Original research and political analysis commissioned to support STAAC's overall programme of activities, including engagement with academic community on anti-corruption.
Output Indicator 4.4 | VfM and project management.