## Annual Review Template – from April 2020

Title: Neglected Tropical Diseases Implementation Research Programme (NIRP) – COUNTDOWN
Programme Value £ (full life): £11,321,225		Review date: June 2020
Programme Code: 203089	AMP start date: 1 November 2014	AMP end date: 31 October 2021

Summary of Programme Performance
Year	2014	2015	2016	2017	2018	2019	2020
Overall Output Score	A	A	A	A+	A+	A+	A+
Risk Rating	Minor	Major	Major	Major	Major	Major	Mod

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-203089/documents
DevTracker Link to results framework:	https://devtracker.dfid.gov.uk/projects/GB-1-203089/documents

A. SUMMARY AND OVERVIEW

Description of programme
COUNTDOWN is a 7 year programme of implementation research (a 2 year extension was awarded in 2019) that is led by Liverpool School of Tropical Medicine (LSTM). The programme is focused on delivering high quality evidence on cost effective, scalable and sustainable solutions necessary to control and eliminate 7 Neglected Tropical Diseases (NTDs) (trachoma, schistosomiasis, river blindness, elephantiasis, and three soil transmitted helminths) that together are responsible for 90% of the total global burden of NTDs. COUNTDOWN has been operating in 4 African countries (Ghana, Liberia, Nigeria and Cameroon) where NTDs are prevalent. The main pillar of Integrated NTD Control Initiatives is delivery of Mass Drug Administration (MDA) to simultaneously treat and control disease.

COUNTDOWN brings together researchers from a range of backgrounds and disciplines, health care providers, policy makers, laboratory scientists, research uptake specialists, Ministries of Health and Non-Government Development Organisations (NGDOs) and presents an opportunity to bridge the knowledge to implementation gap for shared health impact. Across contexts, COUNTDOWN has been working proactively and collaboratively with health policy makers and NTD programme implementers at country level to disseminate research findings on an ongoing basis and help ensure that evidence generated has been of maximum benefit to NTD programmes. It also consolidates the narrative of research to policy change in an accessible manner, supporting evidence informed policy at district (state), national and international levels. The programme’s efforts to increase the reach and scale up of NTD treatments is important in helping to accelerate progress towards meeting the targets set out in the London Declaration on NTDs.

Summary supporting narrative for the overall score in this review
COUNTDOWN has continued to perform very well this year, scoring A+ on 2 of 3 outputs. Research continues to be of high quality and close engagement with key stakeholders in-country is aiding the relevance and dissemination of the consortium’s work. The RPC is working proactively and collaboratively in country to further support the planning, implementation and adapting of NTD implementation programmes, and to make practical, evidence-based changes to existing practice and so enhance performance on the ground. COUNTDOWN continues to effectively engage at the international level. Their work in Ghana on female genital schistosomiasis (FGS) is particularly noteworthy and, in collaboration with UNDP, led to a global webinar on the gender dimensions of NTDs. The extent to which social science, particularly gender and equity, is embedded in COUNTDOWN is a real strength. The RPC has contributed to the development / multi country partner roll out of WHO’s Gender, Equity and Rights Toolkit. In 2019, this was piloted in Kwara, Nigeria, one of the states where COUNTDOWN is active.

Major lessons and recommendations for the year ahead
Lessons:
- The extent to which equity concerns can be effectively mainstreamed into routine NTD programme monitoring; that areas with identified equity issues can be investigated and targeted with tailored programme adaptations through a participatory planning approach and capacity strengthening activities, to better engage and listen to communities.
- The extent to which it has been possible, through virtual interaction, to maintain regular communication, share experiences and support across contexts during the Covid-19 epidemic. Weekly WhatsApp communication with researchers across all partners has been key when face to face communication is restricted. This has enabled desk-based work to continue and the partnership to feel connected as well as adaptation of capacity strengthening and training activities.
Key recommendations:
- To continue to focus on cross-country and multidisciplinary products
- To continue to focus on getting research evidence into policy/practice in the final year of the programme; in particular, to ensure that all communications targeted at policymakers and practitioners are clear and concise in support of this
- To continue to capture and better document the impact of RPC work/difference that has made on the ground
- To continue to advise DFID to any changes in budget forecasts as soon as these become known - more important than ever this year

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The overall logic of COUNTDOWN’s Theory of Change remains valid and continues to guide programme activities. The detail at outcome level (boxes A. and B.) has been amended this year to better align with the logframe for the extension period (revised in 2019 to take account of DFID’s results framework) and the current status of the programme. The RPC continues to build on COUNTDOWN’s earlier work and to strengthen, solidify and extend its impact. A focus on how context impacts differently on programme implementation activities continues to be explored with work in different geographic and socially marginalised populations including a focus on non-urban areas, nomadic groups and state border areas. With fieldwork currently on hold, teams are reflecting on cross country and multidisciplinary insights gained from multiple projects on how barriers to implementation of NTD programmes have been overcome with a focus on generalisable findings that improve equity and effectiveness.

COUNTDOWN continues to represent good value for money, consistent with the original business case and the ambition of the 2012 London Declaration on NTDs. The programme has a strong track record of delivering high quality evidence and of influencing and increasing the effectiveness of NTD programmes in the 4 countries where it works. In Liberia and Nigeria, COUNTDOWN has utilised participatory action research cycles to help strengthen health systems for NTD programme delivery, and to strengthen capacity for evidence-based decision making amongst NTD programme implementers so as to help ensure sustainability and impact. Moreover, the programme has worked to disseminate research evidence and influence/guide policy and programme change at the international (WHO-Geneva) and regional (WHO-AFRO) levels as well as on a national basis. This includes identifying who is overlooked and how marginalised groups are represented in policy design/decision making and packaging outputs into accessible formats to reach the vulnerable.

Working towards universal health coverage and addressing current gender and equity gaps in NTD service provision is central to COUNTDOWN’s agenda. Programme research has highlighted that gendered vulnerabilities and impacts of NTDs is evident at multiple levels and that health systems are not adequately equipped to respond to these challenges. For example, data regarding MDA is not always sufficiently disaggregated by age, gender, disability at national level to enable programmes to identify equity challenges; and programme implementers often lack skills to understand gendered vulnerabilities and how to negotiate power dynamics. An example of the latter was the documentation, in Nigeria. Of many community drug distributors not being able to deliver medicines to, particularly male headed, households due to patriarchial systems and religious norms. COUNTDOWN is working at the community level to develop more gender responsive approaches to NTD management. Preliminary findings from COUNTDOWN research shows a clear need for the strengthening of referral pathways for the management of morbidity associated with NTDs as well as the provision of support for those experiencing mental stress and disability. COUNTDOWN is working with health system actors in Nigeria and Liberia to strengthen referral pathways and ensure connection between NTD programmes, mental health services, disability inclusion and rehabilitation teams.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?
The programme is on track to meet its outcomes. Research is now complete in both Ghana and Cameroon whilst some further dissemination activity, particularly on female genital schistosomiasis (FGS), is planned for Ghana. Research activities in Liberia and Nigeria were generally ahead of schedule when activities were necessarily curtailed by the impact of COVID-19. Overall, programme outputs have been largely achieved as planned (notwithstanding the negative impact of political insecurity on the onchocerciasis control project in Cameroon) and, in some cases, exceeded. The extent to which stakeholder engagement has been achieved - from the community to international arena – continues to be noteworthy.

To illustrate progress over the last year towards outcomes in the Theory of Change:
- Research showed that community sensitisation and materials need to be tailored to the needs of different groups to ensure all people are reached in innovative ways. Required communication mechanisms include: entertainment centres, sporting facilities, women’s organisations and moto parks, to increase awareness of the programme. Examples of change linked to tailoring of sensitisation includes a radio phone-in programme and posters written in the local dialect that helped increase sensitisation in Nigeria.
- Research showed the importance of additional days for training and the valuable use of role plays to increase understanding and engagement with training content. In Nigeria, COUNTDOWN supported the establishment of a new local governmental areas NTD team, which helped in the area of supervision and monitoring during mass administration of medicines (MAM) in Kaduna state. COUNTDOWN also contributed to the revision of training plans for Community Drug Distributors (CDDs) on how to administer medicines to people with disabilities and adapt programmes to meet urban needs.
- COUNTDOWN findings highlighted that inequities exist in NTD coverage for some groups, including Nomadic Fulani, school-aged children not enrolled in school, people living with disabilities (PWDs), homeless people, and women who require the consent of their husbands to accept MAM, particularly when the CDD is male. This led to developing guidelines on MAM counselling being translated to indigenous language for CDDs to avoid misinformation.
- A further two case studies that demonstrate how research activities improve gender equality, equity and/or the situation of the most vulnerable have been produced this year:
  - The Gender Dimensions of Neglected Tropical Diseases https://adphealth.org/upload/resource/2658_ADP_NTDs_and_Gender_factsheet_280120.pdf
  - Developing Sustainable tools to improve community engagement and enhance Neglected Tropical Disease Programme equity https://countdown.lstmed.ac.uk/sites/default/files/centre/Developing%20Sustainable%20tools%20case%20Study%2013.11.19%20V4%20pdf.pdf
Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio
The rationale for the two year extension (approved in 2019) remains valid, the COUNTDOWN programme continues to represent sound vfm and should continue. It is a high performing programme working to control and eliminate common NTDs and so fits with DFID priorities. Supporting the programme to its planned end date will: expand the impact of Countdown’s work, thereby maximising the value gained from DFID’s original investment; allow COUNTDOWN to exert greater influence on national NTD programmes, policies and strategies in the 4 focal countries; allow the programme to influence the inclusion of an equity lens (particularly gender and disability) with national NTD strategies; and enable the application of COUNTDOWN research evidence in a highly urbanised state of Nigeria, a priority endorsed by DFID Nigeria.

## C. DETAILED OUTPUT SCORING

Output Title	COUNTDOWN generates research evidence to respond to priority information needs of NTD policy makers and programme managers
Output number:		1	Output Score:	A+
Impact weighting (%):		60 %	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1. Number of approved research projects	i) Design: 0 / ii) Implementation: 7 / iii) Analysis/ Dissemination: 1 / iv) Completed: 12 / Total: 20	Met expectations. / i) Design: 0 / ii) Implementation: 6 / iii) Analysis/ Dissemination: 2 / iv) Completed: 13 / Total: 21
1.2. Open access research publications: / - Peer reviewed journal articles / - lead or co-author with home institution in LMIC / - female lead/co-author / - female lead/co-author with home institution in LMIC	28 peer reviewed articles in total. / Additional indicators: / - Lead or co-author- home institution in LMIC: 12 / -Female lead/co-author: 20 / -Female lead/co-author- home institution in LMIC: 3	Moderately exceeded expectations. / 33 peer reviewed research articles have been published; there are 2 with acceptance pending; and a further 3 in draft. / Additional indicators: / - Lead or co-author- home institution in LMIC: 21 / - Female lead/co-author: 28 / - Female lead/co-author- home institution in LMIC: 6
1.3. Number of cross-country outputs and/or learnings	3 cross-country products that highlight how research exchanges have enabled change in research approaches, knowledge/skills and/or NTD programme design or delivery	Moderately exceeded expectations. / Achieved - 6
1.4. Open access knowledge products (presentations, blogs, briefs) produced and disseminated	230 knowledge products, including 14 policy briefs, developed and geographic dissemination mapped, including through website download and page views	Moderately exceeded expectations. / Achieved – 272 knowledge products, 17 policy briefs

Output moderately exceeded expectations. Research activities were ahead of schedule in March 2020 when fieldwork was necessarily halted by the impact of COVID-19. Related activities - planning, and analysis, producing papers etc. for research already undertaken - are ongoing, and are the focus of COUNTDOWN’s efforts at this uncertain time.

There are 6 projects at implementation stage: in Liberia, on integrating FGS into health systems, and decentralised MDA; and in Nigeria, on developing an integrated community based detection and referral system for skin-affecting NTDs, establishing a community based support system for people affected by stigmatising skin diseases; evaluating a Participatory Action Research Cycle on an enhanced community engagement package for preventative chemotherapy of NTDs; and strengthening health systems to manage FGS. Analysis and dissemination are ongoing on the gender equity and rights project in Kwara State, Nigeria whilst political insecurity in Cameroon has resulted in scope changes and delays in the dissemination of an onchocerciases control project.

Examples of cross-country outputs/learning include: the effectiveness of Participatory Action Research in strengthening health systems at all levels by promoting joint problem and solution finding between communities and health system actors and supporting policy implementation analysis; identification of core common equity challenges in accessing NTD care across COUNTDOWN countries and the need for multi-pronged strategies that respond to power dynamics at varying levels to ensure universal health coverage through the equitable attainment of development priorities whilst maximising social inclusion and cohesion.

Details of COUNTDOWN’s peer reviewed publications, policy briefs, case studies, and blogs can be found at https://countdown.lstmed.ac.uk/publications-resources, a first version of a video outlining their work and its impact is at https://www.youtube.com/watch?v=bXqIq69_b84&feature=youtu.be

As reflected in the updated logframe and output above, COUNTDOWN have responded well to the recommendation in last year’s annual review to give increased focus to cross country/multidisciplinary products.

A key lesson is the extent to which it takes time and opportunities for mentorship across countries/institutions to build capacity and support a broader range of authors (beyond lead researchers) to lead on writing academic publications/other knowledge products.

A key recommendation for the coming year is that COUNTDOWN should work to ensure that all communications, particularly those targeted at policymakers and practitioners are clear and concise so as to maximise the uptake of their research.

Output Title	COUNTDOWN supports incorporation of evidence to improve policies and operational plans and practices for scale-up of NTD control
Output number:		2	Output Score:	A+
Impact weighting (%):		25 %	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1. Involvement of key stakeholders at national, state and district level in developing linkages, partnerships, across disciplines, sectors and countries to enhance evidence-based NTD policymaking and programming	2 examples of how networks established during COUNTDOWN will be sustained beyond the life of COUNTDOWN to influence change to NTD policy and practice	Moderately exceeded expectations. / Achieved - 4
2.2. COUNTDOWN undertakes research uptake and dissemination activities effectively	3 examples of change to NTD policy and practice resulting from COUNTDOWN evidence and research uptake	Moderately exceeded expectations. / Achieved - 6

Output moderately exceeded expectations. COUNTDOWN has successfully established several sustainable networks to influence change to NTD policy and practice. To illustrate, COUNTDOWN researchers are working with the COR-NTD taskforce and others to establish a community of practice for sharing data on NTD social science and implementation research methods and techniques - key foci will be building junior researcher skills and ensuring wide country engagement; and have been active in the working group of the WHO Gender Equity Rights Network since it’s set up in 2016 to improve gender responsiveness in NTD programming and ensure no one is left behind – engagement in this group led to COUNTDOWN being represented at WHO NTD STAG Working Group Monitoring and Evaluation meetings where their work on the WHO Gender Equity and Rights tool was presented.
COUNTDOWN had ample presence at the most recent ASTMH and COR-NTD annual meetings with substantial inputs, including the launch of the publication on Gender Dimensions Of Neglected Tropical Diseases https://adphealth.org/upload/resource/2523_ADP_Discussion_Paper_NTDs_211119_web.pdf.

In Nigeria, COUNTDOWN evidence has informed action plans to address inequities in mass drug administration coverage due to intersecting issues of gender, religion, age, marginalisation and urbanisation. For example, this has led to new mechanisms for NTD material distribution (via entertainment centres, sporting facilities, women’s groups, moto parks) and a radio phone-in programme, that have enabled increased awareness of the MDA programme amongst diverse population groups. In Liberia, research has influenced health systems interventions to be more inclusive of the needs and experiences of individuals and has led to the inclusion of mental health within the national case management plan for NTDs. Moreover, COUNTDOWN is working to establish specific referral pathways linking mental health, disability, rehabilitation and NTD services within Nigeria and Liberia – these will embed treatment for NTDs within health system planning; and strengthen support structures at community level.

Key lessons this year are: the extent to which co-researchers/stakeholders at all health system levels are key to drive a “bottom up” approach to policy making to help ensure interventions are inclusive of the needs of individuals affected; and how alternative methods of community sensitisation/mobilisation to mass administration of medicine can improve equity – diversifying community drug distributor selection to include women, helped improve access to households in some communities.
Output Title	COUNTDOWN strengthens capacity for evidence-based decision making and planning through learning by doing amongst its staff, associated partners and country-based research communities
Output number:		3	Output Score:	A
Impact weighting (%):		15 %	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1. Organisations engaged in COUNTDOWN implementation research have improved capacity	2 examples of sustainable change resulting from capacity strengthening at an institutional environment	Met expectations. / Achieved - 3
3.2. Individual stakeholders engaged in COUNTDOWN / implementation research has improved capacity	2 examples of sustainable change resulting from capacity strengthening of individual stakeholders	Met expectations. / Achieved - 3

Output met expectations. COUNTDOWN has continued to work with programme partners to successfully enhance capacity at an individual and organisational level and so help build sustainable scientific networks and an environment conducive to effective research uptake.

COUNTDOWN has supported the institutional growth of several local partners through the development of operational manuals/guidance for safeguarding, programme management, inclusion policies, and staff appraisal processes; and raised gender awareness by celebrating the success of female staff and building supportive networks to ensure women are well represented in health and other professions. In particular, LSTM worked with the UL-PIRE Africa Centre to help enhance the working environment, support job enrichment, enhance the quality of work and improve staff morale by supporting a shift to a more decentralised unit that supports empowerment and decision-making at appropriate staff levels. COUNTDOWN support for the expansion of laboratory facilities and staff at CSIR Ghana has helped develop expertise in molecular genetics of infectious diseases and, coupled with practical training on real-time PCR assays, has enabled the lab to currently support diagnostics for COVID-19 testing in Ghana.

COUNTDOWN’s efforts to develop capacity to undertake research and inform policy development have also paid dividends. This is evidenced, for example, by the Cameroon team writing and mapping key reference national policy documents such as “The Atlas of Schistosomiasis Transmission”; and by programme support to the Nigeria state and local government area NTD teams to improve planning ahead of MAM in 2019 through training the trainer approaches to the use of intervention tools, and building skills in: power sharing; knowledge exchange; team building; conflict management; and mutuality and respect.

Various COUNTDOWN initiatives such as mentorship, supporting conference presentations, training etc. have supported staff members who joined COUNTDOWN as junior researchers several years ago to progress to managing teams of people; and to be successful in securing additional resources to conduct further NTD research.

As reflected in the updated logframe and output above, COUNTDOWN have responded well to the recommendation in last year’s annual review to better capture how the programme has been effective at building capacity at the institutional level.

A key lesson is the need to complement the development of research capacity per se with associated programme management capacity to make budgeting, work planning and monitoring more efficient and less time consuming.

D: RISK

Overview of risk management

The overall programme risk has been assessed as Moderate and the risk rating for each category is within DFID’s risk appetite.

Context (Major): The main contextual risk relates to the impact of COVID-19 which has led to the suspension of travel/field work across all countries. COUNTDOWN have requested a 4 month no cost extension; if lockdown continues for an extended period there is a risk that a longer, costed extension will be required to complete planned activities.

Delivery (Major): Homeworking is currently enabling COUNTDOWN staff to deliver on a re-prioritised workplan focused around data analysis, producing papers, maintaining links with other networks etc. If lockdown is prolonged however, there is a risk that there will be insufficient work leading to revised staff hours etc. and a risk to timely delivery overall.

Safeguarding (Moderate): COUNTDOWN are effectively managing safeguarding risks associated with COVID-19 by: supporting staff to adhere to relevant country guidance; banning all fieldwork; facilitating homeworking; encouraging staff to report symptoms in accordance with procedures; maintaining contact with all teams on a weekly basis; and monitoring the situation through weekly programme management calls. All partners have signed up to COUNTDOWN’s safeguarding policies and principles and associated capacity strengthening activities have been ongoing.

Fiduciary (Moderate): COUNTDOWN use LSTM systems which are robust and provide satisfactory assurance that DFID funds are managed appropriately. The impact of COVID-19 on the global economy alongside political instability in COUNTDOWN countries carries an exchange rate risk that is being effectively managed through setting rates in advance and adjusting financial plans, and close monitoring.

Reputational (Minor): LSTM is an experienced DFID research partner with strong governance and ethics and a good understanding of DFID expectations around standards and appropriate use of funds.

Intellectual (Moderate): LSTM is an experienced partner in this field of research. Evidence is presented in a clear and accessible way and this is monitored by DFID staff. The main risk to DFID’s reputation relates to a delayed decision on the proposed extension.

Operational (Moderate): Countdown are familiar with DFID requirements and expectations and the programme has a good track record of effective, proportionate contact/relations with DFID.

E: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and DFID, notably on commercial and financial issues, and including consideration of VfM measures of economy and efficiency

LSTM have been efficient in managing the programme budget and reporting on financial performance throughout the year. In line with DFID’s drive for improved forecasting, spend remained within 1% of the original 2019/20 forecast (a reflection of LSTM revising procedures to receive more regular invoicing and financial reports from partners) for quarters 1, 2 and 3 but returned a significant underspend of £238,104 (against a forecast of £474,000) in quarter 4, as a result of delays associated with fieldwork due to COVID-19. This will have a consequential impact on the programme budget, forecasts and spend for the remainder of the contract period, the detail of which is under consideration. To date, key cost drivers have been: personnel (56%); programme costs (22%); travel (10%); overheads (9%) and equipment (3%).

COUNTDOWN continues to represent good value for money, consistent with the original business case and the ambition of the 2012 London Declaration on NTDs. In terms of DFID’s key vfm framework indicators of economy and efficiency:
Economy - COUNTDOWN pays due attention to cost control, for example by obtaining and comparing several quotes for flights and hotel bookings; using technological solutions rather than travel when possible; and cost-sharing with other programmes.
Efficiency - COUNTDOWN continues to seek to improve efficiency in the use of programme resources and LSTM has made various improvements to partner programme management this year, including on improving systems to monitor forecasts, expenditure and associated outputs. The RPC uses activity based budgeting linked to specific project deliverables and timelines, and progress is closely monitored at pre-defined timeframes. The successful leveraging of funds from various sources (COR-NTD, NIHR, WHO TDR, K4D and UNDP) in support of COUNTDOWN objectives has also enhanced the overall efficiency of the programme.

At a programme level, COUNTDOWN reviews vfm when assessing implementation research and programmatic activities to ensure the affordability of scale up and therefore sustainability of interventions.

LSTM record all equipment/programme assets centrally and update the register quarterly. Assets are audited during programme management team visits to partner institutions.

DFID staff have had ongoing contact with COUNTDOWN throughout the year on a wide range of issues - the extension and associated logframe revisions, finances, reporting and the impact of COVID-19. DFID and COUNTDOWN personnel met in person in Sep’19 and again in Mar’20. COUNTDOWN continue to have strong links and a good relationship with DFID’s health research team, they have met with DFID representatives for Liberia and Nigeria and also highlighted their work to a DFID Minister. They would welcome further engagement with DFID health advisers and others supporting NTD activities.

COUNTDOWN has performed well against contract KPIs, including maintaining and reporting against an action plan on the recommendations from last year’s annual review and maintaining and reporting on progress against an annual workplan covering the entire scope of deliverables. COUNTDOWN has also effectively monitored: the number of policy brief downloads from the programme website (203) over the year and mapped those by geographical location (81 USA, 79 UK, 29 Nigeria, 11 other LMICs); and website visits (the top 5 countries were USA, UK, Nigeria, Ghana and Cameroon).

Date of last narrative financial report	30 Apr’20	Date of last audited annual statement	6 Nov’19