## Logframe with comments
PROJECT NAME | IMPROVED WATER, SANITATION AND HYGIENE IN THE RURAL
IMPACT | Impact Indicator 1 |  | Baseline 2011 (5 old provinces) | Milestone June 2013 | Milestone June 2014 | Milestone June 2015 | Milestone June 2016 | Target October 2016 (5 old provinces) | Baseline October 2016(3 new provinces) |  |  |  | Target October 2019 (3 new provinces) | Target June 2020 (3 new provinces) | Target October 2020 (3 new provinces) | Assumptions 1. There is an improvement in country's economy translating to an investment in social sectors. 2. Natural disasters are mitigated effectively (i.e. floods, disease outbreaks and drought)
Reduction in WASH related burden of disease and women’s workload, improved basic education outcomes, strengthened gender equality, and significant progress towards the MDGs | Proportion of rural population using protected water supplies [i] | Planned | 64.6% |  |  |  |  | 85% | 66.5% |  |  |  | 67% | 67%
|  | Achieved | [5 empty] | 66.4% | [5 empty] | 73.6%
Source
RWP Baseline Survey Report (2014) and Endline Survey Report (2016) for 5 Provinces and Baseline Survey Report for 3 Provinces
| Impact Indicator 2 |  | Baseline 2011 (5 old provinces) | Milestone June 2013 | Milestone June 2014 | Milestone June 2015 | Milestone June 2016 | Target October 2016 (5 old provinces) | Baseline October 2016(3 new provinces) |  |  |  | Target October 2019(3 new provinces) | Target June 2020 (3 new provinces) | Target October 2020 (3 new provinces)
| Prevalence of diarrhea (2 week recall) in children under 5 years of age living in rural areas, disaggregated by wealth quintile | Planned | 31.9% |  |  |  |  | 8.3% | 33.7% |  |  |  | 30% | 30%
|  | Achieved | [5 empty] | 24.8% | [5 empty] | 13.6%
Source
RWP Baseline Survey Report (2014) and Endline Survey Report (2016) for 5 Provinces and Baseline Survey Report for 3 Provinces
| Impact Indicator 3 |  | Baseline 2011 (5 old provinces) | Milestone June 2013 | Milestone June 2014 | Milestone June 2015 | Milestone June 2016 | Target October 2016 (5 old provinces) | Baseline October 2016(3 new provinces) |  |  |  | Target October 2019(3 new provinces) | Target June 2020 (3 new provinces) | Target October 2020 (3 new provinces)
| Proportion of rural population using an improved sanitation[ii] facility (sharing & non sharing), disaggregated by wealth quintile | Planned | 40.2% |  |  |  |  | 55% | 49% |  |  |  | 50% | 50%
|  | Achieved | [5 empty] | 63% | [5 empty] | 63.7%
Source
RWP Baseline Survey Report (2014) and Endline Survey Report (2016) for 5 Provinces and Baseline Survey Report for 3 Provinces
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
| ₤ 40,461,273 |  |  |  | ₤ 40,461,273 |  | 100%
INPUTS (HR) | DFID (FTEs)
OUTCOME | Outcome Indicator 1 |  | Baseline 2011 (5 old provinces) | Milestone June 2013 | Milestone June 2014 | Milestone June 2015 | Milestone June 2016 | MilestoneOctober 2016 | MilestoneApril 2017 | Milestone October 2017 | Milestone October 2018 | Milestone June 2019 | Target October 2019 | Target June 2020 | Target October 2020 | Assumptions
Increased equitable and sustainable use of protected water supplies; use of improved sanitation; adoption of hygiene practices, among the rural population in 42 targeted districts | Number of additional people using improved protected water supplies in targeted rural districts, disaggregated by input (i.e. using a new water supply, or a repaired or renovated water supply) | Planned | Nil | 20000 | 400000 | 1000000 | 1,506,000[iii] | 1506000 |  | 3100000 | 3350000 | 4191960 | 4215960 | 4215960 | 4484027 | Government continues with the sector reform process and provide favourable environment for NGOs and Private Sector to assist with WASH service delivery Sufficient funding available to support WASH interventions in other (non-project) districts There are sufficient population in the proposed 12 new districts relying on boreholes in need of rehabilitation Ground water levels do not recede unreasonably due to extreme drought or climatic conditions
|  | Achieved |  | 54000 | 550000 | 1533720 | 2747303 | 2793260 |  | 3937910 | 4133571 | 4311946 | 4391867 | 4484027
Source
IP/RDC monitoring reports;
| Outcome Indicator 2 |  | Baseline 2011 (5 old provinces) | Milestone June 2013 | Milestone June 2014 | Milestone June 2015 | Milestone June 2016 | Target October 2016 (5 old provinces) | Baseline October 2016(3 new provinces) | Milestone October 2017 | MilestoneOctober 2018 | Milestone June 2019 | Target October 2019 | Target June 2020 | Target October 2020 | Complementary investments in health and education sectors continue The economy does not detoirate to the point where the rural population cannot afford to pay for services Spares are easily available to local entrepenuers for speedy response to breakdowns Recurrent cycles of drought do not significantly affect ground water levels
| Water point ‘down time’ (restored within 2 days) | Planned | 27.9% |  |  |  |  | 35% | 9.2% | [5 empty] | 12%
|  | Achieved | [5 empty] | 13.7%
Source
Baseline survey (2013), Endline survey (2016 and 2018)
| Outcome Indicator 3 |  | Baseline | Milestone June 2013 | Milestone June 2014 | Milestone June 2015 | Milestone June 2016 | MilestoneOctober 2016 | MilestoneApril 2017 | Milestone October 2017 | MilestoneOctober 2018 | Milestone June 2019 | Target October 2019 | Target June 2020 | Target October 2020 | Districts have capacity for implementing a Demand Led Appraoach to Sanitaton,including to contiune follow up for achieving ODF in the 30 old districts
| Number of newly established ODF villages in targeted districts | Planned | 0 | 0 | 0 | 450 | 1320 | 1320 | 2470 | 3000 | 3050 | 3200 | 3250 | 3250 | 3250
|  | Achieved |  | 0 | 0 | 96 | 874 | 2070 | 2555 | 2861 | 2867 | 2954 | 3055 | 3286
Source
ODF Verification Reports from DWSSCs, IP/RDC monitoring reports
| Outcome Indicator 4 |  | Baseline 2011 | Milestone June 2013 | Milestone June 2014 | Milestone June 2015 | Milestone June 2016 | MilestoneOctober 2016 | MilestoneApril 2017 | Milestone October 2017 | MilestoneOctober 2018 | Milestone June 2019 | Target October 2019 | Target June 2020 | Target October 2020
| Number of additional people with functional handwashing facilities and soap / ash at their toilet in targeted rural district | Planned | 0 | 0 | 5000 | 200000 | 500000 | 500000 | 600000 | 688326.5753 | 734215.0137 | 750215.0137 | 771287.1233 | 771287.1233 | 771287.1233
|  | Achieved |  | 0 | 3525 | 138358 | 419644 | 581808 | 586225 | 673018 | 692979 | 710570 | 717249 | 731984
Source
IP/RDC monitoring reports; baseline survey (2013), endline survey (2016)
| Outcome Indicator 5 |  | Baseline | Milestone June 2013 | Milestone June 2014 | Milestone June 2015 | Milestone (June 2016) | MilestoneOctober 2016 | MilestoneApril 2017 | Milestone October 2017 | MilestoneOctober 2018 | Milestone June 2019 | Target October 2019 | Target June 2020 | Target October 2020
| Number of people supported by the RWP with sustainable water supplies to cope the effects of climate change | Planned | Nil | 20000 | 400000 | 1000000 | 1,506,000[iii] | 1506000 |  | 3100000 | 3350000 | 4191960 | 4215960 | 4215960 | 4484027
|  | Achieved |  | 54000 | 550000 | 1533720 | 2747303 | 2793260 |  | 3937910 | 4133571 | 4311946 | 4391867 | 4484027
Source
IPs/RDC’s Report, NAC Report
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | Milestone June 2013 | Milestone June 2014 | Milestone June 2015 | Milestone June 2016 | MilestoneOctober 2016 | MilestoneApril 2017 | Milestone October 2017 | MilestoneOctober 2018 | Milestone June 2019 | Target October 2019 | Target June 2020 | Target October 2020 | Assumptions
Rural populations, especially orphans and other vulnerable children (OVCs), in the target area, have access to safe water supplies and improved school sanitation facilities | Number of new protected water supplies established in rural communities and schools, disaggregated by type | Planned | Nil | 200 | 600 | 1000 | 1446 | 1447 |  |  |  | 1460 | 1460 | 1452 (8 boreholes reprogrammed) |  | Access to protected water supplies and improved sanitation translates into sustained use, implying that communities and school authorities are willing and able to operate and maintain facilities established; Severe or prolonged drought does not lead to widespread failure of water supplies Poliical situation and upcoming elections do not affect IP activities in such a way that they are not allowed to work or engage with communities Liquidity crisis does not significantly detoirate jeopardising access to funds tranferred to UNICEF's local account and also affecting cash flow of implementing partners There are sufficient numbe of sutiable water source with hand pumps for rehabiitation in the targeted provinces
|  | Achieved |  | 140 | 312 boreholes with hand pump | 687 boreholes with hand pump | 1,374 boreholes with hand pump | 1,450 boreholes with hand pumps |  |  |  | 1,450 boreholes with hand pumps | 1,452 boreholes with hand pumps | 1,452 boreholes with hand pumps/1444
Source
IP/RDC monitoring reports
| Output Indicator 1.2 |  | Baseline | Milestone June 2013 | Milestone June 2014 | Milestone June 2015 | Milestone June 2016 | MilestoneOctober 2016 | MilestoneApril 2017 | Milestone October 2017 | MilestoneOctober 2018 | Milestone June 2019 | Target October 2019 | Target June 2020 | Target October 2020
| Number of water supplies repaired or rehabilitated in rural communities disaggregated by type (borehole/piped water scheme) | Planned |  | 0 | 1500 | 4,450, | 7400 | 7400 | 9463 | 9963 | 13463 | 15063 | 15063 | 15063
|  | Achieved |  | 0 | 1655 | 6495 | 9342 | 9463 | 9463 | 13168 | 14578 | 15054 | 15062 | 15063
Source
IP/RDC monitoring reports
| Output Indicator 1.3 |  | Baseline | Milestone June 2013 | Milestone June 2014 | Milestone June 2015 | Milestone June 2016 | MilestoneOctober 2016 | MilestoneApril 2017 | Milestone October 2017 | MilestoneOctober 2018 | Milestone June 2019 | Target October 2019 | Target June 2020 | Target October 2020
| Number of schools receiving new or improved sanitation facilities[vi] disaggregated by school type and level of construction, i.e. new or rehabilitated facilities) | Planned | 0 | 0 | 200 | 850 | 1500 | 1500 |  |  |  | 1537 | 1545 | 1555 | 1555
|  | Achieved |  | 0 | 204 | 834 | 1513 | 1529 |  |  |  |  | 1529 | 1543
IP/RDC monitoring reports
| Output Indicator 1.4 |  | Baseline | Milestone June 2013 | Milestone June 2014 | Milestone June 2015 | Milestone June 2016 | MilestoneOctober 2016 | MilestoneApril 2017 | Milestone October 2017 | Milestone October 2018 | Milestone June 2019 | Target October 2019 | Target June 2020 | Target October 2020
| Number of rehabilitated piped water schemes supported with low carbon technoalgy (solar system) | Planned | 0 |  |  |  |  | 8 |  |  | 16 | 32 | 44 | 44
|  | Achieved | [5 empty] | 8 |  |  | 15 | 18 | 20 | 20
|  | Source | [13 empty] | RISK RATING:
|  | IP/RDC monitoring reports | [13 empty] | MEDIUM
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
| ₤27,733,165 |  |  |  | ₤27733165 |  | 100%
INPUTS (HR) | DFID (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | Milestone June 2013 | Milestone June 2014 | Milestone June 2015 | Milestone June 2016 | MilestoneOctober 2016 | Milestone April 2017 | Milestone October 2017 | Milestone October 2018 | Milestone June 2019 | Target October 2019 | Target June 2020 | Target October 2020 | Assumptions
Rural population in target districts have access to safe sanitation facilities and have knowledge on safe hygiene practices by October 2018 | Number of additional people with access to an improved sanitation facility | Planned | Nil | 0 | 250000 | 200000 | 500000 | 500000 | 610902 | 860408 | 917769 | 937769 | 964109 | 964109 | 964109 | Sufficient access to water for hygiene Poliical situation and upcoming elections do not affect IP activities in such a way that they are not allowed to work or engage with communities
|  | Achieved |  | 0 | 3525 | 160042 | 427502 | 593682 | 732781 | 841272 | 900140 | 923571 | 929402 | 947821
Source: Implementing Partner Reports/ Rural Distrtict Council Reports
| Output Indicator 2.2 |  | Baseline | Milestone June 2013 | Milestone June 2014 | Milestone June 2015 | Target June 2016 | MilestoneOctober 2016 | MilestoneApril 2017 | Milestone October 2017 | MilestoneOctober 2018 | Milestone June 2019 | Target October 2019 | Target June 2020 | Target October 2020
| No of schools with hygiene promotion programmes | Planned | 0 | 0 | 200 | 850 | 1500 | 1500 |  |  |  | 1701 | 1701 | 1975
|  | Achieved |  | 0 | 685 | 1146 | 1685 | 1685 |  |  |  | 1975 | 1975 | 1975
Source: Implementing Partner Reports/ Rural Distrtict Council Reports
IMPACT WEIGHTING | Output Indicator 2.3 |  | Baseline | Milestone June 2013 | Milestone June 2014 | Milestone June 2015 | Target June 2016 | MilestoneOctober 2016 | MilestoneApril 2017 | Milestone October 2017 | MilestoneOctober 2018 | Milestone June 2019 | Target October 2019 | Target June 2020 | Target October 2020
30% | Number of people including school children reached with hygiene promotion activities | Planned | Nil | 500000 | 870000 | 1125000 | 1140000 | 1140000 |  | 2161740 | 2213400 | 2236100 | 2249720 | 2249720 | 2420387
|  | Achieved |  | 0 | 473400 | 1162591 | 1549656 | 2144520 |  | 2271366 | 2363497 | 2364811 | 2420387 | 2420387
|  | Source: Implementing Partner Reports/ Rural Distrtict Council Reports | [13 empty] | RISK RATING: LOW
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%
| ₤ 8027933 |  |  |  | ₤ 8027933 |  | 100%
INPUTS (HR) | DFID (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline 2011 | Milestone June 2013 | Milestone June 2014 | Milestone June 2015 | Milestone June 2016 | MilestoneOctober 2016 | MilestoneApril 2017 | Milestone October 2017 | MilestoneOctober 2018 | Milestone June 2019 | Target October 2019 | Target June 2020 | Target October 2020 | Assumptions
Community based public- private sector partnership supported for sustainable operation and maintenance of rural water supplies in 42 targeted districts | Percentage of new/repaired water sources with trained and functional gender parity (WPCs) | Planned | 0 | 5% | 20% | 50% | 80% | 80% |  | 80% | 90% | 90% | 90% | 90% | 90% | Private Sector Partnership is sustained with sufficient turnover and margins to encourage local entrepreneurs;Communities and local entreprenuers are responsive to the Community Based, O and M linked Rural WASH Information System (RWIMS)
|  | Achieved |  | 2% | 35% | 103% | 87% | 86% |  | 86% | 103.9% | 100% | 92.73% | 95.79%
Source
IP/RDC monitoring reports;RWIMS
| Output Indicator 3.2 |  | Baseline | Milestone June 2013 | Milestone June 2014 | Milestone June 2015 | Milestone June 2016 | MilestoneOctober 2016 | MilestoneApril 2017 | Milestone October 2017 | MilestoneOctober 2018 | Milestone June 2019 | Target October 2019 | Target June 2020 | Target October 2020
| Percentage of Water Point Committees established by project raising funds for operation and maintenance of water points | Planned | 0 | 50% | 60% | 80% | 90% | 90% |  | 60% | 80% | 90% | 90% | 85% | 80%
|  | Achieved |  | 21% | 75% | 85% | 85% | 85% |  | 87% | 81.43% | 100% | 97% | 88%
Source
IMPACT WEIGHTING |  | IP/RDC monitoring reports; baseline survey (2013), endline survey (2016)
| Output Indicator 3.3 |  | Baseline | Milestone June 2013 | Milestone June 2014 | Milestone June 2015 | Target June 2016 | MilestoneOctober 2016 | MilestoneApril 2017 | Milestone October 2017 | MilestoneOctober 2018 | Milestone June 2019 | Target October 2019 | Target June 2020 | Target October 2020
| Percentage of Water Point Committees established by project with access to trained and equipped Village Pump Mechanics (VPM’s){1 VPM for every 5 WPC's) | Planned | 0 | 20% | 80% | 90% | 100% | 100% |  | 80% | 80% | 100% | 100% | 90% | 90%
20% |  | Achieved |  | 17% | 90% | 125% | 118% | 115% |  | 86% | 100% | 100% | 94% | 94%
|  | Source | [13 empty] | RISK RATING
|  | IP/RDC monitoring reports; baseline survey (2013), endline survey (2016) | [13 empty] | MEDIUM
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID Share (%)
| ₤ 2,443,229 |  |  |  | ₤ 2,443,229 |  | 100%
INPUTS (HR) | DFID (FTEs)
OUTPUT 4 | Output Indicator 4.1 |  | Baseline | Milestone June 2013 | Milestone June 2014 | Milestone June 2015 | Milestone June 2016 | MilestoneOctober 2016 | MilestoneApril 2017 | Milestone October 2017 | MilestoneOctober 2018 | Milestone June 2019 | Target October 2019 | Target June 2020 | Target October 2020 | Assumptions
Rural Water Supply and Sanitation Institutions strengthened to legislate, coordinate, plan and monitor scaling-up of rights- and gender-sensitive interventions to promote safe drinking water, adequate sanitation and good hygiene practices | Water Policy Developed and Apporved National Sanitation and Hygiene Policy and Strategy developed and approved | Planned | NA | Water Policy developed and approved |  | Consultations on the Sanitation and Hygiene Policy and Strategy |  | Draft Sanitation and Hygiene Strategy and Policy |  | Draft Sanitation and Hygiene Strategy and Policy endorsed by NAC | Sanitation and Hygiene Strategy Approved by MoHCC | Draft Natioanl Water Policy Strategic Implementation Plan; and Draft WASH Sector Investment Plan endorsed by NAC | Sanitation and Hygiene Policy approved by Cabinet; Water Policy Strategic Implementation plan & WASH Sector Investment Plan approved by the relevant authorities | Sanitation and Hygiene Policy approved by Cabinet; Water Policy Strategic Implementation plan & WASH Sector Investment Plan approved by the relevant authorities | Sanitation and Hygiene Policy approved by Cabinet. | Policy, strategy and plans are linked to resources, and are implemented on the ground Sub-sector Ministries continue to work in close partnership to achieve WASH outcomes and outputs Development of RWIMS in additional 12 districts is subject to UNICEF being able to secure additonal funding Upcoming election politics do not compromise the functions of governace structures (PWSSC and DWSSC)
|  | Achieved |  | Achieved | [5 empty] | Draft Sanitation and Hygiene Strategy and Policy endorsed by NAC | Sanitation and Hygiene Strategy Approved by MoHCC | Joint Sector Review Processes commenced. Plans to be produced as part of the JSR | Policy and Plans prioritised for 2020 by the Joint Sector Review | Sanitation and Hygiene Policy still to be approved
Source
National Action Committee (NAC) Reports
| Output Indicator 4.2 |  | Baseline | Milestone June 2013 | Milestone June 2014 | Milestone June 2015 | Milestone (June 2016) | MilestoneOctober 2016 | MilestoneApril 2017 | Milestone October 2017 | Milestone October 2018 | Milestone June 2019 | Target October 2019 | Target June 2020 | Target October 2020
| Number of districts and provinces capacitated for enhanced WASH service delivery | Planned | 0 | 10 | 25 | 30 | 30 | 30 |  | 42 districts and 8 provinces | 42 districts and 8 provinces | 42 districts and 8 provinces | 42 districts and 8 provinces | 42 districts and 8 provinces | 43 districts and 8 provinces
|  | Achieved | 0 | 0 (partial support provided) | 30 districts reached in 5 provinces | 30 districts reached in 5 provinces | 30 districts reached in 5 provinces | 30 districts reached in 5 provinces |  | 42 districts and 8 provinces | 42 districts and 8 provinces | 42 districts and 8 provinces | 42 districts and 8 provinces | 42 districts and 8 provinces
Source
NAC Reports
| Output Indicator 4.3 |  | Baseline | Milestone June 2013 | Milestone June 2014 | Milestone June 2015 | Milestone (June 2016) | MilestoneOctober 2016 | MilestoneApril 2017 | Milestone October 2017 | MilestoneOctober 2018 | Milestone June 2019 | Target October 2019 | Target June 2020 | Target October 2020
| Number of District and Provincial WASH Governance Structures developing and overseeing for WASH plans | Planned | 0 | 0 | 10 | 30 | 30 | 30 |  | 42 districts and 8 provinces | 42 districts and 8 provinces | 42 districts and 8 provinces | 42 districts and 8 provinces | 42 districts and 8 provinces | 43 districts and 8 provinces
|  | Achieved |  | 0 | 30 districts 5 provinces | 30 districts 5 provinces | 30 districts 5 provinces | 30 districts 5 provinces |  | 42 districts and 8 provinces | 42 districts and 8 provinces | 42 districts and 8 provinces | 42 districts and 8 provinces | 42 districts and 8 provinces
Source
IPs/RDC’s Report, NAC Report
| Output Indicator 4.4 |  | Baseline | Milestone June 2013 | Milestone June 2014 | Milestone June 2015 | Milestone (June 2016) | MilestoneOctober 2016 | MilestoneApril 2017 | Milestone October 2017 | Milestone October 2018 | Milestone June 2019 | Target October 2019 | Target June 2020 | Target October 2020
| Number of districts with an established Rural WASH Information System (RWIMS) | Planned | 0 | 0 | 0 | 15 | 30 | 30 |  | 30 | 45 | 45 | 45 | 45 | 54
|  | Achieved |  | 0 | 0 | 14 | 26 | 30 |  | 30 | 45 | 45 | 45 | 45
Source
IP/RDC Reports, NAC Report
| Output Indicator 4.5 |  | Baseline | Milestone June 2013 | Milestone June 2014 | Milestone June 2015 | Milestone (June 2016) | MilestoneOctober 2016 | MilestoneApril 2017 | Milestone October 2017 | Milestone October 2018 | Milestone June 2019 | Target October 2019 | Target June 2020 | Target October 2020
| Percentage of districts with an established Rural WASH Information System (RWIMS) updating data monthly | Planned | 0 | [8 empty] | 40% | 70% | 80% | 100%
|  | Achieved | [9 empty] | 35.56% | 35.56% | 36%
Source
IP/RDC Reports, NAC Report
| Output Indicator 4.6 |  | Baseline | Milestone June 2013 | Milestone June 2014 | Milestone June 2015 | Milestone (June 2016) | MilestoneOctober 2016 | MilestoneApril 2017 | Milestone October 2017 | Milestone October 2018 | Milestone June 2019 | Target October 2019 | Target June 2020 | Target October 2020
| Percentage of breakdowns attended to by VPM through RWIMS SNR in 12 RWP target districts | Planned | 0 | [8 empty] | 60% | 70% | 50% | 50%
|  | Achieved | [9 empty] | 23% | 24% | 23%
Impact Weighting |  | Source
10% |  | IP/RDC Reports, NAC Report
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID (%) | [8 empty] | RISK RATING
| ₤ 2,256,946 |  |  |  | ₤ 2,256,946 |  | 100% | [8 empty] | MEDIUM
INPUTS (HR) | DFID (FTEs)
OUTPUT 5 | Output Indicator 5.1 |  | Baseline | Milestone June 2013 | Milestone June 2014 | Milestone June 2015 | Milestone June 2016 | MilestoneOctober 2016 | MilestoneApril 2017 | Milestone October 2017 | Milestone October 2018 | Milestone June 2019 | Target October 2019 | Target June 2020 | Target October 2020 | Assumptions
Improved preparedness and response to WASH related emergencies | Number of people affected by WASH-related emergencies accessing basic water supplies | Planned | [8 empty] | 42000 | 84000 | 84000 | 241130 | 434135 | Implementing partners are allowed by Government to continue operating freely in the target districts Businesses are able to supply critical material under the strigent COVID 19 environment
|  | Achieved | [9 empty] | 178375 | 206130 | 233885
Source
National Action Committee (NAC) Reports
| Output Indicator 5.2 |  | Baseline | Milestone June 2013 | Milestone June 2014 | Milestone June 2015 | Milestone (June 2016) | MilestoneOctober 2016 | MilestoneApril 2017 | Milestone October 2017 | MilestoneOctober 2018 | Milestone June 2019 | Target October 2019 | Target June 2020 | Target October 2020
| Number of people affected by WASH-related emergencies reached hygiene promotion | Planned | [8 empty] | 137500 | 275000 | 275000 | 275000 | 847526
|  | Achieved | [9 empty] | 626700 | 682276 | 682276
Source
IPs/RDC’s Report, NAC Report
| Output Indicator 5.3 |  | Baseline | Milestone June 2013 | Milestone June 2014 | Milestone June 2015 | Milestone (June 2016) | MilestoneOctober 2016 | MilestoneApril 2017 | Milestone October 2017 | MilestoneOctober 2018 | Milestone June 2019 | Target October 2019 | Target June 2020 | Target October 2020
| Number of health facilitities/CTCs supported with sanitation facilities in emergencies | Planned | [8 empty] | 3 | 3 | 3 | 3 | TBA
|  | Achieved | [9 empty] | 3 | 3 | 3
Source
IPs/RDC’s Report, NAC Report
| Output Indicator 5.4 |  | Baseline | Milestone June 2013 | Milestone June 2014 | Milestone June 2015 | Milestone (June 2016) | MilestoneOctober 2016 | MilestoneApril 2017 | Milestone October 2017 | MilestoneOctober 2018 | Milestone June 2019 | Target October 2019 | Target June 2020 | Target October 2020
Improved preparedness and response to WASH related emergencies | Number of households reached with WASH Hygiene Kits during Covid-19 response | Planned | [12 empty] | 33050
Achieved
Source
National Action Committee (NAC) Reports
| Output Indicator 5.5 |  | Baseline | Milestone June 2013 | Milestone June 2014 | Milestone June 2015 | Milestone (June 2016) | MilestoneOctober 2016 | MilestoneApril 2017 | Milestone October 2017 | MilestoneOctober 2018 | Milestone June 2019 | Target October 2019 | Target June 2020 | Target October 2020
| Number of public spaces reached with handwashing stations during Covid-19 response | Planned | [12 empty] | 255
Achieved
Source
IPs/RDC’s Report, NAC Report
| Output Indicator 5.6 |  | Baseline | Milestone June 2013 | Milestone June 2014 | Milestone June 2015 | Milestone (June 2016) | MilestoneOctober 2016 | MilestoneApril 2017 | Milestone October 2017 | MilestoneOctober 2018 | Milestone June 2019 | Target October 2019 | Target June 2020 | Target October 2020
| Number of schools supported with cleaning and disinfection materials (disinfectants, soap, cleaning detergents etc) during Covid-19 response | Planned | [12 empty] | 26
Achieved
Source
IPs/RDC’s Report, NAC Report
| Output Indicator 5.7 |  | Baseline | Milestone June 2013 | Milestone June 2014 | Milestone June 2015 | Milestone (June 2016) | MilestoneOctober 2016 | MilestoneApril 2017 | Milestone October 2017 | MilestoneOctober 2018 | Milestone June 2019 | Target October 2019 | Target June 2020 | Target October 2020
| Number of Local Authorities supported with water treatment chemicals during the COVID 19 response | Planned | [12 empty] | 20 Urban Local Authorities and Zinwa Stations in 7 Catchment Areas
Impact Weighting |  | Achieved
Source
IPs/RDC’s Report, NAC Report
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID (%) | [8 empty] | RISK RATING
MEDIUM
INPUTS (HR) | DFID (FTEs)

## Sheet1
1. Number of people affected by WASH-related emergencies accessing basic water supplies (disaggregated by sex)
2.Number of people affected by WASH-related emergencies accessing basic sanitation facilities (disaggregated by sex)
3.Number of people affected by WASH-related emergencies reached with key hygiene messages (disaggregated by sex)
4.Number of districts trained in DRR