Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: / PATH Meningitis Vaccine Project.
Programme Value: £5,775,788		Review Date: November 2016
Programme Code: / 202045	Start Date: / 1 November 2010	End Date: / 31 March 2018

Summary of Programme Performance
Year	2011	2012	2013	2014	2015	2016
Programme Score	75/100	A	A	A	A	A
Risk Rating	High	High	High	High	High	Major

Summary of progress and lessons learnt since last review
The Meningitis Vaccine Project (MVP) has performed strongly over the reporting period. MVP has continued the development of a next-generation, polyvalent meningococcal vaccine (covering serogroups A, C, W, X and Y), known as MCV-5, together with their partner, the Serum Institute of India Private Ltd. (SIIPL). MCV-5 is being developed for use in low-resource countries, particularly those in the African meningitis belt.

During the reporting period MVP completed the manufacturing of the clinical trial material for the first-in-humans (Phase 1) study and the product quality was confirmed by three independent sources, including confirmation that MCV-5 is safe and well tolerated. Agreement has been reached that the phase 1 study will take place in the USA. The US Food and Drug Administration (FDA) has given positive feedback on the pre-Investigational New Drug (IND) submission, required before any clinical trial can begin. A decision has been made that PATH will be the regulatory sponsor of the Phase 1 trial. Planning for a Phase 2 trial (in African toddlers) is advancing well. PATH has led a collaborative modelling team to model the cost-effectiveness of the various MCV-5 introduction strategies on meningococcal disease in the African meningitis belt.

Key lessons
More than 235 million individuals have been vaccinated against group A meningococcal disease (using MenAfriVac®) and this has been an unqualified success. Group A meningococcal disease has virtually disappeared in all countries that have immunised 1-29 year olds with a strong herd immunity effect (indirect protection of unimmunised age groups). 8 countries have applied for funding to include MenAfriVac® in their national childhood immunisation programs in 2016. A polyvalent meningococcal vaccine against serogroups A, C, Y, W and X has the potential to eliminate meningococcal meningitis from the African meningitis belt

During the year PATH revised the clinical plan to build safely and effectively on the success of MenAfriVac®. The new plan incorporates a Phase 1 safety and immunogenicitystudy in adults in the USA followed by a Phase 2 trial in African toddlers. This design provides potential to move directly into two parallel Phase 3 studies in Africa and India that are designed to lead to licensure and WHO prequalification.

Actions on previous recommendations
The logframe was updated as recommended last year.

Summary of recommendations for the next year
The logframe should be amended, to take account of the progress made during the reporting period, by March 2017.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-202045/documents/
DevTracker Link to Log frame:	http://devtracker.dfid.gov.uk/projects/GB-1-202045/documents/

The UK is supporting a product development partnership, the Meningitis Vaccine Project (MVP), to develop a polyvalent meningitis vaccine for Sub-Saharan Africa that will control the remaining 15% to 20% of meningococcal infections not covered by the existing meningitis A vaccine, MenAfriVac®. MVP engages private-sector collaborators to apply their development, manufacturing, and distribution strengths to innovate technologies that would not be a private-sector priority, and therefore achieve maximum sustainable benefit for public health in developing countries. DFID will provide £5,775,788 until March 2018 to this project.

There are currently research gaps into essential technologies, such as vaccines and medicines, to treat neglected diseases that affect the world’s poorest populations. This occurs where there are no current products or where those that exist are too expensive, difficult to access, no longer produced, highly toxic or ineffective. These factors have resulted in a limited research base with MVP being one of only a small number of organisations engaged in this area.

Meningitis is a deadly and debilitating disease that causes an estimated 70,000 cases/year alone in an area of sub-Saharan Africa known as the “African meningitis belt”, which stretches from Senegal in the west to Ethiopia in the east and has the largest burden of meningitis in the world. Despite treatment measures, meningitis kills one in ten people who are infected and leaves one-quarter of survivors severely debilitated. If untreated 50% of those infected die. The number of cases of meningitis has dramatically reduced since the introduction of MenAfriVac® in 2010, but this vaccine does not target all the disease-causing serogroups. New vaccines are required to prevent the remaining 15% to 20% of meningitis infections caused by other meningococcal serogroups (C, W, X and Y).

MVP, based at PATH, is aiming to contribute to the elimination of meningococcal meningitis as a public health problem in Sub-Saharan Africa. The intended outcomes of the research are:

- Development of an affordable, thermostable, polyvalent meningococcal conjugate vaccine that has a four-year shelf life at room temperature and meets a target-price of between £0.82 and £1.65 per dose.
- Produce thermostable Group ACWXY meningococcal conjugate vaccine to meet desired specifications and demonstrate the vaccine’s safety and immunogenicity, in partnership with the Serum Institute of India Private Ltd.

Support to MVP will, in the longer term, contribute to the impact of reduced poverty through improved and affordable prevention of a common disease among the poor in the African meningitis belt. The short term target is to develop and test a new polyvalent meningococcal vaccine that will build upon the successes of MenAfriVac®, which has provided such positive results in preventing meningitis in populations across the African Meningitis Belt.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment A – Outcome met expectations

MVP is making good progress to meet its outcome – that is to develop a pentavalent, heat-stable meningococcal conjugate vaccine that will eliminate epidemic meningococcal meningitis from sub-Saharan Africa.

Overall output score and description A – Outputs met expectations

MVP has made good progress during the reporting period. They have completed the manufacturing of the clinical trial material for the first-in-humans (Phase 1) study, confirmed product quality by three independent sources, including confirmation that MCV-5 is safe and well tolerated. Reached agreement that the Phase 1 study will take place in the USA. The FDA has given positive feedback on the pre-Investigational New Drug (IND) submission, required before any clinical trial can begin. A decision has been made that PATH will be the regulatory sponsor of the Phase 1 trial. Planning for Phase 2 trial (in African toddlers) is advancing well. PATH led a collaborative modelling team to model the cost-effectiveness of the various MCV-5 introduction strategies on meningococcal disease in the African meningitis belt.

Key lessons
More than 235 million individuals have been vaccinated against group A meningococcal disease (using MenAfriVac®) and this has been an unqualified success. Group A meningococcal disease has virtually disappeared in all countries that have immunised 1-29 year olds with a strong herd immunity effect (indirect protection of unimmunised age groups). 8 countries have applied for funding to include MenAfriVac® in their national childhood immunisation programs in 2016. A polyvalent meningococcal vaccine against serogroups A, C, Y, W and X has the potential to eliminate meningococcal meningitis from the African meningitis belt

During the year PATH revised the clinical plan to build safely and effectively on the success of MenAfriVac®. The new plan incorporates a Phase 1 safety and immunogenicitystudy in adults in the USA followed by a Phase 2 trial in African toddlers. This design provides potential to move directly into two parallel Phase 3 studies in Africa and India that are designed to lead to licensure and WHO prequalification.

Key actions
To update the logframe to take into account progress and revised plans, by March 2017.

Has the logframe been updated since the last review? Yes
Both outputs have been updated since the last review, output one now includes later stages in the development of the pentavalent vaccine candidate and output two covers later stage work about ensuring that the vaccine, if successful, can be implemented in routine vaccine programmes.

C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Refine the Pipeline of Effective vaccines for Meningitis
Output number per LF		1	Output Score	A
Risk:		Major	Impact weighting (%):	75
Risk revised since last AR?		Y (new DFID risk category)	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
MCV-5 candidate progressed through manufacturing and preclinical testing	MCV – 5 manufactured and toxicology assessments complete by Q2 2016	Achieved: external assessment confirms MCV-5 candidate safe and well tolerated
Phase 1 study completed	Phase 1 protocol approved by regulatory authorities by Q3 2016	On track: all stages for approval for planned study ongoing
Phase 2 study completed	Contracts and agreements signed by Q1 2017	On track: negotiations ongoing

Key Points

The output met expectations and all work is on track. During the reporting period an external evaluation of the candidate (MCV-5) confirmed the product quality and stability, the toxicology study showed it was safe and well-tolerated. The clinical development plan was amended to take into account external advice for risk-mitigating strategies for the first-in-human (Phase 1) trial, which will take place in the US. The Food and Drug Administration (FDA) has given positive feedback on the pre Investigational New Drug (IND) submission, required before any clinical trials can begin. A decision has been made that PATH will be the regulatory sponsor of the Phase 1 trial. Planning for Phase 2 trial (in African toddlers) is advancing well

Summary of responses to issues raised in previous annual reviews (where relevant)

The logframe was amended to take account of the programmes achievements.

Recommendations

The logframe should be amended, to take account of the progress made during the reporting period, by March 2017.

Output Title	Develop a strategy for the use of the pentavalent vaccine, once available, in place of the existing MenAfriVac® vaccine
Output number per LF		2	Output Score	A
Risk:		Major	Impact weighting (%):	25
Risk revised since last AR?		Y (new DFID risk category)	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
2.1. Undertake modelling work to build evidence base about use of MCV-5 in vaccine programmes	Modelling team engaged by Q4 2015	Achieved: An international team of modellers have been engaged and working on this issue
2.2. Engage with ministries of health in relevant countries to gather support for use of MCV-5	Engagement with at least one ministry of health in the meningitis belt by Q4 2018	On track: results of clinical trials and modelling work required prior to any engagement

Key Points

The output is on track to meet its milestones and targets. PATH has identified a risk that the additional cost of replacing MenAfriVac® with the more expensive pentavalent vaccine may not be viewed as cost-effective by GAVI, the Vaccine Alliance, and other stakeholders. If MCV-5 is not used to replace MenAfriVac® and is instead used as a stockpile for reactive campaigns, meningitis outbreaks in Africa will continue, as evidenced by the 2015 meningococcal serogroup C epidemic in Niger. In mitigation, PATH is leading a collaborative mathematical modelling team with Harvard University, Yale University, Imperial College London, Cambridge University, the US Centers for Disease Control (CDC), the World Health Organisation (WHO), and the Norwegian Public Health Institute to model the cost effectiveness of various MCV-5 introduction strategies on meningococcal disease in the African meningitis belt. The study will use a cost/benefit model to evaluate four strategies (different vaccination approaches) that should lessen the meningitis burden in the African meningitis belt by 2020.

Summary of responses to issues raised in previous annual reviews (where relevant)

Not applicable

Recommendations

The logframe should be amended, to take account of the progress made during the reporting period, by March 2017.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)
Key cost drivers and performance
Vaccine development is a very costly process, particularly in the final stages leading to licensure. As new vaccines progress through the pipeline, they enter into successively more costly phases of development. MVP has a partnership arrangement with SIIPL, who provide cost effective approaches to development of new vaccines. The main drivers are staff time, together with laboratory equipment and consumables. MVP is managing costs appropriately and has been upfront regarding the potential additional costs associated with clinical testing in the US and Africa instead of India.

VfM performance compared to the original VfM proposition in the business case
Funding product development through a Produce Development Partnership (PDP), such as MVP provides value for money through:

Efficiency:
Responsive organisational structures with small core teams and open research models, which reduce operating costs.
Effectiveness:
A robust pipeline of vaccines and provision of support for the most promising candidates, ensuring greater prospect of success. Early go/no go decision making using in-house Scientific Review Committees.
Economy:
- Leveraging contributions from the private sector and/or in-country funds. The relationship with SIIPL demonstrates success in this aspect.
- Developing partnerships with other entities to support joint activities (e.g. clinical trial site development, development of assays).
- MVP staff constantly looking for better technical solutions to develop vaccines and are able to share knowledge and expertise with other vaccine development colleagues.

The modelling work being undertaken will address the issues of cost-effectiveness of using a more expensive vaccine that covers the five groups of meningococcal disease present in the meningitis belt when compared to the existing and highly successful MenAfrVac® which covers one of the groups (Group A). This work is important to build the investment case for Gavi, the vaccine alliance, and other global organisations, to increase the likelihood of financial support for vaccine distribution and uptake. Knowledge sharing opportunities have also been enhanced significantly through MVP’s developed professional networks.

Assessment of whether the programme continues to represent value for money
MVP continues to represent value for money and a good investment for continued DFID funding. The clinical plans have been adapted in the light of lesson learning, and although they will be more expensive (and will take longer) than what had been planned originally, this represents value for money overall because it will lead to faster product licensure and WHO prequalification. The increased cost is due to the complex nature of the trials and because conducting clinical trials in the US and Africa is more expensive than in India. PATH has considerable expertise in conducting clinical trials in the US and Africa.

Quality of financial management
MVP remains responsive to requests for financial and other management information. DFID has recently conducted a due diligence exercise on PATH and consider them to be a “low risk”. They have mature systems in place that help protect donor funding and their most recent Annual Audited Statement for the period to December 2015 is unqualified. PATH provides close oversight of downstream partners ensuring that they too have effective systems to reduce the risk of misappropriation and waste. Through the subrecipient agreements, PATH monitors performance and quickly invokes (when necessary) remedial action to deal with non-compliance or poor performance. PATH has a robust policy on Fraud, Corruption and Dishonesty and in addition provides protection to informants through its Whistleblowing policy, which reflects best practice and provides funders with a high level of assurance.

Date of last narrative financial report	10 October 2016
Date of last audited annual statement	June 2016

E: RISK (½ page)

Overall risk rating: Major

Overview of programme risk

Product development is high risk and potential vaccine candidates can fail at any stage in the development process. PATH staff have good experience in their fields of expertise and lessons learned from one programme are applied across the wider portfolio. The scientific basis and technical approach for the MVP approach is firmly grounded behind the success of a technically similar vaccine, MenAfriVac®. Technical and regulatory challenges continue to be overcome and there is a full expectation that the MVP candidate vaccine will be tested in a clinical trial where its success and impact can first be measured.

During the reporting period MVP has identified a number of additional risks, including that MCV-5 might not be viewed as cost effective by Gavi, the vaccine alliance and other stakeholders, the increased cost of validated assays to evaluate the effectiveness of the vaccine in clinical trials, the potential for increased cost of goods (the vaccine candidate) as its manufacture is scaled up, and potential political instability at African clinical trial sites. Mitigation actions are in place, which include working with partners with extensive technical experience, modelling of the cost effectiveness of different vaccine strategies, as highlighted in output 2, working on ways to keep assay and manufacturing costs to a minimum, and in-depth assessment of instability risks at clinical sites.

Outstanding actions from risk assessment

Risk is assessed by the DFID team regularly throughout the year and risk categories are changed to reflect current developments within the programme. DFID will also discuss ongoing mitigation plans for the risks highlighted, with MVP.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

MVP is on track with the revised plans which were agreed upon with DFID in 2014. Since early 2015 there have been further modifications to the clinical development plan, following expert advice. Having reviewed the clinical trial sites in Africa and found them to be limited, the First in Human (Phase 1) study will now be conducted in the US with the subsequent Phase 2 in a still to be determined African country.

Performance of partnership (s)

MVP has a productive partnership with the Serum Institute of India Private Limited (SIiPL) who have been a collaborator since the inception of this programme. MVP and SIiPL take all operational decisions jointly which helps ensure that they maintain a good working relationship. In addition this helps avoid misunderstanding of roles and ensures a coordinated approach to delivering the workplan. The DFID-MVP relationship is strong and there is regular communication on issues affecting he programme.

Asset monitoring and control

In general terms, PATH safeguards project equipment purchased with donor funds, through spot-checks over the perceived lifecycle of the product. This includes regular stocktakes and maintaining an up to date physical inventory. The Inventory is reconciled to the general ledger on a monthly basis. Due to the nature of DFID funding to PATH MVP, there are no large scale purchases that can be attributed to DFID funds. The inventory/ asset register is available to DFID on request.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

Not applicable as DFID provides core funds to MVP, no support is provided through government systems

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

More than 235 million individuals have been vaccinated against group A meningococcal disease (using MenAfriVac®) and this has been an unqualified success. Group A meningococcal disease has virtually disappeared in all countries that have immunised 1-29 year olds with a strong herd immunity effect (indirect protection of unimmunised age groups). 8 countries have applied for funding to include MenAfriVac® in their national childhood immunisation programs in 2016. A polyvalent meningococcal vaccine against serogroups A, C, Y, W and X has the potential to eliminate meningococcal meningitis from the African meningitis belt.

The importance of having a polyvalent vaccine was highlighted in July 2015, when the WHO released the information about an outbreak of meningitis serogroup C in Niger where there were over 5,000 cases and 260 deaths. An epidemic committee was activated to manage the outbreak at all the country levels. An international team composed of staff from WHO and the US Centers for Disease Control and Prevention (CDC), were deployed to support the Ministry of Public Health’s investigation of the outbreak and reinforce the country’s surveillance capacity. WHO and partners provided support to the government of Niger for the implementation of mass vaccination campaigns and other emergency control measures. The International Coordinating Group for Vaccine Provision for Epidemic Meningitis Control (ICG), with financial support of GAVI, approved four vaccination requests and released 468,000 doses of the older polysaccharide vaccine, which protects against the A, C and W serogroups, 488,500 doses of Mencevax® against ACWY and 200,000 doses of the newer conjugate vaccine, Menactra®, which protects against serogroups A, C, W, and Y. In addition, Niger’s government obtained 200,000 doses of polysaccharide ACWY vaccine from the government of Mali. In addition to the mass campaign immunisation, enhanced surveillance, social mobilisation and case management were performed in all affected areas. These combinations of interventions led to the control of the outbreak. The main lessons learnt from the management of this outbreak include the need of availability of more vaccines in the stockpile and the solidarity of non-affected countries by providing vaccines to Niger.

The polyvalent vaccines mentioned in the information from WHO are available in the developed world and are very costly and too expensive to be used in routine immunisation programmes.

Monitoring progress throughout the review period

The review was carried out by members of the Health research team in DFID’s Research and Evidence Division, with input from other funders and PATH. Members of the review team met with MVP at the PATH headquarters in Seattle and had a number of teleconferences during the year, during which progress and challenges have been discussed.