Programme Completion Report - Top Sheet

This Top Sheet captures the headlines on the programme performances performance over the course of its lifetime. Teams should attach summary sheets from each annual review over the life of the programme.

Review Date:	31 January – 17 February 2015

Title: 2013/14 UK Humanitarian Response in the Sahel (Tranches 1-6)
Programme Code: 203775	Start Date: 18 December 2012 (on ARIES)	End Date: 30 November 2014 (on ARIES)

Summary of Programme Performance

Year	Mar-14	Mar-15
Programme Score	A	A+
Risk Rating	Medium/ High	Medium/High

Financial Position

Original Programme Value	Tranche 1 - £15 million - approved in December 2012.
Extensions/ amendments	Tranche 2 - £5 million- approved in January 2013. / Tranche 3 - £10 million approved in March 2013. / Tranche 4 - £18 million approved in May 2013. / Tranche 5 - £35 million approved in October 2013. / Tranche 6 - £20m- approved in April 2014.
Log-frame revisions (with dates)	Tranche 1- 3 – March 2013. / Tranche 4 – August 2013. / Tranche 5 – October 2013. / Tranche 6 – update May 2014.
Total approved programme spend	£103m

Follow up actions required following closure
- Final report to be received from WFP (World Food Programme) in June 2015 with verified results for 2014. Final report to be received from ICRC (International Committee of the Red Cross/Crescent) in May 2015 for the 2014 results. This programme completion report (PCR) uses WFP’s final reports for 2013, and 2014 results updates. For ICRC it uses the final 2013 report and 2014 mid-year report.
- Close budgets.
- Compile and send information to ECHO (European Commission Humanitarian and Civil Protection Office) about partner performance as part of the information for PHASE (Providing Humanitarian Assistance to Sahel Emergencies; the follow on programme to this one).
- Where appropriate, all action points from the March 2014 Annual Review have been completed.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:

Introduction
This PCR is the final report for the 2013-14 UK Humanitarian Response in the Sahel. The funding was delivered through six tranches of funding from 18 December 2012 to 30th November 2014. Final results reports have been received from all NGO (Non-Governmental Organisations) partners, UNICEF and UNHCR. WFP have submitted a results update for their final results, though verified results against their 2014 PRROs (Protracted Relief and Recovery Operation) and EMOP (Emergency Operation) are not expected until June 2015. ICRC are funded against an annual appeal and so far only results for 2013 and the first part of 2014 have been received. The 2014 final annual report will be received in May 2015.

This review has been completed by members of the Africa Humanitarian Team (AHT) in Africa Regional Department (ARD), drawing on humanitarian advisory and programme management experience, as well as the third party monitoring carried out by Groupe URD. We have reviewed partner reports and conducted field visits to all countries where programmes have been implemented.

Outline of the programme and what it has achieved
The business cases and intervention summaries for the total approved £103 million humanitarian support to the Sahel in 2013/14 are saved on QUEST (document numbers 3813039, 3957204, 3957189, 4148384, 4263134 and 4711232). These documents detail the planned interventions for the approved £103 million of humanitarian assistance to the Sahel. The charts below summarise the proportion of spend to each country and to each agency/organisation. The table below outlines the commitments to each agency against each of the six tranches of support:

Organisation Funded	Tranche 1	Tranche 2	Tranche 3	Tranche 4	Tranche 5	Tranche 6	TOTAL (Tranche 1-6)
WFP (203775-104)	£5,000,000	£1,500,000	£5,000,000	£3,000,000	£13,000,000	£6,000,000	£33,500,000
UNICEF (203775-103 and 203775-106)	£3,000,000	£0	£5,000,000	£1,500,000	£8,600,000	£3,000,000	£21,100,000
UNHCR (203775-102 and 203775-105)	£3,000,000	£0	£0	£1,000,000	£6,000,000	£2,000,000	£12,000,000
ICRC (203775-101)	£4,000,000	£3,500,000	£0	£1,000,000	£7,000,000	£2,000,000	£17,500,000
Save the Children (203775-111)	£0	£0	£0	£2,000,000	£0	£1,300,000	£3,300,000
Oxfam (203775-110)	£0	£0	£0	£3,000,000	£100,000	£1,900,000	£5,000,000
Action Against Hunger (203775-108)	£0	£0	£0	£2,800,000	£0	£1,600,000	£4,350,000
International Rescue Committee (203775-109)	£0	£0	£0	£2,396,000	£0	£1,600,000	£3,996,000
Handicap International (203775-112)	£0	£0	£0	£500,000	£0	£0	£500,000
CARE (203775-113)	£0	£0	£0	£301,000	£0	£288,000	£589,000
Monitoring, Evaluation and Consultancy Costs (203775-107)	£0	£0	£0	£500,000	£300,000	£300,000	£1,100,000
TOTAL	£15,000,000	£5,000,000	£10,000,000	£17,997,000	£35,000,000	£19,988,000	£102,985,000

The approved £103 million commitment of UK funds extended support to the following partners and sectors:
- £31,000,000 to WFP for food assistance, cash for assets and cash transfers;
- £2,500,000 to WFP for UNHAS to run safe and reliable air transportation to deliver humanitarian assistance;
- £21,100,000 to UNICEF for a multi-sectoral package of support including health, nutrition and water and sanitation activities;
- £12,000,000 to UNHCR for a comprehensive package of support, including primary healthcare, education, shelter, protection and non-food items;
- £17,500,000 to ICRC to provide emergency health and medicine, food, seeds and tools, cash for work and livestock support;
- £3,300,000 to Save the Children to provide an integrated package of emergency relief and recovery assistance to vulnerable communities focusing on health, nutrition, child protection and education;
- £5,000,000 to Oxfam GB for water, sanitation and hygiene, food security, rural livelihoods development, governance, resilience building and pre-positioned stock;
- £4,350,000 to Action Against Hunger (ACF) to build resilience through cash transfer programmes, food and livelihoods projects;
- £3,996,000 to International Rescue Committee to address acute malnutrition and improve the recovery in the Sahel through improved access and coverage of quality WASH, health, nutrition and protection services;
- £500,000 to Handicap International to improve food-needs coverage targeted at vulnerable people and resilience;
- £589,000 to CARE for the International NGO Safety Organisation (INSO) to provide a security service for operational NGOs; and
- £1,100,000 for surge staff, monitoring and evaluation.

This programme was implemented across the Sahel region of West Africa in Mauritania, Mali, Burkina Faso, Niger and Chad. The final spend was £102.5m, due to small underspends of £20k by ACF, £12k by CARE/ INSO, £3k by IRC, £20k by Oxfam, £70k by STC, and £430k on the Surge Staff and the Monitoring and Evaluation budget line.
## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)
Overall Outcome Assessment
Combining all sectors together, including nutrition, health, education, livelihoods, water, sanitation and hygiene activities, including logistical support to aid workers across the Sahel, and understanding the potential of overlap in aid provision for some individuals (for example one beneficiary could very likely have received DFID funded food from WFP and WASH support from UNICEF) based on the results information submitted, DFID has reached 6,953,345 (including double counting between agencies and sectors). The overall expected reach of the programme (including double counting) up to the end of November 2014 was 5,856,425 people. This target is therefore reached (119% reached).
Following receipt of reports, the number of unique beneficiaries supported through UKaid to the Sahel region from December 2012 to November 2014 is at least 2,703,522 people or 138% of the target of 1,965,438. This figure is calculated by including the results of the agency reaching the highest number of people in a single sector for each country, depending on which sector reaches the highest number of unique beneficiaries (or the results of multiple agencies in that sector if they operate in entirely different regions of a country), in order to remove any potential double counting of individuals reached by different agencies and different sectors. Since this is a relatively conservative approach, it is likely to be an underestimate of the true number of unique individuals reached with some humanitarian assistance in the Sahel.
For DFID’s corporate reporting, we focus on the number of people reached specifically with food or cash through humanitarian interventions. The total number of unique people reached with food or cash specifically through this programme is 1,841,349 or 118% of the target of 1,559,635. Some of these people will be included in our reporting against the DFID Results Framework indicator on humanitarian food assistance.  We adjust the contribution for this programme to ensure we are not double-counting people who have already reported as beneficiaries of humanitarian food assistance funded through DFID’s 2012 Humanitarian Sahel Response.
In the detailed output section below, beneficiary numbers for both individuals (total reach for the sector) and unique (excluding double counting between locations) are provided. Targets for all sectors have been updated to include the final cumulative targets from across the tranches and this is what the overall actual results have been measured against.
Output Score and Description
Output 1 Food Security (20%): A+ = Outputs moderately exceeded expectation (118%)
Output 2 Nutrition (25%): A+ = Outputs substantially exceeded expectation (151%)
Output 3 Livelihoods (10%): A++ = Outputs substantially exceeded expectation (245%)
Output 4 Protection (5%): A+ = Outputs moderately exceeded expectation (119%)
Output 5 WASH (10%): A+ = Outputs substantially exceeded expectation (155%)
Output 6 Health (20%): A+ = Outputs substantially met expectation (137%)
Output 7 Education (5%): A+ = Outputs substantially met expectation (134%)
Output 8 Logistics (5%): A = Outputs met expectation (97%)
Although a number of outputs reported higher than expected numbers of beneficiaries the nature of this programme spread over two years and six tranches of funding has meant that there have been challenges with the tracking and reporting of beneficiaries from among partners. This programme has delivered beyond expectations given the complexity of the programme and the nature of the operating environment. The livelihoods sector has indeed substantially exceeded expectations but despite the results in other sectors our view is that the programme has exceeded expectations and that although purely on a results basis the programme substantially exceeded expectations (A++) in nutrition, WASH, Health and Education we have maintained these as an A+ rather than awarding an A++.

Lessons and how these have been shared
Groupe URD were contracted to conduct a Real Time Review (RTR) and identified that DFID funded programmes in Sahel have been relevant, efficient, and effective, with a significant positive impact and demonstrating a commendable effort to reach an acceptable level of coherence. DFID do their best to link humanitarian aid and development requirements. Specifically:
- DFID always allocates resources to well-chosen and experienced partners;
- Most of these partners have demonstrated a strong commitment to learning in the last ten years; and
- Despite not having a permanent presence in the field, DFID’s presence and contact with the partners has been regular and frequent enough to establish a climate of confidence and close relations with its partners.
However, six main recommendations and lessons were identified for future programming. These recommendations have been shared with NGO partners through the Sahel Working Group and where possible have been included within the PHASE programme design. The RTR report is a public document on the Groupe URD website and available at QUEST 4851402. The recommendation is noted in italics with the response in normal text:
- Partners need to be able to adapt programmes to changes in the context. Use of ECHO to manage funds in 2015-2017 will enable greater flexibility as their capacity to manage contract amendments is greater than that of the DFID Africa Humanitarian Team.
- Exploring the possibilities of developing locally-produced RUTFs (Ready to Use Therapeutic Foods) or other products for treating malnutrition as an alternative to expensive plumpy (high energy) products. Some positive examples have been presented by partners during field visits of fortified food production and formal RUTF production in country. This will be encouraged under the integrated programme in PHASE.
- Gradually decreasing assistance over time and instigating selective targeting with the goal of promoting self-sufficiency amongst those receiving assistance. This is a key part of the approach that brings together the core Sahel programmes in 2015, PHASE, BRACED (Building Resilience and Adaptation to Climate Extremes and Disasters) and ASP (Adaptive Social Protection). Though DFID recognises that the Strategic Response Plan (SRP) is often underfunded in the Sahel, it may well be some years before this aim is accomplished.
- Increasing the involvement of national institutions in the coordination of humanitarian interventions. Improved coordination between implementing partners and building stronger government leadership is a core part of the integrated nutrition approach.
- Developing a culture of ’agile institutions’ with enhanced and more fluid dialogue between the aid agencies and DFID. We shall continue to maintain our working relationship with the Sahel Working Group of NGOs and have encouraged them to be more proactive in sharing information, raising concerns and working on issues in a structured manner. Our partnership with ECHO should also bring improved coordination and a more fluid dialogue.
- Revising the alert and diagnosis mechanism that forecasts likely future food security needs based on climate information and agricultural production. There is too much uncertainty in the conclusions of the Cadre Harmonisé, which is more based on an attempt to reach consensus between a large panel of stakeholders rather than on sound evidence. The Cadre Harmonisé remains the mechanism of choice and ECHO are providing support to CILSS (Permanent Inter-State Committee for Drought Control in the Sahel) for improving data collection and management. By partnering with ECHO we have the ability to influence this to ensure it becomes a stronger mechanism for early warning and preparedness funding from ICF (International Climate Fund). In PHASE this should contribute to the use of early warning information leading to early action.
Additionally in terms of overarching lessons from implementation, delivering the programme through multiple tranches of funding, while necessary during the early phases of the crisis to maintain pace and avoid long gaps in funding, has been administratively burdensome for DFID and implementing partners. For this reason we have put in place predictable multi-year funding starting in 2015 aligned to the seasonal calendar. This should reduce administration, improve value for money and have greater impact, particularly working alongside new DFID-funded resilience programmes in Sahel. The three core Sahel programmes, PHASE (multi-year humanitarian programme), the ASP programme (a World Bank Trust Fund for social protection), and BRACED (resilience funding through NGOs), jointly address the need to strengthen the resilience of the most vulnerable while improving livelihood outcomes, supporting safety nets and meeting the needs of food insecure and conflict affected people.
Specific recommendations from the RTR include:
- Where funding is available, recommend continued support to livelihood interventions to link with resilience and development programmes; and
- Define the targeting between humanitarian and resilience livelihood programmes.

In response to these recommendations, the PHASE programme is providing continued support to livelihoods as part of the integrated nutrition programme and through the BRACED resilience programme in the Sahel.
Discussion about the use of different targeting mechanisms by humanitarian actors and the World Bank under ASP has resulted in a commitment from both development and humanitarian actors to use community based targeting as part of the process, leading to some form of consensus. Part of the ASP programme will focus on creating a single registry in some countries to ensure better coordination and accountability in targeting.

Recommendations:
Recommendations from the March 2014 Annual Review (2014 UK Humanitarian Response in the Sahel (Tranches 1-5) have been fully implemented for the multi-year humanitarian programme, PHASE for 2015-2017. PHASE adopts a more integrated approach to the nutrition crisis and expects to achieve better value for money through an innovative collaboration with ECHO. Predictable funding also enables implementing partners to develop longer term planning frameworks which should lead to better quality of service delivery and build more innovative programmes.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Most vulnerable households receive cash and/or food transfers to meet basic food needs and to cope with the lean season
Output number per LF		1	Output Score	A+
Risk:		Medium	Impact weighting (%):	20%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Annual Review Results – Mar 2014	Final Results - Nov 2014
Output Indicator 1.1: Total number of people receiving cash or food via this programme. / £103m individual target 2,033,439 / £103m unique target 1,559,635	1,231,763 individuals / M: 336,898 / F: 368,890 / Data not available: 525,975, / 1,182,904 unique beneficiaries / M: 322,125 / F: 354,451 / Data not available: 506,364	1,900,696 individuals / M:597,775 / F: 657,485 / Data not available: 645,436 / 1,841,349 unique beneficiaries / M: 583,002 / F: 637,957 / Data not available: 620,390
Output Indicator 1.2: Number of people receiving food (aid) assistance (subset of indicator 1.1). / £103m target 490,306.	218,222 individuals	346,876 individuals

Partner	Target	Actual	% achieved
ACF	64,076	95,515	149%
IRC	1,003	2,417	241%
Oxfam GB	172,171	173,192	101%
WFP	1,660,332	1,408,821	85%
ICRC	85,071	169,965	200%

Key Points
- Food and cash was the primary delivery mechanism of this response. While the results are considered good for all partners, the distribution of emergency food and cash remains a tool for emergency response and is unlikely to contribute to the wider goal of sustainable resilience strengthening for the targeted populations.
- There is a willingness amongst the key partners involved in food security programmes to move from the old model of food aid to cash based approaches. All partners delivered some cash intervention rather than relying solely on food aid and the larger number of beneficiaries received cash or vouchers rather than food in this response, as can be seen from the number of beneficiaries reached in 1.2 above. Wider DFID learning in 2015 on cash will contribute to better understanding of its use in emergency interventions.
- The results show that ACF, IRC, ICRC and Oxfam exceeded expectations. WFP met expectations in terms of unique beneficiaries but did not meet their overall reach targets. WFP however still reached the majority of beneficiaries. Their delivery is through implementing partners and may be less cost effective than providing funds direct to implementing partners for onward delivery. WFP funding under PHASE will focus on pipeline support rather than distribution.
- Gender disaggregation has improved among partners with all partners reporting some disaggregation. The high number of ‘data not available’ relates to household members of those who received a cash transfer or food assistance. Disaggregation has been done and is reasonably balanced between the genders for those in the household who physically received the food assistance, cash or voucher.

Summary of responses to issues raised in previous annual reviews
- Recommend that funding to support preparedness is considered to ensure food pipelines remain functional. This funding should continue into any further funding through a multi-year business case for the Sahel region. The multi-year business case (PHASE) has been approved and adopts a preparedness funding approach for pipeline emergencies in the Sahel.
- Recommend a further lobbying strategy is developed for the Sahel to increase funding to enable WFP to increase their capacity to deliver. An advocacy strategy is in place and will continue to be updated. This encourages greater resilience strengthening approaches to reduce the number of expensive food aid interventions.
- Recommend that DFID follows this up with partners when assessing future cash transfer proposals and continues to encourage WFP to move to cash as long as there are strong monitoring and post distribution monitoring undertaken. Implementation in PHASE will be directly contracted to NGOs by ECHO rather than using WFP to manage distribution through implementing partners. However, WFP will be funded to secure the pipeline where it is needed.
- Recommends, following the Super Cereal contamination DFID considers the WFP investigation report due to be submitted in April 2014 and acts on the recommendations of the report. This case was followed up with WFP in Rome and has now been acted on. Recent field missions have observed that the issue has been properly addressed and there are no contamination problems presently.
Recommendations for future programmes
- Food assistance projects which strengthen, improve and increase the agricultural production of the poor and the most vulnerable need to be supported throughout the Sahel rather than only food distribution.
- An integrated approach to address chronic vulnerability needs to be adopted.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Children and Pregnant & Lactating Women (PLW) treated for moderate and severe acute malnutrition.
Output number per LF		2	Output Score	A++
Risk:		High	Impact weighting (%):	25%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Annual Review Results – Mar 2014	Final Results - Nov 2014
Output Indicator 2.1: Total number of children and pregnant & lactating women treated for acute malnutrition via this programme. / £103m target Individuals 803, 964. / £103m target: Unique beneficiaries 515,026.	628,309 Individuals / M: 42,583 / F: 60,026 / Data not available: 525,700 / Unique beneficiaries: 521,439 / No disaggregation available from UNICEF.	801,523 Individuals / M: 42,583 / F: 69,524 / Data not available: 689,416 / Unique beneficiaries 794,323 / M: 42,583 / F: 63,888 / Data not available: 687,852
Output Indicator 2.2: Number of children treated for severe acute malnutrition (subset of indicator 2.1). £103m target 251,611.	219,574 individuals	626,737 individuals

*Note that the AR in March 2014 did not include all UNICEF results due to late delivery of reports and so the final results includes additional results from earlier tranches of funding.
Partner	Target	Actual	% achieved
IRC	104,553	129,071	123%
Save the Children	51,688	71,298	138%
UNICEF	659,090	601,154	91%

Key Points
- This output was underperforming at the Annual Review in March 2014 but the final performance has exceeded expectations with 151% of the target number of children reached. The individual target has not quite been reached and the unique beneficiaries reached are higher than expected as a result of minor changes in areas of operation resulting in less overlap of beneficiaries between agencies than originally planned.
- The UNICEF contribution mainly supported RUTF nutrition pipeline, which is an expensive but necessary intervention. Pipeline support was requested by UNICEF and prioritised by DFID partly due to the short term nature in some of the tranches of funding. UNICEF could have prioritised more on the integrated nutrition programme, including WASH, health, education and child protection, and the expectation is that with more predictable funding this will now happen.
- IRC disaggregated 66% of their nutrition data, Save the Children 36% and UNICEF have still been unable to disaggregate data as their results relate to the amount of RUTF distributed for treatment in health centres. They do not track who receives the product.

Summary of responses to issues raised in previous annual reviews (where relevant)
- Recommend that DFID continues support to malnutrition through an integrated approach to nutrition. The PHASE programme has a greater focus on integrated nutrition.
- Recommend that MAM screening is continued as part of a package of further support to tackle malnutrition in the Sahel. The PHASE programme has a greater focus on this in an effort to tackle both MAM and chronic malnutrition.
- Recommend DFID considers further support to deliver RUTF as part of a wider humanitarian strategy in the Sahel. Under PHASE, UNICEF’s RUTF pipeline will be supported, and we will continue to explore ways to ensure the availability of RUTF and locally fortified foods at reduced costs where needed. The lowering of the RUTF pipeline costs will enable greater allocation of resources to the integrated approach.
Recommendations for future programmes
While nutrition is a key component of UNICEF activities in the region, there remains no real nutrition strategy in the region. A regional strategy is a priority for UNICEF, as some countries in the region have and are preparing national strategies. DFID will lobby for regional coherence.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Famers and pastoralist families are more resilient to food insecurity.
Output number per LF		3	Output Score	A++
Risk:		Medium	Impact weighting (%):	10%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Annual Review Results / Mar 2014	Final Results - Nov 2014
Output Indicator 3.1: Total number of people in pastoralist and farming families with improved livelihood security via this programme. £103m target: Individuals 434,690. / £103m target: Unique beneficiaries 338,604.	718,829individuals / M: 209,245 / F: 224,493 / Data not available: 285,091 / 718,829unique beneficiaries / M: 209,245 / F: 224,493 / Data not available: 285,091	866,819individuals / M: 248,781 / F: 266,104 / Data not available: 351,934 / 831,934unique beneficiaries / M: 235,058 / F: 252,380 / Data not available: 344,496
Output Indicator 3.2: Number of people receiving support to improve livestock security (subset of indicator 3.1). £103m target: 265,774.	323,027 individuals / M:89,562 / F: 99,041 / Data not available: 316,838	536,994 individuals / M: 121,853 / F: 162,181 / Data not available: 252,960

* Note that improved data disaggregation for the final reports have been recorded compared to the published £83m Annual Review data for 3.2. The remaining beneficiaries for which disaggregation is not possible are primarily household members, where breakdowns of family members by gender are not recorded.
Partner	Target	Actual	% achieved
ACF	93,990	148,502	158%
Handicap Int.	38,519	38,539	100%
Oxfam GB	39,206	12,817	33%
Save the Children	15,424	23,827	154%
ICRC	247,551	643,134	260%

Key Points
- As indicated by the results and confirmed during field visits, this programme has been very successful with a positive impact on beneficiaries’ income generation and self-sufficiency.
- The only agency which did not perform as expected was Oxfam GB who only reached 33% of their target. This is primarily because the villages identified for the community projects were considerably smaller than initially expected (an average of 181 households per village as opposed to 500 households per village expected, based on the national average).

- Livelihood activities included funding for ‘warrantage’ schemes, creation and maintaining of cereal banks and distributing seeds, tools and livestock. (Under the warrantage system farmers, rather than selling their harvest at once, use it as collateral to obtain bank credit. In return for a loan, farmers store their produce in a locked warehouse with keys held by both parties. The credit allows them to buy essential inputs for the next planting, and hold onto the produce until the lean season where they sell it at a higher price. Farmers then redeem it from the warehouse, sell the produce, repay their loan and make a profit. This system means many farmers repay the loans even before selling their crop as they diversify the money into other income generating activities.)
- An important component of capacity building was included to ensure beneficiaries had the skills to utilise this support.
Summary of responses to issues raised in previous annual reviews
- Recommend that DFID ask partners for further details on how their livelihoods programmes coordinate with others. Improved coordination should be achieved through PHASE, and through the greater focus on the integrated approach and stronger monitoring at field level by ECHO Technical Advisers.
- Recommend remaining flexible on humanitarian programming, allowing agencies to re-orient the project as the changes in context necessitate. Although PHASE is a multi-year model there is flexibility within the ECHO contracting process to allow immediate amendments, and there are full annual reviews.
- Recommend continued support to livelihood interventions to linkage with resilience and development programmes (e.g. through the DFID funded BRACED programme). Targeting discussions with the World Bank on the ASP programme and mapping of the BRACED programme has happened and the results have been made available to ECHO to ensure linkages with the humanitarian programme.
Recommendations for future programmes
- Work closely with other key donors to increase the number of operational projects that will sustainably reinforce the resilience of the poorest populations in the Sahel.
- Focus on this sector is expected to contribute to reversing current trends of increasing number of food insecure people year on year.
- Ensure stronger links and support to the AGIR (Global Alliance for Resilience in West Africa) initiative in the region.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	People affected by the Mali crisis have their basic needs and rights supported.
Output number per LF		4	Output Score	A+
Risk:		Medium/High	Impact weighting (%):	5%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Annual Review Results – Mar 2014	Final Results - Nov 2014
Output Indicator 4.1: Total number of affected people (refugees, returnees, internally displaced people (IDPs), host communities) with their essential protection and assistance needs covered via this programme. £103m target: Individuals 316,095. / £103m target: Unique beneficiaries 216,027 .	231,362 individuals / M: 5,267 / F: 883 / Data not available: 225,212 / 231,362 unique beneficiaries / M: 5,267 / F: 883 / Data not available: 225,212	336,075 individuals / M: 9,879 / F: 8,967 / Data not available: 317,229 / 257,509 unique beneficiaries / M: 9,879 / F: 8,967 / Data not available: 238,663
Output Indicator 4.2: Number of conflict affected Gender Based Violence (GBV) survivors, children and youth cared for and protected with effective case management systems (subset of indicator 4.1). £103m target 1,000	4,418 individuals / F: 0; M: 0; Data not known: 4,418	5,895 individuals / F: 0; M: 0; Data not known: 5,895

Key Points
Partner	Target	Actual	% achieved
IRC	16,299	29,346	180%
Oxfam GB	21,360	25,222	118%
ICRC	1,422	4,576	322%
UNHCR	272,014	263,341	97%
UNICEF	5,000	13,590	272%

- All partners performed well in protection activities. Very few partners managed to disaggregate data for gender. Most partners have not collected data for Output 4.2 and so we cannot say that case management has been effective, or if this is the number of people who have been treated or affected by GBV. The number has been calculated from partner reports and various indicators which mention GBV or people affected by sexual violence.
- The majority of those reached under this output were through UNHCR. UNHCR extended its presence in northern Mali by opening a UNHCR field office in Gao in October 2013, and widened its partnerships in order to increase protection monitoring capacity as well as other basic assistance in Gao, Kidal and Timbuktu regions. In Gao and Timbuktu the Norwegian Refugee Council (NRC), an implementing partner, identified households who would benefit from income generating activities and helped vulnerable households with the rehabilitation and reconstruction of damaged shelters up to December 2013.
- In southern Mali cash transfer projects, run by UNHCR and NRC, which began in April 2013 helped vulnerable displaced Malian families pay rent. This new approach enabled refugees or displaced people to integrate themselves into the community, and by providing more assistance outside of camps, return or reintegration is more likely and more sustainable than just camp support.
- Other UNHCR partners also implemented activities including the construction and the rehabilitation of three schools in the Gao region in Mali by ACTED, the DRC established peace committees composed of community and religious leaders, and the community pre-registration exercise by the IRC.

Summary of responses to issues raised in previous annual reviews (where relevant)
Recommend that UNHCR’s criteria for distributions are communicated effectively with beneficiaries, prior to their biometric registration programme being implemented. This issue was raised in Mbera camp in 2013 and was addressed by UNHCR. Follow up monitoring visits have verified that this issue has been addressed.
Recommendations for future programmes
- Recommend that a variety of responses are used to reduce the number of refugees in camps and encourage with UNHCR, that the out of camp approach which includes host populations being part of the assistance package. This would be done in full respect of the refugees and displaced people rights, with a particular focus on security and protection issues.
- Protection activities should remain a priority area in the emergency programmes in general but specifically in conflict affected areas.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	People have improved access to safe water and hygiene
Output number per LF		5	Output Score	A++
Risk:		Medium	Impact weighting (%):	10%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Annual Review Results – / Mar 2014	Final Results - Nov 2014
Output Indicator 5.1: Total number of people able to access clean water and hygiene promotion via this programme. / £103m target: Individuals 1,261,326. / £103m target: Unique beneficiaries 1,047,151.	1,426,472 individuals / F: 320,277 / M: 169,384 / Data not available: 936,811 / 1,349,254 unique beneficiaries / F: 300,151 / M: 153,365 / Data not available: 895,738	1,674,184 individuals / F: 455,832 / M: 232,393 / Data not available: 979,155 / 1,625,303 unique beneficiaries / F: 451,434 / M: 228,983 / Data not available: 944,886
Output Indicator 5.2: Number of water points rehabilitated/built. £103m target: 311.	78	425

Partner	Target	Actual	% achieved
IRC	48,472	35,304	73%
Oxfam GB	76,656	60,873	79%
Save the Children	366,375	510,632	139%
ICRC	38,901	76,209	196%
UNICEF	712,922	991,166	139%

Key Points
- All partners performed well in WASH. UNICEF achieved higher than expected results in 5.2 as a result of more water points being rehabilitated which is more cost efficient than building new water points. IRC’s lower than expected results are from Chad, and Oxfam GB’s lower than expected results are from Niger which was due to the cost of materials being higher than expected.
- Availability of clean water is crucial in Sahel. The cost of water can be high as many of the region’s water sources are inaccessible and scarce. The livelihood and food security sectors depend highly on water access. Lack of clean water directly impacts the health and nutrition of the people in the region. The biggest constraint to the WASH sector is the lack of funding for often expensive infrastructure projects.
WASH interventions were integrated as part of the nutrition package of UNICEF, Oxfam, IRC and Save the Children. The UNICEF ‘WASH in Nutrition’ programme ensured that WASH services were accessible in all nutrition and health centres. All partners provided safe drinking water and facilities in health centres. Hygiene kits were distributed to families of malnourished children admitted in the centres. Summary of responses to issues raised in previous annual reviews (where relevant)
- Recommend DFID continues to support WASH activities in the Sahel, subject to good progress and NGO partners completing their projects successfully. This is fully integrated into the combatting nutrition approach within the PHASE programme.
- Recommend project funding takes into account the seasonal calendar to enable activities to take place before the agricultural season. The new PHASE programme follows the calendar year rather than the UK financial year which brings financing in line with the seasonal calendar.
- Recommend specific funding of WASH activities to provide safe water for health units throughout the year. This has been integrated into the approach in the PHASE programme.
Recommendations for future programmes
Recommend DFID continues to support WASH activities in the Sahel within the framework of the integrated nutrition approach. And therefore recommend specific funding of WASH activities to provide safe water for health units throughout the year.
## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	People have an improved access to healthcare and immunisation
Output number per LF		6	Output Score	A++
Risk:		Medium	Impact weighting (%):	20%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Annual Review Results – Mar 2014	Final Results - Nov 2014
Output 6.1: Total number of people receiving health treatment via this programme / £103m target: Individuals (includes double counting) 979,936. / £103m target Unique beneficiaries (excludes double counting) : 968,103.	1,262,083 individual and unique beneficiaries / F: 24,535 / M: 155,263 / Data not available: 1,082,285	1,341,309 individuals / F: 24,535 / M: 155,263 / Data not available 1,161,511 / 1,307,592 unique beneficiaries / F: 24,535 / M: 155,263 / Data not available: 1,127,794
Output 6.2: Number of malnourished children immunised via this programme (subset of indicator 6.1) / £103m target: 35,784.	109,065 individuals / F: 32,042 / M: 28,997 / Data not available: 48,026	133,929 individuals / F: 21,154 / M: 18,948 / Data not available: 93,827

Key Points
Partner	Target	Actual	% achieved
IRC	20,751	57,627	278%
Save the Children	85,405	54,654	64%
ICRC	51,430	48,428	94%
UNICEF	822,350	1,170,000	142%

- Performance in health was strong, particularly as a result of UNICEF’s increased coverage.
- Primary health care activities included nutrition, and free treatments comprising of consultations and medicines for children under five suffering from the following common diseases: malaria, diarrhoea, acute respiratory infections, skin infections, and intestinal parasites. Through providing free services to children under five there was improved access to primary health care which reduced the risk of subsequent medical complications and death.
- Awareness raising activities focused on topics including infant and young child feeding practices and hygiene practices. This reinforced communities’ knowledge, as well as encouraging behaviour change.

Summary of responses to issues raised in previous annual reviews (where relevant)
Recommend increasing the health component in nutrition support in further funding in the Sahel region. Health is included as part of the integrated nutrition approach in PHASE.

Recommendations for future programmes
The free primary health care and awareness programmes for children under five are key to preventing infant mortality and have been advocated for by a number of NGOs. However, this is a costly and generally unsustainable intervention as national governments tend not to have the resources to finance this and such interventions would need to be donor financed. Future advocacy work should encourage both the national governments and the international community to support this (France and the EU are both in favour of free health care for children under five.) Where this has been implemented improvements in infant mortality have been noted, although we do not have sufficient evidence to conclusively prove this. Support to health provision under PHASE is only covered where it is focussed on integrating nutrition treatment into health centres. DFID does not currently have any plans to support wider health work in the Sahel.
## .C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Refugee youth are provided with access to education
Output number per LF		7	Output Score	A++
Risk:		Medium	Impact weighting (%):	5%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Annual Review Results – Mar 2014	Final Results - Nov 2014
Output Indicator 7.1: Total number of children provided with access to education via this programme. / £103m target: Individuals (includes double counting) 18,020. / £103m target: Unique beneficiaries (excludes double counting) 18,020.	24,066 individual and unique beneficiaries / F: 863 / M: 1,193 / Data not available:22,010	24,066 individual and unique beneficiaries / F: 863 / M: 1,193 / Data not available:22,010

*Note that the AR in March 2014 did not include all UNICEF results due to late delivery of reports therefore the final results includes additional results from earlier tranches of funding

Key Points
UNICEF has mainstreamed education in its programme for children affected by conflict and food insecurity. Its ‘Education in Emergency’ programme allowed refugee children to return to school and therefore have full rights to education. UNICEF’s programme supported education staff and provided important education material like furniture for schools. Performance by UNICEF was good but as with all sectors, they failed to provide disaggregated data for girls and boys.

Summary of responses to issues raised in previous annual reviews (where relevant)
- Recommend that future education projects strongly link to other sectors e.g. health or nutrition. We estimate there are more results in providing a multi-sectoral intervention (or integrated approach) to reach children that are suffering from malnutrition issues. Any future education projects will be integrated into other sectors. However, education is not a priority due to funding constraints in the PHASE programme, which focusses more on addressing nutrition issues, and the needs of conflict affected people.
- Recommend ongoing monitoring of UNICEF’s education project to ensure the results increase to the expected rate. Monitoring did continue in this programme but as education is not a priority sector in PHASE funding will cease unless additional funding is available from other sources in the future.

Recommendations for future programmes
Education is not a focus of the PHASE programme. DFID is supportive of education as a tool for development and providing refugee children with a sense of normality and stability, but because of severe underfunding of the SRP in key sectors of food and nutrition, our focus will be on integrated nutrition programmes. Education in emergencies would only be considered if there was a significant increase in funding for the Sahel. Given the protracted nature of the crisis in the Sahel, development actors are better placed to intervene in this sector.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Safe and reliable air services during the rainy season, and improved access and security coordination for agencies and NGOs
Output number per LF		8	Output Score	A+
Risk:		Medium	Impact weighting (%):	5%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Annual Review Results – Mar 2014	Final Results - Nov 2014
Output Indicator 8.1: Total number of passenger air journeys via this programme. £103m target 8,955.	6,051	8,673
Output Indicator 8.2: Total metric tonnes (MT) of relief goods transported by air via this programme. £103m target 2014 22.64	14.08 MT	23 MT
Output Indicator 8.3: Number of tailored events improving NGOs security. £103m target 45.	123	123

Key Points
- Air operations are necessary in the Sahel as a result of insecurity, poor road infrastructure, long distances and lack of safe and reliable commercial air operators. The UN Humanitarian Air Service (UNHAS) provides humanitarian agencies air access to remote parts of Chad, Mali, Niger and Mauritania. This is crucial to implement and monitor humanitarian projects. Managed by WFP, UNHAS provides reliable air services to the humanitarian community.
- The International NGO Safety Organisation (INSO) provides high quality, real-time information and analysis of local safety conditions to assist humanitarian agencies in conducting their operations safely and to minimise the risks faced by staff and beneficiaries. 42 NGOs are registered in Mali and INSO provides timely and reliable security information.
- INSO provides regular security reports, face-to-face meetings and manage a flash alert system covering events from rocket strikes and small arms attacks in the north, through to demonstrations and road closures in the capital. NGO’s have fed back positively on the service. INSO have also run orientation services as part of an new staff induction process, and a generic Security Management course to build the skills of those responsible for NGO security management.
Summary of responses to issues raised in previous annual reviews (where relevant)
- Recommend DFID asks OCHA to invite INSO to the Civil Military and Security Cell (CMMC) meeting where important issues such as humanitarian space and security evaluation, are discussed. Groupe URD recommended this during the monitoring of the programme, but INSO confirmed they received a lot of information from CMMC and wanted to remain independent from the CMMC because they do not have a mandate to advocate for humanitarian space but to provide security. On this basis we did not take this recommendation forward.
- Recommend factoring in additional time to any newly funded organisations to allow them to recruit staff and set up offices. If partners are not already operating in an area where we want them to operate, costs will be built into the programme, but this will only be done if there are not more cost efficient solutions.
- Recommend further support to INSO, dependent on final reporting reaching expected targets. Support in PHASE to INSO will be considered by Advisers in discussion with ECHO.
Recommendations for future programmes:
Support to vital logistics services will remain a component of the humanitarian programme in the Sahel but will not be the primary priority.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance
The five countries in the Sahel programme have differing cost drivers, with some commonalities. For example, four of the five target countries are landlocked and require longer time frames for procurement and road transport of goods. The nature of the crisis in the Sahel means these countries don’t produce sufficient food for their populations and therefore must procure and import food from elsewhere.
Transport costs are high across the Sahel with poor road networks and dispersed populations. There is insecurity and poor infrastructure in the region, and in recent years this has become a significant cost driver in Chad. Following the repatriation (mainly to the Sahelian belt) of 70,000 Chadians living in Libya, remittances dried up and pressure on household resources increased. The disruption of imports from Libya, coinciding with the lean season led to an increase in the prices of basic foodstuffs, fuel, and transport costs. The policy of capping cereal prices impacts the availability of stocks, which in the Sahelian belt were 50% lower in 2014 than they were in 2010. Interrupted market supplies due to road closures during the rainy season are likely to contribute to further deterioration in household food security Access routes continue to close - Libya and Sudan are closed due to conflict and now the remaining access through Cameroon is challenging with the outbreak of conflict from Boko Haram and CAR. Transaction costs have dramatically increased in some countries – for example DFID funding to the UNICEF RUTF pipeline in the November 2013 payment showed 19% of the budget in Chad was spent on freight and transport compared to only 5% in neighbouring Niger.
Country	Planned Spend
	Food	Transport	%
Mauritania	7,423,704	5,519,097	74%
Mali	53,708,630	48,256,441	90%
Burkina Faso	18,509,062	4,247,104	23%
Niger	44,506,581	21,001,345	47%
Chad	106,194,353	146,276,157	138%

The table to the left shows WFP’s transport budget as a proportion of the planned PRRO/EMOP. Final reports from 2013 do not detail transport and storage as a separate cost and instead report on ‘food related activities and ‘cash related activities’. However, the table illustrates that transport remains a significant cost driver in the procurement and distribution of food.

VfM performance compared to the original VfM proposition in the business case
Two-thirds of the programme went to three UN agencies, with WFP taking the majority (32% of 2013 UK funding). This was due to the conflict in Mali, and the consecutive displacement of populations, which has reinforced the threat of food crisis in a region where chronic vulnerabilities already existed due to recurrent droughts and crop failures. The ICRC received approximately 19% overall, allowing it to implement its relatively complex multi-sector assistance and protection mandate in areas that others are often unable to reach.
A more detailed analysis of VfM for each partner has been conducted but as partners delivered a wide variety of activities (eight different output areas) it is hard to measure the performance of one agency or organisation against another and as such the VfM analysis presented here touches on statistical analysis, as well as a qualitative review to draw conclusions. Some observations are taken from Groupe URD’s RTR.
Economy: This has been difficult to compare across partners as no partner has procured the same items in a single country, and/ or the cost of items rather than activities has not been provided. Partners have delivered in line with original budgets and made savings through procurement and negotiations with suppliers. For example the service charge to micro finance institutions in Niger was negotiated down by both ACF and Save the Children which enabled more beneficiaries to be reached in the cash transfer programme.
Cost per beneficiary of individual outputs was noted by NGO partners though this is difficult to compare given the very different programmes implemented and the volume and frequency of cash being delivered. Oxfam GB only submitted a summary finance report therefore their information is not easily calculated by output. WFP and UNICEF finance reports are in USD which was converted at an exchange rate in 2013 of $1:£1.54.
The number and the wide range in value of variables mean that the observed values of standard output metrics in DFID’s new more detailed humanitarian budget format (measuring the cost of the same or very similar outputs) actually show wide ranges. For example the cost of delivery of SAM treatment is purely the delivery of RUTF while in others the provision of nutrition treatment might include heath messaging, case identification, and staffing costs as part of the cost of treatment of a child.
Cost per Beneficiary of Cash Transfers
Partner	Burkina Faso	Chad	Mali	Mauritania	Niger
ACF	£22.94	£18.53	£11.87	£43.77	£37.38
Save the Children	£15.41				£46.42
WFP	£7.96	£10.77	£27.46	£22.20	£37.07

The variation in cost is as a result of some partners funding more months of cash transfer than others and some providing condition cash transfers, the cost for which then included some sort of training or activity in addition to the cost of distributing cash.
Cost per beneficiary of nutrition programme
Partner	Burkina Faso	Chad	Mali	Mauritania	Niger
IRC		£11.77	£13.83		£86.22
Save the Children	£4.40				£1.99
UNICEF		£5.11			£41.26

Cost per beneficiary of health care provision
Partner	Burkina Faso	Chad	Mali	Mauritania	Niger
IRC		£10.21	£110.48		£6.11
Save the Children					£13.57

Efficiency: NGOs directly received less than a fifth of the resources but actually delivered more than 50% of the assistance funded by DFID in the Sahel through partnership agreements with UN Agencies.
Allocating resources directly to NGOs could be more efficient in terms of actual percentage of assistance reaching the beneficiaries through a limitation of the number of intermediaries needed to sustain their own institutional set-up. However the financial capacities and geographic coverage of NGOs does limit their absorption capacity. Therefore, at a time when transactional costs become an issue for donors, it is inevitable that large amounts will be directed to large agencies (who charge overhead fees) even if it is at an “efficiency cost”. Initially this programme gave 85% of funding to multilateral agencies. In PHASE, the split of funding between multilaterals and NGOs will aim for a 40:60 split between multilaterals and NGOs.
The cost of staffing as a proportion of the total implementation is an efficiency measure and the four NGOs funded under this programme provided efficient programmes, with all agencies spending around 20% on staffing. Agencies funded were generally operational already in the implementing areas– with the exception of northern Mali. This ensured that a greater proportion of funds could be directed towards beneficiaries and less into logistical set up.
Effectiveness: Beneficiary targets have been reached, and also widely surpassed. In 2013 programmes funded directly through NGOs were less effective because they started mid-way through and towards the end of the lean season. This was due to the time needed for partners and DFID to agree final proposals, although DFID did agree to retrospective eligibility of funds in order to reduce the impact of any delays. Funding to UN agencies and the ICRC – the bulk of the response – had started earlier in the year and was not affected. For 2014 UN agencies received confirmation of funds for key pipelines and preparatory activities in late 2013, and all partners received confirmation of funds from April-September (covering the lean season) in April 2014. In the future this will be improved further with PHASE which will ensure agreements are placed with partners each year well before the start of the lean season. All partners who made savings on their programmes were able to increase the number of beneficiaries they helped.
Effectiveness has significant cost implications which go beyond the budget cost of the programme and the nature of this programme with its six tranches of funding and multiple delivery mechanisms. It is difficult to demonstrate any effectiveness measures, but we know that resilience and early response activities save money; sustained support for pipelines is cheaper than responding to spikes; and quality implementation saves money by increasing impact and therefore reducing the need for further intervention. Effectiveness is context-specific and through PHASE we expect that local presence and knowledge will in turn save money through more appropriate programming. Effectiveness has many dimensions and generic formulations don’t capture key local issues.
Equity: Almost all partners have delivered gender disaggregated data for men and women with the exception of UNICEF and UNHCR. A number of other partners also disaggregated by age though not always by girls and boys. For ICRC and ACF ‘data not available’ refers to children and household members where one person in the household receives an input for the whole household. On the whole, targeting has allowed for a reasonable gender balance in the programme ensuring that women receive access to distributions. Community committees for targeting under the Household Economic Analysis have all had women and men, and elderly and youth representatives.

Assessment of whether the programme represented value for money
The programme represented value for money given the constraints of operating under six tranches of funding in a complex region.
Value for money assessments of DFID’s humanitarian responses take into account three key components of the humanitarian value for money triangle: cost, quality/appropriateness and speed/timeliness. It is important to consider all three together, as there are trade-offs. For example, higher costs may be acceptable in a speedy interventions situation which justifies more costly transport methods such as air, and higher costs of operating in highly insecure areas are justified based on the very high levels of vulnerability and need. For DFID’s work in the Sahel, the situation is that costs may be higher than in other areas of work.
NGOs typically offer better value for money assessments in their proposals and allowed better scrutiny of budgets than UN agencies or the ICRC and as such it has been difficult to offer a more detailed value for money assessment. By establishing value for money metrics at the beginning of the PHASE programme this will ensure that all agencies contribute to this in future.
Quality of financial management during programme
Below is a list of all the organisations we have funded and a short report on their financial performance:
Organisation	Financial Performance
WFP	Financial performance satisfactory and the budget is fully spent for the total grant.
UNICEF	Financial reports throughout the grant have been good, however the narrative was weak. Met deadlines for submitted financial requests and the budget is fully spent for the total grant.
UNHCR	Financial reports strong and provided right level of detail. The budget is fully spent for the total grant.
ICRC	Final report financial information is satisfactory and is fully spent for the total grant. We are awaiting the 2014 financial report which is due on the 1 June 2015.
Save the Children	Spending was slow at the beginning of the project, but picked up later. Best overall financial performance of the NGOs, though throughout the programme they required assistance with the technicalities of the financial reports. Overall they had the highest underspend in their programme of £70,000. This was due to the slow delivery of programmes and the favourable foreign exchange rate on the cash transfers activity in Niger which was fully completed.
Oxfam	Spending was slow to begin with, but picked up later. Throughout the project there were difficulties with providing financial requests. They had an underspend of £20,849 relating to an underspend on their direct project inputs and small overspends on transport, staffing and logistics.
ACF	Spending was slow to begin with but there was a small improvement after the first six months of programming. The PM team had to make repeated requests every quarter for their budgets and funding requests. Overall there was a small underspend of £22,440 in the cash transfer projects in Chad because of better transfer fee rates with the mobile operator, which significantly decreased the cost of this activity. Lower than expected regional office costs also contributed.
International Rescue Committee	Spending was slow to begin with, but they only underspent their total grant by £2,801. They were granted an extra month in 2014 for their programme in Mali due to security issues which allowed nutrition activities to be completed. Some help was required with the financial reports and they struggled to consolidate the budgets from the two periods of funding.
Handicap International	Q1 was very slow but the final report was satisfactory.
CARE	Spending was very slow at the beginning of the programme and a No Cost Extension of one month was granted for Tranche six of the programme. On conclusion of the project there was an underspend of £12,314 on the budget. This was a result of an overall underspend on office related costs.
M&E and Consultancy	Although the M&E work was implemented according to schedule, there were some minor delays from Groupe URD in processing invoices for payment. / CHASE OT surge staff invoicing is often late and inaccurate and there have been a number of delays in recruiting surge staff which has led to an overall underspend of £432,000 on this budget line for the programme.

DFID Programme Management staff worked with partners to ensure that financial reporting was accurate. The changeover between two different budget templates for NGOs within the project resulted in some delays from partners in submitting their reports. However, despite this, some partners did not allow enough time to liaise with their regional offices to complete these tasks on time, which resulted in some delays in submitting reports.

Date of last narrative financial report
Date of last audited annual statement

E: RISK (½ page)
Quality of risk management over the life of the programme
This programme is rated as a high risk programme because of the volume of funds, lack of DFID presence in the Sahel region and the security challenges throughout. Mitigation measures, such as putting in place third party monitoring from October 2013 to March 2014 reduced that risk significantly.
A comprehensive risk register was developed as part of the tranche five business case process in November 2013, which built on the risk previously identified. This was updated on a quarterly basis. During visits, DFID advisors followed up on risks relating to delivery and partners, and ensured that risks to DFID funds were also managed. Some examples of managing risks included:
- Security measures, including contingency plans, the recruitment of security officers, investment in radio and telecommunications and in training were all seen as critical by DFID’s partners.
- Managing programme-induced security concerns was also seen as part of project management. During cash transfer operations, security risks were moderate when they involved the distribution of vouchers. To minimize the risk of theft and hold-ups, only focal people were informed within the community and at a late stage on the exact day and location of the distribution.
- For cash distributions in Timbuktu, Mali, WFP secured the sites by systematically warning the forces of the MINUSMA of the date and exact time of the distribution. Mitigation also involved local traders who were responsible for delivering the cash at the distribution sites (6% charged). The possibility of using of mobile phones is currently being explored.
- Having conducted an evaluation of risks in collaboration with the Gao Rural Engineering Directorate. Mali, Oxfam suggested to re-orientate some activities. The evaluation, evaluated the socio-economic implications of the construction of mini dams, and highlighted the major risk of conflict between sedentary and nomadic communities due to this construction. It was decided to re-direct activities to the rehabilitation of water points. This shows the importance of regular contact between field staff, the capital, Oxfam’s regional office and DFID which allowed a rapid re-orientation of activities.

F: COMMERCIAL CONSIDERATIONS (½ page)
Delivery against planned timeframe
For the overall programme, the majority of our partners delivered against planned deadlines, with only a few (CARE/ INSO and IRC) requiring no cost extensions to complete the agreed work plan targets for the project. Both partner’s programmes were based in Mali and were affected by conflict in the north of the country which forced operations to temporarily close down, and the delay was one month over the agreed timeline.
Performance of partnership (s)
For the overall programme, most partners effectively performed their humanitarian programmes against agreed work plans and budgets for the overall grant. This was managed by the DFID team through quarterly narrative and financial reports, and also monthly phone calls between the partner, the programme manager and the advisor. Field visits to all countries and all partners by Advisers also identified any issues and ensured programmes were on track.
In the final tranche of funding (April-September 2014) there were some issues with the delivery and budget spend by NGO’s which was flagged by the programme management team who had concerns there would be a high underspend on the programme. Increased phone meetings and emails with partners with appropriate revised proposals resulted in a very small underspend on the overall programme and a programme which has delivered positive outcomes for its beneficiaries.
Asset disposal and value obtained by DFID
A number of DFID partners purchased assets for the programmes including motorbikes and vehicles, office and electronic equipment, and generators. Due to the quality of the roads in the countries within the Sahel, at the conclusion of the programmes, the condition of the vehicles was very poor, as well as the office equipment being highly utilised, so a decision was made to transfer all assets to the NGOs within the grant. According to the asset register which NGO’s submitted to DFID, the total value of all assets was £405,000 over the entire £103m grant. The value of the assets, especially the vehicles which had been heavily used throughout the programme were found to have significantly dropped, and considering the costs of freight and resale value in the UK, it was found it was more economical for DFID to gift the assets to the partner organisations.

H: MONITORING & EVALUATION (½ page)
Evidence and evaluation
Groupe URD conducted performance monitoring of the Sahel Programme between October 2013 and March 2014. URD reviewed projects and activities, tracking output results of the individual projects and overall programme. They also conducted a RTR in March 2014 which informed PHASE development and tranche six humanitarian programming.
Adequacy and coherence of the response: The evaluation showed the distribution of DFID aid in the Sahel is coherent with the level of fragility of the different populations. The budget allocated to each country is proportionate to the number of food insecure people. The country which received most aid was Mali followed closely by Niger and Chad. The smaller allocations to Mauritania and Burkina Faso were mainly aimed at Malian refugee camps and operations to combat malnutrition in specific territorial pockets. The wide range of activities funded by DFID in the Sahel reflects a proper understanding of the imperative need for multi-sector action. There is now much more experience in the Sahel of running cash and voucher-based projects.
Efficiency of the response and operations: In 2013, DFID allocated humanitarian resources to a wide range of humanitarian actors, including UN agencies, NGOs and the Red Cross movement. Two-thirds of DFID’s 2013 funding for Sahel went to three UN agencies, with WFP taking the majority (32% of all UK aid in 2013). This was due to the conflict in Mali, and the consecutive displacement of populations, which reinforced the threat of food crisis in a region where chronic vulnerabilities already existed from recurrent droughts and crop failures. The ICRC received approximately 19% of all funding, allowing them to implement their relatively complex multi-sector assistance and protection mandate.
NGOs directly received less than a fifth of the resources but actually delivered more than 50% of the assistance funded by DFID in the Sahel through partnership agreements with UN agencies. Allocating a greater proportion of resources directly to NGOs is more efficient in terms of the percentage of assistance reaching the beneficiaries as it limits the number of layers which are needed to sustain institutional set up, however this increases admin burdens for DFID and decreases flexibility. PHASE balances these considerations.
Accuracy of need assessments and targeting of the response: Significant progress was made in the Sahel in the area of food crisis prediction and diagnosis. The introduction of a West African approach in Integrated Food Security Phase Classification (IPC), named “Cadre Harmonise” was a major step forward for early warning systems in the region. Delays and difficulties in getting this appraisal right affected the implementation of a shared vision and a coordinated response. There remains some crucial time gaps between analysing collected data and the decision-making processes.
The majority of NGOs have internal M&E and programme revision mechanisms. Activity monitoring is largely used by DFID-funded partners across the whole Sahel region as a tool to check activities are on schedule and then completed. Staff on the ground judged the initial timetable of activities to be realistic and feasible, and did not highlight any problems in terms of financial, human or material resources in carrying out the programme. Situation monitoring is also a key element of overall monitoring, and in some cases, programmes were reoriented based on sound contextual factors and changes in needs.
Monitoring progress throughout the programme
- Lesson learning review from the 2012/13 programme. This was carried out in July and August 2013, in conjunction with the support of the CHASE results hub. Lessons are informing our approach for 2013/14 and beyond.
- Increased field visits to funded programmes in the region. The number of field visits to DFID funded projects to assess the implementation and performance by Humanitarian Advisers increased compared to 2012. A plan of visits to ensure systematic and effective coverage of the portfolio was developed. Back to Office reports with clear follow up actions were recorded on return for future follow up and a spreadsheet of follow up on partners was established.
- Establishment of third party monitoring for remote DFID Programmes. This programme was contracted by ARD and operational between October 2013 and April 2014 (the selected supplier was Groupe URD). The monitoring service, including data gathered was used by DFID to support project management and revision for the sixth tranche, improved DFID’s partner monitoring and improved accountability.
- A Real Time Review of the Sahel Humanitarian Programme was conducted during March and April 2014 to provide timely programme analysis to the implementers and managers of the humanitarian response and the DFID team. Information from this review was included in this PCR.
- The direct feedback from stakeholders, including beneficiaries revealed that key interlocutors including district health authorities, local technical services, and local authorities (mayors and prefects etc) appreciated the participatory approach when projects were designed. The beneficiary selection process was based on the involvement of community selection and complaints committees and their in-depth knowledge of households. In the majority of project settings, village leaders did not take a central role in committees.

## Smart Guide

## The Programme Completion Report is the opportunity to reflect on the entire programme, its performance, achievements, lessons and how learning will be shared to inform future programming.
The Programme Completion Report assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with headline information on the programme and any follow up actions
Introduction and Context
Briefly outline the programme, results achieved and contribution to the overall Operational Plan and DFID’s international development objectives. Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Outcome Assessment / Brief assessment of whether the programme achieved the Outcome
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessment
Key points
Summary of response to issues raised in previous annual reviews (where relevant)
Recommendations for future programmes
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case. Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme represented value for money? / Overall view on whether the programme was good value for money
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Quality of risk management over the life of the programme. How were risks managed, the degree to which they were realised and/or mitigated.
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / Could DFID be a more effective partner
Asset disposal and value obtained by DFID / How were assets managed throughout the programme? How have they been (or will they be) disposed to get maximum value?
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the programme / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process