## Annual Review 2020

Title: Global Environment Facility (GEF) Seventh Replenishment
Programme Value £ (full life): up to £250 million		Review date: June 2020
Programme Code: [AMP ID#] 300057	AMP start date: July 2018	AMP end date: June 2022

Summary of Programme Performance
Year	2019	2020
Overall Output Score	A	A
Risk Rating	Minor	Minor

DevTracker Link to Business Case:	37917779
DevTracker Link to results framework:	52177823

A. SUMMARY AND OVERVIEW

Description of programme
The Global Environment Facility (GEF) was set up in 1991 to provide funding to developing countries to address global environmental challenges, including climate change, biodiversity loss, land degradation, marine degradation and chemicals pollution. The GEF provides funding in support of five major international environmental conventions, which are the Convention on Biological Diversity, United Nations Framework Convention on Climate Change, Stockholm Convention on Persistent Organic Pollutants, UN Convention to Combat Desertification, and Minamata Convention on Mercury. The work the UK funds and catalyses through GEF underpins the UK position in the international climate, biodiversity and other environmental negotiations and agreements. GEF funding also supports UK Government priorities including the illegal wildlife trade and marine protection and contributes to the achievement of the Sustainable Development Goals (SDGs).
Since its inception in 1991, the GEF has supported management of more than 3,300 protected areas covering 860 million hectares (an area larger than Brazil), 1,010 climate change mitigation projects contributing to 2.7 billion tonnes of greenhouse gas emission reductions, sustainable management of 34 of the world’s major river basins and provided $131m to the Global Wildlife Programme to tackle the illegal wildlife trade.
The GEF provides grants and other support to developing countries for projects and programmes to address global environmental problems. The GEF works with developing countries, and a set of 18 accredited agencies (including multilateral development banks (MDBs), UN agencies and environmental NGOs), to develop and implement projects and programmes. The GEF is governed by a balanced board (GEF Council) of developed and developing country representatives; its work is co-ordinated by a Secretariat and the World Bank is Trustee. The UK has its own constituency seat on the board, represented by DFID with an Alternate from Defra. The projects and programmes funded by the GEF are developed in accordance with a set of Programming and Policy Directions set at the start of each four-year replenishment period.
The UK has supported the GEF since inception. In the most recent seventh replenishment of the GEF (GEF7) the UK committed £250m, which equates to approximately 10% of total donor contributions to GEF7. The replenishment cycle is informed by a comprehensive evaluation carried out by GEF’s Independent Evaluation Office. At the most recent replenishment the UK pushed for strong alignment with HMG priorities during negotiations, this included successfully securing an increase in allocation to tackling the illegal wildlife trade. GEF7 marks a significant step forward by the GEF in its potential to deliver more transformational results in addressing environmental degradation. It does this through taking a multisectoral integrated multi-stakeholder programming approach which tackles the underlying drivers and systems involved in environmental degradation. The main vehicles for this multisectoral approach are ‘Impact Programmes’ (IPs), which under GEF7 include in Food, Land Use, and Restoration; Amazon Sustainable Landscapes; Congo Sustainable Landscapes; dryland Sustainable Landscapes; and sustainable cities.
[note] More details of GEF’s Impact Programmes available here.

Summary supporting narrative for the overall score in this review
This annual review takes place in the context and takes account of the Covid-19 pandemic. So far GEF has responded well to the crisis, quickly developing GEF short, medium and long-term steps to respond to the pandemic. GEF has also adopted new ways of working to keep international business going with the selection of a new CEO and the June Council Meetings being carried out virtually.

This Annual Review assesses the second year of programming under the 7th replenishment of GEF. The programme is performing well according to the programming and policy directions set at the start of the current replenishment. Through the approval of a work-programme at the June 2020 Council meetings, the half-way point of the 4-year replenishment period, 61% of overall resource programming under GEF-7 has now been approved. In addition, at this mid-point, all 5 focal areas (biodiversity, climate change, land-degradation, chemicals and waste, and international waters) have programmed over 50% of resources. The funds programmed, as captured under output 1 below, are largely delivering the expected results anticipated at this stage of the replenishment cycle, and against some indicators already exceeding the expected results for the entire replenishment period.

Twenty percent of the total UK pledged contribution is conditional on achievement of agreed targets for performance against agreed policy reforms. The GEF has made good progress in these policy areas which include: improved resource allocation; optimising the use of GEF resources in different countries; results reporting; private sector engagement; increased operational efficiency and transparency; improved management of data and information; and gender equality and women’s empowerment. As a result of achieving these targets the GEF received the full amount committed by the UK for this year.

Overall output score and description
Overall output score is A with the following individual output scores:
Output 1 - Global environmental benefits to be delivered through approved GEF7 projects and programmes A.
Output 2 - GEF7 policy recommendations delivered successfully A.

Major lessons and recommendations for the year ahead
- The GEF has made a good start in being proactive and demonstrated flexibility in responding to the Covid-19 pandemic. However, the crisis will continue to dominate the work of GEF for the remainder of this replenishment period, requiring clear leadership and a strategic approach to managing the GEF portfolio.
- The UK will actively engage including exploring how the Global Wildlife Programme can be used to support developing countries’ ecological response to the COVID-19 pandemic.
- With the UK’s interest of promoting a global green recovery to COVID-19, the UK will engage with the GEF Secretariat where adapting existing projects and programmes in the GEF portfolio, such as the Global Wildlife Programme, can integrate short-term and medium-term responses to COVID-19.
- Over the coming year, the impact of the pandemic on the implementation of the current portfolio will need to be closely scrutinised. The inability to carry out aspects of programmes funded by the GEF, will both have an impact of realising results, but also impacting on the gains made over the last years, and even decades, to achieve sustained environmental benefits.
- The UK will continue to engage strongly through the GEF Council in steering policy reforms, through the UK’s results-based funding tranche, and approve work programmes that fit with UK priorities.
## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

Summary of the theory of change
The theory of change is built around the contribution the GEF makes in supporting sustainable development and reducing the detrimental impact of climate change and environmental degradation on the poor. In summary, the assumptions made in the business case and theory of change are that an adequately resourced GEF, which is managed effectively, through delivery of high impact projects will deliver sustained global environmental benefits. Given the poorest people and the poorest countries in the world are the most reliant on the environment for their incomes and livelihoods, delivering these global environmental benefits contributes to delivering the Sustainable Development Goals, particular those related to the environment: SDG13 (climate action) SDG14 (life below water), SDG15 (life on land). GEF’s role in this context is to provide the leadership in demonstrating the practical actions to tackle environmental degradation.

No major changes have been made to the GEF’s theory of change in the past year. However, like all programmes, GEF has been affected by Covid-19. The UK will keep a close eye on this and consider whether the context and assumptions are valid. Should the need arise the UK will work with GEF Secretariat on any modifications.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

GEF7 programming remains highly relevant to addressing the overall impact for the programme: The reduction or reversal of trends in environmental degradation at a global scale. However, GEF resourcing itself only provides a small contribution to the overall financing in the hundreds of billions of dollars required to have a major impact on the tide of global environmental degradation. The challenge remains huge, and any progress made is fragile, and potentially undone by events such as the Covid-19 pandemic. The GEF does however play an important catalytic role and through the integrated Impact Programmes, seeks to deliver a more transformative shift by addressing the systems underlying biodiversity loss and climate change.
[note] Global finance required to achieve the Convention for Biodiversity 2011-2020 Aichi targets was estimated $150-440bn per year.

There is a strong case for GEF to develop a clear position on Covid-19 and its response. The drivers behind the transmission of pathogens from wildlife to human populations include the continuing degradation of nature and natural systems: these are core components of GEF’s remit. In response, the GEF Secretariat has been working across the GEF Partnership (of Implementing Agencies etc), to identify a set of immediate, medium and long-term responses. More detail can be found at section D (below). The GEF’s Covid-19 response is an opportunity to promote positive change, supporting a ‘green-recovery to build back better’.
[note] Response to COVID-19.pdf

Progress towards the implementation of a Private Sector Strategy for GEF is slightly delayed (further detail at Output 2). The private sector is an important element of the GEF7 replenishment, and key to delivering transformative change. While this slower than desired progress is disappointing, it has enabled stronger engagement across all stakeholders in the GEF partnership in considering the important role of the private sector. In the coming 6 months, these stakeholders will work together to deliver a private sector strategy that has the support from all sides of the GEF partnership.

Progress towards impact is measured through the GEF’s Independent Evaluation Office’s Overall Performance Studies (OPSs). OPSs are comprehensive evaluations that assess the performance, institutional effectiveness and impact of GEF. The approach to the proposed seventh comprehensive evaluation of the GEF (OPS7), focussed on the evaluation of GEF7, has begun. The UK agrees with the overall focus on two areas: Strategy and Institutional Issues and GEF Performance, Impact, and Sustainability. Within Strategy and Institutional Issues, GEF proposes to focus an evaluation strand on ‘GEF policies on safeguards; gender; and engagement with stakeholders, indigenous peoples, the private sector, and civil society. This is welcomed. We also support the suggestion to include ‘Institutional processes including results-based management and knowledge management’ as one of the themes addressed in OPS7. We will continue to pursue our request that the evaluation does some early work to look at ways of measuring the impact of GEF programming on zoonotic disease risks. This isn’t presently covered in the approach paper, although the paper is appropriately framed on the context of the COVID-19 pandemic.
[note] OPS7_Approach_paper_June_2020

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

The GEF remains critical in providing the finance to achieving the sustainable development goals, particularly those related to climate and environment. Alongside the trade in wildlife, and markets that sell it, the emergence of coronaviruses can be linked to habitat destruction and human encroachment into wildlife habitats. This arises from agricultural expansion or other development purposes which bring people and their livestock into closer proximity to wildlife, creating opportunities for the emergence of novel infections in human populations. Transformative GEF programming promotes food security through sustainable agriculture, combats illegal wildlife trade, reduces poverty and tackles environmental degradation. All are critical in reducing the risk of future pandemics but also addressing drivers and pressures on the environment that may occur as a result of the economic impact of Covid-19. The above points towards the importance of continuing to support the GEF in promoting transformational change.

## C. DETAILED OUTPUT SCORING

Output Title	Global environmental benefits to be delivered through approved GEF7 projects and programmes
Output number per LF		1	Output Score	A
Impact weighting (%):		70	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones to June 2020	Expected results of projects and programmes approved at June 2019	Expected results of projects and programmes approved at June 2020
1.1 Terrestrial protected areas created or under improved management for conservation and sustainable use (million hectares)	100	70	88.2
1.2 Marine protected areas created or under improved management for conservation and sustainable use (mha)	4	2.9	1,276.3
1.3 Area of landscapes restored (mha)	3	4.7	6.6
1.4 Area of landscapes under improved practices (mha; excl. protected areas)	160	87	107.4
1.5 Area of marine habitat under improved practices (mha; excl. protected areas)	14	1.8	6.6
1.6 Greenhouse gas emissions mitigated (million metric tons of CO2e)	750	581	1,157.9
1.7 Number of shared water ecosystems (fresh or marine) under new or improved cooperative management	16	9	31
1.8 Globally over-exploited marine fisheries moved to more sustainable levels (thousand metric tons) (Percent of fisheries, by volume)	1,750	8.2	1,657
1.9 Reduction, disposal/destruction, phase out, elimination and avoidance of chemicals of global concern and their waste in the environment and in processes, materials and products (thousand metric tons of toxic chemicals reduced)	50	30.9	34.9
1.10 Reduction, avoidance of emissions of POPs to air from point and non-point sources (grams of toxic equivalent [gTEQ])	650	557.8	1,479.6
1.11 Number of direct beneficiaries disaggregated by gender as co-benefit of GEF investment	New indicator	15.2 million / (50% women)	119.7 million / (49% women)
[note] The UK’s logframe includes milestones for each of the 4 years of GEF 7 have been calculated upon an assumption that there is a linear increase in results to the 4-year GEF target. Given the time to develop concepts over the replenishment period in some focal areas in particular the approval of projects and their expected results does not always follow such a linear path.
[note] The results for GEF7 are expected results from the sum of projects approved for funding from financing secured under the GEF7 replenishment. Actual achieved results following implementation may differ.
[note] Corporate_Scorecard_June_2020.
[note] In absence of past, portfolio-level monitoring of beneficiary data, no GEF-7 target is proposed, but the indicator will be monitored across over the GEF-7 period. Of projects that report on the number of direct beneficiaries, however, all are expected to provide gender-disaggregated data.

Briefly describe the output’s activities and provide supporting narrative for the score.

The GEF7 results framework is linked to the GEF7 programming strategy through 11 agreed core indicators. Output 1 of the UK’s logframe for GEF7 is taken from these agreed indicators and targets. The framework allows for the comprehensive monitoring of the results expected by GEF projects and programmes, including multiple benefits across focal areas as well as tracking data on beneficiaries disaggregated by gender.

This annual review takes place halfway through the GEF7 replenishment period. By June 2020, overall GEF7 programming has allocated 61.1% or $2,378m of the overall GEF7 resource allocation of $3,895m. Allocation of resources across focal areas is relatively even, with programming to date varying from International Waters at 50.6% of allocated resources to Land Degradation and Biodiversity at 69.9% and 61.8% respectively. Chemicals and Waste and Climate Change fall within these levels of programming at 54.2% and 58.1% respectively.

The above programme of GEF7 finance is translating into increases across GEF core indicators, and in some cases (1.2, 1.3, 1.10) exceeding the final targets for GEF7. Indicator 1.2 is a significant outlier in comparison with other results and therefore a re-evaluation of the target should be considered. There is no official target for the beneficiary indicator 1.11 but the proportion of women making up the expected beneficiaries of GEF investments has slightly decreased from a reported 50.25% in June 2019 to 48.54% in June 2020.

Most of the Biodiversity Focal Area funding programmed to date has been allocated to mainstreaming approaches in response to a higher country demand relative to projects focused solely on Protected Area management (indicator 1.1). Costs for projects in landscapes and seascapes outside of protected areas (measured in hectares) have been higher than initially estimated, meaning investments have not delivered the same hectarage coverage as past replenishments. This partly explains the slower progress towards indicators 1.4 & 1.5. A ramping up of marine International Waters programming since June 2019 has resulted in substantial delivery against indicator 1.8, nearly achieving the set milestone for June 2020. We are expecting future work programmes to increase investment in improved land and marine management practices both within and outside of national protected area systems. We will continue to monitor future work programmes to ensure expected results in the Biodiversity, International Waters and Chemicals and Waste focal areas match the allocation of resources.
[note] Biodiversity mainstreaming in GEF programming is the process of embedding biodiversity conservation and sustainable use objectives in the management of the production landscapes and seascapes outside of protected areas. This is achieved through support to an array of policies, strategies and practices that engage key public and private sector actors.

During the GEF7, replenishment negotiations, the UK and several other donors pushed for the GEF to increase integrated programming to tackle the underlying drivers and systems involved in environmental degradation. Our expectation was that these Impact Programmes (IPs) would increase both the impact and sustainability of GEF interventions. By June 2020, GEF-7 Impact Program resources have been nearly fully programmed across five programmes (Food, Land Use, and Restoration, three under Sustainable Forest Management for Major Biomes and Sustainable Cities). Programming under the Sustainable Cities Impact Programme appeared during the last Work Programme. The previous annual review had noted that Impact Programmes were contributing significantly to 4 of the core indicators (core indicators 1.1, 1.3, 1.4, and 1.6) with, as had been hoped for, significantly higher proportion of the overall GEF7 proposed results than what would be predicted based on the proportion of resources programmed. This trend has continued with IPs delivering between 21-68% of the results on the 4 core indicators despite programming only 15% of the STAR (System for Transparent Allocation of Resources); the system that determines the amount of GEF resources that a given country can access in a replenishment period.
[note] GEF-7-STAR.pdf

At this half-way stage of GEF7 programming, there has been a significant and relatively even programming of resources across the focal areas. This has translated into good progress against the 11 core indicators. As such this output 1 has been given an aggregate score of A within this annual review.

VfM of this output compared to the proposition in the Business Case, based on performance over the past year

The business case highlights the importance of effectiveness (spending wisely) i.e. ensuring the chosen outputs of an intervention are those most likely to result in the desired outcomes. The new GEF results framework of eleven core indicators, covering the five focal areas for GEF, provides an ability for GEF to capture, monitor, aggregate and report on results across the different types of intervention financed by GEF. This is most relevant to Impact Programmes, which seek to provide multiple benefits across different focal areas. As noted above, the GEF7 allocation for impact programmes has now been almost fully programmed. With the high percentage of core indicator results delivered through such programmes, and with the performance against these indicators broadly on track, GEF can be seen to be delivering value-for-money against the results for this output.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

- The 2019 Annual Review included a recommendation of engaging the GEF Secretariat to highlight the UK’s expectation of seeing programming under the Sustainable Cities Impact Programme appear in the next Work Programme. The UK discussed this Impact Programme with the GEF Secretariat, which was included in the December 2019 Work Programme.
- After a few months into the COVID-19 crisis, GEF expected results have not significantly suffered. However, in the coming year it will be important to monitor the impact of COVID-19 may have in meeting the final GEF7 targets.
- As such, in the coming year, it will be important to continue to track performance against results targets for all core indicators, and resource allocations that have been agreed across the GEF7 portfolio.

C. DETAILED OUTPUT SCORING

Output Title	GEF7 policy recommendations delivered successfully
Output number:		2	Output Score:	A
Impact weighting (%:		30	Weighting revised since last AR?	N

Indicator(s)	Milestones to June 2020	Progress at June 2019	Progress at June 2020
2.1 Resource allocation (System for Transparent Allocation of Resources)	Council agreed updated STAR being implemented. / Secretariat reporting to Council on the programming of funds and expected global environmental benefits across core indicators	Achieved. In June 2018, the GEF Council approved a new Policy for the System for Transparent Allocation of Resources (STAR). / Information on cumulative STAR utilisations was presented at the June 2019 Council meeting, via the corporate scorecard.	Achieved. The latest corporate scorecard from June 2020 provides the GEF-7 utilisation rates against STAR, of funds per focal area, by region, for the group of countries categorised as LDCs, and for the group of countries categorised as Small Island Developing States (SIDS).
2.2 Optimising the use of GEF resources in different countries	Overall GEF portfolio to reach at least 7:1 Co-Financing ratio to GEF Project Financing. / For the portfolio of projects and programmes approved in Upper-Middle Income Countries and High-Income Countries that are not SIDS or LDCs to reach a ratio of Investment Mobilised to GEF financing of at least 5:1	Achieved. 7.8:1 Co-Financing at portfolio level. 5.9:1 Investment Mobilised.	Achieved. 8.3:1 Co-financing. Investment Mobilised 6.0:1
2.3 Results	Council agreed measures on results and sustainability being implemented. / Concrete measures undertaken in the design, monitoring and evaluation of projects and programs that would allow for increased sustainability, including financial sustainability	Achieved. Papers on Measures to Enhance the Sustainability of GEF Projects and Programmes were presented Council meetings in December 2018 and June 2019.	Achieved. In the last year, the Secretariat has engaged in significant consultations on sustainability (or “durability”) across the GEF partnership. These engagements have included discussions with Agencies, with countries, with the Scientific and Technical Panel (STAP), and with the GEF Council itself through two Council papers.
2.4 Private sector engagement	Council agreed strategy on private sector engagement being implemented. / Reporting on private sector co-financing.	Partially Achieved. In the June 2019 meeting the Secretariat informed the Council (GEF/C.56/Inf.05) of the composition of private sector advisory group and of its plan to submit the draft private sector for Council consideration at its 57th meeting in December 2019.	Partially Achieved At the 58th Council Meeting June 2020, The Council requested the GEF Secretariat to prepare an Implementation Plan to be presented at the 59th Council Meeting alongside a revised Private Sector Engagement Strategy. To support this work, a Working Group of interested Council Members and the GEF Secretariat has been created.
2.5 Operational efficiency and transparency	Council agreed measures to enhance operational efficiency and transparency being implemented.	Achieved. In its 55th meeting, the Council approved Policy Measures to Enhance Operational Efficiency, Accountability and Transparency.	Achieved. The new set of policy measures came into effect in March 2019.
2.6 Improved management of data and information	Continued implementation of the improved information management system. / Regular reporting to IATI registry	Partially Achieved. Secretariat initiated the process by creating an IATI publisher account.	Achieved. The GEF became an IATI publisher in June 2019 with its first submission of project level data to the IATI registry.
2.7 Gender equality and women’s empowerment	Council agreed measures in GEF7 gender strategy being implemented according to agreed timetable. Annual updates by the Secretariat on the progress on activities outlined in the Strategy, as well as on the results framework. / Percentage of projects that have conducted a gender analysis, plan to carry out gender-responsive activities / Percentage of projects that include sex-disaggregated and gender-sensitive indicators / Percentage of female beneficiaries	Achieved. Progress report on the GEF gender implementation strategy presented at the June 2019 Council. / 98% of GEF7 projects provided indicative information on gender relevant to the proposed activities. / 85% of projects explicitly stated that they expect to develop sex disaggregated and gender sensitive indicators. / 94% of projects are tagged to contribute to closing gender gaps	Achieved. The GEF-7 corporate scorecard from June 2020, provides information on quality at entry of GEF-7 approved projects and covers the indicators outlined in the GEF-7 Results Framework on Gender Equality and Women’s Empowerment: / 99% of projects that considered gender issues at the initial project design. / 87% of projects expecting to develop gender sensitive indicators / 93% of projects tagged to close gender gaps with 50.4% of the expected beneficiaries in these projects are women. / .
[note] Independent Aid Transparency Initiative

At the Seventh Replenishment of the GEF Trust Fund participants agreed on a set of Policy Recommendations, in line with UK priorities, these form the basis for the indicators of this output and included:

System for Transparent Allocation of Resources (STAR) methodology updated. At the start of the GEF7 replenishment the GEF Secretariat presented a new Policy for the STAR, which introduces new focal area floor allocations, increases the weight of the GDP index, and increases flexibility.

Optimising the use of GEF resources in different countries with a view to mobilising greater investments in measures to achieve global environmental benefits. This included: updating the co-financing policy; introducing the concept of “investment mobilised”; raising the level of ambition for the overall GEF portfolio to reach a co-financing ratio of 7:1; and setting out clearer requirements for Agencies and the Secretariat to document, monitor and report on co-financing and investment mobilised at the project, programme and portfolio levels. The June 2020 Corporate Scorecard reported the ratio of indicative GEF-7 co-financing to GEF project financing at 8.3:1, surpassing the target of ‘at least 7:1’. The ratio of indicative investment mobilised in projects and programmes approved in Upper-Middle Income Countries and High-Income Countries that are not SIDS or LDCS at 6:1 was also greater than the replenishment level target of 5:1.

Results. Updated Results Architecture for GEF7 includes: a simplified results framework of eleven core indicators and associated sub-indicators; agreed GEF7 targets across the core indicators; streamlined monitoring and reporting requirements; measures to enhance the availability, accessibility, quality and timeliness of data and information on results; and the capture of data on beneficiaries. Milestones under this indicator also include measures to increase the sustainability of GEF projects, including their financial sustainability. At the 57th Council, the GEF presented a paper entitled ‘Towards Greater Durability of GEF Investments’ (GEF/C.57/08). This outlined a series of proposals to increase the sustainability or ‘durability’ of projects. The proposals focussed on: the theory of change; multi-stakeholder processes; stakeholder involvement; and adaptive learning. Future work by the GEF Secretariat and GEF Agencies will consider: a greater integration of adaptive theories of change into both design and implementation; soliciting more targeted stakeholder engagements throughout the project cycle stages; strengthening country ownership through Country Support Programme; and an enhancement of knowledge sharing and learning throughout the GEF Partnership.

Enhanced engagement with the private sector The GEF7 replenishment agreed two pillars for implementation on the private sector: expanded use of blended (non-grant) finance instruments; and mobilising the private sector as an agent of market transformation, through the development of a private sector engagement strategy. At the 57th Council, after considering a draft GEF’s Private Sector Engagement Strategy, the Council requested the Secretariat to update the document based on the wide-ranging comments received. At the 58th Council Meeting June 2020, the Council did not approve the Strategy and requested the GEF Secretariat to prepare an Implementation Plan to be presented for consideration and approval by the Council at the 59th Council Meeting alongside a revised Private Sector Engagement Strategy. To support this work, the Council further requested that a Working Group of interested Council Members and the GEF Secretariat be created to support the development of both elements of the Strategy. While progress is slower than expected, there is increasing recognition of the importance of engaging the wide range of actors across the private sector to enable the transformation change needed on the environment.
[note] Document GEF/C.57/06

Operational efficiency and transparency. In March 2019, Policy Measures to Enhance Operational Efficiency, Accountability and Transparency came into effect. These included: a new provision to address timely project preparation; the speed of implementation and Agencies’ compliance with key reporting requirements; and the timing of financial closure (FC) of projects, to require closure within 12 months of submission of a Terminal Evaluation (TE). While the full effect of these measures will only be measurable in the coming months, the GEF Monitoring Report 2019 provided progress data on efficiency metrics, highlighting the percentage of projects reaching endorsement in FY19 within 8 months of Council approval of the Project Identification Form (PIF) and progress in financial closure of projects that have already reached their Terminal Evaluation.
[note] Monitoring Report 202019

Improved management of data and information. GEF became an IATI publisher in June 2019 with its first submission of project level data to the IATI registry. While the GEF’s new information management system – GEF portal – continues to go through improvements and data transfer, the Secretariat is working to implement systemise reporting to IATI registry on a regular basis.
[note] https://www.iatiregistry.org/dataset/gef-activities

Practical approaches to gender mainstreaming and capacity development. The Progress Report on the GEF Gender Equality Implementation Strategy was presented to the Council at the June 2020 meeting as an Information Note. It offered strong references to women’s participation in decision-making and leadership, as well as access to and control of natural resources. It also showed that the percentage of GEF programmes with a gender analysis is steadily increasing. This is good progress, but there is more that could be considered by GEF as flagged under recommendations.
[note] Progress Report on the Gender Equality Implementation Strategy.pdf

Across the 7 areas of policy there are areas where there is greater than expected progress (optimising use of GEF resources), and areas where progress isn’t as far as hoped (private sector). This represents balanced progress and given the nature of the different policy areas overall meeting expectations. In light of this, this output is scored as an A.

VfM of this output compared to the proposition in the Business Case, based on performance over the past year

The business case included consideration of ‘equity’ or how benefits are distributed amongst the population and emphasised that equity was particularly important in delivering DFID’s commitment to ‘leave no one behind’. GEF’s new “Policy on Gender Equality”, which requires gender analysis as part of project design, and improvements on monitoring and reporting in GEF financed projects, is an important commitment by GEF to leave no one behind. Indicator 2.7 of this output (articulated above) directly relates to that policy and demonstrates GEF’s continuing commitment to monitor and deliver against this aspect of equity.
[note] GEF Gender Equality Policy - 2017

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

The role of the private sector is critical in transforming markets and economic systems required to tackle the key drivers of environmental degradation, getting the support across the GEF Partnership, including Council members is a key part of this. GEF is making progress in their engagement. The formation of a working group, which the UK will play an active role, will help this progress.

Recommendations for the year ahead include:

- Engage in the working group being formed to develop the Private Sector Engagement Strategy and Implementation Plan.
- Continue to encourage consideration of greater upstream engagement in programme design, for example more proactive engagement with women’s rights organisations to help support GEF7 gender ambitions, with attention being paid to opportunities with the Impact Programmes.
- Monitor the impact of Covid-19 on safeguarding where the GEF Secretariat is in close communication with its Agencies regarding updates on GEF projects under implementation and continue adherence to GEF environmental and social safeguards.
- In the coming year discussions with the GEF Secretariat on gender should include the consideration of: promote ongoing gender analysis throughout the programme lifecycle; increase the percentage of programming that is gender-responsive; encourage increased engagement with, and leadership of, women’s rights organisations and other grassroots, rights-based actors (such as disabled people’s organisations); increase disaggregation of data by sex, age and disability; and report on the way in which gender intersects with other characteristics (disability, age, socio-economic status, religion, ethnicity, sexuality etc).

D: RISK

Overview of risk management

The overall risk category of ‘minor’ has been maintained in the last year, in light of the due diligence and the new Enhanced Due Diligence on Safeguarding, both completed in January 2020. These indicated that the controls in effect were sufficient to monitor and respond to GEF risks as needed. These controls apply to all GEF’s implementing agencies, including: Minimum Fiduciary Standards for GEF Implementing and Executing Agencies and Minimum Fiduciary Standards on Issues Related to Anti-Money Laundering and Combating the Financing of Terrorism, and; an updated Policy on Environmental and Social Safeguards.

Previous annual Reviews have indicated that the GEF would also benefit from an over-arching internal risk framework, which would allow mutual understanding of the status of various operational or strategic risks across the GEF’s network, as well as of the risk tolerance levels within the GEF. This was pursued as part of the 2020 Due Diligence update and bilateral discussions in March 2020. The GEF Secretariat acknowledges the benefit of an overarching policy. This will contribute towards the GEF’s risk management capabilities and is therefore one of the UK’s priorities to pursue in GEF 7 for implementation in GEF 8.

The risk register for GEF has been maintained since the Business Case risk assessment and aligned with the new DFID risk management framework. Two of the components assessed over the year exceeded the risk appetite and mitigation actions have been taken.

- The risk from the lack of an overall/portfolio wide risk framework. The UK is engaging the GEF Secretariat directly and raising in GEF Council meetings to ensure this is implemented in GEF 8.
- The risk from reporting on cases of non-compliance. The risk identified potentially insufficient processes in place for tracking, responding, and alerting GEF governance to cases of non-compliance (fraud, safeguard etc), limiting HMG's ability to react in a timely fashion. The GEF Secretariat working with the UK and other Council members has approved and is implementing a real-time reporting mechanism.

Covid-19 and Risk Management
The GEF Secretariat has developed a short, medium and long-term response to the risk posed to the GEF portfolio from Covid-19 which in brief include:

Immediate: Focussing GEF’s efforts to deal with the wildlife trade and consumption challenges. Through the GEF Global Wildlife Programme, the largest global effort to tackle wildlife trafficking, GEF are looking at potential additional projects as vehicles for public awareness and behavioural change, and how this platform can be used to support developing countries’ ecological response to the pandemic.

Through a specially created task force of expert and like-minded institutions, the GEF is conducting expert analyses on the future risks linked to emerging infectious diseases along with their root causes, including their connection with deforestation and ecosystem fragmentation. The reference group is also supporting the development of a ‘white paper’ identifying future risks linked to emerging infectious diseases and other issues linking human welfare to environmental degradation such as deforestation and habitat fragmentation.

The GEF Secretariat are identify risks to projects and programmes that may seriously compromise past gains and future outcomes. GEF Agencies are undertaking a broader in-depth risk assessment of their GEF-financed portfolios.

Medium term:	The GEF Secretariat are developing an internal draft blueprint on how to deploy ongoing and upcoming GEF-7 projects that can help lay the foundation for a sustainable post-Covid-19 recovery.

Long-term: At the end of 2020, GEF will start strategic discussions ahead of the next GEF replenishment. Under previous GEF replenishments, GEF has increasingly focussed on the transformational change to systems needed to address the tensions between human and natural ecosystems. These discussions will take account of the origins and consequences of the Covid-19 pandemic as a key part of the domestic and international greener-recovery efforts.

Safeguarding: As per the December 2109 GEF Policy on Environmental and Social safeguards, the GEF continues to rely on its Agencies Environmental and Social Safeguards policies and procedures to supervise, monitor and report the implementation of Environmental and Social Safeguards management plans or equivalents. GEF Secretariat is in close communication with its Agencies regarding updates on GEF projects under implementation and continue adherence to GEF environmental and social safeguards.
[note] Assessment Agencies Compliance.pdf

E: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

The UK has been a member and major contributor to GEF since its inception in 1991. The UK is a permanent member of the GEF Council, which functions as an independent board of directors, with primary responsibility for commissioning, approving, and evaluating GEF programmes. The UK has influence over policy priorities and level of ambition, through the replenishment process, and in driving monitoring operational effectiveness and efficiency through the Council. The experience of the UK team has enabled effective development and promotion of innovation and improvements in implementation, as indicated by the proportion of UK policy proposals adopted and the increases in resource allocation to UK priorities (e.g. Illegal Wildlife Trade – (IWT) and nature-based solutions to climate change) to GEF7.

Defra’s increased engagement in GEF7 enhances the quality and breadth of UK inputs into governing GEF. The UK and the GEF Secretariat continue to have a productive working relationship.

VfM performance compared to the original VfM proposition in the business case

Since inception to March 31, 2020 funding approvals made by the Council and CEO total $20,292m, of which 89% was approved for Projects and Project Preparation activities, 7% for Agency Fees and 4% for Administrative budgets. From the inception of UK support for the GEF, there have been continual efforts by the UK to ensure that there is scrutiny and downward pressure on the fees charged by the implementing agencies. In 2012 the GEF Council approved a new fee policy for GEF agencies, which established a reduced fee for all agencies of 9.5% for project grants up to $10 million, and 9% for project grants above $10 million.
[note] Trust Fund Financial Report 20March 2020

The Secretariat’s budget for FY20 expenses are projected at $21.743m, or 7.6% less than the approved FY20 budget, principally due to the impacts of COVID-19.
[note] The projection of FY20 actual expenditures include data for actual spending through March 30, 2020, and a projected spending during the remaining weeks of the fiscal year, which ends on June 30, 2019
[note] Business Plan and Corporate Budget for FY21

Each year GEF’s Independent Evaluation Office prepares an annual performance report on the performance of completed projects i.e. projects from previous replenishments from inception through to GEF6. This provides a thorough assessment of the improvement (or otherwise) of projects funded through GEF. The headline findings include:

- In comparison to the rating of all projects considered since inception, where 80 percent of projects were rating as satisfactory for their outcomes, in the most set of projects considered 83 percent were rated in the satisfactory range.
- In terms of sustainability (or ‘durability’) Seventy-one percent of the projects in the most recent set of projects assessed are in the likely range for sustainability compared with 62 percent for the cumulative portfolio. This is consistent with the long-term trend of a modest improvement in sustainability ratings for the projects that have been designed from GEF-4 onwards.
  [note] APR_2020.pdf
- In terms of quality of implementation, which assesses the performance of GEF Agencies, 85 percent of the most recent projects assessed were rated in the satisfactory range in comparison to 81 percent for the cumulative portfolio.
- In terms of quality of project execution, which assesses the performance of agencies which execute the GEF supported activities on the ground under the supervision of the GEF Agency, 89 percent of the most recent projects were rated in the satisfactory range in comparison to 81 percent historically.
- In terms of M&E design 71 percent of the projects in the most recent assessment were rated as satisfactory in comparison to 66 percent cumulatively. And 64 percent of the projects in the most recent set of projects were rated as satisfactory for M&E implementation in comparison to 65 percent cumulatively.

Given the most recent assessment from the Independent Evaluation Office, where for all but a slight drop for M&E implementation, there is continuing upward trajectory in value-for-money terms. As such we conclude the programme continues to represent value for money

Quality of financial management
The World Bank as Trustee reports on GEF expenditure and resource availability at the biannual GEF Council meetings. The most recent Financial Report was presented to the GEF Council in June 2020, and highlighted the shortfall being faced by the GEF’s seventh replenishment due to unexpected exchange rate fluctuations. The GEF most recently filed an Independent Auditors’ Report and Statement of Receipts, Disbursements and Fund Balance in October 2019, in which the auditors did not provide any qualifications to their opinion. The independent audit of the GEF Trust Fund by the World Bank’s external auditors have been concluded for the period ended June 30, 2019 and is to be issued in October/November 2020.

Date of last narrative financial report	June 2020	Date of last audited annual statement	October 2019