Project Completion Review - Top Sheet

This Top Sheet captures the headlines on the programmes performance over the course of its lifetime. Teams should attach summary sheets from each annual review over the life of the programme.

Review Date:	28/11/2016

Title: Support to Stabilisation in North East Nigeria / Financial contribution to the US Office for Transition Initiatives (US OTI) North East Regional Initiative (NERI) programme implemented by Creative Associates International (CAI). CSSF funded on DFID platform.
Programme Code: 204910	Start Date / October 2014	End Date: / March 2016
If programme was closed >1 month early please describe in a few words why.

Summary of Programme Performance

Year	2015	2016
Programme Score	No review. Programme under £1m	Reviewed as part of CSSF Annual Review of the Nigeria Conflict Management and Stabilisation Programme (NCMSP). The Support to Stabilisation in North East Nigeria component was one of three components under Output 2. Outputs were not scored. The CSSF Annual review gave a B marking to the overall CSSF programme.
Risk Rating	High (Severe)	Severe

Financial Position

Original Programme Value	£500,000 (Oct. 2014)
Extensions/ amendments	£500,000 (April 2015)
Log-frame revisions (with dates)	CSSF Results Framework reviewed in March 2015
Total programme spend	£ 1,000,000

Follow up actions required following closure

No specific follow up action required.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	5644244
DevTracker Link to Log frame:	5644244

Outline of programme and what it has achieved

The Nigeria Conflict Management and Stabilisation Programme aimed to support peacebuilding and stabilisation in the Niger Delta and the North East. The programme, funded by the Conflict Stability and Security Fund (CSSF) and implemented by DFID had seven components. This Project Completion Review covers the component labelled (in Aries and on AMP) Support to Stabilisation in North East Nigeria. It consisted of a financial contribution to the US Office of Transition Initiatives’ North East Regional Initiative (NERI), implemented by Creative Associates International. The NERI programme had a potential budget of up to $12 million provided by US OTI. UK contribution to this programme was for an initial additional £500,000 in 2014 and a £500,000 uplift in 2015.

The security situation had degraded drastically in North East Nigeria, with the intensification of Boko Haram (BH) insurgency in the North in 2014. In 2015, the country had its first successful democratic transition of power from one party to another, but continued to struggle with insecurity caused by Boko Haram. An escalated military offensive by Nigerian and regional security forces has allowed the Government to reclaim areas previously held by BH, thus providing an opportunity for the government and the international community to provide greater support to the population and start rehabilitation work. However, the insurgency is far from over as Boko Haram has responded by increasing asymmetric attacks in Nigeria and its neighbours in the greater Lake Chad Basin. While public support for Boko Haram is on the decline, a recent nationwide US military African command (AFRICOM) survey showed that one in four people in the Northeast still hold pro-extremist or very pro-extremist views, making the region ripe for the rise of a more ideologically aligned group, like the Barnawi-led faction that is more connected to the global jihadist movement.

The UK aims in Nigeria is to support a more stable, better governed and more prosperous Nigeria that would enhance stability and development in the region. Stability in the North East is a top priority for the UK National Security Strategy. The UK military is supporting an effective Nigerian and regional military response to Boko Haram, while DFID implements conflict management and stabilisation efforts in the North East with CSSF funding, to complement DFID’s development programme and FCO’s political engagement.

DFID had only one major peacebuilding programme implemented in the North East in 2014. DFID therefore decided to diversify its engagement and to contribute funding to a new US OTI programme, which provided a greater focus on countering violent extremism. This mechanism was aiming to reach groups that existing DFID programme could not reach. It was also for the UK an opportunity to work more closely with the US.

OTI was responding to the window of opportunity created by the advances of the Nigerian military to assist in the return of public administration in formerly occupied areas, to counter the violent extremist ideology promoted by Boko Haram, and to address the underlying causes of recruitment. To effectively defeat Boko Haram, military operations must be coupled with efforts to address the underlying drivers of violent extremism in Northeast Nigeria. Through a flexible and adaptive programme, supporting a variety of small-scale projects, the OTI programme seeks to address the drivers of conflict by reducing perceptions of marginalisation, challenging extremist narratives, and providing support for rehabilitation.

The US OTI highlights of the programme include:

Launching the first-ever shortwave radio programme in Kanuri (the primary local language spoken in Northeast Nigeria), with a potential audience of 10 million in the greater Lake Chad Basin. Evaluations show that the programme has a broad and loyal listenership, is building a sense of community and voice, and that regular listeners are more likely to hold the view that their community is willing to stand up to extremism.

Building a sense of purpose, belonging and respect among vulnerable youth by engaging them in productive activities like technical training, sports, peace campaigns and theatre.

Stimulating government presence in areas that have long felt abandoned by partnering with state and local officials to deliver critical public services, sponsor events around public holidays, and renovate public infrastructure in areas previously held by Boko Haram.

Building capacity of local civil society organisations through mentorship support, establishing a dedicated resource and training centre for Civil Society Organisations, and strengthening finance and administrative systems of selected local partners.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Overall Outcome Assessment

According to OTI, initial feedback from beneficiaries and government partners on their community-level activities have been positive and indicates that the OTI programme is working in the right direction when it comes to addressing the identified drivers of violent extremism in Northeast Nigeria. No specific evaluation on community-level activities was shared with DFID. However, the results of the radio programme Dandal Kura cluster evaluation are certainly corroborating this affirmation and this evaluation is attached to the PCR.

Output Score and Description

Output score: A
Outputs met expectation. Out of 6 indicators, 5 achieved or over-achieved their target while 1 was marginally under.

Initially, OTI struggled to implement the programme mainly due to challenges of access and lack of credible local partners. Some funding was redirected to build the capacity of local CSOs and NGOs, refocusing on establishing Civil Society Training Centres in Yobe and Adamawa (to include CSOs from Borno). Funding has resourced these centres and the development of a capacity building programme in budgeting, finance, drafting, programme management and M&E. Each centre is expected to train at least 30 CSOs per year.

In parallel, OTI supported the successful set up of the first Kanuri language radio station (Dandal Kura). UK funding has provided technical and marketing expertise to aid Dandal Kura’s expansion in the North East as well as the donation of solar panels and equipment to provide power stability to the station infrastructure, and Dandal Kura’s local partner, the Borno Radio Television Company. OTI is also implementing a variety of small peacebuilding and Countering Violent Extremism initiatives.

Despite difficulties in implementing the programme due to access and capacity issues, UK funding was used in a flexible manner and full spend was achieved by the end of the programme.

However, we did not receive from OTI the desired level of control and reporting necessary for DFID requirements. US OTI has well established financial and management oversight but has not been proactive in sharing reports. Quarterly reports produced by DFID for the CSSF were compiled after obtaining oral updates from US OTI.

Lessons and how these have been shared

- Collaboration with US OTI did not provide DFID with the minimum oversight required. This should be taken into consideration for any new contractual agreement with US OTI.
- The UK now has the platform and access from which to implement more directly in the Northeast, rather than through another donor. This should be the preferred avenue for future CSSF funded conflict engagement in the North East;
- Positive engagements with select individuals in state governments ensured government ownership and support of activities;
- Youth-focused activities have achieved credible success and could remain a key priority in Yobe, where youth literacy levels and unemployment are big challenges;
- The Dandal Kura radio station reaches a large audience and make a very positive impact, although women are a distinct group for further focus;
- Timely stakeholder engagement ensures initiatives respond to a demand.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Economic and social alternatives combined with radio messaging reduce number of youth engaged in political violence and violent extremism
Output number per LF			Output Score	A
Risk:		Severe	Impact weighting (%):	100%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Develop and produce original radio programming in Hausa and Kanuri languages	7 hours per week	30 hours per week
# of listeners	20% listen regularly in Maiduguri	42% tune in daily in Maiduguri
# of listeners who report impact of radio programming	70% listeners report positive impact	95% of listeners have positive view of radio programme / 80% listeners said programme gives them hope in the midst of a crisis / Building community: / 94% say it builds a better sense of community for Kanuri people / 89% say it provides a platform for Kanuri speakers to air their concerns and grievances
# of youth reached by activities (youth clubs, sports tournaments, conflict mitigation training)	12 activities reaching 300 youth	500 youth reached
# of activities (training youth in Maiduguri in seedling production, modern irrigation, agricultural courses)	10	8 agricultural cooperatives supported to expend production and create jobs
# of CSOs with increased capacity 50	50	50

A result framework was agreed with OTI. This was to inform programming but remained open to changes. The indicator on CSOs capacity building was added in September 2015 to reflect adaptation of the programme to the context.

The goal of the OTI programme is to minimise the conditions that allow extremism to flourish in Northeast Nigeria. Through small-scale, strategically targeted assistance to local partners, OTI supports the following objectives through clusters of programme activities:

•	Reducing perceptions of marginalisation; and
•	Challenging extremist ideas and narratives.

OTI attributed 25 activities to the DFID-funded project in support of both of these programme objectives.

Achievements include:

•	Building a stronger sense of Kanuri community

DFID funds supported content production and broadcasting of the first-ever shortwave radio programme in Kanuri (the primary local language spoken in the areas most affected by Boko Haram) as well as the station’s move to Maiduguri. Evaluations show that Dandal Kura (“meeting place” in Kanuri) has a broad and loyal listenership, is building a sense of community, belonging and voice among a historically marginalised group, and that regular listeners are more likely to hold the view that their community is willing to stand up to extremism. The evaluation attached to this PCR shows that this initiative is a real success and has good impact.

•	Improving government responsiveness

DFID funds contributed to stimulating government presence in areas that have long felt abandoned by the state by supporting officials to rebuild agricultural livelihoods in Biu and Hawul LGAs, Borno state. Eight agricultural cooperatives have either doubled or tripled the size of their farmlands and are looking forward to record harvests as a result of ongoing mentoring from Extension Agents (DFID-funded), as well as tractors and farm tools (USAID-funded), all provided in the name of the Borno State Government (BOSG).

•	Engaging Vulnerable Youth

DFID funds contributed to countering the sense of disconnection and disenfranchisement felt by youth in Damaturu, Yobe state by engaging more than 500 young people in productive activities like technical training, sports tournaments and peace clubs that have exposed them to new ideas, built relationships with peers from diverse backgrounds, and offered opportunities that build self-esteem and respect from other community members.

•	Increasing civil society capacity in the Northeast

DFID funds have increased the capacity of more than 50 civil society organisations in the Northeast in areas such as proposal development, organisational management, M&E and financial management through the establishment of CSO resource centres in Adamawa and Yobe states. These activities are very important, since the dearth of well-organised and developed civil society organisations is a major hindrance to successful programming by large donors – especially USAID, DFID, World Bank and the UN. Having a group of well-established and trained organisations to assist in the implementation of foreign assistance help solve the conflict in the north is essential.

Summary of responses to issues raised in previous annual reviews (where relevant)
N/A

Recommendations for future programmes

See Lessons Learned.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Assessment of whether the programme represented value for money

This is a CSSF funded programme. No business case was submitted for these funds. It is challenging to assess VfM in the absence of indicators and benchmarks on VfM. Contribution to an established US programme represented good VfM for the UK as this “add on” provides better efficiency with a high proportion of funds spent on activity rather than programme management – the cost of core staff for activity delivered with DFID funds was covered by US OTI. The programme spent its full allocation in the agreed timeframe.

US OTI considers that the programme generally performed well in terms of value for money. DFID has not had access to relevant information to corroborate this assessment.

Nigeria experienced currency devaluation, inflation, and rising fuel prices which affected activity budgets as goods and services, as well as transport costs became more expensive.

Quality of financial management during programme

Creative Associates maintained regular communication with OTI about the budget challenges identified above and activity cost modifications were generally submitted on time and were generally reasonable. Creative also took several steps to improve the quality of activity budgets, including hiring a staff engineer and undertaking the procurement process in advance of activity clearance.

Date of last narrative financial report	Quarterly reports produced for CSSF. / Annual Report July 2016
Date of last audited annual statement	USAID is responsible for auditing the programme.

E: RISK (½ page)

Quality of risk management over the life of the programme

Security concerns remained the main challenge for a programme operating in the North East conflict zone. This has affecting delivery with working days lost and events having to be rescheduled due to security reasons. Access to many areas remains challenging or too dangerous.

The programme undoubtedly over-estimated the capacity of local organisations to implement activities. This ended up being the major unforeseen risk for the programme, delaying substantially implementation and leading to a shift towards capacity building for local organisations, which was not envisaged initially.

The quality of financial risk management appears generally good over the life of the programme. The vast majority of support is in-kind, limiting the use and proliferation of cash. The programme also took a deliberate approach to mitigating the risk of giving material support to Proscribed Terrorist Organisations and their members.

F: COMMERCIAL CONSIDERATIONS (½ page)

US OTI awarded a contract to creative Associates International to implement their Northeast Regional Initiative in Nigeria. The Creative Associates field team is led by a Chief of Party who reports directly to the US OTI Country Representative in Abuja. Regular meeting between DFID and US OTI took place to report on activities linked with UK funding but no regular narrative or financial reports where provided to DFID.

Delivery against planned timeframe

There were challenges associated with adhering to the planned timeframe during the initial months of the programme. The programme encountered delays and many envisaged activities could not be implemented as local organisations were not equipped to deliver. This has not substantially affected the UK contribution, which represents only a small portion of the overall OTI programme. Significant steps were taken at a later stage to address these impediments with positive results.

Performance of partnership (s)

Working with US OTI was considered an opportunity to strengthen programming links between the US and the UK. In practice, limited change has happened due to the OTI programme. The level of consultation and coordination between the US and the UK in Nigeria is good and regular coordination meetings are taking place, regularly including other donors. However, no specific exchange, consultation, or planning were linked to the UK funding of an US programme.

Providing a financial contribution to a programme implemented by another donor hampered the ability to monitor proper implementation of projects funded by DFID. The only project that the UK managed to visit a couple of times was the Dandal Kura radio programme in Maiduguri.

The US OTI programme was part of the CSSF funded Nigeria Conflict Management and Stabilisation Programme supervised by DFID in collaboration with the UK Defence team and the British High Commission Political section. The programme reported to the CSSF Nigeria Working Group and Local Strategy Group, which provides the overall oversight.

Asset disposal and value obtained by DFID

No asset purchased with UK funding.

Transmission equipment procured by DFID for the Nigeria Stability and Reconciliation Programme and unused were gifted to the Dandal Kura radio programme. This was a good use of the radio equipment purchased by NSRP and which couldn’t be used as originally planned.

G: CONDITIONALITY (½ page)

Partnership principles assessment

DFID Nigeria’s assessment is that the government of Nigeria currently does not demonstrate a credible and consistent commitment to any of the four partnership principles. Recent changes in political leadership have not yet generated major performance improvement across the four principles:
-	The government is not meeting its responsibility to poverty reduction and the MDGs.
-	There has been only marginal improvement in the government’s record on human rights. Use of excessive force by the police and military is commonplace. Although the Government is more reactive to reports of human rights abuse against the security forces, this has not yet led to systemic changes.
-	Corruption is widespread. The new government was elected on a platform which includes strong commitment to tackling corruption and is prosecuting various cases. Although changes will take time.
-	There has been limited progress in strengthening domestic accountability.

While a direct partnership with the government of Nigeria cannot be justified in a financial sense, DFID has to work through international and local implementers. Nevertheless, the OTI programme has also in its objective to support local government institutions as an important actor in addressing the root causes of conflict in Nigeria and in rehabilitating the devastated North East.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

OTI carries out a cluster evaluation once a critical mass of activities intentionally grouped around a common intended result has been achieved. During this programme period, the Dandal Kura cluster of activities was evaluated. As mentioned in Section A, the evaluation found that Dandal Kura has a broad and loyal listenership, is building a sense of community, belonging and voice among a historically marginalised group, and that regular listeners are more likely to hold the view that their community is willing to stand up to extremism. The Cluster Evaluation of Dandal Kura is attached to this PCR.

The OTI programme plans to commission a quantitative survey to evaluate its Government Responsiveness cluster shortly.

Monitoring progress throughout the programme

Like all OTI programmes, the Nigeria programme utilised three levels of analysis in its M&E system through this programme period. At the activity level, the emphasis of the M&E system is on measuring outputs and immediate outcomes of those activities. At the programme level, the focus is on measuring higher-level effects, utilising clusters to aggregate the effects of individual activities with similar intended results. At the strategic level, the goal is to measure changes in the operating context to ensure the programme remains relevant to and focused on the key drivers of violent extremism in Nigeria.

Activity monitoring included awardee reporting, programme staff monitoring, an activity hotline, and project implementation committees. Following the completion of each activity, programme staff prepared a final evaluation report that calculates actual beneficiaries; actual output, outcome indicator data; and a summary of achievements and/or problems as well as lessons learned. This ensured that the programme quickly learned from its activities and incorporated lessons learned into future efforts.

No monitoring reports were shared with DFID.
Smart Guide
The Programme Completion Review is the opportunity to reflect on the entire programme, its performance, achievements, lessons and how learning will be shared to inform future programming.

The Programme Completion Report assesses and rates outputs using the following rating scale. The Aid Management Platform (AMP) and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with headline information on the programme and any follow up actions / Early closure is likely to be summed up by issues such as ‘poor performance by partners’ and/or ‘major changes in operating environment’
A: Introduction and Context
Briefly outline the programme, results achieved and contribution to the overall Operational Plan and DFID’s international development objectives. Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Outcome Assessment / Brief assessment of whether the programme achieved the Outcome
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Output Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on AMP as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Minor/Moderate/Major/Severe / Enter: Minor, Moderate, Major or Severe / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on AMP as part of loading the Annual Review for approval). / Where the Risk for this Output has been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section E Risk
Key points
Summary of response to issues raised in previous annual reviews (where relevant)
Recommendations for future programmes
Repeat above for each Output.
D: Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case. Performance against vfm measures and any trigger points that were identified to track through the programme / If programme was closed >1 month early please describe in a few words why, what savings were made, as well as what money was spent.
Assessment of whether the programme represented value for money? / Overall view on whether the programme was good value for money
Quality of Financial Management during programme / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E: Risk
Quality of risk management over the life of the programme. / How were risks managed, the degree to which they were realised and/or mitigated? / Did any risks materialised through the duration of the programme which were not foreseen? What where they and how was this managed? / What lessons have been learned?
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / Could DFID be a more effective partner
Asset disposal and value obtained by DFID / How were assets managed throughout the programme? How have they been (or will they be) disposed to get maximum value?
G: Conditionality
Partnership principles assessment / For programmes where we have decided to use the PPs for management and monitoring, PCRs should generally include an assessment of commitment to the PPs, including any concerns that have occurred over the year, the partner government’s response, and details of any response by us. Teams should refer to the DFID guidance on reviewing projects.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the programme / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review and PCR process