Business Case
# Summary Sheet

Title: / Kenya Extractives Programme (K-EXPRO)
Project Purpose: / A growing extractives sector leading to equitable, inclusive and sustainable benefits to Kenyan citizens, reducing negative impacts and risks
Programme Value: up to £24m		Country/ Region: / Eastern Africa - Kenya
Project Code: 204339	Start Date: / 01/07/15	End Date: / 31/12/2019
Overall programme risk rating:	High
Quest Number: 5653770

# Intervention Summary
#### What support will the UK provide?
The UK will contribute up to £24m between 2015-2019 for the Kenya Extractives Programme (K-EXPRO), with the scope to extend if performance is good. This programme is crucial to support Kenya’s exit from aid in the next decade. It proposes support to the generation of a tax base that can pay for services, jobs in new industries, export earnings from new products, and reductions in both the likelihood of community conflict and adverse environmental impacts. It proposes a mix of high level technical advice, support to reap local benefits through community engagement, help for new devolved local government to make the most of these new extractive sectors; and for Kenya to extract its resources transparently. Some estimates put the combined potential contribution of extractives developments in excess of 10% of Gross Domestic Product (GDP)[1], which would be equivalent to more than double the full forecast economic rate of GDP growth for e.g. 2016/2017[2]; so a significant contribution is possible if the ‘Norwegian’ rather than the ‘Nigerian’ model prevails. The World Bank estimates the investment for petroleum/gas related projects in Kenya at between USD 15 and 18 billion in over less than a decade[3]. This programme will support revenues and foreign direct investment from the extractive sectors to be used for the economic development of Kenyans in an inclusive and sustainable way, and ensure that the associated risks, including on corruption and the environment, are mitigated.
[1] These estimates depend heavily on the global oil price that is taken for reference. To note that “combined contribution of new extractives developments” include oil and gas as well as mining, and it also pulls together fiscal revenue (to public sector) and the share of foreign direct investment captured by Kenyan private sector.
[2] World Bank Economic Update March 2015
[3] “Towards a Petroleum Sector Master Plan for Kenya”, PwC for the World Bank (supported by DFID Kenya), June 2015. Downloadable from http://www.pwc.com/ke/petroleum-master-plan – supported by DFID Kenya –
#### What are the main programme activities?
This programme looks comprehensively at emerging petroleum and mining industries in Kenya and provides four main forms of support.
- Firstly, for better governance, technical assistance is provided to build institutional capacity within national and county level government institutions, with transparency, accountability and protection of the environment and adaptation to climate change as priorities.
- Secondly, support is provided to organisations or coalitions at national level to strengthen transparency and social accountability and to private sector associations to advocate for a better business environment in extractive sectors.
- Thirdly, the programme supports county level dialogue and local development discussions, including with women and youth. This will begin with a pilot in Turkana County, the main location of recent oil finds, but also one of the poorest and conflict prone counties in Kenya.
- Finally, working closely with the existing DFID initiative Skills for Oil and Gas Africa (SOGA), the programme supports a pragmatic approach to “local content”[4], by focusing on the capacity of the domestic private sector to capture foreign direct investment related to extractives and so to generate jobs for poor Kenyans, and wherever possible, jobs for women.
  [4] The share of inputs in the production process (jobs, materials, equipment, capital) that come from local sources rather than being imported, i.e. the share of the investment that boosts local economic development
A fifth component is added to the four above to provide regular updates on stakeholders involved in these industries where political and economic sensitivities are so high. This is limited in budget but will provide insights to adapt the programme and our engagement to respond to change, maximise results and reduce adverse effects, including risk of corruption and reputational risk.
Across petroleum and mining, the extractives sector works to longer than five year investment cycles; a case in point is Uganda, which discovered oil in commercial quantities in the Albertine Graben region in 2006 and still has not begun commercial operations. Therefore, it is likely that over a decade of DFID support will be required, to provide interventions that adapt to a changing context as the extractives sector develops and to deliver economic benefits. Depending on progress and performance the initial programme may therefore lead to later scale up and to spin off programmes of support for private sector development, community development, and institutional strengthening.
#### Why is UK support required?
Given the context of low oil prices, a predatory business environment, limited governance systems and potential for conflict in resource-rich areas, extractive industries may not mature with significant investment beyond the current exploration of the oil fields in Turkana by Tullow Oil/Africa Oil, Base Titanium’s mineral sands operation in Kwale and some substandard artisanal mining.
The recent oil price fall offers both challenges and opportunities. Whilst anticipated revenue flows may be delayed, this opens up an opportunity to better prepare to maximise investment impact. Countries have more time to build capacity to manage resources in a transparent and sustainable manner and to prepare manufacturing sectors and skills. The fluctuation in global commodities prices, and pressure on oil price, means that extractives and particularly oil and gas companies are attuned to political risk and investment climate challenges, especially those arising from bad governance and from strained relations between international investors and local communities. Those countries which make the right reforms will set themselves apart.
Support is therefore required to build capacity in government, enhance the business environment for the extractives sector, facilitate the development of dialogue platforms in extractive regions in Kenya and make sure that adverse impacts on communities and environment are reduced to the minimum. These are all outcomes that DFID can deliver on, given its current interim engagement in Kenya and its proven experience on comparable projects in Sub Saharan Africa, such as the Facility for Oil Sector Transparency (FOSTER) programme in Nigeria and the more recent Ghana Oil and Gas for Inclusive Growth programme. A high level of complementarity with DFID global and regional extractive programmes will add value.
There are UK commercial interests in both the petroleum and mining sectors in Kenya. To maintain the trust of the Ministry of Mining (MoM) and Ministry of Energy and Petroleum (MoEP) we will always position support as independent, sharing our experience across companies. This is also part of the ‘UK Companies as Champions for Development’ initiative in Kenya where we encourage companies to lead in showcasing ethical standards and maximising jobs for Kenyans.
#### What are the expected results?
The impact this programme contributes to is reducing poverty in Kenya through its contribution to inclusive and sustainable economic development in the extractives sector, with reduced risks of negative social, political and environmental impacts.
The outcome this programme aims to achieve is better governance and business environment, localised development and inclusive approach to human resources and domestic service provision (“local content”) in the extractive sectors in Kenya.
#### How does the project fit with the department’s strategic objectives?
This programme contributes to DFID Kenya’s Operational Plan and towards DFID’s ‘work in natural resource-rich developing countries, especially in Africa, to ensure that the benefits of natural resources (oil, gas and mining) are used to improve the lives of the poor’. It will also respond directly to Africa Regional Department’s Operational Plan that states that ‘to reduce poverty Africa needs to create jobs through private investment’, and to the objectives laid out in the Secretary of State’s extractives roundtable in which representatives from major international oil and mining companies, in particular through promoting local content in conjunction with the centrally-funded Skills for Oil and Gas Africa (SOGA) programme.
#### What are the key risks to the success of the programme?
Given the track record of corruption and environmental impact associated with extractives globally, the most critical risk is that DFID is associated with any future corruption allegations or with environmental damage. Given the sensitivities of extractives operations, there is also the risk that the programme is implemented in the context of conflict, whether violent conflict in the field, or political economy tensions within national government and between national and county levels, or within local governments themselves. The programme may be perceived negatively or cynically by some stakeholders to be a soft power front for British commercial interests. There is a further risk that there will be a lack of coordination from the Government of Kenya in terms of support initiatives, both government and donor-driven. This may result in weakened or misaligned political will, unnecessary duplication and gaps in support and failure to manage expectations of key stakeholders. Given the current lack of capacity in the extractives line ministries and concerned institutions, there may also be a lack of counterparts for embedded technical assistance and capacity building. Finally, the quality of technical assistance support has a high impact on the entire sector; there is therefore a disproportionate risk associated with low quality, unevenly delivered or late delivery of technical assistance.
The programme adopts a strategy of proactive monitoring and mitigation of these risks. DFID’s policy on fraud, bribery and corruption is one of zero tolerance. We ensure that robust due diligence is followed and only use credible counterparts and service providers for the delivery of individual projects that will have withstood assessments covering governance and control, ability to deliver, and financial stability. All agreements specify DFID’s requirement and timelines for reporting fraud or corruption, or any suspicions thereof. A regular update will be undertaken of stakeholder interests and political economy to mitigate adverse effects, including risks of corruption and reputational risk. DFID will seek to ensure Kenyan legislation, regulation, and procedures embed transparency and accountability measures, particularly around extractives, but also in related business sectors. Examples where we have had some success to date include the inclusion in the Mining Bill of the measures that would enable Kenya to become an Extractive Industries Transparency Initiative (EITI) compliant country, and a fully online Mining Cadastre system, that reduces significantly the need for one-to-one contacts between mining licensees and public servants. We will also continue to engage with business transparently.
The programme proactively tackles low institutional capacity and governance systems, especially to improve transparency, accountability and protection of the environment. A dedicated component will work with devolved local government at county level, to improve community dialogue with institutions and investors, set up systems for inclusive planning - and grievance mechanisms, so ultimately reducing local drivers of conflict. Technical assistance is delivered through pre-qualified DFID framework providers, UK Government organisations, multilateral agencies, or non-governmental organisations that have a proven and substantial track record in delivering DFID programmes.
The programme must be viewed as a high risk but offering a high reward.
# Table of Contents

# List of Abbreviations

AfDB	African Development Bank
ALSF	Africa Legal Support Facility
ARD	Africa Regional Department
ART	Accountability and Results Team
BG	British Gas
BGS	British Geological Society
BMZ	Federal Ministry for Economic Cooperation and Development
CEPSA	Compañía Española de Petróleos, S.A.U.
CNOOC	China National Offshore Oil Corporation
DFAT	Department of Foreign Affairs and Trade
DFID	Department for International Development
EARH	East Africa Research Hub
EITI	Extractive Industries Transparency Initiative
EU	European Union
FCO	Foreign & Commonwealth Office
FDI	Foreign Direct Investment
FOSTER	Facility for Oil Sector Transparency
GDP	Gross Domestic Product
GIZ	Deutsche Gesellschaft für Internationale Zusammenarbeit GmbH
GoK	Government of Kenya
HMG	Her Majesty’s Government
ICES	Information Centre for the Extractives Sector
ICF	International Climate Fund
IFUSE	Investment Facility for Utilising UK Specialist Expertise
ILO	International Labour Organization
IOC	International Oil Company
IMF	International Monetary Fund
KCSPOG	Kenya Civil Society Platform on Oil and Gas
KEIDP	Kenya Extractive Industries Development Programme
K-EXPRO	Kenya Extractives Programme
K-MAP	Kenya Market Assistance Programme
KEPSA	Kenya Private Sector Alliance
KEPTAP	Kenya Petroleum Technical Assistance Project
KOGA	Kenya Oil and Gas Association
LAPSSET	Lamu Port and South Sudan Ethiopia Transport
MA	Managing Agent
MAR	Multilateral Aid Review
M&E	Monitoring and Evaluation
MoEP	Ministry of Energy and Petroleum
MoEWNR	Ministry of Environment, Water and Natural Resources
MoIED	Ministry of Industrialisation and Enterprise Development
MoM	Ministry of Mining
NEMA	National Environmental Management Authority
O&G	Oil and Gas
PCD	Procurement and Commercial Department
PQQ	Pre-qualification Questionnaire
PSA	Production Sharing Agreement
RTPEED	Releasing the Transformational Potential of Extractives for Economic Development
SOGA	Skills for Oil and Gas Africa
SRO	Senior Responsible Owner
TA	Technical Assistance
TVET	Technical Vocational Education and Training
UK	United Kingdom
UNDP	United Nations Development Programme
UNEP	United Nations Environment Programme
UNIDO	United Nations Industrial Development Organization
USAID	United States Agency for International Development
VfM	Value for Money
WBG	World Bank Group
# Strategic Case
## The Petroleum Sector
In terms of the quest for “first oil”, Tullow Oil (UK), with their 50% partner Africa Oil Corp (Canada), continue exploration and testing activities around the 2012 discoveries in Turkana County[5]. The reserves have been confirmed to be of quantity and quality that would make export of crude commercially viable[6]. Further exploration is ongoing, to determine the shape, quality and size of the reservoirs and to test other exploration blocks in the same region. Field development was expected to commence in 2015, and actual extraction perhaps three or four years later, but it might be delayed under the current oil price scenario[7]. Tullow, which was initially “farmed in” by Africa Oil, is rumoured to be looking for majors to “farm out” shares of their Turkana interests in an effort to better shoulder the financial investment of the exploration and development phases[8]; or it might be the target of a takeover by larger companies.
[5] A large arid area on the west and south of Lake Turkana in northeast Kenya, with prevalence of pastoralist communities known to be hunger and conflict prone – see block 10BA on the map overleaf
[6] Estimated at over 600 million barrels of proven reserves in early 2014 and now standing at around 850 million barrels, with an expectation of 1.3-1.5 billion barrels. This compares with Ghanian estimated total reserve of 5 bn barrels. In mid-2014, the threshold to make commercially viable to extract the Kenyan quality of crude from sites that are several hundred kilometres away from a port was somewhere between 400 and 500 million barrels.
[7] Recent oil price fluctuations mean that anticipated revenue flows may be delayed. This opens up an opportunity for new African producer countries to prepare themselves better for oil and gas investments. The pressure on price means that oil and gas companies are more attuned to political risk and investment climate challenges with countries that make the right reforms setting themselves apart from others. On the whole exploration budgets are being scaled back and companies are consolidating their portfolios, although different companies are weathering the storm in different ways; larger IOCs can afford to delay their capital expenditure whereas smaller companies may be forced to sell their interests to protect their share price or could be targets of mergers and acquisitions.
[8] Tullow did the same for their finds in the Albertine region in Uganda, that are now shared with Total (France) and CNOOC (China). Africa Oil has been vocal in recent weeks against Kenyan authorities’ plans to increase substantially capital gains tax and other levies that would impact heavily on any deal to sell out part of all their interests in Kenya. Africa Oil is also rumoured to be willing to sell their rights once their technical development and financial and legal conditions will make them marketable to oil majors.
Several other concessions are at earlier stages of exploration for oil and gas in other parts of Kenya – operated by Tullow and Africa Oil, but also Marathon Oil (USA), British Gas (BG) Group (UK), Afren (UK), Bowleven (UK), CEPSA (Spain) and a number of other smaller companies – as the Turkana discovery has triggered renewed interest in a country that shares geological features with Ugandan oil fields[9] and Tanzania off-shore gas fields[10]. BG Group has recently confirmed that Kenya’s first offshore oil discoveries in June are not yet deemed of commercial value, with Ophir Energy (UK) also having similarly disappointing initial results from offshore exploration[11]. CEPSA and Bowleven have both established sites and are conducting seismic tests but have not commenced drilling.
[9] 1.7 bn barrels proven reserves
[10] Reserves estimated in 2013 at 35tn cubic ft, but more are confirmed almost weekly
[11] Ophir has also given an offshore block back to MoEP after inconclusive finds. Ultra-deep prospects are of reduced interest given low oil prices. Eni has decided to suspend exploration in Kenya. The industry in Kenya is precariously balanced in the short term and some exploration companies may be forced to pull out, opening space for majors with deeper financial resources and longer term return to investment cycles .

Kenya Petroleum Exploration Blocks (source: National Oil Company of Kenya)
confirmed reserves in Turkana ≈ 600m barrels
(Africa Oil / Tullow)
Lamu terminal
(proposed)
pipeline for crude oil export (proposed)
International Oil Companies in Kenya have other interests in the region, including in Uganda, and are looking at ways to optimise investment for export from the various basins. The Kenyan, Ugandan and Rwandan governments have jointly commissioned a prefeasibility study for a pipeline to bring the crude to Lamu terminal, although amidst high uncertainty on the final composition, financing, timeline and the very existence of the LAPSSET corridor[12]. The case for an economically feasible oil-financed regional development corridor crossing northern Kenya will be made very soon. Other competing pipeline options are possible, including on a more direct export route from Uganda oil fields to Mombasa port or to connect Kenya, Uganda and Rwanda for distribution of refined products[13]. When a decision is taken, this will inevitably trigger the design and financing of ancillary – but potentially dual use – transport, energy and water infrastructure. The possibility to merge Ugandan and Kenyan oil exports in one pipeline is likely to bring to Kenya the interests and the investment of other international oil companies, such as Total (France) and CNOOC (China)[14].
[12] Africa Regional Department has prepared a dedicated information note to Directors on LAPSSET with inputs from post. A comprehensive summary study on oil related infrastructure in East Africa and the Great Lakes regions is due to be published by International Alert.
[13] It is interesting to note that the new oil finds in Kenya and Uganda are helping to bring leaderships in Nairobi, Kampala and Kigali politically closer, but also that East African political links with Tanzania are loosening as a consequence
[14] Uganda has 200,000 bpd ready for production (60,000 to be refined locally). It is far ahead of developments in Turkana. There is likely to be strong pressure for the Total-preferred option, i.e. to Mombasa. The positive for Kenya is the prospect of pipeline transfer fees (perhaps allocated equally to the counties along the route).
However, there is a real risk that these promising developments do not result in growth of the oil sector in Kenya within anticipated timelines, for two reasons:
The recent fall in global oil price. Given the relative small size of the oil reserves confirmed so far, Kenya is not viewed as in the top tier petroleum frontier. Industry response has been to scale back exploration budgets, concentrating on development of proven reserves, and minimising additional costs. For Kenya this may mean a delay in production of first commercial oil, and a reduction in reserve estimates. Therefore, in a period of tight exploration budgets and forecasting global oversupply, international investors may decide to reduce or postpone their investment in Kenya.[15]
[15] See the DFID Chief Economist’s Office Country Note “The Oil Collapse and Developing Countries” (Nick Lea, January 2015) and an internal note commissioned by DFID ARD on “Implications of oil and gas prices for investments in future producer countries in East Africa” (Angelique Botella, March 2015).

Bad governance: The pressure on oil price also means that oil and gas companies are more attuned to political risk and investment climate challenges. The new Kenyan Petroleum Bill is under discussion and several of its provisions are contentious to stakeholders. There is a risk that the regulatory framework remains incomplete or not fully implemented, leading to a lack of transparency and cronyism in awarding and managing exploration licences and production sharing agreements.
## The Mining Sector
A combination of the enthusiasm for the oil discovery and of the enactment of the 2010 Constitution which created a new Ministry of Mining[16], provide fertile ground for the rebirth of a mostly dormant mining industry in Kenya.
[16] While cancelling several other ministries in an attempt to rationalise and reduce recurrent expenditure

Kenya Gemstone and Mineral Deposits (source: Kenya Chamber of Mines)

Several different ores and commodities have been exploited or are thought to be commercially viable in different parts of Kenya (soda ash, fluorspar and diatomite, silica sands, rare / heavy minerals – niobium, ilmenite, rutile and zircon – in Kwale, gold in Turkana and the Ndori greenstone belt, gems in Taita Taveta and coal in the Mui basin of Kitui). The scale of mining operations is also much diversified from micro – and mostly informal/illegal – artisanal miners to large scale operations by companies like Base Titanium[17] and Acacia[18]. A new Mining Bill required by the 2010 Constitution has been approved by the National Assembly in October 2014 and is expected to be enacted later in 2015, after a Senate reading and with the approval of a comprehensive set of regulations that will overhaul the sector[19]. The combined economic value of mining industries in Kenya will probably remain smaller than what oil and gas are thought to offer, but individual operations will matter greatly for the economy of a number of counties and for the welfare of people affected by large scale mining and of communities of small scale miners. However, there is a real risk that these promising developments do not result in growth of the mining sector in Kenya, for two reasons:
[17] Base Titanium is a subsidiary of Australian and UK-listed resources company, Base Resources. Its flagship development is the Kwale Mineral Sands Project in Kwale County, 50km south of Mombasa. Large scale exploitation of heavy mineral ore containing ilmenite, rutile and zircon has started in 2013.
[18] Acacia – formerly Africa Barrick Gold – is appraising a very large concession but it is still few years before any investment decision can be made. The global gold price slump is surely delaying investment and the prospect of replicating the large operation that Acacia has in Tanzania
[19] DFID Kenya has been providing key technical assistance to MoM for the drafting of the Bill in line with international best practice and to facilitate the consultative process with industry stakeholders and within the two houses of Parliament (see below on KEIDP project). The same assistance has been provided for developing priority regulations, an electronic cadastre system and a geodata bank that will radically transform how mining is regulated and operated in Kenya.
Bad governance: the new Mining Bill is not enacted yet, and some of its provisions might be contentious to particular stakeholders or interest groups. There is a risk that the regulatory framework remains incomplete or not fully implemented, leading to lack of transparency and cronyism in awarding and managing large and small mining licences.

Poor business environment: Kenya is not viewed as a top tier mining country (compared to Tanzania, Mozambique or Ghana) and is in the bottom ten countries in terms of investment attractiveness of the mining sector according to the 2014 Fraser Institute Annual Survey[20]
[20] https://www.fraserinstitute.org/uploadedFiles/fraser-ca/Content/research-news/research/publications/survey-of-mining-companies-2014.pdf
## A transformative potential for economic development …
The extractives sector currently contributes approximately 1% to Kenya’s GDP, and less than 3% to total export revenues. However, this contribution is set to grow significantly, perhaps to as much as 10% of GDP after 2020. The impact of Africa Oil and Tullow discoveries of oil in northern Kenya, estimated as the same scale as the Forties field in the early 1970’s, in the North Sea, will increase with Kenya’s role as a transit country for reserves in Uganda[21]. Off-shore[22] and on-shore natural gas is being explored with great expectations for domestic use in a fast-growing economy. Various mining operations across the country will add further if the trend set by the Base Titanium’s project in Kwale can be maintained, with Acacia exploring for gold in the highly prospective Ndori greenstone belt and Mayfox mining exploring for gold in Turkana, with a geological prospective at this stage held to be the equivalent of the Niassa Gold Belt in Mozambique.[23]
[21] Transit through LAPSSET corridor of crude from South Sudan and Ethiopia is less likely in the foreseeable future that expected in recent years
[22] Extractives at the moment do not seem to constitute a serious risk of disputes with Kenyan neighbours. Off-shore exploration might be the exception. The Federal Government of Somalia has recently filed a claim for a vast maritime area as their exclusive economic zone at the expense of what Kenya consider its exclusive economic zone.
[23] See http://mayfoxmining.com/the-company/
The fiscal revenues arising from mining and petroleum concessions are likely to have a significant impact on Government budget (see details below in the economic appraisal) and a proportionally greater one for individual mining or oil counties. However the foreign direct investment (FDI) necessary to develop the extraction and delivery to markets of extractive resources is bound to be larger and arriving in the country at much earlier stage in the industry cycle[24]. The World Bank report “Towards a Petroleum Sector Master Plan for Kenya”[25] – supported by DFID Kenya – estimates the possible investment for economically realistic projects related with oil and gas in Kenya at between USD 15 and 18 billion over less than a decade. The vast majority of this investment can only happen through public-private partnerships sustained by foreign investment.
[24] DFID Topic Guide on Extractives industries, Development and the Role of Donors, OPM Sep 2013
[25] PwC, June 2015. Downloadable from http://www.pwc.com/ke/petroleum-master-plan
There is a significant potential for extractives – if wisely managed – to help Kenya to finance its exit from aid and transform the lives of the poorest, as it is the case for a number of African countries endowed with recently discovered petroleum and mineral resources[26]. There are three key ways in which growth of the extractives sector can support a timely and self-financed exit from poverty for Kenya:
[26] See Paul Collier “The Plundered Planet” (2010)
#### B1 – Increased public spending
Kenya suffers from constraints to inclusive growth that can be alleviated through increased public spending e.g. electricity, transport and water infrastructure bottlenecks, agricultural extension services, and access to basic public services. Petroleum foreign direct investment and revenues to government are likely to dwarf total development partner support in the next five to ten years, with estimates that petroleum revenues could reach 10% of GDP under high oil prices. Extractives can therefore be an important way to ensure public spending for inclusive growth and poverty reduction. See the Appraisal Case for more analysis of this.
#### B2 – Job creation
Kenya currently suffers from insufficient creation of productive formal sector jobs (currently 14% of jobs and falling over time)[27], forcing the majority of new entrants into underemployment in agriculture and the informal sector. Estimating human resource requirements is difficult for investments that in large part are yet to start. Research from the Lundin Foundation shows that direct resource demands in oil will create between 6-15,000 new jobs. The vast majority of these jobs will be in construction or ancillary sectors that will serve construction (such as of the crude oil export pipeline to the coast).[28] However, these jobs will not go to Kenyans if the skillsets are not available locally and if the Kenya-based private sector cannot compete to supply the international companies that are investing. Mining operations are likely to require smaller numbers but for longer time, i.e. not only during construction but also in operation. However the skillsets required by the petroleum industry during the short development phase can be transferred to other sectors when construction is over. Although the number of direct jobs offered by the industry will be relatively small, there may be up to four times as many indirect and ten times as many induced jobs created[29], providing goods and services into a growing local economy. Skills related to indirect and induced jobs are more likely to be acquirable by members of poorer households and more likely to be transferrable to jobs and opportunities outside the energy sector, thereby helping the wider economy grow and ensuring the sustainability of growth beyond the oil and gas investment cycle.
[27] World Bank (Dec 2012) Kenya Economic Update.
[28] Summary Report: Education, Skills and Training Needs for Kenya’s Emerging Upstream Oil and Gas Sector, the Lundin Foundation 2014. DFID Kenya is acquiring more evidence on possible jobs created directly or indirectly by oil and gas and mining investments or induced by them. A scoping report on extractives local content in Kenya will be published by Adam Smith International in July 2015 with support from DFID Kenya KEIDP project.
[29] Defining jobs: - Direct jobs: jobs created within the lead firm or industry - Indirect jobs: jobs created by firms’ distributors and suppliers within the value chain - Induced jobs: jobs resulting from direct and indirect employees spending more and increasing consumption (DCED report on ‘Measuring Job Creation’ and IFC Jobs Study, 2013)
#### B3 – Community development
Current petroleum exploration is mostly in the poorest regions of Kenya. Ensuring that there are tangible benefits to local communities from oil production, planned participative and delivered in a transparent and accountable manner is critical to increasing security in those areas, but also for the socio-economic wellbeing of Kenyans who live in those areas.
## … but with high associated risk for poverty reduction
The potential transformative impact of the extractives sector unfortunately comes with high social, political, economic and environmental risks to several counties and to Kenya as a whole. As typical of developing countries endowed with significant natural resources, balancing the promise of prosperity by developing the sector must always be placed in a context of significant risk. For Kenya the main risks for poverty reduction are the following:
#### R1 – Loss of competitiveness of other export sectors
Oil and gas exports tend to lead to an influx of foreign currency, which increases demand for and strengthens the local currency. This in turn makes other export driven parts of the economy less competitive. Appreciation of Kenya’s real exchange rate due to other factors is already a concern, partly responsible for the slow growth of manufacturing exports. Extractives could further exacerbate this. Meanwhile, oil and gas is capital but not labour intensive, and so a growing sector of the economy that may shrink other sectors brings with it fewer jobs.[30] The fall in oil prices since mid-2014 highlights the volatility of commodities and the upstream extractives sector and the cyclical risks of a more significant role for petroleum revenues in the economy. The recent case of Ghana’s economic woes is salient in this regard.[31]
[30] The so-called “Dutch Disease” was first coined by the Economist in 1977 to refer to what had happened in Holland as gas exports soared in the 1960s and 70s http://www.economist.com/blogs/economist-explains/2014/11/economist-explains-2
[31] See the DFID Chief Economist’s Office Country Note “Ghana’s Economic Crises and DFID’s Response” (Nick Lea, April 2014). See also the World Bank working paper on “How Should Donors Respond to Resource Windfalls in Poor Countries?” http://econ.worldbank.org/external/default/main?pagePK=64165259&piPK=64165421&theSitePK=469382&menuPK=64166093&entityID=000158349_20140627104243
#### R2 – Bad governance
With implicit acknowledgment that the risk of a “resource curse”[32] thanks to petroleum revenues is ever present, the Government of Kenya and a number of concerned authorities have started in earnest to reform the relevant policy and regulatory frameworks. This is also required by the 2010 Constitution, which puts the state in charge of managing natural resources, but requires enhanced transparency and devolves to counties safeguard powers as well as a fair share of benefits and the power to plan for their use. National debate on the sharing and use of revenues is lively, although often based on misconceptions and with an apparent risk of conflict among legislative efforts[33] at various levels and among central and county powers, especially when they align along opposite party lines. Institutions managing extractives policy and regulation at the centre are young and have little capacity. Similarly the County Governments that will need to provide oversight. At both levels capacity to plan development on the base of Strategic Environmental Assessments[34] is minimal.
[32] Bad governance provides the opportunity for rent seeking elites to prosper and stay in power without sharing the benefits with the rest of the nation and so choking inclusive economic development and creating the landscape for socio-political instability. See Paul Collier’s extensive work on the risks of bad governance of natural resources, e.g. in “The Plundered Planet” (2010).
[33] While the new Mining Bill has been approved by the National Assembly in October and is now before Senate, partially overlapping Energy and Petroleum Bills have been drafted, with the latter now before the National Assembly. Separate bills on fiscal regime, natural resources benefit sharing, use of land and local content requirements are proposed separately (the Community Lands Bill, the Sovereign Wealth Fund Bill, Concessions Bill and the County Royalties Bill). A few resource rich Counties are also drafting their own regulations that may well end up introducing further duplications or inconsistencies and make requirements for investors impossible without really enhancing benefits for the poor and the marginalised.
[34] Strategic Environmental Assessment (SEA) is a systematic decision support process, aiming to ensure that environmental and possibly other sustainability aspects are considered effectively in policy, plan and programme making. See http://en.wikipedia.org/wiki/Strategic_environmental_assessment and https://www.gov.uk/government/collections/strategic-environmental-assessments
#### R3 – Conflict and insecurity
The announcement of the oil discovery in traditionally marginalised Turkana County created huge expectations, often unrealistic, both nationally and locally. Expectations are also immediate, with little consideration of the time and investment necessary before any revenue can be actually accrued and the lifecycle of a petroleum project. The risk that this fuels a pre-existing tendency to violent conflict has potentially massive implications for the future of the business and for the political stability of the region.
In the current exploration phase, national elites scramble and wrestle to secure their future place at the table for the top largest segments of an inverted benefits pyramid. Local communities have immediate expectations as they already feel the pain (or at least have a perception) of the sharp edge at the bottom of the pyramid: issues arise around land ownership and use, environmental impacts, inflow of labour and skilled personnel from outside, unequal distribution of scarce resources and services, etc. Local Authorities set up by the devolutionary process enshrined in the 2010 Constitution are currently unable to effectively represent communities and to convey their grievances in a way that allows for an effective response. Industry operators tend to “buy their social licence to operate” with localised, short term and unsustainable – although expensive – hand-outs. Unsustainable demands can only grow. In an already conflict prone area as pastoralist Turkana is, security can easily deteriorate. Central authorities may react by sending in special security forces, inevitably provoking further grievances. International companies risk to be caught in the middle and often are ill equipped, culturally as well as technically, to devise long term solutions while keeping efficient their massive engineering operation on the ground. In Kenyan politics, local tensions could well spill over at national level with dramatic consequences.
## Existing and planned donor support
#### DFID support
A DFID Kenya scoping study on extractives was conducted from March to September 2013, which involved desk study and consultations in Nairobi and in three extractives-rich counties (Turkana, Taita Taveta and Kwale). The study made recommendations to ensure that Kenya mitigates the risks and leverages the significant opportunities presented by the exploitation of its extractive resources[35]. Following on from approval of the scoping study by the Government of Kenya, DFID Kenya set up an interim follow-up intervention, the Kenya Extractive Industries Development Programme (KEIDP, £3.5m over 18 months up to June 2015), under the Kenya Market Assistance Programme (K-MAP[36]). KEIDP’s remit is to selectively address the high priority recommendations of the scoping study. See the ANNEX in QUEST 5031100 for a summary of achievements and lessons learned from KEIDP.
[35] UK Department for International Development (June 2013) Recommendations for the Development of Kenya's Extractive Industries (ASI)
[36] £24.4m (2012-2017), including three large components: Extractives (£3.5m); Youth employment (£5.1m); Kenya Markets trust (£14.9m) plus a monitoring and evaluation component (£0.9m). http://devtracker.dfid.gov.uk/projects/GB-1-202698/
A major contribution from DFID Africa Regional Department (ARD) is of up to £25m over 5 years (2015-2019) to co-finance with the German Federal Ministry for Economic Cooperation and Development (BMZ) the Skills for Oil and Gas Africa programme (SOGA) programme[37] targeting four countries; Kenya, Uganda, Tanzania and Mozambique. This will build technical and vocational skills in each of the four countries, to ensure that domestic workforce benefits from the opportunities opened up by new investments in oil and gas. In Kenya, we are looking at the possibility of country-level contributions to increase the scope and, crucially, to attract key development partners and industry around the same table: Tullow and Africa Oil have a pilot initiative in Turkana – upgrading Lodwar Polytechnic – that could be coordinated or even merged; the Canadian Cooperation is a potential additional actor we are engaging with. Other options will be explored during SOGA inception. See the ANNEX in QUEST 5031100 for a summary of SOGA features.
[37] http://devtracker.dfid.gov.uk/projects/GB-1-204639/
DFID ARD also manages, at the centre, the Releasing the Transformational Potential of Extractives for Economic Development (RTPEED) programme (£34m, 2014-19)[38] to improve governance, accountability, and transparency in developing countries endowed with oil, gas and minerals. RTPEED may complement work to build social accountability relevant to extractives in Kenya. See the ANNEX in QUEST 5031100 for a summary of RTPEED features.
[38] http://devtracker.dfid.gov.uk/projects/GB-1-203308/
DFID ARD organises Extractive Industries Executive Courses on environmental, land, health & safety and social governance through IFUSE[39], aimed at senior government officials in Africa. This is delivered by UK agencies (British Geological Society (BGS), The Coal Authority, Ordnance Survey, The Health and Safety Executive and the Foreign & Commonwealth Office (FCO)). Kenyan participants are identified from a range of institutions relevant for extractives, but preferably other than those we have been supporting with KEIDP, such as the Ministry of Environment, Water and Natural Resources (MoEWNR), the National Environmental Management Authority (NEMA), the Council of the County Governors and the Parliament. Attendance helps to develop relationships on environmental and mineral governance, with potential for follow up technical assistance from UK government agencies, funded through IFUSE.
[39] The Investment Facility for Utilising UK Specialist Expertise (IFUSE), an existing DFID programme, supplies specialist government-to-government expertise to support business environment improvement in DFID’s partner countries and regions. IFUSE matches demand with expertise from a broad range of UK government departments, agencies and related standards bodies in the form of short term, targeted deployments.
Kenya Ministry of Mining has been negating assistance from the Africa Legal Support Facility (ALSF), a regional programme managed by the African Development Bank (AfDB) – with substantial contribution from UK Aid (£7m 2014-17)[40] – to support governments to negotiate complex extractives contracts. This could include deployment of lawyers to deal with legal transactional issues and advise on ongoing court cases and mining contract negotiations, as well as training for lawyers in Kenya (both government and private sector).
[40] £7m (2014-17) http://devtracker.dfid.gov.uk/projects/GB-1-203974/
The East Africa Research Hub[41] (EARH) has commissioned a one year synthesis study to deepen understanding on the impact of extractives on political settlements and conflict in East Africa – i.e. to summarise the evidence on an actual / potential ‘resource curse’. Kenya is one of the country case studies. The expected outcome is robust evidence to inform policy and actors (including DFID) on measures that can mitigate risk for East African countries to grow sustainably through exploiting their natural resources. The study findings will be summarised in policy briefing notes due in June 2015 and academic papers due in December 2015.
[41] http://devtracker.dfid.gov.uk/projects/GB-1-204570/
#### Other donors and international actors
DFID has moved earlier than most in acknowledging the transformative potential of extractives in Kenya. Other players are now catching up with enthusiasm, many by exploring the sector across the board, while fewer have started focusing on subsectors or segments where they can really add value. An Extractive Industries Donors’ Working Group was started in 2013 as a spin-off of the Private Sector Development group, and it is currently chaired by the Canadian Development Cooperation, with DFID Kenya co-chairing. Formal engagement of the group as such with Government has not yet started.
Most active bilateral donors are those of countries with relevant commercial interests. Besides Canada, committed but so far with limited appetite for coordinated programming, other bilaterals (USAID, France, Japan, Norway, Netherlands and Belgium) and the EU are currently on a watching brief or are looking at areas of overlapping with their programming in other sectors, egg on devolution, private sector development or energy. Australian DFAT had expressed interest to collaborate with DFID on extractives, but it is now closing down its entire Africa programme.
On the multilateral front, the World Bank launched in late 2014 the Kenya Petroleum Technical Assistance Project (KEPTAP). This is a 6 year, $50m programme, mostly executed by the Kenyan Ministry of Energy and Petroleum (MoEP) or other GoK institutions to further: a) Petroleum sector reforms and capacity building; b) Revenue and investment management reforms and capacity building; and c) Sustainable impact of the oil and gas industry with reforms and capacity building. DFID Kenya contributed to KEPTAP design through the KEIDP project and has started discussion with the WB and MoEP to identify a possible contribution to KEPTAP to complement our technical assistance efforts currently mostly directed to Ministry of Mines. See the ANNEX in QUEST 5031100 for a summary of KEPTAP features.
The IMF has assisted the Treasury and the Kenya Revenue Authority (KRA) since 2013 to advise on the fiscal regime and production sharing agreements (PSAs) under the IMF’s topical multi donor Trust Fund: Managing Natural Resource Wealth[42]. The Kenya programme has concluded the work on extractive industries fiscal regime in November 2014, with final provisions added to the new Finance Act (enacted Dec 2014). A subsequent IMF mission also provided clarifications to the Kenya Oil and Gas Association (KOGA) regarding the taxation of capital gains accrued in the sale of non-resident interests that own Kenyan petroleum rights and on the model Production Sharing Agreement that Kenya has adopted. In the opinion of IMF, the Kenyan new tax code on extractives is not very different from what is in most European countries. IMF will now start a new phase of work around extractive industries revenue administration, hopefully in close complementary with World Bank assistance provided through KEPTAP.
[42] Contributors are Netherlands, Norway and Switzerland. The Fund is managed by the IMF Fiscal Affairs Department.
The AfDB is hosting the (DFID funded) Information Centre for the Extractives Sector (ICES)[43], a public information web-platform that addresses concerns around the extractives industry by promoting knowledge, transparency and evidence-based dialogue. However it appears that the AfDB’s Africa Natural Resources Centre – announced last year – is yet to spell out its strategy and operating model and it is unlikely that the AfDB can sustain ICES going forwards.
[43] http://ices.or.ke/ entirely financed by DFID Kenya through MAP-KEIDP (see above) for its first year of operation (2014).
UNDP current programme[44] is piloting extractive industry dialogue mechanisms, both at national and in selected Counties, and it will produce a number of analyses on risks, challenges and opportunities of mining operations in specific counties. See the ANNEX in QUEST 5031100 for a summary of UNDP extractives programme. Regional and country offices of UN Women have been also active in scoping their potential role on extractives, to ensure that a gender perspective is factored in industries where women have a traditionally marginal role and are anyway disempowered. Other UN agencies (UNEP, ILO, UNIDO) might come to the fore later on particular segments of extractives if called in by other players. It is not yet clear how effective UNDP’s approach can be for leading a possible coordinated UN effort on extractives in Kenya, both at national and local levels.
[44] Two years, up to 2015, with about £0.4m contribution from DFID Kenya through MAP-KEIDP (see above) and £0.5m of UNDP resources
A number of national and international NGOs are busy shaping their space in Kenyan debate and development initiatives around extractives. A commendable effort to provide coherence and leadership is the Kenya Civil Society Platform on Oil and Gas (KCSPOG), a network of 16 organisations[45] in Kenya that seeks to provide a collective civil society voice.[46]
[45] Hosted by Oxfam and including Danish Demining Group, Transparency International, Kenya Human Rights Commission and Friends of Lake Turkana. Other international NGOs active in the sector are International Alert, Cordaid, Trocaire and the Institute for Human Rights and Business
[46] Which is supported by the FCO for the launch of the Voluntary Principles platform in Kenya
Gaps in support
From the above analysis it may be argued that there are gaps in donor support on the following:
- Ensuring that there is a competitive business environment to attract Foreign Direct Investment into oil and mining sectors that is necessary to generate the revenues and other benefits;
- Maximising the impact of the oil sector on jobs and Kenyan suppliers;
- Community development and conflict prevention;
- Ensuring that oil revenues accruing to county governments are managed efficiently and effectively, and that mining revenues accruing to the national government are managed efficiently and effectively.
## Why DFID?
DFID should fill the gaps in donor support outlined above for the following reasons:
- Strategic fit – HMG: There are British commercial interests in both the petroleum and mining sectors in Kenya[47]. And necessarily we need to deal with major players – also with a general expectation that DFID and the British High Commission in Kenya are particularly well placed to do it. To maintain the trust of the Government we position our support as independent. We do however engage with these British companies (and other investors) on some of their corporate social responsibilities and share our own experience on community engagement and the development needs of the communities they are working with. This is part of a broader ‘UK companies as Champions for Development’ initiative[48] where we encourage (all) British companies to maximise the number of Kenyans they employ; adopt young leader-type programmes; provide social programmes; lead other businesses in showcasing their own ethical business standards, including on transparency and the environment. The principles associated with this initiative are promoted by DFID to all investors.
  [47] Tullow is the most important large early stage investor in the most visible of the industries; but alongside other large international companies in Kenya, e.g. Base and Acacia/ABG in mining. In oil, major international oil companies – of any nationality – are likely to be “farmed in” by the current smaller operators as soon as the feasibility of a crude exporting project will be confirmed.
  [48] INSERT REFERENCE.
- Strategic fit – DFID: Extractives were flagged as a priority in DFID Kenya’s Country Poverty Reduction Diagnostic, and as a potential growth driver in Kenya’s Arid and Semi-Arid Lands in the Inclusive Growth Diagnostic.
- Comparative advantage: DFID has considerable expertise in extractives from a network of extractives advisers (with one based in Kenya working on Kenya, Somalia and Tanzania) and extractives programmes. This proposed programme fits well within DFID’s coordinated portfolio of DFID Kenya bilateral and ARD regional support which are addressing the challenges and opportunities outlined above. The close collaboration between the Kenya country office and the Africa Regional Department through the extractives team of advisers has brought about deep synergies thanks to a wide range of shared contacts[49], resources and expertise[50] which adds value to our work. In addition we’re drawing on initiatives from other divisions that are relevant for our extractives agenda.
  [49] Particularly important as we try to combine partnerships with traditional actors (bilateral donors like Norway, Canada and Australia, and IFIs, like WB, IMF and AfDB), specialist facilities (e.g. ALSF – see below) and, most importantly, international private sector (e.g. BG Group and Tullow Oil).
  [50] ARD headquarters and country based extractives advisers include professional background on private sector development, infrastructure, governance and conflict, climate and environment and economics
## Strategic Choices
#### How to prioritise between petroleum and mining
The balance of priority between the two extractive sectors, petroleum and mining, can be determined considering the following five themes:
1. Level of political engagement: the Ministry of Mining is currently devoting energy and enthusiasm in developing the mining sector, but petroleum sector development is of far greater significance for Kenyan politics in the next few years, especially in the context of the infrastructure that needs to be developed to facilitate export of crude and as the backbone of economic development of traditionally marginal and underdeveloped semi-arid areas in the north section of Kenya.
2. Potential for increased FDI and revenues (growth): the revenues from oil and gas dwarf potential revenues from mining.
3. Potential for job creation (inclusive growth): there is greater long term employment potential (and stronger linkages with local economies) in the mining sector than in petroleum, although a higher peak of employment in a relatively short construction period can nurture the skilled workforce that will subsequently find employment in other parts of the economy
4. Potential for conflict prevention: while there have been significant issues with mining sector development in Kenya (for instance, in Kwale), by far the greater threats to security are in the northern areas of petroleum development, such as in Turkana.
5. Gaps in donor support (our comparative advantage): There is no KEPTAP-type programme planned for the mining sector
From the criteria above it may be argued that programme resources should be spent equally on average between the two sectors. However it is clear that this balance will not be equal across the programme components that will address different outcome areas.
#### Impact statement, indicators and theory of change
Based on the above analysis, it is suggested that the Impact Statement is as follows: Reduced poverty through inclusive and sustainable development of extractives.
For the theory of change at the Impact level see the Theory of Change diagram. This puts the reduction of poverty at the top, which will be indicated by the headcount poverty rates in Turkana, Taita Taveta or other Counties which will particularly benefit from the programme components. This long-term reduction of poverty will be achieved through the following lower level impacts (based on maximising the benefits while minimising the risks):
1. Increased public spending: from higher extractives revenues due to increased FDI, and better management of those revenues (for oil by county governments, for mining by national government). It is not possible to monitor public spending enabled by extractives revenues since they are pooled with other revenues, and so the main Impact indicators are the revenues themselves and changes in FDI in oil and mining and ancillary sectors.
2. Job creation: from the FDI in oil and mining and ancillary sectors. The Impact indicator for this is employment levels in the sectors, ideally disaggregated by gender.
3. Conflict prevention through community development: the Impact indicator for this is the number of working days lost by extractives companies as a result of local conflict.
FDI and working days lost should show an improvement during the lifetime of the project. The other indicators may not be expected to change, within the initial five years of this programme, but it is still of value to specify them now in order to be clear about the Theory of Change, and they can be tracked if there is a follow up programme and/or an evaluation of the programme two years after its end.
#### Gender Equality
Women suffer multiple disadvantages in benefiting from economic development in Kenya, for instance because inequitable access to education, productive assets (notably land), capital, technical skills and voice. The project will ensure that marginalised groups are specifically targeted and will aim to address inequalities of opportunity in the extractives sector. Results measurement, disaggregated by gender and age will ensure that women and youth are well targeted and captured; this can be in form of percentage of women and youth in sustainable jobs, number of women and youth with raised incomes by a given percentage, participation of women in local and national planning and in community grievances mechanisms. Activities would be designed to ensure that they attract more girls by considering appropriate and all inclusive project delivery mechanisms.
The risk of women and girls not being adequately included in the programme can be mitigated through community engagement and government commitment on the programme objectives (both at county and national level).

#### Outcome statement, indicators and theory of change
In order to identify the outcomes that the programme will have to achieve, we analysed the main constraints that need to be addressed to contribute to each of the impact areas prioritised above – increased public spending, job creation and conflict prevention. See the ANNEX in QUEST 5031100 for a summary of the analysis of constraints, ways to address them and assumptions. Evidence and assumptions for the outcomes to lead to the impacts are also given. This outlines the theory of change at the Outcome level – see Theory of Change diagram on page 22.
Based on the analysis below, it is suggested that the Outcome Statement is as follows: a better governance and business environment, community development and a localised and inclusive approach to human resources and local service provision in the extractives sector in Kenya. We will have achieved this Outcome if we obtain:
- Investor-friendly O&G/mining policy implemented: a possible indicator of this is Kenya’s Fraser Institute scores on policy perceptions and the regulatory environment (in both oil and mining).
- Improved governance of revenues from O&G/mining industries: a possible indicator of this is Kenya’s score on the NRGI Resource Governance Index.
- Improved transparency of O&G/mining industries: a possible indicator of this is the number of documented case studies where civil society and industry bodies have changed policies or their implementation.
- Increased competitiveness of local suppliers to O&G/mining industries: this may be measured by the percentage of contracts or of their value as share of FDI that are sourced from Kenyan firms.
- Better employability of local workers: possible indicators of this are: the Fraser Institute Ranking on labour availability and skills (in both oil and mining); and the number of people trained in extractives-related skills in focal TVET institutions who have gone on to be employed in the sector (disaggregated by gender).
- Communities benefit from O&G/mining and are supportive of investors: this could be measured using a survey of communities in Turkana, Taita Taveta and any other target counties.
#### Timeframe for impact
Across petroleum and mining, the extractives sector works to longer than five year timespans[51]. Therefore, it is likely that well over a decade of DFID support may be required, to provide interventions that change as the extractives sector develops and begins to mature. It is recommended that rather than last for ten years, this programme last for an initial five years with scope to scale up support or spin off dedicated programmes on private sector development, community development, institutional strengthening (for instance, in terms of environmental regulation) and so on. This five years engagement, in itself a successor of an interim 18-months initiative, will allow DFID Kenya to achieve initial results while testing effective delivery mechanisms on the various components. It will also provide us with the opportunity to have a break point to re-assess extractives footprint in Kenya and reflect on the programme continuous learning before committing further resources.
[51] A case in point is Uganda, which discovered oil in commercial quantities in the Albertine Graben region in 2006 and still has not begun commercial operations

# Appraisal Case
## Feasible Options
To achieve the Outcome, the programme needs to provide four forms of support across emerging extractive industries in Kenya. Firstly, in terms of better governance, technical assistance to strengthen the institutional capacity where required within national and county level government institutions, with transparency, accountability and protection of the environment as thematic priorities. Secondly, to build capacity in social accountability organisations and coalitions at national level and also support the capacity of private sector bodies to research and advocate for a better business environment in the extractives sector. Thirdly, to support the development of a county level dialogue and participative development platform, beginning with a pilot in Turkana County – also one of the poorest counties in Kenya. Finally, the programme will support a more inclusive approach to local content[52], by focusing on the capacity of local private sector to capture foreign direct investment related to extractives and so to generate jobs for poor Kenyans (complementary to improvements of the technical and vocational skills of the Kenyan workforce addressed by DFID’s Skills for Oil and Gas in Africa programme).
[52] The share of inputs in the production process (jobs, materials, equipment, capital) that come from local sources rather than being imported, i.e. the share of the investment that boosts local economic development
Given the high impact and likely frequent changes of the political economy background at, and between, all levels of government as well as community level, the programme will also need to regularly re-assess the position, interests and influence of stakeholders and to adapt continuously to them. This will be crucial to adapt the programme and our engagement to respond to change, maximise results and reduce adverse effects, including risk of corruption and reputational risk. This will also be needed to confirm that counterpart institutions are fit for purpose[53].
[53] Not just relevant line Ministries (MoEP, Treasury) but also authorities such as the newly created Upstream Regulatory Authority (URA), the National Environmental Management Authority (NEMA) and the Kenya Revenue Authority (KRA), as well as County Governments, Parliament and County Assemblies.
The above requires a multi-component approach, as follows. See the ANNEX in QUEST 5031100 for a full discussion and appraisal of alternative feasible options for each component.
#### 1. Institutional Strengthening of GoK Institutions
This section discusses feasible options and intended outputs for achieving the following Outcomes:
- Improved governance of O&G/mining industries
- Investor-friendly O&G/mining policy implemented
- Improved transparency of O&G/mining industries
The preferred option is to establish a flexible technical assistance facility with governance arrangements, robust criteria for allocation of resources and financial availability adequate to respond and adapt effectively to technical assistance demands from institutions relevant for extractives in Kenya (line Ministries MoM and MoEP, but also Treasury, Ministry of Environment and the NEMA).
If successful this component could be expanded into a dedicated, programme for technical assistance to improve strategic environmental assessments and planning capabilities, possibly supported by the International Climate Fund (ICF). Depending on a number of factors, this could focus on extractive industries only or more generally deal with a range of large scale economic infrastructure projects.
#### 2. Private Sector Development (“Local Content”)
This section discusses feasible options and intended outputs for achieving the following Outcomes:
- Increased competitiveness of local suppliers to O&G/mining industries
- Better employability of local workers
The preferred option is to integrate support to the Local Content component of World Bank KEPTAP into the DFID programme, ensuring complementarity and coordination with our SOGA programme, and to address value chain development and linkages through Ministry of Industrialisation and Enterprise Development (MoIED), and also through additional value chain support directed to industry associations and including mining alongside petroleum.
To note that value chains and skills development in direct support of industry bodies has the potential to attract substantial co-funding from international investors, which can benefit from direct improvement of their own value chains, as well as matching funds from Government at national or local levels. Substantial scale up is also possible over time, depending on actual investment decisions.
#### 3. County Engagement
This section discusses feasible options and intended outputs for achieving (outcome):
Communities benefit from O&G/mining and are supportive
The preferred option is to support dialogue and development platforms in selected counties, starting in Turkana (communication and community engagement in oil exploration areas) and at least one mining county (environmental, health and safety training for artisanal miners) and to stand ready for opportunities to set up social investment / local development funds that deliver on projects, funded by corporate responsibility funds and/or national government natural resource revenue allocations, and to then replicate success beyond the initial pilot counties.
Support for community development is likely to require interventions after the initial five year intervention, which may take the form of either an additional funded extension or a spin-off programme.
#### 4. Transparency and Social Accountability
This section discusses feasible options and intended outputs for achieving (outcome):
Improved transparency of O&G/mining industries
The preferred option is to set up a challenge fund to provide demand-driven support to petroleum and mining civil society organisations and industry bodies to enhance social accountability and respond to emerging opportunities towards revenue monitoring and transparency schemes (EITI, the Natural Resources Charter, etc.) and to support the sustainability of ICES services.
This component of the programme may attract other donors or from global transparency initiatives.
#### 5. Stakeholder Mapping
The preferred option is to deliver a baseline and regular (bi-annual) updates of a mapping of position, interests and influence of stakeholders relevant for oil and gas and mining in Kenya at, and between, all levels of government as well as community level.
## Summary of selected option
Based on the appraisal above the programme is structured in five thematic components that will deliver outputs contributing to one or more of the expected outcomes. Links between outputs and outcomes and the associated assumptions are shown in the theory of change (page 22). Since the programme is envisaged as testing approaches that can then be scaled up and/or spun off into separate programmes (which may be able to attract funding from donors, GoK and firms), the cost to each component has been estimated as the minimum commitment necessary to have an impact on the Outcome indicators. These costs and the potential for scale up and co-funding are outlined in the following table.

Components		Minimum financial / commitment		Potential for future
				Scale-up/spin-off?	Co-funding?
1	Institutional Strengthening	£ 9.00m	38%	Yes	-
2	Private Sector Development (“Local Cont.”	£ 5.00m	21%	Yes	Yes
3	County Engagement	£ 5.00m	21%	Yes	Yes
4	Transparency and Social Accountability	£ 3.50m	12%	-	Yes
5	Stakeholder Mapping	£ 0.50m	2%	-	-
	Sub-total	£23.00m	96%	-	-
6	Coordination and M&E (Programme staff)	£ 1.00m	4%	-	-
	Total	£24.00m	100%	-	-

The five thematic components are related to each other and to relevant interventions external to the programme as per the diagram on next page.

## Assessment of the Preferred Design compared to the Counterfactual
Counterfactual
The counterfactual option is to stop DFID Kenya funded activity in extractives in Kenya once the KEIDP programme ends in June 2015. This would involve terminating technical assistance to the Ministry for Mining and Ministry for Energy and Petroleum, with the likely result that the regulations and policies being prepared by these Ministries would be of a lower standard and significantly delayed. The impact would be most significant in the mining sector, as World Bank support is starting to the MoEP and to other national institutions on upstream petroleum governance. The other gap would be assistance at the sub-national level which is currently not envisaged by any other programme and any support to engagement on policy coordination across extractives. Alongside this, the community engagement element of KEIDP would stop with the result that the nascent community engagement experience would cease. On efforts to support jobs, the counterfactual would see no DFID Kenya support to local content policies and to private sector to increase their likely capture of value chains generated by foreign investment in extractives. SOGA programme on skills would not be complemented, which will reduce the number of jobs that SOGA could actually provide.
Given the context (business environment, governance capacity, conflict risks in areas rich in natural resources), the counterfactual situation outlined above would likely mean that the extractives sector in Kenya does not develop and mature significantly beyond the exploitation of the oil fields in Turkana by Tullow/Africa oil, the Base Titanium’s mineral sands operation in Kwale and some substandard artisanal mining in areas rich in gemstone and gold.
Whilst there are other donors considering entering the extractives sector DFID’s first mover responsibility covered by the preferred funding option mean that there would likely be a minimum six months - possibly some years - before other donors stepped up their activity in these areas if they do so at all. The assessment below assumes that no other donor would take up these activities.
Incremental Costs
- DFID financial cost: £24million over five years (from 2015 – 2019)
- DFID staff cost: one full-time equivalent locally engaged programme funded A2/A2L staff member (or an equivalent resource sourced from for example a services provider). 5% of Team Leader as SRO. 30% of extractives advisor. 20% of time of wealth creation team programme manager.
- Costs to other stakeholders: The preferred option does not rely on funds from other sources to achieve its outputs. However, some components may attract co-funding in due course from other donors, private sector or Government which may contribute to or widen the anticipated impact. In particular it is likely that the community engagement component would attract funding from IOCs, as is already been seen for the SOGA programme (particularly in Tanzania) and for the Western Region Coastal Foundation programme in Ghana[54]. There are also opportunity costs in terms of stakeholder engagement through the programme but these are marginal as the demands of community and other stakeholders as a result of the programme are not anticipated to be onerous.
  [54] http://devtracker.dfid.gov.uk/projects/GB-1-202476/
See the Financial Case for the profile of budget over the lifespan of the programme.
Incremental Benefits[55]
[55] Other incremental benefits could be added such as livelihoods for self-employed artisanal miners, including women, and improved environmental safeguards and better planning. However actual scope for them can only be determined at inception or by the continuous adjustments that the programme will face in response to the regular mapping of stakeholders
Stage 1: Description	Stage 2: Quantification	Stage 3: Monetary value
Public spending: increased public spending from higher revenues and from higher FDI arising from improved business environment, and better county level management.	Improvement in relevant international petroleum and mining business environment indices[56] (Outcome indicator)	Public spending from oil revenues has the potential to increase Kenya’s non-oil GDP by up to 10% by 2042[57]. The project will increase the probability of this, but impossible to estimate the extent.
Conflict prevention: local conflict prevented or mitigated from communities being supportive of extractives due to community development and management of expectations.	Reduced days of stopped oil exploration as a result of local conflict (Impact indicator)	Violent protests at a Tullow rig in Turkana cost Tullow an estimated $1million per day. The project will reduce the probability of this, but impossible to estimate the extent.
Community development: more effective community programmes funded by extractives companies contribute to poverty eradication	Satisfaction rating of local communities with development projects (Outcome indicator)	Not possible to monetise.
Jobs: increased jobs created for Kenyans in the extractives industries and supply chains from better employability of workers and competitiveness of local suppliers.	Number of people trained who found work in the sector (Outcome indicator) / Number of Kenyans employed in oil and mining (Impact indicator)	Not possible to monetise.
[56] E.g. Fraser Institute Survey of Mining Companies http://www.fraserinstitute.org/research-news/display.aspx?id=22259 and Global Petroleum Survey http://www.fraserinstitute.org/research-news/display.aspx?id=21976
[57] Baselines to be confirmed at inception stage

Public spending
Extractives are labour intensive only in the infrastructure construction phase or in the case of artisanal mining, and have limited links to the rest of the economy. The main benefit from them is in providing fiscal revenues that can fund increased public spending and in expanded foreign direct investment during development that in turn can pave the way for development of critical infrastructure beneficial for other parts of the economy (resource corridors). Most information is available for oil, and so this analysis focuses on it rather than mining. The pattern of revenue generation under baseline and low oil price scenarios is given below, with revenues peaking between 2022 and 2030[58].
[58] Oil prices are projected until 2040 by the USEIA, and kept constant after that. Total quantity of production incorporates both probable reserves identified in Kenya

Production Value and Fiscal Revenues
Source: Authorities, USEIA Price Projections, World Bank Staff Calculations

Although oil is neither a necessary nor sufficient condition for sustained economic growth, there is a growing set of examples of the potential of extractives to generate revenues and economic growth, where the sector is well governed by strong institutions.[59] Specifically for Kenya, the World Bank[60] suggest that the development impact from this spending can be maximised by: ‘moderate frontloading’ of spending funded by borrowing against future extractives revenues; and ‘balanced composition’ of spending between infrastructure, health and education since physical and human capital are complementary. If this is followed, the impact on fiscal revenues and GDP growth is estimated as follows (estimates for the low oil price scenario are currently being revised by the Bank):
[59] DFID commissioned report ‘International Standards in the Mining Sector’ (2011).
[60] Levine et al (2014) Fiscal rules in a DSGE model of Kenya. Unpublished but summarised in the World Bank’s upcoming Country Economic Memorandum for Kenya.
Oil price scenario	Fiscal revenues during peak (2022-2030)	Increase in GDP by 2042[61]
Baseline oil price	$3.2bn a year, 8% GDP	10%
Low oil price	$2bn a year, 5% GDP	n/a
[61] Baselines to be confirmed at inception stage

This increase in GDP and higher public spending will have the following development impacts:
- Reduced income poverty: World Bank projections suggest that if Kenya’s average economic growth rate can be increased from its historical rate of 4% to 6% (while inequality remains the same), the poverty headcount rate in 2030 will fall from 27% to 13%. Extractives can contribute towards this.
- Improved health and education outcomes: for instance, the revenues can enable government health spending to increase to international standards.
It is impossible to estimate the extent to which the programme will increase the probability of these gains being realised. However, given the large size of the benefits, all that is required is to provide a strong case that at least a small increase in the probability will be achieved. This case is as follows:
- Programme very likely to increase FDI in oil: as is shown above, the programme will address the key areas of weakness in the business environment for oil, and the evidence that this will result in an increase in FDI is Strong.
- Programme will help counties and communities to manage oil revenues: Current negotiations anticipate that 20% of oil revenues will go to counties and 5% to communities. Although these revenues will not arrive during the period of the project, it will put in place the building blocks to enable it to be well spent through the Institutional Strengthening and Community Engagement components.
Conflict prevention
The indicative cost of $1m per day for a drilling rig stopping activities is based on a Kenyan example in 2014. The figure comes from Tullow and is considered accurate. At exploration stage the private sector bears this risk and cost but it will be shared with Government once exports start in the form of lost Government revenues.
It is considered that there is medium evidence of the impact of the community engagement platforms on conflict prevention. Successful use of dialogue fora have been seen in Uganda to mitigate conflict, where like in Kenya Tullow Oil was a primary actor.[62]
[62] CARE International UK: Peacebuilding with Impact, 2011, quoted in the Western Ghana Business Case.
Jobs
Africa Oil’s Lundin Foundation estimates that over the next ten years, when human resource demand is at its highest during the construction phase (such as pipeline construction to the coast), the oil and gas sector will create between 6,000 to 15,000 new jobs in Kenya, with the majority requiring technical or vocational training. These jobs will not go to Kenyans if they are not upskilled quickly.
Mining is more labour intensive than oil. By increasing Kenya’s competitiveness and supporting growth of a mining sector that can accommodate large international firms as well as local artisanal minors, this intervention has the potential to create a significant number of jobs.
A detailed study of evidence indicates that where there is good governance there is an extensive multiplier involved in the industry, but benefits do not arise immediately.
Risks
The main risks of negative impacts from the programme are as follows:
- Environment: proactive mitigation of environmental risks is built into the project through the Institutional Strengthening component. Clear evidence from other countries is that better managed extractives sector development processes are less likely to lead to environmental degradation. See the ANNEX in QUEST 5031100 for a Climate and Environment Assessment of the programme. Accordingly a dedicated indicator is established in the logframe at outcome level. The other components – Private Sector Development, County Engagement and Transparency and Social Accountability – will all contain explicit actions, to be defined at inception, to improve the environmental sustainability of extractive industries.
- Dutch disease: this will be managed by World Bank and IMF support to GoK’s management of fiscal revenues.
- Governance: mitigating governance risks is built into the project through the Institutional Strengthening component. Accordingly, dedicated indicators are established in the logframe at outcome and output levels. The other components – Private Sector Development, County Engagement and Transparency and Social Accountability – will all contain explicit actions, to be defined at inception, to improve the governance systems of extractive industries.
Balance of costs, benefits and risks
The largest benefit will be through the impact of higher public spending from revenues. Potential benefits of this are high and the theory of change is based on strong evidence, so there is a strong case that the £12m to be spent on the oil sector, and £24m overall, will provide good value for money. The case for mining activities rests more on the job creation impacts. More evidence will be gathered at inception.
VfM Measures and VfM Statement
This kind of programme is not very amenable to VfM measurement, given that Outputs and Outcomes are relatively unique to the programme and so cannot be easily compared. The main way to ensure VfM is therefore: a) an effective M&E system to track the quality of technical assistance provided (Efficiency) and outcomes (Effectiveness); and b) good systems in place to maximise VfM, drawing on DFID Kenya’s VfM Good Practices Table e.g. procurement (for Economy), considering different methods of delivery and quality assurance (for Efficiency), and maintaining a valid Theory of Change (Effectiveness).

The following VfM measures will be used, together with those that are being used for SOGA:

Economy
Consultancy fees for the TA facility will be benchmarked with other DFID programmes.
Efficiency
We will consider measuring the efficiency of the community engagement element of this programme by using the projected per person cost. It is anticipated that by spending £5.5million we will facilitate engagement with over 630,000 people[63].
[63] Based on estimates from DFID Ghana programme ‘Western Region Coastal Foundation’ where the per person cost is estimated at £6.86.
Cost Effectiveness
Cost per job created will be used for the local content component.

VfM Statement
The recommended funding option of £24 million over five years spent on the five components outlined above is likely to provide Value for Money. This is on the following grounds:
- Options appraisal: The options chosen are properly targeted, manage risk and are realistic for the Kenyan context based on lessons learned from KEIDP and other African extractives programmes.
- Design issues: delivery mechanisms have been selected to maximise efficiency and effectiveness, making best use of existing programmes and partners, and building on lessons from KEIDP.
- Theory of Change: the theory of change is valid, with few assumptions having weak evidence.
- Cost-benefit analysis against the counterfactual: the value of the benefits from increased public spending and conflict prevention are significant with a strong theory of change. There are additional benefits in terms of job creation, community development and female economic empowerment.
- VfM Measures: a reasonable set of measures has been proposed to ensure VfM during project implementation, which will be finalised during project inception.

Theory of Change
The theory of change for the KEIDP programme is show in the diagram below.

# Commercial Case
Flowing from the appraisal, the commercial approach will be driven by value for money (VfM) concerns. There will be diverse implementation mechanisms which will enable DFID to balance risks.
Given that circumstances are rapidly changing in the extractives sector, and the long-term nature of this programme, flexibility has been built into the commercial options to enable DFID adapt to change.
The programme intends to:
1. Engage a management agent to manage the flexible technical assistance facility; the agent will be responsible for implementing the transparency, accountability, stakeholder engagement and part of the institutional strengthening components.
2. Engage with the World Bank Group or a similar institution on high level institutional strengthening.
3. Engage with and liaise closely with the GIZ-implemented Skills for Oil and Gas (SOGA) programme on specific aspects of private sector development and investor engagement.
Details of these commercial options are further discussed below.
## Direct procurement
DFID will directly procure a Managing Agent (MA) through a competitive process to manage, disburse funds and coordinate reporting for the programme, as well as perform due diligence checks on downstream partners. The MA will be expected to embed a dedicated resource, focused on cross cutting coordination and stakeholder management across the whole Extractives sector. This resource will be partly based in DFID office. Given that circumstances are rapidly changing in the sector, and the long-term nature of the programme, the terms of reference for this procurement will be cast flexibly to enable DFID to adapt to any changes.
The MA will be selected through a competitive tender process, which will be limited to pre-qualified providers under the DFID Wealth Framework. The contract will have a break point at the end of an inception phase of six months, at which point DFID will consider whether the contract should be upheld for the remaining period. Where core activities, such as institutional strengthening will be set up through the MA, amendments will be made to the contract, clarifying objectives and governance arrangements.
## How do we expect the market to respond to this opportunity?
The DFID Wealth Framework now includes several firms with recognised capabilities in extractives. Initial contact with several of the companies during the current KEIDP two year cycle has confirmed a general intent to seek partnership with DFID in Kenya should an opportunity arise. Initial conversations with Procurement and Commercial Department (PCD) staff indicate that this is the most appropriate channel for this sourcing. DFID Kenya will therefore work closely with PCD through the Wealth Framework to identify and procure a MA.
DFID Kenya intends to hold at least one supplier event in Kenya as part of the early market engagement; and if possible a further event in the UK to ensure that a competitive range of responses are achieved during the procurement process. This will have the secondary effect of ensuring that multi-component terms of reference addressing points raised in the Appraisal Case are adequately understood by the suppliers before the bidding process is undertaken.
Further details on resources are given below. To specifically support the design of the MA terms of reference, tender process and contract management, 15 to 20% of a programme officer will be allocated, supported by a DFID Kenya Wealth Creation team committee consisting of the SRO, senior programme manager, and the extractives adviser. On the tendering process, the development of the pre-qualification questionnaire (PQQ) and tender evaluation criteria will be assisted by a dedicated PCD officer.
The bid assessment will be based on relevant skills and experience at 65% and finance at 35%. A detailed set of evaluation criteria based on the thematic components will be drawn up after the Business Case approval.
Optimal contract management will be achieved by adopting lessons learnt through the evaluation of MAs to be conducted by the DFID Kenya ART team in the spring of 2015. The MA will be required to operate in accordance with an annual work plan with clear outputs, governed by a Project Steering Group. Periodic outputs will be determined in consultation and agreement with the Steering Group and confirmed by the SRO. The MA is expected to prepare the initial work plan during the inception phase; revisions will be possible on a quarterly basis. The responsibility for delivering outputs and where appropriate poor performance will however rest with the MA. In addition to annual reviews, a midterm review will be conducted two years after inception.
The principal cost driver is likely to be the level of expertise required to address the multi component MA role. While it is expected that competition will drive costs down, DFID Kenya is also in the mid-point of conducting multi-sector benchmarking of consultancy rates in different market segments for these and similar services engaged by DFID in Kenya. It is important to note that the Nairobi market is rapidly transforming and taking similar characteristics to those of a global business hub. As such, contracting and maintaining highly skilled and experienced international and national staff can be expensive. Where feasible, contracts will provide for further benchmarking activities.
Oversight and accountability will be through the management structure of DFID’s Sustainable Economic Development Section as expounded in the Management Case.
Within the overall contract, specific provision will be made to address the different needs of NGOs, national government institutions, and other partners at county or national level, who will implement different project sub-components. Sub components will be implemented through two core instruments: i) a flexible TA facility, and ii) a transparency challenge fund. These will have separate resourcing oversight, risk management and reporting arrangements. The management agent will develop ToRs in consultation with DFID for sourcing services to manage the challenge fund and invite bidders to tender; an oversight board will however be constituted to review and evaluate the bids.
The county engagement platform, stakeholder analysis component, and other components including the Information Centre for Extractives Sector (ICES), and private sector support will similarly be subject to distinct reporting arrangements. These are reflected in the monitoring and evaluation section of the Management Case.
## Strategic partnership approach
It is likely that the programme will be delivered through one or more third party entities, primarily multilaterals e.g. the UN agencies and the World Bank Group (WBG); and possibly through NGOs as well.
A number of multilaterals including the WBG and the UN have developed some expertise and helpful engagement with several institutional partners in Kenya e.g. MoEP in petroleum technical assistance under component one (institutional strengthening). DFID will contribute funds to KEPTAP to support Oil and Gas value chains subject to the outcome of the negotiations with the WBG outlined below.
It is critical for a strategic programme of this nature to undertake due diligence analysis and obtain assurance on third party agencies’ delivery capabilities and capacities. DFID Kenya’s review of MAs, which include Multilaterals, will provide evidence to underpin this assurance. Current evidence is variable amongst the multilaterals and third party agencies DFID is currently working with. Contracting decisions on third parties will mainly be based on their ability to deliver outputs on time and to the agreed standard; and DFID Kenya’s assessment of the risk associated with engaging them.
WBG is currently implementing KEPTAP (whose design has been partly DFID-funded). The project applies well established WBG procurement guidelines reviewed in the recent multilateral aid review (MAR) and also separately reviewed by DFID Kenya. These guidelines provide the general assurance that procurement will be managed to guarantee competition and value for money. The procurement process from sourcing and contracting suppliers varies depending on thresholds, but is equally competitive. Whilst a decision on whether to extend the WBG/KEPTAP has not yet been made, negotiations are underway between DFID and the WBG to establish flexibility on KEPTAP’s operational mode to accommodate DFID funding. The programme is currently implemented through MoEP, but an adjustment would be required to ensure WB aligns the funding channel with DFID Kenya’s guidance on the use of GoK systems for it to be considered an effective route for UK funds.
In the event that an engagement decision is taken not to extend the WBG/KEPTAP relationship, a further component on institutional strengthening and private sector supply chain development will alternatively be implemented via the MA facility.
Finally, a separate DFID project, Skills for Oil and Gas (SOGA) is currently being implemented through a skills sector partnership with GIZ. It is envisaged that should further skills and private sector development activities or coordination activities be assessed as necessary in the life of this programme, a strong option would be to ride on the existing partnership arrangement. This option would have the benefit of shared management costs. It is also possible that a partnership with the Kenya Private Sector Alliance (KEPSA) or similar industry body may be explored as a possible alternative route and a detailed pre-funding assessment will take place at the right point in the programme’s life.
Given that circumstances are rapidly changing in the sector, and the long-term nature of the programme, any shift in the mode of operation would require SRO approval in consultation with the DFID Kenya Head of Office as appropriate.
# Financial Case
The total programme value is £24m. The DFID Wealth Creation team estimates that the MA implementing the transparency, accountability, stakeholder engagement and part of the institutional strengthening components of the programme will incur about 11% of the individual component costs and this has been built into the component estimates. This is based on similar cost experiences within DFID Kenya. It is also anticipated that the overall project budget will cover the MA’s fees, due diligence assessments and any planned audit work. The MA will be expected to operate in accordance with an annual budget plan, which mirrors the annual work plan. Revisions will be possible on a quarterly basis, determined by agreement with the steering group and confirmed by the SRO. The MA will be expected to stay within budget limits.
## Spending profile
The table below summarises the projected spending profile over five years per project element (all figures in millions of pounds sterling).
Implementer	Component		FY1 / 15/16	FY2 / 16/17	FY3 / 17/18	FY4 / 18/19	FY5 / 19/20	Total
Management Agent	Institutional Strengthening		1.00	2.00	2.00	2.00	2.00	9.00	38%
	County Development		0.30	0.50	1.20	1.50	1.50	5.00	21%
	Transparency & Social Accountability	ICES	0.10	0.10	0.10	0.10	0.10	0.50	2%
		Challenge Fund	0.00	0.50	0.50	1.00	1.00	3.00	13%
	Stakeholder Maps		0.10	0.10	0.10	0.10	0.10	0.50	2%
MA Sub Total			1.50	3.20	3.90	4.70	4.70	18.00	75%
WB or other 3rd party agencies (UNs or NGOs)	Local content		1.00	1.00	1.00	1.00	1.00	5.00	21%
DFID Kenya	Coordination, M&E		0.05	0.25	0.25	0.25	0.20	1.00	4%
Grand Total			2.55	4.45	5.15	5.95	5.90	24.00	100%

The above forecast remains an estimate and is subject to change once the MA is in place as well as agreements with the other partners. The Wealth Creation Programme Management team will work closely with identified programme partners, to ensure accurate and timely forecasting. The programme team will review, on a monthly basis, quarterly and annual forecasts to identify any inaccuracies and risks of over, or under-spend. Slippage against the budget will be monitored monthly through a dashboard approach, which will include active risk monitoring and mitigation.
## Costs incurred by implementing partners
The implications for third party costs are set out in the table below.
Partner	Costs
Third party agencies	WB charges a management fee of 5%
MA	Estimated at 11% based on current MA costs within DFID Kenya

DFID Kenya anticipates that for any sub-grantees managed by the MA, their management costs will not be beyond the 7-15%, applied to most of grantees within the Kenya programme.
## Conditionality
The programme does not involve financial aid to governments (both national and county). DFID Kenya has judged that the partnership principles do not apply in the detailed management and monitoring of this programme.
## Affordability
The funding required for this project will be from resource spending, no capital funding is anticipated. Funding is available for FY 15/16 through the current DFID Kenya Operational Planning process. As stated in the strategic case above, DFID Kenya is seeking to commit funding beyond the spending review period, through this programme Business Case. The outcome and impact from the extractives sector, especially from Oil are unlikely to be felt before fifteen years are over; Kenya is currently at the exploration point. An assessment will be done after the five years of the programme to determine whether to continue with the interventions and/or include other components. The programme components have varying life spans.
## Financial and fraud risk assessment
It is assessed that financial and fraud risk is low, since the programme will be largely technical assistance. It is important to flag that the KEPTAP document has flagged procurement risk associated with the KEPTAP project, and rates it as high. Risk mitigation measures included as part of Project activities are : (i) ensuring that qualified procurement specialists proficient in Bank-funded procurement are recruited and retained; (ii) ensuring the procurement decision making is fully covered in the Project Operations Manual and is available/known to staff; (iii) ensuring a clear linkage between Project objectives and the procurement plan through appropriate support to staff, training and tools in preparing and monitoring of the procurement plan. However, in the event that a decision is made to pool funds through KEPTAP, DFID’s contribution would purely be used for technical assistance, hence lowering the fraud risk.
All agreements/contract will specify DFID’s requirement and timelines for reporting fraud or corruption, or any suspicions of fraud or corruption. Any DFID or partner concerns about fraud and corruption will be reported within the required timeframe to the Head of Internal Audit and/or the Counter Fraud and Whistleblowing Unit.
As part of DFID’s procedures on due diligence, any sub-grantees selected by the MA will also undergo an assessment to ensure that their financial management and other systems are sufficiently robust to manage funds and deliver activities and results. The MA selected to implement the project will be responsible for such due diligence on sub-contracted firms.
## Key cost drivers
As indicated in the commercial case, it is likely that the principal cost driver will be the level of expertise required to address the multi-component MA role. DFID Kenya is in the mid-point of conducting a multi-sector benchmarking of process within the different market places for these and similar services managed from Nairobi.
## Monitoring, reporting and accounting for funds
The Head of the Wealth Creation team is ultimately accountable for the expenditure of funds against this Business Case (including decisions on which organisations will be funded). DFID’s ARIES system will be used to monitor report and account for expenditure.
The Wealth Creation Programme Officer will be responsible for producing reports on actual and forecast spend against each of the components on a monthly basis. These reports will be reviewed by the team, including the Head. If any inaccuracies, risks or issues are identified this will trigger a discussion with project partners. Wealth Creation team’s financial management will also contribute into division-wide monthly expenditure monitoring and reporting which is reviewed by the senior management team in DFID Kenya.
Payments to the MA will be based on a reimbursement basis or “just-in-time” basis. Expenditure will be monitored through quarterly financial reports which will be scrutinised by the DFID Wealth Creation team to ensure that value for money principles are being applied.
DFID will require the MA to give annual audited accounts for the funds they disburse during the programme lifetime. This will provide independent assurance that funds are disbursed appropriately.
# Management Case
The management case is built to ensure strong programme oversight and management during implementation, which will be key to ensure quality and effective delivery of all programme components, value for money, as well as continuously incorporating learning into the delivery cycle.
The proposed management structure also reflects the lessons learnt from the MAP Kenya Extractives Industry Development Programme (KEIDP) component:
- The importance of beneficiary buy-in and expectation management - the management structure will ensure that the proposed programme will be accompanied by a stakeholder mechanism that ensures buy-in
- Continued review of the political economy and interest in the sector
## What are the management arrangements for implementing the intervention?
Overall, the programme will be managed by the DFID Kenya Wealth Creation team, under the leadership of the SRO. The principal DFID staff members to be involved in implementation will include:
- Head of Office: formal engagements at Cabinet level and similar high level relationships
- Team Leader (A1) Senior Private Sector Adviser, providing leadership role and high level political advice and engagement. The A1 will assume the Senior Responsible Owner (SRO) role, ensuring that the programme delivers results and value for money, and that risks are appropriately managed. (5%)
- Extractives Adviser (A2) will offer technical leadership and advice in the course of implementation, ensuring that programme components are effectively managed; relationships with stakeholders are developed; risks are minimised. (30%)
- Senior Programme Officer (B1), leading on contract management, reviewing reports, payments, annual and project completion reviews.
- Programme Officer (C1) supporting the Senior Programme Officer in contract management, due diligence and assurance audits, reviewing reports, payments, asset management, annual and project completion reviews.
Given the political economy of the sector and its significance to DFID, the British High Commissioner will be briefed and engaged where required, through the Head of Office or as appropriate.
The sector has the potential to transform the Kenyan economy and tax base, and assist moving Kenya beyond aid. Whilst other donors have an interest in the sector, they are largely focused on single issues; previous attempts to ensure coherence and alignment have been resourced largely through DFID support. To support coordination and fund management role, the MA will be expected to secure a dedicated resource, to work more closely with the DFID team. The resource will focus on cross cutting coordination and stakeholder management across the whole extractives sector; responsible for fund management and engagement/liaison on extractives sector issues with the Counties. Detailed terms of reference will be drafted to reflect these needs. Ideally, this would be in the form of a programme-funded staff working closely with the implementing partners.
## Stakeholder Engagement and Management mechanism
A multi stakeholder Advisory Group, meeting quarterly, and involving representative bodies from the private sector, NGOs and Government, will be formed. Currently these may be a combination of KEPSA, KOGA and/or the Chamber of Mines, for the private sector, all of whom are already engaged in the sector; the national extractives sector NGO coordination body, and/or the NGO Coordination forum, and either one or both of the principal Ministries. The KEPTAP project team will also be represented in the Group. A core role of the overall programme coordinator, appointed by the MA will be to support the advisory group.
Given that the commercial options have been built with some flexibility to enable adaptation to the rapidly changing circumstances in the extractives sector, the management arrangements have also been designed to be flexible to these changes. However it is also envisaged that a formal project Steering Group will be formed consisting of DFID, the MA, GIZ and any other third party agents. A key element of this will be to ensure adequate resources to manage and take decisions on any activities of the flexible fund. The project Steering group will be convened quarterly in parallel to the stakeholder Advisory Group and will be informed by consultation with the Group.
The MA will manage the flexible technical assistance facility and fund which will be responsible for implementing the transparency, accountability, stakeholder engagement and part of the institutional strengthening components.
The current proposed project implementation management arrangements are shown in the chart below.

## How will progress and results be monitored, measured and evaluated?
The programme will commence on approval with an inception phase of approximately nine months which will be conducted in parallel with selected implementation activities including institutional strengthening activities initiated under the MAP KEIDP.
A draft log frame has been established (QUEST 5113450) and this will be finalised and indicators, including at outcome level, amended where appropriate during the inception phase. This will also include establishing data collection requirements including sources and availability of data at baseline and more regularly throughout the programme cycle. Where appropriate, data will be disaggregated e.g. by gender and poverty quintile. The log frame will provide the formal structure for tracking component progress. Results reporting will be aligned to the log frame, which will in turn contribute directly to the overarching Wealth Creation pillar’s results framework. There should be a formal periodic update of the logframe – following on from the inputs from the political economy analysis inputs. The suggested update period of the logframe is annual (but with Political Economy Analysis updates every six months).
The overall responsibility for monitoring the programme progress and risk will rest with the SRO with support from the programme management team. The extractives adviser and the programme coordinator will be responsible for technical oversight and progress; and the B1 Senior Programme Officer will lead the programme team in managing day to day engagement with the MA and other directly engaged partners.
The MA’s operations will be guided by an annual work plan with clear outputs. Periodic outputs will be determined in agreement with the project Steering Group and confirmed by the SRO. An initial programme delivery plan will be prepared during the inception phase. Revisions will be made on a continuous basis based on need; the responsibility for delivering outputs and where appropriate poor performance will continue to rest with the MA. Progress and financial reports will be submitted to DFID by the MA on a quarterly basis; a provision will be made for ad hoc meetings to catch up on progress and institute relevant changes as necessary to deliver the programme effectively. Also, annual reviews and a mid-term review (held two years after inception) will be undertaken.
The MA’s monitoring responsibilities, performance and results management will be clearly set out in the terms of reference. DFID Kenya will assess whether the MA’s systems for monitoring, evaluation and impact measurement are in place, in line with DFID’s increasing priorities for strong monitoring and demonstrating impact on the poor with clear evidence. DFID Kenya will continuously assess impact on the poor, and re-work log frame indicators where they need further work to demonstrate impact on the poor, women and girls. M&E arrangements will make explicit reference to gender, excluded groups, revenues, transparency, local content, conflict and other key factors noted in the Strategic Case.
As discussed in the Commercial Case, the MA’s contract will have a break point at the end of the inception phase, at which point DFID will consider whether the contract should be upheld to the end of the project.
In engaging with third party entities such as multilaterals and NGOs, the monitoring responsibilities will be set out in the Administrative Arrangements/Accountable Grants/MoUs entered; these will be managed directly by DFID Kenya.
It is foreseen that evaluation may be required in the course of the delivery cycle to bridge evidence gaps in the theory of change, as well as to inform decisions over scale up or spin off. Details on this will be shaped during the implementation of the programme.
DFID will rely on programme reviews to evaluate the effectiveness of all the components and progress towards impact. To further strengthen this, real time learning in the course of implementation is proposed. This would be in the form of a learning workshop to feedback implementation lessons, distil and verify monitoring data. The MA will have a function on learning and monitoring beyond DFID’s internal M & E structures. This will require a dedicated resource. It is envisaged that the MA will sub-contract this functionality. This will be clearly spelt out in the terms of reference. Part of the terms of reference for the sub-contractor will include monitoring revenues, transparency indexes and local content monitoring.
There will be a mid-point review two years into the programme to assess progress against overall objectives and to realign the programme if required; stakeholder and beneficiary engagement will underpin this process.
## What are the risks and how will they be managed?
The risk matrix is outlined below. There are no killer risks with both High Probability and High Impact. However, there are three risks with either High Probability Medium Impact or Medium Probability High Impact. These are the following:
1. Global oil and mining commodities market conditions prevent or delay investment decisions.
2. Lack of effective political will to fully engage with the Programme affecting effectiveness and sustainability of project gains
3. Inertia as a result of political challenges and lack of clarity in County roles and responsivities in the devolved governance structure and inter and intra national government coordination
The programme will adopt a strategy of proactive monitoring and mitigation of these risks. DFID’s policy on fraud, bribery and corruption is one of zero tolerance. DFID will ensure that robust due diligence is followed and will only use credible counterparts and service providers for the delivery of individual programmes that will have withstood due diligence assessments covering governance and control, ability to deliver, and financial stability. All agreements will specify DFID’s requirements and timelines for reporting fraud or corruption, or any suspicions of them.
Regular updates will be provided to DFID senior management team and the British High Commission on stakeholders involved and their interests in concerned industries to timely gain crucial insights to reduce adverse effects, including risk of corruption and reputational risk. DFID and the wider UK team at post will continue in an effort to systematically ensure Kenyan legislation, regulation, and procedures contain embedded transparency and accountability measures, particularly around extractives, but also in related business sectors. Examples where we have had some success to date include the inclusion in the Mining Bill of the measures that would enable Kenya to become an EITI compliant country, and a fully online Mining Cadastre system, that reduces significantly the need for contacts between mining licensees and public servants. We will also continue to engage with British and non-British businesses transparently and always adhere to the principles of the DFID Kenya ‘UK Companies as Champions for Development’ initiative.
The programme will actively tackle low institutional capacity and governance systems, especially to improve transparency, accountability and protection of the environment. A dedicated component will intervene at County level, to improve communities’ dialogue with institutions and investors and to set up systems for inclusive planning and grievance mechanisms, thereby ultimately reducing local drivers of conflict. Technical assistance will only be provided through providers pre-qualified in DFID framework agreements or UK Government organisations or multilateral agencies or non-governmental organisations that have a proven and substantial track record in delivering DFID programmes.
For all these reasons, the programme must be viewed as a High Risk.
Risk will be managed by the senior programme officer within the programme delivery plan by means of a risk register updated and discussed with implementing partners on a six-monthly base. However quarterly reports will contain a risk update section that can highlight change of the risk position between formal updates of the risk register. This will be complemented by the output of the stakeholder mapping component of the programme (see the Appraisal Case) which is designed to help steer the programme in reaction to timely insights on changes of the political economy landscape or conflict assessments both at national and local levels.
The risk register will be composed of two matrices:
DFID Kenya Risk Matrix, including:
1. Fragility and conflict (highly relevant for K-EXPRO in target counties like Turkana)
2. Environmental (relevant in K-EXPRO target counties like Turkana)
3. Economic (highly relevant for extractives investment decisions)
4. Fraud and Corruption (relevant for K-EXPRO institutional strengthening and county engagement components)
5. Delivery (highly relevant for K-EXPRO as a complex multi-component programme with some of the impact expected on a long term horizon)
6. Partners’ capacity (relevant for K-EXPRO as it requires specialist capabilities)
7. Human Resources (relevant for K-EXPRO as its political sensitivity requires close DFID monitoring and steering)
Extractive-specific risk matrix
Risk	Mitigation measures	Probability (residual)	Impact (residual)	Direction of travel[64]	Explanation/ / action points	Owner
Global oil and mining commodities market conditions prevent or delay investment decisions	Keep up to date with the industry and adopt a flexible approach to the rapidly changing context	Medium	High		Probability is medium and risk high in the short term, mainly due to reduction of investors exploration budgets. However current analysis consider that international prices and investors’ interests in Kenya will adjust well within the life of the programme
Delayed enactment of relevant laws, regulations and administrative provisions due to procedural and bureaucratic factors beyond the Program’s control.	Continued strong engagement with institutional counterparts, offering provision of key technical assistance to unblock bottlenecks. / Build flexibility into program planning.	Medium	Low		The turnaround time for laws in Kenya is relatively long. However global market conditions make the current momentum of the legislative process adequate compared with the likely time of investment decisions.
Lack of effective political will to fully engage with the Programme affecting effectiveness and sustainability of project gains	Using existing DFID contacts in government, as well as linking individual component programme objectives to the national/county development agendas / Negotiate with the respective parties; understand the motivations for the vested interest and identify an appropriate interlocutor to address the issue.	High	Medium		This is possibly due to vested interests and elite networks push back on reform. All components of the programmes should be strategically steered by the in-built regular stakeholder mapping to support reform champions and expose spoilers.
Inertia as a result of political challenges and lack of clarity in County roles and responsivities in the devolved governance structure and inter and intra national government coordination	Build in flexibility in planning activities to allow for greater scope of implementation and ensure county representation / Seek to build increased county and central administration understanding of impact of changes / Provide strategic assistance for national policy coordination efforts and to link central and County authorities	High	Medium		This is possibly due to vested interests and elite networks push back on reform or will to rump up their local power base. All components of the programmes should be strategically steered by the in-built regular stakeholder mapping to support reform champions and expose spoilers.
High, unrealistic expectations due to incorrect communication on levels of project funding may affect relations with the respective County governments and their communities and hamper effective implementation	Continuous engagement and communication with the respective County governments and their community(ies); feedback mechanisms providing evidence that community priorities are acted upon and Transparency of data collection	Medium	Medium		Lessons learned from DFID Kenya predecessor programme allowed adjusting the management structure to highly reduce probability and impact of this risk
Less than desirable coordination among the program components and lack of correct political steer due to inadequate capacity of implementing partners	In-built DFID programme monitoring and coordination staff	Low	Low		Lessons learned from DFID Kenya predecessor programme allowed adjusting the management structure to highly reduce probability and impact of this risk
Fluidity in the oil and gas sector is which may affect the mapping of the supply and demand of goods and services	Keep up to date with the industry and adopt a flexible approach to the rapidly changing context	Medium	Low
Inadequate targeting of support to beneficiaries result in increasing inequalities	Close linkages between dialogue feedback, regional planning data and targeted interventions, especially regarding matching funds for local government and sector development activities	Medium	Medium
Jobs created during the ‘boom’ associated with the oil and gas investments are short-term and do not provide a sustained route to grow incomes and opportunities	By focusing the programme’s activities on medium-low grade skills, rather than highly technical industry-specific skills, the intention is to create a core of local people with relevant, transferable skills who can work in or outside of the oil and gas sector.	Low	Medium
[64] Risk increasing, decreasing or staying the same compared with previous period

# Endnotes and references