Annual Review - Summary Sheet

Title: Ethiopia Productive Safety Net Programme Phase 4 (PSNP 4)
Programme Value: £276 million (2015-2020)		Review Date: 21 November - 2 December 2016
Programme Code: 204290	Start Date: 15.12.14 (design) / 7.7.15 (implementation)	End Date: / July 2020

Summary of Programme Performance
Year	2015	2016	2017	2018	2019	2020
Programme Score	A	A
Risk Rating	medium	major

This is the second annual review (AR) of the Productive Safety Net Programme – Phase 4 (PSNP4), which covers the first full year of implementation, GoE financial year 2015/2016 (July to June). The first DFID AR covered programme design and mobilisation.

Summary of progress and lessons learnt since last review

Overall progress towards delivering PSNP4’s outputs is satisfactory i.e. has met expectation.

In the first full year of implementation, PSNP4 has scaled up to target and deliver cash or food transfers to 7.99m beneficiaries in 2016, from 5.16m clients in 2015, under PSNP3. Of these 1.11m receive unconditional transfers (permanent direct support (PDS) beneficiaries) and 6.88m benefit from transfers paid on the basis of public works (PW). Despite some delays, on the whole transfers were delivered in a timely fashion. PSNP4 has operated in a difficult environment caused by the largest drought in recent history. The programme has shown flexibility during the drought through local level adaptions e.g. waiving the public works requirement, changing PW projects to water harvesting ones, shifts from food to cash in Somali Region due to delays in food procurement and dispatch and introducing arrangements for flexible repayment of loans for livelihoods clients.

The foundations for more effective social protection systems have begun to be laid during the past year. These include the engagement of new partners, such as the Ministry of Labour and Social Affairs (MoLSA), in implementing PSNP4 (PDS caseload is expected to transition to MoLSA in 206/17 as capacity is built). There has been good progress towards developing an integrated social protection Management Information System (MIS) under MoLSA’s leadership, and a service provider is currently being selected to design the PSNP MIS. PSNP has piloted e-payment mechanisms in 20 woredas in the first year and plans to expand to reach 68 woredas in 2016/17. It has also piloted social accountability mechanisms to strengthen grievance redress in the programme which GoE plans to expand.

However, PSNP has also faced challenges which undermine the operationalisation of its vision to establish a scalable rural safety net. The first of these is the inefficiencies in the food management system which has led to delays in food distribution to beneficiaries, as a result of parallel systems emerging for relief food and PSNP. This has been exacerbated by a lack of systems integration between the humanitarian system and PSNP.

Performance in Afar and Somali regions is a concern. The impact evaluation baseline conducted in January 2016 shows that targeting in Afar and Somali regions is not effective in identifying the poorest (despite some improvement in Somali) and implementation in both regions in 2015/2016 has faced challenges (improvements in Somali not withstanding).

Finally PSNP4’s significant financing gap begins to bite in 2017/18 and will require either increased resourcing from GoE or ‘right sizing’ the programme to meet the available resource envelope.

Summary of recommendations for the next year

- Continuum of response: it will be a priority to demonstrate progress towards a scalable rural safety net in 2016/2017 and the vision of a continuum of response. This will require addressing the political and institutional challenges associated with creation of a parallel system for PSNP and humanitarian food management.
- Financing: PSNP4 faces a significant financing gap from 2017/18, which requires resolution. If no additional GoE financing is mobilised the programme will need to be ‘right sized’ to fit with available resources. A clear decision is needed in the next 3 months to allow smooth planning for the next financial year.
- Lowlands performance: Targeting has not improved in the lowland region of Afar and only marginally improved in Somali, impacting programme performance. An action plan to address performance challenges in these two regions should be developed immediately. As part of this, it is recommended that the planned review of targeting is expedited, to include qualitative study of reasons for targeting challenges in these two lowland regions, including perceptions of fairness and factors related to social organisation and developing options which draw on lessons from similar contexts.
- Monitoring: The overall PSNP4 programme logframe will be revised over the next quarter to ensure that indicators are measureable and milestones and targets are realistic. DFID should revise its programme logframe accordingly, selecting a sub set of indicators to support DFID monitoring purposes, whilst ensuring that milestones and targets are realistic.
- Reporting: Reporting should better accommodate gender and social development (nutrition) aspects of the programme.
- Audit: under PSNP 4 MoFEC should ensure that it follows up on commodity and procurement audits as it does financial audits, ensuring transparency and accountability of expenditures

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	204290	DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-204290/documents

PSNP4 is DFID’s fourth phase of support to Ethiopia’s flagship safety net programme. PSNP originated in a 2005 consensus between Government of Ethiopia (GoE) and donors that successive annual emergency food aid appeals were not a suitable or effective way of dealing with chronic hunger.

PSNP4 will directly deliver a range of results in poverty reduction, food security, climate change mitigation and adaptation and improved outcomes for women and girls. It is a central part of DFID Ethiopia’s Business Plan (2015-2020), contributing to DFID’s Single Departmental Plan strategic objectives on strengthening resilience and response to crises and tackling extreme poverty and helping the world’s most vulnerable. Our investment in PSNP contributes to DFID’s overall results on nutrition.

The programme aims to support an impact of “Resilience to shocks and livelihoods enhanced and food security and nutrition improved for rural households vulnerable to food insecurity”. The objective of PSNP4 is to deliver “enhanced participation in improved rural safety net, livelihoods and nutrition services by food insecure female/male headed households”.

PSNP 4 has four main outputs:
1. Strengthened systems (targeting, management information system, disaster risk management systems, social accountability, planning, coordination and governance)
2. Appropriate, timely and accessible transfers to beneficiaries
3. Sustainable community assets and enhanced access to social services
4. Livelihoods opportunities facilitated (crop and livestock, off farm, employment)

Under PSNP 4 DFID contributes £276m to a total programme cost estimated at £2.35bn. PSNP is supported by 11 donors, with an increasing GoE financial and in kind contribution. A Donor Coordination Team (DCT) supports coordination and programme management and leads liaison between Ministry of Agriculture and Natural Resources (MoANR) and development partners (DPs).

Since the design of PSNP4, the food security situation in Ethiopia has declined significantly as a result of the worst drought in 40 years. The combination of failed rains and El Niño-induced drought in 2015/16 had dramatic impacts on over 18 million people across east and southern Ethiopia. The drought response, coupled with institutional changes in the Ministerial responsibilities for components of PSNP4 implementation since late 2015, has stretched GoE capacity.

Despite the vision of PSNP4 to become the vehicle through which the Government and its partners will respond to the food assistance needs created by such shocks, this drought proved too significant and too soon under the new programme to realize a scalable social protection system. From January, 10.2 million people facing transitory food insecurity began receiving “relief” food aid distributions through the newly formed National Disaster Risk Management Commission (NDRMC), which reports directly to the Prime Minister. Additionally, 8 million clients enrolled in PSNP4 began receiving food and/or cash transfers through the Food Security Coordination Directorate (FSCD) of the Ministry of Agriculture and Natural Resources (MoANR).

As a result of the increased need, DFID brought forward £25m of financing from outer years to contribute to the federal contingency budget line and World Bank allocated an additional $100m from the Rapid Response Fund. There is a significant programme funding gap, which bites from July 2017. Dialogue is underway to decide whether this gap can be met from GoE resources, or whether PSNP will need to be ‘right sized’, so that the programme scope fits the available financing envelope (this could mean reducing the total number of beneficiaries, reducing the transfer size, or reducing the duration of the transfer).

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

This second annual review takes place after one complete year of implementation of PSNP4 (Ethiopian fiscal year 2015/16). The programme has made reasonable progress towards its outcome of “enhanced participation in improved rural safety net, livelihoods and nutrition services by food insecure female/male headed households” at the end of the first year. Participation by food insecure households in an improved rural safety net has increased.

Progress towards the outcome is measured through indicators on coverage, the number of years clients receive transfers, food insecurity, and livelihood diversification. PSNP has re-targeted and expanded to reach 7.99m clients in 2015/16 (comprising 4.47m previously enrolled clients and 3.52m new clients who were previously receiving humanitarian relief food assistance), across 318 districts, exceeding expectation. Of these clients, approximately 1.11m benefit from unconditional cash transfers (permanent direct support paid to clients who are disabled, older people or female headed households i.e. considered to have no labour capacity) and 51% are women. New provisions on gender and nutrition have been included in PSNP4 and foundations for their implementation have been laid but require further work across partners.

However, the institutional split between the Food Security Coordination Directorate of MoANR and the newly created NDRMC has resulted in inefficiencies in delivering food transfers to the most needy during a drought year. It has undermined the vision of PSNP4 as a scalable rural safety net, ensuring a continuum of response for food insecure households.

Performance in the pastoral lowland areas of Afar and Somali regions requires immediate attention. The Impact Evaluation Baseline (2016) shows a need to improve targeting of the poorest in both regions. In addition, governance challenges with programme delivery in Afar have not been successfully resolved and both regions have faced continued challenges in implementation. This may require a re-appraisal of programme design in these regions in order to deliver on the ambitions of the outcome.

Overall output score and description

Despite the challenges set out above, overall performance against the programme outputs in the first year has been satisfactory. Overall, performance against the outputs is scored an A – met expectation.

Table 1: Summary of output performance:

Output	Output Description	Impact Weight (%)	Output Performance	Risk
1	Prioritised instruments and tools in place to support an effective system for Social Protection and Disaster Risk Management	10	A	Moderate
2	Appropriate, timely and accessible transfers received by male and female clients	40	A	Moderate
3	Sustainable community assets built up and access to social services enhanced	25	B	Major
4	Clients’ livelihood opportunities facilitated through three pathways: crop and livestock, off-farm income generation, and employment	15	B	Major
5	Effective management and operational processes in place to manage the programme	10	B	Moderate

Key lessons

It is increasingly apparent that the existing institutional structure requires revision to bring PSNP and humanitarian assistance under the same management system in order to deliver a continuum of response. GoE has reiterated its commitment to the vision of a scalable safety net in a series of high level discussions over the past year. However, who or which institution will drive the delivery of this vision remains unclear.

Since its launch PSNP 4 has faced a financing gap. The assumption at design that increased donor finance would be forthcoming was overly optimistic, in light of the global aid context. There is, therefore, an urgent requirement to either clarify additional financing from GoE, or to re-design or ‘right size’ the programme according to a realistic assessment of available resources going forward.

Key actions
- Urgently clarify whether additional GoE financing is available to bridge the financing gap or whether programme ‘right-sizing’ needs to take place before the new annual planning cycle, which begins in February 2017.
- Development partners to raise the issue of GoE’s commitment in practice to a scalable rural safety net at the most senior levels.
- Revision of design, including approach to targeting, in pastoral lowland regions of Afar and Somali on the basis of an action plan to be agreed between development partners, Ministry of Agriculture, Ministry of Finance and Economic Cooperation and the Regional Governments.

Has the logframe been updated since the last review?

Yes. The logframe outputs and indicators used during the First Annual Review were selected to measure progress against the design and mobilisation phase of PSNP4. This review has assessed progress against PSNP4’s logframe (included in the business case) but for DFID management purposes a selection of output level indicators have been prioritised (from 49 to 25 indicators). The Impact, Outcome, and Output level statements have not been changed.

## C: DETAILED OUTPUT SCORING

Output Title	Prioritised instruments and tools in place to support an effective system for Social Protection and Disaster Risk Management
Output number per LF		1	Output Score	A
Risk:		Moderate	Impact weighting (%):	10%
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	Y

Indicator(s)	Milestones	Progress
1.1 Percentage of safety net woredas where MIS and single registry are operational	0% core modules ready for data entry in pilot woredas	Met expectation: A / Concept note and roadmap on integrated SP MIS (including single registry) finalised by Systems Technical Committee. MIS guidelines finalised and PSNP MIS development procurement underway.
	0% (MIS)
1.2 Percentage of kebeles where poverty index is used to complement community targeting	Indices developed	Moderately did not meet expectation: B / ToRs for an interim PMT analysis under development. This will inform a GoE decision on whether it is feasible and desirable to complement community targeting with a poverty index, given current good performance of targeting in highland regions.
1.3 Percentage of woredas providing regular (12 months/ year) EW monitoring data to the regions	50%	No data collected on this indicator. / This indicator will be reviewed as part of logframe revision.
1.4 Percentage of clients and non-clients who are aware of programme objectives and entitlements (disaggregate by sex, and by permanent DS and other clients)	No milestones for 2015/16	Met expectation: A / The household impact survey confirms good programme awareness (in highlands [81%], lowlands [94%], across women and men and DS and PW clients). / Qualitative data indicates mixed awareness of entitlements, with good understanding amongst kebele officials but lower awareness amongst PDS clients.
1.5 Number of safety net kebeles implementing social accountability tools	30	Exceeded expectation: A+ / Social accountability tools (citizen report cards and community scorecards) extended to 19 woredas (from 4) across 6 regions, under bridging phase of Ethiopia Social Accountability Programme
1.6 Capacity development indicators which are expected to be developed after the development of CD strategy	TBD	Met expectation: A / HR assessment completed. Capacity development strategy completed Sep 2015 and shared with regions in June 2016. Indicators still to be agreed.

Key Points

Output 1 seeks to deliver improved tools to support the implementation of PSNP4 and to also provide the operational underpinnings for the wider, emerging social protection system (which will be delivered across different implementing Ministries). The systems agenda has overall progressed well through 2015/2016 and progress towards the output has met expectation.

Indicator 1.1 There has been good progress toward developing an integrated Management Information System (MIS) and a social protection (SP) single registry. SP MIS Guidelines have been completed under MoLSA’s leadership, with participation from MoANR FSCD, other relevant ministries and DPs and wide consultation, culminating in a multi-stakeholder workshop in early September. A concept note on Integrated Social Protection MIS (comprising programme MISs, a national household registry and central MIS or single registry) has also been finalised. This was completed, with technical assistance provided by UNICEF, and overseen by the systems technical committee (TC). With PSNP DCT technical oversight, MoLSA has selected a firm to develop the PSNP Programme MIS which will begin MIS development in 2017, to be fully operational by 2020.

Indicator 1.2 The design of PSNP4 commits to implement poverty indices (or some form of proxy means testing, PMT) to complement community targeting. Further work is needed to understand what is reasonable and feasible within the Ethiopian context and so this has not yet been developed. The Impact Evaluation Baseline 2016 shows that community targeting is accurate in the highlands but needs significant improvement in the lowlands (Somali and Afar). The Integrated SP MIS Concept Note recommends that the systems TC, chaired by MoLSA, support GoE in deciding whether to proceed with PMT or continue with community based targeting, with some form of kebele ranking. This will be a priority for the systems TC and the DCT over the 2016/17 financial year.

PSNP Effectively Targets the Poorest Households in the Highland Regions but not in the Lowland Regions
The Baseline Impact Evaluation (2016) assessed the characteristics of PDS and PW households in the highland and lowland regions and compared their assets, landholdings, and education to non-PSNP households.

In the highlands (71% of PSNP beneficiaries):
- The median PDS household has assets worth 34% of what non-PSNP households own
- The median PW household has assets worth 60% of what non-PSNP households own
- Landholdings are similar in size but PSNP beneficiaries have less productive assets, less consumer durables and less livestock.
In highland regions the probability of a destitute household being selected for PSNP is high (e.g.. 79% in Tigray), sharply declining for better off and rich households (15%).

In the lowland regions of Afar and Somali:
The median DS household has assets worth 83% (Afar) and 80% (Somali) of what non-PSNP households own
The median PW household has assets worth 73% (Afar) and 125% (Somali) of what non-PSNP households own, meaning Somali PW households are wealthier in asset holdings than a non-PSNP hh.
A poor household in Afar has a 63% probability of being selected, this barely changes with wealth, as a rich household has more or less the same probability of being selected (60%). The pattern is similar in Somali, with little difference in probability of selection across destitute, poor, median and better off households.

Indicator 1.4 Client’s awareness of programme objectives and entitlements was not expected to be assessed at this point since survey data will be available next year. Nonetheless, the impact evaluation baseline survey (2016) indicates high levels of programme awareness amongst clients, both public works and direct support, and for male and female headed households in both highland and lowland areas. The qualitative component of the baseline suggests that awareness of the changes in programme design and programme entitlements amongst kebele officials is good, but is low amongst PDS clients (only one of 12 focus groups knew that they are now entitled to 12 months of transfers). On transfer timeliness and amounts of food/cash which should be received, clients appeared to be more aware of their entitlements. A refreshed communication strategy, currently under design, will help to improve client’s understanding of their entitlements.
Meeting the needs of those most in need
Seven PSNP clients from the market area of Libso kebele in Habru Woreda, North Wollo, gather around and take a seat to discuss their experiences with the programme. They are a group of mostly elderly women, but also include a younger woman and man who are disabled. All of them understand clearly why they have been selected to receive transfers without a labour requirement, or Permanent Direct Support (PDS) – they are the very poorest in their communities and cannot manage physical labour.

A new PDS client explains why she was targeted this year, but not previously: “I used to have my husband and children around me, but now he has died and my children are gone. I am alone and in need of assistance.” The group describes their impoverished situation and how they use their transfer entirely to purchase food. They are not aware that they are now entitled to 12 months of continuous support under PSNP4. They received 6 transfers earlier in the year, but are not aware when the next payment might come.

Habru woreda has provided transfers to PSNP clients in cash for the last 6 years, but in 2016 they piloted an e-payment modality using MBirr in partnership with Axi Bank. Instead of physical cash being distributed to each of the 35 kebeles on a monthly basis, beneficiaries now travel to one of six branch locations in the woreda to receive their payment. While the distance they travel is further, PDS beneficiaries feel there is more flexibility in the new system in the event that they miss their payment day due to illness or other personal reasons. Previously, clients would have had to travel to the woreda capital and making alternative payment arrangements was difficult and time consuming. While there is a set day to receive their e-payments, if clients come on another day they can still easily access their payment through their MBirr transfer account. PDS clients also can assign someone else to receive their payment for them, with the signature of the kebele administrator, which further provides them increased flexibility and access.

Indicator 1.5 Social Accountability under PSNP4 has been pursued through the Ethiopia Social Accountability Programme (ESAP), which uses citizen report cards and community score cards to strengthen accountability between citizens, communities and local government. Under the current EASP2 bridging phase (April 2016-December 2017 whilst ESAP3 is being designed), the number of PSNP woredas has expanded from 4 to 19, in 3 to 6 regions, to also include the lowland regions (Afar, Somali, Tigray, SNNP, Oromiya and Amhara). Social accountability tools will now be applied to public works and livelihoods activities in addition to targeting and transfers. In 2015 a Roving Appeals Audit was conducted to review the operation of the Kebele Appeals Committees (KACs). In response to the findings a Grievance Redress Manual has been developed to strengthen KAC’s performance.

Indicator 1.6 The Capacity Development Strategy, covering human and physical resources, was completed in September 2015, but was only formally shared by FSCD with the regions and federal implementing agencies in June 2016. In October 2016, technical proposals for the establishment of the Capacity Development Facility (CDF) were reviewed and the final firm has now been contracted. A Human Resources Assessment was completed in 2016, which identified gaps and needs for the CDF. The CDF will provide leadership training, Federal Technical Advisors (TAs) and Regional CD experts to MoANR. Indicators to measure capacity development will be agreed under the planned logframe review in 2017.

Summary of responses to issues raised in previous annual reviews (where relevant)

Despite efforts to coordinate, there has been unnecessary duplication and inefficiency in delivery between PSNP and relief response. This has been exacerbated by the institutional split, and separate accountability lines for NDRMC and FSCD. Under DFID’s 6 month tenureship of the donor chair role between January-July 2016, significant efforts were made to improve coordination and move closer towards the vision of continuum of response. To achieve this will require political commitment at the highest level and practical operational adjustments.

Recommendations

- PSNP4’s ambition is to strengthen the rural safety net through better linkages with a wider range of implementing partners. At regional level this will require improved coordination across stakeholders for implementation at woreda level and ensuring appropriate stakeholders from the range of implementing partners participate in trainings.
- Timely preparation of annual plan to enable budget release and avoid delays in implementing activities, working across multiple stakeholders.
- A joint, structured planning process should be realised for NDRMC and PSNP, to ensure timely submission and approval of annual work plans and budget transfers.
- Targeting has not improved in the lowland region of Afar and only marginally improved in Somali. It is recommended that the planned review of targeting is expedited, to include qualitative study of reasons for targeting challenges in these two lowland regions, including perceptions of fairness, and factors related to social organisation and developing options which draw on lessons from similar contexts.
- The logframe should be revised to ensure that indicators are meaningful and data is available to measure progress. PSNP’s M and E plan should be aligned with a revised logframe, ensuring that planning and reporting templates align with the logframe to facilitate reporting.

Output Title	Appropriate, timely and accessible transfers received by male and female clients
Output number per LF		2	Output Score	A
Risk:		Moderate	Impact weighting (%):	40%
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	Y

Indicator(s)	Milestones	Progress
2.1 Percentage of clients paid within the agreed timeframe (20 days for cash and 30 days for food)	60%	Moderately did not meet expectation: B / Met expectation in highlands. Highlands: 61% cash, 53% food / Below expectation in lowlands. / Lowlands: 18% food
2.2 Percentage of clients reporting that they receive cash or food transfers at a place less than 3 hours walking from their home – disaggregated by sex	HL no milestone this year	Met expectation: A / No national data - this will be measured through 2017 survey. / Qualitative component of impact evaluation shows that in sampled woredas expectation met: Amhara 1-2.5 hours; Oromiya 1-2 hours; SNNPR 40 minutes.
	LL no milestone this year	Met expectation: A / No national data / In woredas sampled in qualitative component expectation largely met: Afar 30 minutes – 2.5 hours; Somali: 45 minutes – 4 hours.
2.3 % transfers received that have a value of at least 15 kg of cereals and 4 kg of pulses per person per month	50%	Moderately exceeded expectation: A+ / 93% according to EFY2008 wage rate study. This is currently being revised on the request of some zonal administrations.
2.4 Percentage of clients receiving federal contingency budget resources within 60 days of identification of needs	50%	Did not meet expectation: C / Release of federal contingency budget took more than 60 days.

Key Points

Overall progress towards output 2 “appropriate, timely and accessible transfers received by male and female clients” has met expectation, though there have been significant challenges with food distribution this year as a result of issues outside PSNP’s control. In 2015/16 7.99m clients received PSNP cash, food, or a mix of cash and food transfers. Of these clients, approximately 1.13m benefited from unconditional transfers (permanent direct support) with the remainder benefiting from transfers in exchange for public works. 51% of beneficiaries were women.

Indicator 2.1 Transfer timeliness has met expectation in the highland regions (which account for 71% beneficiaries) but not in the lowland regions. Despite challenges, transfers were more timely in 2015/16 than in earlier years (with the exception of 2014/2015, which was PSNP’s best performing year). This is illustrated in the two figures below, which compare cash and food transfer completions against the ideal between years. Following initial delays, by May 2016, cash transfers were ahead of schedule with nearly 100% of transfers disbursed by the end of July.

The figure below, illustrating food transfer rates illustrates delays faced at different points throughout the transfer season, compared with the “ideal”. The first transfers were behind schedule during the first month of the programme, as the humanitarian relief system completed an additional “bridging round” of transfers to PSNP clients in December 2015 and January 2016. Food import delays also caused inertia in May, with final completion of delayed transfers across July, August, and September.

Disbursement of funds from the federal level to regions was completed in a timely manner in 2015/16. 99% of cash transfers and 85% planned food transfers reached clients by end September 2016 (FIC report, October 2016). Delays in beneficiaries receiving food transfers were due to logistical bottlenecks in the wider food management system (food held in port in Djibouti, competition with relief food for warehouse space and transport services, and staff shortages), exacerbated by the split between MoANR FSCD and NDRMC. As a result of these significant constraints, Somali region shifted to make increased use of cash transfers mid-year.
Timely Cash Transfers in SNNP (Southern Nations, Nationalities and Peoples Region)
In order to ensure that cash transfers reached beneficiaries within the 20 day target, BoFEC and BoANR officials in SNNP region prepared a payment schedule. Deadlines for payroll submission and payment requests were set and adhered to, with the ‘primacy of transfers’ message internalised across the woredas. Payment schedules were posted at kebele buildings and in 2016, SNNP averaged 16 days to distribute cash transfers. By contrast, food transfers for SNNP’s pastoral woredas at times took between 60-81 days to process. Cash is more timely than food, particularly when proper planning and scheduling is practiced.

Indicator 2.2 Accessibility to transfer sites will be measured next year on the basis of quantitative survey data collected through the impact evaluation. In the 20 woredas sampled for the qualitative component, accessibility to payment sites was reported to have improved in all regions and largely met the benchmark of under 3 hours walking.

The current e-payment pilot operating in 20 woredas in Amhara, Oromia, Tigray and SNNP (DFID’s centrally managed Hi Fi project supports the evaluation) has much to offer on improving transfer timeliness and accessibility through use of community based agents. An evaluation of the pilot is underway and is generating useful insights in how to improve performance, including accessibility. In 2009 MoFEC and the regions plan to scale up to 64 woredas, including 4 in Somali.

Indicator 2.3 The % of transfers received that have a value of at least 15kg of cereals and 4 kg of pulses per person per month has been difficult to measure through administrative data systems but will be measured through data sets collected for impact evaluation. Whilst the overall value of transfers has increased and transfer values have been standardised, there are indications from field visits that larger households are less likely to receive their full entitlement, as woreda and kebele officials seek to ration transfers in order to reach more beneficiary households.

Indicator 2.4 The federal contingency budget has been used to provide additional extended support to the core client list of PSNP beyond the regular six transfer rounds. Additional beneficiaries in need of assistance as a result of the drought have been covered under the Humanitarian Requirements Document (HRD), revised in August 2016. A total of 100,957,721 Birr was transferred to the regions from the federal contingency budget in 2015/16, and utilised by woredas in July. Data on timeliness is not available, as triggers to release funds once needs are identified have not been clarified.

Contingency Budget Responds to Local Needs
The Woreda Contingency Budget, equalling 5% of the annual budget, was released alongside Habru Woreda’s first quarter payment in early EFY 2009. The timing was critical, as the woreda struggled to meet the needs of families who had been affected by flooding during the summer kiremt rains. The equivalent of 5 days wages were transferred to 1,038 clients living in 5 affected kebeles. Female headed households and those who had lost their crops and/or livestock in the floods were targeted. Locally available contingency budgets allow local administrators to use funds to meet the acute and specific needs in their districts quickly, as also evidenced in other areas during the drought.

In addition, woredas utilised 305,736,854 Birr woreda contingency budget line to meet local level needs. This included providing additional transfers to additional clients and meeting ad-hoc beneficiary needs. Programme reporting on use of contingency budgets should be improved, to better understand how and for whom woredas use the contingency budget line.

Summary of responses to issues raised in previous annual reviews
Timeliness of payments has been raised in previous annual reviews. Performance was excellent in 2014/15 but it has declined slightly in 2015/16, in large part due to issues largely outside PSNP’s control: significant delays in clearing food imports at the Port of Djibouti and additional pressures faced by GoE during the drought response.

The significant deterioration in food security over the past year has put considerable pressure on the programme and on transfer timeliness, particularly food. As a result of challenges in procurement and distribution of food items, beneficiaries in Somali and Afar regions in particular have seen delays in transfers, with full transfer rounds being completed in November.

Previously concerns about the value of cash transfers were raised. A variable wage rate study was completed and informed the adjustment of wage rates for 2015/16 transfers, reflecting differences in market prices by zone, thus addressing this issue. In advance of 2016/17 transfers, an assessment team is currently considering whether revisions are required in the 15 zones and Dire Dawa, which raised issues related to 2015/16 rates.

Recommendations
- Delays in paying PDS beneficiaries have been incurred in the first quarter of 2016/17 financial year, whilst beneficiary lists have been ‘re-certified’. It is recommended that this is avoided in future financial years by either rolling over beneficiary lists for example, or completing re-certification of PDS clients before the start of the new financial year.
- To address the in-efficiencies in food transfers and move towards a continuum of response, DFID should advocate for the split between FSCD and NDRMC to be reconsidered. To deliver the vision of a scalable safety net will require one system, based on one analysis of needs at woreda level, one beneficiary list, one payroll, and one monitoring and audit system.
- To improve the monitoring of the timely receipt of transfers by beneficiaries, FSCD should work with the regions to improve reporting templates (e.g. additional analysis of transfer rates, cross referencing with Commodity Allocation Tracking System data) and processes and establish a Regional Information Centre in Afar.
- The planned evaluation of drought response should inform the preparation of the delayed Continuum of Response Guidance, ensuring that lessons learned are reflected in the new guidance.
- Woreda reporting on use of woreda level contingency budgets should be improved, and the reporting format adjusted to include a breakdown of how woredas used contingency budgets.

Output Title	Sustainable community assets built up and access to social services enhanced
Output number per LF		3	Output Score	B
Risk:		Major	Impact weighting (%):	25%
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	Y

Indicator(s)	Milestones	Progress
3.1 % public works planned and implemented following the GoE's CBPWD Guidelines or Rangeland Management Guidelines integrated with DRR/Adaptation and mitigation plan	Highland 75% / Lowland 50%	Moderately exceeded expectation: A+ / 100% / 100%
3.2 Total closed area subject to enhanced management for climate adaptation	37,500 ha	Moderately exceeded expectation: A+ / Total closed area 236,884 ha
3.3 Percentage of clients that feel PW sub-projects reflect their needs - disaggregated by sex	82%	No data / Pending PW Impact Assessment and wider Impact Evaluation data
3.4 Percentage of PW plans prepared following GSD considerations	76% highland / 65% lowland	Limited data / No data available since public works review has not taken place. 100% projects have been screened for ESMF compliance in highland areas and 71% in pastoral regions.
3.5 Percentage of clients who receive community-based nutrition counselling services	50%	No data has been collected on this indicator
3.6 Percentage of pregnant women transitioning to temporary direct support before 4 months on the basis of health facility referral [amongst women who reach the 4th month of pregnancy during the public works period]	No milestone	Limited data / Based on small sample of pregnant women able to report on this indicator, 40% pregnant women transferred to temporary DS on average at 5.4 months pregnancy in highland areas. No data for lowlands.

Key Points
Overall progress towards the output “Sustainable community assets built up and access to social services enhanced” is assessed as moderately not meeting expectations. There is limited data available to measure the indicator milestones at this point of the programme. This is for two reasons: some of the data will be measured through the impact evaluation (and data will be collected in January 2018) and some of the data should have been measured through bi-annual Public Works Reviews. These have been delayed due to a disputed winning bidder. The procurement has been relaunched for a multi-year contract, with selection anticipated by May 2017. Gender and social development aspects of this output are not well captured in existing reporting. Nonetheless significant numbers of public works projects have been delivered, provisions for pregnant and lactating women are being implemented and community based nutrition counselling services have been piloted.

Indicator 3.1 The public works coordination unit delivered training on GIS/GPS, watershed planning and water harvesting to 42 federal, regional and woreda staff. 78 regional staff received updated training on planning community based public works. GoE’s Public Works Guidelines were used to plan and implement 35,774 public works projects, covering 10,706 watersheds and 756 pastoral kebeles. This has enabled the conservation of 244,000 ha of degraded land. In addition through PSNP’s public works 6,755 km roads have been constructed or rehabilitated and 7,245 water projects completed. Overall the quality of these projects is good – with 82% projects meeting the technical standard in highlands and 72% in lowlands (Joint Review and Implementation Support Mission (JRIS) November 2016 presentation). The pastoral workload is reduced by 40%, with an expectation of 5 labour days per month per highland male client and 3 per pastoral male. Women public works clients workload is reduced by 50%.

Assets built by PSNP clients improve crop productivity

Neesharag Alim has 0.25ha of land to support herself and her 10 year old daughter in Libso kebele of Habru Woreda in North Wollo, Amhara Region. In 2015, her family and 306 other community members benefited from a PSNP Public Works project which converted a traditional mud canal into a concrete lined 3km-long irrigation canal. The quality and quantity of water reaching her small farm plot is now sufficient to grow teff and maize during the meher season and vegetables like tomato, onion, and pepper during the belg season. With her 162 Birr per month cash transfer from PSNP for 6 months this year, she was able to buy fertilizer and seeds, and use some spare funds for books for her daughter’s schooling. Her crops are recuperating after the bad drought last year, where everyone suffered.

The canal was constructed by combining a capital budget of approximately £14,000 (400,000 Birr) for materials and semi-skilled labour, with five days working labour per month from PSNP Public Works clients. PSNP’s support has benefitted 306 community members, 156 of whom are also PSNP beneficiaries. The canal links a nearby river source to 103ha of cropland and is managed by a local irrigation association which charges minimal fees (10 Birr) to users to keep it clean throughout the year.

Community members want the canal extended another 1000 metres to benefit more residents, but kebele officials feel the pressure to spread out their limited capital budget to reach other areas with similar projects. This year, public works will focus on water harvesting structures, which require little capital investment but also contribute to the quality of soil and environmental degradation.

The general performance of PW was high in most places, delivering 99% of the planned person days with 70,476,933 person days completed across nine categories of subprojects. This included 1.2 million person days delivered through social infrastructure construction and 1.7 million person days on nutrition-based PW activities, enhancing access to social services.

Indicator 3.4 Gender and Social Development considerations are increasingly being implemented across the programme though reporting should be improved. The requirement for women’s workload to be half that of men in recognition of their domestic workload, enables them to arrive late and leave early from work sites to manage their other household responsibilities, was taken into account in planning. “The 2008 EFY PW plan was prepared based on [gender workload] considerations while estimating and assigning PD [person days] to various types of PW sub-projects.” (GoE 2008 Annual Report, p25). In 2015/16 a gender assessment of PSNP in the lowlands has been prepared and GSD and nutrition training material has been developed.

Indicator 3.5 Community-based nutrition counselling services were piloted and public works beneficiaries are able to transfer 3 work days to attendance at community based nutrition counselling services. A Behaviour Change Communication (BCC) job aid has been developed under the leadership of the gender and social development taskforce, in partnership with the Ministry of Health (MoH). This now needs to be effectively cascaded to implementing partners.

Creating Social Infrastructure in SNNP

PSNP4 is helping improve access to social services through targeted public works projects. Efforts were made in SNNP in 2015/2016 to construct social infrastructure which was both labour intensive and required minimal capital expenditure. Low cost blocks produced by client enterprises under the livelihoods component, using local labour and raw materials, were used to construct social infrastructure through the PW programme.

Indicator 3.6 Provisions in the Programme Implementation Manual (PIM) for pregnant and lactating women (PLW) to be transitioned to temporary direct support are being implemented, though the impact evaluation baseline indicates that there is scope to increase understanding of and compliance with this new provision. According to programme reporting, 41,209 pregnant and 13,208 lactating women were temporarily exempted from PW and benefited from unconditional transfers through temporary DS.

Summary of responses to issues raised in previous annual reviews (where relevant)

There were no recommendations related to Output 3 in the previous AR. In the PSNP3 PCR, however, it was recommended to review the indicators for public works and ensure that measures of quality were taken into account. The sub-set of indicators selected for DFID’s logframe reflect quality (e.g. gender and nutrition sensitivity) but as yet there is limited data to measure performance.

Recommendations

- Ensure the Public Works Reviews are initiated again in 2017, as they provide critical information about the progress and quality of PWs.
- Update the PW reporting framework to accommodate gender and nutrition aspects of public works programming
- Cascade the BCC job aid to implementing partners to support effective implementation
- Conduct GSD and nutrition monitoring mission to selected regions, led by GSD Taskforce, to assess progress
- Consider how to incentivise quality and timely PW reporting, e.g. through releasing budget on the basis of reporting

Output Title	Clients’ livelihood opportunities facilitated through three pathways: crop and livestock, off-farm income generation, and employment
Output number per LF		4	Output Score	B
Risk:		Major	Impact weighting (%):	15%
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	Y

Indicator(s)	Milestones	Progress
4.1 % and number of safety net clients who complete livelihoods checklist (training package)	30%	Moderately did not meet expectation: B / Of those targeted for the livelihoods component in 2015/16, 84% completed the livelihoods checklist . Overall / 13% (173,104) completed.
4.2 % of safety net households who report saving regularly (disaggregated by sex)	25%	Did not meet expectation: C / 8.4% households are saving (10.5% male headed, 6.9% female headed). / This is below expectation but drought made it difficult for households to save.
4.3 % of clients with business plans developed	40%, cumulative (over past 3 years)	Moderately did not meet expectation: B / In 2015/16, 159,000 business plans developed out of 1,325,546 PW households (12%).
4.4 % of safety net households receiving credit for their business plan after completion of checklist	50%	Met expectation: A / 91,766 business plans were financed out of 173,104 completing livelihoods checklist (53%)
4.5 % of ultra-poor safety net households receiving livelihoods transfers	30%	Met expectation: A / 8,389 households in 8 woredas / All households included in the transfer pilot have received the transfer / (Indicator requires revision)

Overall this output, “Clients’ livelihood opportunities facilitated through three pathways: crop and livestock, off-farm income generation, and employment”, moderately did not meet expectation. Nonetheless, positive examples of progress have been made: the livelihoods transfer and the checklists are functioning well and feedback on the quality of targeting for livelihoods transfer is positive. The livelihoods component of the PSNP is designed to support the livelihoods of individuals/households to build assets, increase income and strengthen resilience to shocks through interventions in three pathways: (i) the crop-livestock pathway, (ii) the off-farm income generation pathway, (iii) the employment pathway. The programme provides technical/skills development support and a livelihood transfer to PSNP households. High staff turnover at woreda level is hindering activities under this output and drought made it difficult for households to save.

Indicator 4.1 Percentage of safety net clients who complete livelihoods checklist (with all training packages) More than 173,000 clients had access to the full training package and have completed the livelihoods checklist (84% of those targeted for the livelihoods component). In 2015/16 204,564 PSNP clients were targeted to benefit from the livelihoods component, of which 81,182 were women (39%). Clients were formed into 9,023 livelihood development groups for the purpose of delivering financial literacy training, coaching and mentoring support. Attendance at training sessions is tracked through a livelihoods checklist (part of the PSNP clients ID card). According to 2016 baseline data, all woreda and regional staff responses demonstrated an understanding of the details of the redesigned PSNP4 livelihoods component, in particular the three pathways and the PIM provisions. The Impact Evaluation Baseline (2016) estimates that 16% of all PSNP beneficiaries have joined the livelihoods component.

Indicator 4.2 % of safety net households who report saving regularly (disaggregated by sex). In the 2015/16 financial year PSNP clients saved 166,890,204 Birr, of which 38% was deposited by female clients. An estimated 8.4% households are saving. Engaging in saving activity is one of the steps for clients to participate in livelihoods interventions, since it is understood to demonstrate financial discipline and preparation for managing cash and credit within enterprises. Government data shows that the majority of current savers in rural areas save in Rusaccos. This is confirmed by the Impact Evaluation Baseline (2016) which indicates that of livelihoods households, a larger proportion have savings in Rusaccos (11.6% of male respondents, 2.8% of female), while fewer save in Micro Finance Institutions (MFIs: 5.7% male and 1.7% female) and village savings and loans associations (VSLAs: 4.9% male and 3.9% female).

Indicator 4.3 % of clients with business plans developed. 159,000 business plans were developed. Out of 1,325,546 PW households (12%) targeted for the livelihoods component. The majority of these business plans (135,700) are for on-farm activities (crop and livestock development), with only 23,700 for off-farm income generating activities. Business plans are developed by poor households, with assistance from woreda Development Agents (DAs), once a household has completed the training packages and is aware of the support they could get from the livelihoods component. Participation is voluntary and individuals are expected to self-select to access the support. Performance of off-farm and employment pathways continues to face problems due to a skill gap for DAs and limited engagement of institutions such as MOLSA, TVET and FEMSeda. 22,209 clients (of which 9,846 women) have been referred to one stop centres to develop their enterprise plans and a further 24,555 clients (of which 7,256) clients have been referred to woredas to link them to wage employment opportunities.

Indicator 4.4 % of safety net households receiving credit for their business plan after completing checklist. 91,766 business plans (53%) have received financing. Finance is not provided by PSNP but through existing credit sources. Regions are incentivised to avail funds for credit by making the capacity building budget (for the livelihoods component) contingent on capitalisation of credit by regions. In 2015/16 417.2million Birr was allocated by regions (less than a third of the planned amount) and households accessed 33.5 million Birr of this. In practice the late release of livelihood building capacity budgets, whilst the provision of credit was documented, has hindered implementation.

Indicator 4.5 % of ultra-poor safety net households receiving livelihoods transfers. Under the initial two year pilot, a total of 8,389 people (of which 56% women) in 8 woredas (in Amhara, Tigray, Oromia and SNNP) have received a livelihoods transfer after completion of checklists. A cash grant of 4,000 Birr per client is given to the poorest households that are otherwise unable to access credit from financial

Addressing Livelihoods Needs
The Impact Evaluation Baseline (2016) interviewed clients to discuss livelihood opportunities and trainings provided under PSNP4. The results illustrated interest and willingness of clients to participate in various components.

A male client in Kuyu woreda, Oromia explained how “the training on financial literacy has helped us to enhance our awareness and capacity on business skill, savings culture. The specific technical training and support help us to enhance our knowledge on oxen fattening, dairy cow rearing, forage production and marketing related issues.”

The selection of clients to receive one time livelihood transfers (4,000 Birr) was “posted in the kebele office gate.” A client in Tigray explained that he “knew in person most of the targeted households and they deserve the transfer support.” A similarly transparent process was described by another client: “Two weeks ago the KFSTF has presented 75 households targeted for the livelihoods transfer in community evaluation. The initial selection is done by KFSTF and was finally displayed in a public meeting to evaluate their eligibility. We know that most of the targeted households are very poor and the community has unanimously endorsed the list.” A female client selected in Amhara confirms: “Yes, I am one of those people targeted for the livelihoods transfer for very poor PSNP households. I am targeted because I have nothing at all. So they targeted me so that I can engage in animal husbandry and change my life.”

Kebele officials and beneficiaries alike, believe that the livelihoods activities will help clients graduate from PSNP4, though the amount is small and their environment vulnerable to shocks. A client in Amhara describes: “Yes, the loan will help us to enable us to graduate. But our fear is the climate change. We can’t predict the natural problem especially the existence of drought. If conditions are good we will able to graduate within two to three years.” In Oromia, a client thinks: “The support could help households prepare for graduation but the loan amount is too small and the loan repayment period is too short.”

services to improve their livelihoods. The Impact Evaluation Baseline indicates that targeting of the livelihoods transfer was fair and transparent. The livelihoods transfer is also attached to intensive supervision by the DAs of the recipient households through bi-weekly visits. The DAs noted that “while the frequent visit to households is time demanding, the experience is rewarding and that they are noticing visible changes in the performance of households”.

Summary of response to programme issues raised in previous annual reviews

Recommendations
- The logframe should be revised to ensure that indicators are meaningful and targets are realistic
- The programme design assumes that credit will be forthcoming at regional level and this assumption should be carefully monitored
- Lessons from the livelihoods transfer pilot (2015-2017) should be systematically documented and used for decision making for 2018 expansion
- High levels of staff turnover at regional, zonal and woreda level should be addressed by addressing staff salary disparities between PSNP and other flagship programmes of MoANR.
- The planned evaluation of the drought response, should seek to understand the impact of the drought on clients’ livelihoods activities and choices

Output Title	Effective management and operational processes in place to manage the programme
Output number per LF		5	Output Score	B
Risk:		Moderate	Impact weighting (%):	10%
Risk revised since last AR?		Y/N	Impact weighting % revised since last AR?	Y

Indicator(s)	Milestones	Progress
5.1 Percentage of safety net woredas/regions meeting minimum safety net staffing standards –disaggregated by highland/lowland and new woredas	82%	Moderately did not meet expectation: B / 77% in highlands and 43% in lowlands. Roles and responsibilities of staff have been clarified. Capacity building facility has conducted HR audit and made recommendations.
5.2 Incidence of recurrent audit findings (financial, commodity and procurement) on resources at woreda, regional and federal levels	No milestone set	Met expectation: A / EFY 2007 audit findings closed. / EFY 2008 semi-annual audit – only one audit finding is pending and corrective actions have been taken. / EFY 2008 annual audits (financial, commodity and procurement) due in January.
5.3 Percentage of permanent direct support caseload under MOLSA management	No milestone set	In progress
5.4 Level of implementation of the gender action plan	A minimum of 80% of gender action plan activities included in the PSNP annual plan are implemented	In progress and met expectation: A

Overall performance against output 5, “Effective management and operational processes in place to manage the programme”, has moderately not met expectation. Overall there has been improvement in financial management systems – extensive use of IBEX for reporting (i.e. GoE’s financial management information system), reports are largely submitted on time (with the exception of Afar region), and financial audit has been unqualified. But food management has been challenged – in large part because of the drought and changes in institutional arrangements. In this first year progress has been made in developing a structured approach capacity development and some progress has been made in transitioning safety net delivery across different agencies.

Key Points

Indicator 5.1 Whilst there is no comprehensive data to report on the milestone, longstanding staff shortages are being addressed in the woredas. A systematic approach to capacity development has been adopted – with a human resources audit completed and recommendations for capacity development made by the capacity development consultancy. This report is awaiting Government’s approval.

Indicator 5.2 Significant improvements have been made on the closure of financial audits over the past year. All past audits have been closed and only one finding from the EFY 2008 semi-annual audit is pending. Audit findings continue to be followed up by the Financial Management Taskforce, chaired by MoFEC (Ministry of Finance and Economic Cooperation), with the support of the DCT financial management experts. Under PSNP4 there are increased requirements for transparency and accountability of the commodity transfers, considering the volume of food procured and distributed (in 2015/16 this was 450,000 Metric Tonnes). Ineligible expenditures identified in commodity audits now have to be repaid. A new Commodity Management Procedure Manual has been rolled out to support regional bureaus to compile commodity receipts and distribution reports. In the medium term it is expected that commodities will be managed through the Commodity and Allocation Tracking System (CATS). However improvements in the food management system are not rolling out as swiftly as planned in most regions and this will require concerted effort to deliver improvements.

Indicator 5.3 MoLSA’s management of the PDS caseload has not yet come into effect, but has progressed this past year. The June JRIS Mission noted that BoLSA minimum capacity and structures in some regions were not yet adequate to take over management of the PDS caseload. This will require a discussion on accessing the GoE’s in-kind commitment of $250m to PSNP4 to staff BoLSA and WoLSA for PDS takeover for EFY 2009 and appropriate follow up, monitoring and supervision systems. It was agreed that the Gender and Social Development Expert at woreda level should work closely with BoLSA.

Indicator 5.4 The Gender Action Plan (GAP) is prepared and updated with the status of each activity at least two times per year, with oversight provided by the Social Development Task Force (SDTF). While the narrative status update was last provided in June 2016 and illustrated actions on the majority of activities, it is too soon to determine the “level of implementation” of the GAP and assess whether 80% of actions have been achieved or not. Of the 17 actions identified for 2015/16, 11 have been completed and the rest are ongoing, with only two issues pending without progress. Key actions completed include: inclusion of a module on complaints processes related to gender PIM (Programme Implementation Manual) provisions and use of household transfers in the Grievance Redress Manual (GRM); completion of the ESMF Annex 13: Health, Safety, and Child Labour Guidelines; advertisement of a Request for Proposals (RFP) for a Gender Contextual Assessment in Lowland Areas; and the hiring of Social Development Experts in Tigray and SNNPR.

Women’s participation in capacity development planning and implementation remains low, which inhibits the application of learning to programme implementation. Emphasis on ensuring adequate active participation of women in committees, task forces, technical and steering committees is an important component of the coordination tasks of the government. This should encompass: community level participation of women in PSNP planning, public works selection and accessing appropriate services to enhance their livelihoods; and the engagement of the Ministry of Women Children and Youth Affairs at all levels, their directorates within the various implementing agencies, and the social development experts at regional and woreda levels in planning, monitoring, reviewing and decision making in the programme.

A notable achievement this year is the inclusion of many issues identified in the GAP into the Capacity Development (CD) Facility TOR (described above under Output 1). The CD Facility will, in collaboration with the SDTF, develop tools, which will be used by the CD resource pool, to integrate gender and the empowerment of women in PSNP 4’s CD interventions. It will develop capacity of the CD resource pool to ensure CD is designed, delivered and followed up in a gender sensitive manner that enables women to be active participants in all aspects of the programme. The CD Facility and SDTF will advise the government on how CD can also adequately address other social issues relevant to the programme using the technical expertise already existing within the programme and provide technical assistance to the government on how to integrate gender considerations in coordination tasks at all levels of government, as well as other social development issues, while also supporting the active participation of women.

Summary of responses to issues raised in previous annual reviews (where relevant)
The previous AR recommended that planning and budgeting should be aligned with the government calendar – a review and refresh of the JRIS has taken place, which has focused on aligning this six monthly review and implementation support mission with GoE planning cycle and the PSNP timetable.

The recommendation made at PCR to set up and operationalise the Commodity Management Unit at NDRMC (to manage PSNP and relief food) is outstanding. A Commodity Management and Food Logistics Directorate was established at MoANR in 2016 as a focal point.

Recommendations
- MoFEC to clarify budget source for new procurement officers in PSNP woredas to enable their recruitment
- Appoint focal staff at regional and woreda level for Food Management
- MoLSA to follow closely capacity building of BoLSA to take over PSD caseload, to avoid delays in delivering 12 months of monthly transfers to PDS clients.
- MoFEC to follow up on commodity audits as it does financial audits, ensuring transparency and accountability of expenditures.
- Encourage the SDTF to either revise the GAP indicator in the logframe, or produce a numerical update on their progress according to the Logframe measure.

D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Overview of spend portfolio
DFID’s total approved budget for PSNP4 is £276m. During EFY2008, DFID transferred two tranches to MoFEC: the scheduled £74m payment in October 2015 and an additional £25m in May 2016, brought forward from outer years to assist in responding to the drought. DFID’s next scheduled payment of £53.6 million contribution to the EFY2009 was delayed until December 2016, until HMT approval of the full business case was received and due to additional due diligence conducted. This has contributed to cash flow issues for the programme, impeding the second round of transfers to regions in 2016/17. DFID also supported the DCT with an initial £4.5m contribution in 2015 and a scheduled payment of £833,000 in September 2016.

Key cost drivers and performance
Roughly 80% of financial resources are used as cash or food transfer payments to households, making them the main cost driver for PSNP4. Transfer payment costs are determined by the number of recipients, the average sum paid to each beneficiary, and the number of transfers per year. Spending is highest from January to June when public works transfers are paid, but financial contributions are required by the 2nd quarter of the Ethiopian financial year, given the time for funds to flow down to woredas and the need to procure capital inputs and food ahead of the public works.

Key cost drivers of the PSNP programme, 2015/16

In EFY2008, 5,401,617,250 Birr was paid in cash to clients and 310,199 MT of food was delivered to reach a total of 7.99m clients with 6 rounds of transfers. Overall 38% clients received cash only, 39% received food, while 23% received a mix of cash and food. Somali and Afar rely primarily on in-kind food transfers, while Amhara and SNNP Regions have focused on cash transfers.

VfM performance compared to the original VfM proposition in the business case
Economy
Costs savings have been experienced for key inputs in EFY 2008. The global drop in international grain prices had a large impact on the EFY2008 input expenditures for PSNP4, given the significant amount of budget spent on procuring cereals for food transfers. Between 2010 and 2015 (PSNP3), the price of wheat grain fluctuated between US$361 to $464 per metric tonne (MT). In 2015/16, the price dropped to $292/MT. Given that a substantially larger quantity of wheat was procured in EFY2008 over previous years, as shown in the table below, the procurement of 451,000 MT resulted in a direct saving of $54.3 million (£37.8m)[1] from the estimated budget. These savings were pooled back into other programme delivery budget lines.
[1] At approximate time of procurement: 1 USD = 0.696 GBP, 1 GBP = 1.439 USD (1 Feb 2106)

Table 1: PSNP procurement quantities and price of food grain annually
Budget Year	2010/11	2011/12	2012/13	2013/14	2014/15	2015/16
Quantity purchased (MT)	211,200	297,000	160,600	171,600	154,000	451,000
Average unit price ($/MT)	417.83	406.38	421.75	464.44	361.75	291.63

Source: DCT analysis

Economies of scale have also been obtained through bulk procurements of specific items, particularly capital goods, for PSNP4. In addition to food grain, at the national level, vehicles, storage facilities and IT equipment is procured. At the regional-level IT equipment and client cards have been procured, whereas woredas are responsible for their own procurement of PW inputs (i.e. construction materials). Experience has shown that it is more efficient and timely for woredas to procure their own inputs locally, whilst supporting local economies across the country.

Management processes to ensure competitive procurement processes and oversight have resulted in enhanced value for money (VfM) for the programme. All federal and regional procurement plans are reviewed by the DCT’s procurement expert to ensure alignment with the PSNP4 Annual Plan and that costs are reflective of market rates. Numerous revisions and ultimately costs savings were highlighted through this review process in EFY2008 when a number of new procurements have been launched to identify new suppliers for PSNP4. New multi-year contracts for the Capacity Development Facility, JRIS Facilitation, and Public Works Review will avoid annual tender processes and delays, enhancing efficiency and effectiveness and creating cost savings.

An exchange rate loss of 23.83 million Birr (£842,000 GBP)[2] was recorded during the 4th Quarter IFR, due to the reduced value of the GBP against US$ and Birr following the EU referendum.
[2] At approximate time of calculation: 1 BIRR = 0.035 GBP , 1 GBP = 28.3 BIRR (6 Jul 2106)

Efficiency
Total cost-to-transfer ratio (TCTR) is the most basic measure of cost-efficiency for a safety net programme and was used to measure VfM in PSNP3. The TCTR in 2014/15 (PSNP3) was 1.30 (i.e. it cost a total of 1.30 Birr, 0.30 Birr in non-transfer costs, to deliver one Birr of transfers to a beneficiary household).

According to EFY2008 final expenditure reports, the calculation of TCTR is estimated to be 1.288. This is an incomplete calculation since food procurement has not yet been fully reflected (goods worth approximately £60m have not yet been fully received and receipted), as a result of importation delays. It is recommended that the TCTR is recalculated for EFY2008 when final data is available. On current calculations, transfer costs represent 78% of expenditures, and this is estimated to rise to 82% once complete expenditure data is available. PSNP4 aims to have 80% expenditures spent on transfers.

Global assessments generally indicate that cash payments represent a more efficient use of resources, though it is difficult to measure the total delivery cost of cash payments versus in-kind food transfers, due to a lack of specificity in transport costs. Between EFY2008 and 2009, the proportion of beneficiaries receiving payment in cash is expected to increase (from 38% to 60%). Furthermore, 64 woredas are expected to utilize e-payment mechanisms for cash transfers in EFY2009 (from 20 in EFY 2008). A full evaluation of e-payments is currently underway, which should include an assessment of their efficiency and cost-effectiveness.

Effectiveness
Previous reviews in 2011 and 2013 of PW Impact Assessments have derived the net present value (NPV) and economic benefit-cost ratios (BCRs) to illustrate the cost-effectiveness of PW investments. In all cases, there were high rates of return associated with public works projects under PSNP3. While the same is anticipated under PSNP4, the PW Impact Assessment for EFY2008 has yet to be completed. It is recommended that this indicator be measured in future ARs, once data is available.

Recent analysis by ESSP/IFPRI (2016[3]) shows that on an economy wide basis, the benefits of PSNP exceed the total cost of PSNP. National agricultural production increases by 1.33% due to PSNP, and together with the PSNP transfers themselves, this raises household income by nearly 6% in PSNP areas and by nearly 2% in non PSNP areas. Productivity increases and income spillovers add the equivalent of 0.99% Ethiopia’s GDP to the benefits of PSNP.
[3] ESSP Research Note 57, July 2016, Synopsis: Economy-wide impacts of the Productive Safety Net Programme.

A key driver of cost effectiveness in social protection programming is targeting: whether the programme is reaching its intended beneficiaries. PSNP4 is targeted at the poorest, and the Impact Evaluation Baseline 2016 confirms “considerable evidence” that PSNP4 “has been targeted towards the right households as specified in [the programme guidance]. Non-PSNP households are considerably richer than those household selected for PSNP4.[4]” Qualitative evidence shows that community participation is perceived to have improved and kebele officials perceive that exclusion errors have reduced. This is not the case for Afar and Somali regions where targeting performance requires significant improvement, as discussed under Output 2.
[4] Targeting Chapter Presentation, Slide 6 - PowerPoint, Baseline Impact Evaluation, IFPRI, 4 November 2016.

Investments in institutional capacity and systems, such as the MIS and e-payments, are expected to strengthen the performance of the programme and lead to greater achievements in impact over time, thereby improving cost-effectiveness. Given the large number of beneficiaries reached by PSNP4, even relatively large investments in strengthening the programme have a low per beneficiary cost. Over the course of PSNP4 GoE is expected to incrementally increase its contribution to PSNP. In 2015/16 GoE made its anticipated cash contribution of Birr 300 million, in line with its commitments.

Equity
There is no new data to assess the equity dimension of VfM. However, the initial targeting analysis undertaken in the impact evaluation baseline shows that, overall, the programme is successfully identifying the poor and so transfers will impact poverty depth. In addition, PSNP4 has improved support for some of the most vulnerable in Ethiopia’s poorest communities (older people, people with disabilities and female headed households with no labour capacity), now providing a monthly transfer over twelve months rather than six.

Assessment of whether PSNP continues to represent value for money
The programme’s theory of change remains valid and the PSNP continues to be relevant to the food security and poverty reduction objectives of the GoE. It effectively responded to the household food gap with predictable, timely transfers to help targeted households meet their consumption needs. Considering this and the economy, efficiency, effectiveness and equity indicators above, PSNP4 continues to represent VfM. It is recommended that DFID Ethiopia updates its VfM assessment of PSNP following the mid-term review in 2017 (and any design changes that follow) and once impact evaluation data is available.

Quality of financial management
The November 2016 J-RIS noted a number of key achievements in the financial management systems of the programme: extensive use of IBEX (GoE’s financial management information system), interim financial reports submitted on time, unqualified audit. However both IBEX and PASS (the programme’s payroll system) implementation is still required in Afar. The J-RIS also noted inaccurate budgeting/planning which had led to 5 budget revisions in 2015/16.

PSNP4 is subject to World Bank financial management procedures and World Bank carries out a minimum of two financial management missions per year, in addition to adhoc missions carried out by the DCT and DPs. Two DFID staff participated in the World Bank’s bi-annual Financial Management Mission in Amhara in November 2016, observing close follow up with woreda and regional level BoFEC accountants on the implementation of a variety of FM protocols. An August FM Taskforce mission to Somali region reviewed the newly implemented cash transfer system and indicated that “serious and continuous attention was given to the programme by high levels of leadership.”

MoFEC plays a strong financial oversight role, including through its role as chair of PSNP’s financial management taskforce. Over the past year MoFEC has recruited a monitoring and evaluation specialist who is mandated to prepare audit action plans. The only pending audit findings relate to 2008 EFY bi-annual financial audit. MoFEC oversaw and DCT with World Bank, as donor chair, facilitated an independent investigation into allegations of funds misuse in two woredas in August 2016, which provided assurances that funds were used for the purposes intended in the two districts.

Commodity management: PSNP4 has increased requirements for transparency and accountability in the management of food resources within the programme. A Commodity Audit is due to report in January 2017, which will identify any ineligible commodity expenditures. A Commodities Management, Logistics and Finance Directorate has been established at MoANR, but it requires additional human resources and leadership. The November 2016 JRIS re-iterated a previous recommendation, still pending, to establish to establish a Commodity Management Unit (CMU) in NDRMC to enable better management of commodities.

Date of last narrative financial report	Financial 1 September 2016 / Annual report for 2015/16 received August 2016
Date of last audited annual statement	None yet for PSNP 4. Due Jan 2017.

E: RISKS

Overall risk rating: Major

The overall risk rating has been updated since the last AR to reflect the updated DFID Risk Management Guidance and the 2015 AR rating of ‘medium’ has now been updated to ‘major’. This rating acknowledges that there is a higher probability of risks materializing, and that if this occurs some outcomes would be reduced while other important outcomes would still be likely realized.

Overview of programme risk

PSNP4 is a large, complex and ambitious programme, which promises large-scale benefits but also entails a number of risks. The programme is assessed as overall major risk with a number of moderate probability risks existing that hold the potential to impact the programme’s results if they materialise. The programme Risk Register has been updated in November 2016 to reflect risks across six categories (delivery, context, operational, safeguarding, reputational, financial) and recent changes in the risk context. The programme is major risk, high development return and lies within DFID E’s risk appetite.

As flagged in last year’s AR, a number of important risks have been realised. The serious drought caused the doubling of need across the country and the institutional split between MoANR and NDRMC has undermined PSNP4’s vision of a continuum of response. No graduation has taken place in EFY2008, in acknowledgment of the impact of the drought on household livelihoods. Food management related concerns were realized over the past year, with transport and delivery systems substantially stretched and delayed. Widespread localised protests in many areas of Ethiopia caused problems for delivery in August and September – these were largely managed in October through the declaration of the State of Emergency. Finally the programme faces a significant financing gap which requires either mobilisation of significant finance from GoE or programme ‘right sizing’.

DFID has completed its annual statement of progress on the Fiduciary Risk Assessment of PSNP4 in October 2016 and noted steady progress in strengthening financial management and a credible programme of financial management reforms. It noted progress on mitigating some risks but also recorded two new risks. Fiduciary risk and corruption risk are assessed as moderate.

Outstanding actions from risk assessment
AR 2015 Issues	Actions
Sustained attention to coordination related to the provision of humanitarian food, stocks available, procurements, and ability to draw upon ESFRA stocks.	November J-RIS has recommended that PSNP and humanitarian system should be managed through one system to improve efficiencies, reduce duplication and gaps and improve effectiveness.
Re-assessment of EFY2007 PSNP3 clients identified for graduation.	No graduation took place in EFY2008 in recognition of the drought.
Closely monitor the roll-out of FMIP recommendations.	November J-RIS has made the same recommendation.
Agree a strategy to improve Afar and Somali targeting outcomes.	November J-RIS has recommended an analysis of and revision to both the targeting and safety net design and delivery in Afar and Somali. Donor Partners have raised with GoE in official feedback since lagging performance in these regions represents a risk to the wider programme.

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe
Overall the programme is delivering against the timescales in the approved business case.

However some activities were delayed in 2015/2016 (e.g. procurement of foodstuffs and distribution) as a result of demands on the food management system, during Ethiopia’s worst drought in decades. Drought response notwithstanding, foundations were still laid during 2015/16 to deliver on PSNP4’s ambition to work across government agencies and lay the foundations for a social protection system (e.g. the roadmap for an integrated social protection MIS and MoLSA taking responsibility for the PDS client caseload).

Against overall performance, implementation in Afar has specifically lagged behind – both in programme delivery (e.g. core operations such as targeting) and in programme reporting (e.g. establishing a Regional Information Centre (RIC), or using the PASS and IBEX financial management tools). The November JRIS has recommended remedial action to deliver improvements in both Afar and Somali regions.

Performance of partnerships

MoANR, in close partnership with MoLSA, is responsible for the management and coordination of the programme. MoFEC is responsible for financial management and reporting, and channels resources to MoANR, MoLSA, and Regions. A Memorandum of Understanding (MOU) between all partners articulating rights, obligations and coordination arrangements of the partnership is developed and signed off. In 2016, there has been increased participation from MoLSA in engaging on PDS client planning and Ministry of Health (MoH) on implementing nutrition-sensitive related components of the programme. Engagement at the regional and woreda-levels across bureaux will need to be strengthened. Collaboration between MoANR and NDRMC has performed less well and the institutional divisions have created obstacles for food delivery systems.

The DCT is housed within the World Bank and plays a secretariat function for the Donor Working Group (DWG). With 8 full time staff and individual consultancy positions, the DCT has played a central role in general coordination activities, such as facilitation of DWG meetings, participation in all technical committees and working groups, coordination meetings with senior GoE officials, arranging monitoring missions and visits, and preparation of two Joint Review Implementation Support (JRIS) missions. The DCT has also played a significant role in preparing the TORs and contracting a number of programme consultancies and workshops this year, including the large Impact Evaluation. DFID engaged positively in the annual evaluation of the DCT and in helping prioritise workplanning, which has also including leading discussions on addressing the programme financing gap.

DFID is an active participant in a variety of Task Forces and Technical Committees, including those focused on social protection, livelihoods, financial management, commodity management, and systems development. The quality of its technical inputs by the Senior Social Development Adviser and Livelihoods Adviser were noted by other development partners and the DCT.

DFID acted as donor chair from January until June 2016 and has received positive feedback on its role. Feedback has noted that DFID strengths lay in: wide consultation to steer difficult conversations with other Development Partners (DPs); DFID deployed its leadership and technical staff well to push on the development-humanitarian continuum of response in the midst of the drought; and DFID’s politically aware approach to engaging GoE on key strategic issues (e.g. the financing gap and continuum of response). However, feedback also noted that DFID appeared stretched in undertaking the DC role, with significant strain on key individual staff. Operational requirements of the DC role should be better addressed before DFID takes this role in the future (the role rotates between donors every 6 months).

Asset monitoring and control
PSNP4’s PIM introduces new procedures to improve the management of physical assets in the programme. In 2016, a Physical Asset Assessment report has inventorised IT and transportation equipment and assessed the management and maintenance of assets at federal, regional, zonal and woreda levels. The assessment made 17 recommendations and suggested that PSNP4 should initiate a comprehensive physical asset management programme. It also recommended establishing a national registry of all PSNP physical assets (to include items procured by Government and items contributed by NGOs and donors) and to provide more training on government directives on physical resource management, such as the Directive on the use of Government Property, the Government Vehicle Utilization and Fleet Management, and the Ethiopian Transport Authority Proclamation. Recommendations on capacity building will be considered by the Capacity Development Facility.

G: CONDITIONALITY (½ page)

Update on partnership principles

As aligned non-budget support financial aid, our engagement with PSNP is governed by the Partnership Principles directing DFID’s overall relationship with the GoE. These Principles cover (i) commitment to poverty reduction and the Millennium Development Goals; (ii) respecting human rights and other international obligations; (iii) improving public financial management, promoting good governance and transparency and fighting corruption; and (iv) strengthening domestic accountability.

The updated Partnership Principles Assessment (PPA), June 2016, judged that “on the basis of the 2016 PPA it remains appropriate to use aligned financial aid in Ethiopia to deliver results for poor people.”

In addition to the DFID Ethiopia PPA, the programme-level PPA was updated in August 2016 to assess the application of the Principles specifically with regard to PSNP4. This concluded that “On the basis of this assessment we conclude that, at the programme level, there remains evidence of a credible commitment of GoE across the PPs and that aligned non budget support financial aid remains appropriate to deliver results for the poorest in Ethiopia through PSNP.”

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation
PSNP4 has a dedicated impact and performance evaluation in place: a 6 year contract has been awarded to an IFPRI (International Food Policy Research Institute) led consortium to conduct evaluations of performance and impact every two years, based on household surveys (representative at regional level) and qualitative research. This evidence allows some disaggregation by region, by programme instrument, sex and age.

The baseline survey was conducted in January 2016, and initial findings and draft chapters (on implementation of PSNP, targeting, transfers, household assets, food security, health and nutrition, livelihoods and well-being), have been presented and reviewed by GoE, DCT and members of the DWG. Subsequent rounds will be fielded in January 2018 and January 2020.

The findings of the baseline survey provide updated evidence on targeting performance and confirm that in the highlands PSNP is effectively targeting the poor but that in Afar and Somali there have been no improvements in targeting. This evidence provides the basis to recommend an analysis and revision to the targeting approach in the lowland regions, and the wider design of the safety net.

The theory of change and assumptions underlying the programme design are still relevant.

Monitoring progress throughout the review period

The AR has been conducted by DFID staff working on PSNP (the Senior Social Development Adviser, a short term technical assistant, the Livelihoods Adviser and Programme Officer). The AR has drawn on programme documentation (annual report 2015/16, interim financial reports, reviews and audits); the November J-RIS (Joint Review and Implementation Support mission) process; discussions with DCT technical staff and other development partners; and visits made as part of the J-RIS to Afar and SNNP and a financial management visit to North Wollo. During these visits discussions took place with Government of Ethiopia staff responsible for programme implementation at regional, woreda and kebele level and with a small number of programme clients through focus group discussion and during PW site visits. Direct feedback from stakeholders has been incorporated into the main body of this review.