Terms of Reference

      Post Completion Review for Development Impact Bond- ARIES Code : 203604

Introduction
DFID measures the results of its projects and demonstrates Value for Money (VfM) through regular and effective monitoring, reviewing and lesson learning. Reviews of programmes are important to establish progress against planned outputs in an objective and transparent way.

At the end of a project, DFID undertakes a Project Completion Review to determine the progress made and evaluate the success of the project.

DFID provided £1.64 million for inception work on development of a completely new development financing instrument to address sleeping sickness. The work was undertaken by Social Finance UK and other experts over a 2 year period. This work was intended not only to develop the new instrument but also test the effectiveness of a new type of payment by results instrument in a specific context of addressing the spread of sleeping sickness.

Background

This new instrument, a Development Impact Partnership (DIB), allows an entity to raise its own capital from social investors. The entity then commissions service provider (in this case a private sector provider) to deliver DFID agreed targets. The investors get repaid by DFID. The repayment being dependent on the independent verification of the result achieved. The instrument adapts an approach, a Social Impact Bond, first used globally by Social Finance UK to address re-offending in the UK, for a developing country context.

The new instrument’s design sought to address an issue that sub-Saharan African has struggled with – the up-take of research on sleeping sickness that has already proven to have had results but struggled to be successfully implemented. The work aimed to deliver programme outputs that will be of use internationally - to both donors and social investors who want to address key development challenges. The work also sought to DfID’s effectiveness by informing Payments by Results Strategy.

The programme aimed to enable the uptake of research on sleeping sickness in Uganda and deliver a significant and sustainable reduction in parasite prevalence. The inception work’s objectives were:

1. to understand the scope of the work by having a clear baseline on the spread of sleeping sickness
2. develop the detailed design for the new instrument
3. use both the existing and design work to set suitable targets
4. structure the management and private financing components of a programme
5. understand how to best treat cattle with an insecticide and a trypanocidal drug to reduce the parasite that transmits the disease to a point where it becomes a low risk to humans
6. fully cost the intervention
7. determine and price risk; and understand what an appropriate value for money payment for the work would be before engaging with a DIB provider.

The inception work aimed to provide the detailed information to DFID to determine value and provide enough detail to investors for them to willing take the risk and finance a completely new £20mn 8 year output based instrument in a low income country.

The evidence programme aimed to inform:

Whether enabling private sector engagement to deliver the control - through the use of the DIP - is a better way of delivering results at scale (specifically - in relation to the uptake of research on sleeping sickness).

How the instrument encouraged innovation in delivery of the sleeping sickness control.

The beneficial impact on the poor in Uganda

How to leverage social investor finance for this and other development challenges.

The impact of the inception work was to define a feasible way to foster the use of research for a cattle treatment using a new instrument.

The intended outputs of the design work were to be:

- A detailed survey to measure cattle numbers and parasite prevalence. This will inform the baseline (it will sample and surveying 150 villages – as the last extensive survey was in 2008);
- A documented and costed pilot to develop an operational ready model for treating cattle;
- A calibration of payment triggers;
- Independent verification and testing of systems to accurately record the data on which the payments will be made.
- Confirmation of national and local government support for the proposed project.
- A detailed report on ‘lessons learnt’ detailing what worked and what could have worked better.
An engagement and communications plan for programme beneficiaries.

Objectives of the Review
- Assess programme in line with the aims of the inception work;
- Review the outputs
- Comment on the innovation delivered
- Assess the DFID processes to deliver on the work
- Comment on working with partners, their performance and the quality of work delivered.
- Comment on outputs, what has been published and capacity built
- Make recommendations and capture lessons learnt regarding major issues and addressing problems faced; and
- Comment on Value for Money of the inception work

Scope and Methodology

The annual review will be carried out by an internal DFID team, involving Lesley Hamill (SRO, Agriculture Research Team, RED), Tim Leyland (Independent), Ben Cattermoul (Country Office) and Ajay Sharma (Economic Adviser, Agriculture Research Team, RED).

In undertaking the review the team will interview partners, review the project documentation, financial reporting, and project outputs and the reports produced.

The team will also interview to key stakeholders in, DFID, Uganda and in independent Think Tanks who developed the payment by results concept.

Reporting

The team will use the latest PCR template.

Timeframe
The review started in October and will be completed by 6 December 2016.

RED annual review checklist

Stakeholder Involvement (Ensure key stakeholders/beneficiaries are involved in reviews)
Independent Review (All Annual Reviews must have at least one external person as part of the review team. A list of those available to conduct reviews from teams across RED (and other departments) should be compiled and made available on the RED teamsite to make it easier to identify external reviewers. Review participants could be drawn from someone else in the team if they were deemed to be independent, colleagues from other parts of RED, or other divisions.) Request for additional resource requirements for visit arrangements can be made to the Director of Research Office. Review teams may wish to bring on members who bring needed expertise (e.g. gender)
Terms of Reference (All Annual Reviews must have a Terms of Reference. The Reviews should be undertaken in good time for them to be loaded onto the system at least 2 weeks before the approval date so Approvers have time to read and challenge.)
Desk-Based Reviews (A review based solely on available documentation (progress reports, information from conferences previously attended, information from websites, other reports provided by the organization) undertaken by DFID staff and conducted with no or minimal external participation qualifies as a desk based review.Please note where possible desk-based reviews should be avoided. All desk based reviews are subject to approval by the senior management (Director of Research) on a case by case basis)
Recommendations (Previous recommendations should be re-visited and monitored as part of the review process. All recommendations must be clearly listed under section 7 of the AR form, and reviewing these must be part of the AR TORs)
Results (Information/figures should be included on how far logical framework milestones/targets are being met.
Gender The review should include assessment on how gender issues are addressed in research (design, methods, and outputs), capacity building efforts, and/or research uptake strategies, as well as any gender-focused results. It may also include attention to what has enabled or constrained integration of gender. This should be included as part of Section A on detailed output scoring, Section B on results, and any associated recommendations.]
Logical Framework (Decisions on whether to realign programmes should be taken at the very least at the annual review stage. If the logical framework is being revised as a result of the annual review the new version should be submitted for approval at the same time as the review template). It should be clearly dated and numbered so all involved are clear which logframe is current.
Value for Money (The annual review should update the economic appraisal and value for money statement in the business case and assess how the principles of economy, efficiency and effectiveness are being achieved) (Refer to How to Note on Reviewing and Scoring Projects – page 16/17)
Risk Assessment (The annual review should update the question; ‘are the funds being used as intended’ using evidence, which should then be referenced/ recorded clearly. Risk matrixes in business cases should be revisited and level of risk to the programme reassessed. Additional mitigation measures should be identified and consideration needs to be given to whether the programme should be realigned as a result of any additional risk or failed mitigation (Refer to How to Note on Reviewing and Scoring Projects – page 15)
Risk Register (Every programme must have a risk register which is reviewed at each Annual Review. This should include financial risks and risks to money not being spent as planned.)
Corruption and Fraud Risk (The section on ‘are the funds being used as intended to’ in the Annual Review template should include an assessment of corruption and fraud risk levels in the programme. Evidence of the partners’ control environment should be clearly listed– i.e. annex their anti-fraud policy, financial management reports, audited statements, declaration of conflicts of interest etc. In case of suspicion the Whistleblowing Unit should immediately be contacted)
Financial Management (An assessment of how accurately expenditure is being forecast and how quickly funds are being disbursed should be made during annual reviews/PCRs and any measures to improve financial management identified. Implementing partners should be made fully accountable for this and be aware this also reflects on the performance of the programme)
Agreement checks (Apart from the logical framework the Annual Review process should also monitor performance against clauses (Open Access Policy, Right to audit checks, Anti-Corruption and Fraud Policy, etc.) mentioned in agreements are being adhered to by all Partners
Budget changes (Any budget changes made during the year or as part of the annual review process should be fully justified and discussed within teams)
Lesson Learning (Annual Reviews/PCRs should include a summary of lessons learnt and how they will applied to the programme in future or to any other interventions)
Transparency (Once approved Annual Review/PCR should be declared as a record on QUEST and published on the DFID website. There should also be a formal approval from the project partners to publish)
Evidence (All evidence used should be clearly listed including quest numbers and dates)
Project Documents (Project documents must include a record of any review meetings held throughout the year and the quest reference given)
Annual Audited Statements (Annual audited statements should be scrutinized and referred to when reporting against financial forecasts or the ‘risk of funds not being used for their intended purposes’)
Reporting (If the implementing agency has an anti-fraud or corruption policy, or conflict of interest policy this should be annexed to the review. Financial reporting such as audited accounts should also be attached.)
Quality Assurance (All Annual Reviews should be quality assured by Research Manager and/or Team Leaders internally prior to being sent for external quality assurance. Programme managers are responsible for the spelling and grammar in an Annual Review and must be mindful that as these are public documents they need to be of a high standard)
ARIES (Once saved on QUEST, a summary of the findings should be recorded in ARIES. Please ensure information used is accurate and complete since some of this information will be published. Next the project should be sent for approval using workflow 30 (for PCRs, workflow 40). You must then choose a project approver for the approval task, usually the Head of Department, and save. If required previous reviews can be accessed through ARIES using Portfolio Quality Reports and archived material. Refer to ARIES e-learning modules on MoneySight – ‘Project Reviews and Completion’ for more details).