Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Support to the World Bank project ‘Enabling the Business of Agriculture’
Programme Value: £4,900,000 total (£3,000,000 disbursed)		Review Date: 11/11/2016
Programme Code: 204123	Start Date: 18/11/2013	End Date: 30/11/2020

Summary of Programme Performance
Year	2014	2015	2016
Programme Score	A	A	A
Risk Rating	Medium	Medium	Moderate

Summary of progress and lessons learnt since last review

This is the third annual review of the Enabling the Business of Agriculture project (EBA), a 3-year programme commencing in 2013. The continued performance of the project and its contribution to DfID’s goals led to a cost and time extension being approved this year, extending the project for another three years to the end of 2019/20. This funding is expected to deliver biannual data collection and publication of the EBA indicators, the fulfilment of a dissemination and uptake strategy, development of an implementation efficiency index and further refinement of the methodology and gender aspects of the index. Given the ‘Deep Dive’ activities of the project have now been removed, DfID’s priority for the next year is to ensure the EBA delivers opportunities for smallholders and agribusinesses through reforms driven by its policy relevance and uptake. To achieve this there should be clear feedback mechanisms with other parts of the World Bank, CSOs and other stakeholders, the ability to respond to specific influencing opportunities, and further work to create products which give colour and context to the EBA data.

The EBA team has made substantial progress in the past year. The 2016 report was published in January, followed by dissemination and outreach activities. Meanwhile, further refinements to the methodology were undertaken so that data collection and analysis could begin for an increased number of countries for the 2017 report (due in February).The team included four additional indicators this year; land, water, information communication technology and livestock. Furthermore, steps have been taken to integrate indicators on gender discrimination and environmental sustainability across the topics in which they are relevant and could be measured.

In the past year, the team successfully scaled up data collection and analysis from 40 to 62 countries and thus exceeded the logframe target of 60 countries. In addition, the team has also looked into developing an approach to collect data at sub-national level. Here, this EBA team started collecting data in four states in India as a pilot study for this approach.

The EBA is starting to show it is having an impact on regulatory reform and improving laws and legislation. This is a strong sign, as the ‘Doing Business’ index and report, on which it is based, took many years to demonstrate substantial impact on policy. In the past year, the EBA team directly engaged with the Rwandan government, delivering a briefing note which subsequently was used to inform the new Rwanda government’s Strategic Plan for the Transformation of Agriculture. The EBA team has also engaged with the government of Vietnam on reforming regulations regarding the seed sector. In addition, there are ongoing discussions with further eight governments, which will be taken forward in Phase II of the project.

The team reached out to other stakeholders and progressed on disseminating findings widely. The milestone for June 2016 (2 events) was substantially exceeded, with the team organising 9 workshops and 5 webinars. The success of raising awareness for the EBA can also be seen in the 119% increase of website visits in the past year, receiving a total of 28,217 visits. In addition, the team implemented recommendation from last year’s Annual Review, such as making the data more easily accessible and the report more public-facing.

The EBA project has performed well over the past year and has made significant progress against outcomes. The selection of indicators in the logframe, and the 50/50 weighting of the outputs mean this project has scored an A overall, and is recognised for meeting expectations. It should be noted however that the range of activities carried out, the ability of the team to deliver a complex product and the capacity to learn and adapt makes this a strong project, reflected in the approval of a three year extension. A revision of the logframe for future years should aim to capture a wider range of outputs and weight these so that the performance of the project is assessed in a more nuanced way.

Summary of recommendations for the next year

During the year, an extension of funding was approved for three years. As the plan for the next phase of the programme is finalised, the DfID SRO should work with the EBA team and other donors to develop the programme so it delivers reforms that benefit smallholders and agribusinesses for inclusive economic development. Within this, the following elements should be prioritised:

1. The programme should move to a biannual publication cycle following the publication of the 2017 report. This gives time for the team to focus on uptake of the report’s content to create more opportunity for impact, e.g. for reforms to take place.
2. The EBA team should strengthen and deepen indicators and analysis on gender and environmental sustainability across topics. Data should be presented in two standalone chapters on gender and environmental sustainability in the 2017 report
3. The EBA team should develop an implementation efficiency index for data collection in 2018, to improve understanding of policy practice and implementation of laws and regulations which are needed to create an enabling environment for agribusiness.
4. The EBA team should further strengthen collaboration and feedback mechanisms with other World Bank staff, in particular operational staff providing technical assistance to governments in country as well as Washington based policy and programme teams. Progress should be reported in the next annual review.
5. The SRO should work with the EBA team to ensure DFID focus countries are included in the index as far as possible,
6. For Phase II, the EBA team should be ready to publish regional, country specific or topic focussed outputs on an annual basis, as well as develop products to respond to specific opportunities for policy influence.
7. Over the next three years the project should move towards a more sustainable funding model, by seeking non-donor funding, e.g. through countries self-funding their inclusion, or from the private sector or other partnerships.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	Business Case
DevTracker Link to Log frame:	Logframe

The ‘Enabling the Business of Agriculture’ (EBA) programme is a multi-donor, multi country programme housed in the World Bank. It collects data on indicators that measure legal barriers for businesses operating across the agricultural value chain, and the transaction costs in dealing with government regulations. The ultimate aim is to promote smart regulations that ensure safety and quality control as well as efficient regulatory processes that support thriving agribusinesses. The intended impact is to provide opportunities for smallholders and workers through these agribusinesses and promote long term economic development. In this way, the index supports the monitoring and delivery of Global Goal 2 of ending hunger, achieving food security, improving nutrition, and promoting sustainable agriculture, and also contributes to Goals 1 (ending poverty) and 8 (economic growth) amongst others. It contributes to the delivery of DFID’s strategic framework on economic development as well as DFID’s conceptual framework on agriculture.

Three years on, the index is starting to become a trusted source of information for governments, including in DFID focus countries. The EBA measures regulations, policies and transaction costs that affect the emergence and sustainability of agriculture-related businesses. The project aims to provide policy-makers with an evidence-backed tool that can be used to inform policy reform, for example improve regulation around certifying and importing fertilizers. In the past year, the EBA started to show direct impacts on policy reforms in agriculture, e.g. in Rwanda and Vietnam.

The first phase of the EBA aimed to develop two components: (i) Regulatory indicators and (ii) Deep-Dive policy and practice assessments, known as Market Metrics (MMs).

1. Regulatory indicators: these indicators focus on the laws and regulations that are the most important for agricultural productivity in countries around the world – developed and developing. The indicators will be consistent and comparable across economies, enabling benchmarking to take place.
2. Market Metrics (MMs) multi-country studies: these metrics will examine a broader range of factors affecting agricultural productivity, market access, and the policy environment for agriculture. MMs will bring new benchmarks to the attention of policymakers and will provide a number of important new metrics to better enable policy-makers to establish their country's position in relation to their neighbours and countries at a similar stage of agricultural development.

The EBA started with 6 indicators, which have been scaled up to 10 indicators this year including the following topics: seeds, fertilisers, mechanisation, land, water, livestock, transport, finance, information communication technology (ICT), and markets. Other topics, such as contracting agricultural production, were considered at an earlier stage, however the comparability of data across countries has led to the project settling on the 10 topics selected. In addition indicators focussing on gender and environmental sustainability were integrated across a number of topics.

The Market Metrics as they were named have been removed following work by the Technical Advisory Committee and Donor Committee which found the methodology unable to deliver sufficiently robust information. Whilst the aims of the market metrics remain relevant, the programme is adapting so that it will deliver these outcomes in different ways, for example by creating country specific profiles or regional analysis, developing partnerships and feedback mechanisms and focussing on policy relevance and uptake.

The EBA indicators were developed over three years, starting with a pilot phase of data collection in 10 countries in 2013, scaling up to 40 countries in year 2 and 62 countries in year 3, including a range of DFID focus countries. The chosen countries represent a range of geographic regions at different stages of agricultural development so that comparisons between countries can be made.
## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment
The EBA’s objective is to become a key policy tool for policymakers, leading to indicator-informed regulatory reform. This past year was the third and last year of the pilot phase of the EBA. Due to the positive progress made during the pilot phase, funding for the project has been extended for another three years and therefore the EBA will continue to make progress against the outcomes sought in the logframe. However, as this year marks the end of the original pilot phase, outcomes are reviewed in more detail.

The programme has four outcome indicators and the following was achieved:

1. Countries' understanding of impact of agribusiness enabling environment is enhanced by dissemination of EBA report: The target for June 2016 was an increase by 50% of website visits, which has been substantially exceeded with an increase of 119% and 28,217 total visits. Assessment: Exceeded.
2. Number of countries actively using the EBA indicators to inform policy improvements: The EBA team has met the target of engaging with 10 countries to use EBA data to inform policy making. The ten countries are Cambodia, Cote d'Ivoire, Ethiopia, Guatemala, Laos, Russian Federation, Rwanda, Sudan, Tanzania and Vietnam. In particular, engagement with Rwanda and Vietnam has been very successful, starting a reform process on regulations concerning seed input markets in Vietnam and informing the development of the Strategic Plan for the Transformation in Agriculture in Rwanda. Assessment: Target met ahead of schedule.
3. Number of laws/regulations/codes enacted or amended - the enactment or amendment directly informed, influenced or recommended by EBA indicators: The aim was to influence the amendment of laws/regulations in eight countries. The EBA has directly influenced regulations in two countries (Rwanda and Vietnam), and is engaging closely with another eight countries (Cambodia, Cote d'Ivoire, Ethiopia, Guatemala, Laos, Russian Federation, Sudan, Tanzania) to discuss how the EBA can inform amending regulations. While the EBA team has made good progress on this target, changing laws and regulation takes time. As the team is in discussion with further eight countries, it is expected that by the end of the extension period the overall target will be met. In the meantime, the milestone should be rephrased in the logframe, to account for the time it takes from a policy decision to change legislation to the actual implementation of this legislation. Assessment: On track.
4. Number of procedures/policies/practices/standards improved or eliminated - the improvement or elimination directly informed, influenced or recommended by EBA indicators: The EBA has directly influenced the improvement of procedures, i.e. developing seed ordinance and thus improving current practices in seed input markets regulations in Rwanda. As mentioned above, the EBA is closely engaging with nine other countries (Cambodia, Cote d'Ivoire, Ethiopia, Guatemala, Laos, Russian Federation, Sudan, Tanzania and Vietnam) and in discussion how the EBA data can inform policy making to improve policies/ practices/ procedures. Given that it takes significant time to bring stakeholders together to agree policy decisions, it is expected that by the end of the project extension the final target will be met. As with outcome 3, this target should be rephrased to take into account for the time it takes to make policy decisions. As outcome 3 and 4 are very similar, the two should be combined into one outcome. Assessment: On track.

The assessment of the outcome indicators reflects the good work of the project team on dissemination and uptake, whilst simultaneously developing methods and collecting data. The team managed to directly influence legislature in Rwanda and Vietnam. In Rwanda, for example, the team closely engaged with the operational staff of the World Bank in country, issuing a briefing note for the Rwandan government, which subsequently informed the development of the Strategic Plan for the Transformation of Agriculture in Rwanda.

Overall, the performance of the EBA has met and in part slightly exceeded expectations. The small EBA team was faced with a challenging task of collecting data in more than 60 countries (starting with 10 countries in the first year and expanding to more than 60 in the third year), expanding topics, as well as making indicators methodologically more robust. Overall, the 2nd year report has increased in scope compared to the first report. It further has taken recommendations from the last annual review into account, making improvements to its web presence and making the data available in a more accessible format. In addition, the EBA has actively disseminated research findings, engaged with country governments, and facilitated a variety of outreach events (see Annex I). Work on the 3rd year report is well under way, including a further scale up of data collection to 62 countries.

Overall output score and description
The overall output score after the second year of the project is A.

The EBA has two main outputs: 1) development and roll-out of Doing Business in Agriculture methodology, and 2) development of Deep Dive multi-country studies.

Output 1: Under output 1, the team develops indicators for doing business in agriculture, and collects data on these. In the past year, the team has refined indicators and made them more robust, added indicators on water, land, livestock, and information communication technology and scaled data collection up to 62 countries. The team has also mainstreamed indicators on gender and environmental sustainability. Overall, the team has met expectations. While the team has exceeded the number of countries, indicators on gender and environmental sustainability need strengthening and a deeper analysis to make findings more meaningful. This should be undertaken in the next phase of the project.

Score: A

Output 2: Output 2 aims to bring about change to laws and regulations relevant for agribusiness in countries through a more focussed analysis within the country context. The donor committee together with the Technical Advisory Committee (TAC) has decided to refocus work under this output. Together, donors and the TAC agreed to change the methodology under this output. Instead of producing Deep Dive indicators and reports, the EBA team would produce country specific outputs, improve collaboration with World Bank country offices and look for other ways to influence and respond to opportunities. For example, following a request by DFID Asia regional department, the EBA team produced a set of country specific data sheets on DFID focus countries. In addition, the EBA team sought closer partnerships with country governments and donor staff in country.

This change in methodological approach demonstrates that the programme has actively learnt and adapted during its first phase. The EBA team managed to take recommendations by the Technical Advisory Committee and donors on board, despite the small size of the EBA team. This demonstrates highly effective and efficient work by the team, and should be commended.

Score: A

Key lessons

- Data on policy practice needs to be included to produce a meaningful index: While indicators measuring the regulatory environment and assessing laws are important, to make the results of the EBA more meaningful indicators on policy practice and implementation of laws and regulations need to be included in the EBA. The team has started to devise indicators to include in future reports (after 2017).
- Make data more useful for policy: The EBA data is highly aggregated and thus makes it difficult for policy makers to design adequate policies based on this information. To make the data more useful, country specific outputs are required, including in-depth analysis. This could also include collection of sub-national data in specific countries.
- Engaging with stakeholders: The team has engaged directly with governments and other stakeholders, and has seen the direct benefits of this engagement. The EBA has come under some criticism from civil society during its first phase that it supports large agribusiness at the expense of inclusive economic development. This criticism demonstrates the ongoing need for the EBA to consult and listen to the views of a broad range of stakeholders, engage civil society organisations in feedback mechanisms, as well as communicate the scope and limitations of the data. In the past year, this has helped to reduce criticism and has increased their buy-in and collaboration with the project. The direct engagement strategy should be continued in the coming year.
- Policy change needs time: While the EBA data is useful to policy makers and the team has started to engage closely with some governments, it takes time for policy change to take place and be enacted. Taking this into consideration, the publishing cycle of the EBA report should become biannual. Since a baseline has been established during the three-year pilot phase, data collection should take place every two years to enable the team to focus on dissemination and uptake separately from data collection, and to reflect the time it takes for policy and regulation to change.

Key actions

- The EBA team to create an index for efficiency implementation of laws and regulations and develop this in the next round of data collection in 2018;
- The EBA team should expand the gender discrimination and environmental sustainability indicators and deepen analysis, including consideration of indicators from ‘Women, Business and the Law’ in the 2017 report and 2018 data collection round;
- By the next annual review the EBA team should have sought out partnerships and strengthened collaboration to strategically tie ‘Enabling the Business of Agriculture’ data into the Bank’s policy operations. This could be demonstrated through the integration of EBA data into World Bank products or policy processes
- By the next annual review, the EBA team should have formalised feedback mechanisms from relevant civil society organizations;
- The programme should move to biannual publication of indicators and reports for the full sample of countries, with the next report being published in early 2019;
- To increase the policy relevance of the data, and by the next annual review, the team should consider generating indicators and reports for specific geographies in between publishing the full EBA report, as well as mechanisms to respond to demands from World Bank colleagues and other stakeholders.
- The DfID SRO should update the logframe to include lessons learned from the pilot phase of the EBA and the targets for the next phase.

Has the logframe been updated since the last review?

No.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Development and roll-out of Doing Business in Agriculture methodology
Output number per LF		1	Output Score	A
Risk:		Moderate	Impact weighting (%):	50%
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
1.1 Number of DBA indicators developed	10 indicator topic areas: (1) Access to Finance, (2-3) Access to Inputs (seeds and fertilizer) (4) land, (5) Access to markets, (6) Access to transport, (7) Water, (8) ICT, (9) Mechanisation; and (10) livestock / Gender and environmental sustainability integrated across relevant indicators	Robust indicators have been developed for 10 areas: seeds, fertilisers, mechanisation, land, water, livestock, transport, finance, and markets. Data is presented on ICT, in addition to gender and environmental sustainability which are integrated across relevant topic areas. / However, the analysis of the gender and environmental sustainability indicators is not yet sufficient. More detail and depth should be added, including seeking to integrate ‘Women, Business and the Law’ Indicators. Further, in the future the EBA should feature standalone chapters on gender and environmental sustainability.
1.2 Number of countries in which DBA is rolled out	60 countries	62 countries
1.3 Number of DBA reports produced.	3rd year report	Third year report due to be published in February 2017. This is slightly delayed to last year’s report published in December. To delay to the original timing indicated in BC was caused in prior years. The logframe should be updated to reflect the change in timeframe.
1.4 Number of workshops, seminars, conferences organised or co-organised	At least 2 events	9 events, in addition to 5 webinars

Key Points

Robust indicators have been developed for 10 topic areas (seeds, fertilisers, mechanisation, land, water, livestock, transport, finance, ICT and markets). Cross-cutting issues, gender and environmental sustainability, were integrated in a number of topic areas, and the data is presented separately in chapter 8 of the second year report. However, the analysis of the gender and environmental sustainability aspects needs improvement and strengthening in order to be useful for governments to inspire regulatory reform that really encourages inclusive and sustainable development of the agriculture and agribusiness sector. To improve the depth and data presentation, the next EBA report should include standalone chapters on gender and environmental sustainability.

In discussions with the EBA team, Phase II of the project should develop indicators on policy practice and implementation effectiveness of legislation. This will make the index stronger and more meaningful. So far, the EBA measures and analyses the type of regulations and law, which are formally in place. However, Phase II will continue updating data on the indicators developed in the pilot phase, and in addition measure to what extend rules and regulations are implemented and how implementation looks like in practice.

The EBA report is published annually in June. However, due to a delay from previous years, the publication date has moved to December/ January. The coming report will be published in February 2017, and thus will only be slightly delayed. The change in publication date needs to be updated in the logframe.

The indicators have been scaled from 10 countries in the first year, to 40 in the second year report. The third year report to be published in February 2017 will include data on 62 countries, therefore exceeding the target in the logframe. The team will further scale up data collection to 80 in the next phase. Whereas the last AR recommended to reduce to scale up and limit the EBA to 60 countries, the EBA team has received increasing interest from governments for their country to be included in the report, which is a positive sign for the programme. Therefore, DFID has agreed to include a greater number of countries in the EBA, as long as DFID focus countries are included in the index wherever possible, and any developed countries requesting inclusion in the index provide or raise funds for this.

Nine outreach and engagement events took place, in addition to five webinars. This has greatly exceeded the milestone in the logframe. To note in particular is the impact of these engagement events, and outreach to governments. The EBA has successfully managed to raise its profile during the past year, and as mentioned previously has received high interest by a number of governments (e.g. Rwanda, Vietnam). Further, the 119% increase of website visits in the past year (28,217 visits) is shows the rising interest in and awareness of the report.

Summary of responses to issues raised in previous annual reviews (where relevant)

Last year’s annual review recommended the inclusion of indicators on gender and environmental sustainability. The two cross-cutting topics are integrated in the second year report, and the soon to be published third year report. Whereas at first, separate indicators were developed for the two topics, after piloting the indicators the decision was taken that mainstreaming the indicators across the topic areas was of greater value. While improvements have been made on data presentation, data on gender and environmental sustainability should be presented in stand-alone chapters, and be clearly signposted throughout the report.

The last AR recommended limiting the number of countries to 60. The SRO discussed this point with the EBA team and the other donors of the programme. The decision was taken that due to the increased interest of countries in the report, countries, which are asking to be included in the report, should provide their own funding or partial funding for the data collection. Therefore the decision was revised so that as many as 80 countries could be included, as long as this set includes relevant DFID focus countries.

Recommendations

1. The EBA team should strengthen and deepen indicators and analysis on gender and environmental sustainability across all topics. Consider using indicators from ‘Women, Business and the Law’, and present data in two standalone chapters on gender and environmental sustainability in the 2017 report.
2. By the 2018 data collection round, indicators on implementation effectiveness should be included to improve understanding of policy practice and implementation of laws and regulations which are needed to create an enabling environment for agribusiness.
3. The DfID SRO should update the logframe to reflect changed times of milestones and modified outputs.

Output Title	Development of Deep Dive multi-country studies
Output number per LF		2	Output Score	A
Risk:		Moderate	Impact weighting (%):	50%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
2.1 Number of DD indicators developed	9 indicators: (1) Access to Finance, (2-3) Access to Inputs (seeds and fertilizer) (4) Access to secure property rights on land, (5) Access to markets, (6) Access to transport, (7) Water, (8) Rural electricity, (9) and Mechanization	Indicators that capture practice-related dimensions of EBA topic areas continue to be developed, and will be presented in the 2017 Report for 5 topic areas: (1) Seed (2) Fertilizer (3) Agricultural machinery (4) Markets (5) Transport / The donor committee has decided to refocus work under this output and agreed to a changed methodology. Instead of producing a deep dive, the EBA team was encouraged to look for partnerships with World Bank colleagues to improve dissemination and take up by governments of EBA findings. / The EBA team is to make sure products are country specific.
2.2 Number of DD reports produced	3rd Year Report (to be published in February 2017)	Refocussing of the project to policy relevant information. Policy focussed sections are included in the report. / Results on these indicators will be reported in EBA's third year report.

Key Points
The aim of output 2 is to provide regional and country specific information which can help bring about regulatory reform in specific areas. After much discussion and difficulty in developing a robust method for this work, the Technical Advisory Committee (TAC) advised the removal of the market metrics from the programme as a stand-alone output. Whilst the outcomes sought through these outputs remain relevant to the programme, donors and the TAC felt that the methodology and scope of the deep drive was too vague. Instead, donors and the TAC agreed that the team should produce other types of country specific information, as well as seek partnerships with the operational staff of the World Bank to improve dissemination and uptake of the EBA data.

Progress has been made against the new approach so far. Following the launch of the second EBA report in January 2016, a number of opportunities have been developed to introduce its findings to policy operations. So far, 10 governments have engaged in policy discussions around EBA indicators in view of its applications to their national reform agenda, or expressed interest in the EBA data and are advocating its use at the policy level and for guiding investment decisions. For example, the Secretary of State of the Ministry of Agriculture of Cambodia has called for the formation of a Taskforce to analyse EBA data and formulate applications to agricultural sector policy reforms in the country. In Sudan, the Minister of Agriculture has deemed the EBA 2016 report a key document for improving the country’s agribusiness environment and is taking steps, in coordination with the World Bank Country Office and the EBA team, to identify reforms which can be implemented in the short to medium term. EBA findings on seed and fertilizer have been included in a position paper on policy dialogue with the Laotian Government, which is being used for developing a Development Policy Operation series which lay out the options for future budget support to Lao PDR. The team have also demonstrated responsiveness, as when the DfID Asia regional department asked the EBA team for a series of country products for Asia, these were delivered within a week.

It is important to make sure that the EBA builds on this work during the second phase, actively building partnerships and creating information and products that will respond to the needs of practitioners and governments and inspire regulatory and system reform, and creating feedback loops to further refine the methodology.

Summary of responses to issues raised in previous annual reviews (where relevant)

The EBA team has further scaled up data collection to 62 countries. These are well-lined up with DFID focus countries, and data produced by the EBA team has been deemed valuable by DFID country offices. For example DFID Rwanda fed back during the review process that it will use the EBA data to inform the design of new projects.

Recommendations
1. The DfID SRO should update the logframe to reflect changed methodological approach by March 2017.
2. The EBA team should further strengthen collaboration and feedback mechanisms with other World Bank staff, in particular operational staff providing technical assistance to governments in country as well as Washington based policy and programme teams. Progress should be reported in the next annual review.
3. For Phase II, the DfID SRO should work with other donors and the EBA team to ensure the project has sufficient focus on policy relevant outputs that drive reforms to ultimately benefit agribusinesses, smallholders and workers. This could include, but is not limited to, publishing regional reports and other country specific outputs on an annual basis, topic analysis, as well as creating products to meet demands for specific influencing opportunities.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

The business case identified two cost drivers (i) the design and development of indicators (economic efficiency) and (ii) the take up and impact of the findings and deep dive indicators in the decision making of policymakers in developing countries (economic effectiveness).

VfM performance compared to the original VfM proposition in the business case

The UK has disbursed £3m to Phase 1 of the EBA pilot, equalling £1m per year/ report against a total project budget of $17.6m. Other funding came from BMGF, the Government of the Netherlands, DANIDA and USAID. The total funding ask for the extension of the project as a whole is $14.9m over 5 years (2017- 2021).

The addendum for £1.8m over three years represents a relative reduction in our funding compared to the first three years to reflect the need for the EBA to bring new funders on board and to move to a more sustainable model where some countries self-fund. Our burden share for the 3 year period would be just under 25%, our current burden share for the first three years is 28.6% (GBP 3,000,000 = USD 5,058,181/USD 17,689,000).

In the past year (June 2015- June 2016), DFID disbursed over $ 2 million, equal to a total burden share of 29%. Most of DFID funding went to finance data collection and analysis through covering staff and consultants costs as well as travel expenses. Therefore, DFID funding has been predominantly spent on value-adding operations.

Table 1: DFID budget support to total EBA budget with budget split for each component (June 2015-June 2016)

Assessment of whether the programme continues to represent value for money

The EBA team has produced high quality data and achieved impact within the pilot phase. The cost drivers of the project are predominantly staff costs and uptake activities, relying heavily on high quality personnel and networks. The team has kept within the original budget and has now received a cost extension of £ 1.8 million for three years, contingent on match funding being received from other funders. This presents a reduction in funding from DFID, as the project moves towards a more sustainable model where some countries self-fund. Under the current assessment, the project still presents value for money.

Quality of financial management

DFID’s £500,000 contribution for this financial year has been disbursed in March 2016. For Phase II of the project, financial forecasting and amount disbursed is expected to change, as DFID’s contributions to the trust fund has almost halved for the next three year period. Therefore, the amount of regular contributions to the EBA will decrease. The World Bank’s next annual audit is due to be released months following the end of the Bank’s fiscal year.

Date of last narrative financial report	n/a
Date of last audited annual statement	n/a

E: RISK (½ page)

Overall risk rating: Moderate

The Business Case identified two types of risk: (i) the purpose and methodology of EBA is not well understood; and (ii) the programme cannot achieve buy-in among policymakers and key users. The risks, mitigation strategies and updates on any progress made and changes in context are provided in the table below.

Overview of programme risk

Risk identified in business case	Risk rating	How will risk be managed?	Annual Review Update
Methodology
Confusion over or misinterpretation of what the indicators do and don’t measure.	Moderate	EBA to continually communicate the range and limits of the data.	The EBA team has communicated the range and limits of the data through the 2015 and 2016 EBA reports, the EBA website and a large number of engagement/dissemination meetings (Annex 1). This will be reinforced in the upcoming 2017 report, due for launch in February 2017, and in the ensuing communications and dissemination campaign.
The programme narrowly focuses on indicators that measure the status of laws and regulations in the books and does not reflect the experience of businesses in reality.	Moderate	EBA is expanding its indicator set to capture the practice and efficiency of processes to comply with laws and regulations.	The EBA 2017 Report will present indicators that capture practice-related dimensions for 5 EBA topic areas - seed, fertilizer, agricultural machinery, markets and transport – and to overlay them across legal indicators. These indicators will be used to further expand this area in upcoming iterations of EBA.
Significant variations between the regulatory frameworks for different agricultural commodities limit the comparability of EBA indicators.	Minor	Indicators will use a standardised case study to allow comparison across different countries.	A standardised case assumption methodology has been developed and applied during the last 3 years.
Indicators produced are not considered to be relevant and/or rigorous.	Moderate	A broad group of experts and stakeholders (including researchers and target users) have been consulted and their advice is informing indicator selection and subsequent refinements.	Data points used to build indicators are backed up by documented laws and regulations, and verified by target country governments and World Bank country offices. A growing circle of technical and operational experts are being consulted to ensure the relevance of the indicators and to vet them, and a Technical Advisory Committee formed in 2015 has provided guidance on the approach for strengthening them. Engagement has been held and continues to be planned with stakeholders, such as government representatives, policy sector players, CSOs and the research community, to collect and incorporate relevant feedback.
Countries selected are not aligned to programme objectives.	Minor	The World Bank will consult donors on the country selection process. A geographically diverse set of countries at different stages of agricultural growth will be selected to allow for sub-comparisons.	Countries were selected in consultation with donors and World Bank agricultural operations experts. Geographical, income level and agricultural transformation diversity, as well as relevance to programme objectives, was considered and ensured for country selection.
Insufficient attention given to gender and environmental sustainability	Minor	Integration across relevant topic areas such as land, financial access and water	Gender and environmental sustainability were integrated into the 2016 report, and will be further expanded in the 2017 report.
Take-up and Buy-In
Lack of government buy-in	Moderate	Governments of countries covered by the EBA are being targeted for dissemination and consultation. Proper interpretation and understanding of the evidence provided by EBA indicators will be fostered through dissemination events and technical workshops.	The EBA team has worked with World Bank country office specialists to present the report and hold discussions with governments and other stakeholders in a number of countries, including Vietnam, Rwanda, Russia, Cambodia, Sudan, Cote d’Ivoire and Laos. Engagement has generated substantial interest in using EBA data for policy planning. The EBA team is planning to expand and reinforce outreach in order to engage governments further in the use of EBA indicators.
Programme activities do not lead to regulatory changes.	Moderate	EBA team will work closely with operational colleagues in the World Bank, and in other institutions, to translate findings into policy dialogue and actions that trigger changes in the regulatory environment related to the project’s interventions.	A dissemination and operationalization strategy are being developed to follow up the third year report, and to build on 2016 developments in this area. This includes meetings/workshops in at least 3 regions and presenting the EBA at several key conferences.
Pressure over regulatory indicators and country rankings lead to a pushback on the EBA.	Moderate	EBA should carefully consider pros and cons before proceeding with country rankings.	In EBA’s communication and engagement efforts, it has been clarified that for the time being rankings are not being considered as a mechanism. Following up on the 2016 Report, reporting will be based on scores which allows for benchmarking without doing rankings.
Unintended consequences	Moderate	The programme will devise a way to model the expected policy responses from the indicators to ensure against negative outcomes.	Research on the regulatory environment and links to agriculture transformation should help inform the sequencing and impacts of these types of indicators.
Governments narrowly target their reform efforts to trigger EBA indicators only.	Moderate	Besides broadening EBA indicators to measure practice-related elements of the regulatory framework, the team will work with other World Bank units to support their programs providing technical assistance to client governments that go beyond what is measured by the indicators. The team will also devise a way to model the expected policy responses from the indicators to ensure against this risks of narrow reforms. Finally, the team will continue to clarify and emphasize that business regulation reforms are one element of a strategy aimed at improving competitiveness and establishing a solid foundation for sustainable economic growth in the context of dissemination as well as of interactions with governments, other institutions, partners and stakeholders in general.	Increased engagement and integration with the Bank’s policy operations will encourage a broad reform discussion as opposed to narrow indicator focused reforms.
The process of agreeing to policy changes is not sufficiently inclusive and consultative at country level.	Moderate	The programme is paying attention to not only encouraging policy reforms, but how they have been achieved, particularly in terms of including key stakeholders in the discussions that EBA indicators generate.	The EBA team has increased their outreach activities, ensuring a wider range of stakeholders are involved in the process.
Programme is not sufficiently proactive to engage stakeholders.	Minor	Specific actions including a strategic outreach plan should be a central component of the programme.	A stakeholder engagement plan has been implemented over the last year, which has included dialogue meetings, participation at topic specific conferences, communication strategy and online discussions (further details in Annex 1)
The programme is not financially sustainable over the long-term	Major	The EBA team needs to fundraise money from sources other than donors. This should include country governments financing data collection for the indicator in their own country. Further, the team should explore if there is interest in the private sector or with CSOs to finance the EBA.	The EBA team is currently liaising with a number of country governments regarding financing the EBA. Countries, which so far have not been included but would like to be featured in the EBA are asked to finance 2/3 of the costs for data collection, with 1/3 coming from the multi-donor trust fund. Further, there are ongoing talks with the AfDB how they can contribute, as they are considering a roll-out of the EBA across all African countries.

Outstanding actions from risk assessment
The majority of risks to the project’s ability to deliver results remain relevant, as the project goes into Phase II. However, a number of risks have had their risk rating downgraded to minor. “The programme is not financially sustainable over the long-term” has been added to risks, which is seen as major and will need to be closely monitored during Phase II.

Regarding main risks, that were raised in last year’s annual review, i.e. the level of uptake of EBA indicators and their ability to bring about reform, the EBA team mitigated the risk with their outreach and dissemination activities in the past year, the direct and continuous engagement with government, as well as improving collaboration with World Bank colleagues, mainstreaming the EBA findings in other World Bank activities.
Therefore, while these risks still remain, their risk level might reduce in the future due to ongoing and successful mitigation activities.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
The EBA team have delivered against their milestones. These are slightly out of sync with the original business case owing to a delay in starting operations in the first year. The new project cycle means reports will be finalised by the end of the calendar year, rather than in the summer. The third report is therefore only slightly delayed and publicly available in February, 2017. In Phase II, reports will only be published biannually, reducing the pressure on the team to meet publication deadlines whilst also trying to disseminate the previous report. This should allow increased emphasis on uptake and therefore a better contribution to the outcomes of the project.

Performance of partnership (s)
The EBA team have remained responsive to the donors in the multi-donor trust fund. They have kept donors up to date on progress and informed the group on proposed changes as well as the process to make decisions. The multi-donor trust fund has met face to-face once in year 3 in June 2016 in Rome. There has also been regular email correspondence allowing for more real time communication between the EBA team and the donor group and the EBA team presented to DfID staff during the spring of 2016.

Asset monitoring and control

Not applicable

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

It was not deemed relevant to use the partnership principles for management and monitoring when the programme was approved

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

The cost extension for Phase II has earmarked £ 100,000 to finance an independent mid-term evaluation of the EBA.

Monitoring progress throughout the review period

The EBA monitoring and evaluation follows World Bank standards and requirements for project implementation. Two key steps highlight this process:

Concept Note approval – at the beginning of each year of project implementation, a concept note and work programme for the year is developed, reviewed and approved to determine deliverables and ensure alignment to project goals.

Decision Making – review and approval of the project deliverables, in this case the yearly report, ensuring that the proposed goals are met.

For this annual review, views were gathered from the EBA team and additional World Bank colleagues, and other EBA donors. Views were also gathered from civil society representatives based in the UK and from DFID Rwanda.

Annex 1- EBA stakeholder consultations/engagement, 2015-2016

Government Outreach and Stakeholder Dialogue
Date	Location	Details
Dec 2015	Vietnam	EBA Dissemination/Discussion Event: A workshop with over 50 individuals, from the Government, policy think tanks and legislators, private sector and CSOs to present and discuss EBA 2016 results.
March 2016	Laos	EBA Dissemination/Discussion Event: A workshop with government officials, the research community, development organizations and CSOs to present and discuss EBA 2016 results.
March 2016	Cambodia	EBA Dissemination/Discussion Event: A workshop with over 50 individuals, from the Government, policy think tanks and legislators, private sector and CSOs to present and discuss EBA 2016 results, followed by a meeting with the Ministry of Agriculture on the use of EBA in Cambodia.
March 2016	Russian Federation	EBA Presentation/Discussion with Russian Ministry of Agriculture.
May 2016	Sudan	EBA Dissemination/Discussion Event: A conference with over 50 individuals, from the Government, regional organizations, legislators, private sector and CSOs to present and discuss EBA 2016 results, followed by a meeting with the Ministry of Agriculture on the use of EBA in Sudan.
May 2016	Rwanda	EBA Discussions with the Ministry of Agriculture, to discuss applications of EBA indicators to Rwanda’s policy strategy for the next 4 years.
June 2016	Cote d’Ivoire	EBA Discussions with several Ministries on the applications of EBA indicators to Cote d’Ivoire Investment Climate planning.
Regional and Global Convening
Nov 2015	Prague	18th MFC (Microfinance Center) Annual Conference / Presentation on EBA finance indicators.
Dec 2015	Manila	3rd Forum on Sustainable Agricultural Mechanization in Asia and the Pacific, organized by the United Nations’ Economic and Social Commission for Asia and the Pacific (ESCAP) and the Centre for Sustainable Agricultural Mechanization (CSAM). / Presentation on EBA machinery indicators.
Jan 2016	Berlin	Global Forum for Food and Agriculture (part of International Green Week). / Presentation on EBA
Jan 2016	Berlin	AGCO Africa Summit / Introduced EBA project to numerous representatives from the private agro-industry, financial institutions and other stakeholders and recruited contributors for EBA17 data collection.
Feb 2016	Marrakech	Argus FMB Africa. / Presentation on EBA fertilizer indicators.
March 2016	Washington DC	World Bank Land & Poverty Conference 2016. / Includes pre-conference Steering Committee meeting and main session Panel Discussion on “Learning from Good Practices on Land for Enabling the Business of Agriculture”. / The session, which brought together 8 panel speakers representing different regions and stakeholders, highlighted EBA’s work on developing land indicators.
March 2016	Brussels	Forum for the Future of Agriculture 2016. / EBA was presented at the launch event for the RISE 2015-2016 research report “Nutrient Recovery and Reuse in European Agriculture”. The conference was attended by representatives from the agro-industry, the European Commission, international organizations and academia. The presentation introduced the EBA project to numerous policy makers, representatives from the private agro-industry and other stakeholders.
April 2016	Washington DC	Seeds For All: Moving The Agenda Forward on Seed Regulations and Seed Quality Assurance Workshop
April 2016	New York	Global Partnership on Sustainable Transport (GPST) Meeting. / Presentation on EBA and on its transport indicators.
May 2016	Washington DC	Commercial and Sustainable Supply for Early Generation Seed (EGS) for Food Crops in Sub-Saharan Africa Seminar. / Presented and discussed EBA indicators as they related to regulations shaping access to EGS.
July 2016	Washington DC	Agrievolution Event – meeting of the global federation of agricultural machinery manufacturers. / Presentation on EBA and EBA machinery indicators.
July 2016	Ravello, Italy	International Consortium on Applied Bioeconomy Research Conference 2016. / Two presentations, on EBA and on EBA land indicators, to the academic and research community.
July 2016	Washington DC	Plant-Related IP and Related International Developments Conference (US Patent & Trademark Office)
September 2016	Beijing	Global SME Finance Forum. / Presentation on EBA finance indicators
September 2016	Arlington	SEEP Network Conference. / Offered a main session and a discussion workshop on EBA to large number of organizations gathered at this conference.
September 2016	Rome	FAO Conference: Rural transformation, agricultural and food system transition: Building the evidence base for policies that promote sustainable development, food and nutrition security and poverty reduction / Presentation of EBA research paper “The role of Regulations for Structural Transformation in Agriculture”
September 2016	London	International Coffee Organization Summit / Presentation of EBA markets indicators
September 2016	Nairobi	Presentation of EBA fertilizer indicators at International Fertilizer Industry Association/Bill & Melinda Gates Foundation, Indicators of Fertilizer Access and Use for Smallholder Farmers in Africa Conference
October 2016	Des Moines, IA	The World Food Prize, Borlaug Dialogue
Online & Telephonic Roundtables
Feb 2016		Global CSO Telephonic Roundtable / The EBA team joined a World Bank global CSO telephonic roundtable to discuss the project and its focus on gender issues.
April 2016		EBA Online Webinars / Four online webinars, in English, French, Spanish and Russian to present EBA to 200 participants worldwide
May 2016		Feed the Future – Knowledge-Driven Agricultural Development Project Webinar / Presentation of EBA to 120 participants around the world
Targeted Government Outreach
March 2016	Vietnam	The EBA team met with the Ministry of Agriculture Office in charge of drafting and proposing the new Seed Law, which collected input from EBA indicators for this development.
May 2016	Rwanda	The EBA team met with the Minister of Agricuture, her Permanent Secretary and the Minister of State to discuss use of EBA indicators for policy planning. World Bank operational colleagues have followed up and submitted EBA-based material to the Cabinet. Specific input was also provided for the Seed Ordinances being developed at the time to supplement the new Seed Law.
Communication channels
Website. The EBA website is a core component for EBA’s communications. Under the Stakeholder Engagement Plan, minor changes have been made to clarify language for recruiting survey contributors. More extensive changes have been proposed that include a set of “How to Engage” pages for sharing feedback and input to the EBA project. These pages would also have a calendar of upcoming events and moments for when stakeholders and external partners can contribute to the project
LinkedIn. The EBA team has used its LinkedIn group to disseminate the EBA 2016 Report, and as a tool to manage and better engage current and future survey contributors. It is a platform for sharing updates on the EBA project along with general news and trends in the global agriculture sector..